## Executive Summary
Metric | Value
Project Status | On Track
P50 Duration (days) | 500.2
P80 Duration (days) | 520
P90 Duration (days) | 529.8
Schedule Issues | 1373
Cost Issues | 2266
Progress Issues | 1367
Float Issues | 524
Very High Risk Activities | 87

## Top Risks
task_code | task_name | SPI | CPI | progress_variance | float_days | dynamic_risk_score | risk_category
HCMEB4Z5220 | B4 Z4 :Cable Tray Installation | 0.8 | 0.71813 | -20 | 45 | 85 | Very High
HCSW2FZ1070 | Installation of steel columns and beams | 0.84 | 0.76978 | -16 | 0 | 83.5 | Very High
HCSW2FZ2090 | Casting concrete for slab topping | 0.8 | 0.68625 | -20 | 0 | 83.5 | Very High
HMMOAZ050 | Removal of Tower crane # 1 | 0.82 | 0.73852 | -18 | 0 | 83.5 | Very High
HCFWF2Z3069 | F2 Z3 :Plaster Final Layer | 0.81 | 0.74922 | -19 | 0 | 83.5 | Very High
HCESCN010 | s/c nomination: Steel structure subcontractor | 0.86 | 0.71509 | -14 | 0 | 83.5 | Very High
HCSW4FZ3090 | Casting concrete for slab topping | 0.81 | 0.70065 | -19 | 0 | 83.5 | Very High
HCFWF2Z3096 | F2 Z3 :Plaster Second Layer | 0.82 | 0.72422 | -18 | 0 | 83.5 | Very High
HCSW4FZ2070 | Installation of steel columns and beams | 0.86 | 0.75699 | -14 | 0 | 83.5 | Very High
HCFWF5Z3177 | F5 Z3 :Trawelled smooth Concrete screed | 0.8 | 0.6528 | -20 | 0 | 83.5 | Very High
H0000 | Start Date | 0.85 | 0.7182 | -15 | 0 | 83.5 | Very High
HCFWGFZ3010 | GF Z3 :Gybsum Board Partitions | 0.86 | 0.78126 | -14 | 0 | 83.5 | Very High
HCESCN000 | s/c nomination: MEP subcontractor | 0.84 | 0.68214 | -16 | 0 | 83.5 | Very High
HCSW5FZ1070 | Installation of steel columns and beams | 0.8 | 0.71123 | -20 | 0 | 83.5 | Very High
HCSW6FZ2080 | Steel Deck | 0.84 | 0.68776 | -16 | 0 | 83.5 | Very High
HCSW7FZ3080 | Steel Deck | 0.83 | 0.67807 | -17 | 0 | 83.5 | Very High
HCMEB2Z1340 | B2 Z1 :Mechanical final Fix | 0.84 | 0.70132 | -16 | 0 | 83.5 | Very High
HCMEF7Z1755 | F7 :Electrical Final Fix for All Systems & Boards (Vertical Elements) | 0.86 | 0.77847 | -14 | 0 | 83.5 | Very High
HCMEB3Z1205 | B3 Z1 :Cable Tray Installation | 0.83 | 0.79546 | -17 | 0 | 83.5 | Very High
HCSWGFZ2070 | GF Z2 :Installation of steel columns and beams | 0.84 | 0.78291 | -16 | 0 | 83.5 | Very High

## Top Delay Drivers
task_code | task_name | baseline_duration_days | SPI | forecast_duration_days | forecast_delay_days | escalation_level
HCSDAMEP010 | SD approval: MEP Plans & Details | 398 | 0.8 | 497.5 | 99.5 | Executive
HEPSCVS0010 | Manufacturing & Importing Materials | 364 | 0.83 | 438.5542 | 74.5542 | Executive
HEPSAME1180 | Windows Washing Machine | 291 | 0.83 | 350.6024 | 59.6024 | Executive
HEPSAME1300 | CableTrays | 287 | 0.83 | 345.7831 | 58.7831 | Executive
HEPSAME1290 | Cables | 262 | 0.83 | 315.6627 | 53.6627 | Executive
HEPSAFI0270 | Toilet Toilet & corian vanity tops | 214 | 0.8 | 267.5 | 53.5 | Executive
HEPSAAL0060 | Glass panels | 237 | 0.86 | 275.5814 | 38.5814 | Executive
HEPSAAL0030 | Sky lights | 364 | 0.91 | 400 | 36 | Executive
HCFWAFAZ000 | Finish Left over areas (Crane #3) | 169 | 0.84 | 201.1905 | 32.1905 | Executive
HEPSAME1130 | Ducts & pipes | 189 | 0.86 | 219.7674 | 30.7674 | Executive
HEPSAME1310 | Electrical Boards | 170 | 0.85 | 200 | 30 | Project Manager
HCEXWWFP010 | EXT :Water Feature All Works | 143 | 0.84 | 170.2381 | 27.2381 | Project Manager
HEPSAFI0210 | Floor Tiles | 279 | 0.92 | 303.2609 | 24.2609 | Project Manager
HEPSAFI0070 | Steel doors and frames | 144 | 0.87 | 165.5172 | 21.5172 | Project Manager
HEPSAME1170 | Grills | 238 | 0.92 | 258.6957 | 20.6957 | Project Manager
HCSDAFW040 | SD approval: Special Interiors | 177 | 0.9 | 196.6667 | 19.6667 | Project Manager
HESDACI0010 | SD approval: Reinforced Concrete Shopdrawings | 155 | 0.89 | 174.1573 | 19.1573 | Project Manager
HCFWAFAZ010 | Finish Left over areas (Crane #2) | 97 | 0.85 | 114.1176 | 17.1176 | Project Manager
HCSDSMEP010 | SD submission: MEP Plans & Details | 403 | 0.96 | 419.7917 | 16.7917 | Project Manager
HCMEPSLS150 | SPS :lighting points | 72 | 0.84 | 85.7143 | 13.7143 | Monitor

## Recommendations
Recommendations
Conduct cost review and strengthen cost controls.
Schedule uncertainty is moderate. Monitor critical packages closely.
Conduct executive review of very high-risk activities.