## Sheet1
delay_id | task_id | task_code | task_name | delay_event | delay_start | delay_finish | delay_days | delay_type | notice_issued | evidence_available
D001 | 146847 | HCMEF2Z3340 | F2 Z3 :Duct Insulation Work | Severe rainfall | 2026-06-01 | 2026-06-04 | 19 | Third Party | No | Yes
D002 | 144154 | HCSWB1Z3240 | B1 Z3 :Cure and De-shutter slab formwork | Subcontractor delay | 2026-06-03 | 2026-06-06 | 8 | Third Party | Yes | No
D003 | 145981 | HCFWF6Z2238 | F6 Z4 :Steel Fire Rated Doors | Subcontractor delay | 2026-06-05 | 2026-06-08 | 8 | Exceptional Event | No | Yes
D004 | 146735 | HCMEF1Z2230 | F1 Z2 :Cable Tray Installation | Late drawing approval | 2026-06-07 | 2026-06-10 | 11 | Employer | No | No
D005 | 147622 | HCSWSSZ6325 | SS Z6 :Fill imported base course under SOG | Equipment breakdown | 2026-06-09 | 2026-06-12 | 16 | Contractor | Yes | No
D006 | 147056 | HCMEF5Z1320 | F5 Z1 :Plastering Finish Date for All Parts | Site access restriction | 2026-06-11 | 2026-06-14 | 14 | Contractor | Yes | Yes
D007 | 145561 | HCFWF4Z2110 | F4 Z2 :Plaster Second Layer | Site access restriction | 2026-06-13 | 2026-06-16 | 4 | Employer | Yes | No
D008 | 143892 | HCSWB3Z3140 | B3 Z3 :De-shutter core wall formwork | Utility relocation delay | 2026-06-15 | 2026-06-18 | 8 | Third Party | No | No
D009 | 147550 | HEMSSME1200 | MS submission: Stand by Generator | Delayed material delivery | 2026-06-17 | 2026-06-20 | 16 | Contractor | No | Yes
D010 | 144019 | HCSWB2Z3150 | B2 Z3 :Fix Steel Rebar for columns | Late drawing approval | 2026-06-19 | 2026-06-22 | 17 | Exceptional Event | Yes | No
D011 | 143719 | HCSWB4Z1030 | B4 Z1 :Fix MEP first fix in walls | Utility relocation delay | 2026-06-21 | 2026-06-24 | 4 | Unknown | Yes | Yes
D012 | 147432 | HCMEPSSWW010 | SPS :Installation for Window Washing system | Subcontractor delay | 2026-06-23 | 2026-06-26 | 13 | Employer | No | Yes
D013 | 145687 | HCFWF5Z1151 | F5 Z1 :Foam Concrete Under Floorings | Subcontractor delay | 2026-06-25 | 2026-06-28 | 16 | Employer | No | No
D014 | 146221 | HCMEB3Z2300 | B3 Z2 :Duct Installation& Dusct Accecories Installation, Fan coil Unit | Subcontractor delay | 2026-06-27 | 2026-06-30 | 16 | Contractor | No | No
D015 | 145291 | HCFWF1Z2028 | F1 Z2 :Paint putty coat | Late drawing approval | 2026-06-29 | 2026-07-02 | 19 | Employer | No | No
D016 | 145243 | HCFWGFZ3032 | GF Z3 :Mirror | Subcontractor delay | 2026-07-01 | 2026-07-04 | 15 | Exceptional Event | Yes | Yes
D017 | 147408 | HCFWF7AZ080 | F7 :Paint putty coat | Late drawing approval | 2026-07-03 | 2026-07-06 | 19 | Exceptional Event | Yes | Yes
D018 | 146074 | HCMEB4Z2345 | B4 Z2 :All Vertical Piping Works | Utility relocation delay | 2026-07-05 | 2026-07-08 | 10 | Contractor | Yes | No
D019 | 144913 | HCFWB3Z1014 | B3 Z1 :Plaster Second Layer | Severe rainfall | 2026-07-07 | 2026-07-10 | 16 | Exceptional Event | No | Yes
D020 | 144155 | HCSWB1Z4010 | B1 Z4 :Formwork retaining walls shutters - 1st side | Severe rainfall | 2026-07-09 | 2026-07-12 | 12 | Employer | Yes | No
D021 | 145158 | HCFWB1Z6017 | B1 Z6 :B1 Z6 :Plaster First Layer | Severe rainfall | 2026-07-11 | 2026-07-14 | 19 | Employer | No | Yes
D022 | 144643 | HCFWB4Z2012 | B4 Z2 :Paint Final Layer | Subcontractor delay | 2026-07-13 | 2026-07-16 | 5 | Employer | Yes | Yes
D023 | 147618 | HCSWSSZ2225 | SS Z2 :Fill imported base course around Foundations P2 & under SOG | Subcontractor delay | 2026-07-15 | 2026-07-18 | 10 | Third Party | No | No
D024 | 145094 | HCFWB1Z4009 | B1 Z4 :Plaster First Layer | Utility relocation delay | 2026-07-17 | 2026-07-20 | 4 | Exceptional Event | Yes | Yes
D025 | 145562 | HCFWF4Z2115 | F4 Z2 :Plaster First Layer | Delayed material delivery | 2026-07-19 | 2026-07-22 | 5 | Unknown | Yes | No
D026 | 146910 | HCMEF3Z3245 | F3 Z3 :Cable Tray Installation | Site access restriction | 2026-07-21 | 2026-07-24 | 3 | Contractor | Yes | Yes
D027 | 147404 | HCFWF7AZ020 | F7 :Plaster First Layer | Delayed material delivery | 2026-07-23 | 2026-07-26 | 15 | Contractor | Yes | No
D028 | 146892 | HCMEF3Z2090 | F3 Z2 :Mechanical Final Fix | Design change instruction | 2026-07-25 | 2026-07-28 | 15 | Contractor | No | Yes
D029 | 144046 | HCSWB2Z4240 | B2 Z4 :Cure and De-shutter slab formwork | Utility relocation delay | 2026-07-27 | 2026-07-30 | 16 | Contractor | Yes | Yes
D030 | 145940 | HCFWF6Z1175 | F6 Z1 :Stone Cladding | Equipment breakdown | 2026-07-29 | 2026-08-01 | 20 | Third Party | No | Yes