## Executive_KPIs
KPI | Value
Total Activities | 4217
Green Activities | 1458
Yellow Activities | 1491
Orange Activities | 1136
Red Activities | 132

## Top_Escalation_Activities
task_code | task_name | SPI | CPI | progress_variance | float_days | alert_score | alert_level | recommendation
HCSWSSZ3010 | SS Z3 :Pour blinding under membrane - P1 | 0.85 | 0.88763 | -15 | 4 | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
HCSWSSZ3020 | SS Z3 :Construct block works (formwork) | 0.81 | 0.76629 | -19 | 2 | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
HCSWSSZ3050 | SS Z3 :Cast concrete for foundations | 0.8 | 0.7672 | -20 | 2 | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
HCSWSSZ1050 | SS Z1 :Cast concrete for foundations | 0.86 | 0.74547 | -14 | 2 | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
HCFWB3Z1011 | B3 Z1 :Paint Final Layer | 0.82 | 0.69524 | -18 | 3 | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
HCFWB3Z1004 | B3 Z1 :Epoxy Screed Finish Works | 0.88 | 0.72756 | -12 | 3 | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
HCFWGFZ3014 | GF Z3 :Plaster Final Layer | 0.8 | 0.85121 | -20 | 0 | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
HCFWGFZ3021 | GF Z3 :Plaster Second Layer | 0.88 | 0.86703 | -12 | 0 | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
HCFWGFZ3010 | GF Z3 :Gybsum Board Partitions | 0.86 | 0.78126 | -14 | 0 | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
HCFWF2Z3069 | F2 Z3 :Plaster Final Layer | 0.81 | 0.74922 | -19 | 0 | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
HCFWF2Z3078 | F2 Z3 :Plaster Second Layer | 0.84 | 0.71966 | -16 | 0 | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
HCFWF2Z3096 | F2 Z3 :Plaster Second Layer | 0.82 | 0.72422 | -18 | 0 | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
HCFWF3Z3121 | F3 Z3 :Foam Concrete Under Floorings | 0.81 | 0.85891 | -19 | 0 | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
HCFWF3Z3099 | F3 Z3 :Plaster Final Layer | 0.86 | 0.83424 | -14 | 0 | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
HCFWF5Z3177 | F5 Z3 :Trawelled smooth Concrete screed | 0.8 | 0.6528 | -20 | 0 | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
HCFWF5Z3216 | F5 Z3 :Plaster Second Layer | 0.84 | 0.78344 | -16 | 0 | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
HCSWGFZ2090 | GF Z2 :Casting concrete for slab topping | 0.82 | 0.69266 | -18 | 0 | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
HCSWB4Z5130 | B4 Z5 :Cast concrete for core wall | 0.82 | 0.75183 | -18 | 1 | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
HCSWSSZ5250 | SS Z5 :Cast Concrete for SOG | 0.84 | 0.72671 | -16 | 1 | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
HCSWSSZ6010 | SS Z6 :Pour blinding under membrane | 0.86 | 0.83974 | -14 | 2 | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.

## Early_Warning_Dataset
task_id | task_code | task_name | wbs_id | target_start_date | target_end_date | baseline_duration_days | total_float_hr_cnt | planned_percent | actual_percent | progress_variance | budget_cost | PV | EV | AC | SPI | CPI | cost_issue | progress_issue | schedule_issue | float_days | float_issue | alert_score | alert_level | recommendation
143649 | HCSWSSZ1000 | SS Z1 :Excavation Works - P1 | 25860 | 2012-06-05 08:00 | 2012-06-20 16:00 | 15 | 16 | 100 | 86 | -14 | 24390 | 24390 | 20975.4 | 24999.5737 | 0.86 | 0.83903 | TRUE | TRUE | TRUE | 2 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
143650 | HCSWSSZ1010 | SS Z1 :Pour blinding under membrane | 25880 | 2012-06-10 08:00 | 2012-06-23 16:00 | 13 | 16 | 100 | 99 | -1 | 25467 | 25467 | 25212.33 | 30639.1886 | 0.99 | 0.82288 | TRUE | FALSE | FALSE | 2 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143651 | HMMOAZ000 | Erect Tower crane # 1 | 25702 | 2012-06-07 08:00 | 2012-06-21 16:00 | 14 | 296 | 100 | 100 | 0 | 19040 | 19040 | 19040 | 16579.2776 | 1 | 1.1484 | FALSE | FALSE | FALSE | 37 | FALSE | 0 | Green | Continue normal monitoring.
143652 | HMMOAZ010 | Erect Tower crane # 2 | 25702 | 2012-07-01 08:00 | 2012-07-23 16:00 | 22 | 240 | 100 | 94 | -6 | 39468 | 39468 | 37099.92 | 36565.0293 | 0.94 | 1.0146 | FALSE | FALSE | FALSE | 30 | FALSE | 0 | Green | Continue normal monitoring.
143653 | HMMOAZ020 | Erect Tower crane # 3 | 25702 | 2012-07-28 08:00 | 2012-08-22 16:00 | 25 | 112 | 100 | 90 | -10 | 40750 | 40750 | 36675 | 39691.878 | 0.9 | 0.92399 | FALSE | FALSE | FALSE | 14 | FALSE | 0 | Green | Continue normal monitoring.
143654 | HCSWSSZ1020 | SS Z1 :Construct block works (formwork) | 25880 | 2012-06-14 08:00 | 2012-06-26 16:00 | 12 | 16 | 100 | 87 | -13 | 19140 | 19140 | 16651.8 | 21871.0846 | 0.87 | 0.76136 | TRUE | TRUE | TRUE | 2 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
143655 | HCSWSSZ1030 | SS Z1 :Apply water Proofing and protection (inside) | 25880 | 2012-06-16 08:00 | 2012-06-28 16:00 | 12 | 16 | 100 | 100 | 0 | 18528 | 18528 | 18528 | 20496.6785 | 1 | 0.90395 | FALSE | FALSE | FALSE | 2 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143656 | HCSWSSZ1040 | SS Z1 :Formwork and rebar for foundations | 25880 | 2012-06-25 08:00 | 2012-07-24 16:00 | 29 | 16 | 100 | 100 | 0 | 18009 | 18009 | 18009 | 18303.9435 | 1 | 0.98389 | FALSE | FALSE | FALSE | 2 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143657 | HCSWSSZ1050 | SS Z1 :Cast concrete for foundations | 25880 | 2012-07-01 08:00 | 2012-07-25 16:00 | 24 | 16 | 100 | 86 | -14 | 23184 | 23184 | 19938.24 | 26745.7017 | 0.86 | 0.74547 | TRUE | TRUE | TRUE | 2 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
143658 | HCSWSSZ1060 | SS Z1 :De-shutter formwork | 25880 | 2012-07-14 08:00 | 2012-07-26 16:00 | 12 | 136 | 100 | 100 | 0 | 20856 | 20856 | 20856 | 22813.3858 | 1 | 0.9142 | FALSE | FALSE | FALSE | 17 | FALSE | 0 | Green | Continue normal monitoring.
143659 | HCSWSSZ1220 | SS Z1 :Fill imported base course around Foundations P1 | 25879 | 2012-07-18 08:00 | 2012-07-31 16:00 | 13 | 136 | 100 | 98 | -2 | 10790 | 10790 | 10574.2 | 13038.8121 | 0.98 | 0.81098 | TRUE | FALSE | FALSE | 17 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
143660 | HCSWSSZ1230 | SS Z1 :Lay polythene sheets under SOG | 25879 | 2012-08-29 08:00 | 2012-08-29 16:00 | 1 | 24 | 100 | 100 | 0 | 1982 | 1982 | 1982 | 2333.2316 | 1 | 0.84947 | TRUE | FALSE | FALSE | 3 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143661 | HCSWSSZ1240 | SS Z1 :Formworks and Erect steel for SOG | 25879 | 2012-08-30 08:00 | 2012-09-01 16:00 | 2 | 24 | 100 | 90 | -10 | 1174 | 1174 | 1056.6 | 1116.6213 | 0.9 | 0.94625 | FALSE | FALSE | FALSE | 3 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143662 | HCSWSSZ1250 | SS Z1 :Cast Concrete for SOG | 25879 | 2012-09-01 08:00 | 2012-09-02 16:00 | 1 | 24 | 100 | 90 | -10 | 1896 | 1896 | 1706.4 | 1817.459 | 0.9 | 0.93889 | FALSE | FALSE | FALSE | 3 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143663 | HCSWSSZ2000 | SS Z2 :Excavation Works - P1 | 25787 | 2012-06-21 08:00 | 2012-06-30 16:00 | 9 | 16 | 100 | 100 | 0 | 14607 | 14607 | 14607 | 13148.3828 | 1 | 1.1109 | FALSE | FALSE | FALSE | 2 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143664 | HCSWSSZ2010 | SS Z2 :Pour blinding under membrane | 25873 | 2012-06-27 08:00 | 2012-07-03 16:00 | 6 | 269 | 100 | 100 | 0 | 8226 | 8226 | 8226 | 8100.8487 | 1 | 1.0154 | FALSE | FALSE | FALSE | 33.625 | FALSE | 0 | Green | Continue normal monitoring.
143665 | HCSWSSZ2020 | SS Z2 :Construct block works (formwork) | 25873 | 2012-06-30 08:00 | 2012-07-11 16:00 | 11 | 269 | 100 | 83 | -17 | 6930 | 6930 | 5751.9 | 8661.2357 | 0.83 | 0.6641 | TRUE | TRUE | TRUE | 33.625 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143666 | HCSWSSZ2030 | SS Z2 :Apply water Proofing and protection (inside) | 25873 | 2012-07-02 08:00 | 2012-07-12 16:00 | 10 | 269 | 100 | 87 | -13 | 18320 | 18320 | 15938.4 | 18545.3446 | 0.87 | 0.85943 | TRUE | TRUE | TRUE | 33.625 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143667 | HCSWSSZ2040 | SS Z2 :Formwork and rebar for foundations | 25873 | 2012-07-05 08:00 | 2012-07-21 16:00 | 16 | 269 | 100 | 100 | 0 | 20304 | 20304 | 20304 | 19049.1189 | 1 | 1.0659 | FALSE | FALSE | FALSE | 33.625 | FALSE | 0 | Green | Continue normal monitoring.
143668 | HCSWSSZ2050 | SS Z2 :Cast concrete for foundations | 25873 | 2012-07-12 08:00 | 2012-07-22 16:00 | 10 | 269 | 100 | 82 | -18 | 8430 | 8430 | 6912.6 | 9736.5923 | 0.82 | 0.70996 | TRUE | TRUE | TRUE | 33.625 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143669 | HCSWSSZ2060 | SS Z2 :De-shutter formwork | 25873 | 2012-07-14 08:00 | 2012-07-24 16:00 | 10 | 269 | 100 | 100 | 0 | 19370 | 19370 | 19370 | 20667.5653 | 1 | 0.93722 | FALSE | FALSE | FALSE | 33.625 | FALSE | 0 | Green | Continue normal monitoring.
143670 | HCSWSSZ2220 | SS Z2 :Fill imported base course around Foundations P1 | 25908 | 2012-07-22 08:00 | 2012-07-30 16:00 | 8 | 269 | 100 | 100 | 0 | 10440 | 10440 | 10440 | 9498.7357 | 1 | 1.0991 | FALSE | FALSE | FALSE | 33.625 | FALSE | 0 | Green | Continue normal monitoring.
143671 | HCSWSSZ2230 | SS Z2 :Lay polythene sheets under SOG | 25908 | 2012-08-23 08:00 | 2012-08-23 16:00 | 1 | 173 | 100 | 81 | -19 | 885 | 885 | 716.85 | 887.0141 | 0.81 | 0.80816 | TRUE | TRUE | TRUE | 21.625 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143672 | HCSWSSZ2240 | SS Z2 :Formworks and Erect steel for SOG | 25908 | 2012-08-25 08:00 | 2012-08-26 16:00 | 1 | 173 | 100 | 100 | 0 | 1715 | 1715 | 1715 | 1742.0762 | 1 | 0.98446 | FALSE | FALSE | FALSE | 21.625 | FALSE | 0 | Green | Continue normal monitoring.
143673 | HCSWSSZ2250 | SS Z2 :Cast Concrete for SOG | 25908 | 2012-08-26 08:00 | 2012-08-27 16:00 | 1 | 173 | 100 | 91 | -9 | 1455 | 1455 | 1324.05 | 1675.4789 | 0.91 | 0.79025 | TRUE | FALSE | FALSE | 21.625 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
143674 | HCSWSSZ3000 | SS Z3 :Excavation Works - P1 | 25783 | 2012-07-01 08:00 | 2012-07-15 16:00 | 14 | 16 | 100 | 100 | 0 | 10864 | 10864 | 10864 | 9324.2295 | 1 | 1.1651 | FALSE | FALSE | FALSE | 2 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143675 | HCSWSSZ3010 | SS Z3 :Pour blinding under membrane - P1 | 25926 | 2012-07-05 08:00 | 2012-07-22 16:00 | 17 | 32 | 100 | 85 | -15 | 28628 | 28628 | 24333.8 | 27414.3978 | 0.85 | 0.88763 | TRUE | TRUE | TRUE | 4 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
143676 | HCSWSSZ3020 | SS Z3 :Construct block works (formwork) | 25926 | 2012-07-15 08:00 | 2012-08-16 16:00 | 32 | 16 | 100 | 81 | -19 | 30688 | 30688 | 24857.28 | 32438.3981 | 0.81 | 0.76629 | TRUE | TRUE | TRUE | 2 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
143677 | HCSWSSZ3030 | SS Z3 :Apply water Proofing and protection (inside) | 25926 | 2012-07-17 08:00 | 2012-08-22 16:00 | 36 | 16 | 100 | 100 | 0 | 66132 | 66132 | 66132 | 63323.9491 | 1 | 1.0443 | FALSE | FALSE | FALSE | 2 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143678 | HCSWSSZ3040 | SS Z3 :Formwork and rebar for foundations | 25926 | 2012-07-21 08:00 | 2012-08-25 16:00 | 35 | 16 | 100 | 100 | 0 | 18235 | 18235 | 18235 | 20083.5479 | 1 | 0.90796 | FALSE | FALSE | FALSE | 2 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143679 | HCSWSSZ3050 | SS Z3 :Cast concrete for foundations | 25926 | 2012-07-25 08:00 | 2012-08-29 16:00 | 35 | 16 | 100 | 80 | -20 | 26320 | 26320 | 21056 | 27445.1008 | 0.8 | 0.7672 | TRUE | TRUE | TRUE | 2 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
143680 | HCSWSSZ3060 | SS Z3 :De-shutter formwork | 25926 | 2012-07-26 08:00 | 2012-08-30 16:00 | 35 | 16 | 100 | 91 | -9 | 43645 | 43645 | 39716.95 | 43412.9876 | 0.91 | 0.91486 | FALSE | FALSE | FALSE | 2 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143681 | HCSWSSZ3220 | SS Z3 :Fill imported base course around Foundations | 25927 | 2012-08-26 08:00 | 2012-09-02 16:00 | 7 | 16 | 100 | 100 | 0 | 9492 | 9492 | 9492 | 11672.1553 | 1 | 0.81322 | TRUE | FALSE | FALSE | 2 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143682 | HCSWSSZ3230 | SS Z3 :Lay polythene sheets under SOG | 25927 | 2012-09-06 08:00 | 2012-09-06 16:00 | 1 | 16 | 100 | 100 | 0 | 974 | 974 | 974 | 1074.1893 | 1 | 0.90673 | FALSE | FALSE | FALSE | 2 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143683 | HCSWSSZ3240 | SS Z3 :Formworks and Erect steel for SOG | 25927 | 2012-09-08 08:00 | 2012-09-09 16:00 | 1 | 16 | 100 | 100 | 0 | 1582 | 1582 | 1582 | 1426.9269 | 1 | 1.1087 | FALSE | FALSE | FALSE | 2 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143684 | HCSWSSZ3250 | SS Z3 :Cast Concrete for SOG | 25927 | 2012-09-09 08:00 | 2012-09-10 16:00 | 1 | 16 | 100 | 91 | -9 | 1010 | 1010 | 919.1 | 1084.777 | 0.91 | 0.84727 | TRUE | FALSE | FALSE | 2 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143685 | HCSWSSZ4000 | SS Z4 :Excavation Works - P1 | 25766 | 2012-07-16 08:00 | 2012-07-23 16:00 | 7 | 16 | 100 | 100 | 0 | 13993 | 13993 | 13993 | 16263.9623 | 1 | 0.86037 | TRUE | FALSE | FALSE | 2 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143686 | HCSWSSZ4010 | SS Z4 :Pour blinding under membrane | 25929 | 2012-07-22 08:00 | 2012-08-04 16:00 | 13 | 150 | 100 | 96 | -4 | 15587 | 15587 | 14963.52 | 17666.2416 | 0.96 | 0.84701 | TRUE | FALSE | FALSE | 18.75 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
143687 | HCSWSSZ4020 | SS Z4 :Construct block works (formwork) | 25929 | 2012-07-26 08:00 | 2012-08-06 16:00 | 11 | 150 | 100 | 100 | 0 | 16225 | 16225 | 16225 | 14908.1091 | 1 | 1.0883 | FALSE | FALSE | FALSE | 18.75 | FALSE | 0 | Green | Continue normal monitoring.
143688 | HCSWSSZ4030 | SS Z4 :Apply water Proofing and protection (inside) | 25929 | 2012-07-29 08:00 | 2012-08-09 16:00 | 11 | 150 | 100 | 100 | 0 | 7579 | 7579 | 7579 | 9390.1385 | 1 | 0.80712 | TRUE | FALSE | FALSE | 18.75 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
143689 | HCSWSSZ4050 | SS Z4 :Cast concrete for foundations | 25929 | 2012-08-25 08:00 | 2012-09-05 16:00 | 11 | 102 | 100 | 100 | 0 | 16027 | 16027 | 16027 | 16500.2045 | 1 | 0.97132 | FALSE | FALSE | FALSE | 12.75 | FALSE | 0 | Green | Continue normal monitoring.
143690 | HCSWSSZ4060 | SS Z4 :De-shutter formwork | 25929 | 2012-08-27 08:00 | 2012-09-06 16:00 | 10 | 102 | 100 | 89 | -11 | 11860 | 11860 | 10555.4 | 10835.4146 | 0.89 | 0.97416 | FALSE | TRUE | TRUE | 12.75 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143691 | HCSWSSZ4220 | SS Z4 :Fill imported base course around Foundations P1 | 25930 | 2012-09-03 08:00 | 2012-09-09 16:00 | 6 | 102 | 100 | 100 | 0 | 8742 | 8742 | 8742 | 8060.8085 | 1 | 1.0845 | FALSE | FALSE | FALSE | 12.75 | FALSE | 0 | Green | Continue normal monitoring.
143692 | HCSWSSZ4230 | SS Z4 :Lay polythene sheets under SOG | 25930 | 2012-09-15 08:00 | 2012-09-15 16:00 | 1 | 102 | 100 | 100 | 0 | 1062 | 1062 | 1062 | 944.4302 | 1 | 1.1245 | FALSE | FALSE | FALSE | 12.75 | FALSE | 0 | Green | Continue normal monitoring.
143693 | HCSWSSZ4240 | SS Z4 :Formworks and Erect steel for SOG | 25930 | 2012-09-16 08:00 | 2012-09-19 16:00 | 3 | 102 | 100 | 95 | -5 | 5301 | 5301 | 5035.95 | 6209.6298 | 0.95 | 0.81099 | TRUE | FALSE | FALSE | 12.75 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
143694 | HCSWSSZ4250 | SS Z4 :Cast Concrete for SOG | 25930 | 2012-09-17 08:00 | 2012-09-20 16:00 | 3 | 102 | 100 | 94 | -6 | 3993 | 3993 | 3753.42 | 3588.9571 | 0.94 | 1.0458 | FALSE | FALSE | FALSE | 12.75 | FALSE | 0 | Green | Continue normal monitoring.
143695 | HCSWSSZ5000 | SS Z5 :Excavation Works | 25773 | 2012-06-21 08:00 | 2012-08-09 16:00 | 49 | 8 | 100 | 100 | 0 | 81046 | 81046 | 81046 | 72945.4606 | 1 | 1.111 | FALSE | FALSE | FALSE | 1 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143696 | HCSWSSZ5010 | SS Z5 :Pour blinding under membrane | 25932 | 2012-07-10 08:00 | 2012-08-22 16:00 | 43 | 8 | 100 | 100 | 0 | 49278 | 49278 | 49278 | 58650.1161 | 1 | 0.8402 | TRUE | FALSE | FALSE | 1 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143697 | HCSWSSZ5020 | SS Z5 :Construct block works (formwork) | 25932 | 2012-07-16 08:00 | 2012-08-28 16:00 | 43 | 8 | 100 | 94 | -6 | 22360 | 22360 | 21018.4 | 22088.1389 | 0.94 | 0.95157 | FALSE | FALSE | FALSE | 1 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143698 | HCSWSSZ5030 | SS Z5 :Apply water Proofing and protection (inside) | 25932 | 2012-07-19 08:00 | 2012-09-01 16:00 | 44 | 8 | 100 | 100 | 0 | 58960 | 58960 | 58960 | 50843.7528 | 1 | 1.1596 | FALSE | FALSE | FALSE | 1 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143699 | HCSWSSZ5040 | SS Z5 :Formwork and rebar for foundations | 25932 | 2012-07-26 08:00 | 2012-09-08 16:00 | 44 | 8 | 100 | 98 | -2 | 29304 | 29304 | 28717.92 | 25516.6959 | 0.98 | 1.1255 | FALSE | FALSE | FALSE | 1 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143700 | HCSWSSZ5050 | SS Z5 :Cast concrete for foundations | 25932 | 2012-08-01 08:00 | 2012-09-09 16:00 | 39 | 8 | 100 | 91 | -9 | 70083 | 70083 | 63775.53 | 63556.0426 | 0.91 | 1.0035 | FALSE | FALSE | FALSE | 1 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143701 | HCSWSSZ5060 | SS Z5 :De-shutter formwork | 25932 | 2012-08-02 08:00 | 2012-09-13 16:00 | 42 | 8 | 100 | 100 | 0 | 37254 | 37254 | 37254 | 34845.8023 | 1 | 1.0691 | FALSE | FALSE | FALSE | 1 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143702 | HCSWSSZ5220 | SS Z5 :Fill imported base course around Foundations | 26042 | 2012-09-11 08:00 | 2012-09-16 16:00 | 5 | 8 | 100 | 99 | -1 | 5500 | 5500 | 5445 | 6138.3216 | 0.99 | 0.88705 | TRUE | FALSE | FALSE | 1 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143703 | HCSWSSZ5230 | SS Z5 :Lay polythene sheets under SOG | 26042 | 2012-09-20 08:00 | 2012-09-20 16:00 | 1 | 8 | 100 | 100 | 0 | 815 | 815 | 815 | 744.0384 | 1 | 1.0954 | FALSE | FALSE | FALSE | 1 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143704 | HCSWSSZ5240 | SS Z5 :Formworks and Erect steel for SOG | 26042 | 2012-09-22 08:00 | 2012-09-24 16:00 | 2 | 8 | 100 | 82 | -18 | 1026 | 1026 | 841.32 | 920.8861 | 0.82 | 0.9136 | FALSE | TRUE | TRUE | 1 | TRUE | 4 | Orange | Develop recovery plan and review schedule and cost exposure.
143705 | HCSWSSZ5250 | SS Z5 :Cast Concrete for SOG | 26042 | 2012-09-23 08:00 | 2012-09-25 16:00 | 2 | 8 | 100 | 84 | -16 | 1482 | 1482 | 1244.88 | 1713.0255 | 0.84 | 0.72671 | TRUE | TRUE | TRUE | 1 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
143706 | HCSWSSZ6000 | SS Z6 :Excavation Works & remove of the access ramps | 25839 | 2012-08-11 08:00 | 2012-09-02 16:00 | 22 | 16 | 100 | 98 | -2 | 28072 | 28072 | 27510.56 | 31396.3456 | 0.98 | 0.87623 | TRUE | FALSE | FALSE | 2 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143707 | HCSWSSZ6010 | SS Z6 :Pour blinding under membrane | 25935 | 2012-08-26 08:00 | 2012-09-15 16:00 | 20 | 16 | 100 | 86 | -14 | 37380 | 37380 | 32146.8 | 38281.9678 | 0.86 | 0.83974 | TRUE | TRUE | TRUE | 2 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
143708 | HCSWSSZ6020 | SS Z6 :Construct block works (formwork) | 25935 | 2012-08-29 08:00 | 2012-09-18 16:00 | 20 | 16 | 100 | 100 | 0 | 21280 | 21280 | 21280 | 22763.7248 | 1 | 0.93482 | FALSE | FALSE | FALSE | 2 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143709 | HCSWSSZ6030 | SS Z6 :Apply water Proofing and protection (inside) | 25935 | 2012-09-02 08:00 | 2012-09-22 16:00 | 20 | 16 | 100 | 88 | -12 | 27940 | 27940 | 24587.2 | 27235.7334 | 0.88 | 0.90276 | FALSE | TRUE | TRUE | 2 | TRUE | 4 | Orange | Develop recovery plan and review schedule and cost exposure.
143710 | HCSWSSZ6040 | SS Z6 :Formwork and rebar for foundations | 25935 | 2012-09-06 08:00 | 2012-09-26 16:00 | 20 | 16 | 100 | 86 | -14 | 37260 | 37260 | 32043.6 | 38862.1863 | 0.86 | 0.82454 | TRUE | TRUE | TRUE | 2 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
143711 | HCSWSSZ6050 | SS Z6 :Cast concrete for foundations | 25935 | 2012-09-12 08:00 | 2012-10-04 16:00 | 22 | 16 | 100 | 97 | -3 | 13002 | 13002 | 12611.94 | 13686.8031 | 0.97 | 0.92147 | FALSE | FALSE | FALSE | 2 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143712 | HCSWSSZ6060 | SS Z6 :De-shutter formwork | 25935 | 2012-09-13 08:00 | 2012-10-06 16:00 | 23 | 16 | 100 | 83 | -17 | 43470 | 43470 | 36080.1 | 43682.7817 | 0.83 | 0.82596 | TRUE | TRUE | TRUE | 2 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
143713 | HCSWSSZ6220 | SS Z6 :Fill imported base course around Foundations | 25994 | 2012-10-04 08:00 | 2012-10-08 16:00 | 4 | 16 | 100 | 100 | 0 | 5820 | 5820 | 5820 | 7057.5001 | 1 | 0.82465 | TRUE | FALSE | FALSE | 2 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143714 | HCSWSSZ6230 | SS Z6 :Lay polythene sheets under SOG | 25994 | 2012-10-09 08:00 | 2012-10-09 16:00 | 1 | 24 | 100 | 100 | 0 | 1978 | 1978 | 1978 | 1694.0081 | 1 | 1.1676 | FALSE | FALSE | FALSE | 3 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143715 | HCSWSSZ6240 | SS Z6 :Formworks and Erect steel for SOG | 25994 | 2012-10-10 08:00 | 2012-10-13 16:00 | 3 | 24 | 100 | 93 | -7 | 5853 | 5853 | 5443.29 | 6806.2694 | 0.93 | 0.79975 | TRUE | FALSE | FALSE | 3 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143716 | HCSWSSZ6250 | SS Z6 :Cast Concrete for SOG | 25994 | 2012-10-14 08:00 | 2012-10-15 16:00 | 1 | 16 | 100 | 97 | -3 | 1008 | 1008 | 977.76 | 906.9512 | 0.97 | 1.0781 | FALSE | FALSE | FALSE | 2 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143717 | HCSWB4Z1010 | B4 Z1 :Formwork retaining walls shutters - 1st side | 25995 | 2012-07-26 08:00 | 2012-08-04 16:00 | 9 | 16 | 100 | 100 | 0 | 11475 | 11475 | 11475 | 13414.4924 | 1 | 0.85542 | TRUE | FALSE | FALSE | 2 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143718 | HCSWB4Z1020 | B4 Z1 :Fix steel rebar for reatining walls | 25995 | 2012-07-28 08:00 | 2012-08-05 16:00 | 8 | 144 | 100 | 88 | -12 | 4272 | 4272 | 3759.36 | 4683.6703 | 0.88 | 0.80265 | TRUE | TRUE | TRUE | 18 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143719 | HCSWB4Z1030 | B4 Z1 :Fix MEP first fix in walls | 25995 | 2012-07-28 08:00 | 2012-08-05 16:00 | 8 | 144 | 100 | 100 | 0 | 5640 | 5640 | 5640 | 6696.4354 | 1 | 0.84224 | TRUE | FALSE | FALSE | 18 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
143720 | HCSWB4Z1040 | B4 Z1 :Close shutter for retaining walls | 25995 | 2012-07-29 08:00 | 2012-08-06 16:00 | 8 | 144 | 100 | 100 | 0 | 12832 | 12832 | 12832 | 11407.7215 | 1 | 1.1249 | FALSE | FALSE | FALSE | 18 | FALSE | 0 | Green | Continue normal monitoring.
143721 | HCSWB4Z1050 | B4 Z1 :Cast concrete for retaining walls | 25995 | 2012-07-30 08:00 | 2012-08-07 16:00 | 8 | 144 | 100 | 81 | -19 | 15288 | 15288 | 12383.28 | 16413.0784 | 0.81 | 0.75448 | TRUE | TRUE | TRUE | 18 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143722 | HCSWB4Z1060 | B4 Z1 :De-shutter retaining walls | 25995 | 2012-07-31 08:00 | 2012-08-08 16:00 | 8 | 144 | 100 | 99 | -1 | 12200 | 12200 | 12078 | 12815.3089 | 0.99 | 0.94247 | FALSE | FALSE | FALSE | 18 | FALSE | 0 | Green | Continue normal monitoring.
143723 | HCSWB4Z1070 | B4 Z1 :Apply water proofing membrane behind Basement Walls | 25995 | 2012-08-05 08:00 | 2012-08-26 16:00 | 21 | 592 | 100 | 100 | 0 | 31941 | 31941 | 31941 | 36172.4566 | 1 | 0.88302 | TRUE | FALSE | FALSE | 74 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
143724 | HCSWB4Z1080 | B4 Z1 :Apply Protection for Basement Walls | 25995 | 2012-08-07 08:00 | 2012-08-28 16:00 | 21 | 592 | 100 | 94 | -6 | 40173 | 40173 | 37762.62 | 42732.6717 | 0.94 | 0.88369 | TRUE | FALSE | FALSE | 74 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
143725 | HCSWB4Z1090 | B4 Z1 :Formwork core wall shutters - 1st side | 25941 | 2012-08-01 08:00 | 2012-08-12 16:00 | 11 | 16 | 100 | 100 | 0 | 11715 | 11715 | 11715 | 12491.6322 | 1 | 0.93783 | FALSE | FALSE | FALSE | 2 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143726 | HCSWB4Z1100 | B4 Z1 :Fix steel rebar for core wall | 25941 | 2012-08-13 08:00 | 2012-08-23 16:00 | 10 | 16 | 100 | 86 | -14 | 16290 | 16290 | 14009.4 | 16645.7472 | 0.86 | 0.84162 | TRUE | TRUE | TRUE | 2 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
143727 | HCSWB4Z1110 | B4 Z1 :Fix MEP first fix in core wall | 25941 | 2012-08-25 08:00 | 2012-08-25 16:00 | 1 | 16 | 100 | 91 | -9 | 1202 | 1202 | 1093.82 | 1170.1876 | 0.91 | 0.93474 | FALSE | FALSE | FALSE | 2 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143728 | HCSWB4Z1120 | B4 Z1 :Close shutter for core wall | 25941 | 2012-08-26 08:00 | 2012-08-28 16:00 | 2 | 16 | 100 | 100 | 0 | 1802 | 1802 | 1802 | 1879.3162 | 1 | 0.95886 | FALSE | FALSE | FALSE | 2 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143729 | HCSWB4Z1130 | B4 Z1 :Cast concrete for core wall | 25941 | 2012-08-29 08:00 | 2012-08-29 16:00 | 1 | 16 | 100 | 87 | -13 | 1229 | 1229 | 1069.23 | 1102.9008 | 0.87 | 0.96947 | FALSE | TRUE | TRUE | 2 | TRUE | 4 | Orange | Develop recovery plan and review schedule and cost exposure.
143730 | HCSWB4Z1140 | B4 Z1 :De-shutter core wall formwork | 25941 | 2012-08-30 08:00 | 2012-09-01 16:00 | 2 | 16 | 100 | 94 | -6 | 1322 | 1322 | 1242.68 | 1632.1483 | 0.94 | 0.76138 | TRUE | FALSE | FALSE | 2 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143731 | HCSWB4Z1150 | B4 Z1 :Fix Steel Rebar for columns | 25939 | 2012-07-26 08:00 | 2012-08-06 16:00 | 11 | 168 | 100 | 82 | -18 | 7711 | 7711 | 6323.02 | 8757.8786 | 0.82 | 0.72198 | TRUE | TRUE | TRUE | 21 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143732 | HCSWB4Z1160 | B4 Z1 :Erect columns formwork | 25939 | 2012-07-28 08:00 | 2012-08-07 16:00 | 10 | 168 | 100 | 93 | -7 | 14950 | 14950 | 13903.5 | 18403.2534 | 0.93 | 0.75549 | TRUE | FALSE | FALSE | 21 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
143733 | HCSWB4Z1170 | B4 Z1 :Cast concrete for columns | 25939 | 2012-07-29 08:00 | 2012-08-08 16:00 | 10 | 168 | 100 | 96 | -4 | 7690 | 7690 | 7382.4 | 7233.9134 | 0.96 | 1.0205 | FALSE | FALSE | FALSE | 21 | FALSE | 0 | Green | Continue normal monitoring.
143734 | HCSWB4Z1180 | B4 Z1 :De-shutter columns formwork | 25939 | 2012-07-30 08:00 | 2012-08-09 16:00 | 10 | 168 | 100 | 83 | -17 | 13150 | 13150 | 10914.5 | 15802.8338 | 0.83 | 0.69067 | TRUE | TRUE | TRUE | 21 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143735 | HCSWB4Z1190 | B4 Z1 :Erect slab formwork and proping | 25940 | 2012-08-30 08:00 | 2012-09-08 16:00 | 9 | 16 | 100 | 97 | -3 | 16146 | 16146 | 15661.62 | 18947.5892 | 0.97 | 0.82658 | TRUE | FALSE | FALSE | 2 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143736 | HCSWB4Z1200 | B4 Z1 :Fix steel rebar for slab | 25940 | 2012-09-09 08:00 | 2012-09-11 16:00 | 2 | 16 | 100 | 87 | -13 | 1910 | 1910 | 1661.7 | 2140.8444 | 0.87 | 0.77619 | TRUE | TRUE | TRUE | 2 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
143737 | HCSWB4Z1210 | B4 Z1 :Fix MEP first Fix for slab | 25940 | 2012-09-12 08:00 | 2012-09-13 16:00 | 1 | 16 | 100 | 83 | -17 | 1985 | 1985 | 1647.55 | 2183.5232 | 0.83 | 0.75454 | TRUE | TRUE | TRUE | 2 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
143738 | HCSWB4Z1220 | B4 Z1 :Fix side shutters and casting guides for slab | 25940 | 2012-09-13 08:00 | 2012-09-15 16:00 | 2 | 16 | 100 | 81 | -19 | 3550 | 3550 | 2875.5 | 3467.0005 | 0.81 | 0.82939 | TRUE | TRUE | TRUE | 2 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
143739 | HCSWB4Z1230 | B4 Z1 :Cast concrete for slab | 25940 | 2012-09-16 08:00 | 2012-09-16 16:00 | 1 | 16 | 100 | 100 | 0 | 1516 | 1516 | 1516 | 1783.6715 | 1 | 0.84993 | TRUE | FALSE | FALSE | 2 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143740 | HCSWB4Z1240 | B4 Z1 :Cure and De-shutter slab formwork | 25940 | 2012-09-16 16:00 | 2012-09-30 16:00 | 14 | 16 | 100 | 85 | -15 | 11130 | 11130 | 9460.5 | 11693.2468 | 0.85 | 0.80906 | TRUE | TRUE | TRUE | 2 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
143741 | HCSWB4Z2010 | B4 Z2 :Formwork retaining walls shutters - 1st side | 26049 | 2012-07-23 08:00 | 2012-07-31 16:00 | 8 | 293 | 100 | 100 | 0 | 9752 | 9752 | 9752 | 8565.7339 | 1 | 1.1385 | FALSE | FALSE | FALSE | 36.625 | FALSE | 0 | Green | Continue normal monitoring.
143742 | HCSWB4Z2020 | B4 Z2 :Fix steel rebar for reatining walls | 26049 | 2012-07-23 08:00 | 2012-07-31 16:00 | 8 | 293 | 100 | 89 | -11 | 6696 | 6696 | 5959.44 | 6529.5727 | 0.89 | 0.91268 | FALSE | TRUE | TRUE | 36.625 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143743 | HCSWB4Z2030 | B4 Z2 :Fix MEP first fix in walls | 26049 | 2012-07-24 08:00 | 2012-08-01 16:00 | 8 | 293 | 100 | 83 | -17 | 11024 | 11024 | 9149.92 | 13494.6861 | 0.83 | 0.67804 | TRUE | TRUE | TRUE | 36.625 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143744 | HCSWB4Z2040 | B4 Z2 :Close shutter for retaining walls | 26049 | 2012-07-25 08:00 | 2012-08-02 16:00 | 8 | 293 | 100 | 100 | 0 | 12608 | 12608 | 12608 | 15006.9507 | 1 | 0.84014 | TRUE | FALSE | FALSE | 36.625 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
143745 | HCSWB4Z2050 | B4 Z2 :Cast concrete for retaining walls | 26049 | 2012-07-26 08:00 | 2012-08-04 16:00 | 9 | 293 | 100 | 100 | 0 | 11619 | 11619 | 11619 | 14439.6549 | 1 | 0.80466 | TRUE | FALSE | FALSE | 36.625 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
143746 | HCSWB4Z2060 | B4 Z2 :De-shutter retaining walls | 26049 | 2012-07-28 08:00 | 2012-08-05 16:00 | 8 | 293 | 100 | 100 | 0 | 5728 | 5728 | 5728 | 6307.6584 | 1 | 0.9081 | FALSE | FALSE | FALSE | 36.625 | FALSE | 0 | Green | Continue normal monitoring.
143747 | HCSWB4Z2070 | B4 Z2 :Apply water proofing membrane behind Basement Walls | 26049 | 2012-08-01 08:00 | 2012-08-09 16:00 | 8 | 672 | 100 | 97 | -3 | 10104 | 10104 | 9800.88 | 9588.7367 | 0.97 | 1.0221 | FALSE | FALSE | FALSE | 84 | FALSE | 0 | Green | Continue normal monitoring.
143748 | HCSWB4Z2080 | B4 Z2 :Apply Protection for Basement Walls | 26049 | 2012-08-04 08:00 | 2012-08-12 16:00 | 8 | 672 | 100 | 100 | 0 | 5496 | 5496 | 5496 | 5029.5326 | 1 | 1.0927 | FALSE | FALSE | FALSE | 84 | FALSE | 0 | Green | Continue normal monitoring.
143749 | HCSWB4Z2150 | B4 Z2 :Fix Steel Rebar for columns | 26051 | 2012-07-23 08:00 | 2012-07-31 16:00 | 8 | 333 | 100 | 91 | -9 | 7032 | 7032 | 6399.12 | 6502.9529 | 0.91 | 0.98403 | FALSE | FALSE | FALSE | 41.625 | FALSE | 0 | Green | Continue normal monitoring.
143750 | HCSWB4Z2160 | B4 Z2 :Erect columns formwork | 26051 | 2012-07-24 08:00 | 2012-08-01 16:00 | 8 | 333 | 100 | 81 | -19 | 7936 | 7936 | 6428.16 | 6808.4393 | 0.81 | 0.94415 | FALSE | TRUE | TRUE | 41.625 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143751 | HCSWB4Z2170 | B4 Z2 :Cast concrete for columns | 26051 | 2012-07-25 08:00 | 2012-08-02 16:00 | 8 | 333 | 100 | 89 | -11 | 12512 | 12512 | 11135.68 | 12590.4858 | 0.89 | 0.88445 | TRUE | TRUE | TRUE | 41.625 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143752 | HCSWB4Z2180 | B4 Z2 :De-shutter columns formwork | 26051 | 2012-07-26 08:00 | 2012-08-04 16:00 | 9 | 333 | 100 | 100 | 0 | 15120 | 15120 | 15120 | 14009.7546 | 1 | 1.0792 | FALSE | FALSE | FALSE | 41.625 | FALSE | 0 | Green | Continue normal monitoring.
143753 | HCSWB4Z2190 | B4 Z2 :Erect slab formwork and proping | 25945 | 2012-08-28 08:00 | 2012-09-03 16:00 | 6 | 173 | 100 | 83 | -17 | 3084 | 3084 | 2559.72 | 3129.2182 | 0.83 | 0.81801 | TRUE | TRUE | TRUE | 21.625 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143754 | HCSWB4Z2200 | B4 Z2 :Fix steel rebar for slab | 25945 | 2012-09-04 08:00 | 2012-09-06 16:00 | 2 | 173 | 100 | 93 | -7 | 1128 | 1128 | 1049.04 | 1380.6695 | 0.93 | 0.75981 | TRUE | FALSE | FALSE | 21.625 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
143755 | HCSWB4Z2210 | B4 Z2 :Fix MEP first Fix for slab | 25945 | 2012-09-08 08:00 | 2012-09-09 16:00 | 1 | 173 | 100 | 100 | 0 | 1020 | 1020 | 1020 | 1042.6604 | 1 | 0.97827 | FALSE | FALSE | FALSE | 21.625 | FALSE | 0 | Green | Continue normal monitoring.
143756 | HCSWB4Z2220 | B4 Z2 :Fix side shutters and casting guides for slab | 25945 | 2012-09-09 08:00 | 2012-09-10 16:00 | 1 | 173 | 100 | 95 | -5 | 1867 | 1867 | 1773.65 | 2242.6288 | 0.95 | 0.79088 | TRUE | FALSE | FALSE | 21.625 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
143757 | HCSWB4Z2230 | B4 Z2 :Cast concrete for slab | 25945 | 2012-09-11 08:00 | 2012-09-11 16:00 | 1 | 173 | 100 | 94 | -6 | 1652 | 1652 | 1552.88 | 1804.3175 | 0.94 | 0.86065 | TRUE | FALSE | FALSE | 21.625 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
143758 | HCSWB4Z2240 | B4 Z2 :Cure and De-shutter slab formwork | 25945 | 2012-09-11 16:00 | 2012-09-25 16:00 | 14 | 205 | 100 | 87 | -13 | 16058 | 16058 | 13970.46 | 15236.6754 | 0.87 | 0.9169 | FALSE | TRUE | TRUE | 25.625 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143759 | HCSWB4Z3010 | B4 Z3 :Formwork retaining walls shutters - 1st side | 25947 | 2012-08-26 08:00 | 2012-08-30 16:00 | 4 | 24 | 100 | 93 | -7 | 7980 | 7980 | 7421.4 | 7918.8884 | 0.93 | 0.93718 | FALSE | FALSE | FALSE | 3 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143760 | HCSWB4Z3020 | B4 Z3 :Fix steel rebar for reatining walls | 25947 | 2012-08-26 08:00 | 2012-08-30 16:00 | 4 | 72 | 100 | 100 | 0 | 6344 | 6344 | 6344 | 5605.3542 | 1 | 1.1318 | FALSE | FALSE | FALSE | 9 | FALSE | 0 | Green | Continue normal monitoring.
143761 | HCSWB4Z3030 | B4 Z3 :Fix MEP first fix in walls | 25947 | 2012-08-27 08:00 | 2012-09-01 16:00 | 5 | 72 | 100 | 100 | 0 | 8310 | 8310 | 8310 | 8171.9297 | 1 | 1.0169 | FALSE | FALSE | FALSE | 9 | FALSE | 0 | Green | Continue normal monitoring.
143762 | HCSWB4Z3040 | B4 Z3 :Close shutter for retaining walls | 25947 | 2012-08-28 08:00 | 2012-09-02 16:00 | 5 | 72 | 100 | 100 | 0 | 5460 | 5460 | 5460 | 6120.7494 | 1 | 0.89205 | TRUE | FALSE | FALSE | 9 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
143763 | HCSWB4Z3050 | B4 Z3 :Cast concrete for retaining walls | 25947 | 2012-08-29 08:00 | 2012-09-03 16:00 | 5 | 72 | 100 | 100 | 0 | 4455 | 4455 | 4455 | 3915.252 | 1 | 1.1379 | FALSE | FALSE | FALSE | 9 | FALSE | 0 | Green | Continue normal monitoring.
143764 | HCSWB4Z3060 | B4 Z3 :De-shutter retaining walls | 25947 | 2012-08-30 08:00 | 2012-09-04 16:00 | 5 | 72 | 100 | 87 | -13 | 4590 | 4590 | 3993.3 | 4278.617 | 0.87 | 0.93332 | FALSE | TRUE | TRUE | 9 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143765 | HCSWB4Z3070 | B4 Z3 :Apply water proofing membrane behind Basement Walls | 25947 | 2012-09-03 08:00 | 2012-09-08 16:00 | 5 | 1040 | 100 | 100 | 0 | 3940 | 3940 | 3940 | 3950.1511 | 1 | 0.99743 | FALSE | FALSE | FALSE | 130 | FALSE | 0 | Green | Continue normal monitoring.
143766 | HCSWB4Z3080 | B4 Z3 :Apply Protection for Basement Walls | 25947 | 2012-09-05 08:00 | 2012-09-10 16:00 | 5 | 1040 | 100 | 95 | -5 | 4390 | 4390 | 4170.5 | 5455.979 | 0.95 | 0.76439 | TRUE | FALSE | FALSE | 130 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
143767 | HCSWB4Z3090 | B4 Z3 :Formwork core wall shutters - 1st side | 25948 | 2012-08-26 08:00 | 2012-08-30 16:00 | 4 | 24 | 100 | 92 | -8 | 2920 | 2920 | 2686.4 | 3398.7186 | 0.92 | 0.79042 | TRUE | FALSE | FALSE | 3 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143768 | HCSWB4Z3100 | B4 Z3 :Fix steel rebar for core wall | 25948 | 2012-09-01 08:00 | 2012-09-03 16:00 | 2 | 24 | 100 | 97 | -3 | 3034 | 3034 | 2942.98 | 3469.0595 | 0.97 | 0.84835 | TRUE | FALSE | FALSE | 3 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143769 | HCSWB4Z3110 | B4 Z3 :Fix MEP first fix in core wall | 25948 | 2012-09-04 08:00 | 2012-09-04 16:00 | 1 | 24 | 100 | 94 | -6 | 540 | 540 | 507.6 | 484.0972 | 0.94 | 1.0485 | FALSE | FALSE | FALSE | 3 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143770 | HCSWB4Z3120 | B4 Z3 :Close shutter for core wall | 25948 | 2012-09-05 08:00 | 2012-09-06 16:00 | 1 | 24 | 100 | 100 | 0 | 1551 | 1551 | 1551 | 1802.8799 | 1 | 0.86029 | TRUE | FALSE | FALSE | 3 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143771 | HCSWB4Z3130 | B4 Z3 :Cast concrete for core wall | 25948 | 2012-09-08 08:00 | 2012-09-08 16:00 | 1 | 24 | 100 | 100 | 0 | 634 | 634 | 634 | 738.0442 | 1 | 0.85903 | TRUE | FALSE | FALSE | 3 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143772 | HCSWB4Z3140 | B4 Z3 :De-shutter core wall formwork | 25948 | 2012-09-09 08:00 | 2012-09-10 16:00 | 1 | 24 | 100 | 100 | 0 | 700 | 700 | 700 | 763.3088 | 1 | 0.91706 | FALSE | FALSE | FALSE | 3 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143773 | HCSWB4Z3150 | B4 Z3 :Fix Steel Rebar for columns | 25949 | 2012-08-26 08:00 | 2012-08-28 16:00 | 2 | 88 | 100 | 100 | 0 | 2558 | 2558 | 2558 | 3187.6382 | 1 | 0.80248 | TRUE | FALSE | FALSE | 11 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
143774 | HCSWB4Z3160 | B4 Z3 :Erect columns formwork | 25949 | 2012-08-27 08:00 | 2012-08-29 16:00 | 2 | 88 | 100 | 100 | 0 | 2858 | 2858 | 2858 | 2801.1303 | 1 | 1.0203 | FALSE | FALSE | FALSE | 11 | FALSE | 0 | Green | Continue normal monitoring.
143775 | HCSWB4Z3170 | B4 Z3 :Cast concrete for columns | 25949 | 2012-08-28 08:00 | 2012-08-30 16:00 | 2 | 88 | 100 | 100 | 0 | 3112 | 3112 | 3112 | 3816.8959 | 1 | 0.81532 | TRUE | FALSE | FALSE | 11 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
143776 | HCSWB4Z3180 | B4 Z3 :De-shutter columns formwork | 25949 | 2012-08-29 08:00 | 2012-09-01 16:00 | 3 | 88 | 100 | 100 | 0 | 4713 | 4713 | 4713 | 5730.5011 | 1 | 0.82244 | TRUE | FALSE | FALSE | 11 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
143777 | HCSWB4Z3190 | B4 Z3 :Erect slab formwork and proping | 25950 | 2012-09-11 08:00 | 2012-09-18 16:00 | 7 | 16 | 100 | 92 | -8 | 7014 | 7014 | 6452.88 | 5994.1101 | 0.92 | 1.0765 | FALSE | FALSE | FALSE | 2 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143778 | HCSWB4Z3200 | B4 Z3 :Fix steel rebar for slab | 25950 | 2012-09-19 08:00 | 2012-09-22 16:00 | 3 | 16 | 100 | 88 | -12 | 2718 | 2718 | 2391.84 | 2799.6667 | 0.88 | 0.85433 | TRUE | TRUE | TRUE | 2 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
143779 | HCSWB4Z3210 | B4 Z3 :Fix MEP first Fix for slab | 25950 | 2012-09-23 08:00 | 2012-09-24 16:00 | 1 | 16 | 100 | 100 | 0 | 1304 | 1304 | 1304 | 1618.0576 | 1 | 0.8059 | TRUE | FALSE | FALSE | 2 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143780 | HCSWB4Z3220 | B4 Z3 :Fix side shutters and casting guides for slab | 25950 | 2012-09-24 08:00 | 2012-09-25 16:00 | 1 | 16 | 100 | 94 | -6 | 598 | 598 | 562.12 | 532.9666 | 0.94 | 1.0547 | FALSE | FALSE | FALSE | 2 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143781 | HCSWB4Z3230 | B4 Z3 :Cast concrete for slab | 25950 | 2012-09-26 08:00 | 2012-09-26 16:00 | 1 | 16 | 100 | 92 | -8 | 1183 | 1183 | 1088.36 | 1264.7617 | 0.92 | 0.86053 | TRUE | FALSE | FALSE | 2 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143782 | HCSWB4Z3240 | B4 Z3 :Cure and De-shutter slab formwork | 25950 | 2012-09-26 16:00 | 2012-10-10 16:00 | 14 | 24 | 100 | 80 | -20 | 17150 | 17150 | 13720 | 21293.1485 | 0.8 | 0.64434 | TRUE | TRUE | TRUE | 3 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
143783 | HCSWB4Z4010 | B4 Z4 :Formwork retaining walls shutters - 1st side | 25952 | 2012-09-06 08:00 | 2012-09-11 16:00 | 5 | 126 | 100 | 100 | 0 | 7300 | 7300 | 7300 | 7827.0466 | 1 | 0.93266 | FALSE | FALSE | FALSE | 15.75 | FALSE | 0 | Green | Continue normal monitoring.
143784 | HCSWB4Z4020 | B4 Z4 :Fix steel rebar for reatining walls | 25952 | 2012-09-06 08:00 | 2012-09-11 16:00 | 5 | 142 | 100 | 86 | -14 | 5560 | 5560 | 4781.6 | 5148.1492 | 0.86 | 0.9288 | FALSE | TRUE | TRUE | 17.75 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143785 | HCSWB4Z4030 | B4 Z4 :Fix MEP first fix in walls | 25952 | 2012-09-08 08:00 | 2012-09-12 16:00 | 4 | 142 | 100 | 88 | -12 | 7940 | 7940 | 6987.2 | 8598.0139 | 0.88 | 0.81265 | TRUE | TRUE | TRUE | 17.75 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143786 | HCSWB4Z4040 | B4 Z4 :Close shutter for retaining walls | 25952 | 2012-09-09 08:00 | 2012-09-13 16:00 | 4 | 142 | 100 | 100 | 0 | 4568 | 4568 | 4568 | 4256.3538 | 1 | 1.0732 | FALSE | FALSE | FALSE | 17.75 | FALSE | 0 | Green | Continue normal monitoring.
143787 | HCSWB4Z4050 | B4 Z4 :Cast concrete for retaining walls | 25952 | 2012-09-10 08:00 | 2012-09-15 16:00 | 5 | 142 | 100 | 80 | -20 | 7640 | 7640 | 6112 | 8082.2162 | 0.8 | 0.75623 | TRUE | TRUE | TRUE | 17.75 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143788 | HCSWB4Z4060 | B4 Z4 :De-shutter retaining walls | 25952 | 2012-09-11 08:00 | 2012-09-16 16:00 | 5 | 142 | 100 | 91 | -9 | 8705 | 8705 | 7921.55 | 7657.065 | 0.91 | 1.0345 | FALSE | FALSE | FALSE | 17.75 | FALSE | 0 | Green | Continue normal monitoring.
143789 | HCSWB4Z4070 | B4 Z4 :Apply water proofing membrane behind Basement Walls | 25952 | 2012-09-15 08:00 | 2012-09-19 16:00 | 4 | 944 | 100 | 87 | -13 | 4008 | 4008 | 3486.96 | 4377.5098 | 0.87 | 0.79656 | TRUE | TRUE | TRUE | 118 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143790 | HCSWB4Z4080 | B4 Z4 :Apply Protection for Basement Walls | 25952 | 2012-09-17 08:00 | 2012-09-22 16:00 | 5 | 944 | 100 | 100 | 0 | 6330 | 6330 | 6330 | 6689.0121 | 1 | 0.94633 | FALSE | FALSE | FALSE | 118 | FALSE | 0 | Green | Continue normal monitoring.
143791 | HCSWB4Z4150 | B4 Z4 :Fix Steel Rebar for columns | 25953 | 2012-09-06 08:00 | 2012-09-15 16:00 | 9 | 126 | 100 | 100 | 0 | 8073 | 8073 | 8073 | 9252.1791 | 1 | 0.87255 | TRUE | FALSE | FALSE | 15.75 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
143792 | HCSWB4Z4160 | B4 Z4 :Erect columns formwork | 25953 | 2012-09-08 08:00 | 2012-09-16 16:00 | 8 | 126 | 100 | 90 | -10 | 10960 | 10960 | 9864 | 12080.9909 | 0.9 | 0.81649 | TRUE | FALSE | FALSE | 15.75 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
143793 | HCSWB4Z4170 | B4 Z4 :Cast concrete for columns | 25953 | 2012-09-09 08:00 | 2012-09-17 16:00 | 8 | 126 | 100 | 98 | -2 | 10352 | 10352 | 10144.96 | 11075.0096 | 0.98 | 0.91602 | FALSE | FALSE | FALSE | 15.75 | FALSE | 0 | Green | Continue normal monitoring.
143794 | HCSWB4Z4180 | B4 Z4 :De-shutter columns formwork | 25953 | 2012-09-10 08:00 | 2012-09-18 16:00 | 8 | 126 | 100 | 96 | -4 | 7136 | 7136 | 6850.56 | 8034.5047 | 0.96 | 0.85264 | TRUE | FALSE | FALSE | 15.75 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
143795 | HCSWB4Z4190 | B4 Z4 :Erect slab formwork and proping | 25963 | 2012-09-22 08:00 | 2012-09-27 16:00 | 5 | 102 | 100 | 87 | -13 | 3530 | 3530 | 3071.1 | 3203.746 | 0.87 | 0.9586 | FALSE | TRUE | TRUE | 12.75 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143796 | HCSWB4Z4200 | B4 Z4 :Fix steel rebar for slab | 25963 | 2012-10-01 08:00 | 2012-10-03 16:00 | 2 | 102 | 100 | 82 | -18 | 3076 | 3076 | 2522.32 | 3347.1305 | 0.82 | 0.75358 | TRUE | TRUE | TRUE | 12.75 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143797 | HCSWB4Z4210 | B4 Z4 :Fix MEP first Fix for slab | 25963 | 2012-10-04 08:00 | 2012-10-06 16:00 | 2 | 102 | 100 | 82 | -18 | 2782 | 2782 | 2281.24 | 2556.2247 | 0.82 | 0.89243 | TRUE | TRUE | TRUE | 12.75 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143798 | HCSWB4Z4220 | B4 Z4 :Fix side shutters and casting guides for slab | 25963 | 2012-10-06 08:00 | 2012-10-07 16:00 | 1 | 102 | 100 | 80 | -20 | 1984 | 1984 | 1587.2 | 2420.8944 | 0.8 | 0.65563 | TRUE | TRUE | TRUE | 12.75 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143799 | HCSWB4Z4230 | B4 Z4 :Cast concrete for slab | 25963 | 2012-10-08 08:00 | 2012-10-08 16:00 | 1 | 102 | 100 | 100 | 0 | 1363 | 1363 | 1363 | 1195.8058 | 1 | 1.1398 | FALSE | FALSE | FALSE | 12.75 | FALSE | 0 | Green | Continue normal monitoring.
143800 | HCSWB4Z4240 | B4 Z4 :Cure and De-shutter slab formwork | 25963 | 2012-10-08 16:00 | 2012-10-22 16:00 | 14 | 118 | 100 | 84 | -16 | 17388 | 17388 | 14605.92 | 17773.1425 | 0.84 | 0.8218 | TRUE | TRUE | TRUE | 14.75 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143801 | HCSWB4Z5010 | B4 Z5 :Formwork retaining walls shutters - 1st side | 25979 | 2012-09-10 08:00 | 2012-09-18 16:00 | 8 | 8 | 100 | 89 | -11 | 14112 | 14112 | 12559.68 | 15922.8376 | 0.89 | 0.78878 | TRUE | TRUE | TRUE | 1 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
143802 | HCSWB4Z5020 | B4 Z5 :Fix steel rebar for reatining walls | 25979 | 2012-09-10 08:00 | 2012-09-18 16:00 | 8 | 48 | 100 | 86 | -14 | 8504 | 8504 | 7313.44 | 8786.4084 | 0.86 | 0.83236 | TRUE | TRUE | TRUE | 6 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143803 | HCSWB4Z5030 | B4 Z5 :Fix MEP first fix in walls | 25979 | 2012-09-11 08:00 | 2012-09-19 16:00 | 8 | 48 | 100 | 100 | 0 | 12160 | 12160 | 12160 | 10783.9513 | 1 | 1.1276 | FALSE | FALSE | FALSE | 6 | FALSE | 0 | Green | Continue normal monitoring.
143804 | HCSWB4Z5040 | B4 Z5 :Close shutter for retaining walls | 25979 | 2012-09-12 08:00 | 2012-09-20 16:00 | 8 | 48 | 100 | 88 | -12 | 4760 | 4760 | 4188.8 | 5099.6336 | 0.88 | 0.82139 | TRUE | TRUE | TRUE | 6 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143805 | HCSWB4Z5050 | B4 Z5 :Cast concrete for retaining walls | 25979 | 2012-09-13 08:00 | 2012-09-22 16:00 | 9 | 48 | 100 | 100 | 0 | 8856 | 8856 | 8856 | 9800.5169 | 1 | 0.90363 | FALSE | FALSE | FALSE | 6 | FALSE | 0 | Green | Continue normal monitoring.
143806 | HCSWB4Z5060 | B4 Z5 :De-shutter retaining walls | 25979 | 2012-09-15 08:00 | 2012-09-23 16:00 | 8 | 48 | 100 | 86 | -14 | 15440 | 15440 | 13278.4 | 17470.6213 | 0.86 | 0.76004 | TRUE | TRUE | TRUE | 6 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143807 | HCSWB4Z5070 | B4 Z5 :Apply water proofing membrane behind Basement Walls | 25979 | 2012-09-20 08:00 | 2012-09-29 16:00 | 9 | 424 | 100 | 88 | -12 | 6570 | 6570 | 5781.6 | 6565.4268 | 0.88 | 0.88061 | TRUE | TRUE | TRUE | 53 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143808 | HCSWB4Z5080 | B4 Z5 :Apply Protection for Basement Walls | 25979 | 2012-09-23 08:00 | 2012-10-01 16:00 | 8 | 424 | 100 | 87 | -13 | 9984 | 9984 | 8686.08 | 10737.4325 | 0.87 | 0.80895 | TRUE | TRUE | TRUE | 53 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143809 | HCSWB4Z5150 | B4 Z5 :Fix Steel Rebar for columns | 25883 | 2012-09-10 08:00 | 2012-09-12 16:00 | 2 | 96 | 100 | 91 | -9 | 3388 | 3388 | 3083.08 | 3490.5703 | 0.91 | 0.88326 | TRUE | FALSE | FALSE | 12 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
143810 | HCSWB4Z5160 | B4 Z5 :Erect columns formwork | 25883 | 2012-09-11 08:00 | 2012-09-13 16:00 | 2 | 96 | 100 | 81 | -19 | 2080 | 2080 | 1684.8 | 2327.1506 | 0.81 | 0.72398 | TRUE | TRUE | TRUE | 12 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143811 | HCSWB4Z5170 | B4 Z5 :Cast concrete for columns | 25883 | 2012-09-12 08:00 | 2012-09-15 16:00 | 3 | 96 | 100 | 80 | -20 | 4677 | 4677 | 3741.6 | 5067.1684 | 0.8 | 0.7384 | TRUE | TRUE | TRUE | 12 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143812 | HCSWB4Z5180 | B4 Z5 :De-shutter columns formwork | 25883 | 2012-09-13 08:00 | 2012-09-16 16:00 | 3 | 96 | 100 | 95 | -5 | 3072 | 3072 | 2918.4 | 3257.2492 | 0.95 | 0.89597 | TRUE | FALSE | FALSE | 12 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
143813 | HCSWB4Z5190 | B4 Z5 :Erect slab formwork and proping | 26058 | 2012-09-26 08:00 | 2012-10-04 16:00 | 8 | 8 | 100 | 100 | 0 | 13464 | 13464 | 13464 | 12788.2384 | 1 | 1.0528 | FALSE | FALSE | FALSE | 1 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143814 | HCSWB4Z5200 | B4 Z5 :Fix steel rebar for slab | 26058 | 2012-10-06 08:00 | 2012-10-08 16:00 | 2 | 8 | 100 | 100 | 0 | 3532 | 3532 | 3532 | 3005.0518 | 1 | 1.1754 | FALSE | FALSE | FALSE | 1 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143815 | HCSWB4Z5210 | B4 Z5 :Fix MEP first Fix for slab | 26058 | 2012-10-09 08:00 | 2012-10-10 16:00 | 1 | 8 | 100 | 100 | 0 | 1609 | 1609 | 1609 | 1479.689 | 1 | 1.0874 | FALSE | FALSE | FALSE | 1 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143816 | HCSWB4Z5220 | B4 Z5 :Fix side shutters and casting guides for slab | 26058 | 2012-10-10 08:00 | 2012-10-11 16:00 | 1 | 8 | 100 | 100 | 0 | 1077 | 1077 | 1077 | 965.8821 | 1 | 1.115 | FALSE | FALSE | FALSE | 1 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143817 | HCSWB4Z5230 | B4 Z5 :Cast concrete for slab | 26058 | 2012-10-13 08:00 | 2012-10-13 16:00 | 1 | 8 | 100 | 84 | -16 | 1181 | 1181 | 992.04 | 1215.9976 | 0.84 | 0.81582 | TRUE | TRUE | TRUE | 1 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
143818 | HCSWB4Z5240 | B4 Z5 :Cure and De-shutter slab formwork | 26058 | 2012-10-13 16:00 | 2012-10-27 16:00 | 14 | 8 | 100 | 82 | -18 | 14784 | 14784 | 12122.88 | 16187.0498 | 0.82 | 0.74892 | TRUE | TRUE | TRUE | 1 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
143819 | HCSWB4Z6010 | B4 Z6 :Formwork retaining walls shutters - 1st side | 26069 | 2012-10-06 08:00 | 2012-10-14 16:00 | 8 | 56 | 100 | 91 | -9 | 12096 | 12096 | 11007.36 | 11312.5905 | 0.91 | 0.97302 | FALSE | FALSE | FALSE | 7 | FALSE | 0 | Green | Continue normal monitoring.
143820 | HCSWB4Z6020 | B4 Z6 :Fix steel rebar for reatining walls | 26069 | 2012-10-06 08:00 | 2012-10-14 16:00 | 8 | 56 | 100 | 87 | -13 | 9160 | 9160 | 7969.2 | 11226.7052 | 0.87 | 0.70984 | TRUE | TRUE | TRUE | 7 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143821 | HCSWB4Z6030 | B4 Z6 :Fix MEP first fix in walls | 26069 | 2012-10-07 08:00 | 2012-10-15 16:00 | 8 | 56 | 100 | 100 | 0 | 10360 | 10360 | 10360 | 8833.6907 | 1 | 1.1728 | FALSE | FALSE | FALSE | 7 | FALSE | 0 | Green | Continue normal monitoring.
143822 | HCSWB4Z6040 | B4 Z6 :Close shutter for retaining walls | 26069 | 2012-10-08 08:00 | 2012-10-16 16:00 | 8 | 56 | 100 | 100 | 0 | 12408 | 12408 | 12408 | 14379.8844 | 1 | 0.86287 | TRUE | FALSE | FALSE | 7 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
143823 | HCSWB4Z6050 | B4 Z6 :Cast concrete for retaining walls | 26069 | 2012-10-09 08:00 | 2012-10-17 16:00 | 8 | 56 | 100 | 82 | -18 | 14904 | 14904 | 12221.28 | 16395.6208 | 0.82 | 0.7454 | TRUE | TRUE | TRUE | 7 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143824 | HCSWB4Z6060 | B4 Z6 :De-shutter retaining walls | 26069 | 2012-10-10 08:00 | 2012-10-18 16:00 | 8 | 56 | 100 | 80 | -20 | 14832 | 14832 | 11865.6 | 14823.4259 | 0.8 | 0.80046 | TRUE | TRUE | TRUE | 7 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143825 | HCSWB4Z6070 | B4 Z6 :Apply water proofing membrane behind Basement Walls | 26069 | 2012-10-16 08:00 | 2012-10-24 16:00 | 8 | 248 | 100 | 82 | -18 | 14968 | 14968 | 12273.76 | 13025.0874 | 0.82 | 0.94232 | FALSE | TRUE | TRUE | 31 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143826 | HCSWB4Z6080 | B4 Z6 :Apply Protection for Basement Walls | 26069 | 2012-10-18 08:00 | 2012-10-31 16:00 | 13 | 248 | 100 | 84 | -16 | 25948 | 25948 | 21796.32 | 28568.6086 | 0.84 | 0.76295 | TRUE | TRUE | TRUE | 31 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143827 | HCSWB4Z6150 | B4 Z6 :Fix Steel Rebar for columns | 25909 | 2012-10-06 08:00 | 2012-10-08 16:00 | 2 | 56 | 100 | 94 | -6 | 3508 | 3508 | 3297.52 | 3522.8929 | 0.94 | 0.93603 | FALSE | FALSE | FALSE | 7 | FALSE | 0 | Green | Continue normal monitoring.
143828 | HCSWB4Z6160 | B4 Z6 :Erect columns formwork | 25909 | 2012-10-07 08:00 | 2012-10-09 16:00 | 2 | 56 | 100 | 93 | -7 | 1378 | 1378 | 1281.54 | 1687.3704 | 0.93 | 0.75949 | TRUE | FALSE | FALSE | 7 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
143829 | HCSWB4Z6170 | B4 Z6 :Cast concrete for columns | 25909 | 2012-10-08 08:00 | 2012-10-10 16:00 | 2 | 56 | 100 | 82 | -18 | 3496 | 3496 | 2866.72 | 3729.5189 | 0.82 | 0.76866 | TRUE | TRUE | TRUE | 7 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143830 | HCSWB4Z6180 | B4 Z6 :De-shutter columns formwork | 25909 | 2012-10-09 08:00 | 2012-10-11 16:00 | 2 | 112 | 100 | 80 | -20 | 3816 | 3816 | 3052.8 | 4677.8841 | 0.8 | 0.6526 | TRUE | TRUE | TRUE | 14 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143831 | HCSWB4Z6190 | B4 Z6 :Erect slab formwork and proping | 25962 | 2012-10-16 08:00 | 2012-11-05 16:00 | 20 | 16 | 100 | 84 | -16 | 38000 | 38000 | 31920 | 35651.3521 | 0.84 | 0.89534 | TRUE | TRUE | TRUE | 2 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
143832 | HCSWB4Z6200 | B4 Z6 :Fix steel rebar for slab | 25962 | 2012-11-06 08:00 | 2012-11-08 16:00 | 2 | 16 | 100 | 100 | 0 | 3612 | 3612 | 3612 | 4118.7288 | 1 | 0.87697 | TRUE | FALSE | FALSE | 2 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143833 | HCSWB4Z6210 | B4 Z6 :Fix MEP first Fix for slab | 25962 | 2012-11-10 08:00 | 2012-11-11 16:00 | 1 | 16 | 100 | 100 | 0 | 1132 | 1132 | 1132 | 1241.6904 | 1 | 0.91166 | FALSE | FALSE | FALSE | 2 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143834 | HCSWB4Z6220 | B4 Z6 :Fix side shutters and casting guides for slab | 25962 | 2012-11-11 08:00 | 2012-11-12 16:00 | 1 | 16 | 100 | 100 | 0 | 1127 | 1127 | 1127 | 1291.2752 | 1 | 0.87278 | TRUE | FALSE | FALSE | 2 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143835 | HCSWB4Z6230 | B4 Z6 :Cast concrete for slab | 25962 | 2012-11-13 08:00 | 2012-11-13 16:00 | 1 | 16 | 100 | 93 | -7 | 1472 | 1472 | 1368.96 | 1377.5964 | 0.93 | 0.99373 | FALSE | FALSE | FALSE | 2 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143836 | HCSWB4Z6240 | B4 Z6 :Cure and De-shutter slab formwork | 25962 | 2012-11-13 16:00 | 2012-11-27 16:00 | 14 | 32 | 100 | 86 | -14 | 24948 | 24948 | 21455.28 | 27841.9133 | 0.86 | 0.77061 | TRUE | TRUE | TRUE | 4 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
143837 | HCSWB3Z1010 | B3 Z1 :Formwork retaining walls shutters - 1st side | 25965 | 2012-09-17 08:00 | 2012-09-25 16:00 | 8 | 72 | 100 | 100 | 0 | 15056 | 15056 | 15056 | 15796.9985 | 1 | 0.95309 | FALSE | FALSE | FALSE | 9 | FALSE | 0 | Green | Continue normal monitoring.
143838 | HCSWB3Z1020 | B3 Z1 :Fix steel rebar for reatining walls | 25965 | 2012-09-17 08:00 | 2012-09-25 16:00 | 8 | 72 | 100 | 88 | -12 | 9672 | 9672 | 8511.36 | 11095.0413 | 0.88 | 0.76713 | TRUE | TRUE | TRUE | 9 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143839 | HCSWB3Z1030 | B3 Z1 :Fix MEP first fix in walls | 25965 | 2012-09-18 08:00 | 2012-09-26 16:00 | 8 | 72 | 100 | 94 | -6 | 15832 | 15832 | 14882.08 | 15528.3083 | 0.94 | 0.95838 | FALSE | FALSE | FALSE | 9 | FALSE | 0 | Green | Continue normal monitoring.
143840 | HCSWB3Z1040 | B3 Z1 :Close shutter for retaining walls | 25965 | 2012-09-19 08:00 | 2012-09-27 16:00 | 8 | 72 | 100 | 94 | -6 | 15472 | 15472 | 14543.68 | 18659.5849 | 0.94 | 0.77942 | TRUE | FALSE | FALSE | 9 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
143841 | HCSWB3Z1050 | B3 Z1 :Cast concrete for retaining walls | 25965 | 2012-09-20 08:00 | 2012-09-29 16:00 | 9 | 72 | 100 | 100 | 0 | 10332 | 10332 | 10332 | 9130.6005 | 1 | 1.1316 | FALSE | FALSE | FALSE | 9 | FALSE | 0 | Green | Continue normal monitoring.
143842 | HCSWB3Z1060 | B3 Z1 :De-shutter retaining walls | 25965 | 2012-09-22 08:00 | 2012-09-30 16:00 | 8 | 72 | 100 | 89 | -11 | 6536 | 6536 | 5817.04 | 7665.9158 | 0.89 | 0.75882 | TRUE | TRUE | TRUE | 9 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143843 | HCSWB3Z1070 | B3 Z1 :Apply water proofing membrane behind Basement Walls | 25965 | 2012-09-27 08:00 | 2012-10-06 16:00 | 9 | 576 | 100 | 100 | 0 | 15732 | 15732 | 15732 | 18792.3121 | 1 | 0.83715 | TRUE | FALSE | FALSE | 72 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
143844 | HCSWB3Z1080 | B3 Z1 :Apply Protection for Basement Walls | 25965 | 2012-09-30 08:00 | 2012-10-08 16:00 | 8 | 576 | 100 | 92 | -8 | 14056 | 14056 | 12931.52 | 16542.5194 | 0.92 | 0.78171 | TRUE | FALSE | FALSE | 72 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
143845 | HCSWB3Z1090 | B3 Z1 :Formwork core wall shutters - 1st side | 25966 | 2012-09-17 08:00 | 2012-09-23 16:00 | 6 | 32 | 100 | 98 | -2 | 7098 | 7098 | 6956.04 | 7489.0328 | 0.98 | 0.92883 | FALSE | FALSE | FALSE | 4 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143846 | HCSWB3Z1100 | B3 Z1 :Fix steel rebar for core wall | 25966 | 2012-09-24 08:00 | 2012-09-27 16:00 | 3 | 32 | 100 | 100 | 0 | 3489 | 3489 | 3489 | 3577.4601 | 1 | 0.97527 | FALSE | FALSE | FALSE | 4 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143847 | HCSWB3Z1110 | B3 Z1 :Fix MEP first fix in core wall | 25966 | 2012-09-29 08:00 | 2012-09-29 16:00 | 1 | 32 | 100 | 86 | -14 | 1897 | 1897 | 1631.42 | 2368.4138 | 0.86 | 0.68882 | TRUE | TRUE | TRUE | 4 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
143848 | HCSWB3Z1120 | B3 Z1 :Close shutter for core wall | 25966 | 2012-09-30 08:00 | 2012-10-02 16:00 | 2 | 32 | 100 | 96 | -4 | 3990 | 3990 | 3830.4 | 3757.2584 | 0.96 | 1.0195 | FALSE | FALSE | FALSE | 4 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143849 | HCSWB3Z1130 | B3 Z1 :Cast concrete for core wall | 25966 | 2012-10-03 08:00 | 2012-10-03 16:00 | 1 | 32 | 100 | 99 | -1 | 1756 | 1756 | 1738.44 | 1876.7257 | 0.99 | 0.92632 | FALSE | FALSE | FALSE | 4 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143850 | HCSWB3Z1140 | B3 Z1 :De-shutter core wall formwork | 25966 | 2012-10-04 08:00 | 2012-10-06 16:00 | 2 | 32 | 100 | 100 | 0 | 3272 | 3272 | 3272 | 3658.9801 | 1 | 0.89424 | TRUE | FALSE | FALSE | 4 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143851 | HCSWB3Z1150 | B3 Z1 :Fix Steel Rebar for columns | 26067 | 2012-09-17 08:00 | 2012-09-19 16:00 | 2 | 120 | 100 | 83 | -17 | 1882 | 1882 | 1562.06 | 2127.3132 | 0.83 | 0.73429 | TRUE | TRUE | TRUE | 15 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143852 | HCSWB3Z1160 | B3 Z1 :Erect columns formwork | 26067 | 2012-09-18 08:00 | 2012-09-20 16:00 | 2 | 120 | 100 | 100 | 0 | 2126 | 2126 | 2126 | 1980.6026 | 1 | 1.0734 | FALSE | FALSE | FALSE | 15 | FALSE | 0 | Green | Continue normal monitoring.
143853 | HCSWB3Z1170 | B3 Z1 :Cast concrete for columns | 26067 | 2012-09-19 08:00 | 2012-09-22 16:00 | 3 | 120 | 100 | 84 | -16 | 5373 | 5373 | 4513.32 | 5972.6141 | 0.84 | 0.75567 | TRUE | TRUE | TRUE | 15 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143854 | HCSWB3Z1180 | B3 Z1 :De-shutter columns formwork | 26067 | 2012-09-20 08:00 | 2012-09-23 16:00 | 3 | 120 | 100 | 100 | 0 | 5727 | 5727 | 5727 | 6742.671 | 1 | 0.84937 | TRUE | FALSE | FALSE | 15 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
143855 | HCSWB3Z1190 | B3 Z1 :Erect slab formwork and proping | 26068 | 2012-10-06 08:00 | 2012-10-14 16:00 | 8 | 24 | 100 | 86 | -14 | 15280 | 15280 | 13140.8 | 13293.7135 | 0.86 | 0.9885 | FALSE | TRUE | TRUE | 3 | TRUE | 4 | Orange | Develop recovery plan and review schedule and cost exposure.
143856 | HCSWB3Z1200 | B3 Z1 :Fix steel rebar for slab | 26068 | 2012-10-15 08:00 | 2012-10-17 16:00 | 2 | 24 | 100 | 92 | -8 | 3272 | 3272 | 3010.24 | 3974.1991 | 0.92 | 0.75745 | TRUE | FALSE | FALSE | 3 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143857 | HCSWB3Z1210 | B3 Z1 :Fix MEP first Fix for slab | 26068 | 2012-10-18 08:00 | 2012-10-20 16:00 | 2 | 24 | 100 | 94 | -6 | 2902 | 2902 | 2727.88 | 2500.9483 | 0.94 | 1.0907 | FALSE | FALSE | FALSE | 3 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143858 | HCSWB3Z1220 | B3 Z1 :Fix side shutters and casting guides for slab | 26068 | 2012-10-20 08:00 | 2012-10-21 16:00 | 1 | 24 | 100 | 90 | -10 | 1604 | 1604 | 1443.6 | 1591.791 | 0.9 | 0.9069 | FALSE | FALSE | FALSE | 3 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143859 | HCSWB3Z1230 | B3 Z1 :Cast concrete for slab | 26068 | 2012-10-22 08:00 | 2012-10-22 16:00 | 1 | 24 | 100 | 100 | 0 | 1198 | 1198 | 1198 | 1025.8777 | 1 | 1.1678 | FALSE | FALSE | FALSE | 3 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143860 | HCSWB3Z1240 | B3 Z1 :Cure and De-shutter slab formwork | 26068 | 2012-10-22 16:00 | 2012-11-05 16:00 | 14 | 64 | 100 | 83 | -17 | 8568 | 8568 | 7111.44 | 7547.1919 | 0.83 | 0.94226 | FALSE | TRUE | TRUE | 8 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143861 | HCSWB3Z2010 | B3 Z2 :Formwork retaining walls shutters - 1st side | 26070 | 2012-09-12 08:00 | 2012-09-20 16:00 | 8 | 230 | 100 | 92 | -8 | 4008 | 4008 | 3687.36 | 4867.585 | 0.92 | 0.75753 | TRUE | FALSE | FALSE | 28.75 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
143862 | HCSWB3Z2020 | B3 Z2 :Fix steel rebar for reatining walls | 26070 | 2012-09-12 08:00 | 2012-09-20 16:00 | 8 | 230 | 100 | 86 | -14 | 9128 | 9128 | 7850.08 | 9054.4679 | 0.86 | 0.86698 | TRUE | TRUE | TRUE | 28.75 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143863 | HCSWB3Z2030 | B3 Z2 :Fix MEP first fix in walls | 26070 | 2012-09-13 08:00 | 2012-09-22 16:00 | 9 | 230 | 100 | 100 | 0 | 6471 | 6471 | 6471 | 6599.8286 | 1 | 0.98048 | FALSE | FALSE | FALSE | 28.75 | FALSE | 0 | Green | Continue normal monitoring.
143864 | HCSWB3Z2040 | B3 Z2 :Close shutter for retaining walls | 26070 | 2012-09-15 08:00 | 2012-09-23 16:00 | 8 | 230 | 100 | 98 | -2 | 10832 | 10832 | 10615.36 | 10140.2441 | 0.98 | 1.0469 | FALSE | FALSE | FALSE | 28.75 | FALSE | 0 | Green | Continue normal monitoring.
143865 | HCSWB3Z2050 | B3 Z2 :Cast concrete for retaining walls | 26070 | 2012-09-16 08:00 | 2012-09-24 16:00 | 8 | 230 | 100 | 100 | 0 | 13984 | 13984 | 13984 | 15226.3149 | 1 | 0.91841 | FALSE | FALSE | FALSE | 28.75 | FALSE | 0 | Green | Continue normal monitoring.
143866 | HCSWB3Z2060 | B3 Z2 :De-shutter retaining walls | 26070 | 2012-09-17 08:00 | 2012-09-25 16:00 | 8 | 230 | 100 | 100 | 0 | 7072 | 7072 | 7072 | 7693.7793 | 1 | 0.91918 | FALSE | FALSE | FALSE | 28.75 | FALSE | 0 | Green | Continue normal monitoring.
143867 | HCSWB3Z2070 | B3 Z2 :Apply water proofing membrane behind Basement Walls | 26070 | 2012-09-23 08:00 | 2012-10-01 16:00 | 8 | 608 | 100 | 81 | -19 | 15408 | 15408 | 12480.48 | 15390.7455 | 0.81 | 0.81091 | TRUE | TRUE | TRUE | 76 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143868 | HCSWB3Z2080 | B3 Z2 :Apply Protection for Basement Walls | 26070 | 2012-09-25 08:00 | 2012-10-03 16:00 | 8 | 608 | 100 | 89 | -11 | 13224 | 13224 | 11769.36 | 13002.0213 | 0.89 | 0.90519 | FALSE | TRUE | TRUE | 76 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143869 | HCSWB3Z2150 | B3 Z2 :Fix Steel Rebar for columns | 25971 | 2012-09-12 08:00 | 2012-09-15 16:00 | 3 | 278 | 100 | 92 | -8 | 4728 | 4728 | 4349.76 | 5692.4445 | 0.92 | 0.76413 | TRUE | FALSE | FALSE | 34.75 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
143870 | HCSWB3Z2160 | B3 Z2 :Erect columns formwork | 25971 | 2012-09-13 08:00 | 2012-09-16 16:00 | 3 | 278 | 100 | 100 | 0 | 3687 | 3687 | 3687 | 3699.2176 | 1 | 0.9967 | FALSE | FALSE | FALSE | 34.75 | FALSE | 0 | Green | Continue normal monitoring.
143871 | HCSWB3Z2170 | B3 Z2 :Cast concrete for columns | 25971 | 2012-09-15 08:00 | 2012-09-17 16:00 | 2 | 278 | 100 | 100 | 0 | 3878 | 3878 | 3878 | 4061.8187 | 1 | 0.95474 | FALSE | FALSE | FALSE | 34.75 | FALSE | 0 | Green | Continue normal monitoring.
143872 | HCSWB3Z2180 | B3 Z2 :De-shutter columns formwork | 25971 | 2012-09-16 08:00 | 2012-09-18 16:00 | 2 | 278 | 100 | 100 | 0 | 1492 | 1492 | 1492 | 1437.2763 | 1 | 1.0381 | FALSE | FALSE | FALSE | 34.75 | FALSE | 0 | Green | Continue normal monitoring.
143873 | HCSWB3Z2190 | B3 Z2 :Erect slab formwork and proping | 25972 | 2012-10-18 08:00 | 2012-10-24 16:00 | 6 | 78 | 100 | 85 | -15 | 8010 | 8010 | 6808.5 | 9329.3095 | 0.85 | 0.7298 | TRUE | TRUE | TRUE | 9.75 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143874 | HCSWB3Z2200 | B3 Z2 :Fix steel rebar for slab | 25972 | 2012-10-30 08:00 | 2012-11-01 16:00 | 2 | 78 | 100 | 100 | 0 | 3924 | 3924 | 3924 | 3959.2346 | 1 | 0.9911 | FALSE | FALSE | FALSE | 9.75 | FALSE | 0 | Green | Continue normal monitoring.
143875 | HCSWB3Z2210 | B3 Z2 :Fix MEP first Fix for slab | 25972 | 2012-11-03 08:00 | 2012-11-04 16:00 | 1 | 78 | 100 | 100 | 0 | 702 | 702 | 702 | 740.922 | 1 | 0.94747 | FALSE | FALSE | FALSE | 9.75 | FALSE | 0 | Green | Continue normal monitoring.
143876 | HCSWB3Z2220 | B3 Z2 :Fix side shutters and casting guides for slab | 25972 | 2012-11-04 08:00 | 2012-11-05 16:00 | 1 | 78 | 100 | 91 | -9 | 1707 | 1707 | 1553.37 | 1623.9423 | 0.91 | 0.95654 | FALSE | FALSE | FALSE | 9.75 | FALSE | 0 | Green | Continue normal monitoring.
143877 | HCSWB3Z2230 | B3 Z2 :Cast concrete for slab | 25972 | 2012-11-06 08:00 | 2012-11-06 16:00 | 1 | 78 | 100 | 91 | -9 | 622 | 622 | 566.02 | 774.4297 | 0.91 | 0.73089 | TRUE | FALSE | FALSE | 9.75 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
143878 | HCSWB3Z2240 | B3 Z2 :Cure and De-shutter slab formwork | 25972 | 2012-11-06 16:00 | 2012-11-20 16:00 | 14 | 102 | 100 | 99 | -1 | 12600 | 12600 | 12474 | 12179.1385 | 0.99 | 1.0242 | FALSE | FALSE | FALSE | 12.75 | FALSE | 0 | Green | Continue normal monitoring.
143879 | HCSWB3Z3010 | B3 Z3 :Formwork retaining walls shutters - 1st side | 26055 | 2012-09-27 08:00 | 2012-10-02 16:00 | 5 | 96 | 100 | 100 | 0 | 6330 | 6330 | 6330 | 7332.0201 | 1 | 0.86334 | TRUE | FALSE | FALSE | 12 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
143880 | HCSWB3Z3020 | B3 Z3 :Fix steel rebar for reatining walls | 26055 | 2012-09-27 08:00 | 2012-10-02 16:00 | 5 | 96 | 100 | 100 | 0 | 3965 | 3965 | 3965 | 4048.2581 | 1 | 0.97943 | FALSE | FALSE | FALSE | 12 | FALSE | 0 | Green | Continue normal monitoring.
143881 | HCSWB3Z3030 | B3 Z3 :Fix MEP first fix in walls | 26055 | 2012-09-29 08:00 | 2012-10-03 16:00 | 4 | 96 | 100 | 90 | -10 | 3116 | 3116 | 2804.4 | 2905.6294 | 0.9 | 0.96516 | FALSE | FALSE | FALSE | 12 | FALSE | 0 | Green | Continue normal monitoring.
143882 | HCSWB3Z3040 | B3 Z3 :Close shutter for retaining walls | 26055 | 2012-09-30 08:00 | 2012-10-04 16:00 | 4 | 96 | 100 | 100 | 0 | 5532 | 5532 | 5532 | 6471.8177 | 1 | 0.85478 | TRUE | FALSE | FALSE | 12 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
143883 | HCSWB3Z3050 | B3 Z3 :Cast concrete for retaining walls | 26055 | 2012-10-01 08:00 | 2012-10-06 16:00 | 5 | 96 | 100 | 100 | 0 | 3485 | 3485 | 3485 | 3427.2979 | 1 | 1.0168 | FALSE | FALSE | FALSE | 12 | FALSE | 0 | Green | Continue normal monitoring.
143884 | HCSWB3Z3060 | B3 Z3 :De-shutter retaining walls | 26055 | 2012-10-02 08:00 | 2012-10-07 16:00 | 5 | 96 | 100 | 100 | 0 | 7405 | 7405 | 7405 | 8856.9527 | 1 | 0.83607 | TRUE | FALSE | FALSE | 12 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
143885 | HCSWB3Z3070 | B3 Z3 :Apply water proofing membrane behind Basement Walls | 26055 | 2012-10-06 08:00 | 2012-10-10 16:00 | 4 | 960 | 100 | 100 | 0 | 5004 | 5004 | 5004 | 6085.3788 | 1 | 0.8223 | TRUE | FALSE | FALSE | 120 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
143886 | HCSWB3Z3080 | B3 Z3 :Apply Protection for Basement Walls | 26055 | 2012-10-08 08:00 | 2012-10-13 16:00 | 5 | 960 | 100 | 86 | -14 | 3215 | 3215 | 2764.9 | 3838.4835 | 0.86 | 0.72031 | TRUE | TRUE | TRUE | 120 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143887 | HCSWB3Z3090 | B3 Z3 :Formwork core wall shutters - 1st side | 26056 | 2012-09-27 08:00 | 2012-10-03 16:00 | 6 | 32 | 100 | 100 | 0 | 6648 | 6648 | 6648 | 5743.893 | 1 | 1.1574 | FALSE | FALSE | FALSE | 4 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143888 | HCSWB3Z3100 | B3 Z3 :Fix steel rebar for core wall | 26056 | 2012-10-04 08:00 | 2012-10-08 16:00 | 4 | 32 | 100 | 80 | -20 | 6896 | 6896 | 5516.8 | 8033.4906 | 0.8 | 0.68673 | TRUE | TRUE | TRUE | 4 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
143889 | HCSWB3Z3110 | B3 Z3 :Fix MEP first fix in core wall | 26056 | 2012-10-09 08:00 | 2012-10-09 16:00 | 1 | 32 | 100 | 80 | -20 | 1647 | 1647 | 1317.6 | 1670.9404 | 0.8 | 0.78854 | TRUE | TRUE | TRUE | 4 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
143890 | HCSWB3Z3120 | B3 Z3 :Close shutter for core wall | 26056 | 2012-10-10 08:00 | 2012-10-13 16:00 | 3 | 32 | 100 | 100 | 0 | 2058 | 2058 | 2058 | 2468.5487 | 1 | 0.83369 | TRUE | FALSE | FALSE | 4 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143891 | HCSWB3Z3130 | B3 Z3 :Cast concrete for core wall | 26056 | 2012-10-14 08:00 | 2012-10-14 16:00 | 1 | 32 | 100 | 100 | 0 | 1849 | 1849 | 1849 | 2043.481 | 1 | 0.90483 | FALSE | FALSE | FALSE | 4 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143892 | HCSWB3Z3140 | B3 Z3 :De-shutter core wall formwork | 26056 | 2012-10-15 08:00 | 2012-10-16 16:00 | 1 | 32 | 100 | 100 | 0 | 963 | 963 | 963 | 1139.6693 | 1 | 0.84498 | TRUE | FALSE | FALSE | 4 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143893 | HCSWB3Z3150 | B3 Z3 :Fix Steel Rebar for columns | 26057 | 2012-09-27 08:00 | 2012-09-30 16:00 | 3 | 120 | 100 | 100 | 0 | 5616 | 5616 | 5616 | 5895.5235 | 1 | 0.95259 | FALSE | FALSE | FALSE | 15 | FALSE | 0 | Green | Continue normal monitoring.
143894 | HCSWB3Z3160 | B3 Z3 :Erect columns formwork | 26057 | 2012-09-29 08:00 | 2012-10-01 16:00 | 2 | 120 | 100 | 99 | -1 | 2318 | 2318 | 2294.82 | 2466.3756 | 0.99 | 0.93044 | FALSE | FALSE | FALSE | 15 | FALSE | 0 | Green | Continue normal monitoring.
143895 | HCSWB3Z3170 | B3 Z3 :Cast concrete for columns | 26057 | 2012-09-30 08:00 | 2012-10-02 16:00 | 2 | 120 | 100 | 92 | -8 | 2526 | 2526 | 2323.92 | 2292.9893 | 0.92 | 1.0135 | FALSE | FALSE | FALSE | 15 | FALSE | 0 | Green | Continue normal monitoring.
143896 | HCSWB3Z3180 | B3 Z3 :De-shutter columns formwork | 26057 | 2012-10-01 08:00 | 2012-10-03 16:00 | 2 | 120 | 100 | 88 | -12 | 2908 | 2908 | 2559.04 | 3383.7341 | 0.88 | 0.75628 | TRUE | TRUE | TRUE | 15 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143897 | HCSWB3Z3190 | B3 Z3 :Erect slab formwork and proping | 25975 | 2012-10-18 08:00 | 2012-10-31 16:00 | 13 | 8 | 100 | 82 | -18 | 11726 | 11726 | 9615.32 | 11934.205 | 0.82 | 0.80569 | TRUE | TRUE | TRUE | 1 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
143898 | HCSWB3Z3200 | B3 Z3 :Fix steel rebar for slab | 25975 | 2012-11-01 08:00 | 2012-11-04 16:00 | 3 | 8 | 100 | 86 | -14 | 5607 | 5607 | 4822.02 | 5887.5297 | 0.86 | 0.81902 | TRUE | TRUE | TRUE | 1 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
143899 | HCSWB3Z3210 | B3 Z3 :Fix MEP first Fix for slab | 25975 | 2012-11-05 08:00 | 2012-11-06 16:00 | 1 | 8 | 100 | 85 | -15 | 646 | 646 | 549.1 | 751.9692 | 0.85 | 0.73022 | TRUE | TRUE | TRUE | 1 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
143900 | HCSWB3Z3220 | B3 Z3 :Fix side shutters and casting guides for slab | 25975 | 2012-11-06 08:00 | 2012-11-07 16:00 | 1 | 8 | 100 | 87 | -13 | 1671 | 1671 | 1453.77 | 1820.6183 | 0.87 | 0.7985 | TRUE | TRUE | TRUE | 1 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
143901 | HCSWB3Z3230 | B3 Z3 :Cast concrete for slab | 25975 | 2012-11-08 08:00 | 2012-11-08 16:00 | 1 | 8 | 100 | 100 | 0 | 1363 | 1363 | 1363 | 1268.189 | 1 | 1.0748 | FALSE | FALSE | FALSE | 1 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143902 | HCSWB3Z3240 | B3 Z3 :Cure and De-shutter slab formwork | 25975 | 2012-11-08 16:00 | 2012-11-22 16:00 | 14 | 16 | 100 | 88 | -12 | 13832 | 13832 | 12172.16 | 15022.8393 | 0.88 | 0.81024 | TRUE | TRUE | TRUE | 2 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
143903 | HCSWB3Z4010 | B3 Z4 :Formwork retaining walls shutters - 1st side | 25900 | 2012-10-09 08:00 | 2012-10-14 16:00 | 5 | 240 | 100 | 100 | 0 | 7140 | 7140 | 7140 | 7233.1994 | 1 | 0.98712 | FALSE | FALSE | FALSE | 30 | FALSE | 0 | Green | Continue normal monitoring.
143904 | HCSWB3Z4020 | B3 Z4 :Fix steel rebar for reatining walls | 25900 | 2012-10-09 08:00 | 2012-10-14 16:00 | 5 | 240 | 100 | 84 | -16 | 5250 | 5250 | 4410 | 5448.5036 | 0.84 | 0.8094 | TRUE | TRUE | TRUE | 30 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143905 | HCSWB3Z4030 | B3 Z4 :Fix MEP first fix in walls | 25900 | 2012-10-10 08:00 | 2012-10-15 16:00 | 5 | 240 | 100 | 80 | -20 | 4185 | 4185 | 3348 | 3604.6431 | 0.8 | 0.9288 | FALSE | TRUE | TRUE | 30 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143906 | HCSWB3Z4040 | B3 Z4 :Close shutter for retaining walls | 25900 | 2012-10-11 08:00 | 2012-10-16 16:00 | 5 | 240 | 100 | 98 | -2 | 6855 | 6855 | 6717.9 | 6402.6505 | 0.98 | 1.0492 | FALSE | FALSE | FALSE | 30 | FALSE | 0 | Green | Continue normal monitoring.
143907 | HCSWB3Z4050 | B3 Z4 :Cast concrete for retaining walls | 25900 | 2012-10-13 08:00 | 2012-10-17 16:00 | 4 | 240 | 100 | 89 | -11 | 4560 | 4560 | 4058.4 | 4388.6135 | 0.89 | 0.92476 | FALSE | TRUE | TRUE | 30 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143908 | HCSWB3Z4060 | B3 Z4 :De-shutter retaining walls | 25900 | 2012-10-14 08:00 | 2012-10-18 16:00 | 4 | 240 | 100 | 91 | -9 | 3888 | 3888 | 3538.08 | 4413.5954 | 0.91 | 0.80163 | TRUE | FALSE | FALSE | 30 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
143909 | HCSWB3Z4070 | B3 Z4 :Apply water proofing membrane behind Basement Walls | 25900 | 2012-10-17 08:00 | 2012-10-22 16:00 | 5 | 864 | 100 | 100 | 0 | 3250 | 3250 | 3250 | 2777.4402 | 1 | 1.1701 | FALSE | FALSE | FALSE | 108 | FALSE | 0 | Green | Continue normal monitoring.
143910 | HCSWB3Z4080 | B3 Z4 :Apply Protection for Basement Walls | 25900 | 2012-10-20 08:00 | 2012-10-24 16:00 | 4 | 864 | 100 | 94 | -6 | 7752 | 7752 | 7286.88 | 7856.7365 | 0.94 | 0.92747 | FALSE | FALSE | FALSE | 108 | FALSE | 0 | Green | Continue normal monitoring.
143911 | HCSWB3Z4150 | B3 Z4 :Fix Steel Rebar for columns | 25887 | 2012-10-09 08:00 | 2012-10-11 16:00 | 2 | 264 | 100 | 100 | 0 | 3642 | 3642 | 3642 | 4441.8223 | 1 | 0.81993 | TRUE | FALSE | FALSE | 33 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
143912 | HCSWB3Z4160 | B3 Z4 :Erect columns formwork | 25887 | 2012-10-10 08:00 | 2012-10-13 16:00 | 3 | 264 | 100 | 100 | 0 | 2286 | 2286 | 2286 | 2045.4036 | 1 | 1.1176 | FALSE | FALSE | FALSE | 33 | FALSE | 0 | Green | Continue normal monitoring.
143913 | HCSWB3Z4170 | B3 Z4 :Cast concrete for columns | 25887 | 2012-10-11 08:00 | 2012-10-14 16:00 | 3 | 264 | 100 | 100 | 0 | 1929 | 1929 | 1929 | 2038.1231 | 1 | 0.94646 | FALSE | FALSE | FALSE | 33 | FALSE | 0 | Green | Continue normal monitoring.
143914 | HCSWB3Z4180 | B3 Z4 :De-shutter columns formwork | 25887 | 2012-10-13 08:00 | 2012-10-15 16:00 | 2 | 264 | 100 | 88 | -12 | 1690 | 1690 | 1487.2 | 1968.1891 | 0.88 | 0.75562 | TRUE | TRUE | TRUE | 33 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143915 | HCSWB3Z4190 | B3 Z4 :Erect slab formwork and proping | 25892 | 2012-11-25 08:00 | 2012-12-01 16:00 | 6 | 32 | 100 | 99 | -1 | 6738 | 6738 | 6670.62 | 8267.6104 | 0.99 | 0.80684 | TRUE | FALSE | FALSE | 4 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143916 | HCSWB3Z4200 | B3 Z4 :Fix steel rebar for slab | 25892 | 2012-12-04 08:00 | 2012-12-06 16:00 | 2 | 32 | 100 | 96 | -4 | 3032 | 3032 | 2910.72 | 3482.8907 | 0.96 | 0.83572 | TRUE | FALSE | FALSE | 4 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143917 | HCSWB3Z4210 | B3 Z4 :Fix MEP first Fix for slab | 25892 | 2012-12-08 08:00 | 2012-12-09 16:00 | 1 | 32 | 100 | 100 | 0 | 1380 | 1380 | 1380 | 1570.7522 | 1 | 0.87856 | TRUE | FALSE | FALSE | 4 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143918 | HCSWB3Z4220 | B3 Z4 :Fix side shutters and casting guides for slab | 25892 | 2012-12-09 08:00 | 2012-12-10 16:00 | 1 | 32 | 100 | 96 | -4 | 501 | 501 | 480.96 | 591.4782 | 0.96 | 0.81315 | TRUE | FALSE | FALSE | 4 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143919 | HCSWB3Z4230 | B3 Z4 :Cast concrete for slab | 25892 | 2012-12-11 08:00 | 2012-12-11 16:00 | 1 | 32 | 100 | 100 | 0 | 1396 | 1396 | 1396 | 1435.7588 | 1 | 0.97231 | FALSE | FALSE | FALSE | 4 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143920 | HCSWB3Z4240 | B3 Z4 :Cure and De-shutter slab formwork | 25892 | 2012-12-11 16:00 | 2012-12-25 16:00 | 14 | 40 | 100 | 99 | -1 | 25578 | 25578 | 25322.22 | 29986.0566 | 0.99 | 0.84447 | TRUE | FALSE | FALSE | 5 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143921 | HCSWB3Z5010 | B3 Z5 :Formwork retaining walls shutters - 1st side | 25890 | 2012-10-14 08:00 | 2012-10-22 16:00 | 8 | 64 | 100 | 91 | -9 | 6024 | 6024 | 5481.84 | 5139.591 | 0.91 | 1.0666 | FALSE | FALSE | FALSE | 8 | FALSE | 0 | Green | Continue normal monitoring.
143922 | HCSWB3Z5020 | B3 Z5 :Fix steel rebar for reatining walls | 25890 | 2012-10-14 08:00 | 2012-10-22 16:00 | 8 | 64 | 100 | 100 | 0 | 7616 | 7616 | 7616 | 9290.1828 | 1 | 0.81979 | TRUE | FALSE | FALSE | 8 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
143923 | HCSWB3Z5030 | B3 Z5 :Fix MEP first fix in walls | 25890 | 2012-10-15 08:00 | 2012-10-23 16:00 | 8 | 64 | 100 | 86 | -14 | 12480 | 12480 | 10732.8 | 12820.9861 | 0.86 | 0.83713 | TRUE | TRUE | TRUE | 8 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143924 | HCSWB3Z5040 | B3 Z5 :Close shutter for retaining walls | 25890 | 2012-10-16 08:00 | 2012-10-24 16:00 | 8 | 64 | 100 | 81 | -19 | 13464 | 13464 | 10905.84 | 14424.6843 | 0.81 | 0.75605 | TRUE | TRUE | TRUE | 8 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143925 | HCSWB3Z5050 | B3 Z5 :Cast concrete for retaining walls | 25890 | 2012-10-17 08:00 | 2012-10-30 16:00 | 13 | 64 | 100 | 82 | -18 | 19682 | 19682 | 16139.24 | 18736.337 | 0.82 | 0.86139 | TRUE | TRUE | TRUE | 8 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143926 | HCSWB3Z5060 | B3 Z5 :De-shutter retaining walls | 25890 | 2012-10-18 08:00 | 2012-10-31 16:00 | 13 | 64 | 100 | 96 | -4 | 6604 | 6604 | 6339.84 | 7574.8694 | 0.96 | 0.83696 | TRUE | FALSE | FALSE | 8 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
143927 | HCSWB3Z5070 | B3 Z5 :Apply water proofing membrane behind Basement Walls | 25890 | 2012-10-24 08:00 | 2012-11-06 16:00 | 13 | 704 | 100 | 84 | -16 | 22828 | 22828 | 19175.52 | 20103.5769 | 0.84 | 0.95384 | FALSE | TRUE | TRUE | 88 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143928 | HCSWB3Z5080 | B3 Z5 :Apply Protection for Basement Walls | 25890 | 2012-10-31 08:00 | 2012-11-08 16:00 | 8 | 704 | 100 | 96 | -4 | 12976 | 12976 | 12456.96 | 15558.9289 | 0.96 | 0.80063 | TRUE | FALSE | FALSE | 88 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
143929 | HCSWB3Z5090 | B3 Z5 :Formwork core wall shutters - 1st side | 25988 | 2012-10-14 08:00 | 2012-10-20 16:00 | 6 | 24 | 100 | 100 | 0 | 7890 | 7890 | 7890 | 9320.0367 | 1 | 0.84656 | TRUE | FALSE | FALSE | 3 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143930 | HCSWB3Z5100 | B3 Z5 :Fix steel rebar for core wall | 25988 | 2012-10-21 08:00 | 2012-10-24 16:00 | 3 | 24 | 100 | 96 | -4 | 2121 | 2121 | 2036.16 | 1986.1554 | 0.96 | 1.0252 | FALSE | FALSE | FALSE | 3 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143931 | HCSWB3Z5110 | B3 Z5 :Fix MEP first fix in core wall | 25988 | 2012-10-30 08:00 | 2012-10-30 16:00 | 1 | 24 | 100 | 100 | 0 | 1654 | 1654 | 1654 | 1941.349 | 1 | 0.85198 | TRUE | FALSE | FALSE | 3 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143932 | HCSWB3Z5120 | B3 Z5 :Close shutter for core wall | 25988 | 2012-10-31 08:00 | 2012-11-03 16:00 | 3 | 24 | 100 | 96 | -4 | 2709 | 2709 | 2600.64 | 3154.7472 | 0.96 | 0.82436 | TRUE | FALSE | FALSE | 3 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143933 | HCSWB3Z5130 | B3 Z5 :Cast concrete for core wall | 25988 | 2012-11-04 08:00 | 2012-11-04 16:00 | 1 | 24 | 100 | 81 | -19 | 651 | 651 | 527.31 | 717.9792 | 0.81 | 0.73444 | TRUE | TRUE | TRUE | 3 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
143934 | HCSWB3Z5140 | B3 Z5 :De-shutter core wall formwork | 25988 | 2012-11-05 08:00 | 2012-11-06 16:00 | 1 | 24 | 100 | 81 | -19 | 553 | 553 | 447.93 | 552.6727 | 0.81 | 0.81048 | TRUE | TRUE | TRUE | 3 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
143935 | HCSWB3Z5150 | B3 Z5 :Fix Steel Rebar for columns | 26001 | 2012-10-14 08:00 | 2012-10-16 16:00 | 2 | 112 | 100 | 100 | 0 | 3286 | 3286 | 3286 | 3149.958 | 1 | 1.0432 | FALSE | FALSE | FALSE | 14 | FALSE | 0 | Green | Continue normal monitoring.
143936 | HCSWB3Z5160 | B3 Z5 :Erect columns formwork | 26001 | 2012-10-15 08:00 | 2012-10-17 16:00 | 2 | 112 | 100 | 100 | 0 | 2254 | 2254 | 2254 | 2124.8761 | 1 | 1.0608 | FALSE | FALSE | FALSE | 14 | FALSE | 0 | Green | Continue normal monitoring.
143937 | HCSWB3Z5170 | B3 Z5 :Cast concrete for columns | 26001 | 2012-10-16 08:00 | 2012-10-18 16:00 | 2 | 112 | 100 | 100 | 0 | 2172 | 2172 | 2172 | 2123.0075 | 1 | 1.0231 | FALSE | FALSE | FALSE | 14 | FALSE | 0 | Green | Continue normal monitoring.
143938 | HCSWB3Z5180 | B3 Z5 :De-shutter columns formwork | 26001 | 2012-10-17 08:00 | 2012-10-20 16:00 | 3 | 112 | 100 | 84 | -16 | 5829 | 5829 | 4896.36 | 7061.3869 | 0.84 | 0.6934 | TRUE | TRUE | TRUE | 14 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143939 | HCSWB3Z5190 | B3 Z5 :Erect slab formwork and proping | 25868 | 2012-10-23 08:00 | 2012-11-12 16:00 | 20 | 24 | 100 | 80 | -20 | 38900 | 38900 | 31120 | 34273.0905 | 0.8 | 0.908 | FALSE | TRUE | TRUE | 3 | TRUE | 4 | Orange | Develop recovery plan and review schedule and cost exposure.
143940 | HCSWB3Z5200 | B3 Z5 :Fix steel rebar for slab | 25868 | 2012-11-17 08:00 | 2012-11-19 16:00 | 2 | 24 | 100 | 80 | -20 | 1206 | 1206 | 964.8 | 1424.9475 | 0.8 | 0.67708 | TRUE | TRUE | TRUE | 3 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
143941 | HCSWB3Z5210 | B3 Z5 :Fix MEP first Fix for slab | 25868 | 2012-11-20 08:00 | 2012-11-21 16:00 | 1 | 24 | 100 | 98 | -2 | 753 | 753 | 737.94 | 745.1357 | 0.98 | 0.99034 | FALSE | FALSE | FALSE | 3 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143942 | HCSWB3Z5220 | B3 Z5 :Fix side shutters and casting guides for slab | 25868 | 2012-11-21 08:00 | 2012-11-22 16:00 | 1 | 24 | 100 | 100 | 0 | 1750 | 1750 | 1750 | 1852.6196 | 1 | 0.94461 | FALSE | FALSE | FALSE | 3 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143943 | HCSWB3Z5230 | B3 Z5 :Cast concrete for slab | 25868 | 2012-11-24 08:00 | 2012-11-24 16:00 | 1 | 24 | 100 | 81 | -19 | 1635 | 1635 | 1324.35 | 1909.3436 | 0.81 | 0.69362 | TRUE | TRUE | TRUE | 3 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
143944 | HCSWB3Z5240 | B3 Z5 :Cure and De-shutter slab formwork | 25868 | 2012-11-24 16:00 | 2012-12-08 16:00 | 14 | 32 | 100 | 100 | 0 | 14126 | 14126 | 14126 | 17004.1812 | 1 | 0.83074 | TRUE | FALSE | FALSE | 4 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143945 | HCSWB3Z6010 | B3 Z6 :Formwork retaining walls shutters - 1st side | 25931 | 2012-11-14 08:00 | 2012-11-24 16:00 | 10 | 128 | 100 | 91 | -9 | 19960 | 19960 | 18163.6 | 19718.7349 | 0.91 | 0.92113 | FALSE | FALSE | FALSE | 16 | FALSE | 0 | Green | Continue normal monitoring.
143946 | HCSWB3Z6020 | B3 Z6 :Fix steel rebar for reatining walls | 25931 | 2012-11-14 08:00 | 2012-11-24 16:00 | 10 | 128 | 100 | 100 | 0 | 5980 | 5980 | 5980 | 6187.7296 | 1 | 0.96643 | FALSE | FALSE | FALSE | 16 | FALSE | 0 | Green | Continue normal monitoring.
143947 | HCSWB3Z6030 | B3 Z6 :Fix MEP first fix in walls | 25931 | 2012-11-17 08:00 | 2012-11-25 16:00 | 8 | 128 | 100 | 85 | -15 | 5216 | 5216 | 4433.6 | 5298.4463 | 0.85 | 0.83677 | TRUE | TRUE | TRUE | 16 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143948 | HCSWB3Z6040 | B3 Z6 :Close shutter for retaining walls | 25931 | 2012-11-18 08:00 | 2012-11-26 16:00 | 8 | 128 | 100 | 100 | 0 | 11304 | 11304 | 11304 | 9668.3159 | 1 | 1.1692 | FALSE | FALSE | FALSE | 16 | FALSE | 0 | Green | Continue normal monitoring.
143949 | HCSWB3Z6050 | B3 Z6 :Cast concrete for retaining walls | 25931 | 2012-11-19 08:00 | 2012-11-27 16:00 | 8 | 128 | 100 | 83 | -17 | 11016 | 11016 | 9143.28 | 10667.6427 | 0.83 | 0.8571 | TRUE | TRUE | TRUE | 16 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143950 | HCSWB3Z6060 | B3 Z6 :De-shutter retaining walls | 25931 | 2012-11-20 08:00 | 2012-11-28 16:00 | 8 | 128 | 100 | 100 | 0 | 6696 | 6696 | 6696 | 6921.4924 | 1 | 0.96742 | FALSE | FALSE | FALSE | 16 | FALSE | 0 | Green | Continue normal monitoring.
143951 | HCSWB3Z6070 | B3 Z6 :Apply water proofing membrane behind Basement Walls | 25931 | 2012-11-26 08:00 | 2012-12-04 16:00 | 8 | 248 | 100 | 90 | -10 | 10568 | 10568 | 9511.2 | 10720.5749 | 0.9 | 0.88719 | TRUE | FALSE | FALSE | 31 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
143952 | HCSWB3Z6080 | B3 Z6 :Apply Protection for Basement Walls | 25931 | 2012-11-27 08:00 | 2012-12-05 16:00 | 8 | 248 | 100 | 100 | 0 | 13488 | 13488 | 13488 | 15359.7526 | 1 | 0.87814 | TRUE | FALSE | FALSE | 31 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
143953 | HCSWB3Z6150 | B3 Z6 :Fix Steel Rebar for columns | 25865 | 2012-11-14 08:00 | 2012-11-18 16:00 | 4 | 176 | 100 | 100 | 0 | 5824 | 5824 | 5824 | 5846.8385 | 1 | 0.99609 | FALSE | FALSE | FALSE | 22 | FALSE | 0 | Green | Continue normal monitoring.
143954 | HCSWB3Z6160 | B3 Z6 :Erect columns formwork | 25865 | 2012-11-17 08:00 | 2012-11-19 16:00 | 2 | 176 | 100 | 96 | -4 | 1320 | 1320 | 1267.2 | 1380.3908 | 0.96 | 0.918 | FALSE | FALSE | FALSE | 22 | FALSE | 0 | Green | Continue normal monitoring.
143955 | HCSWB3Z6170 | B3 Z6 :Cast concrete for columns | 25865 | 2012-11-18 08:00 | 2012-11-20 16:00 | 2 | 176 | 100 | 100 | 0 | 2600 | 2600 | 2600 | 2656.7929 | 1 | 0.97862 | FALSE | FALSE | FALSE | 22 | FALSE | 0 | Green | Continue normal monitoring.
143956 | HCSWB3Z6180 | B3 Z6 :De-shutter columns formwork | 25865 | 2012-11-19 08:00 | 2012-11-21 16:00 | 2 | 176 | 100 | 85 | -15 | 1794 | 1794 | 1524.9 | 2056.3733 | 0.85 | 0.74155 | TRUE | TRUE | TRUE | 22 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143957 | HCSWB3Z6190 | B3 Z6 :Erect slab formwork and proping | 25969 | 2012-11-29 08:00 | 2012-12-05 16:00 | 6 | 128 | 100 | 100 | 0 | 10800 | 10800 | 10800 | 12908.0408 | 1 | 0.83669 | TRUE | FALSE | FALSE | 16 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
143958 | HCSWB3Z6200 | B3 Z6 :Fix steel rebar for slab | 25969 | 2012-12-06 08:00 | 2012-12-09 16:00 | 3 | 128 | 100 | 84 | -16 | 3945 | 3945 | 3313.8 | 4192.571 | 0.84 | 0.7904 | TRUE | TRUE | TRUE | 16 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143959 | HCSWB3Z6210 | B3 Z6 :Fix MEP first Fix for slab | 25969 | 2012-12-10 08:00 | 2012-12-11 16:00 | 1 | 128 | 100 | 99 | -1 | 1915 | 1915 | 1895.85 | 2232.4551 | 0.99 | 0.84922 | TRUE | FALSE | FALSE | 16 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
143960 | HCSWB3Z6220 | B3 Z6 :Fix side shutters and casting guides for slab | 25969 | 2012-12-11 08:00 | 2012-12-12 16:00 | 1 | 128 | 100 | 81 | -19 | 1658 | 1658 | 1342.98 | 1606.1289 | 0.81 | 0.83616 | TRUE | TRUE | TRUE | 16 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143961 | HCSWB3Z6230 | B3 Z6 :Cast concrete for slab | 25969 | 2012-12-13 08:00 | 2012-12-13 16:00 | 1 | 128 | 100 | 85 | -15 | 1718 | 1718 | 1460.3 | 1832.3292 | 0.85 | 0.79696 | TRUE | TRUE | TRUE | 16 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143962 | HCSWB3Z6240 | B3 Z6 :Cure and De-shutter slab formwork | 25969 | 2012-12-13 16:00 | 2012-12-27 16:00 | 14 | 280 | 100 | 100 | 0 | 12600 | 12600 | 12600 | 12449.959 | 1 | 1.0121 | FALSE | FALSE | FALSE | 35 | FALSE | 0 | Green | Continue normal monitoring.
143963 | HCSWB2Z1010 | B2 Z1 :Formwork retaining walls shutters - 1st side | 25934 | 2012-10-23 08:00 | 2012-11-05 16:00 | 13 | 72 | 100 | 90 | -10 | 14807 | 14807 | 13326.3 | 15039.1792 | 0.9 | 0.88611 | TRUE | FALSE | FALSE | 9 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
143964 | HCSWB2Z1020 | B2 Z1 :Fix steel rebar for reatining walls | 25934 | 2012-10-23 08:00 | 2012-11-05 16:00 | 13 | 72 | 100 | 100 | 0 | 20228 | 20228 | 20228 | 23119.9071 | 1 | 0.87492 | TRUE | FALSE | FALSE | 9 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
143965 | HCSWB2Z1030 | B2 Z1 :Fix MEP first fix in walls | 25934 | 2012-10-24 08:00 | 2012-11-06 16:00 | 13 | 72 | 100 | 95 | -5 | 15431 | 15431 | 14659.45 | 18558.3235 | 0.95 | 0.78991 | TRUE | FALSE | FALSE | 9 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
143966 | HCSWB2Z1040 | B2 Z1 :Close shutter for retaining walls | 25934 | 2012-10-30 08:00 | 2012-11-07 16:00 | 8 | 72 | 100 | 95 | -5 | 7672 | 7672 | 7288.4 | 6894.0451 | 0.95 | 1.0572 | FALSE | FALSE | FALSE | 9 | FALSE | 0 | Green | Continue normal monitoring.
143967 | HCSWB2Z1050 | B2 Z1 :Cast concrete for retaining walls | 25934 | 2012-10-31 08:00 | 2012-11-08 16:00 | 8 | 72 | 100 | 80 | -20 | 11632 | 11632 | 9305.6 | 12840.0495 | 0.8 | 0.72473 | TRUE | TRUE | TRUE | 9 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143968 | HCSWB2Z1060 | B2 Z1 :De-shutter retaining walls | 25934 | 2012-11-01 08:00 | 2012-11-10 16:00 | 9 | 72 | 100 | 88 | -12 | 8721 | 8721 | 7674.48 | 9443.6005 | 0.88 | 0.81266 | TRUE | TRUE | TRUE | 9 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143969 | HCSWB2Z1070 | B2 Z1 :Apply water proofing membrane behind Basement Walls | 25934 | 2012-11-07 08:00 | 2012-11-17 16:00 | 10 | 592 | 100 | 100 | 0 | 18980 | 18980 | 18980 | 17032.007 | 1 | 1.1144 | FALSE | FALSE | FALSE | 74 | FALSE | 0 | Green | Continue normal monitoring.
143970 | HCSWB2Z1080 | B2 Z1 :Apply Protection for Basement Walls | 25934 | 2012-11-10 08:00 | 2012-11-19 16:00 | 9 | 592 | 100 | 100 | 0 | 13905 | 13905 | 13905 | 12997.8063 | 1 | 1.0698 | FALSE | FALSE | FALSE | 74 | FALSE | 0 | Green | Continue normal monitoring.
143971 | HCSWB2Z1090 | B2 Z1 :Formwork core wall shutters - 1st side | 25970 | 2012-10-23 08:00 | 2012-11-03 16:00 | 11 | 32 | 100 | 85 | -15 | 13739 | 13739 | 11678.15 | 13387.2953 | 0.85 | 0.87233 | TRUE | TRUE | TRUE | 4 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
143972 | HCSWB2Z1100 | B2 Z1 :Fix steel rebar for core wall | 25970 | 2012-11-04 08:00 | 2012-11-07 16:00 | 3 | 32 | 100 | 95 | -5 | 1611 | 1611 | 1530.45 | 1476.9204 | 0.95 | 1.0362 | FALSE | FALSE | FALSE | 4 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143973 | HCSWB2Z1110 | B2 Z1 :Fix MEP first fix in core wall | 25970 | 2012-11-08 08:00 | 2012-11-08 16:00 | 1 | 32 | 100 | 100 | 0 | 729 | 729 | 729 | 690.7215 | 1 | 1.0554 | FALSE | FALSE | FALSE | 4 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143974 | HCSWB2Z1120 | B2 Z1 :Close shutter for core wall | 25970 | 2012-11-10 08:00 | 2012-11-12 16:00 | 2 | 32 | 100 | 82 | -18 | 3776 | 3776 | 3096.32 | 3613.7842 | 0.82 | 0.85681 | TRUE | TRUE | TRUE | 4 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
143975 | HCSWB2Z1130 | B2 Z1 :Cast concrete for core wall | 25970 | 2012-11-13 08:00 | 2012-11-13 16:00 | 1 | 32 | 100 | 99 | -1 | 1062 | 1062 | 1051.38 | 1045.2942 | 0.99 | 1.0058 | FALSE | FALSE | FALSE | 4 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143976 | HCSWB2Z1140 | B2 Z1 :De-shutter core wall formwork | 25970 | 2012-11-14 08:00 | 2012-11-17 16:00 | 3 | 32 | 100 | 100 | 0 | 2811 | 2811 | 2811 | 3231.9646 | 1 | 0.86975 | TRUE | FALSE | FALSE | 4 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143977 | HCSWB2Z1150 | B2 Z1 :Fix Steel Rebar for columns | 25902 | 2012-10-23 08:00 | 2012-10-30 16:00 | 7 | 120 | 100 | 100 | 0 | 12642 | 12642 | 12642 | 13637.7456 | 1 | 0.92699 | FALSE | FALSE | FALSE | 15 | FALSE | 0 | Green | Continue normal monitoring.
143978 | HCSWB2Z1160 | B2 Z1 :Erect columns formwork | 25902 | 2012-10-24 08:00 | 2012-10-31 16:00 | 7 | 120 | 100 | 83 | -17 | 3682 | 3682 | 3056.06 | 4582.2441 | 0.83 | 0.66694 | TRUE | TRUE | TRUE | 15 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143979 | HCSWB2Z1170 | B2 Z1 :Cast concrete for columns | 25902 | 2012-10-30 08:00 | 2012-11-01 16:00 | 2 | 120 | 100 | 98 | -2 | 1450 | 1450 | 1421 | 1473.0468 | 0.98 | 0.96467 | FALSE | FALSE | FALSE | 15 | FALSE | 0 | Green | Continue normal monitoring.
143980 | HCSWB2Z1180 | B2 Z1 :De-shutter columns formwork | 25902 | 2012-10-31 08:00 | 2012-11-03 16:00 | 3 | 120 | 100 | 100 | 0 | 5400 | 5400 | 5400 | 6218.3486 | 1 | 0.8684 | TRUE | FALSE | FALSE | 15 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
143981 | HCSWB2Z1190 | B2 Z1 :Erect slab formwork and proping | 25903 | 2012-11-18 08:00 | 2012-11-26 16:00 | 8 | 16 | 100 | 82 | -18 | 10376 | 10376 | 8508.32 | 12436.5425 | 0.82 | 0.68414 | TRUE | TRUE | TRUE | 2 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
143982 | HCSWB2Z1200 | B2 Z1 :Fix steel rebar for slab | 25903 | 2012-11-27 08:00 | 2012-11-29 16:00 | 2 | 16 | 100 | 100 | 0 | 1566 | 1566 | 1566 | 1756.4121 | 1 | 0.89159 | TRUE | FALSE | FALSE | 2 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143983 | HCSWB2Z1210 | B2 Z1 :Fix MEP first Fix for slab | 25903 | 2012-12-01 08:00 | 2012-12-02 16:00 | 1 | 16 | 100 | 98 | -2 | 1378 | 1378 | 1350.44 | 1398.3198 | 0.98 | 0.96576 | FALSE | FALSE | FALSE | 2 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143984 | HCSWB2Z1220 | B2 Z1 :Fix side shutters and casting guides for slab | 25903 | 2012-12-02 08:00 | 2012-12-03 16:00 | 1 | 16 | 100 | 99 | -1 | 1459 | 1459 | 1444.41 | 1679.9478 | 0.99 | 0.85979 | TRUE | FALSE | FALSE | 2 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143985 | HCSWB2Z1230 | B2 Z1 :Cast concrete for slab | 25903 | 2012-12-04 08:00 | 2012-12-04 16:00 | 1 | 16 | 100 | 86 | -14 | 952 | 952 | 818.72 | 886.7564 | 0.86 | 0.92327 | FALSE | TRUE | TRUE | 2 | TRUE | 4 | Orange | Develop recovery plan and review schedule and cost exposure.
143986 | HCSWB2Z1240 | B2 Z1 :Cure and De-shutter slab formwork | 25903 | 2012-12-04 16:00 | 2012-12-18 16:00 | 14 | 16 | 100 | 99 | -1 | 21266 | 21266 | 21053.34 | 20862.3897 | 0.99 | 1.0092 | FALSE | FALSE | FALSE | 2 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143987 | HCSWB2Z2010 | B2 Z2 :Formwork retaining walls shutters - 1st side | 25905 | 2012-11-07 08:00 | 2012-11-17 16:00 | 10 | 240 | 100 | 88 | -12 | 13150 | 13150 | 11572 | 14053.0644 | 0.88 | 0.82345 | TRUE | TRUE | TRUE | 30 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143988 | HCSWB2Z2020 | B2 Z2 :Fix steel rebar for reatining walls | 25905 | 2012-11-07 08:00 | 2012-11-17 16:00 | 10 | 240 | 100 | 80 | -20 | 11580 | 11580 | 9264 | 12508.2963 | 0.8 | 0.74063 | TRUE | TRUE | TRUE | 30 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143989 | HCSWB2Z2030 | B2 Z2 :Fix MEP first fix in walls | 25905 | 2012-11-08 08:00 | 2012-11-18 16:00 | 10 | 240 | 100 | 87 | -13 | 10460 | 10460 | 9100.2 | 8983.6399 | 0.87 | 1.013 | FALSE | TRUE | TRUE | 30 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
143990 | HCSWB2Z2040 | B2 Z2 :Close shutter for retaining walls | 25905 | 2012-11-10 08:00 | 2012-11-19 16:00 | 9 | 240 | 100 | 86 | -14 | 15435 | 15435 | 13274.1 | 18954.885 | 0.86 | 0.7003 | TRUE | TRUE | TRUE | 30 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143991 | HCSWB2Z2050 | B2 Z2 :Cast concrete for retaining walls | 25905 | 2012-11-11 08:00 | 2012-11-20 16:00 | 9 | 240 | 100 | 97 | -3 | 14148 | 14148 | 13723.56 | 15968.1531 | 0.97 | 0.85943 | TRUE | FALSE | FALSE | 30 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
143992 | HCSWB2Z2060 | B2 Z2 :De-shutter retaining walls | 25905 | 2012-11-12 08:00 | 2012-11-21 16:00 | 9 | 240 | 100 | 87 | -13 | 4644 | 4644 | 4040.28 | 4868.2193 | 0.87 | 0.82993 | TRUE | TRUE | TRUE | 30 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143993 | HCSWB2Z2070 | B2 Z2 :Apply water proofing membrane behind Basement Walls | 25905 | 2012-11-19 08:00 | 2012-11-27 16:00 | 8 | 520 | 100 | 80 | -20 | 13560 | 13560 | 10848 | 16587.2821 | 0.8 | 0.654 | TRUE | TRUE | TRUE | 65 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
143994 | HCSWB2Z2080 | B2 Z2 :Apply Protection for Basement Walls | 25905 | 2012-11-21 08:00 | 2012-11-29 16:00 | 8 | 520 | 100 | 90 | -10 | 13944 | 13944 | 12549.6 | 14301.4994 | 0.9 | 0.8775 | TRUE | FALSE | FALSE | 65 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
143995 | HCSWB2Z2150 | B2 Z2 :Fix Steel Rebar for columns | 25876 | 2012-11-07 08:00 | 2012-11-10 16:00 | 3 | 288 | 100 | 100 | 0 | 1971 | 1971 | 1971 | 2448.3254 | 1 | 0.80504 | TRUE | FALSE | FALSE | 36 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
143996 | HCSWB2Z2160 | B2 Z2 :Erect columns formwork | 25876 | 2012-11-08 08:00 | 2012-11-11 16:00 | 3 | 288 | 100 | 100 | 0 | 2928 | 2928 | 2928 | 3088.7879 | 1 | 0.94794 | FALSE | FALSE | FALSE | 36 | FALSE | 0 | Green | Continue normal monitoring.
143997 | HCSWB2Z2170 | B2 Z2 :Cast concrete for columns | 25876 | 2012-11-10 08:00 | 2012-11-12 16:00 | 2 | 288 | 100 | 100 | 0 | 3138 | 3138 | 3138 | 2810.7515 | 1 | 1.1164 | FALSE | FALSE | FALSE | 36 | FALSE | 0 | Green | Continue normal monitoring.
143998 | HCSWB2Z2180 | B2 Z2 :De-shutter columns formwork | 25876 | 2012-11-11 08:00 | 2012-11-13 16:00 | 2 | 288 | 100 | 97 | -3 | 3792 | 3792 | 3678.24 | 4383.2501 | 0.97 | 0.83916 | TRUE | FALSE | FALSE | 36 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
143999 | HCSWB2Z2190 | B2 Z2 :Erect slab formwork and proping | 25874 | 2012-12-23 08:00 | 2012-12-29 16:00 | 6 | 32 | 100 | 100 | 0 | 6102 | 6102 | 6102 | 6843.7536 | 1 | 0.89162 | TRUE | FALSE | FALSE | 4 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144000 | HCSWB2Z2200 | B2 Z2 :Fix steel rebar for slab | 25874 | 2012-12-30 08:00 | 2013-01-02 16:00 | 3 | 32 | 100 | 100 | 0 | 1794 | 1794 | 1794 | 2079.5953 | 1 | 0.86267 | TRUE | FALSE | FALSE | 4 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144001 | HCSWB2Z2210 | B2 Z2 :Fix MEP first Fix for slab | 25874 | 2013-01-03 08:00 | 2013-01-05 16:00 | 2 | 32 | 100 | 100 | 0 | 3120 | 3120 | 3120 | 3839.3997 | 1 | 0.81263 | TRUE | FALSE | FALSE | 4 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144002 | HCSWB2Z2220 | B2 Z2 :Fix side shutters and casting guides for slab | 25874 | 2013-01-05 08:00 | 2013-01-06 16:00 | 1 | 32 | 100 | 89 | -11 | 779 | 779 | 693.31 | 904.1041 | 0.89 | 0.76685 | TRUE | TRUE | TRUE | 4 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
144003 | HCSWB2Z2230 | B2 Z2 :Cast concrete for slab | 25874 | 2013-01-07 08:00 | 2013-01-07 16:00 | 1 | 32 | 100 | 82 | -18 | 1872 | 1872 | 1535.04 | 2048.9688 | 0.82 | 0.74918 | TRUE | TRUE | TRUE | 4 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
144004 | HCSWB2Z2240 | B2 Z2 :Cure and De-shutter slab formwork | 25874 | 2013-01-07 16:00 | 2013-01-21 16:00 | 14 | 41 | 100 | 86 | -14 | 13944 | 13944 | 11991.84 | 16634.1261 | 0.86 | 0.72092 | TRUE | TRUE | TRUE | 5.125 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144005 | HCSWB2Z3010 | B2 Z3 :Formwork retaining walls shutters - 1st side | 25922 | 2012-11-10 08:00 | 2012-11-14 16:00 | 4 | 128 | 100 | 100 | 0 | 3204 | 3204 | 3204 | 3586.2326 | 1 | 0.89342 | TRUE | FALSE | FALSE | 16 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144006 | HCSWB2Z3020 | B2 Z3 :Fix steel rebar for reatining walls | 25922 | 2012-11-10 08:00 | 2012-11-14 16:00 | 4 | 128 | 100 | 95 | -5 | 2720 | 2720 | 2584 | 2756.0335 | 0.95 | 0.93758 | FALSE | FALSE | FALSE | 16 | FALSE | 0 | Green | Continue normal monitoring.
144007 | HCSWB2Z3030 | B2 Z3 :Fix MEP first fix in walls | 25922 | 2012-11-11 08:00 | 2012-11-17 16:00 | 6 | 128 | 100 | 100 | 0 | 6636 | 6636 | 6636 | 7991.3891 | 1 | 0.83039 | TRUE | FALSE | FALSE | 16 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144008 | HCSWB2Z3040 | B2 Z3 :Close shutter for retaining walls | 25922 | 2012-11-12 08:00 | 2012-11-18 16:00 | 6 | 128 | 100 | 95 | -5 | 9732 | 9732 | 9245.4 | 9136.0141 | 0.95 | 1.012 | FALSE | FALSE | FALSE | 16 | FALSE | 0 | Green | Continue normal monitoring.
144009 | HCSWB2Z3050 | B2 Z3 :Cast concrete for retaining walls | 25922 | 2012-11-13 08:00 | 2012-11-19 16:00 | 6 | 128 | 100 | 100 | 0 | 7194 | 7194 | 7194 | 8171.3517 | 1 | 0.88039 | TRUE | FALSE | FALSE | 16 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144010 | HCSWB2Z3060 | B2 Z3 :De-shutter retaining walls | 25922 | 2012-11-14 08:00 | 2012-11-20 16:00 | 6 | 128 | 100 | 99 | -1 | 8952 | 8952 | 8862.48 | 10765.9024 | 0.99 | 0.8232 | TRUE | FALSE | FALSE | 16 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144011 | HCSWB2Z3070 | B2 Z3 :Apply water proofing membrane behind Basement Walls | 25922 | 2012-11-19 08:00 | 2012-11-24 16:00 | 5 | 840 | 100 | 100 | 0 | 8195 | 8195 | 8195 | 9363.0056 | 1 | 0.87525 | TRUE | FALSE | FALSE | 105 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144012 | HCSWB2Z3080 | B2 Z3 :Apply Protection for Basement Walls | 25922 | 2012-11-21 08:00 | 2012-11-26 16:00 | 5 | 840 | 100 | 96 | -4 | 3450 | 3450 | 3312 | 3894.7401 | 0.96 | 0.85038 | TRUE | FALSE | FALSE | 105 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144013 | HCSWB2Z3090 | B2 Z3 :Formwork core wall shutters - 1st side | 25910 | 2012-11-10 08:00 | 2012-11-17 16:00 | 7 | 64 | 100 | 81 | -19 | 5264 | 5264 | 4263.84 | 6059.1552 | 0.81 | 0.7037 | TRUE | TRUE | TRUE | 8 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144014 | HCSWB2Z3100 | B2 Z3 :Fix steel rebar for core wall | 25910 | 2012-11-18 08:00 | 2012-11-21 16:00 | 3 | 64 | 100 | 80 | -20 | 4440 | 4440 | 3552 | 4599.9381 | 0.8 | 0.77218 | TRUE | TRUE | TRUE | 8 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144015 | HCSWB2Z3110 | B2 Z3 :Fix MEP first fix in core wall | 25910 | 2012-11-22 08:00 | 2012-11-22 16:00 | 1 | 64 | 100 | 95 | -5 | 1427 | 1427 | 1355.65 | 1711.9266 | 0.95 | 0.79189 | TRUE | FALSE | FALSE | 8 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144016 | HCSWB2Z3120 | B2 Z3 :Close shutter for core wall | 25910 | 2012-11-24 08:00 | 2012-11-26 16:00 | 2 | 64 | 100 | 100 | 0 | 3368 | 3368 | 3368 | 3136.8696 | 1 | 1.0737 | FALSE | FALSE | FALSE | 8 | FALSE | 0 | Green | Continue normal monitoring.
144017 | HCSWB2Z3130 | B2 Z3 :Cast concrete for core wall | 25910 | 2012-11-27 08:00 | 2012-11-27 16:00 | 1 | 64 | 100 | 91 | -9 | 1779 | 1779 | 1618.89 | 1602.7982 | 0.91 | 1.01 | FALSE | FALSE | FALSE | 8 | FALSE | 0 | Green | Continue normal monitoring.
144018 | HCSWB2Z3140 | B2 Z3 :De-shutter core wall formwork | 25910 | 2012-11-28 08:00 | 2012-11-29 16:00 | 1 | 64 | 100 | 84 | -16 | 1846 | 1846 | 1550.64 | 1779.9197 | 0.84 | 0.87119 | TRUE | TRUE | TRUE | 8 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144019 | HCSWB2Z3150 | B2 Z3 :Fix Steel Rebar for columns | 25878 | 2012-11-10 08:00 | 2012-11-12 16:00 | 2 | 152 | 100 | 84 | -16 | 1254 | 1254 | 1053.36 | 1332.5392 | 0.84 | 0.79049 | TRUE | TRUE | TRUE | 19 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144020 | HCSWB2Z3160 | B2 Z3 :Erect columns formwork | 25878 | 2012-11-11 08:00 | 2012-11-13 16:00 | 2 | 152 | 100 | 100 | 0 | 1034 | 1034 | 1034 | 1090.0684 | 1 | 0.94856 | FALSE | FALSE | FALSE | 19 | FALSE | 0 | Green | Continue normal monitoring.
144021 | HCSWB2Z3170 | B2 Z3 :Cast concrete for columns | 25878 | 2012-11-12 08:00 | 2012-11-14 16:00 | 2 | 152 | 100 | 100 | 0 | 2130 | 2130 | 2130 | 2509.6501 | 1 | 0.84872 | TRUE | FALSE | FALSE | 19 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144022 | HCSWB2Z3180 | B2 Z3 :De-shutter columns formwork | 25878 | 2012-11-13 08:00 | 2012-11-17 16:00 | 4 | 152 | 100 | 88 | -12 | 4276 | 4276 | 3762.88 | 4326.5742 | 0.88 | 0.86971 | TRUE | TRUE | TRUE | 19 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144023 | HCSWB2Z3190 | B2 Z3 :Erect slab formwork and proping | 25912 | 2012-12-04 08:00 | 2012-12-12 16:00 | 8 | 24 | 100 | 88 | -12 | 14768 | 14768 | 12995.84 | 15413.9194 | 0.88 | 0.84312 | TRUE | TRUE | TRUE | 3 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
144024 | HCSWB2Z3200 | B2 Z3 :Fix steel rebar for slab | 25912 | 2012-12-13 08:00 | 2012-12-16 16:00 | 3 | 24 | 100 | 82 | -18 | 3555 | 3555 | 2915.1 | 3040.7588 | 0.82 | 0.95868 | FALSE | TRUE | TRUE | 3 | TRUE | 4 | Orange | Develop recovery plan and review schedule and cost exposure.
144025 | HCSWB2Z3210 | B2 Z3 :Fix MEP first Fix for slab | 25912 | 2012-12-17 08:00 | 2012-12-18 16:00 | 1 | 24 | 100 | 98 | -2 | 1125 | 1125 | 1102.5 | 1140.6327 | 0.98 | 0.96657 | FALSE | FALSE | FALSE | 3 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144026 | HCSWB2Z3220 | B2 Z3 :Fix side shutters and casting guides for slab | 25912 | 2012-12-18 08:00 | 2012-12-19 16:00 | 1 | 24 | 100 | 95 | -5 | 1811 | 1811 | 1720.45 | 2008.5977 | 0.95 | 0.85654 | TRUE | FALSE | FALSE | 3 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144027 | HCSWB2Z3230 | B2 Z3 :Cast concrete for slab | 25912 | 2012-12-20 08:00 | 2012-12-20 16:00 | 1 | 24 | 100 | 95 | -5 | 1353 | 1353 | 1285.35 | 1158.4431 | 0.95 | 1.1095 | FALSE | FALSE | FALSE | 3 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144028 | HCSWB2Z3240 | B2 Z3 :Cure and De-shutter slab formwork | 25912 | 2012-12-20 16:00 | 2013-01-03 16:00 | 14 | 376 | 100 | 82 | -18 | 20454 | 20454 | 16772.28 | 19683.9639 | 0.82 | 0.85208 | TRUE | TRUE | TRUE | 47 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144029 | HCSWB2Z4010 | B2 Z4 :Formwork retaining walls shutters - 1st side | 25870 | 2012-12-12 08:00 | 2012-12-17 16:00 | 5 | 240 | 100 | 99 | -1 | 3270 | 3270 | 3237.3 | 3051.5069 | 0.99 | 1.0609 | FALSE | FALSE | FALSE | 30 | FALSE | 0 | Green | Continue normal monitoring.
144030 | HCSWB2Z4020 | B2 Z4 :Fix steel rebar for reatining walls | 25870 | 2012-12-12 08:00 | 2012-12-17 16:00 | 5 | 240 | 100 | 100 | 0 | 4945 | 4945 | 4945 | 4286.2972 | 1 | 1.1537 | FALSE | FALSE | FALSE | 30 | FALSE | 0 | Green | Continue normal monitoring.
144031 | HCSWB2Z4030 | B2 Z4 :Fix MEP first fix in walls | 25870 | 2012-12-13 08:00 | 2012-12-18 16:00 | 5 | 240 | 100 | 100 | 0 | 9545 | 9545 | 9545 | 9943.065 | 1 | 0.95997 | FALSE | FALSE | FALSE | 30 | FALSE | 0 | Green | Continue normal monitoring.
144032 | HCSWB2Z4040 | B2 Z4 :Close shutter for retaining walls | 25870 | 2012-12-15 08:00 | 2012-12-19 16:00 | 4 | 240 | 100 | 100 | 0 | 5136 | 5136 | 5136 | 4738.9323 | 1 | 1.0838 | FALSE | FALSE | FALSE | 30 | FALSE | 0 | Green | Continue normal monitoring.
144033 | HCSWB2Z4050 | B2 Z4 :Cast concrete for retaining walls | 25870 | 2012-12-16 08:00 | 2012-12-20 16:00 | 4 | 240 | 100 | 80 | -20 | 6508 | 6508 | 5206.4 | 7466.1899 | 0.8 | 0.69733 | TRUE | TRUE | TRUE | 30 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144034 | HCSWB2Z4060 | B2 Z4 :De-shutter retaining walls | 25870 | 2012-12-17 08:00 | 2012-12-22 16:00 | 5 | 240 | 100 | 100 | 0 | 9580 | 9580 | 9580 | 11392.2597 | 1 | 0.84092 | TRUE | FALSE | FALSE | 30 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144035 | HCSWB2Z4070 | B2 Z4 :Apply water proofing membrane behind Basement Walls | 25870 | 2012-12-20 08:00 | 2012-12-25 16:00 | 5 | 608 | 100 | 99 | -1 | 3725 | 3725 | 3687.75 | 3979.1719 | 0.99 | 0.92676 | FALSE | FALSE | FALSE | 76 | FALSE | 0 | Green | Continue normal monitoring.
144036 | HCSWB2Z4080 | B2 Z4 :Apply Protection for Basement Walls | 25870 | 2012-12-23 08:00 | 2012-12-27 16:00 | 4 | 608 | 100 | 90 | -10 | 6796 | 6796 | 6116.4 | 8445.2732 | 0.9 | 0.72424 | TRUE | FALSE | FALSE | 76 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144037 | HCSWB2Z4150 | B2 Z4 :Fix Steel Rebar for columns | 25915 | 2012-12-12 08:00 | 2012-12-15 16:00 | 3 | 264 | 100 | 96 | -4 | 4686 | 4686 | 4498.56 | 4827.477 | 0.96 | 0.93187 | FALSE | FALSE | FALSE | 33 | FALSE | 0 | Green | Continue normal monitoring.
144038 | HCSWB2Z4160 | B2 Z4 :Erect columns formwork | 25915 | 2012-12-13 08:00 | 2012-12-16 16:00 | 3 | 264 | 100 | 87 | -13 | 3774 | 3774 | 3283.38 | 3982.8807 | 0.87 | 0.82437 | TRUE | TRUE | TRUE | 33 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144039 | HCSWB2Z4170 | B2 Z4 :Cast concrete for columns | 25915 | 2012-12-15 08:00 | 2012-12-17 16:00 | 2 | 264 | 100 | 83 | -17 | 2074 | 2074 | 1721.42 | 2583.555 | 0.83 | 0.6663 | TRUE | TRUE | TRUE | 33 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144040 | HCSWB2Z4180 | B2 Z4 :De-shutter columns formwork | 25915 | 2012-12-16 08:00 | 2012-12-18 16:00 | 2 | 264 | 100 | 85 | -15 | 2840 | 2840 | 2414 | 2677.039 | 0.85 | 0.90174 | FALSE | TRUE | TRUE | 33 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144041 | HCSWB2Z4190 | B2 Z4 :Erect slab formwork and proping | 25889 | 2012-12-25 08:00 | 2012-12-31 16:00 | 6 | 224 | 100 | 87 | -13 | 5442 | 5442 | 4734.54 | 6677.434 | 0.87 | 0.70904 | TRUE | TRUE | TRUE | 28 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144042 | HCSWB2Z4200 | B2 Z4 :Fix steel rebar for slab | 25889 | 2013-01-02 08:00 | 2013-01-05 16:00 | 3 | 224 | 100 | 99 | -1 | 3072 | 3072 | 3041.28 | 2663.8388 | 0.99 | 1.1417 | FALSE | FALSE | FALSE | 28 | FALSE | 0 | Green | Continue normal monitoring.
144043 | HCSWB2Z4210 | B2 Z4 :Fix MEP first Fix for slab | 25889 | 2013-01-06 08:00 | 2013-01-07 16:00 | 1 | 224 | 100 | 100 | 0 | 1327 | 1327 | 1327 | 1364.8922 | 1 | 0.97224 | FALSE | FALSE | FALSE | 28 | FALSE | 0 | Green | Continue normal monitoring.
144044 | HCSWB2Z4220 | B2 Z4 :Fix side shutters and casting guides for slab | 25889 | 2013-01-07 08:00 | 2013-01-08 16:00 | 1 | 224 | 100 | 82 | -18 | 1402 | 1402 | 1149.64 | 1230.958 | 0.82 | 0.93394 | FALSE | TRUE | TRUE | 28 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144045 | HCSWB2Z4230 | B2 Z4 :Cast concrete for slab | 25889 | 2013-01-09 08:00 | 2013-01-09 16:00 | 1 | 224 | 100 | 95 | -5 | 535 | 535 | 508.25 | 610.8062 | 0.95 | 0.8321 | TRUE | FALSE | FALSE | 28 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144046 | HCSWB2Z4240 | B2 Z4 :Cure and De-shutter slab formwork | 25889 | 2013-01-09 16:00 | 2013-01-23 16:00 | 14 | 272 | 100 | 100 | 0 | 16576 | 16576 | 16576 | 18123.5946 | 1 | 0.91461 | FALSE | FALSE | FALSE | 34 | FALSE | 0 | Green | Continue normal monitoring.
144047 | HCSWB2Z5010 | B2 Z5 :Formwork retaining walls shutters - 1st side | 25918 | 2012-11-25 08:00 | 2012-12-03 16:00 | 8 | 64 | 100 | 100 | 0 | 4152 | 4152 | 4152 | 4702.7782 | 1 | 0.88288 | TRUE | FALSE | FALSE | 8 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144048 | HCSWB2Z5020 | B2 Z5 :Fix steel rebar for reatining walls | 25918 | 2012-11-25 08:00 | 2012-12-03 16:00 | 8 | 64 | 100 | 82 | -18 | 6560 | 6560 | 5379.2 | 6558.6366 | 0.82 | 0.82017 | TRUE | TRUE | TRUE | 8 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144049 | HCSWB2Z5030 | B2 Z5 :Fix MEP first fix in walls | 25918 | 2012-11-26 08:00 | 2012-12-04 16:00 | 8 | 64 | 100 | 100 | 0 | 8088 | 8088 | 8088 | 8070.148 | 1 | 1.0022 | FALSE | FALSE | FALSE | 8 | FALSE | 0 | Green | Continue normal monitoring.
144050 | HCSWB2Z5040 | B2 Z5 :Close shutter for retaining walls | 25918 | 2012-11-27 08:00 | 2012-12-05 16:00 | 8 | 64 | 100 | 100 | 0 | 7192 | 7192 | 7192 | 6243.5745 | 1 | 1.1519 | FALSE | FALSE | FALSE | 8 | FALSE | 0 | Green | Continue normal monitoring.
144051 | HCSWB2Z5050 | B2 Z5 :Cast concrete for retaining walls | 25918 | 2012-11-28 08:00 | 2012-12-06 16:00 | 8 | 64 | 100 | 97 | -3 | 9224 | 9224 | 8947.28 | 9131.5568 | 0.97 | 0.97982 | FALSE | FALSE | FALSE | 8 | FALSE | 0 | Green | Continue normal monitoring.
144052 | HCSWB2Z5060 | B2 Z5 :De-shutter retaining walls | 25918 | 2012-11-29 08:00 | 2012-12-08 16:00 | 9 | 64 | 100 | 93 | -7 | 13239 | 13239 | 12312.27 | 16174.2897 | 0.93 | 0.76122 | TRUE | FALSE | FALSE | 8 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144053 | HCSWB2Z5070 | B2 Z5 :Apply water proofing membrane behind Basement Walls | 25918 | 2012-12-05 08:00 | 2012-12-13 16:00 | 8 | 712 | 100 | 97 | -3 | 7760 | 7760 | 7527.2 | 7773.1192 | 0.97 | 0.96836 | FALSE | FALSE | FALSE | 89 | FALSE | 0 | Green | Continue normal monitoring.
144054 | HCSWB2Z5080 | B2 Z5 :Apply Protection for Basement Walls | 25918 | 2012-12-08 08:00 | 2012-12-16 16:00 | 8 | 712 | 100 | 81 | -19 | 13328 | 13328 | 10795.68 | 15760.9875 | 0.81 | 0.68496 | TRUE | TRUE | TRUE | 89 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144055 | HCSWB2Z5090 | B2 Z5 :Formwork core wall shutters - 1st side | 25867 | 2012-11-25 08:00 | 2012-12-01 16:00 | 6 | 24 | 100 | 100 | 0 | 9690 | 9690 | 9690 | 11501.3537 | 1 | 0.84251 | TRUE | FALSE | FALSE | 3 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144056 | HCSWB2Z5100 | B2 Z5 :Fix steel rebar for core wall | 25867 | 2012-12-02 08:00 | 2012-12-05 16:00 | 3 | 24 | 100 | 82 | -18 | 5631 | 5631 | 4617.42 | 5627.0384 | 0.82 | 0.82058 | TRUE | TRUE | TRUE | 3 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
144057 | HCSWB2Z5110 | B2 Z5 :Fix MEP first fix in core wall | 25867 | 2012-12-06 08:00 | 2012-12-06 16:00 | 1 | 24 | 100 | 95 | -5 | 1333 | 1333 | 1266.35 | 1470.0264 | 0.95 | 0.86145 | TRUE | FALSE | FALSE | 3 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144058 | HCSWB2Z5120 | B2 Z5 :Close shutter for core wall | 25867 | 2012-12-08 08:00 | 2012-12-10 16:00 | 2 | 24 | 100 | 100 | 0 | 2452 | 2452 | 2452 | 2177.7405 | 1 | 1.1259 | FALSE | FALSE | FALSE | 3 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144059 | HCSWB2Z5130 | B2 Z5 :Cast concrete for core wall | 25867 | 2012-12-11 08:00 | 2012-12-11 16:00 | 1 | 24 | 100 | 88 | -12 | 1353 | 1353 | 1190.64 | 1206.1608 | 0.88 | 0.98713 | FALSE | TRUE | TRUE | 3 | TRUE | 4 | Orange | Develop recovery plan and review schedule and cost exposure.
144060 | HCSWB2Z5140 | B2 Z5 :De-shutter core wall formwork | 25867 | 2012-12-12 08:00 | 2012-12-13 16:00 | 1 | 24 | 100 | 83 | -17 | 550 | 550 | 456.5 | 478.2047 | 0.83 | 0.95461 | FALSE | TRUE | TRUE | 3 | TRUE | 4 | Orange | Develop recovery plan and review schedule and cost exposure.
144061 | HCSWB2Z5150 | B2 Z5 :Fix Steel Rebar for columns | 25871 | 2012-11-25 08:00 | 2012-11-27 16:00 | 2 | 112 | 100 | 80 | -20 | 2148 | 2148 | 1718.4 | 2325.0082 | 0.8 | 0.73909 | TRUE | TRUE | TRUE | 14 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144062 | HCSWB2Z5160 | B2 Z5 :Erect columns formwork | 25871 | 2012-11-26 08:00 | 2012-11-28 16:00 | 2 | 112 | 100 | 83 | -17 | 3426 | 3426 | 2843.58 | 3495.9877 | 0.83 | 0.81338 | TRUE | TRUE | TRUE | 14 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144063 | HCSWB2Z5170 | B2 Z5 :Cast concrete for columns | 25871 | 2012-11-27 08:00 | 2012-11-29 16:00 | 2 | 112 | 100 | 80 | -20 | 3296 | 3296 | 2636.8 | 3524.1259 | 0.8 | 0.74821 | TRUE | TRUE | TRUE | 14 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144064 | HCSWB2Z5180 | B2 Z5 :De-shutter columns formwork | 25871 | 2012-11-28 08:00 | 2012-12-01 16:00 | 3 | 112 | 100 | 93 | -7 | 1947 | 1947 | 1810.71 | 2060.7618 | 0.93 | 0.87866 | TRUE | FALSE | FALSE | 14 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144065 | HCSWB2Z5190 | B2 Z5 :Erect slab formwork and proping | 26000 | 2012-12-13 08:00 | 2012-12-22 16:00 | 9 | 16 | 100 | 100 | 0 | 7317 | 7317 | 7317 | 7244.4241 | 1 | 1.01 | FALSE | FALSE | FALSE | 2 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144066 | HCSWB2Z5200 | B2 Z5 :Fix steel rebar for slab | 26000 | 2012-12-23 08:00 | 2012-12-25 16:00 | 2 | 16 | 100 | 95 | -5 | 2138 | 2138 | 2031.1 | 2396.6753 | 0.95 | 0.84747 | TRUE | FALSE | FALSE | 2 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144067 | HCSWB2Z5210 | B2 Z5 :Fix MEP first Fix for slab | 26000 | 2012-12-26 08:00 | 2012-12-27 16:00 | 1 | 16 | 100 | 99 | -1 | 1865 | 1865 | 1846.35 | 2151.0924 | 0.99 | 0.85833 | TRUE | FALSE | FALSE | 2 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144068 | HCSWB2Z5220 | B2 Z5 :Fix side shutters and casting guides for slab | 26000 | 2012-12-27 08:00 | 2012-12-29 16:00 | 2 | 16 | 100 | 100 | 0 | 1608 | 1608 | 1608 | 1376.2089 | 1 | 1.1684 | FALSE | FALSE | FALSE | 2 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144069 | HCSWB2Z5230 | B2 Z5 :Cast concrete for slab | 26000 | 2012-12-30 08:00 | 2012-12-30 16:00 | 1 | 16 | 100 | 87 | -13 | 1181 | 1181 | 1027.47 | 1101.7513 | 0.87 | 0.93258 | FALSE | TRUE | TRUE | 2 | TRUE | 4 | Orange | Develop recovery plan and review schedule and cost exposure.
144070 | HCSWB2Z5240 | B2 Z5 :Cure and De-shutter slab formwork | 26000 | 2012-12-30 16:00 | 2013-01-13 16:00 | 14 | 24 | 100 | 86 | -14 | 18718 | 18718 | 16097.48 | 21250.4396 | 0.86 | 0.75751 | TRUE | TRUE | TRUE | 3 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
144071 | HCSWB2Z6010 | B2 Z6 :Formwork retaining walls shutters - 1st side | 26025 | 2012-12-15 08:00 | 2012-12-23 16:00 | 8 | 128 | 100 | 82 | -18 | 12616 | 12616 | 10345.12 | 12674.64 | 0.82 | 0.81621 | TRUE | TRUE | TRUE | 16 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144072 | HCSWB2Z6020 | B2 Z6 :Fix steel rebar for reatining walls | 26025 | 2012-12-15 08:00 | 2012-12-23 16:00 | 8 | 128 | 100 | 96 | -4 | 12016 | 12016 | 11535.36 | 13397.7628 | 0.96 | 0.86099 | TRUE | FALSE | FALSE | 16 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144073 | HCSWB2Z6030 | B2 Z6 :Fix MEP first fix in walls | 26025 | 2012-12-15 08:00 | 2012-12-23 16:00 | 8 | 128 | 100 | 80 | -20 | 7544 | 7544 | 6035.2 | 7459.3945 | 0.8 | 0.80907 | TRUE | TRUE | TRUE | 16 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144074 | HCSWB2Z6040 | B2 Z6 :Close shutter for retaining walls | 26025 | 2012-12-16 08:00 | 2012-12-24 16:00 | 8 | 128 | 100 | 95 | -5 | 8896 | 8896 | 8451.2 | 8952.0631 | 0.95 | 0.94405 | FALSE | FALSE | FALSE | 16 | FALSE | 0 | Green | Continue normal monitoring.
144075 | HCSWB2Z6050 | B2 Z6 :Cast concrete for retaining walls | 26025 | 2012-12-17 08:00 | 2012-12-25 16:00 | 8 | 128 | 100 | 91 | -9 | 11936 | 11936 | 10861.76 | 10903.1964 | 0.91 | 0.9962 | FALSE | FALSE | FALSE | 16 | FALSE | 0 | Green | Continue normal monitoring.
144076 | HCSWB2Z6060 | B2 Z6 :De-shutter retaining walls | 26025 | 2012-12-18 08:00 | 2012-12-26 16:00 | 8 | 128 | 100 | 100 | 0 | 6104 | 6104 | 6104 | 5818.8969 | 1 | 1.049 | FALSE | FALSE | FALSE | 16 | FALSE | 0 | Green | Continue normal monitoring.
144077 | HCSWB2Z6070 | B2 Z6 :Apply water proofing membrane behind Basement Walls | 26025 | 2012-12-24 08:00 | 2013-01-02 16:00 | 9 | 128 | 100 | 98 | -2 | 14184 | 14184 | 13900.32 | 15491.2641 | 0.98 | 0.8973 | TRUE | FALSE | FALSE | 16 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144078 | HCSWB2Z6080 | B2 Z6 :Apply Protection for Basement Walls | 26025 | 2012-12-26 08:00 | 2013-01-05 16:00 | 10 | 128 | 100 | 100 | 0 | 15030 | 15030 | 15030 | 15379.6766 | 1 | 0.97726 | FALSE | FALSE | FALSE | 16 | FALSE | 0 | Green | Continue normal monitoring.
144079 | HCSWB2Z6150 | B2 Z6 :Fix Steel Rebar for columns | 25891 | 2012-12-15 08:00 | 2012-12-17 16:00 | 2 | 408 | 100 | 100 | 0 | 1008 | 1008 | 1008 | 1168.9988 | 1 | 0.86228 | TRUE | FALSE | FALSE | 51 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144080 | HCSWB2Z6160 | B2 Z6 :Erect columns formwork | 25891 | 2012-12-16 08:00 | 2012-12-18 16:00 | 2 | 408 | 100 | 100 | 0 | 3252 | 3252 | 3252 | 3873.2425 | 1 | 0.83961 | TRUE | FALSE | FALSE | 51 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144081 | HCSWB2Z6170 | B2 Z6 :Cast concrete for columns | 25891 | 2012-12-17 08:00 | 2012-12-19 16:00 | 2 | 408 | 100 | 93 | -7 | 3438 | 3438 | 3197.34 | 3667.1722 | 0.93 | 0.87188 | TRUE | FALSE | FALSE | 51 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144082 | HCSWB2Z6180 | B2 Z6 :De-shutter columns formwork | 25891 | 2012-12-18 08:00 | 2012-12-20 16:00 | 2 | 408 | 100 | 100 | 0 | 2546 | 2546 | 2546 | 2936.3194 | 1 | 0.86707 | TRUE | FALSE | FALSE | 51 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144083 | HCSWB2Z6190 | B2 Z6 :Erect slab formwork and proping | 25978 | 2013-01-17 08:00 | 2013-01-23 16:00 | 6 | 232 | 100 | 85 | -15 | 8256 | 8256 | 7017.6 | 8031.1215 | 0.85 | 0.8738 | TRUE | TRUE | TRUE | 29 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144084 | HCSWB2Z6200 | B2 Z6 :Fix steel rebar for slab | 25978 | 2013-01-26 08:00 | 2013-01-28 16:00 | 2 | 232 | 100 | 85 | -15 | 2982 | 2982 | 2534.7 | 3029.6777 | 0.85 | 0.83662 | TRUE | TRUE | TRUE | 29 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144085 | HCSWB2Z6210 | B2 Z6 :Fix MEP first Fix for slab | 25978 | 2013-01-29 08:00 | 2013-01-30 16:00 | 1 | 232 | 100 | 92 | -8 | 1383 | 1383 | 1272.36 | 1569.8586 | 0.92 | 0.81049 | TRUE | FALSE | FALSE | 29 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144086 | HCSWB2Z6220 | B2 Z6 :Fix side shutters and casting guides for slab | 25978 | 2013-01-30 08:00 | 2013-01-31 16:00 | 1 | 232 | 100 | 98 | -2 | 1873 | 1873 | 1835.54 | 1881.4 | 0.98 | 0.97562 | FALSE | FALSE | FALSE | 29 | FALSE | 0 | Green | Continue normal monitoring.
144087 | HCSWB2Z6230 | B2 Z6 :Cast concrete for slab | 25978 | 2013-02-02 08:00 | 2013-02-02 16:00 | 1 | 232 | 100 | 100 | 0 | 546 | 546 | 546 | 592.6295 | 1 | 0.92132 | FALSE | FALSE | FALSE | 29 | FALSE | 0 | Green | Continue normal monitoring.
144088 | HCSWB2Z6240 | B2 Z6 :Cure and De-shutter slab formwork | 25978 | 2013-02-02 16:00 | 2013-02-16 16:00 | 14 | 416 | 100 | 87 | -13 | 19124 | 19124 | 16637.88 | 17673.4276 | 0.87 | 0.94141 | FALSE | TRUE | TRUE | 52 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144089 | HCSWB1Z1010 | B1 Z1 :Formwork retaining walls shutters - 1st side | 25864 | 2012-12-05 08:00 | 2012-12-13 16:00 | 8 | 400 | 100 | 100 | 0 | 10576 | 10576 | 10576 | 11526.8726 | 1 | 0.91751 | FALSE | FALSE | FALSE | 50 | FALSE | 0 | Green | Continue normal monitoring.
144090 | HCSWB1Z1020 | B1 Z1 :Fix steel rebar for reatining walls | 25864 | 2012-12-05 08:00 | 2012-12-13 16:00 | 8 | 400 | 100 | 100 | 0 | 11480 | 11480 | 11480 | 13714.0709 | 1 | 0.8371 | TRUE | FALSE | FALSE | 50 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144091 | HCSWB1Z1030 | B1 Z1 :Fix MEP first fix in walls | 25864 | 2012-12-06 08:00 | 2012-12-15 16:00 | 9 | 400 | 100 | 81 | -19 | 10395 | 10395 | 8419.95 | 12447.5536 | 0.81 | 0.67643 | TRUE | TRUE | TRUE | 50 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144092 | HCSWB1Z1040 | B1 Z1 :Close shutter for retaining walls | 25864 | 2012-12-08 08:00 | 2012-12-16 16:00 | 8 | 400 | 100 | 100 | 0 | 6144 | 6144 | 6144 | 7002.5488 | 1 | 0.87739 | TRUE | FALSE | FALSE | 50 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144093 | HCSWB1Z1050 | B1 Z1 :Cast concrete for retaining walls | 25864 | 2012-12-09 08:00 | 2012-12-17 16:00 | 8 | 400 | 100 | 100 | 0 | 6952 | 6952 | 6952 | 7982.991 | 1 | 0.87085 | TRUE | FALSE | FALSE | 50 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144094 | HCSWB1Z1060 | B1 Z1 :De-shutter retaining walls | 25864 | 2012-12-10 08:00 | 2012-12-18 16:00 | 8 | 400 | 100 | 80 | -20 | 9080 | 9080 | 7264 | 9744.3925 | 0.8 | 0.74545 | TRUE | TRUE | TRUE | 50 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144095 | HCSWB1Z1070 | B1 Z1 :Apply water proofing membrane behind Basement Walls | 25864 | 2012-12-16 08:00 | 2012-12-24 16:00 | 8 | 624 | 100 | 100 | 0 | 13032 | 13032 | 13032 | 14124.9578 | 1 | 0.92262 | FALSE | FALSE | FALSE | 78 | FALSE | 0 | Green | Continue normal monitoring.
144096 | HCSWB1Z1080 | B1 Z1 :Apply Protection for Basement Walls | 25864 | 2012-12-18 08:00 | 2012-12-26 16:00 | 8 | 624 | 100 | 94 | -6 | 9248 | 9248 | 8693.12 | 8355.2002 | 0.94 | 1.0404 | FALSE | FALSE | FALSE | 78 | FALSE | 0 | Green | Continue normal monitoring.
144097 | HCSWB1Z1090 | B1 Z1 :Formwork core wall shutters - 1st side | 25907 | 2012-12-05 08:00 | 2012-12-11 16:00 | 6 | 360 | 100 | 80 | -20 | 3714 | 3714 | 2971.2 | 3816.2972 | 0.8 | 0.77856 | TRUE | TRUE | TRUE | 45 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144098 | HCSWB1Z1100 | B1 Z1 :Fix steel rebar for core wall | 25907 | 2012-12-12 08:00 | 2012-12-16 16:00 | 4 | 360 | 100 | 84 | -16 | 5320 | 5320 | 4468.8 | 5481.2519 | 0.84 | 0.81529 | TRUE | TRUE | TRUE | 45 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144099 | HCSWB1Z1110 | B1 Z1 :Fix MEP first fix in core wall | 25907 | 2012-12-17 08:00 | 2012-12-17 16:00 | 1 | 360 | 100 | 100 | 0 | 1581 | 1581 | 1581 | 1950.004 | 1 | 0.81077 | TRUE | FALSE | FALSE | 45 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144100 | HCSWB1Z1120 | B1 Z1 :Close shutter for core wall | 25907 | 2012-12-18 08:00 | 2012-12-20 16:00 | 2 | 360 | 100 | 100 | 0 | 3738 | 3738 | 3738 | 3821.8611 | 1 | 0.97806 | FALSE | FALSE | FALSE | 45 | FALSE | 0 | Green | Continue normal monitoring.
144101 | HCSWB1Z1130 | B1 Z1 :Cast concrete for core wall | 25907 | 2012-12-22 08:00 | 2012-12-22 16:00 | 1 | 360 | 100 | 95 | -5 | 1240 | 1240 | 1178 | 1326.474 | 0.95 | 0.88807 | TRUE | FALSE | FALSE | 45 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144102 | HCSWB1Z1140 | B1 Z1 :De-shutter core wall formwork | 25907 | 2012-12-23 08:00 | 2012-12-24 16:00 | 1 | 360 | 100 | 98 | -2 | 1997 | 1997 | 1957.06 | 2123.4112 | 0.98 | 0.92166 | FALSE | FALSE | FALSE | 45 | FALSE | 0 | Green | Continue normal monitoring.
144103 | HCSWB1Z1150 | B1 Z1 :Fix Steel Rebar for columns | 25872 | 2012-12-05 08:00 | 2012-12-08 16:00 | 3 | 448 | 100 | 83 | -17 | 1848 | 1848 | 1533.84 | 2041.4943 | 0.83 | 0.75133 | TRUE | TRUE | TRUE | 56 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144104 | HCSWB1Z1160 | B1 Z1 :Erect columns formwork | 25872 | 2012-12-06 08:00 | 2012-12-09 16:00 | 3 | 448 | 100 | 82 | -18 | 3870 | 3870 | 3173.4 | 4447.7644 | 0.82 | 0.71348 | TRUE | TRUE | TRUE | 56 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144105 | HCSWB1Z1170 | B1 Z1 :Cast concrete for columns | 25872 | 2012-12-08 08:00 | 2012-12-10 16:00 | 2 | 448 | 100 | 96 | -4 | 3300 | 3300 | 3168 | 3102.0553 | 0.96 | 1.0213 | FALSE | FALSE | FALSE | 56 | FALSE | 0 | Green | Continue normal monitoring.
144106 | HCSWB1Z1180 | B1 Z1 :De-shutter columns formwork | 25872 | 2012-12-09 08:00 | 2012-12-11 16:00 | 2 | 448 | 100 | 96 | -4 | 3832 | 3832 | 3678.72 | 4067.6288 | 0.96 | 0.90439 | FALSE | FALSE | FALSE | 56 | FALSE | 0 | Green | Continue normal monitoring.
144107 | HCSWB1Z1190 | B1 Z1 :Erect slab formwork and proping | 26024 | 2012-12-29 08:00 | 2013-01-07 16:00 | 9 | 312 | 100 | 91 | -9 | 13608 | 13608 | 12383.28 | 16062.4353 | 0.91 | 0.77095 | TRUE | FALSE | FALSE | 39 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144108 | HCSWB1Z1200 | B1 Z1 :Fix steel rebar for slab | 26024 | 2013-01-08 08:00 | 2013-01-10 16:00 | 2 | 312 | 100 | 100 | 0 | 3162 | 3162 | 3162 | 3273.4475 | 1 | 0.96595 | FALSE | FALSE | FALSE | 39 | FALSE | 0 | Green | Continue normal monitoring.
144109 | HCSWB1Z1210 | B1 Z1 :Fix MEP first Fix for slab | 26024 | 2013-01-12 08:00 | 2013-01-13 16:00 | 1 | 312 | 100 | 100 | 0 | 1133 | 1133 | 1133 | 1089.247 | 1 | 1.0402 | FALSE | FALSE | FALSE | 39 | FALSE | 0 | Green | Continue normal monitoring.
144110 | HCSWB1Z1220 | B1 Z1 :Fix side shutters and casting guides for slab | 26024 | 2013-01-13 08:00 | 2013-01-14 16:00 | 1 | 312 | 100 | 100 | 0 | 1012 | 1012 | 1012 | 1125.2262 | 1 | 0.89937 | TRUE | FALSE | FALSE | 39 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144111 | HCSWB1Z1230 | B1 Z1 :Cast concrete for slab | 26024 | 2013-01-15 08:00 | 2013-01-15 16:00 | 1 | 312 | 100 | 93 | -7 | 1301 | 1301 | 1209.93 | 1534.5386 | 0.93 | 0.78847 | TRUE | FALSE | FALSE | 39 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144112 | HCSWB1Z1240 | B1 Z1 :Cure and De-shutter slab formwork | 26024 | 2013-01-15 16:00 | 2013-01-29 16:00 | 14 | 377 | 100 | 100 | 0 | 22666 | 22666 | 22666 | 19838.5552 | 1 | 1.1425 | FALSE | FALSE | FALSE | 47.125 | FALSE | 0 | Green | Continue normal monitoring.
144113 | HCSWB1Z2010 | B1 Z2 :Formwork retaining walls shutters - 1st side | 26026 | 2013-01-08 08:00 | 2013-01-16 16:00 | 8 | 216 | 100 | 85 | -15 | 13128 | 13128 | 11158.8 | 15237.8822 | 0.85 | 0.73231 | TRUE | TRUE | TRUE | 27 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144114 | HCSWB1Z2020 | B1 Z2 :Fix steel rebar for reatining walls | 26026 | 2013-01-08 08:00 | 2013-01-16 16:00 | 8 | 216 | 100 | 82 | -18 | 8472 | 8472 | 6947.04 | 9985.6005 | 0.82 | 0.69571 | TRUE | TRUE | TRUE | 27 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144115 | HCSWB1Z2030 | B1 Z2 :Fix MEP first fix in walls | 26026 | 2013-01-09 08:00 | 2013-01-17 16:00 | 8 | 216 | 100 | 100 | 0 | 7896 | 7896 | 7896 | 8169.274 | 1 | 0.96655 | FALSE | FALSE | FALSE | 27 | FALSE | 0 | Green | Continue normal monitoring.
144116 | HCSWB1Z2040 | B1 Z2 :Close shutter for retaining walls | 26026 | 2013-01-10 08:00 | 2013-01-19 16:00 | 9 | 216 | 100 | 88 | -12 | 15840 | 15840 | 13939.2 | 19694.2246 | 0.88 | 0.70778 | TRUE | TRUE | TRUE | 27 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144117 | HCSWB1Z2050 | B1 Z2 :Cast concrete for retaining walls | 26026 | 2013-01-12 08:00 | 2013-01-20 16:00 | 8 | 216 | 100 | 84 | -16 | 11168 | 11168 | 9381.12 | 13007.1835 | 0.84 | 0.72123 | TRUE | TRUE | TRUE | 27 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144118 | HCSWB1Z2060 | B1 Z2 :De-shutter retaining walls | 26026 | 2013-01-13 08:00 | 2013-01-21 16:00 | 8 | 216 | 100 | 100 | 0 | 14360 | 14360 | 14360 | 16649.9178 | 1 | 0.86247 | TRUE | FALSE | FALSE | 27 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144119 | HCSWB1Z2070 | B1 Z2 :Apply water proofing membrane behind Basement Walls | 26026 | 2013-01-19 08:00 | 2013-01-28 16:00 | 9 | 400 | 100 | 100 | 0 | 15408 | 15408 | 15408 | 17705.8787 | 1 | 0.87022 | TRUE | FALSE | FALSE | 50 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144120 | HCSWB1Z2080 | B1 Z2 :Apply Protection for Basement Walls | 26026 | 2013-01-21 08:00 | 2013-01-30 16:00 | 9 | 400 | 100 | 96 | -4 | 10827 | 10827 | 10393.92 | 9855.2036 | 0.96 | 1.0547 | FALSE | FALSE | FALSE | 50 | FALSE | 0 | Green | Continue normal monitoring.
144121 | HCSWB1Z2150 | B1 Z2 :Fix Steel Rebar for columns | 26027 | 2013-01-08 08:00 | 2013-01-10 16:00 | 2 | 264 | 100 | 93 | -7 | 3940 | 3940 | 3664.2 | 3691.3559 | 0.93 | 0.99264 | FALSE | FALSE | FALSE | 33 | FALSE | 0 | Green | Continue normal monitoring.
144122 | HCSWB1Z2160 | B1 Z2 :Erect columns formwork | 26027 | 2013-01-09 08:00 | 2013-01-12 16:00 | 3 | 264 | 100 | 100 | 0 | 3240 | 3240 | 3240 | 3355.3312 | 1 | 0.96563 | FALSE | FALSE | FALSE | 33 | FALSE | 0 | Green | Continue normal monitoring.
144123 | HCSWB1Z2170 | B1 Z2 :Cast concrete for columns | 26027 | 2013-01-10 08:00 | 2013-01-13 16:00 | 3 | 264 | 100 | 100 | 0 | 3867 | 3867 | 3867 | 3695.3119 | 1 | 1.0465 | FALSE | FALSE | FALSE | 33 | FALSE | 0 | Green | Continue normal monitoring.
144124 | HCSWB1Z2180 | B1 Z2 :De-shutter columns formwork | 26027 | 2013-01-12 08:00 | 2013-01-14 16:00 | 2 | 264 | 100 | 82 | -18 | 2720 | 2720 | 2230.4 | 2763.7822 | 0.82 | 0.80701 | TRUE | TRUE | TRUE | 33 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144125 | HCSWB1Z2190 | B1 Z2 :Erect slab formwork and proping | 26028 | 2013-01-22 08:00 | 2013-01-29 16:00 | 7 | 216 | 100 | 100 | 0 | 5222 | 5222 | 5222 | 6294.5238 | 1 | 0.82961 | TRUE | FALSE | FALSE | 27 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144126 | HCSWB1Z2200 | B1 Z2 :Fix steel rebar for slab | 26028 | 2013-01-30 08:00 | 2013-02-02 16:00 | 3 | 216 | 100 | 80 | -20 | 4797 | 4797 | 3837.6 | 5659.1684 | 0.8 | 0.67812 | TRUE | TRUE | TRUE | 27 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144127 | HCSWB1Z2210 | B1 Z2 :Fix MEP first Fix for slab | 26028 | 2013-02-03 08:00 | 2013-02-04 16:00 | 1 | 216 | 100 | 99 | -1 | 653 | 653 | 646.47 | 719.6164 | 0.99 | 0.89835 | TRUE | FALSE | FALSE | 27 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144128 | HCSWB1Z2220 | B1 Z2 :Fix side shutters and casting guides for slab | 26028 | 2013-02-04 08:00 | 2013-02-05 16:00 | 1 | 216 | 100 | 100 | 0 | 1958 | 1958 | 1958 | 2336.3799 | 1 | 0.83805 | TRUE | FALSE | FALSE | 27 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144129 | HCSWB1Z2230 | B1 Z2 :Cast concrete for slab | 26028 | 2013-02-06 08:00 | 2013-02-06 16:00 | 1 | 216 | 100 | 100 | 0 | 1496 | 1496 | 1496 | 1740.6094 | 1 | 0.85947 | TRUE | FALSE | FALSE | 27 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144130 | HCSWB1Z2240 | B1 Z2 :Cure and De-shutter slab formwork | 26028 | 2013-02-06 16:00 | 2013-02-20 16:00 | 14 | 256 | 100 | 100 | 0 | 22526 | 22526 | 22526 | 23012.4258 | 1 | 0.97886 | FALSE | FALSE | FALSE | 32 | FALSE | 0 | Green | Continue normal monitoring.
144131 | HCSWB1Z3010 | B1 Z3 :Formwork retaining walls shutters - 1st side | 26120 | 2012-12-22 08:00 | 2012-12-26 16:00 | 4 | 88 | 100 | 100 | 0 | 4784 | 4784 | 4784 | 4451.1583 | 1 | 1.0748 | FALSE | FALSE | FALSE | 11 | FALSE | 0 | Green | Continue normal monitoring.
144132 | HCSWB1Z3020 | B1 Z3 :Fix steel rebar for reatining walls | 26120 | 2012-12-22 08:00 | 2012-12-26 16:00 | 4 | 88 | 100 | 80 | -20 | 7232 | 7232 | 5785.6 | 7634.6808 | 0.8 | 0.75781 | TRUE | TRUE | TRUE | 11 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144133 | HCSWB1Z3030 | B1 Z3 :Fix MEP first fix in walls | 26120 | 2012-12-23 08:00 | 2012-12-27 16:00 | 4 | 88 | 100 | 82 | -18 | 6972 | 6972 | 5717.04 | 7979.3951 | 0.82 | 0.71648 | TRUE | TRUE | TRUE | 11 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144134 | HCSWB1Z3040 | B1 Z3 :Close shutter for retaining walls | 26120 | 2012-12-24 08:00 | 2012-12-29 16:00 | 5 | 88 | 100 | 97 | -3 | 7960 | 7960 | 7721.2 | 8155.56 | 0.97 | 0.94674 | FALSE | FALSE | FALSE | 11 | FALSE | 0 | Green | Continue normal monitoring.
144135 | HCSWB1Z3050 | B1 Z3 :Cast concrete for retaining walls | 26120 | 2012-12-25 08:00 | 2012-12-30 16:00 | 5 | 88 | 100 | 100 | 0 | 7850 | 7850 | 7850 | 8766.1638 | 1 | 0.89549 | TRUE | FALSE | FALSE | 11 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144136 | HCSWB1Z3060 | B1 Z3 :De-shutter retaining walls | 26120 | 2012-12-26 08:00 | 2012-12-31 16:00 | 5 | 88 | 100 | 89 | -11 | 7540 | 7540 | 6710.6 | 6693.4915 | 0.89 | 1.0026 | FALSE | TRUE | TRUE | 11 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144137 | HCSWB1Z3070 | B1 Z3 :Apply water proofing membrane behind Basement Walls | 26120 | 2012-12-30 08:00 | 2013-01-05 16:00 | 6 | 704 | 100 | 100 | 0 | 3558 | 3558 | 3558 | 4088.8603 | 1 | 0.87017 | TRUE | FALSE | FALSE | 88 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144138 | HCSWB1Z3080 | B1 Z3 :Apply Protection for Basement Walls | 26120 | 2013-01-02 08:00 | 2013-01-07 16:00 | 5 | 704 | 100 | 100 | 0 | 7285 | 7285 | 7285 | 8560.4975 | 1 | 0.851 | TRUE | FALSE | FALSE | 88 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144139 | HCSWB1Z3090 | B1 Z3 :Formwork core wall shutters - 1st side | 25875 | 2012-12-22 08:00 | 2012-12-27 16:00 | 5 | 24 | 100 | 100 | 0 | 7555 | 7555 | 7555 | 8557.814 | 1 | 0.88282 | TRUE | FALSE | FALSE | 3 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144140 | HCSWB1Z3100 | B1 Z3 :Fix steel rebar for core wall | 25875 | 2012-12-29 08:00 | 2013-01-02 16:00 | 4 | 24 | 100 | 82 | -18 | 3808 | 3808 | 3122.56 | 4710.1359 | 0.82 | 0.66294 | TRUE | TRUE | TRUE | 3 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
144141 | HCSWB1Z3110 | B1 Z3 :Fix MEP first fix in core wall | 25875 | 2013-01-03 08:00 | 2013-01-03 16:00 | 1 | 24 | 100 | 87 | -13 | 1727 | 1727 | 1502.49 | 2039.0012 | 0.87 | 0.73688 | TRUE | TRUE | TRUE | 3 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
144142 | HCSWB1Z3120 | B1 Z3 :Close shutter for core wall | 25875 | 2013-01-05 08:00 | 2013-01-07 16:00 | 2 | 24 | 100 | 93 | -7 | 2822 | 2822 | 2624.46 | 3418.1122 | 0.93 | 0.76781 | TRUE | FALSE | FALSE | 3 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144143 | HCSWB1Z3130 | B1 Z3 :Cast concrete for core wall | 25875 | 2013-01-08 08:00 | 2013-01-08 16:00 | 1 | 24 | 100 | 100 | 0 | 717 | 717 | 717 | 877.1982 | 1 | 0.81738 | TRUE | FALSE | FALSE | 3 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144144 | HCSWB1Z3140 | B1 Z3 :De-shutter core wall formwork | 25875 | 2013-01-09 08:00 | 2013-01-10 16:00 | 1 | 24 | 100 | 97 | -3 | 973 | 973 | 943.81 | 1138.9346 | 0.97 | 0.82868 | TRUE | FALSE | FALSE | 3 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144145 | HCSWB1Z3150 | B1 Z3 :Fix Steel Rebar for columns | 25973 | 2012-12-22 08:00 | 2012-12-24 16:00 | 2 | 112 | 100 | 94 | -6 | 1862 | 1862 | 1750.28 | 2084.888 | 0.94 | 0.83951 | TRUE | FALSE | FALSE | 14 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144146 | HCSWB1Z3160 | B1 Z3 :Erect columns formwork | 25973 | 2012-12-23 08:00 | 2012-12-25 16:00 | 2 | 112 | 100 | 100 | 0 | 1680 | 1680 | 1680 | 1431.8429 | 1 | 1.1733 | FALSE | FALSE | FALSE | 14 | FALSE | 0 | Green | Continue normal monitoring.
144147 | HCSWB1Z3170 | B1 Z3 :Cast concrete for columns | 25973 | 2012-12-24 08:00 | 2012-12-26 16:00 | 2 | 112 | 100 | 100 | 0 | 2100 | 2100 | 2100 | 2176.2936 | 1 | 0.96494 | FALSE | FALSE | FALSE | 14 | FALSE | 0 | Green | Continue normal monitoring.
144148 | HCSWB1Z3180 | B1 Z3 :De-shutter columns formwork | 25973 | 2012-12-25 08:00 | 2012-12-27 16:00 | 2 | 112 | 100 | 81 | -19 | 3624 | 3624 | 2935.44 | 3908.3569 | 0.81 | 0.75107 | TRUE | TRUE | TRUE | 14 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144149 | HCSWB1Z3190 | B1 Z3 :Erect slab formwork and proping | 25933 | 2013-01-10 08:00 | 2013-01-17 16:00 | 7 | 16 | 100 | 100 | 0 | 12439 | 12439 | 12439 | 12085.883 | 1 | 1.0292 | FALSE | FALSE | FALSE | 2 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144150 | HCSWB1Z3200 | B1 Z3 :Fix steel rebar for slab | 25933 | 2013-01-19 08:00 | 2013-01-21 16:00 | 2 | 16 | 100 | 100 | 0 | 1712 | 1712 | 1712 | 1673.0379 | 1 | 1.0233 | FALSE | FALSE | FALSE | 2 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144151 | HCSWB1Z3210 | B1 Z3 :Fix MEP first Fix for slab | 25933 | 2013-01-22 08:00 | 2013-01-23 16:00 | 1 | 16 | 100 | 89 | -11 | 522 | 522 | 464.58 | 644.3901 | 0.89 | 0.72096 | TRUE | TRUE | TRUE | 2 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
144152 | HCSWB1Z3220 | B1 Z3 :Fix side shutters and casting guides for slab | 25933 | 2013-01-23 08:00 | 2013-01-26 16:00 | 3 | 16 | 100 | 81 | -19 | 3063 | 3063 | 2481.03 | 3696.0742 | 0.81 | 0.67126 | TRUE | TRUE | TRUE | 2 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
144153 | HCSWB1Z3230 | B1 Z3 :Cast concrete for slab | 25933 | 2013-01-27 08:00 | 2013-01-27 16:00 | 1 | 16 | 100 | 100 | 0 | 1623 | 1623 | 1623 | 1930.837 | 1 | 0.84057 | TRUE | FALSE | FALSE | 2 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144154 | HCSWB1Z3240 | B1 Z3 :Cure and De-shutter slab formwork | 25933 | 2013-01-27 16:00 | 2013-02-10 16:00 | 14 | 881 | 100 | 96 | -4 | 18214 | 18214 | 17485.44 | 18439.9396 | 0.96 | 0.94824 | FALSE | FALSE | FALSE | 110.125 | FALSE | 0 | Green | Continue normal monitoring.
144155 | HCSWB1Z4010 | B1 Z4 :Formwork retaining walls shutters - 1st side | 25944 | 2013-01-10 08:00 | 2013-01-15 16:00 | 5 | 512 | 100 | 87 | -13 | 8515 | 8515 | 7408.05 | 7284.4073 | 0.87 | 1.017 | FALSE | TRUE | TRUE | 64 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144156 | HCSWB1Z4020 | B1 Z4 :Fix steel rebar for reatining walls | 25944 | 2013-01-10 08:00 | 2013-01-15 16:00 | 5 | 512 | 100 | 80 | -20 | 8730 | 8730 | 6984 | 7700.6361 | 0.8 | 0.90694 | FALSE | TRUE | TRUE | 64 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144157 | HCSWB1Z4030 | B1 Z4 :Fix MEP first fix in walls | 25944 | 2013-01-12 08:00 | 2013-01-16 16:00 | 4 | 512 | 100 | 88 | -12 | 5044 | 5044 | 4438.72 | 4917.2874 | 0.88 | 0.90268 | FALSE | TRUE | TRUE | 64 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144158 | HCSWB1Z4040 | B1 Z4 :Close shutter for retaining walls | 25944 | 2013-01-13 08:00 | 2013-01-17 16:00 | 4 | 512 | 100 | 90 | -10 | 3764 | 3764 | 3387.6 | 3223.1025 | 0.9 | 1.051 | FALSE | FALSE | FALSE | 64 | FALSE | 0 | Green | Continue normal monitoring.
144159 | HCSWB1Z4050 | B1 Z4 :Cast concrete for retaining walls | 25944 | 2013-01-14 08:00 | 2013-01-19 16:00 | 5 | 512 | 100 | 100 | 0 | 6340 | 6340 | 6340 | 5432.4918 | 1 | 1.1671 | FALSE | FALSE | FALSE | 64 | FALSE | 0 | Green | Continue normal monitoring.
144160 | HCSWB1Z4060 | B1 Z4 :De-shutter retaining walls | 25944 | 2013-01-15 08:00 | 2013-01-20 16:00 | 5 | 512 | 100 | 95 | -5 | 7575 | 7575 | 7196.25 | 9216.058 | 0.95 | 0.78084 | TRUE | FALSE | FALSE | 64 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144161 | HCSWB1Z4070 | B1 Z4 :Apply water proofing membrane behind Basement Walls | 25944 | 2013-01-19 08:00 | 2013-01-23 16:00 | 4 | 576 | 100 | 86 | -14 | 7392 | 7392 | 6357.12 | 8371.1695 | 0.86 | 0.75941 | TRUE | TRUE | TRUE | 72 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144162 | HCSWB1Z4080 | B1 Z4 :Apply Protection for Basement Walls | 25944 | 2013-01-21 08:00 | 2013-01-27 16:00 | 6 | 576 | 100 | 100 | 0 | 6090 | 6090 | 6090 | 5929.1168 | 1 | 1.0271 | FALSE | FALSE | FALSE | 72 | FALSE | 0 | Green | Continue normal monitoring.
144163 | HCSWB1Z4150 | B1 Z4 :Fix Steel Rebar for columns | 25974 | 2013-01-10 08:00 | 2013-01-13 16:00 | 3 | 536 | 100 | 89 | -11 | 4617 | 4617 | 4109.13 | 4169.418 | 0.89 | 0.98554 | FALSE | TRUE | TRUE | 67 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144164 | HCSWB1Z4160 | B1 Z4 :Erect columns formwork | 25974 | 2013-01-12 08:00 | 2013-01-14 16:00 | 2 | 536 | 100 | 100 | 0 | 2582 | 2582 | 2582 | 2723.1174 | 1 | 0.94818 | FALSE | FALSE | FALSE | 67 | FALSE | 0 | Green | Continue normal monitoring.
144165 | HCSWB1Z4170 | B1 Z4 :Cast concrete for columns | 25974 | 2013-01-13 08:00 | 2013-01-15 16:00 | 2 | 536 | 100 | 100 | 0 | 1670 | 1670 | 1670 | 1423.0712 | 1 | 1.1735 | FALSE | FALSE | FALSE | 67 | FALSE | 0 | Green | Continue normal monitoring.
144166 | HCSWB1Z4180 | B1 Z4 :De-shutter columns formwork | 25974 | 2013-01-14 08:00 | 2013-01-16 16:00 | 2 | 536 | 100 | 82 | -18 | 1514 | 1514 | 1241.48 | 1855.2034 | 0.82 | 0.66919 | TRUE | TRUE | TRUE | 67 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144167 | HCSWB1Z4190 | B1 Z4 :Erect slab formwork and proping | 25917 | 2013-02-14 08:00 | 2013-02-20 16:00 | 6 | 352 | 100 | 97 | -3 | 5976 | 5976 | 5796.72 | 6071.1741 | 0.97 | 0.95479 | FALSE | FALSE | FALSE | 44 | FALSE | 0 | Green | Continue normal monitoring.
144168 | HCSWB1Z4200 | B1 Z4 :Fix steel rebar for slab | 25917 | 2013-02-21 08:00 | 2013-02-24 16:00 | 3 | 352 | 100 | 100 | 0 | 4185 | 4185 | 4185 | 4230.7587 | 1 | 0.98918 | FALSE | FALSE | FALSE | 44 | FALSE | 0 | Green | Continue normal monitoring.
144169 | HCSWB1Z4210 | B1 Z4 :Fix MEP first Fix for slab | 25917 | 2013-02-25 08:00 | 2013-02-26 16:00 | 1 | 352 | 100 | 100 | 0 | 659 | 659 | 659 | 663.1105 | 1 | 0.9938 | FALSE | FALSE | FALSE | 44 | FALSE | 0 | Green | Continue normal monitoring.
144170 | HCSWB1Z4220 | B1 Z4 :Fix side shutters and casting guides for slab | 25917 | 2013-02-26 08:00 | 2013-02-27 16:00 | 1 | 352 | 100 | 92 | -8 | 1998 | 1998 | 1838.16 | 1753.7072 | 0.92 | 1.0482 | FALSE | FALSE | FALSE | 44 | FALSE | 0 | Green | Continue normal monitoring.
144171 | HCSWB1Z4230 | B1 Z4 :Cast concrete for slab | 25917 | 2013-02-28 08:00 | 2013-02-28 16:00 | 1 | 352 | 100 | 100 | 0 | 1351 | 1351 | 1351 | 1493.2993 | 1 | 0.90471 | FALSE | FALSE | FALSE | 44 | FALSE | 0 | Green | Continue normal monitoring.
144172 | HCSWB1Z4240 | B1 Z4 :Cure and De-shutter slab formwork | 25917 | 2013-02-28 16:00 | 2013-03-14 16:00 | 14 | 1227 | 100 | 100 | 0 | 16646 | 16646 | 16646 | 19029.7313 | 1 | 0.87474 | TRUE | FALSE | FALSE | 153.375 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144173 | HCSWB1Z5010 | B1 Z5 :Formwork retaining walls shutters - 1st side | 25914 | 2012-12-31 08:00 | 2013-01-09 16:00 | 9 | 600 | 100 | 86 | -14 | 7911 | 7911 | 6803.46 | 8863.8812 | 0.86 | 0.76755 | TRUE | TRUE | TRUE | 75 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144174 | HCSWB1Z5020 | B1 Z5 :Fix steel rebar for reatining walls | 25914 | 2012-12-31 08:00 | 2013-01-09 16:00 | 9 | 600 | 100 | 100 | 0 | 13104 | 13104 | 13104 | 11864.0235 | 1 | 1.1045 | FALSE | FALSE | FALSE | 75 | FALSE | 0 | Green | Continue normal monitoring.
144175 | HCSWB1Z5030 | B1 Z5 :Fix MEP first fix in walls | 25914 | 2013-01-02 08:00 | 2013-01-10 16:00 | 8 | 600 | 100 | 83 | -17 | 9520 | 9520 | 7901.6 | 10296.2234 | 0.83 | 0.76743 | TRUE | TRUE | TRUE | 75 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144176 | HCSWB1Z5040 | B1 Z5 :Close shutter for retaining walls | 25914 | 2013-01-03 08:00 | 2013-01-12 16:00 | 9 | 600 | 100 | 92 | -8 | 17550 | 17550 | 16146 | 18915.2811 | 0.92 | 0.8536 | TRUE | FALSE | FALSE | 75 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144177 | HCSWB1Z5050 | B1 Z5 :Cast concrete for retaining walls | 25914 | 2013-01-05 08:00 | 2013-01-13 16:00 | 8 | 600 | 100 | 99 | -1 | 14328 | 14328 | 14184.72 | 17155.8359 | 0.99 | 0.82682 | TRUE | FALSE | FALSE | 75 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144178 | HCSWB1Z5060 | B1 Z5 :De-shutter retaining walls | 25914 | 2013-01-06 08:00 | 2013-01-14 16:00 | 8 | 600 | 100 | 80 | -20 | 15520 | 15520 | 12416 | 15545.6245 | 0.8 | 0.79868 | TRUE | TRUE | TRUE | 75 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144179 | HCSWB1Z5070 | B1 Z5 :Apply water proofing membrane behind Basement Walls | 25914 | 2013-01-12 08:00 | 2013-01-20 16:00 | 8 | 640 | 100 | 87 | -13 | 13528 | 13528 | 11769.36 | 13508.9847 | 0.87 | 0.87122 | TRUE | TRUE | TRUE | 80 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144180 | HCSWB1Z5080 | B1 Z5 :Apply Protection for Basement Walls | 25914 | 2013-01-14 08:00 | 2013-01-22 16:00 | 8 | 640 | 100 | 93 | -7 | 12528 | 12528 | 11651.04 | 13748.3628 | 0.93 | 0.84745 | TRUE | FALSE | FALSE | 80 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144181 | HCSWB1Z5090 | B1 Z5 :Formwork core wall shutters - 1st side | 25981 | 2012-12-31 08:00 | 2013-01-07 16:00 | 7 | 560 | 100 | 95 | -5 | 5488 | 5488 | 5213.6 | 6054.5211 | 0.95 | 0.86111 | TRUE | FALSE | FALSE | 70 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144182 | HCSWB1Z5100 | B1 Z5 :Fix steel rebar for core wall | 25981 | 2013-01-08 08:00 | 2013-01-12 16:00 | 4 | 560 | 100 | 93 | -7 | 3584 | 3584 | 3333.12 | 3719.1673 | 0.93 | 0.8962 | TRUE | FALSE | FALSE | 70 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144183 | HCSWB1Z5110 | B1 Z5 :Fix MEP first fix in core wall | 25981 | 2013-01-13 08:00 | 2013-01-13 16:00 | 1 | 560 | 100 | 91 | -9 | 511 | 511 | 465.01 | 524.9113 | 0.91 | 0.88588 | TRUE | FALSE | FALSE | 70 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144184 | HCSWB1Z5120 | B1 Z5 :Close shutter for core wall | 25981 | 2013-01-14 08:00 | 2013-01-16 16:00 | 2 | 560 | 100 | 98 | -2 | 3650 | 3650 | 3577 | 3823.9556 | 0.98 | 0.93542 | FALSE | FALSE | FALSE | 70 | FALSE | 0 | Green | Continue normal monitoring.
144185 | HCSWB1Z5130 | B1 Z5 :Cast concrete for core wall | 25981 | 2013-01-17 08:00 | 2013-01-17 16:00 | 1 | 560 | 100 | 100 | 0 | 1776 | 1776 | 1776 | 2121.2866 | 1 | 0.83723 | TRUE | FALSE | FALSE | 70 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144186 | HCSWB1Z5140 | B1 Z5 :De-shutter core wall formwork | 25981 | 2013-01-19 08:00 | 2013-01-20 16:00 | 1 | 560 | 100 | 94 | -6 | 998 | 998 | 938.12 | 1032.3978 | 0.94 | 0.90868 | FALSE | FALSE | FALSE | 70 | FALSE | 0 | Green | Continue normal monitoring.
144187 | HCSWB1Z5150 | B1 Z5 :Fix Steel Rebar for columns | 25877 | 2012-12-31 08:00 | 2013-01-03 16:00 | 3 | 640 | 100 | 100 | 0 | 3759 | 3759 | 3759 | 4608.4314 | 1 | 0.81568 | TRUE | FALSE | FALSE | 80 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144188 | HCSWB1Z5160 | B1 Z5 :Erect columns formwork | 25877 | 2013-01-02 08:00 | 2013-01-05 16:00 | 3 | 640 | 100 | 81 | -19 | 1602 | 1602 | 1297.62 | 1684.6656 | 0.81 | 0.77025 | TRUE | TRUE | TRUE | 80 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144189 | HCSWB1Z5170 | B1 Z5 :Cast concrete for columns | 25877 | 2013-01-03 08:00 | 2013-01-06 16:00 | 3 | 640 | 100 | 81 | -19 | 3678 | 3678 | 2979.18 | 4522.7641 | 0.81 | 0.65871 | TRUE | TRUE | TRUE | 80 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144190 | HCSWB1Z5180 | B1 Z5 :De-shutter columns formwork | 25877 | 2013-01-05 08:00 | 2013-01-07 16:00 | 2 | 640 | 100 | 100 | 0 | 2696 | 2696 | 2696 | 3189.7259 | 1 | 0.84521 | TRUE | FALSE | FALSE | 80 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144191 | HCSWB1Z5190 | B1 Z5 :Erect slab formwork and proping | 25942 | 2013-01-27 08:00 | 2013-02-02 16:00 | 6 | 520 | 100 | 100 | 0 | 3534 | 3534 | 3534 | 3516.2329 | 1 | 1.0051 | FALSE | FALSE | FALSE | 65 | FALSE | 0 | Green | Continue normal monitoring.
144192 | HCSWB1Z5200 | B1 Z5 :Fix steel rebar for slab | 25942 | 2013-02-03 08:00 | 2013-02-05 16:00 | 2 | 520 | 100 | 100 | 0 | 2550 | 2550 | 2550 | 3048.4142 | 1 | 0.8365 | TRUE | FALSE | FALSE | 65 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144193 | HCSWB1Z5210 | B1 Z5 :Fix MEP first Fix for slab | 25942 | 2013-02-06 08:00 | 2013-02-07 16:00 | 1 | 520 | 100 | 98 | -2 | 1104 | 1104 | 1081.92 | 987.0039 | 0.98 | 1.0962 | FALSE | FALSE | FALSE | 65 | FALSE | 0 | Green | Continue normal monitoring.
144194 | HCSWB1Z5220 | B1 Z5 :Fix side shutters and casting guides for slab | 25942 | 2013-02-07 08:00 | 2013-02-09 16:00 | 2 | 520 | 100 | 100 | 0 | 2938 | 2938 | 2938 | 3584.4154 | 1 | 0.81966 | TRUE | FALSE | FALSE | 65 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144195 | HCSWB1Z5230 | B1 Z5 :Cast concrete for slab | 25942 | 2013-02-10 08:00 | 2013-02-10 16:00 | 1 | 520 | 100 | 100 | 0 | 1521 | 1521 | 1521 | 1677.1419 | 1 | 0.9069 | FALSE | FALSE | FALSE | 65 | FALSE | 0 | Green | Continue normal monitoring.
144196 | HCSWB1Z5240 | B1 Z5 :Cure and De-shutter slab formwork | 25942 | 2013-02-10 16:00 | 2013-02-24 16:00 | 14 | 1681 | 100 | 100 | 0 | 12838 | 12838 | 12838 | 11191.6074 | 1 | 1.1471 | FALSE | FALSE | FALSE | 210.125 | FALSE | 0 | Green | Continue normal monitoring.
144197 | HCSWB1Z6010 | B1 Z6 :B1 Z6 :Formwork retaining walls shutters - 1st side | 25866 | 2013-02-03 08:00 | 2013-02-11 16:00 | 8 | 232 | 100 | 100 | 0 | 4912 | 4912 | 4912 | 5441.0356 | 1 | 0.90277 | FALSE | FALSE | FALSE | 29 | FALSE | 0 | Green | Continue normal monitoring.
144198 | HCSWB1Z6020 | B1 Z6 :B1 Z6 :Fix steel rebar for reatining walls | 25866 | 2013-02-03 08:00 | 2013-02-11 16:00 | 8 | 232 | 100 | 100 | 0 | 8928 | 8928 | 8928 | 11068.0332 | 1 | 0.80665 | TRUE | FALSE | FALSE | 29 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144199 | HCSWB1Z6030 | B1 Z6 :B1 Z6 :Fix MEP first fix in walls | 25866 | 2013-02-04 08:00 | 2013-02-12 16:00 | 8 | 232 | 100 | 100 | 0 | 13752 | 13752 | 13752 | 12073.1594 | 1 | 1.1391 | FALSE | FALSE | FALSE | 29 | FALSE | 0 | Green | Continue normal monitoring.
144200 | HCSWB1Z6040 | B1 Z6 :B1 Z6 :Close shutter for retaining walls | 25866 | 2013-02-05 08:00 | 2013-02-13 16:00 | 8 | 232 | 100 | 100 | 0 | 10600 | 10600 | 10600 | 11361.8759 | 1 | 0.93294 | FALSE | FALSE | FALSE | 29 | FALSE | 0 | Green | Continue normal monitoring.
144201 | HCSWB1Z6050 | B1 Z6 :B1 Z6 :Cast concrete for retaining walls | 25866 | 2013-02-06 08:00 | 2013-02-14 16:00 | 8 | 232 | 100 | 100 | 0 | 12784 | 12784 | 12784 | 14690.3212 | 1 | 0.87023 | TRUE | FALSE | FALSE | 29 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144202 | HCSWB1Z6060 | B1 Z6 :B1 Z6 :De-shutter retaining walls | 25866 | 2013-02-07 08:00 | 2013-02-16 16:00 | 9 | 232 | 100 | 100 | 0 | 8208 | 8208 | 8208 | 9637.041 | 1 | 0.85171 | TRUE | FALSE | FALSE | 29 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144203 | HCSWB1Z6070 | B1 Z6 :B1 Z6 :Apply water proofing membrane behind Basement Walls | 25866 | 2013-02-13 08:00 | 2013-02-21 16:00 | 8 | 424 | 100 | 96 | -4 | 15192 | 15192 | 14584.32 | 15427.9467 | 0.96 | 0.94532 | FALSE | FALSE | FALSE | 53 | FALSE | 0 | Green | Continue normal monitoring.
144204 | HCSWB1Z6080 | B1 Z6 :B1 Z6 :Apply Protection for Basement Walls | 25866 | 2013-02-16 08:00 | 2013-02-24 16:00 | 8 | 424 | 100 | 99 | -1 | 15544 | 15544 | 15388.56 | 14481.826 | 0.99 | 1.0626 | FALSE | FALSE | FALSE | 53 | FALSE | 0 | Green | Continue normal monitoring.
144205 | HCSWB1Z6150 | B1 Z6 :B1 Z6 :Fix Steel Rebar for columns | 25886 | 2013-02-03 08:00 | 2013-02-05 16:00 | 2 | 280 | 100 | 89 | -11 | 2456 | 2456 | 2185.84 | 2129.1971 | 0.89 | 1.0266 | FALSE | TRUE | TRUE | 35 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144206 | HCSWB1Z6160 | B1 Z6 :B1 Z6 :Erect columns formwork | 25886 | 2013-02-04 08:00 | 2013-02-06 16:00 | 2 | 280 | 100 | 85 | -15 | 3600 | 3600 | 3060 | 3894.8057 | 0.85 | 0.78566 | TRUE | TRUE | TRUE | 35 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144207 | HCSWB1Z6170 | B1 Z6 :B1 Z6 :Cast concrete for columns | 25886 | 2013-02-05 08:00 | 2013-02-07 16:00 | 2 | 280 | 100 | 94 | -6 | 3040 | 3040 | 2857.6 | 3134.7399 | 0.94 | 0.91159 | FALSE | FALSE | FALSE | 35 | FALSE | 0 | Green | Continue normal monitoring.
144208 | HCSWB1Z6180 | B1 Z6 :B1 Z6 :De-shutter columns formwork | 25886 | 2013-02-06 08:00 | 2013-02-09 16:00 | 3 | 280 | 100 | 100 | 0 | 3780 | 3780 | 3780 | 4647.5015 | 1 | 0.81334 | TRUE | FALSE | FALSE | 35 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144209 | HCSWB1Z6190 | B1 Z6 :B1 Z6 :Erect slab formwork and proping | 25946 | 2013-02-27 08:00 | 2013-03-10 16:00 | 11 | 128 | 100 | 90 | -10 | 12925 | 12925 | 11632.5 | 11299.5774 | 0.9 | 1.0295 | FALSE | FALSE | FALSE | 16 | FALSE | 0 | Green | Continue normal monitoring.
144210 | HCSWB1Z6200 | B1 Z6 :B1 Z6 :Fix steel rebar for slab | 25946 | 2013-03-11 08:00 | 2013-03-13 16:00 | 2 | 128 | 100 | 100 | 0 | 3834 | 3834 | 3834 | 4310.0223 | 1 | 0.88955 | TRUE | FALSE | FALSE | 16 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144211 | HCSWB1Z6210 | B1 Z6 :B1 Z6 :Fix MEP first Fix for slab | 25946 | 2013-03-14 08:00 | 2013-03-16 16:00 | 2 | 128 | 100 | 84 | -16 | 1912 | 1912 | 1606.08 | 1644.2942 | 0.84 | 0.97676 | FALSE | TRUE | TRUE | 16 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144212 | HCSWB1Z6220 | B1 Z6 :B1 Z6 :Fix side shutters and casting guides for slab | 25946 | 2013-03-16 08:00 | 2013-03-17 16:00 | 1 | 128 | 100 | 80 | -20 | 1419 | 1419 | 1135.2 | 1303.456 | 0.8 | 0.87092 | TRUE | TRUE | TRUE | 16 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144213 | HCSWB1Z6230 | B1 Z6 :B1 Z6 :Cast concrete for slab | 25946 | 2013-03-18 08:00 | 2013-03-18 16:00 | 1 | 128 | 100 | 87 | -13 | 691 | 691 | 601.17 | 712.7192 | 0.87 | 0.84349 | TRUE | TRUE | TRUE | 16 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144214 | HCSWB1Z6240 | B1 Z6 :B1 Z6 :Cure and De-shutter slab formwork | 25946 | 2013-03-18 16:00 | 2013-04-01 16:00 | 14 | 1275 | 100 | 100 | 0 | 17332 | 17332 | 17332 | 17885.7397 | 1 | 0.96904 | FALSE | FALSE | FALSE | 159.375 | FALSE | 0 | Green | Continue normal monitoring.
144215 | HCSWFFZ1070 | FF Z1 :Installation of steel columns and beams | 25885 | 2013-02-13 08:00 | 2013-02-16 16:00 | 3 | 0 | 100 | 100 | 0 | 4866 | 4866 | 4866 | 5470.7475 | 1 | 0.88946 | TRUE | FALSE | FALSE | 0 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144216 | HCSWFFZ1080 | FF Z1 :Steel Deck | 25885 | 2013-02-25 08:00 | 2013-02-27 16:00 | 2 | 0 | 100 | 91 | -9 | 2954 | 2954 | 2688.14 | 3586.4077 | 0.91 | 0.74954 | TRUE | FALSE | FALSE | 0 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144217 | HCSWFFZ1090 | FF Z1 :Casting concrete for slab topping | 25885 | 2013-02-28 08:00 | 2013-02-28 16:00 | 1 | 0 | 100 | 91 | -9 | 1508 | 1508 | 1372.28 | 1667.2642 | 0.91 | 0.82307 | TRUE | FALSE | FALSE | 0 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144218 | HCESCN000 | s/c nomination: MEP subcontractor | 25737 | 2012-06-20 08:00 | 2012-07-23 16:00 | 33 | 0 | 100 | 84 | -16 | 19635 | 19635 | 16493.4 | 24178.8147 | 0.84 | 0.68214 | TRUE | TRUE | TRUE | 0 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
144219 | HCESCN010 | s/c nomination: Steel structure subcontractor | 25737 | 2012-06-05 08:00 | 2012-06-16 16:00 | 11 | 0 | 100 | 86 | -14 | 12782 | 12782 | 10992.52 | 15372.2244 | 0.86 | 0.71509 | TRUE | TRUE | TRUE | 0 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
144220 | HCESCN020 | s/c nomination: Aluminum subcontractor | 25737 | 2012-06-05 08:00 | 2012-06-16 16:00 | 11 | 344 | 100 | 83 | -17 | 18843 | 18843 | 15639.69 | 20422.0419 | 0.83 | 0.76582 | TRUE | TRUE | TRUE | 43 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144221 | H0000 | Start Date | 25701 | 2012-06-04 08:00 | 2012-06-04 16:00 | 1 | 0 | 100 | 85 | -15 | 536 | 536 | 455.6 | 634.365 | 0.85 | 0.7182 | TRUE | TRUE | TRUE | 0 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
144222 | H0010 | Finish Date | 25701 | 2014-07-23 08:00 | 2014-07-23 16:00 | 1 | 0 | 100 | 92 | -8 | 1892 | 1892 | 1740.64 | 2094.5027 | 0.92 | 0.83105 | TRUE | FALSE | FALSE | 0 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144223 | HMMOAZ030 | Prepare site office | 25702 | 2012-06-05 08:00 | 2012-06-21 16:00 | 16 | 0 | 100 | 99 | -1 | 12448 | 12448 | 12323.52 | 10971.9552 | 0.99 | 1.1232 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144224 | HMMOAZ040 | Prepare stores and workshops | 25702 | 2012-06-05 08:00 | 2012-06-21 16:00 | 16 | 296 | 100 | 100 | 0 | 11456 | 11456 | 11456 | 13131.1638 | 1 | 0.87243 | TRUE | FALSE | FALSE | 37 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144225 | HCSWFFZ2000 | Formwork core wall shutters - 1st side | 25955 | 2013-02-20 08:00 | 2013-02-25 16:00 | 5 | 16 | 100 | 94 | -6 | 6830 | 6830 | 6420.2 | 6064.7899 | 0.94 | 1.0586 | FALSE | FALSE | FALSE | 2 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144226 | HCSWFFZ2010 | Fix steel rebar for core wall | 25955 | 2013-02-26 08:00 | 2013-02-27 16:00 | 1 | 16 | 100 | 82 | -18 | 1372 | 1372 | 1125.04 | 1492.2326 | 0.82 | 0.75393 | TRUE | TRUE | TRUE | 2 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
144227 | HCSWFFZ2020 | Fix MEP first fix in core wall | 25955 | 2013-02-28 08:00 | 2013-02-28 16:00 | 1 | 16 | 100 | 100 | 0 | 1796 | 1796 | 1796 | 2031.3767 | 1 | 0.88413 | TRUE | FALSE | FALSE | 2 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144228 | HCSWFFZ2030 | Close shutter for core wall | 25955 | 2013-03-02 08:00 | 2013-03-03 16:00 | 1 | 16 | 100 | 87 | -13 | 561 | 561 | 488.07 | 491.7788 | 0.87 | 0.99246 | FALSE | TRUE | TRUE | 2 | TRUE | 4 | Orange | Develop recovery plan and review schedule and cost exposure.
144229 | HCSWFFZ2040 | Cast concrete for core wall | 25955 | 2013-03-04 08:00 | 2013-03-04 16:00 | 1 | 16 | 100 | 99 | -1 | 1095 | 1095 | 1084.05 | 1031.8381 | 0.99 | 1.0506 | FALSE | FALSE | FALSE | 2 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144230 | HCSWFFZ2050 | De-shutter core wall formwork | 25955 | 2013-03-05 08:00 | 2013-03-05 16:00 | 1 | 256 | 100 | 95 | -5 | 1228 | 1228 | 1166.6 | 1493.5782 | 0.95 | 0.78108 | TRUE | FALSE | FALSE | 32 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144231 | HCSWFFZ2060 | Provision & Installation of steel embedded plates | 25895 | 2013-02-28 08:00 | 2013-02-28 16:00 | 1 | 16 | 100 | 92 | -8 | 1865 | 1865 | 1715.8 | 2045.0206 | 0.92 | 0.83901 | TRUE | FALSE | FALSE | 2 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144232 | HCSWFFZ2070 | Installation of steel columns and beams | 25895 | 2013-04-20 08:00 | 2013-04-22 16:00 | 2 | 0 | 100 | 97 | -3 | 1792 | 1792 | 1738.24 | 1699.7378 | 0.97 | 1.0227 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144233 | HCSWFFZ2080 | Steel Deck | 25895 | 2013-04-23 08:00 | 2013-04-24 16:00 | 1 | 0 | 100 | 100 | 0 | 1198 | 1198 | 1198 | 1349.2737 | 1 | 0.88789 | TRUE | FALSE | FALSE | 0 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144234 | HCSWFFZ2090 | Casting concrete for slab topping | 25895 | 2013-04-25 08:00 | 2013-04-25 16:00 | 1 | 0 | 100 | 89 | -11 | 1542 | 1542 | 1372.38 | 1678.7917 | 0.89 | 0.81748 | TRUE | TRUE | TRUE | 0 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
144235 | HCSWFFZ3000 | Formwork core wall shutters - 1st side | 25958 | 2013-04-02 08:00 | 2013-04-07 16:00 | 5 | 128 | 100 | 100 | 0 | 3380 | 3380 | 3380 | 3551.1303 | 1 | 0.95181 | FALSE | FALSE | FALSE | 16 | FALSE | 0 | Green | Continue normal monitoring.
144236 | HCSWFFZ3010 | Fix steel rebar for core wall | 25958 | 2013-04-08 08:00 | 2013-04-09 16:00 | 1 | 128 | 100 | 98 | -2 | 895 | 895 | 877.1 | 1110.2249 | 0.98 | 0.79002 | TRUE | FALSE | FALSE | 16 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144237 | HCSWFFZ3020 | Fix MEP first fix in core wall | 25958 | 2013-04-10 08:00 | 2013-04-10 16:00 | 1 | 128 | 100 | 96 | -4 | 944 | 944 | 906.24 | 1060.4721 | 0.96 | 0.85456 | TRUE | FALSE | FALSE | 16 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144238 | HCSWFFZ3030 | Close shutter for core wall | 25958 | 2013-04-11 08:00 | 2013-04-13 16:00 | 2 | 128 | 100 | 100 | 0 | 3512 | 3512 | 3512 | 3512.6197 | 1 | 0.99982 | FALSE | FALSE | FALSE | 16 | FALSE | 0 | Green | Continue normal monitoring.
144239 | HCSWFFZ3040 | Cast concrete for core wall | 25958 | 2013-04-14 08:00 | 2013-04-14 16:00 | 1 | 128 | 100 | 100 | 0 | 575 | 575 | 575 | 672.7669 | 1 | 0.85468 | TRUE | FALSE | FALSE | 16 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144240 | HCSWFFZ3050 | De-shutter core wall formwork | 25958 | 2013-04-15 08:00 | 2013-04-15 16:00 | 1 | 344 | 100 | 98 | -2 | 764 | 764 | 748.72 | 919.7287 | 0.98 | 0.81407 | TRUE | FALSE | FALSE | 43 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144241 | HCSWFFZ3060 | Provision & Installation of steel embedded plates | 25898 | 2013-04-10 08:00 | 2013-04-10 16:00 | 1 | 128 | 100 | 100 | 0 | 954 | 954 | 954 | 858.6842 | 1 | 1.111 | FALSE | FALSE | FALSE | 16 | FALSE | 0 | Green | Continue normal monitoring.
144242 | HCSWFFZ3070 | Installation of steel columns and beams | 25898 | 2013-06-06 08:00 | 2013-06-10 16:00 | 4 | 0 | 100 | 100 | 0 | 4868 | 4868 | 4868 | 4528.3168 | 1 | 1.075 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144243 | HCSWFFZ3080 | Steel Deck | 25898 | 2013-06-11 08:00 | 2013-06-13 16:00 | 2 | 0 | 100 | 100 | 0 | 2468 | 2468 | 2468 | 2311.2593 | 1 | 1.0678 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144244 | HCSWFFZ3090 | Casting concrete for slab topping | 25898 | 2013-06-15 08:00 | 2013-06-15 16:00 | 1 | 0 | 100 | 100 | 0 | 1907 | 1907 | 1907 | 2148.2064 | 1 | 0.88772 | TRUE | FALSE | FALSE | 0 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144245 | HCSW2FZ1070 | Installation of steel columns and beams | 25884 | 2013-03-02 08:00 | 2013-03-04 16:00 | 2 | 0 | 100 | 84 | -16 | 2700 | 2700 | 2268 | 2946.2827 | 0.84 | 0.76978 | TRUE | TRUE | TRUE | 0 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
144246 | HCSW2FZ1080 | Steel Deck | 25884 | 2013-03-05 08:00 | 2013-03-06 16:00 | 1 | 0 | 100 | 100 | 0 | 1890 | 1890 | 1890 | 2074.4576 | 1 | 0.91108 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144247 | HCSW2FZ1090 | Casting concrete for slab topping | 25884 | 2013-03-07 08:00 | 2013-03-07 16:00 | 1 | 0 | 100 | 100 | 0 | 643 | 643 | 643 | 788.5169 | 1 | 0.81545 | TRUE | FALSE | FALSE | 0 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144248 | HCSW2FZ2000 | Formwork core wall shutters - 1st side | 25964 | 2013-03-05 08:00 | 2013-03-10 16:00 | 5 | 16 | 100 | 100 | 0 | 6920 | 6920 | 6920 | 8029.7231 | 1 | 0.8618 | TRUE | FALSE | FALSE | 2 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144249 | HCSW2FZ2010 | Fix steel rebar for core wall | 25964 | 2013-03-11 08:00 | 2013-03-12 16:00 | 1 | 16 | 100 | 100 | 0 | 1592 | 1592 | 1592 | 1434.6702 | 1 | 1.1097 | FALSE | FALSE | FALSE | 2 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144250 | HCSW2FZ2020 | Fix MEP first fix in core wall | 25964 | 2013-03-13 08:00 | 2013-03-13 16:00 | 1 | 16 | 100 | 100 | 0 | 1622 | 1622 | 1622 | 1604.1626 | 1 | 1.0111 | FALSE | FALSE | FALSE | 2 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144251 | HCSW2FZ2030 | Close shutter for core wall | 25964 | 2013-03-14 08:00 | 2013-03-16 16:00 | 2 | 16 | 100 | 88 | -12 | 1790 | 1790 | 1575.2 | 1833.2419 | 0.88 | 0.85924 | TRUE | TRUE | TRUE | 2 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
144252 | HCSW2FZ2040 | Cast concrete for core wall | 25964 | 2013-03-17 08:00 | 2013-03-17 16:00 | 1 | 16 | 100 | 91 | -9 | 1548 | 1548 | 1408.68 | 1560.9794 | 0.91 | 0.90243 | FALSE | FALSE | FALSE | 2 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144253 | HCSW2FZ2050 | De-shutter core wall formwork | 25964 | 2013-03-18 08:00 | 2013-03-18 16:00 | 1 | 216 | 100 | 100 | 0 | 1447 | 1447 | 1447 | 1617.3458 | 1 | 0.89468 | TRUE | FALSE | FALSE | 27 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144254 | HCSW2FZ2060 | Provision & Installation of steel embedded plates | 25882 | 2013-03-13 08:00 | 2013-03-13 16:00 | 1 | 16 | 100 | 80 | -20 | 1390 | 1390 | 1112 | 1677.3926 | 0.8 | 0.66293 | TRUE | TRUE | TRUE | 2 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
144255 | HCSW2FZ2070 | Installation of steel columns and beams | 25882 | 2013-04-27 08:00 | 2013-04-29 16:00 | 2 | 0 | 100 | 100 | 0 | 3984 | 3984 | 3984 | 3874.1236 | 1 | 1.0284 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144256 | HCSW2FZ2080 | Steel Deck | 25882 | 2013-04-30 08:00 | 2013-05-02 16:00 | 2 | 0 | 100 | 100 | 0 | 3348 | 3348 | 3348 | 3584.8739 | 1 | 0.93392 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144257 | HCSW2FZ2090 | Casting concrete for slab topping | 25882 | 2013-05-04 08:00 | 2013-05-04 16:00 | 1 | 0 | 100 | 80 | -20 | 1667 | 1667 | 1333.6 | 1943.3282 | 0.8 | 0.68625 | TRUE | TRUE | TRUE | 0 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
144258 | HCSW2FZ3000 | Formwork core wall shutters - 1st side | 25967 | 2013-04-15 08:00 | 2013-04-20 16:00 | 5 | 128 | 100 | 94 | -6 | 5340 | 5340 | 5019.6 | 5428.0418 | 0.94 | 0.92475 | FALSE | FALSE | FALSE | 16 | FALSE | 0 | Green | Continue normal monitoring.
144259 | HCSW2FZ3010 | Fix steel rebar for core wall | 25967 | 2013-04-21 08:00 | 2013-04-22 16:00 | 1 | 128 | 100 | 81 | -19 | 1562 | 1562 | 1265.22 | 1432.7402 | 0.81 | 0.88308 | TRUE | TRUE | TRUE | 16 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144260 | HCSW2FZ3020 | Fix MEP first fix in core wall | 25967 | 2013-04-23 08:00 | 2013-04-23 16:00 | 1 | 128 | 100 | 100 | 0 | 608 | 608 | 608 | 632.3081 | 1 | 0.96156 | FALSE | FALSE | FALSE | 16 | FALSE | 0 | Green | Continue normal monitoring.
144261 | HCSW2FZ3030 | Close shutter for core wall | 25967 | 2013-04-24 08:00 | 2013-04-25 16:00 | 1 | 128 | 100 | 100 | 0 | 1565 | 1565 | 1565 | 1364.8193 | 1 | 1.1467 | FALSE | FALSE | FALSE | 16 | FALSE | 0 | Green | Continue normal monitoring.
144262 | HCSW2FZ3040 | Cast concrete for core wall | 25967 | 2013-04-27 08:00 | 2013-04-27 16:00 | 1 | 128 | 100 | 95 | -5 | 1709 | 1709 | 1623.55 | 2096.8633 | 0.95 | 0.77428 | TRUE | FALSE | FALSE | 16 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144263 | HCSW2FZ3050 | De-shutter core wall formwork | 25967 | 2013-04-28 08:00 | 2013-04-28 16:00 | 1 | 248 | 100 | 100 | 0 | 1434 | 1434 | 1434 | 1261.8174 | 1 | 1.1365 | FALSE | FALSE | FALSE | 31 | FALSE | 0 | Green | Continue normal monitoring.
144264 | HCSW2FZ3060 | Provision & Installation of steel embedded plates | 25968 | 2013-04-23 08:00 | 2013-04-23 16:00 | 1 | 128 | 100 | 87 | -13 | 897 | 897 | 780.39 | 919.7683 | 0.87 | 0.84846 | TRUE | TRUE | TRUE | 16 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144265 | HCSW2FZ3070 | Installation of steel columns and beams | 25968 | 2013-06-16 08:00 | 2013-06-19 16:00 | 3 | 0 | 100 | 92 | -8 | 5238 | 5238 | 4818.96 | 5562.5072 | 0.92 | 0.86633 | TRUE | FALSE | FALSE | 0 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144266 | HCSW2FZ3080 | Steel Deck | 25968 | 2013-06-20 08:00 | 2013-06-23 16:00 | 3 | 0 | 100 | 100 | 0 | 3399 | 3399 | 3399 | 4228.7691 | 1 | 0.80378 | TRUE | FALSE | FALSE | 0 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144267 | HCSW2FZ3090 | Casting concrete for slab topping | 25968 | 2013-06-24 08:00 | 2013-06-24 16:00 | 1 | 0 | 100 | 80 | -20 | 1656 | 1656 | 1324.8 | 1517.5729 | 0.8 | 0.87297 | TRUE | TRUE | TRUE | 0 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
144268 | HCSW3FZ1070 | Installation of steel columns and beams | 25869 | 2013-03-09 08:00 | 2013-03-11 16:00 | 2 | 0 | 100 | 95 | -5 | 3372 | 3372 | 3203.4 | 3020.5452 | 0.95 | 1.0605 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144269 | HCSW3FZ1080 | Steel Deck | 25869 | 2013-03-12 08:00 | 2013-03-13 16:00 | 1 | 0 | 100 | 100 | 0 | 1738 | 1738 | 1738 | 1483.3525 | 1 | 1.1717 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144270 | HCSW3FZ1090 | Casting concrete for slab topping | 25869 | 2013-03-14 08:00 | 2013-03-14 16:00 | 1 | 0 | 100 | 86 | -14 | 1232 | 1232 | 1059.52 | 1123.8656 | 0.86 | 0.94275 | FALSE | TRUE | TRUE | 0 | TRUE | 4 | Orange | Develop recovery plan and review schedule and cost exposure.
144271 | HCSW3FZ2000 | Formwork core wall shutters - 1st side | 26054 | 2013-03-18 08:00 | 2013-03-23 16:00 | 5 | 16 | 100 | 100 | 0 | 3670 | 3670 | 3670 | 3423.7767 | 1 | 1.0719 | FALSE | FALSE | FALSE | 2 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144272 | HCSW3FZ2010 | Fix steel rebar for core wall | 26054 | 2013-03-24 08:00 | 2013-03-25 16:00 | 1 | 16 | 100 | 84 | -16 | 1157 | 1157 | 971.88 | 1275.2829 | 0.84 | 0.76209 | TRUE | TRUE | TRUE | 2 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
144273 | HCSW3FZ2020 | Fix MEP first fix in core wall | 26054 | 2013-03-26 08:00 | 2013-03-26 16:00 | 1 | 16 | 100 | 100 | 0 | 1250 | 1250 | 1250 | 1172.3534 | 1 | 1.0662 | FALSE | FALSE | FALSE | 2 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144274 | HCSW3FZ2030 | Close shutter for core wall | 26054 | 2013-03-27 08:00 | 2013-03-28 16:00 | 1 | 16 | 100 | 100 | 0 | 1087 | 1087 | 1087 | 932.8725 | 1 | 1.1652 | FALSE | FALSE | FALSE | 2 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144275 | HCSW3FZ2040 | Cast concrete for core wall | 26054 | 2013-03-30 08:00 | 2013-03-30 16:00 | 1 | 16 | 100 | 100 | 0 | 1532 | 1532 | 1532 | 1808.7517 | 1 | 0.84699 | TRUE | FALSE | FALSE | 2 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144276 | HCSW3FZ2050 | De-shutter core wall formwork | 26054 | 2013-03-31 08:00 | 2013-03-31 16:00 | 1 | 176 | 100 | 82 | -18 | 1597 | 1597 | 1309.54 | 1590.9925 | 0.82 | 0.8231 | TRUE | TRUE | TRUE | 22 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144277 | HCSW3FZ2060 | Provision & Installation of steel embedded plates | 25913 | 2013-03-26 08:00 | 2013-03-26 16:00 | 1 | 16 | 100 | 91 | -9 | 1453 | 1453 | 1322.23 | 1440.6185 | 0.91 | 0.91782 | FALSE | FALSE | FALSE | 2 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144278 | HCSW3FZ2070 | Installation of steel columns and beams | 25913 | 2013-05-05 08:00 | 2013-05-07 16:00 | 2 | 0 | 100 | 100 | 0 | 1982 | 1982 | 1982 | 1924.5054 | 1 | 1.0299 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144279 | HCSW3FZ2080 | Steel Deck | 25913 | 2013-05-08 08:00 | 2013-05-09 16:00 | 1 | 0 | 100 | 95 | -5 | 1412 | 1412 | 1341.4 | 1751.0908 | 0.95 | 0.76604 | TRUE | FALSE | FALSE | 0 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144280 | HCSW3FZ2090 | Casting concrete for slab topping | 25913 | 2013-05-11 08:00 | 2013-05-11 16:00 | 1 | 0 | 100 | 98 | -2 | 1776 | 1776 | 1740.48 | 1630.45 | 0.98 | 1.0675 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144281 | HCSW3FZ3000 | Formwork core wall shutters - 1st side | 25976 | 2013-04-28 08:00 | 2013-05-04 16:00 | 6 | 128 | 100 | 84 | -16 | 10518 | 10518 | 8835.12 | 12719.3672 | 0.84 | 0.69462 | TRUE | TRUE | TRUE | 16 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144282 | HCSW3FZ3010 | Fix steel rebar for core wall | 25976 | 2013-05-05 08:00 | 2013-05-06 16:00 | 1 | 128 | 100 | 100 | 0 | 1697 | 1697 | 1697 | 1969.7441 | 1 | 0.86153 | TRUE | FALSE | FALSE | 16 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144283 | HCSW3FZ3020 | Fix MEP first fix in core wall | 25976 | 2013-05-07 08:00 | 2013-05-07 16:00 | 1 | 128 | 100 | 100 | 0 | 1691 | 1691 | 1691 | 1489.081 | 1 | 1.1356 | FALSE | FALSE | FALSE | 16 | FALSE | 0 | Green | Continue normal monitoring.
144284 | HCSW3FZ3030 | Close shutter for core wall | 25976 | 2013-05-08 08:00 | 2013-05-09 16:00 | 1 | 128 | 100 | 100 | 0 | 669 | 669 | 669 | 832.6987 | 1 | 0.80341 | TRUE | FALSE | FALSE | 16 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144285 | HCSW3FZ3040 | Cast concrete for core wall | 25976 | 2013-05-11 08:00 | 2013-05-11 16:00 | 1 | 128 | 100 | 93 | -7 | 1916 | 1916 | 1781.88 | 1836.5749 | 0.93 | 0.97022 | FALSE | FALSE | FALSE | 16 | FALSE | 0 | Green | Continue normal monitoring.
144286 | HCSW3FZ3050 | De-shutter core wall formwork | 25976 | 2013-05-12 08:00 | 2013-05-12 16:00 | 1 | 224 | 100 | 100 | 0 | 1445 | 1445 | 1445 | 1285.2309 | 1 | 1.1243 | FALSE | FALSE | FALSE | 28 | FALSE | 0 | Green | Continue normal monitoring.
144287 | HCSW3FZ3060 | Provision & Installation of steel embedded plates | 25977 | 2013-05-07 08:00 | 2013-05-07 16:00 | 1 | 128 | 100 | 84 | -16 | 1294 | 1294 | 1086.96 | 1529.153 | 0.84 | 0.71082 | TRUE | TRUE | TRUE | 16 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144288 | HCSW3FZ3070 | Installation of steel columns and beams | 25977 | 2013-06-25 08:00 | 2013-06-29 16:00 | 4 | 0 | 100 | 94 | -6 | 4532 | 4532 | 4260.08 | 5133.2614 | 0.94 | 0.8299 | TRUE | FALSE | FALSE | 0 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144289 | HCSW3FZ3080 | Steel Deck | 25977 | 2013-06-30 08:00 | 2013-07-02 16:00 | 2 | 0 | 100 | 96 | -4 | 3434 | 3434 | 3296.64 | 3766.7118 | 0.96 | 0.8752 | TRUE | FALSE | FALSE | 0 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144290 | HCSW3FZ3090 | Casting concrete for slab topping | 25977 | 2013-07-03 08:00 | 2013-07-03 16:00 | 1 | 0 | 100 | 100 | 0 | 528 | 528 | 528 | 481.7432 | 1 | 1.096 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144291 | HCSW4FZ1070 | Installation of steel columns and beams | 25980 | 2013-03-16 08:00 | 2013-03-18 16:00 | 2 | 0 | 100 | 93 | -7 | 3376 | 3376 | 3139.68 | 3515.7612 | 0.93 | 0.89303 | TRUE | FALSE | FALSE | 0 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144292 | HCSW4FZ1080 | Steel Deck | 25980 | 2013-03-19 08:00 | 2013-03-20 16:00 | 1 | 0 | 100 | 100 | 0 | 1945 | 1945 | 1945 | 2260.5226 | 1 | 0.86042 | TRUE | FALSE | FALSE | 0 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144293 | HCSW4FZ1090 | Casting concrete for slab topping | 25980 | 2013-03-21 08:00 | 2013-03-21 16:00 | 1 | 0 | 100 | 99 | -1 | 838 | 838 | 829.62 | 814.0747 | 0.99 | 1.0191 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144294 | HCSW4FZ2000 | Formwork core wall shutters - 1st side | 25921 | 2013-03-31 08:00 | 2013-04-04 16:00 | 4 | 16 | 100 | 84 | -16 | 7552 | 7552 | 6343.68 | 7360.7526 | 0.84 | 0.86182 | TRUE | TRUE | TRUE | 2 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
144295 | HCSW4FZ2010 | Fix steel rebar for core wall | 25921 | 2013-04-06 08:00 | 2013-04-07 16:00 | 1 | 16 | 100 | 91 | -9 | 1865 | 1865 | 1697.15 | 1587.5931 | 0.91 | 1.069 | FALSE | FALSE | FALSE | 2 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144296 | HCSW4FZ2020 | Fix MEP first fix in core wall | 25921 | 2013-04-08 08:00 | 2013-04-08 16:00 | 1 | 16 | 100 | 95 | -5 | 999 | 999 | 949.05 | 918.7777 | 0.95 | 1.0329 | FALSE | FALSE | FALSE | 2 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144297 | HCSW4FZ2030 | Close shutter for core wall | 25921 | 2013-04-09 08:00 | 2013-04-10 16:00 | 1 | 16 | 100 | 100 | 0 | 1010 | 1010 | 1010 | 1212.1639 | 1 | 0.83322 | TRUE | FALSE | FALSE | 2 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144298 | HCSW4FZ2040 | Cast concrete for core wall | 25921 | 2013-04-11 08:00 | 2013-04-11 16:00 | 1 | 16 | 100 | 100 | 0 | 1850 | 1850 | 1850 | 1899.3924 | 1 | 0.974 | FALSE | FALSE | FALSE | 2 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144299 | HCSW4FZ2050 | De-shutter core wall formwork | 25921 | 2013-04-13 08:00 | 2013-04-13 16:00 | 1 | 136 | 100 | 95 | -5 | 716 | 716 | 680.2 | 890.4848 | 0.95 | 0.76385 | TRUE | FALSE | FALSE | 17 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144300 | HCSW4FZ2060 | Provision & Installation of steel embedded plates | 25881 | 2013-04-08 08:00 | 2013-04-08 16:00 | 1 | 16 | 100 | 100 | 0 | 1824 | 1824 | 1824 | 1839.1085 | 1 | 0.99178 | FALSE | FALSE | FALSE | 2 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144301 | HCSW4FZ2070 | Installation of steel columns and beams | 25881 | 2013-05-12 08:00 | 2013-05-14 16:00 | 2 | 0 | 100 | 86 | -14 | 3310 | 3310 | 2846.6 | 3760.4069 | 0.86 | 0.75699 | TRUE | TRUE | TRUE | 0 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
144302 | HCSW4FZ2080 | Steel Deck | 25881 | 2013-05-15 08:00 | 2013-05-16 16:00 | 1 | 0 | 100 | 83 | -17 | 1593 | 1593 | 1322.19 | 1533.6888 | 0.83 | 0.8621 | TRUE | TRUE | TRUE | 0 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
144303 | HCSW4FZ2090 | Casting concrete for slab topping | 25881 | 2013-05-18 08:00 | 2013-05-18 16:00 | 1 | 0 | 100 | 80 | -20 | 1775 | 1775 | 1420 | 1767.0548 | 0.8 | 0.8036 | TRUE | TRUE | TRUE | 0 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
144304 | HCSW4FZ3000 | Formwork core wall shutters - 1st side | 25992 | 2013-05-12 08:00 | 2013-05-16 16:00 | 4 | 128 | 100 | 100 | 0 | 7752 | 7752 | 7752 | 7180.6031 | 1 | 1.0796 | FALSE | FALSE | FALSE | 16 | FALSE | 0 | Green | Continue normal monitoring.
144305 | HCSW4FZ3010 | Fix steel rebar for core wall | 25992 | 2013-05-18 08:00 | 2013-05-19 16:00 | 1 | 128 | 100 | 100 | 0 | 944 | 944 | 944 | 933.4508 | 1 | 1.0113 | FALSE | FALSE | FALSE | 16 | FALSE | 0 | Green | Continue normal monitoring.
144306 | HCSW4FZ3020 | Fix MEP first fix in core wall | 25992 | 2013-05-20 08:00 | 2013-05-20 16:00 | 1 | 128 | 100 | 84 | -16 | 1375 | 1375 | 1155 | 1469.7306 | 0.84 | 0.78586 | TRUE | TRUE | TRUE | 16 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144307 | HCSW4FZ3030 | Close shutter for core wall | 25992 | 2013-05-21 08:00 | 2013-05-22 16:00 | 1 | 128 | 100 | 100 | 0 | 1705 | 1705 | 1705 | 2125.6391 | 1 | 0.80211 | TRUE | FALSE | FALSE | 16 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144308 | HCSW4FZ3040 | Cast concrete for core wall | 25992 | 2013-05-23 08:00 | 2013-05-23 16:00 | 1 | 128 | 100 | 100 | 0 | 666 | 666 | 666 | 743.0433 | 1 | 0.89631 | TRUE | FALSE | FALSE | 16 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144309 | HCSW4FZ3050 | De-shutter core wall formwork | 25992 | 2013-05-26 08:00 | 2013-05-26 16:00 | 1 | 200 | 100 | 89 | -11 | 590 | 590 | 525.1 | 548.522 | 0.89 | 0.9573 | FALSE | TRUE | TRUE | 25 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144310 | HCSW4FZ3060 | Provision & Installation of steel embedded plates | 25993 | 2013-05-20 08:00 | 2013-05-20 16:00 | 1 | 128 | 100 | 100 | 0 | 1213 | 1213 | 1213 | 1052.8653 | 1 | 1.1521 | FALSE | FALSE | FALSE | 16 | FALSE | 0 | Green | Continue normal monitoring.
144311 | HCSW4FZ3070 | Installation of steel columns and beams | 25993 | 2013-07-04 08:00 | 2013-07-08 16:00 | 4 | 0 | 100 | 84 | -16 | 2152 | 2152 | 1807.68 | 1937.9677 | 0.84 | 0.93277 | FALSE | TRUE | TRUE | 0 | TRUE | 4 | Orange | Develop recovery plan and review schedule and cost exposure.
144312 | HCSW4FZ3080 | Steel Deck | 25993 | 2013-07-09 08:00 | 2013-07-11 16:00 | 2 | 0 | 100 | 83 | -17 | 3298 | 3298 | 2737.34 | 3545.4228 | 0.83 | 0.77208 | TRUE | TRUE | TRUE | 0 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
144313 | HCSW4FZ3090 | Casting concrete for slab topping | 25993 | 2013-07-13 08:00 | 2013-07-13 16:00 | 1 | 0 | 100 | 81 | -19 | 1974 | 1974 | 1598.94 | 2282.0706 | 0.81 | 0.70065 | TRUE | TRUE | TRUE | 0 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
144314 | HCSW4FZ4070 | Installation of steel columns and beams | 25925 | 2013-08-07 08:00 | 2013-08-14 16:00 | 7 | 80 | 100 | 99 | -1 | 4704 | 4704 | 4656.96 | 5767.8928 | 0.99 | 0.80739 | TRUE | FALSE | FALSE | 10 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144315 | HCSW4FZ4080 | Steel Deck | 25925 | 2013-08-15 08:00 | 2013-08-19 16:00 | 4 | 80 | 100 | 100 | 0 | 4608 | 4608 | 4608 | 3945.9653 | 1 | 1.1678 | FALSE | FALSE | FALSE | 10 | FALSE | 0 | Green | Continue normal monitoring.
144316 | HCSW4FZ4090 | Casting concrete for slab topping | 25925 | 2013-08-20 08:00 | 2013-08-20 16:00 | 1 | 80 | 100 | 89 | -11 | 1253 | 1253 | 1115.17 | 1327.0574 | 0.89 | 0.84033 | TRUE | TRUE | TRUE | 10 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144317 | HCSW4FZ5070 | Installation of steel columns and beams | 25888 | 2013-08-13 08:00 | 2013-08-15 16:00 | 2 | 136 | 100 | 100 | 0 | 3486 | 3486 | 3486 | 3619.6774 | 1 | 0.96307 | FALSE | FALSE | FALSE | 17 | FALSE | 0 | Green | Continue normal monitoring.
144318 | HCSW4FZ5080 | Steel Deck | 25888 | 2013-08-17 08:00 | 2013-08-18 16:00 | 1 | 136 | 100 | 98 | -2 | 1581 | 1581 | 1549.38 | 1758.7392 | 0.98 | 0.88096 | TRUE | FALSE | FALSE | 17 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144319 | HCSW4FZ5090 | Casting concrete for slab topping | 25888 | 2013-08-19 08:00 | 2013-08-19 16:00 | 1 | 136 | 100 | 100 | 0 | 975 | 975 | 975 | 1046.9858 | 1 | 0.93124 | FALSE | FALSE | FALSE | 17 | FALSE | 0 | Green | Continue normal monitoring.
144320 | HCSW5FZ1070 | Installation of steel columns and beams | 25928 | 2013-03-23 08:00 | 2013-03-25 16:00 | 2 | 0 | 100 | 80 | -20 | 1910 | 1910 | 1528 | 2148.3979 | 0.8 | 0.71123 | TRUE | TRUE | TRUE | 0 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
144321 | HCSW5FZ1080 | Steel Deck | 25928 | 2013-03-26 08:00 | 2013-03-27 16:00 | 1 | 0 | 100 | 100 | 0 | 1328 | 1328 | 1328 | 1478.3735 | 1 | 0.89828 | TRUE | FALSE | FALSE | 0 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144322 | HCSW5FZ1090 | Casting concrete for slab topping | 25928 | 2013-03-28 08:00 | 2013-03-28 16:00 | 1 | 0 | 100 | 84 | -16 | 1394 | 1394 | 1170.96 | 1250.1457 | 0.84 | 0.93666 | FALSE | TRUE | TRUE | 0 | TRUE | 4 | Orange | Develop recovery plan and review schedule and cost exposure.
144323 | HCSW5FZ2000 | Formwork core wall shutters - 1st side | 25893 | 2013-04-13 08:00 | 2013-04-17 16:00 | 4 | 16 | 100 | 92 | -8 | 7536 | 7536 | 6933.12 | 8816.2697 | 0.92 | 0.7864 | TRUE | FALSE | FALSE | 2 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144324 | HCSW5FZ2010 | Fix steel rebar for core wall | 25893 | 2013-04-18 08:00 | 2013-04-20 16:00 | 2 | 16 | 100 | 83 | -17 | 3048 | 3048 | 2529.84 | 2741.0452 | 0.83 | 0.92295 | FALSE | TRUE | TRUE | 2 | TRUE | 4 | Orange | Develop recovery plan and review schedule and cost exposure.
144325 | HCSW5FZ2020 | Fix MEP first fix in core wall | 25893 | 2013-04-21 08:00 | 2013-04-21 16:00 | 1 | 16 | 100 | 95 | -5 | 886 | 886 | 841.7 | 1000.6593 | 0.95 | 0.84115 | TRUE | FALSE | FALSE | 2 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144326 | HCSW5FZ2030 | Close shutter for core wall | 25893 | 2013-04-22 08:00 | 2013-04-23 16:00 | 1 | 16 | 100 | 100 | 0 | 847 | 847 | 847 | 860.9401 | 1 | 0.98381 | FALSE | FALSE | FALSE | 2 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144327 | HCSW5FZ2040 | Cast concrete for core wall | 25893 | 2013-04-24 08:00 | 2013-04-24 16:00 | 1 | 16 | 100 | 95 | -5 | 689 | 689 | 654.55 | 727.2673 | 0.95 | 0.90001 | FALSE | FALSE | FALSE | 2 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144328 | HCSW5FZ2050 | De-shutter core wall formwork | 25893 | 2013-04-25 08:00 | 2013-04-25 16:00 | 1 | 96 | 100 | 100 | 0 | 1004 | 1004 | 1004 | 1216.1645 | 1 | 0.82555 | TRUE | FALSE | FALSE | 12 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144329 | HCSW5FZ2060 | Provision & Installation of steel embedded plates | 25894 | 2013-04-21 08:00 | 2013-04-21 16:00 | 1 | 16 | 100 | 81 | -19 | 1714 | 1714 | 1388.34 | 2067.0043 | 0.81 | 0.67167 | TRUE | TRUE | TRUE | 2 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
144330 | HCSW5FZ2070 | Installation of steel columns and beams | 25894 | 2013-05-19 08:00 | 2013-05-21 16:00 | 2 | 0 | 100 | 96 | -4 | 3784 | 3784 | 3632.64 | 4454.3073 | 0.96 | 0.81553 | TRUE | FALSE | FALSE | 0 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144331 | HCSW5FZ2080 | Steel Deck | 25894 | 2013-05-22 08:00 | 2013-05-23 16:00 | 1 | 0 | 100 | 100 | 0 | 1932 | 1932 | 1932 | 2036.4427 | 1 | 0.94871 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144332 | HCSW5FZ2090 | Casting concrete for slab topping | 25894 | 2013-05-26 08:00 | 2013-05-26 16:00 | 1 | 0 | 100 | 100 | 0 | 1323 | 1323 | 1323 | 1514.1681 | 1 | 0.87375 | TRUE | FALSE | FALSE | 0 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144333 | HCSW5FZ3000 | Formwork core wall shutters - 1st side | 25896 | 2013-05-26 08:00 | 2013-05-30 16:00 | 4 | 128 | 100 | 99 | -1 | 5712 | 5712 | 5654.88 | 6027.0672 | 0.99 | 0.93825 | FALSE | FALSE | FALSE | 16 | FALSE | 0 | Green | Continue normal monitoring.
144334 | HCSW5FZ3010 | Fix steel rebar for core wall | 25896 | 2013-06-01 08:00 | 2013-06-02 16:00 | 1 | 128 | 100 | 100 | 0 | 1433 | 1433 | 1433 | 1716.5082 | 1 | 0.83483 | TRUE | FALSE | FALSE | 16 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144335 | HCSW5FZ3020 | Fix MEP first fix in core wall | 25896 | 2013-06-03 08:00 | 2013-06-03 16:00 | 1 | 128 | 100 | 91 | -9 | 1640 | 1640 | 1492.4 | 1658.2209 | 0.91 | 0.9 | FALSE | FALSE | FALSE | 16 | FALSE | 0 | Green | Continue normal monitoring.
144336 | HCSW5FZ3030 | Close shutter for core wall | 25896 | 2013-06-04 08:00 | 2013-06-05 16:00 | 1 | 128 | 100 | 97 | -3 | 633 | 633 | 614.01 | 783.7136 | 0.97 | 0.78346 | TRUE | FALSE | FALSE | 16 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144337 | HCSW5FZ3040 | Cast concrete for core wall | 25896 | 2013-06-06 08:00 | 2013-06-06 16:00 | 1 | 128 | 100 | 82 | -18 | 557 | 557 | 456.74 | 681.1715 | 0.82 | 0.67052 | TRUE | TRUE | TRUE | 16 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144338 | HCSW5FZ3050 | De-shutter core wall formwork | 25896 | 2013-06-08 08:00 | 2013-06-08 16:00 | 1 | 176 | 100 | 100 | 0 | 1184 | 1184 | 1184 | 1357.623 | 1 | 0.87211 | TRUE | FALSE | FALSE | 22 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144339 | HCSW5FZ3060 | Provision & Installation of steel embedded plates | 25897 | 2013-06-03 08:00 | 2013-06-03 16:00 | 1 | 128 | 100 | 80 | -20 | 1171 | 1171 | 936.8 | 1126.2284 | 0.8 | 0.8318 | TRUE | TRUE | TRUE | 16 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144340 | HCSW5FZ3070 | Installation of steel columns and beams | 25897 | 2013-07-14 08:00 | 2013-07-17 16:00 | 3 | 0 | 100 | 80 | -20 | 2016 | 2016 | 1612.8 | 1819.7655 | 0.8 | 0.88627 | TRUE | TRUE | TRUE | 0 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
144341 | HCSW5FZ3080 | Steel Deck | 25897 | 2013-07-18 08:00 | 2013-07-21 16:00 | 3 | 0 | 100 | 100 | 0 | 3942 | 3942 | 3942 | 4698.3964 | 1 | 0.83901 | TRUE | FALSE | FALSE | 0 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144342 | HCSW5FZ3090 | Casting concrete for slab topping | 25897 | 2013-07-22 08:00 | 2013-07-22 16:00 | 1 | 0 | 100 | 98 | -2 | 1672 | 1672 | 1638.56 | 1531.7542 | 0.98 | 1.0697 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144343 | HCSW5FZ4070 | Installation of steel columns and beams | 25899 | 2013-08-21 08:00 | 2013-08-25 16:00 | 4 | 80 | 100 | 90 | -10 | 2316 | 2316 | 2084.4 | 2759.9872 | 0.9 | 0.75522 | TRUE | FALSE | FALSE | 10 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144344 | HCSW5FZ4080 | Steel Deck | 25899 | 2013-08-26 08:00 | 2013-08-29 16:00 | 3 | 80 | 100 | 84 | -16 | 4155 | 4155 | 3490.2 | 4347.4014 | 0.84 | 0.80282 | TRUE | TRUE | TRUE | 10 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144345 | HCSW5FZ4090 | Casting concrete for slab topping | 25899 | 2013-08-31 08:00 | 2013-08-31 16:00 | 1 | 80 | 100 | 91 | -9 | 1736 | 1736 | 1579.76 | 1757.913 | 0.91 | 0.89866 | TRUE | FALSE | FALSE | 10 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144346 | HCSW5FZ5070 | Installation of steel columns and beams | 25901 | 2013-08-20 08:00 | 2013-08-22 16:00 | 2 | 136 | 100 | 82 | -18 | 1404 | 1404 | 1151.28 | 1700.6319 | 0.82 | 0.67697 | TRUE | TRUE | TRUE | 17 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144347 | HCSW5FZ5080 | Steel Deck | 25901 | 2013-08-24 08:00 | 2013-08-25 16:00 | 1 | 136 | 100 | 80 | -20 | 1263 | 1263 | 1010.4 | 1378.6155 | 0.8 | 0.73291 | TRUE | TRUE | TRUE | 17 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144348 | HCSW5FZ5090 | Casting concrete for slab topping | 25901 | 2013-08-26 08:00 | 2013-08-26 16:00 | 1 | 136 | 100 | 80 | -20 | 1752 | 1752 | 1401.6 | 1893.2911 | 0.8 | 0.7403 | TRUE | TRUE | TRUE | 17 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144349 | HCSW6FZ1070 | Installation of steel columns and beams | 25904 | 2013-03-30 08:00 | 2013-04-01 16:00 | 2 | 0 | 100 | 87 | -13 | 3500 | 3500 | 3045 | 3757.2723 | 0.87 | 0.81043 | TRUE | TRUE | TRUE | 0 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
144350 | HCSW6FZ1080 | Steel Deck | 25904 | 2013-04-02 08:00 | 2013-04-03 16:00 | 1 | 0 | 100 | 89 | -11 | 1964 | 1964 | 1747.96 | 1960.9908 | 0.89 | 0.89137 | TRUE | TRUE | TRUE | 0 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
144351 | HCSW6FZ1090 | Casting concrete for slab topping | 25904 | 2013-04-04 08:00 | 2013-04-04 16:00 | 1 | 0 | 100 | 90 | -10 | 1925 | 1925 | 1732.5 | 2241.1952 | 0.9 | 0.77303 | TRUE | FALSE | FALSE | 0 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144352 | HCSW6FZ3000 | Formwork core wall shutters - 1st side | 25906 | 2013-06-08 08:00 | 2013-06-12 16:00 | 4 | 128 | 100 | 91 | -9 | 2184 | 2184 | 1987.44 | 2077.2447 | 0.91 | 0.95677 | FALSE | FALSE | FALSE | 16 | FALSE | 0 | Green | Continue normal monitoring.
144353 | HCSW6FZ3010 | Fix steel rebar for core wall | 25906 | 2013-06-13 08:00 | 2013-06-15 16:00 | 2 | 128 | 100 | 100 | 0 | 3512 | 3512 | 3512 | 4304.1596 | 1 | 0.81595 | TRUE | FALSE | FALSE | 16 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144354 | HCSW6FZ3020 | Fix MEP first fix in core wall | 25906 | 2013-06-16 08:00 | 2013-06-16 16:00 | 1 | 128 | 100 | 92 | -8 | 1828 | 1828 | 1681.76 | 2207.482 | 0.92 | 0.76185 | TRUE | FALSE | FALSE | 16 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144355 | HCSW6FZ3030 | Close shutter for core wall | 25906 | 2013-06-17 08:00 | 2013-06-18 16:00 | 1 | 128 | 100 | 91 | -9 | 1666 | 1666 | 1516.06 | 1640.9969 | 0.91 | 0.92387 | FALSE | FALSE | FALSE | 16 | FALSE | 0 | Green | Continue normal monitoring.
144356 | HCSW6FZ3040 | Cast concrete for core wall | 25906 | 2013-06-19 08:00 | 2013-06-19 16:00 | 1 | 128 | 100 | 100 | 0 | 1938 | 1938 | 1938 | 2212.7803 | 1 | 0.87582 | TRUE | FALSE | FALSE | 16 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144357 | HCSW6FZ3050 | De-shutter core wall formwork | 25906 | 2013-06-20 08:00 | 2013-06-20 16:00 | 1 | 152 | 100 | 93 | -7 | 1896 | 1896 | 1763.28 | 2046.3325 | 0.93 | 0.86168 | TRUE | FALSE | FALSE | 19 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144358 | HCSW6FZ3060 | Provision & Installation of steel embedded plates | 26016 | 2013-06-16 08:00 | 2013-06-16 16:00 | 1 | 128 | 100 | 81 | -19 | 1782 | 1782 | 1443.42 | 1755.3764 | 0.81 | 0.82229 | TRUE | TRUE | TRUE | 16 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144359 | HCSW6FZ3070 | Installation of steel columns and beams | 26016 | 2013-07-23 08:00 | 2013-07-27 16:00 | 4 | 0 | 100 | 100 | 0 | 4620 | 4620 | 4620 | 5753.788 | 1 | 0.80295 | TRUE | FALSE | FALSE | 0 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144360 | HCSW6FZ3080 | Steel Deck | 26016 | 2013-07-28 08:00 | 2013-07-30 16:00 | 2 | 0 | 100 | 98 | -2 | 1940 | 1940 | 1901.2 | 1668.5842 | 0.98 | 1.1394 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144361 | HCSW6FZ3090 | Casting concrete for slab topping | 26016 | 2013-07-31 08:00 | 2013-07-31 16:00 | 1 | 0 | 100 | 97 | -3 | 1470 | 1470 | 1425.9 | 1398.0559 | 0.97 | 1.0199 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144362 | HCSW6FZ4070 | Installation of steel columns and beams | 25943 | 2013-09-01 08:00 | 2013-09-04 16:00 | 3 | 80 | 100 | 82 | -18 | 4605 | 4605 | 3776.1 | 4872.2264 | 0.82 | 0.77503 | TRUE | TRUE | TRUE | 10 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144363 | HCSW6FZ4080 | Steel Deck | 25943 | 2013-09-05 08:00 | 2013-09-09 16:00 | 4 | 80 | 100 | 100 | 0 | 7412 | 7412 | 7412 | 7847.6863 | 1 | 0.94448 | FALSE | FALSE | FALSE | 10 | FALSE | 0 | Green | Continue normal monitoring.
144364 | HCSW6FZ4090 | Casting concrete for slab topping | 25943 | 2013-09-10 08:00 | 2013-09-10 16:00 | 1 | 80 | 100 | 96 | -4 | 1235 | 1235 | 1185.6 | 1340.6829 | 0.96 | 0.88433 | TRUE | FALSE | FALSE | 10 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144365 | HCSW6FZ5070 | Installation of steel columns and beams | 25911 | 2013-08-27 08:00 | 2013-08-29 16:00 | 2 | 136 | 100 | 100 | 0 | 2566 | 2566 | 2566 | 2952.6204 | 1 | 0.86906 | TRUE | FALSE | FALSE | 17 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144366 | HCSW6FZ5080 | Steel Deck | 25911 | 2013-08-31 08:00 | 2013-09-01 16:00 | 1 | 136 | 100 | 87 | -13 | 1467 | 1467 | 1276.29 | 1612.8068 | 0.87 | 0.79135 | TRUE | TRUE | TRUE | 17 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144367 | HCSW6FZ5090 | Casting concrete for slab topping | 25911 | 2013-09-02 08:00 | 2013-09-02 16:00 | 1 | 136 | 100 | 100 | 0 | 857 | 857 | 857 | 934.2265 | 1 | 0.91734 | FALSE | FALSE | FALSE | 17 | FALSE | 0 | Green | Continue normal monitoring.
144368 | HCSW7FZ1070 | Installation of steel columns and beams | 26023 | 2013-04-06 08:00 | 2013-04-08 16:00 | 2 | 0 | 100 | 100 | 0 | 2942 | 2942 | 2942 | 2563.6758 | 1 | 1.1476 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144369 | HCSW7FZ1080 | Steel Deck | 26023 | 2013-04-09 08:00 | 2013-04-10 16:00 | 1 | 0 | 100 | 89 | -11 | 1931 | 1931 | 1718.59 | 1932.182 | 0.89 | 0.88946 | TRUE | TRUE | TRUE | 0 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
144370 | HCSW7FZ1090 | Casting concrete for slab topping | 26023 | 2013-04-11 08:00 | 2013-04-11 16:00 | 1 | 0 | 100 | 100 | 0 | 1167 | 1167 | 1167 | 1100.2736 | 1 | 1.0606 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144371 | HCSW7FZ2000 | Formwork core wall shutters - 1st side | 25916 | 2013-05-09 08:00 | 2013-05-14 16:00 | 5 | 16 | 100 | 100 | 0 | 4360 | 4360 | 4360 | 4168.8055 | 1 | 1.0459 | FALSE | FALSE | FALSE | 2 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144372 | HCSW7FZ2010 | Fix steel rebar for core wall | 25916 | 2013-05-15 08:00 | 2013-05-16 16:00 | 1 | 16 | 100 | 81 | -19 | 1531 | 1531 | 1240.11 | 1640.8263 | 0.81 | 0.75578 | TRUE | TRUE | TRUE | 2 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
144373 | HCSW7FZ2020 | Fix MEP first fix in core wall | 25916 | 2013-05-18 08:00 | 2013-05-18 16:00 | 1 | 16 | 100 | 98 | -2 | 1645 | 1645 | 1612.1 | 1529.5245 | 0.98 | 1.054 | FALSE | FALSE | FALSE | 2 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144374 | HCSW7FZ2030 | Close shutter for core wall | 25916 | 2013-05-19 08:00 | 2013-05-20 16:00 | 1 | 16 | 100 | 88 | -12 | 1871 | 1871 | 1646.48 | 1810.3415 | 0.88 | 0.90949 | FALSE | TRUE | TRUE | 2 | TRUE | 4 | Orange | Develop recovery plan and review schedule and cost exposure.
144375 | HCSW7FZ2040 | Cast concrete for core wall | 25916 | 2013-05-21 08:00 | 2013-05-21 16:00 | 1 | 16 | 100 | 86 | -14 | 1175 | 1175 | 1010.5 | 1110.1798 | 0.86 | 0.91021 | FALSE | TRUE | TRUE | 2 | TRUE | 4 | Orange | Develop recovery plan and review schedule and cost exposure.
144376 | HCSW7FZ2050 | De-shutter core wall formwork | 25916 | 2013-05-22 08:00 | 2013-05-22 16:00 | 1 | 16 | 100 | 83 | -17 | 589 | 589 | 488.87 | 724.1173 | 0.83 | 0.67513 | TRUE | TRUE | TRUE | 2 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
144377 | HCSW7FZ2060 | Provision & Installation of steel embedded plates | 25951 | 2013-05-18 08:00 | 2013-05-18 16:00 | 1 | 16 | 100 | 100 | 0 | 1197 | 1197 | 1197 | 1469.756 | 1 | 0.81442 | TRUE | FALSE | FALSE | 2 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144378 | HCSW7FZ2070 | Installation of steel columns and beams | 25951 | 2013-06-03 08:00 | 2013-06-04 16:00 | 1 | 0 | 100 | 100 | 0 | 1839 | 1839 | 1839 | 2011.823 | 1 | 0.9141 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144379 | HCSW7FZ2080 | Steel Deck | 25951 | 2013-06-05 08:00 | 2013-06-05 16:00 | 1 | 0 | 100 | 97 | -3 | 1701 | 1701 | 1649.97 | 2074.8951 | 0.97 | 0.79521 | TRUE | FALSE | FALSE | 0 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144380 | HCSW7FZ2090 | Casting concrete for slab topping | 25951 | 2013-06-06 08:00 | 2013-06-06 16:00 | 1 | 0 | 100 | 92 | -8 | 1039 | 1039 | 955.88 | 1209.7337 | 0.92 | 0.79016 | TRUE | FALSE | FALSE | 0 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144381 | HCSW7FZ3000 | Formwork core wall shutters - 1st side | 25919 | 2013-06-20 08:00 | 2013-06-25 16:00 | 5 | 128 | 100 | 90 | -10 | 6155 | 6155 | 5539.5 | 6684.2017 | 0.9 | 0.82875 | TRUE | FALSE | FALSE | 16 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144382 | HCSW7FZ3010 | Fix steel rebar for core wall | 25919 | 2013-06-26 08:00 | 2013-06-27 16:00 | 1 | 128 | 100 | 100 | 0 | 1368 | 1368 | 1368 | 1166.3213 | 1 | 1.1729 | FALSE | FALSE | FALSE | 16 | FALSE | 0 | Green | Continue normal monitoring.
144383 | HCSW7FZ3020 | Fix MEP first fix in core wall | 25919 | 2013-06-29 08:00 | 2013-06-29 16:00 | 1 | 128 | 100 | 100 | 0 | 540 | 540 | 540 | 625.8635 | 1 | 0.86281 | TRUE | FALSE | FALSE | 16 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144384 | HCSW7FZ3030 | Close shutter for core wall | 25919 | 2013-06-30 08:00 | 2013-07-01 16:00 | 1 | 128 | 100 | 83 | -17 | 1239 | 1239 | 1028.37 | 1401.3032 | 0.83 | 0.73387 | TRUE | TRUE | TRUE | 16 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144385 | HCSW7FZ3040 | Cast concrete for core wall | 25919 | 2013-07-02 08:00 | 2013-07-02 16:00 | 1 | 128 | 100 | 100 | 0 | 1001 | 1001 | 1001 | 1097.1976 | 1 | 0.91232 | FALSE | FALSE | FALSE | 16 | FALSE | 0 | Green | Continue normal monitoring.
144386 | HCSW7FZ3050 | De-shutter core wall formwork | 25919 | 2013-07-03 08:00 | 2013-07-03 16:00 | 1 | 128 | 100 | 100 | 0 | 1458 | 1458 | 1458 | 1682.7795 | 1 | 0.86642 | TRUE | FALSE | FALSE | 16 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144387 | HCSW7FZ3060 | Provision & Installation of steel embedded plates | 25920 | 2013-06-29 08:00 | 2013-06-29 16:00 | 1 | 128 | 100 | 100 | 0 | 1668 | 1668 | 1668 | 1760.0217 | 1 | 0.94772 | FALSE | FALSE | FALSE | 16 | FALSE | 0 | Green | Continue normal monitoring.
144388 | HCSW7FZ3070 | Installation of steel columns and beams | 25920 | 2013-08-01 08:00 | 2013-08-04 16:00 | 3 | 0 | 100 | 100 | 0 | 5172 | 5172 | 5172 | 5852.8075 | 1 | 0.88368 | TRUE | FALSE | FALSE | 0 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144389 | HCSW7FZ3080 | Steel Deck | 25920 | 2013-08-05 08:00 | 2013-08-06 16:00 | 1 | 0 | 100 | 83 | -17 | 1428 | 1428 | 1185.24 | 1747.9703 | 0.83 | 0.67807 | TRUE | TRUE | TRUE | 0 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
144390 | HCSW7FZ3090 | Casting concrete for slab topping | 25920 | 2013-08-07 08:00 | 2013-08-07 16:00 | 1 | 336 | 100 | 89 | -11 | 960 | 960 | 854.4 | 960.3091 | 0.89 | 0.88971 | TRUE | TRUE | TRUE | 42 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144391 | HCSW7FZ4070 | Installation of steel columns and beams | 26030 | 2013-09-11 08:00 | 2013-09-14 16:00 | 3 | 80 | 100 | 84 | -16 | 3693 | 3693 | 3102.12 | 4185.0876 | 0.84 | 0.74123 | TRUE | TRUE | TRUE | 10 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144392 | HCSW7FZ4080 | Steel Deck | 26030 | 2013-09-15 08:00 | 2013-09-16 16:00 | 1 | 80 | 100 | 88 | -12 | 1251 | 1251 | 1100.88 | 1301.3842 | 0.88 | 0.84593 | TRUE | TRUE | TRUE | 10 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144393 | HCSW7FZ4090 | Casting concrete for slab topping | 26030 | 2013-09-17 08:00 | 2013-09-17 16:00 | 1 | 80 | 100 | 100 | 0 | 1424 | 1424 | 1424 | 1594.538 | 1 | 0.89305 | TRUE | FALSE | FALSE | 10 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144394 | HCSW7FZ5070 | Installation of steel columns and beams | 25923 | 2013-09-03 08:00 | 2013-09-05 16:00 | 2 | 136 | 100 | 82 | -18 | 2816 | 2816 | 2309.12 | 3252.9231 | 0.82 | 0.70986 | TRUE | TRUE | TRUE | 17 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144395 | HCSW7FZ5080 | Steel Deck | 25923 | 2013-09-07 08:00 | 2013-09-08 16:00 | 1 | 136 | 100 | 96 | -4 | 1776 | 1776 | 1704.96 | 1541.8895 | 0.96 | 1.1058 | FALSE | FALSE | FALSE | 17 | FALSE | 0 | Green | Continue normal monitoring.
144396 | HCSW7FZ5090 | Casting concrete for slab topping | 25923 | 2013-09-09 08:00 | 2013-09-09 16:00 | 1 | 136 | 100 | 82 | -18 | 889 | 889 | 728.98 | 985.5811 | 0.82 | 0.73964 | TRUE | TRUE | TRUE | 17 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144397 | HCSW6FZ2000 | Formwork core wall shutters - 1st side | 25924 | 2013-04-25 08:00 | 2013-04-30 16:00 | 5 | 16 | 100 | 95 | -5 | 6910 | 6910 | 6564.5 | 6500.2126 | 0.95 | 1.0099 | FALSE | FALSE | FALSE | 2 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144398 | HCSW6FZ2010 | Fix steel rebar for core wall | 25924 | 2013-05-02 08:00 | 2013-05-04 16:00 | 2 | 16 | 100 | 83 | -17 | 1510 | 1510 | 1253.3 | 1688.1997 | 0.83 | 0.74239 | TRUE | TRUE | TRUE | 2 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
144399 | HCSW6FZ2020 | Fix MEP first fix in core wall | 25924 | 2013-05-05 08:00 | 2013-05-05 16:00 | 1 | 16 | 100 | 97 | -3 | 1208 | 1208 | 1171.76 | 1253.0971 | 0.97 | 0.93509 | FALSE | FALSE | FALSE | 2 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144400 | HCSW6FZ2030 | Close shutter for core wall | 25924 | 2013-05-06 08:00 | 2013-05-07 16:00 | 1 | 16 | 100 | 96 | -4 | 949 | 949 | 911.04 | 1100.2906 | 0.96 | 0.828 | TRUE | FALSE | FALSE | 2 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144401 | HCSW6FZ2040 | Cast concrete for core wall | 25924 | 2013-05-08 08:00 | 2013-05-08 16:00 | 1 | 16 | 100 | 86 | -14 | 509 | 509 | 437.74 | 457.7744 | 0.86 | 0.95624 | FALSE | TRUE | TRUE | 2 | TRUE | 4 | Orange | Develop recovery plan and review schedule and cost exposure.
144402 | HCSW6FZ2050 | De-shutter core wall formwork | 25924 | 2013-05-09 08:00 | 2013-05-09 16:00 | 1 | 104 | 100 | 100 | 0 | 1323 | 1323 | 1323 | 1455.9998 | 1 | 0.90865 | FALSE | FALSE | FALSE | 13 | FALSE | 0 | Green | Continue normal monitoring.
144403 | HCSW6FZ2060 | Provision & Installation of steel embedded plates | 26029 | 2013-05-05 08:00 | 2013-05-05 16:00 | 1 | 16 | 100 | 100 | 0 | 1297 | 1297 | 1297 | 1246.9206 | 1 | 1.0402 | FALSE | FALSE | FALSE | 2 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144404 | HCSW6FZ2070 | Installation of steel columns and beams | 26029 | 2013-05-27 08:00 | 2013-05-29 16:00 | 2 | 0 | 100 | 100 | 0 | 3530 | 3530 | 3530 | 4204.9106 | 1 | 0.83949 | TRUE | FALSE | FALSE | 0 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144405 | HCSW6FZ2080 | Steel Deck | 26029 | 2013-05-30 08:00 | 2013-06-01 16:00 | 2 | 0 | 100 | 84 | -16 | 3548 | 3548 | 2980.32 | 4333.3619 | 0.84 | 0.68776 | TRUE | TRUE | TRUE | 0 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
144406 | HCSW6FZ2090 | Casting concrete for slab topping | 26029 | 2013-06-02 08:00 | 2013-06-02 16:00 | 1 | 0 | 100 | 91 | -9 | 1376 | 1376 | 1252.16 | 1718.0176 | 0.91 | 0.72884 | TRUE | FALSE | FALSE | 0 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144407 | HEMSSCI0000 | MS submission: Concrete mix design | 25808 | 2012-06-05 08:00 | 2012-06-12 16:00 | 7 | 16 | 100 | 96 | -4 | 10696 | 10696 | 10268.16 | 12497.2381 | 0.96 | 0.82163 | TRUE | FALSE | FALSE | 2 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144408 | HEMSSSS0000 | MS submission: Structural steel | 25767 | 2012-07-04 08:00 | 2012-08-13 16:00 | 40 | 64 | 100 | 100 | 0 | 65680 | 65680 | 65680 | 75630.1015 | 1 | 0.86844 | TRUE | FALSE | FALSE | 8 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144409 | HEMSSSS0010 | MS submission: Metal deck and fire proofing | 25767 | 2012-07-04 08:00 | 2012-08-13 16:00 | 40 | 64 | 100 | 92 | -8 | 60600 | 60600 | 55752 | 56733.7384 | 0.92 | 0.9827 | FALSE | FALSE | FALSE | 8 | FALSE | 0 | Green | Continue normal monitoring.
144410 | HEMSSFI0070 | MS submission:Steel doors and frames | 25761 | 2013-02-07 08:00 | 2013-03-13 16:00 | 34 | 720 | 100 | 100 | 0 | 29682 | 29682 | 29682 | 29219.0446 | 1 | 1.0158 | FALSE | FALSE | FALSE | 90 | FALSE | 0 | Green | Continue normal monitoring.
144411 | HEMSSFI0150 | MS submission: Acoustical tile ceilings | 25761 | 2012-12-03 08:00 | 2012-12-25 16:00 | 22 | 600 | 100 | 100 | 0 | 34936 | 34936 | 34936 | 36203.2341 | 1 | 0.965 | FALSE | FALSE | FALSE | 75 | FALSE | 0 | Green | Continue normal monitoring.
144412 | HEMSSFI0160 | MS submission: Gybsum board ceilings | 25761 | 2012-12-03 08:00 | 2013-01-07 16:00 | 35 | 600 | 100 | 82 | -18 | 22575 | 22575 | 18511.5 | 26172.3809 | 0.82 | 0.70729 | TRUE | TRUE | TRUE | 75 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144413 | HEMSSFI0170 | MS submission: Basalt stone flooring | 25761 | 2012-12-09 08:00 | 2012-12-22 16:00 | 13 | 80 | 100 | 88 | -12 | 9399 | 9399 | 8271.12 | 11429.0557 | 0.88 | 0.72369 | TRUE | TRUE | TRUE | 10 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144414 | HEMSSFI0180 | MS submission: Quarry tiles flooring | 25761 | 2012-12-23 08:00 | 2013-01-06 16:00 | 14 | 80 | 100 | 100 | 0 | 24668 | 24668 | 24668 | 22834.0733 | 1 | 1.0803 | FALSE | FALSE | FALSE | 10 | FALSE | 0 | Green | Continue normal monitoring.
144415 | HEMSSFI0190 | MS submission: Resilient flooring tiles | 25761 | 2013-01-07 08:00 | 2013-01-20 16:00 | 13 | 80 | 100 | 96 | -4 | 8788 | 8788 | 8436.48 | 10712.1062 | 0.96 | 0.78757 | TRUE | FALSE | FALSE | 10 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144416 | HEMSSFI0200 | MS submission: Terrazzo flooring | 25761 | 2013-01-21 08:00 | 2013-02-04 16:00 | 14 | 80 | 100 | 96 | -4 | 18928 | 18928 | 18170.88 | 21355.5134 | 0.96 | 0.85088 | TRUE | FALSE | FALSE | 10 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144417 | HEMSSFI0210 | MS submission:Carpet tiles | 25761 | 2013-01-21 08:00 | 2013-02-23 16:00 | 33 | 80 | 100 | 100 | 0 | 59565 | 59565 | 59565 | 65182.4734 | 1 | 0.91382 | FALSE | FALSE | FALSE | 10 | FALSE | 0 | Green | Continue normal monitoring.
144418 | HEMSSAL0000 | MS submission: Aluminum louvers | 25764 | 2012-08-25 08:00 | 2012-12-01 16:00 | 98 | 608 | 100 | 99 | -1 | 55076 | 55076 | 54525.24 | 51217.1831 | 0.99 | 1.0646 | FALSE | FALSE | FALSE | 76 | FALSE | 0 | Green | Continue normal monitoring.
144419 | HEMSSAL0010 | MS submission: Curtain walls | 25764 | 2012-07-04 08:00 | 2012-09-08 16:00 | 66 | 344 | 100 | 95 | -5 | 114840 | 114840 | 109098 | 100164.5979 | 0.95 | 1.0892 | FALSE | FALSE | FALSE | 43 | FALSE | 0 | Green | Continue normal monitoring.
144420 | HEMSSAL0020 | MS submission: Handrails & Railling | 25764 | 2012-08-04 08:00 | 2012-09-11 16:00 | 38 | 344 | 100 | 100 | 0 | 50388 | 50388 | 50388 | 54287.3237 | 1 | 0.92817 | FALSE | FALSE | FALSE | 43 | FALSE | 0 | Green | Continue normal monitoring.
144421 | HEMSSAL0030 | MS submission: Sky lights | 25764 | 2012-08-04 08:00 | 2012-10-16 16:00 | 73 | 1040 | 100 | 100 | 0 | 94462 | 94462 | 94462 | 104910.0898 | 1 | 0.90041 | FALSE | FALSE | FALSE | 130 | FALSE | 0 | Green | Continue normal monitoring.
144422 | HEMSSFI0460 | MS submission: Glass wall tiles | 25761 | 2012-11-07 08:00 | 2012-11-21 16:00 | 14 | 56 | 100 | 92 | -8 | 16632 | 16632 | 15301.44 | 15539.4868 | 0.92 | 0.98468 | FALSE | FALSE | FALSE | 7 | FALSE | 0 | Green | Continue normal monitoring.
144423 | HEMSSAL0050 | MS submission: Revolving entrance doors | 25764 | 2012-10-10 08:00 | 2013-01-17 16:00 | 99 | 448 | 100 | 100 | 0 | 196416 | 196416 | 196416 | 210672.3608 | 1 | 0.93233 | FALSE | FALSE | FALSE | 56 | FALSE | 0 | Green | Continue normal monitoring.
144424 | HEMSSAL0060 | MS submission: Glass panels | 25764 | 2012-08-14 08:00 | 2012-11-25 16:00 | 103 | 648 | 100 | 98 | -2 | 62212 | 62212 | 60967.76 | 74193.867 | 0.98 | 0.82174 | TRUE | FALSE | FALSE | 81 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144425 | HEMSSAL0070 | MS submission: Storefront tension cable system | 25764 | 2012-09-29 08:00 | 2012-11-19 16:00 | 51 | 368 | 100 | 96 | -4 | 82722 | 82722 | 79413.12 | 97945.0301 | 0.96 | 0.81079 | TRUE | FALSE | FALSE | 46 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144426 | HEMSSFI0550 | MS submission: Wooden doors | 25761 | 2012-10-17 08:00 | 2012-11-26 16:00 | 40 | 520 | 100 | 83 | -17 | 40400 | 40400 | 33532 | 49326.0597 | 0.83 | 0.6798 | TRUE | TRUE | TRUE | 65 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144427 | HCSW4FZ4000 | Scafolding under steel structure | 25830 | 2013-05-05 08:00 | 2013-08-06 16:00 | 93 | 80 | 100 | 91 | -9 | 82212 | 82212 | 74812.92 | 81912.2817 | 0.91 | 0.91333 | FALSE | FALSE | FALSE | 10 | FALSE | 0 | Green | Continue normal monitoring.
144428 | HCSW4FZ6000 | Scafolding under steel structure | 25845 | 2013-05-07 08:00 | 2013-08-12 16:00 | 97 | 136 | 100 | 100 | 0 | 87688 | 87688 | 87688 | 85690.4524 | 1 | 1.0233 | FALSE | FALSE | FALSE | 17 | FALSE | 0 | Green | Continue normal monitoring.
144429 | HESDSCI0000 | SD submission: Excavation Plans and sections Z1- Z4 | 25806 | 2012-06-05 08:00 | 2012-06-06 16:00 | 1 | 8 | 100 | 88 | -12 | 1322 | 1322 | 1163.36 | 1519.9965 | 0.88 | 0.76537 | TRUE | TRUE | TRUE | 1 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
144430 | HESDACI0000 | SD approval: Excavation Plans and sections | 25836 | 2012-06-07 08:00 | 2012-06-09 16:00 | 2 | 8 | 100 | 98 | -2 | 2034 | 2034 | 1993.32 | 2079.6531 | 0.98 | 0.95849 | FALSE | FALSE | FALSE | 1 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144431 | HCESCA000 | s/c approval: MEP subcontractor | 25733 | 2012-07-24 08:00 | 2012-08-08 16:00 | 15 | 0 | 100 | 91 | -9 | 14625 | 14625 | 13308.75 | 12943.4097 | 0.91 | 1.0282 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144432 | HCESCA010 | s/c approval: Steel structure subcontractor | 25733 | 2012-06-18 08:00 | 2012-07-03 16:00 | 15 | 0 | 100 | 88 | -12 | 18120 | 18120 | 15945.6 | 17451.7426 | 0.88 | 0.9137 | FALSE | TRUE | TRUE | 0 | TRUE | 4 | Orange | Develop recovery plan and review schedule and cost exposure.
144433 | HCESCA020 | s/c approval: Aluminum subcontractor | 25733 | 2012-06-18 08:00 | 2012-07-03 16:00 | 15 | 344 | 100 | 86 | -14 | 19050 | 19050 | 16383 | 19382.097 | 0.86 | 0.84526 | TRUE | TRUE | TRUE | 43 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144434 | HESDSSS0000 | SD submission: Steel Strucutre shopdrawings | 25785 | 2012-07-04 08:00 | 2012-11-06 16:00 | 125 | 0 | 100 | 100 | 0 | 245000 | 245000 | 245000 | 236916.6097 | 1 | 1.0341 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144435 | HESDASS0000 | SD approval: Steel Strucutre shopdrawings | 25772 | 2012-07-21 08:00 | 2012-11-24 16:00 | 126 | 0 | 100 | 93 | -7 | 194796 | 194796 | 181160.28 | 191461.5266 | 0.93 | 0.9462 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144436 | HEMSASS0000 | MS approval: Structural steel | 25779 | 2012-08-13 16:00 | 2012-08-27 16:00 | 14 | 113 | 100 | 100 | 0 | 20944 | 20944 | 20944 | 20263.537 | 1 | 1.0336 | FALSE | FALSE | FALSE | 14.125 | FALSE | 0 | Green | Continue normal monitoring.
144437 | HEMSASS0010 | MS approval: Metal deck and fire proofing | 25779 | 2012-08-13 16:00 | 2012-08-27 16:00 | 14 | 113 | 100 | 99 | -1 | 16464 | 16464 | 16299.36 | 14267.6969 | 0.99 | 1.1424 | FALSE | FALSE | FALSE | 14.125 | FALSE | 0 | Green | Continue normal monitoring.
144438 | HEPSS00000 | Material Procurement | 25716 | 2012-08-27 16:00 | 2013-01-24 16:00 | 150 | 113 | 100 | 98 | -2 | 181950 | 181950 | 178311 | 201025.2523 | 0.98 | 0.88701 | TRUE | FALSE | FALSE | 14.125 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144439 | HEPSS00010 | Fabrication & Painting | 25716 | 2012-11-24 16:00 | 2013-04-23 16:00 | 150 | 1 | 100 | 100 | 0 | 297150 | 297150 | 297150 | 323571.6771 | 1 | 0.91834 | FALSE | FALSE | FALSE | 0.125 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144440 | HEPSS00020 | Delivery / Shipment | 25716 | 2013-01-14 16:00 | 2013-06-13 16:00 | 150 | 1 | 100 | 94 | -6 | 87300 | 87300 | 82062 | 97021.1518 | 0.94 | 0.84582 | TRUE | FALSE | FALSE | 0.125 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144441 | HCSWSSZ6260 | SS Z6 :Pour blinding under membrane | 25936 | 2012-09-19 08:00 | 2012-10-04 16:00 | 15 | 200 | 100 | 95 | -5 | 25020 | 25020 | 23769 | 23191.6374 | 0.95 | 1.0249 | FALSE | FALSE | FALSE | 25 | FALSE | 0 | Green | Continue normal monitoring.
144442 | HCSWSSZ6270 | SS Z6 :Construct block works (formwork) | 25936 | 2012-09-20 08:00 | 2012-10-06 16:00 | 16 | 200 | 100 | 100 | 0 | 25728 | 25728 | 25728 | 24911.44 | 1 | 1.0328 | FALSE | FALSE | FALSE | 25 | FALSE | 0 | Green | Continue normal monitoring.
144443 | HCSWSSZ6280 | SS Z6 :Apply water Proofing and protection (inside) | 25936 | 2012-09-22 08:00 | 2012-10-07 16:00 | 15 | 200 | 100 | 84 | -16 | 24015 | 24015 | 20172.6 | 26364.7806 | 0.84 | 0.76513 | TRUE | TRUE | TRUE | 25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144444 | HCSWSSZ6290 | SS Z6 :Formwork and rebar for foundations | 25936 | 2012-09-24 08:00 | 2012-10-09 16:00 | 15 | 200 | 100 | 82 | -18 | 14340 | 14340 | 11758.8 | 15628.4637 | 0.82 | 0.7524 | TRUE | TRUE | TRUE | 25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144445 | HCSWSSZ6300 | SS Z6 :Cast concrete for foundations | 25936 | 2012-09-30 08:00 | 2012-10-15 16:00 | 15 | 200 | 100 | 91 | -9 | 7500 | 7500 | 6825 | 7893.9909 | 0.91 | 0.86458 | TRUE | FALSE | FALSE | 25 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144446 | HCSWSSZ6310 | SS Z6 :De-shutter formwork | 25936 | 2012-10-01 08:00 | 2012-10-16 16:00 | 15 | 344 | 100 | 100 | 0 | 8250 | 8250 | 8250 | 8168.8637 | 1 | 1.0099 | FALSE | FALSE | FALSE | 43 | FALSE | 0 | Green | Continue normal monitoring.
144447 | HCSWB3Z6250 | B3 Z6 :Formwork retaining walls shutters - 1st side | 25937 | 2012-10-16 08:00 | 2012-10-24 16:00 | 8 | 200 | 100 | 99 | -1 | 9472 | 9472 | 9377.28 | 11510.113 | 0.99 | 0.8147 | TRUE | FALSE | FALSE | 25 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144448 | HCSWB3Z6260 | B3 Z6 :Fix steel rebar for reatining walls | 25937 | 2012-10-16 08:00 | 2012-10-24 16:00 | 8 | 200 | 100 | 100 | 0 | 9728 | 9728 | 9728 | 9590.914 | 1 | 1.0143 | FALSE | FALSE | FALSE | 25 | FALSE | 0 | Green | Continue normal monitoring.
144449 | HCSWB3Z6270 | B3 Z6 :Fix MEP first fix in walls | 25937 | 2012-10-17 08:00 | 2012-10-30 16:00 | 13 | 200 | 100 | 100 | 0 | 25597 | 25597 | 25597 | 26422.4434 | 1 | 0.96876 | FALSE | FALSE | FALSE | 25 | FALSE | 0 | Green | Continue normal monitoring.
144450 | HCSWB3Z6280 | B3 Z6 :Close shutter for retaining walls | 25937 | 2012-10-18 08:00 | 2012-10-31 16:00 | 13 | 200 | 100 | 83 | -17 | 12324 | 12324 | 10228.92 | 13818.2299 | 0.83 | 0.74025 | TRUE | TRUE | TRUE | 25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144451 | HCSWB3Z6290 | B3 Z6 :Cast concrete for retaining walls | 25937 | 2012-10-20 08:00 | 2012-11-01 16:00 | 12 | 200 | 100 | 100 | 0 | 16560 | 16560 | 16560 | 17672.974 | 1 | 0.93702 | FALSE | FALSE | FALSE | 25 | FALSE | 0 | Green | Continue normal monitoring.
144452 | HCSWB3Z6300 | B3 Z6 :De-shutter retaining walls | 25937 | 2012-10-21 08:00 | 2012-11-03 16:00 | 13 | 200 | 100 | 100 | 0 | 12831 | 12831 | 12831 | 12686.7076 | 1 | 1.0114 | FALSE | FALSE | FALSE | 25 | FALSE | 0 | Green | Continue normal monitoring.
144453 | HCSWB3Z6310 | B3 Z6 :Apply water proofing membrane behind Basement Walls | 25937 | 2012-10-31 08:00 | 2012-11-08 16:00 | 8 | 200 | 100 | 95 | -5 | 4264 | 4264 | 4050.8 | 4367.4358 | 0.95 | 0.9275 | FALSE | FALSE | FALSE | 25 | FALSE | 0 | Green | Continue normal monitoring.
144454 | HCSWB3Z6320 | B3 Z6 :Apply Protection for Basement Walls | 25937 | 2012-11-03 08:00 | 2012-11-11 16:00 | 8 | 200 | 100 | 100 | 0 | 14968 | 14968 | 14968 | 17479.5156 | 1 | 0.85632 | TRUE | FALSE | FALSE | 25 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144455 | HCSWSSZ6340 | SS Z6 :Fill imported base course around Foundations & under SOG | 25938 | 2012-11-08 08:00 | 2012-11-18 16:00 | 10 | 200 | 100 | 86 | -14 | 5940 | 5940 | 5108.4 | 5709.8349 | 0.86 | 0.89467 | TRUE | TRUE | TRUE | 25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144456 | HCSWSSZ6350 | SS Z6 :Lay polythene sheets under SOG | 25938 | 2012-11-19 08:00 | 2012-11-19 16:00 | 1 | 306 | 100 | 92 | -8 | 1595 | 1595 | 1467.4 | 1446.5088 | 0.92 | 1.0144 | FALSE | FALSE | FALSE | 38.25 | FALSE | 0 | Green | Continue normal monitoring.
144457 | HCSWSSZ6360 | SS Z6 :Formwork and Erect steel for SOG | 25938 | 2012-11-20 08:00 | 2012-11-26 16:00 | 6 | 306 | 100 | 100 | 0 | 3918 | 3918 | 3918 | 3821.0894 | 1 | 1.0254 | FALSE | FALSE | FALSE | 38.25 | FALSE | 0 | Green | Continue normal monitoring.
144458 | HCSWSSZ6370 | SS Z6 :Cast Concrete for SOG | 25938 | 2012-11-27 08:00 | 2012-11-27 16:00 | 1 | 306 | 100 | 89 | -11 | 749 | 749 | 666.61 | 891.1705 | 0.89 | 0.74802 | TRUE | TRUE | TRUE | 38.25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144459 | HEMSMCI0000 | MS approval: Concrete mix design | 25762 | 2012-06-13 08:00 | 2012-06-30 16:00 | 17 | 16 | 100 | 100 | 0 | 19941 | 19941 | 19941 | 17659.6676 | 1 | 1.1292 | FALSE | FALSE | FALSE | 2 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144460 | HEMSAFI0070 | MS approval: Steel doors and frames | 25781 | 2013-03-14 08:00 | 2013-04-17 16:00 | 34 | 720 | 100 | 86 | -14 | 31858 | 31858 | 27397.88 | 39716.6814 | 0.86 | 0.68983 | TRUE | TRUE | TRUE | 90 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144461 | HEMSAFI0150 | MS approval: Acoustical tile ceilings | 25781 | 2012-12-26 08:00 | 2013-01-12 16:00 | 17 | 3688 | 100 | 93 | -7 | 10489 | 10489 | 9754.77 | 11185.4818 | 0.93 | 0.87209 | TRUE | FALSE | FALSE | 461 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144462 | HEMSAFI0160 | MS approval: Gybsum board ceilings | 25781 | 2013-01-08 08:00 | 2013-01-23 16:00 | 15 | 760 | 100 | 100 | 0 | 19050 | 19050 | 19050 | 23697.0246 | 1 | 0.8039 | TRUE | FALSE | FALSE | 95 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144463 | HEMSAFI0170 | MS approval: Basalt stone flooring | 25781 | 2012-12-23 08:00 | 2013-01-06 16:00 | 14 | 3728 | 100 | 100 | 0 | 25606 | 25606 | 25606 | 31382.677 | 1 | 0.81593 | TRUE | FALSE | FALSE | 466 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144464 | HEMSAFI0180 | MS approval: Quarry tiles flooring | 25781 | 2013-01-07 08:00 | 2013-01-22 16:00 | 15 | 3616 | 100 | 84 | -16 | 11505 | 11505 | 9664.2 | 11863.0987 | 0.84 | 0.81464 | TRUE | TRUE | TRUE | 452 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144465 | HEMSAFI0190 | MS approval: Resilient flooring tiles | 25781 | 2013-01-21 08:00 | 2013-02-06 16:00 | 16 | 3520 | 100 | 82 | -18 | 25232 | 25232 | 20690.24 | 23450.5307 | 0.82 | 0.88229 | TRUE | TRUE | TRUE | 440 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144466 | HEMSAFI0200 | MS approval: Terrazzo flooring | 25781 | 2013-02-05 08:00 | 2013-02-20 16:00 | 15 | 3424 | 100 | 100 | 0 | 11025 | 11025 | 11025 | 10098.3919 | 1 | 1.0918 | FALSE | FALSE | FALSE | 428 | FALSE | 0 | Green | Continue normal monitoring.
144467 | HEMSAFI0210 | MS approval: Carpet tiles | 25781 | 2013-02-24 08:00 | 2013-03-11 16:00 | 15 | 80 | 100 | 100 | 0 | 13320 | 13320 | 13320 | 12600.6633 | 1 | 1.0571 | FALSE | FALSE | FALSE | 10 | FALSE | 0 | Green | Continue normal monitoring.
144468 | HEMSAFI0270 | MS approval: Toilet & corian vanity tops | 25781 | 2012-11-20 08:00 | 2012-12-05 16:00 | 15 | 1768 | 100 | 90 | -10 | 22335 | 22335 | 20101.5 | 25329.075 | 0.9 | 0.79361 | TRUE | FALSE | FALSE | 221 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144469 | HEMSAFI0320 | MS approval:Metal works | 25781 | 2013-01-31 08:00 | 2013-03-06 16:00 | 34 | 520 | 100 | 90 | -10 | 42908 | 42908 | 38617.2 | 41156.4953 | 0.9 | 0.9383 | FALSE | FALSE | FALSE | 65 | FALSE | 0 | Green | Continue normal monitoring.
144470 | HEMSAFI0460 | MS approval: Glass wall tiles | 25781 | 2012-11-22 08:00 | 2012-12-08 16:00 | 16 | 56 | 100 | 97 | -3 | 14400 | 14400 | 13968 | 14206.6096 | 0.97 | 0.9832 | FALSE | FALSE | FALSE | 7 | FALSE | 0 | Green | Continue normal monitoring.
144471 | HEMSAFI0550 | MS approval: Wooden doors | 25781 | 2012-11-07 08:00 | 2012-12-12 16:00 | 35 | 520 | 100 | 94 | -6 | 39305 | 39305 | 36946.7 | 40464.9504 | 0.94 | 0.91305 | FALSE | FALSE | FALSE | 65 | FALSE | 0 | Green | Continue normal monitoring.
144472 | HEMSSME1050 | MS submission: Sprinklers | 25832 | 2012-12-15 08:00 | 2012-12-30 16:00 | 15 | 304 | 100 | 91 | -9 | 18990 | 18990 | 17280.9 | 23078.4154 | 0.91 | 0.74879 | TRUE | FALSE | FALSE | 38 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144473 | HEMSSME1130 | MS submission: Ducts | 25832 | 2012-11-08 08:00 | 2012-12-13 16:00 | 35 | 120 | 100 | 88 | -12 | 63910 | 63910 | 56240.8 | 59165.1533 | 0.88 | 0.95057 | FALSE | TRUE | TRUE | 15 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144474 | HEMSSME1160 | MS submission: Diffusers | 25832 | 2013-01-08 08:00 | 2013-01-23 16:00 | 15 | 0 | 100 | 89 | -11 | 21270 | 21270 | 18930.3 | 18122.2659 | 0.89 | 1.0446 | FALSE | TRUE | TRUE | 0 | TRUE | 4 | Orange | Develop recovery plan and review schedule and cost exposure.
144475 | HEMSSME1170 | MS submission: Grills | 25832 | 2013-02-13 08:00 | 2013-02-28 16:00 | 15 | 120 | 100 | 100 | 0 | 25950 | 25950 | 25950 | 22681.3007 | 1 | 1.1441 | FALSE | FALSE | FALSE | 15 | FALSE | 0 | Green | Continue normal monitoring.
144476 | HEMSSME1290 | MS submission: Cables | 25832 | 2012-12-15 08:00 | 2012-12-25 16:00 | 10 | 48 | 100 | 91 | -9 | 17520 | 17520 | 15943.2 | 21232.6025 | 0.91 | 0.75088 | TRUE | FALSE | FALSE | 6 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144477 | HEMSSME1300 | MS submission: Cable Trays | 25832 | 2012-11-08 08:00 | 2012-11-25 16:00 | 17 | 0 | 100 | 96 | -4 | 22984 | 22984 | 22064.64 | 25489.4074 | 0.96 | 0.86564 | TRUE | FALSE | FALSE | 0 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144478 | HEMSSME1310 | MS submission: Electrical Boards | 25832 | 2012-09-06 08:00 | 2012-10-03 16:00 | 27 | 368 | 100 | 100 | 0 | 29079 | 29079 | 29079 | 27893.0493 | 1 | 1.0425 | FALSE | FALSE | FALSE | 46 | FALSE | 0 | Green | Continue normal monitoring.
144479 | HEMSSME1440 | MS submission: Wiring | 25832 | 2012-12-09 08:00 | 2012-12-24 16:00 | 15 | 248 | 100 | 85 | -15 | 8610 | 8610 | 7318.5 | 7928.751 | 0.85 | 0.92303 | FALSE | TRUE | TRUE | 31 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144480 | HEMSAME1050 | MS approval: Sprinklers | 25812 | 2012-12-31 08:00 | 2013-01-16 16:00 | 16 | 304 | 100 | 86 | -14 | 14944 | 14944 | 12851.84 | 14461.4088 | 0.86 | 0.8887 | TRUE | TRUE | TRUE | 38 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144481 | HEMSAME1130 | MS approval: Ducts | 25812 | 2012-11-26 08:00 | 2013-01-17 16:00 | 52 | 120 | 100 | 93 | -7 | 31304 | 31304 | 29112.72 | 28045.8412 | 0.93 | 1.038 | FALSE | FALSE | FALSE | 15 | FALSE | 0 | Green | Continue normal monitoring.
144482 | HEMSAME1160 | MS approval: Diffusers | 25812 | 2013-01-26 08:00 | 2013-02-10 16:00 | 15 | 0 | 100 | 92 | -8 | 29175 | 29175 | 26841 | 35786.4391 | 0.92 | 0.75003 | TRUE | FALSE | FALSE | 0 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144483 | HEMSAME1170 | MS approval: Grills | 25812 | 2013-03-02 08:00 | 2013-03-17 16:00 | 15 | 120 | 100 | 87 | -13 | 18945 | 18945 | 16482.15 | 22045.9644 | 0.87 | 0.74763 | TRUE | TRUE | TRUE | 15 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144484 | HEMSAME1290 | MS approval: Cables | 25812 | 2012-12-26 08:00 | 2013-01-12 16:00 | 17 | 48 | 100 | 89 | -11 | 21029 | 21029 | 18715.81 | 21764.0996 | 0.89 | 0.85994 | TRUE | TRUE | TRUE | 6 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144485 | HEMSAME1300 | MS approval: Cable Trays | 25812 | 2012-11-26 08:00 | 2012-12-11 16:00 | 15 | 0 | 100 | 88 | -12 | 19575 | 19575 | 17226 | 23411.4072 | 0.88 | 0.7358 | TRUE | TRUE | TRUE | 0 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
144486 | HEMSAME1310 | MS approval: Electrical Boards | 25812 | 2012-09-23 08:00 | 2012-10-20 16:00 | 27 | 368 | 100 | 97 | -3 | 49383 | 49383 | 47901.51 | 46903.1478 | 0.97 | 1.0213 | FALSE | FALSE | FALSE | 46 | FALSE | 0 | Green | Continue normal monitoring.
144487 | HEMSAME1440 | MS approval: Wiring | 25812 | 2012-12-25 08:00 | 2013-01-10 16:00 | 16 | 248 | 100 | 100 | 0 | 9552 | 9552 | 9552 | 10859.1743 | 1 | 0.87962 | TRUE | FALSE | FALSE | 31 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144488 | HEMSAAL0000 | MS approval: Aluminum louvers | 25817 | 2012-12-02 08:00 | 2012-12-17 16:00 | 15 | 608 | 100 | 100 | 0 | 19455 | 19455 | 19455 | 23199.1731 | 1 | 0.83861 | TRUE | FALSE | FALSE | 76 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144489 | HEMSAAL0010 | MS approval: Curtain walls | 25817 | 2012-09-09 08:00 | 2012-09-24 16:00 | 15 | 344 | 100 | 81 | -19 | 27870 | 27870 | 22574.7 | 27666.7576 | 0.81 | 0.81595 | TRUE | TRUE | TRUE | 43 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144490 | HEMSAAL0020 | MS approval: Handrails & Railling | 25817 | 2012-09-12 08:00 | 2012-09-27 16:00 | 15 | 344 | 100 | 84 | -16 | 20370 | 20370 | 17110.8 | 23486.3203 | 0.84 | 0.72854 | TRUE | TRUE | TRUE | 43 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144491 | HEMSAAL0030 | MS approval: Sky lights | 25817 | 2012-10-17 08:00 | 2012-11-06 16:00 | 20 | 1040 | 100 | 100 | 0 | 18680 | 18680 | 18680 | 18082.7806 | 1 | 1.033 | FALSE | FALSE | FALSE | 130 | FALSE | 0 | Green | Continue normal monitoring.
144492 | HEMSAAL0050 | MS approval: Revolving entrance doors | 25817 | 2013-01-19 08:00 | 2013-02-04 16:00 | 16 | 448 | 100 | 84 | -16 | 15136 | 15136 | 12714.24 | 14675.0006 | 0.84 | 0.86639 | TRUE | TRUE | TRUE | 56 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144493 | HEMSAAL0060 | MS approval: Glass panels | 25817 | 2012-11-26 08:00 | 2012-12-11 16:00 | 15 | 648 | 100 | 85 | -15 | 27465 | 27465 | 23345.25 | 24521.3802 | 0.85 | 0.95204 | FALSE | TRUE | TRUE | 81 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144494 | HEMSAAL0070 | MS approval: Storefront tension cable system | 25817 | 2012-11-20 08:00 | 2012-12-05 16:00 | 15 | 368 | 100 | 98 | -2 | 11220 | 11220 | 10995.6 | 11511.9805 | 0.98 | 0.95514 | FALSE | FALSE | FALSE | 46 | FALSE | 0 | Green | Continue normal monitoring.
144495 | HEPSAFI0070 | Steel doors and frames | 25712 | 2013-03-31 08:00 | 2013-08-22 16:00 | 144 | 720 | 100 | 87 | -13 | 95760 | 95760 | 83311.2 | 109346.8849 | 0.87 | 0.7619 | TRUE | TRUE | TRUE | 90 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144496 | HEPSAFI0160 | Ceilings Systems | 25712 | 2013-04-16 08:00 | 2013-10-01 16:00 | 168 | 208 | 100 | 95 | -5 | 249144 | 249144 | 236686.8 | 305472.549 | 0.95 | 0.77482 | TRUE | FALSE | FALSE | 26 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144497 | HEPSAFI0210 | Floor Tiles | 25712 | 2013-03-12 08:00 | 2013-12-16 16:00 | 279 | 80 | 100 | 92 | -8 | 518382 | 518382 | 476911.44 | 565823.6969 | 0.92 | 0.84286 | TRUE | FALSE | FALSE | 10 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144498 | HEPSAFI0270 | Toilet Toilet & corian vanity tops | 25712 | 2013-02-17 08:00 | 2013-09-19 16:00 | 214 | 1288 | 100 | 80 | -20 | 325066 | 325066 | 260052.8 | 388536.5067 | 0.8 | 0.66931 | TRUE | TRUE | TRUE | 161 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144499 | HEPSAFI0320 | Metal works | 25712 | 2013-03-07 08:00 | 2013-12-23 16:00 | 291 | 520 | 100 | 100 | 0 | 302931 | 302931 | 302931 | 357155.0006 | 1 | 0.84818 | TRUE | FALSE | FALSE | 65 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144500 | HEPSAFI0460 | Wall tiles & Cladding | 25712 | 2012-12-09 08:00 | 2013-12-07 16:00 | 363 | 56 | 100 | 99 | -1 | 456654 | 456654 | 452087.46 | 419819.0194 | 0.99 | 1.0769 | FALSE | FALSE | FALSE | 7 | FALSE | 0 | Green | Continue normal monitoring.
144501 | HEPSAFI0550 | Wooden Works | 25712 | 2012-12-13 08:00 | 2013-09-26 16:00 | 287 | 520 | 100 | 96 | -4 | 467523 | 467523 | 448822.08 | 488246.8787 | 0.96 | 0.91925 | FALSE | FALSE | FALSE | 65 | FALSE | 0 | Green | Continue normal monitoring.
144502 | HEPSAME1050 | Sprinklers | 25719 | 2013-01-17 08:00 | 2013-11-04 16:00 | 291 | 304 | 100 | 100 | 0 | 168780 | 168780 | 168780 | 151356.7417 | 1 | 1.1151 | FALSE | FALSE | FALSE | 38 | FALSE | 0 | Green | Continue normal monitoring.
144503 | HEPSAME1130 | Ducts & pipes | 25719 | 2013-01-03 08:00 | 2013-07-11 16:00 | 189 | 120 | 100 | 86 | -14 | 119448 | 119448 | 102725.28 | 134123.5323 | 0.86 | 0.7659 | TRUE | TRUE | TRUE | 15 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144504 | HEPSAME1160 | Diffusers | 25719 | 2013-02-11 08:00 | 2013-11-28 16:00 | 290 | 0 | 100 | 100 | 0 | 375840 | 375840 | 375840 | 462268.1165 | 1 | 0.81303 | TRUE | FALSE | FALSE | 0 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144505 | HEPSAME1170 | Grills | 25719 | 2013-03-18 08:00 | 2013-11-11 16:00 | 238 | 120 | 100 | 92 | -8 | 332962 | 332962 | 306325.04 | 301275.9321 | 0.92 | 1.0168 | FALSE | FALSE | FALSE | 15 | FALSE | 0 | Green | Continue normal monitoring.
144506 | HEPSAME1290 | Cables | 25719 | 2013-01-13 08:00 | 2013-10-02 16:00 | 262 | 48 | 100 | 83 | -17 | 166894 | 166894 | 138522.02 | 190852.1765 | 0.83 | 0.72581 | TRUE | TRUE | TRUE | 6 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144507 | HEPSAME1300 | CableTrays | 25719 | 2012-12-12 08:00 | 2013-09-25 16:00 | 287 | 0 | 100 | 83 | -17 | 196021 | 196021 | 162697.43 | 216190.6318 | 0.83 | 0.75256 | TRUE | TRUE | TRUE | 0 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
144508 | HEPSAME1310 | Electrical Boards | 25719 | 2012-10-09 08:00 | 2013-03-28 16:00 | 170 | 368 | 100 | 85 | -15 | 327080 | 327080 | 278018 | 354372.2142 | 0.85 | 0.78454 | TRUE | TRUE | TRUE | 46 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144509 | HEPSAME1440 | Wiring | 25719 | 2013-01-12 08:00 | 2013-04-27 16:00 | 105 | 248 | 100 | 100 | 0 | 194565 | 194565 | 194565 | 195741.7474 | 1 | 0.99399 | FALSE | FALSE | FALSE | 31 | FALSE | 0 | Green | Continue normal monitoring.
144510 | HEPSAAL0000 | Aluminum louvers | 25718 | 2012-12-18 08:00 | 2013-08-15 16:00 | 240 | 608 | 100 | 100 | 0 | 308160 | 308160 | 308160 | 305710.9474 | 1 | 1.008 | FALSE | FALSE | FALSE | 76 | FALSE | 0 | Green | Continue normal monitoring.
144511 | HEPSAAL0010 | Curtain walls | 25718 | 2012-09-25 08:00 | 2013-09-23 16:00 | 363 | 344 | 100 | 98 | -2 | 538329 | 538329 | 527562.42 | 467323.2303 | 0.98 | 1.1289 | FALSE | FALSE | FALSE | 43 | FALSE | 0 | Green | Continue normal monitoring.
144512 | HEPSAAL0020 | Handrails & Railling | 25718 | 2012-09-29 08:00 | 2013-09-26 16:00 | 362 | 344 | 100 | 100 | 0 | 205616 | 205616 | 205616 | 192695.8068 | 1 | 1.067 | FALSE | FALSE | FALSE | 43 | FALSE | 0 | Green | Continue normal monitoring.
144513 | HEPSAAL0030 | Sky lights | 25718 | 2012-11-07 08:00 | 2013-11-06 16:00 | 364 | 1040 | 100 | 91 | -9 | 380380 | 380380 | 346145.8 | 325632.193 | 0.91 | 1.063 | FALSE | FALSE | FALSE | 130 | FALSE | 0 | Green | Continue normal monitoring.
144514 | HEPSAAL0050 | Revolving entrance doors | 25718 | 2013-02-05 08:00 | 2014-02-04 16:00 | 364 | 448 | 100 | 100 | 0 | 200928 | 200928 | 200928 | 217517.9905 | 1 | 0.92373 | FALSE | FALSE | FALSE | 56 | FALSE | 0 | Green | Continue normal monitoring.
144515 | HEPSAAL0060 | Glass panels | 25718 | 2012-12-12 08:00 | 2013-08-06 16:00 | 237 | 648 | 100 | 86 | -14 | 467601 | 467601 | 402136.86 | 417259.6816 | 0.86 | 0.96376 | FALSE | TRUE | TRUE | 81 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144516 | HEPSAAL0070 | Storefront tension cable system | 25718 | 2012-12-06 08:00 | 2013-09-19 16:00 | 287 | 368 | 100 | 100 | 0 | 202048 | 202048 | 202048 | 242297.529 | 1 | 0.83388 | TRUE | FALSE | FALSE | 46 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144517 | HCEWAFZ1000 | ENV :Release (from structure / steel structure works) | 25745 | 2013-04-13 08:00 | 2013-04-13 08:00 | 1 | 1232 | 100 | 89 | -11 | 625 | 625 | 556.25 | 662.0358 | 0.89 | 0.84021 | TRUE | TRUE | TRUE | 154 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144518 | HCEWAFZ1010 | ENV :Survey and setting out | 25745 | 2013-04-13 08:00 | 2013-04-23 16:00 | 10 | 1232 | 100 | 100 | 0 | 5420 | 5420 | 5420 | 6123.9277 | 1 | 0.88505 | TRUE | FALSE | FALSE | 154 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144519 | HCEWAFZ1020 | ENV :Bracket installation | 25745 | 2013-04-24 08:00 | 2013-06-11 16:00 | 48 | 1232 | 100 | 98 | -2 | 29280 | 29280 | 28694.4 | 29699.9583 | 0.98 | 0.96614 | FALSE | FALSE | FALSE | 154 | FALSE | 0 | Green | Continue normal monitoring.
144520 | HCEWAFZ1030 | ENV :Steel frame installation | 25745 | 2013-04-30 08:00 | 2013-06-17 16:00 | 48 | 1232 | 100 | 86 | -14 | 60480 | 60480 | 52012.8 | 64969.5467 | 0.86 | 0.80057 | TRUE | TRUE | TRUE | 154 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144521 | HCEWAFZ1040 | ENV :Aluminum panels installation | 25745 | 2013-05-07 08:00 | 2013-06-23 16:00 | 47 | 1232 | 100 | 100 | 0 | 80182 | 80182 | 80182 | 98388.4193 | 1 | 0.81495 | TRUE | FALSE | FALSE | 154 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144522 | HCEWAFZ1050 | ENV :Unit installation | 25745 | 2013-09-24 08:00 | 2013-11-14 16:00 | 51 | 344 | 100 | 82 | -18 | 68697 | 68697 | 56331.54 | 60665.8821 | 0.82 | 0.92855 | FALSE | TRUE | TRUE | 43 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144523 | HCEWAFZ1060 | ENV :Stone installation | 25745 | 2013-09-30 08:00 | 2013-11-20 16:00 | 51 | 344 | 100 | 92 | -8 | 30294 | 30294 | 27870.48 | 28827.0163 | 0.92 | 0.96682 | FALSE | FALSE | FALSE | 43 | FALSE | 0 | Green | Continue normal monitoring.
144524 | HCEWAFZ2000 | ENV :Release (from structure / steel structure works) | 25758 | 2013-06-08 08:00 | 2013-06-08 08:00 | 1 | 1184 | 100 | 92 | -8 | 1897 | 1897 | 1745.24 | 2204.3051 | 0.92 | 0.79174 | TRUE | FALSE | FALSE | 148 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144525 | HCEWAFZ2010 | ENV :Survey and setting out | 25758 | 2013-06-08 08:00 | 2013-06-18 16:00 | 10 | 1184 | 100 | 97 | -3 | 13990 | 13990 | 13570.3 | 12444.0334 | 0.97 | 1.0905 | FALSE | FALSE | FALSE | 148 | FALSE | 0 | Green | Continue normal monitoring.
144526 | HCEWAFZ2020 | ENV :Bracket installation | 25758 | 2013-06-19 08:00 | 2013-08-04 16:00 | 46 | 1184 | 100 | 100 | 0 | 39514 | 39514 | 39514 | 34782.7691 | 1 | 1.136 | FALSE | FALSE | FALSE | 148 | FALSE | 0 | Green | Continue normal monitoring.
144527 | HCEWAFZ2030 | ENV :Steel frame installation | 25758 | 2013-06-25 08:00 | 2013-08-13 16:00 | 49 | 1184 | 100 | 100 | 0 | 68551 | 68551 | 68551 | 68181.9598 | 1 | 1.0054 | FALSE | FALSE | FALSE | 148 | FALSE | 0 | Green | Continue normal monitoring.
144528 | HCEWAFZ2040 | ENV :Aluminum panels installation | 25758 | 2013-09-24 08:00 | 2013-11-14 16:00 | 51 | 624 | 100 | 100 | 0 | 39780 | 39780 | 39780 | 35279.5766 | 1 | 1.1276 | FALSE | FALSE | FALSE | 78 | FALSE | 0 | Green | Continue normal monitoring.
144529 | HCEWAFZ2050 | ENV :Unit installation | 25758 | 2013-09-30 08:00 | 2013-11-20 16:00 | 51 | 624 | 100 | 99 | -1 | 87618 | 87618 | 86741.82 | 94980.6612 | 0.99 | 0.91326 | FALSE | FALSE | FALSE | 78 | FALSE | 0 | Green | Continue normal monitoring.
144530 | HCEWAFZ2060 | ENV :Stone installation | 25758 | 2013-11-21 08:00 | 2014-01-08 16:00 | 48 | 344 | 100 | 100 | 0 | 82464 | 82464 | 82464 | 77558.2249 | 1 | 1.0633 | FALSE | FALSE | FALSE | 43 | FALSE | 0 | Green | Continue normal monitoring.
144531 | HCEWAFZ3000 | ENV :Release (from structure / steel structure works) | 25749 | 2013-08-12 08:00 | 2013-08-12 08:00 | 1 | 1080 | 100 | 87 | -13 | 1166 | 1166 | 1014.42 | 1408.8535 | 0.87 | 0.72003 | TRUE | TRUE | TRUE | 135 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144532 | HCEWAFZ3010 | ENV :Survey and setting out | 25749 | 2013-08-12 08:00 | 2013-08-22 16:00 | 10 | 1080 | 100 | 100 | 0 | 5920 | 5920 | 5920 | 6887.3282 | 1 | 0.85955 | TRUE | FALSE | FALSE | 135 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144533 | HCEWAFZ3020 | ENV :Bracket installation | 25749 | 2013-08-24 08:00 | 2013-10-08 16:00 | 45 | 1080 | 100 | 100 | 0 | 52695 | 52695 | 52695 | 59539.1363 | 1 | 0.88505 | TRUE | FALSE | FALSE | 135 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144534 | HCEWAFZ3030 | ENV :Steel frame installation | 25749 | 2013-08-29 08:00 | 2013-10-14 16:00 | 46 | 1080 | 100 | 88 | -12 | 25760 | 25760 | 22668.8 | 28252.9913 | 0.88 | 0.80235 | TRUE | TRUE | TRUE | 135 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144535 | HCEWAFZ3040 | ENV :Aluminum panels installation | 25749 | 2013-09-04 08:00 | 2013-10-24 16:00 | 50 | 1080 | 100 | 86 | -14 | 56650 | 56650 | 48719 | 67718.6334 | 0.86 | 0.71943 | TRUE | TRUE | TRUE | 135 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144536 | HCEWAFZ3050 | ENV :Unit installation | 25749 | 2013-09-10 08:00 | 2013-10-30 16:00 | 50 | 1080 | 100 | 80 | -20 | 78700 | 78700 | 62960 | 73916.9937 | 0.8 | 0.85177 | TRUE | TRUE | TRUE | 135 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144537 | HCEWAFZ3060 | ENV :Stone installation | 25749 | 2014-01-09 08:00 | 2014-02-25 16:00 | 47 | 344 | 100 | 82 | -18 | 90522 | 90522 | 74228.04 | 108557.9235 | 0.82 | 0.68376 | TRUE | TRUE | TRUE | 43 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144538 | HCEWAFZ4000 | ENV :Release (from structure / steel structure works) | 25728 | 2013-09-18 08:00 | 2013-09-18 08:00 | 1 | 1144 | 100 | 92 | -8 | 1528 | 1528 | 1405.76 | 1781.3377 | 0.92 | 0.78916 | TRUE | FALSE | FALSE | 143 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144539 | HCEWAFZ4010 | ENV :Survey and setting out | 25728 | 2013-09-18 08:00 | 2013-09-29 16:00 | 11 | 1144 | 100 | 100 | 0 | 21879 | 21879 | 21879 | 25144.7543 | 1 | 0.87012 | TRUE | FALSE | FALSE | 143 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144540 | HCEWAFZ4020 | ENV :Bracket installation | 25728 | 2013-09-30 08:00 | 2013-11-20 16:00 | 51 | 1144 | 100 | 100 | 0 | 56253 | 56253 | 56253 | 60443.9763 | 1 | 0.93066 | FALSE | FALSE | FALSE | 143 | FALSE | 0 | Green | Continue normal monitoring.
144541 | HCEWAFZ4030 | ENV :Steel frame installation | 25728 | 2013-10-06 08:00 | 2013-11-26 16:00 | 51 | 1144 | 100 | 100 | 0 | 60231 | 60231 | 60231 | 57128.9628 | 1 | 1.0543 | FALSE | FALSE | FALSE | 143 | FALSE | 0 | Green | Continue normal monitoring.
144542 | HCEWAFZ4040 | ENV :Aluminum panels installation | 25728 | 2013-10-12 08:00 | 2013-12-02 16:00 | 51 | 1144 | 100 | 100 | 0 | 52683 | 52683 | 52683 | 53706.0599 | 1 | 0.98095 | FALSE | FALSE | FALSE | 143 | FALSE | 0 | Green | Continue normal monitoring.
144543 | HCEWAFZ4050 | ENV :Unit installation | 25728 | 2014-02-05 08:00 | 2014-03-23 16:00 | 46 | 448 | 100 | 100 | 0 | 88688 | 88688 | 88688 | 103536.8777 | 1 | 0.85658 | TRUE | FALSE | FALSE | 56 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144544 | HCEWAFZ4060 | ENV :Stone installation | 25728 | 2014-02-26 08:00 | 2014-04-13 16:00 | 46 | 344 | 100 | 96 | -4 | 61502 | 61502 | 59041.92 | 53058.4761 | 0.96 | 1.1128 | FALSE | FALSE | FALSE | 43 | FALSE | 0 | Green | Continue normal monitoring.
144545 | HCEWAFZ5000 | ENV :Release (from structure / steel structure works) | 25744 | 2013-09-18 08:00 | 2013-09-18 08:00 | 1 | 104 | 100 | 100 | 0 | 1144 | 1144 | 1144 | 1330.2664 | 1 | 0.85998 | TRUE | FALSE | FALSE | 13 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144546 | HCEWAFZ5010 | ENV :Survey and setting out | 25744 | 2013-09-18 08:00 | 2013-09-29 16:00 | 11 | 104 | 100 | 100 | 0 | 8052 | 8052 | 8052 | 7617.4198 | 1 | 1.0571 | FALSE | FALSE | FALSE | 13 | FALSE | 0 | Green | Continue normal monitoring.
144547 | HCEWAFZ5020 | ENV :Steel frame installation | 25744 | 2013-09-30 08:00 | 2013-11-09 16:00 | 40 | 104 | 100 | 80 | -20 | 40920 | 40920 | 32736 | 37144.053 | 0.8 | 0.88133 | TRUE | TRUE | TRUE | 13 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144548 | HCEWAFZ5030 | ENV :Glass installation | 25744 | 2013-11-10 08:00 | 2013-12-26 16:00 | 46 | 104 | 100 | 85 | -15 | 38870 | 38870 | 33039.5 | 34838.4241 | 0.85 | 0.94836 | FALSE | TRUE | TRUE | 13 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144549 | HCEWAFZ5040 | ENV :Aluminum panel installation | 25744 | 2013-12-28 08:00 | 2014-01-08 16:00 | 11 | 104 | 100 | 100 | 0 | 17259 | 17259 | 17259 | 14858.2732 | 1 | 1.1616 | FALSE | FALSE | FALSE | 13 | FALSE | 0 | Green | Continue normal monitoring.
144550 | HCEWAFZ5050 | ENV :Railing installation | 25744 | 2014-01-09 08:00 | 2014-01-21 16:00 | 12 | 104 | 100 | 85 | -15 | 12540 | 12540 | 10659 | 13285.3098 | 0.85 | 0.80231 | TRUE | TRUE | TRUE | 13 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144551 | HCEWAFZ5060 | ENV :Unit installation | 25744 | 2014-01-22 08:00 | 2014-02-02 16:00 | 11 | 104 | 100 | 100 | 0 | 17611 | 17611 | 17611 | 16506.8598 | 1 | 1.0669 | FALSE | FALSE | FALSE | 13 | FALSE | 0 | Green | Continue normal monitoring.
144552 | HCEWAFZ5070 | ENV :Cleaning | 25744 | 2014-02-03 08:00 | 2014-02-18 16:00 | 15 | 712 | 100 | 91 | -9 | 23940 | 23940 | 21785.4 | 29823.7986 | 0.91 | 0.73047 | TRUE | FALSE | FALSE | 89 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144553 | HCSWGFZ1070 | GF Z1 :Installation of steel columns and beams | 25954 | 2013-01-29 08:00 | 2013-02-02 16:00 | 4 | 0 | 100 | 92 | -8 | 5172 | 5172 | 4758.24 | 5584.5948 | 0.92 | 0.85203 | TRUE | FALSE | FALSE | 0 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144554 | HCSWGFZ1080 | GF Z1 :Steel Deck | 25954 | 2013-02-10 08:00 | 2013-02-11 16:00 | 1 | 0 | 100 | 92 | -8 | 748 | 748 | 688.16 | 677.0553 | 0.92 | 1.0164 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144555 | HCSWGFZ1090 | GF Z1 :Casting concrete for slab topping | 25954 | 2013-02-12 08:00 | 2013-02-12 16:00 | 1 | 0 | 100 | 100 | 0 | 546 | 546 | 546 | 614.5257 | 1 | 0.88849 | TRUE | FALSE | FALSE | 0 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144556 | HCSWGFZ2000 | GF Z2 :Formwork core wall shutters - 1st side | 25956 | 2013-01-28 08:00 | 2013-02-05 16:00 | 8 | 16 | 100 | 94 | -6 | 13152 | 13152 | 12362.88 | 15902.0494 | 0.94 | 0.77744 | TRUE | FALSE | FALSE | 2 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144557 | HCSWGFZ2010 | GF Z2 :Fix steel rebar for core wall | 25956 | 2013-02-06 08:00 | 2013-02-10 16:00 | 4 | 16 | 100 | 100 | 0 | 2852 | 2852 | 2852 | 3274.3008 | 1 | 0.87103 | TRUE | FALSE | FALSE | 2 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144558 | HCSWGFZ2020 | GF Z2 :Fix MEP first fix in core wall | 25956 | 2013-02-12 08:00 | 2013-02-12 16:00 | 1 | 16 | 100 | 95 | -5 | 738 | 738 | 701.1 | 649.865 | 0.95 | 1.0788 | FALSE | FALSE | FALSE | 2 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144559 | HCSWGFZ2030 | GF Z2 :Close shutter for core wall | 25956 | 2013-02-13 08:00 | 2013-02-17 16:00 | 4 | 16 | 100 | 100 | 0 | 6316 | 6316 | 6316 | 7631.9618 | 1 | 0.82757 | TRUE | FALSE | FALSE | 2 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144560 | HCSWGFZ2040 | GF Z2 :Cast concrete for core wall | 25956 | 2013-02-18 08:00 | 2013-02-18 16:00 | 1 | 16 | 100 | 100 | 0 | 849 | 849 | 849 | 991.2684 | 1 | 0.85648 | TRUE | FALSE | FALSE | 2 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144561 | HCSWGFZ2050 | GF Z2 :De-shutter core wall formwork | 25956 | 2013-02-19 08:00 | 2013-02-19 16:00 | 1 | 16 | 100 | 90 | -10 | 606 | 606 | 545.4 | 553.4729 | 0.9 | 0.98541 | FALSE | FALSE | TRUE | 2 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144562 | HCSWGFZ2060 | GF Z2 :Provision & Installation of steel embedded plates | 25957 | 2013-02-11 08:00 | 2013-02-12 16:00 | 1 | 16 | 100 | 100 | 0 | 1330 | 1330 | 1330 | 1158.0501 | 1 | 1.1485 | FALSE | FALSE | FALSE | 2 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144563 | HCSWGFZ2070 | GF Z2 :Installation of steel columns and beams | 25957 | 2013-04-13 08:00 | 2013-04-15 16:00 | 2 | 0 | 100 | 84 | -16 | 1094 | 1094 | 918.96 | 1173.7791 | 0.84 | 0.78291 | TRUE | TRUE | TRUE | 0 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
144564 | HCSWGFZ2080 | GF Z2 :Steel Deck | 25957 | 2013-04-16 08:00 | 2013-04-17 16:00 | 1 | 0 | 100 | 83 | -17 | 836 | 836 | 693.88 | 762.7784 | 0.83 | 0.90967 | FALSE | TRUE | TRUE | 0 | TRUE | 4 | Orange | Develop recovery plan and review schedule and cost exposure.
144565 | HCSWGFZ2090 | GF Z2 :Casting concrete for slab topping | 25957 | 2013-04-18 08:00 | 2013-04-18 16:00 | 1 | 0 | 100 | 82 | -18 | 1549 | 1549 | 1270.18 | 1833.7626 | 0.82 | 0.69266 | TRUE | TRUE | TRUE | 0 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
144566 | HCSWGFZ3000 | GF Z3 :Formwork core wall shutters - 1st side | 25959 | 2013-03-19 08:00 | 2013-03-24 16:00 | 5 | 128 | 100 | 98 | -2 | 6515 | 6515 | 6384.7 | 6471.5701 | 0.98 | 0.98658 | FALSE | FALSE | FALSE | 16 | FALSE | 0 | Green | Continue normal monitoring.
144567 | HCSWGFZ3010 | GF Z3 :Fix steel rebar for core wall | 25959 | 2013-03-25 08:00 | 2013-03-26 16:00 | 1 | 128 | 100 | 99 | -1 | 1780 | 1780 | 1762.2 | 2162.9794 | 0.99 | 0.81471 | TRUE | FALSE | FALSE | 16 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144568 | HCSWGFZ3020 | GF Z3 :Fix MEP first fix in core wall | 25959 | 2013-03-27 08:00 | 2013-03-27 16:00 | 1 | 128 | 100 | 100 | 0 | 507 | 507 | 507 | 545.6716 | 1 | 0.92913 | FALSE | FALSE | FALSE | 16 | FALSE | 0 | Green | Continue normal monitoring.
144569 | HCSWGFZ3030 | GF Z3 :Close shutter for core wall | 25959 | 2013-03-28 08:00 | 2013-03-30 16:00 | 2 | 128 | 100 | 97 | -3 | 2248 | 2248 | 2180.56 | 2075.059 | 0.97 | 1.0508 | FALSE | FALSE | FALSE | 16 | FALSE | 0 | Green | Continue normal monitoring.
144570 | HCSWGFZ3040 | GF Z3 :Cast concrete for core wall | 25959 | 2013-03-31 08:00 | 2013-03-31 16:00 | 1 | 128 | 100 | 94 | -6 | 1776 | 1776 | 1669.44 | 1608.771 | 0.94 | 1.0377 | FALSE | FALSE | FALSE | 16 | FALSE | 0 | Green | Continue normal monitoring.
144571 | HCSWGFZ3050 | GF Z3 :De-shutter core wall formwork | 25959 | 2013-04-01 08:00 | 2013-04-01 16:00 | 1 | 128 | 100 | 88 | -12 | 1218 | 1218 | 1071.84 | 1316.1574 | 0.88 | 0.81437 | TRUE | TRUE | TRUE | 16 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144572 | HCSWGFZ3060 | GF Z3 :Provision & Installation of steel embedded plates | 25960 | 2013-03-27 08:00 | 2013-03-27 16:00 | 1 | 128 | 100 | 96 | -4 | 802 | 802 | 769.92 | 926.1123 | 0.96 | 0.83135 | TRUE | FALSE | FALSE | 16 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144573 | HCSWGFZ3070 | GF Z3 :Installation of steel columns and beams | 25960 | 2013-06-08 08:00 | 2013-06-11 16:00 | 3 | 0 | 100 | 93 | -7 | 3414 | 3414 | 3175.02 | 3969.1241 | 0.93 | 0.79993 | TRUE | FALSE | FALSE | 0 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144574 | HCSWGFZ3080 | GF Z3 :Steel Deck | 25960 | 2013-06-12 08:00 | 2013-06-15 16:00 | 3 | 0 | 100 | 94 | -6 | 1665 | 1665 | 1565.1 | 1598.9044 | 0.94 | 0.97886 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144575 | HCSSGFZ3090 | GF Z3 :Casting concrete for slab topping | 25960 | 2013-06-16 08:00 | 2013-06-16 16:00 | 1 | 0 | 100 | 100 | 0 | 1225 | 1225 | 1225 | 1141.3309 | 1 | 1.0733 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144576 | HCSWB4Z5090 | B4 Z5 :Formwork core wall shutters - 1st side | 25961 | 2012-09-10 08:00 | 2012-09-16 16:00 | 6 | 8 | 100 | 80 | -20 | 6150 | 6150 | 4920 | 5268.7205 | 0.8 | 0.93381 | FALSE | TRUE | TRUE | 1 | TRUE | 4 | Orange | Develop recovery plan and review schedule and cost exposure.
144577 | HCSWB4Z5100 | B4 Z5 :Fix steel rebar for core wall | 25961 | 2012-09-17 08:00 | 2012-09-20 16:00 | 3 | 8 | 100 | 100 | 0 | 2919 | 2919 | 2919 | 3274.1829 | 1 | 0.89152 | TRUE | FALSE | FALSE | 1 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144578 | HCSWB4Z5110 | B4 Z5 :Fix MEP first fix in core wall | 25961 | 2012-09-22 08:00 | 2012-09-22 16:00 | 1 | 8 | 100 | 100 | 0 | 527 | 527 | 527 | 464.0906 | 1 | 1.1356 | FALSE | FALSE | FALSE | 1 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144579 | HCSWB4Z5120 | B4 Z5 :Close shutter for core wall | 25961 | 2012-09-23 08:00 | 2012-09-25 16:00 | 2 | 8 | 100 | 100 | 0 | 1154 | 1154 | 1154 | 1175.1234 | 1 | 0.98202 | FALSE | FALSE | FALSE | 1 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144580 | HCSWB4Z5130 | B4 Z5 :Cast concrete for core wall | 25961 | 2012-09-26 08:00 | 2012-09-26 16:00 | 1 | 8 | 100 | 82 | -18 | 1739 | 1739 | 1425.98 | 1896.6801 | 0.82 | 0.75183 | TRUE | TRUE | TRUE | 1 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
144581 | HCSWB4Z5140 | B4 Z5 :De-shutter core wall formwork | 25961 | 2012-09-27 08:00 | 2012-09-29 16:00 | 2 | 8 | 100 | 95 | -5 | 3818 | 3818 | 3627.1 | 4676.4528 | 0.95 | 0.77561 | TRUE | FALSE | FALSE | 1 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144582 | HCSWB4Z1250 | B4 Z1 :Backfill behind basement walls up to anchor level | 26110 | 2012-09-17 08:00 | 2012-10-09 16:00 | 22 | 464 | 100 | 100 | 0 | 19008 | 19008 | 19008 | 18527.494 | 1 | 1.0259 | FALSE | FALSE | FALSE | 58 | FALSE | 0 | Green | Continue normal monitoring.
144583 | HCSWB4Z2090 | B4 Z2 :Backfill behind basement walls up to anchor level | 26111 | 2012-09-12 08:00 | 2012-10-04 16:00 | 22 | 496 | 100 | 100 | 0 | 25630 | 25630 | 25630 | 24346.1642 | 1 | 1.0527 | FALSE | FALSE | FALSE | 62 | FALSE | 0 | Green | Continue normal monitoring.
144584 | HCSWB4Z3250 | B4 Z3 :Backfill behind basement walls up to anchor level | 26112 | 2012-09-27 08:00 | 2012-10-10 16:00 | 13 | 928 | 100 | 90 | -10 | 13325 | 13325 | 11992.5 | 14812.9236 | 0.9 | 0.8096 | TRUE | FALSE | FALSE | 116 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144585 | HCSWB4Z4090 | B4 Z4 :Backfill behind basement walls up to anchor level | 26113 | 2012-10-09 08:00 | 2012-10-22 16:00 | 13 | 832 | 100 | 91 | -9 | 15574 | 15574 | 14172.34 | 17095.5115 | 0.91 | 0.82901 | TRUE | FALSE | FALSE | 104 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144586 | HCSWB4Z5250 | B4 Z5 :Backfill behind basement walls up to anchor level | 26114 | 2012-10-14 08:00 | 2012-11-03 16:00 | 20 | 680 | 100 | 89 | -11 | 36700 | 36700 | 32663 | 36070.3716 | 0.89 | 0.90554 | FALSE | TRUE | TRUE | 85 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144587 | HCSWB4Z6090 | B4 Z6 :Backfill behind basement walls up to anchor level | 26115 | 2012-11-14 08:00 | 2012-12-01 16:00 | 17 | 576 | 100 | 95 | -5 | 23494 | 23494 | 22319.3 | 28691.8298 | 0.95 | 0.7779 | TRUE | FALSE | FALSE | 72 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144588 | HCSWB4Z6100 | B4 Z6 :De-tensioning | 26115 | 2012-12-02 08:00 | 2012-12-03 16:00 | 1 | 576 | 100 | 87 | -13 | 1530 | 1530 | 1331.1 | 1817.5557 | 0.87 | 0.73236 | TRUE | TRUE | TRUE | 72 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144589 | HCFWB400000 | Start Finishing Works B4 | 25831 | 2012-10-01 08:00 | 2012-10-01 08:00 | 1 | 220 | 100 | 85 | -15 | 1526 | 1526 | 1297.1 | 1433.8189 | 0.85 | 0.90465 | FALSE | TRUE | TRUE | 27.5 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144590 | HCFWB400001 | End Finishing Works B4 | 25831 | 2014-01-21 16:00 | 2014-01-21 16:00 | 1 | 904 | 100 | 91 | -9 | 1418 | 1418 | 1290.38 | 1340.9417 | 0.91 | 0.96229 | FALSE | FALSE | FALSE | 113 | FALSE | 0 | Green | Continue normal monitoring.
144591 | HCFWB1Z1002 | B1 Z1 :Trawelled smooth Concrete screed | 26187 | 2013-04-04 12:00 | 2013-04-14 12:00 | 10 | 554 | 100 | 100 | 0 | 12490 | 12490 | 12490 | 13175.9525 | 1 | 0.94794 | FALSE | FALSE | FALSE | 69.25 | FALSE | 0 | Green | Continue normal monitoring.
144592 | HCFWB1Z1003 | B1 Z1 :Sealed Concrete | 26187 | 2013-05-22 14:00 | 2013-06-02 14:00 | 11 | 1186 | 100 | 100 | 0 | 9482 | 9482 | 9482 | 10993.7043 | 1 | 0.86249 | TRUE | FALSE | FALSE | 148.25 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144593 | HCFWB1Z1011 | B1 Z1 :Block Works | 26249 | 2013-02-04 08:00 | 2013-02-14 16:00 | 10 | 288 | 100 | 100 | 0 | 17970 | 17970 | 17970 | 15591.0622 | 1 | 1.1526 | FALSE | FALSE | FALSE | 36 | FALSE | 0 | Green | Continue normal monitoring.
144594 | HCFWB1Z1006 | B1 Z1 :Plaster First Layer | 26249 | 2013-02-16 08:00 | 2013-02-25 14:00 | 9 | 554 | 100 | 87 | -13 | 11745 | 11745 | 10218.15 | 13240.5386 | 0.87 | 0.77173 | TRUE | TRUE | TRUE | 69.25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144595 | HCFWB1Z1001 | B1 Z1 :Foam Concrete Under Floorings | 26187 | 2013-03-17 12:00 | 2013-04-04 12:00 | 18 | 554 | 100 | 100 | 0 | 22284 | 22284 | 22284 | 24719.5155 | 1 | 0.90147 | FALSE | FALSE | FALSE | 69.25 | FALSE | 0 | Green | Continue normal monitoring.
144596 | HCFWB1Z1008 | B1 Z1 :Plaster Final Layer | 26249 | 2013-03-06 14:00 | 2013-03-17 12:00 | 10 | 554 | 100 | 100 | 0 | 15380 | 15380 | 15380 | 14497.0656 | 1 | 1.0609 | FALSE | FALSE | FALSE | 69.25 | FALSE | 0 | Green | Continue normal monitoring.
144597 | HCFWB1Z1009 | B1 Z1 :Paint First Layer | 26249 | 2013-06-02 14:00 | 2013-06-16 14:00 | 14 | 1186 | 100 | 83 | -17 | 24010 | 24010 | 19928.3 | 26952.2143 | 0.83 | 0.73939 | TRUE | TRUE | TRUE | 148.25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144598 | HCFWB1Z1010 | B1 Z1 :Paint Final Layer | 26249 | 2013-07-14 08:00 | 2013-07-27 16:00 | 13 | 1336 | 100 | 100 | 0 | 12792 | 12792 | 12792 | 15683.9294 | 1 | 0.81561 | TRUE | FALSE | FALSE | 167 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144599 | HCFWB1Z1012 | B1 Z1 :Plaster First Layer | 26238 | 2013-04-14 12:00 | 2013-04-24 10:00 | 9 | 554 | 100 | 87 | -13 | 4743 | 4743 | 4126.41 | 4120.3121 | 0.87 | 1.0015 | FALSE | TRUE | TRUE | 69.25 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144600 | HCFWB1Z1014 | B1 Z1 :Plaster Final Layer | 26238 | 2013-05-05 10:00 | 2013-05-22 14:00 | 17 | 554 | 100 | 100 | 0 | 20621 | 20621 | 20621 | 20164.468 | 1 | 1.0226 | FALSE | FALSE | FALSE | 69.25 | FALSE | 0 | Green | Continue normal monitoring.
144601 | HCFWB1Z1015 | B1 Z1 :Paint First Layer | 26238 | 2013-06-16 14:00 | 2013-06-27 14:00 | 11 | 1186 | 100 | 100 | 0 | 17182 | 17182 | 17182 | 17616.2009 | 1 | 0.97535 | FALSE | FALSE | FALSE | 148.25 | FALSE | 0 | Green | Continue normal monitoring.
144602 | HCFWB1Z1016 | B1 Z1 :Paint Final Layer | 26238 | 2013-06-27 14:00 | 2013-07-09 14:00 | 12 | 1186 | 100 | 97 | -3 | 21552 | 21552 | 20905.44 | 26071.5437 | 0.97 | 0.80185 | TRUE | FALSE | FALSE | 148.25 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144603 | HCFWB1Z1020 | B1 Z1 :Steel Fire Rated Doors | 26250 | 2013-12-09 08:00 | 2013-12-19 16:00 | 10 | 424 | 100 | 100 | 0 | 17540 | 17540 | 17540 | 21660.2263 | 1 | 0.80978 | TRUE | FALSE | FALSE | 53 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144604 | HCFWB1Z1004 | B1 Z1 :Rubber Flooring | 26187 | 2013-05-22 14:00 | 2013-06-04 14:00 | 13 | 554 | 100 | 100 | 0 | 7605 | 7605 | 7605 | 7815.2486 | 1 | 0.9731 | FALSE | FALSE | FALSE | 69.25 | FALSE | 0 | Green | Continue normal monitoring.
144605 | HCFWB1Z1005 | B1 Z1 :Rubber Skirting | 26187 | 2013-12-18 08:00 | 2013-12-19 16:00 | 1 | 208 | 100 | 84 | -16 | 1997 | 1997 | 1677.48 | 2296.5727 | 0.84 | 0.73043 | TRUE | TRUE | TRUE | 26 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144606 | HCFWB1Z1019 | B1 Z1 :Steel Doors | 26250 | 2013-12-21 08:00 | 2014-01-02 16:00 | 12 | 344 | 100 | 88 | -12 | 7500 | 7500 | 6600 | 7969.9831 | 0.88 | 0.82811 | TRUE | TRUE | TRUE | 43 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144607 | HCFWB1Z1021 | B1 Z1 :Wooden & Glass Doors & Partitions | 26250 | 2013-12-21 08:00 | 2014-01-08 16:00 | 18 | 344 | 100 | 83 | -17 | 23598 | 23598 | 19586.34 | 25134.5407 | 0.83 | 0.77926 | TRUE | TRUE | TRUE | 43 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144608 | HCFWB10000 | Start Finishing Works B1 | 25854 | 2013-01-30 08:00 | 2013-01-30 08:00 | 1 | 320 | 100 | 100 | 0 | 1036 | 1036 | 1036 | 995.8444 | 1 | 1.0403 | FALSE | FALSE | FALSE | 40 | FALSE | 0 | Green | Continue normal monitoring.
144609 | HCFWB10001 | End Finishing Works B1 | 25854 | 2014-03-24 12:00 | 2014-03-24 12:00 | 1 | 164 | 100 | 100 | 0 | 644 | 644 | 644 | 603.2879 | 1 | 1.0675 | FALSE | FALSE | FALSE | 20.5 | FALSE | 0 | Green | Continue normal monitoring.
144610 | HCFWB1Z1017 | B1 Z1 :Gybsum Board Ceiling | 26238 | 2013-11-27 08:00 | 2013-12-12 16:00 | 15 | 288 | 100 | 100 | 0 | 26025 | 26025 | 26025 | 25119.3857 | 1 | 1.0361 | FALSE | FALSE | FALSE | 36 | FALSE | 0 | Green | Continue normal monitoring.
144611 | HCFWB1Z1018 | B1 Z1 :Metal Works | 26250 | 2013-12-09 08:00 | 2013-12-19 16:00 | 10 | 208 | 100 | 96 | -4 | 5240 | 5240 | 5030.4 | 5620.0635 | 0.96 | 0.89508 | TRUE | FALSE | FALSE | 26 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144612 | HCFWB1Z1022 | B1 Z1 :Handrails & Railling | 26250 | 2013-12-15 08:00 | 2014-01-02 16:00 | 18 | 224 | 100 | 88 | -12 | 34506 | 34506 | 30365.28 | 29732.5115 | 0.88 | 1.0213 | FALSE | TRUE | TRUE | 28 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144613 | HCFWB4Z1002 | B4 Z1 :Trawelled smooth Concrete screed | 26248 | 2013-01-13 14:00 | 2013-01-22 14:00 | 9 | 650 | 100 | 80 | -20 | 5094 | 5094 | 4075.2 | 6178.5104 | 0.8 | 0.65958 | TRUE | TRUE | TRUE | 81.25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144614 | HCFWB4Z1004 | B4 Z1 :Sealed Concrete | 26248 | 2013-02-16 14:00 | 2013-02-25 14:00 | 9 | 650 | 100 | 100 | 0 | 6588 | 6588 | 6588 | 6011.6388 | 1 | 1.0959 | FALSE | FALSE | FALSE | 81.25 | FALSE | 0 | Green | Continue normal monitoring.
144615 | HCFWB4Z1007 | B4 Z1 :Block Works | 26369 | 2012-10-01 08:00 | 2012-10-11 16:00 | 10 | 140 | 100 | 99 | -1 | 6080 | 6080 | 6019.2 | 5703.2557 | 0.99 | 1.0554 | FALSE | FALSE | FALSE | 17.5 | FALSE | 0 | Green | Continue normal monitoring.
144616 | HCFWB4Z1008 | B4 Z1 :Plaster First Layer | 26369 | 2012-10-13 08:00 | 2012-10-22 14:00 | 9 | 140 | 100 | 92 | -8 | 15021 | 15021 | 13819.32 | 15881.8606 | 0.92 | 0.87013 | TRUE | FALSE | FALSE | 17.5 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144617 | HCFWB4Z1001 | B4 Z1 :Foam Concrete & Proofing Membrane Under Floorings | 26248 | 2012-12-24 14:00 | 2013-01-13 14:00 | 20 | 650 | 100 | 100 | 0 | 12200 | 12200 | 12200 | 13835.3601 | 1 | 0.8818 | TRUE | FALSE | FALSE | 81.25 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144618 | HCFWB4Z1010 | B4 Z1 :Plaster Final Layer | 26369 | 2012-11-05 14:00 | 2012-11-17 12:00 | 11 | 650 | 100 | 95 | -5 | 7997 | 7997 | 7597.15 | 7103.6681 | 0.95 | 1.0695 | FALSE | FALSE | FALSE | 81.25 | FALSE | 0 | Green | Continue normal monitoring.
144619 | HCFWB4Z1011 | B4 Z1 :Paint First Layer | 26369 | 2013-06-16 08:00 | 2013-06-19 16:00 | 3 | 24 | 100 | 100 | 0 | 1830 | 1830 | 1830 | 1788.0525 | 1 | 1.0235 | FALSE | FALSE | FALSE | 3 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144620 | HCFWB4Z1012 | B4 Z1 :Paint Final Layer | 26369 | 2013-06-20 08:00 | 2013-06-24 16:00 | 4 | 24 | 100 | 92 | -8 | 7972 | 7972 | 7334.24 | 9865.1096 | 0.92 | 0.74345 | TRUE | FALSE | FALSE | 3 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144621 | HCFWB4Z1003 | B4 Z1 :Epoxy Screed Finish Works | 26248 | 2013-02-04 14:00 | 2013-02-16 14:00 | 12 | 730 | 100 | 93 | -7 | 6396 | 6396 | 5948.28 | 6107.7782 | 0.93 | 0.97389 | FALSE | FALSE | FALSE | 91.25 | FALSE | 0 | Green | Continue normal monitoring.
144622 | HCFWB4Z1013 | B4 Z1 :Plaster First Layer | 26130 | 2012-11-17 12:00 | 2012-11-27 10:00 | 9 | 650 | 100 | 82 | -18 | 10098 | 10098 | 8280.36 | 9847.7721 | 0.82 | 0.84084 | TRUE | TRUE | TRUE | 81.25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144623 | HCFWB4Z1015 | B4 Z1 :Plaster Final Layer | 26130 | 2012-12-06 10:00 | 2012-12-24 14:00 | 18 | 650 | 100 | 100 | 0 | 34056 | 34056 | 34056 | 40342.717 | 1 | 0.84417 | TRUE | FALSE | FALSE | 81.25 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144624 | HCFWB4Z1016 | B4 Z1 :Paint First Layer | 26130 | 2013-01-22 14:00 | 2013-02-04 14:00 | 13 | 650 | 100 | 85 | -15 | 16211 | 16211 | 13779.35 | 14104.9605 | 0.85 | 0.97692 | FALSE | TRUE | TRUE | 81.25 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144625 | HCFWB4Z1017 | B4 Z1 :Paint Final Layer | 26130 | 2013-02-04 14:00 | 2013-02-16 14:00 | 12 | 650 | 100 | 97 | -3 | 13128 | 13128 | 12734.16 | 13598.5767 | 0.97 | 0.93643 | FALSE | FALSE | FALSE | 81.25 | FALSE | 0 | Green | Continue normal monitoring.
144626 | HCFWB4Z1021 | B4 Z1 :Steel Fire Rated Doors | 26335 | 2013-10-09 08:00 | 2013-10-24 16:00 | 15 | 480 | 100 | 98 | -2 | 13860 | 13860 | 13582.8 | 13885.5953 | 0.98 | 0.97819 | FALSE | FALSE | FALSE | 60 | FALSE | 0 | Green | Continue normal monitoring.
144627 | HCFWB4Z1005 | B4 Z1 :Rubber Flooring With Spicial Adhesive | 26248 | 2013-02-16 14:00 | 2013-02-27 14:00 | 11 | 650 | 100 | 84 | -16 | 12232 | 12232 | 10274.88 | 11946.1957 | 0.84 | 0.8601 | TRUE | TRUE | TRUE | 81.25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144628 | HCFWB4Z1006 | B4 Z1 :Rubber Skirting | 26248 | 2013-02-27 14:00 | 2013-03-02 14:00 | 3 | 1850 | 100 | 94 | -6 | 3573 | 3573 | 3358.62 | 3445.3719 | 0.94 | 0.97482 | FALSE | FALSE | FALSE | 231.25 | FALSE | 0 | Green | Continue normal monitoring.
144629 | HCFWB4Z1020 | B4 Z1 :Steel Doors | 26335 | 2013-09-28 08:00 | 2013-10-08 16:00 | 10 | 480 | 100 | 100 | 0 | 18050 | 18050 | 18050 | 16002.221 | 1 | 1.128 | FALSE | FALSE | FALSE | 60 | FALSE | 0 | Green | Continue normal monitoring.
144630 | HCFWB4Z1022 | B4 Z1 :Wooden Doors | 26335 | 2013-10-26 08:00 | 2013-11-06 16:00 | 11 | 480 | 100 | 81 | -19 | 20273 | 20273 | 16421.13 | 19785.0356 | 0.81 | 0.82998 | TRUE | TRUE | TRUE | 60 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144631 | HCFWB4Z1018 | B4 Z1 :Gybsum Board Ceiling | 26130 | 2013-10-02 08:00 | 2013-10-23 16:00 | 21 | 208 | 100 | 89 | -11 | 41286 | 41286 | 36744.54 | 35804.0846 | 0.89 | 1.0263 | FALSE | TRUE | TRUE | 26 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144632 | HCFWB4Z1019 | B4 Z1 :Metal Works & Gutters | 26335 | 2013-09-28 08:00 | 2013-10-08 16:00 | 10 | 424 | 100 | 100 | 0 | 8140 | 8140 | 8140 | 9461.8183 | 1 | 0.8603 | TRUE | FALSE | FALSE | 53 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144633 | HCFWB4Z1023 | B4 Z1 :Handrails & Railling | 26335 | 2013-09-28 08:00 | 2013-10-14 16:00 | 16 | 344 | 100 | 100 | 0 | 22016 | 22016 | 22016 | 22220.5532 | 1 | 0.99079 | FALSE | FALSE | FALSE | 43 | FALSE | 0 | Green | Continue normal monitoring.
144634 | HCFWB4Z1009 | B4 Z1 :Plaster Second Layer | 26369 | 2012-10-22 14:00 | 2012-11-05 14:00 | 14 | 650 | 100 | 97 | -3 | 26600 | 26600 | 25802 | 27333.1368 | 0.97 | 0.94398 | FALSE | FALSE | FALSE | 81.25 | FALSE | 0 | Green | Continue normal monitoring.
144635 | HCFWB4Z1014 | B4 Z1 :Plaster Second Layer | 26130 | 2012-11-27 10:00 | 2012-12-06 10:00 | 9 | 650 | 100 | 100 | 0 | 16308 | 16308 | 16308 | 19690.8962 | 1 | 0.8282 | TRUE | FALSE | FALSE | 81.25 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144636 | HCFWB4Z2003 | B4 Z2 :Trawelled smooth Concrete screed | 26218 | 2012-12-05 12:00 | 2012-12-15 12:00 | 10 | 140 | 100 | 92 | -8 | 19600 | 19600 | 18032 | 21819.1511 | 0.92 | 0.82643 | TRUE | FALSE | FALSE | 17.5 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144637 | HCFWB4Z2001 | B4 Z2 :Sealed Concrete | 26218 | 2013-02-16 14:00 | 2013-02-25 14:00 | 9 | 650 | 100 | 84 | -16 | 10449 | 10449 | 8777.16 | 8915.3338 | 0.84 | 0.9845 | FALSE | TRUE | TRUE | 81.25 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144638 | HCFWB4Z2000 | B4 Z2 :Block Works | 26191 | 2012-09-26 08:00 | 2012-10-07 16:00 | 11 | 172 | 100 | 100 | 0 | 8536 | 8536 | 8536 | 10475.9761 | 1 | 0.81482 | TRUE | FALSE | FALSE | 21.5 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144639 | HCFWB4Z20000 | B4 Z2 :Plaster First Layer | 26191 | 2012-10-13 08:00 | 2012-10-22 14:00 | 9 | 140 | 100 | 100 | 0 | 10107 | 10107 | 10107 | 9549.6776 | 1 | 1.0584 | FALSE | FALSE | FALSE | 17.5 | FALSE | 0 | Green | Continue normal monitoring.
144640 | HCFWB4Z2002 | B4 Z2 :Foam Concrete & Proofing Membrane Under Floorings | 26218 | 2012-11-17 12:00 | 2012-12-05 12:00 | 18 | 140 | 100 | 80 | -20 | 18270 | 18270 | 14616 | 16315.9445 | 0.8 | 0.89581 | TRUE | TRUE | TRUE | 17.5 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144641 | HCFWB4Z2007 | B4 Z2 :Plaster Final Layer | 26191 | 2012-11-05 14:00 | 2012-11-17 12:00 | 11 | 140 | 100 | 100 | 0 | 20603 | 20603 | 20603 | 23842.8479 | 1 | 0.86412 | TRUE | FALSE | FALSE | 17.5 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144642 | HCFWB4Z2009 | B4 Z2 :Paint First Layer | 26191 | 2012-11-17 12:00 | 2012-12-01 12:00 | 14 | 908 | 100 | 80 | -20 | 18788 | 18788 | 15030.4 | 19730.9871 | 0.8 | 0.76177 | TRUE | TRUE | TRUE | 113.5 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144643 | HCFWB4Z2012 | B4 Z2 :Paint Final Layer | 26191 | 2012-12-01 12:00 | 2012-12-15 12:00 | 14 | 908 | 100 | 97 | -3 | 27566 | 27566 | 26739.02 | 28214.0278 | 0.97 | 0.94772 | FALSE | FALSE | FALSE | 113.5 | FALSE | 0 | Green | Continue normal monitoring.
144644 | HCFWB4Z2004 | B4 Z2 :Epoxy Screed Finish Works | 26218 | 2013-02-16 14:00 | 2013-02-27 14:00 | 11 | 650 | 100 | 94 | -6 | 9339 | 9339 | 8778.66 | 8870.1937 | 0.94 | 0.98968 | FALSE | FALSE | FALSE | 81.25 | FALSE | 0 | Green | Continue normal monitoring.
144645 | HCFWB4Z2015 | B4 Z2 :Plaster First Layer | 26128 | 2012-12-15 12:00 | 2012-12-25 10:00 | 9 | 140 | 100 | 96 | -4 | 11898 | 11898 | 11422.08 | 12718.8263 | 0.96 | 0.89805 | TRUE | FALSE | FALSE | 17.5 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144646 | HCFWB4Z2013 | B4 Z2 :Plaster Final Layer | 26128 | 2013-01-05 10:00 | 2013-01-22 14:00 | 17 | 650 | 100 | 90 | -10 | 28220 | 28220 | 25398 | 27084.2534 | 0.9 | 0.93774 | FALSE | FALSE | FALSE | 81.25 | FALSE | 0 | Green | Continue normal monitoring.
144647 | HCFWB4Z2014 | B4 Z2 :Paint First Layer | 26128 | 2013-01-22 14:00 | 2013-02-04 14:00 | 13 | 650 | 100 | 100 | 0 | 16354 | 16354 | 16354 | 19798.6954 | 1 | 0.82601 | TRUE | FALSE | FALSE | 81.25 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144648 | HCFWB4Z2017 | B4 Z2 :Paint Final Layer | 26128 | 2013-02-04 14:00 | 2013-02-16 14:00 | 12 | 650 | 100 | 100 | 0 | 16776 | 16776 | 16776 | 15703.7081 | 1 | 1.0683 | FALSE | FALSE | FALSE | 81.25 | FALSE | 0 | Green | Continue normal monitoring.
144649 | HCFWB4Z2021 | B4 Z2 :Steel Fire Rated Doors | 26180 | 2013-10-20 08:00 | 2013-10-30 16:00 | 10 | 560 | 100 | 100 | 0 | 7420 | 7420 | 7420 | 8931.7661 | 1 | 0.83074 | TRUE | FALSE | FALSE | 70 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144650 | HCFWB4Z2005 | B4 Z2 :Rubber Flooring With Spicial Adhesive | 26218 | 2013-02-16 14:00 | 2013-02-27 14:00 | 11 | 650 | 100 | 100 | 0 | 11462 | 11462 | 11462 | 12307.462 | 1 | 0.9313 | FALSE | FALSE | FALSE | 81.25 | FALSE | 0 | Green | Continue normal monitoring.
144651 | HCFWB4Z2006 | B4 Z2 :Rubber Skirting | 26218 | 2013-03-02 14:00 | 2013-03-04 14:00 | 2 | 1850 | 100 | 100 | 0 | 3126 | 3126 | 3126 | 3693.0416 | 1 | 0.84646 | TRUE | FALSE | FALSE | 231.25 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144652 | HCFWB4Z2020 | B4 Z2 :Steel Doors | 26180 | 2013-10-20 08:00 | 2013-10-30 16:00 | 10 | 560 | 100 | 100 | 0 | 7280 | 7280 | 7280 | 8263.8075 | 1 | 0.88095 | TRUE | FALSE | FALSE | 70 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144653 | HCFWB4Z2022 | B4 Z2 :Wooden Doors | 26180 | 2013-10-20 08:00 | 2013-10-30 16:00 | 10 | 640 | 100 | 100 | 0 | 10470 | 10470 | 10470 | 11817.2591 | 1 | 0.88599 | TRUE | FALSE | FALSE | 80 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144654 | HCFWB4Z2018 | B4 Z2 :Gybsum Board Ceiling | 26128 | 2013-10-02 08:00 | 2013-10-22 16:00 | 20 | 296 | 100 | 96 | -4 | 28380 | 28380 | 27244.8 | 27804.9736 | 0.96 | 0.97985 | FALSE | FALSE | FALSE | 37 | FALSE | 0 | Green | Continue normal monitoring.
144655 | HCFWB4Z2019 | B4 Z2 :Metal Works & Gutters | 26180 | 2013-09-28 08:00 | 2013-10-08 16:00 | 10 | 424 | 100 | 92 | -8 | 17460 | 17460 | 16063.2 | 16474.5362 | 0.92 | 0.97503 | FALSE | FALSE | FALSE | 53 | FALSE | 0 | Green | Continue normal monitoring.
144656 | HCFWB4Z2023 | B4 Z2 :Handrails & Railling | 26180 | 2013-09-28 08:00 | 2013-10-14 16:00 | 16 | 344 | 100 | 80 | -20 | 8080 | 8080 | 6464 | 7549.5843 | 0.8 | 0.85621 | TRUE | TRUE | TRUE | 43 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144657 | HCFWB4Z2011 | B4 Z2 :Plaster Second Layer | 26191 | 2012-10-22 14:00 | 2012-11-05 14:00 | 14 | 140 | 100 | 81 | -19 | 25830 | 25830 | 20922.3 | 30812.0042 | 0.81 | 0.67903 | TRUE | TRUE | TRUE | 17.5 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144658 | HCFWB4Z2016 | B4 Z2 :Plaster Second Layer | 26128 | 2012-12-25 10:00 | 2013-01-05 10:00 | 11 | 650 | 100 | 88 | -12 | 10637 | 10637 | 9360.56 | 12532.202 | 0.88 | 0.74692 | TRUE | TRUE | TRUE | 81.25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144659 | HCFWB4Z3002 | B4 Z3 :Trawelled smooth Concrete screed | 26326 | 2013-02-03 10:00 | 2013-02-12 10:00 | 9 | 990 | 100 | 82 | -18 | 5166 | 5166 | 4236.12 | 5301.5011 | 0.82 | 0.79904 | TRUE | TRUE | TRUE | 123.75 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144660 | HCFWB4Z3004 | B4 Z3 :Sealed Concrete | 26326 | 2013-10-29 08:00 | 2013-11-07 16:00 | 9 | 208 | 100 | 100 | 0 | 4527 | 4527 | 4527 | 4087.7083 | 1 | 1.1075 | FALSE | FALSE | FALSE | 26 | FALSE | 0 | Green | Continue normal monitoring.
144661 | HCFWB4Z3009 | B4 Z3 :Block Works | 26327 | 2012-10-11 08:00 | 2012-10-31 16:00 | 20 | 432 | 100 | 80 | -20 | 22900 | 22900 | 18320 | 22966.4306 | 0.8 | 0.79769 | TRUE | TRUE | TRUE | 54 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144662 | HCFWB4Z3010 | B4 Z3 :Plaster First Layer | 26327 | 2012-12-15 12:00 | 2012-12-25 10:00 | 9 | 140 | 100 | 100 | 0 | 5553 | 5553 | 5553 | 6095.7357 | 1 | 0.91096 | FALSE | FALSE | FALSE | 17.5 | FALSE | 0 | Green | Continue normal monitoring.
144663 | HCFWB4Z3001 | B4 Z3 :Foam Concrete & Proofing Membrane Under Floorings | 26326 | 2013-01-14 10:00 | 2013-02-03 10:00 | 20 | 990 | 100 | 95 | -5 | 27600 | 27600 | 26220 | 28476.6108 | 0.95 | 0.92076 | FALSE | FALSE | FALSE | 123.75 | FALSE | 0 | Green | Continue normal monitoring.
144664 | HCFWB4Z3012 | B4 Z3 :Plaster Final Layer | 26327 | 2013-01-05 10:00 | 2013-01-14 10:00 | 9 | 200 | 100 | 100 | 0 | 9027 | 9027 | 9027 | 10490.0574 | 1 | 0.86053 | TRUE | FALSE | FALSE | 25 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144665 | HCFWB4Z3013 | B4 Z3 :Paint First Layer | 26327 | 2013-01-14 10:00 | 2013-01-23 10:00 | 9 | 1486 | 100 | 85 | -15 | 13014 | 13014 | 11061.9 | 16255.1254 | 0.85 | 0.68052 | TRUE | TRUE | TRUE | 185.75 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144666 | HCFWB4Z3014 | B4 Z3 :Paint Final Layer | 26327 | 2013-01-23 10:00 | 2013-02-03 10:00 | 11 | 1486 | 100 | 100 | 0 | 11803 | 11803 | 11803 | 10934.9228 | 1 | 1.0794 | FALSE | FALSE | FALSE | 185.75 | FALSE | 0 | Green | Continue normal monitoring.
144667 | HCFWB4Z3003 | B4 Z3 :Epoxy Screed Finish Works | 26326 | 2013-10-29 08:00 | 2013-11-10 16:00 | 12 | 208 | 100 | 96 | -4 | 23568 | 23568 | 22625.28 | 24366.0202 | 0.96 | 0.92856 | FALSE | FALSE | FALSE | 26 | FALSE | 0 | Green | Continue normal monitoring.
144668 | HCFWB4Z3016 | B4 Z3 :Plaster First Layer | 26372 | 2013-02-12 10:00 | 2013-02-21 16:00 | 9 | 990 | 100 | 84 | -16 | 6237 | 6237 | 5239.08 | 6376.6686 | 0.84 | 0.8216 | TRUE | TRUE | TRUE | 123.75 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144669 | HCFWB4Z3018 | B4 Z3 :Plaster Final Layer | 26372 | 2013-03-04 08:00 | 2013-03-12 16:00 | 8 | 990 | 100 | 100 | 0 | 10768 | 10768 | 10768 | 10464.3102 | 1 | 1.029 | FALSE | FALSE | FALSE | 123.75 | FALSE | 0 | Green | Continue normal monitoring.
144670 | HCFWB4Z3019 | B4 Z3 :Paint First Layer | 26372 | 2013-03-13 08:00 | 2013-03-24 16:00 | 11 | 1592 | 100 | 84 | -16 | 13354 | 13354 | 11217.36 | 12409.047 | 0.84 | 0.90397 | FALSE | TRUE | TRUE | 199 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144671 | HCFWB4Z3020 | B4 Z3 :Paint Final Layer | 26372 | 2013-10-23 08:00 | 2013-10-28 16:00 | 5 | 208 | 100 | 85 | -15 | 9575 | 9575 | 8138.75 | 8390.3508 | 0.85 | 0.97001 | FALSE | TRUE | TRUE | 26 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144672 | HCFWB4Z3024 | B4 Z3 :Steel Fire Rated Doors | 26247 | 2013-08-24 08:00 | 2013-09-03 16:00 | 10 | 760 | 100 | 82 | -18 | 15490 | 15490 | 12701.8 | 18663.0913 | 0.82 | 0.68058 | TRUE | TRUE | TRUE | 95 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144673 | HCFWB4Z3005 | B4 Z3 :Rubber Flooring With Spicial Adhesive | 26326 | 2013-10-29 08:00 | 2013-11-10 16:00 | 12 | 208 | 100 | 100 | 0 | 23496 | 23496 | 23496 | 23917.506 | 1 | 0.98238 | FALSE | FALSE | FALSE | 26 | FALSE | 0 | Green | Continue normal monitoring.
144674 | HCFWB4Z3006 | B4 Z3 :Rubber Skirting | 26326 | 2013-11-11 08:00 | 2013-11-12 16:00 | 1 | 208 | 100 | 100 | 0 | 672 | 672 | 672 | 704.7655 | 1 | 0.95351 | FALSE | FALSE | FALSE | 26 | FALSE | 0 | Green | Continue normal monitoring.
144675 | HCFWB4Z3023 | B4 Z3 :Steel Doors | 26247 | 2013-09-28 08:00 | 2013-10-08 16:00 | 10 | 520 | 100 | 84 | -16 | 18230 | 18230 | 15313.2 | 22181.8414 | 0.84 | 0.69035 | TRUE | TRUE | TRUE | 65 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144676 | HCFWB4Z3025 | B4 Z3 :Wooden Doors | 26247 | 2013-09-28 08:00 | 2013-10-08 16:00 | 10 | 520 | 100 | 100 | 0 | 8250 | 8250 | 8250 | 9574.2586 | 1 | 0.86169 | TRUE | FALSE | FALSE | 65 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144677 | HCFWB4Z3021 | B4 Z3 :Gybsum Board Ceiling | 26372 | 2013-10-02 08:00 | 2013-10-22 16:00 | 20 | 208 | 100 | 84 | -16 | 38660 | 38660 | 32474.4 | 34879.0715 | 0.84 | 0.93106 | FALSE | TRUE | TRUE | 26 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144678 | HCFWB4Z3022 | B4 Z3 :Metal Works & Gutters | 26247 | 2013-09-28 08:00 | 2013-10-08 16:00 | 10 | 480 | 100 | 89 | -11 | 16410 | 16410 | 14604.9 | 17659.9167 | 0.89 | 0.82701 | TRUE | TRUE | TRUE | 60 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144679 | HCFWB4Z3026 | B4 Z3 :Handrails & Railling | 26247 | 2013-09-28 08:00 | 2013-10-14 16:00 | 16 | 360 | 100 | 89 | -11 | 21360 | 21360 | 19010.4 | 21934.6035 | 0.89 | 0.86669 | TRUE | TRUE | TRUE | 45 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144680 | HCFWB4Z3011 | B4 Z3 :Plaster Second Layer | 26327 | 2012-12-25 10:00 | 2013-01-05 10:00 | 11 | 200 | 100 | 98 | -2 | 13453 | 13453 | 13183.94 | 15725.0022 | 0.98 | 0.83841 | TRUE | FALSE | FALSE | 25 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144681 | HCFWB4Z3017 | B4 Z3 :Plaster Second Layer | 26372 | 2013-02-23 08:00 | 2013-03-03 16:00 | 8 | 990 | 100 | 96 | -4 | 5792 | 5792 | 5560.32 | 6601.102 | 0.96 | 0.84233 | TRUE | FALSE | FALSE | 123.75 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144682 | HCFWB4Z3007 | B4 Z3 :Stone Flooring | 26326 | 2013-10-29 08:00 | 2013-11-12 16:00 | 14 | 336 | 100 | 100 | 0 | 14434 | 14434 | 14434 | 16255.0265 | 1 | 0.88797 | TRUE | FALSE | FALSE | 42 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144683 | HCFWB4Z3008 | B4 Z3 :Stone Skirting | 26326 | 2013-11-13 08:00 | 2013-11-24 16:00 | 11 | 1280 | 100 | 93 | -7 | 6732 | 6732 | 6260.76 | 6639.2191 | 0.93 | 0.943 | FALSE | FALSE | FALSE | 160 | FALSE | 0 | Green | Continue normal monitoring.
144684 | HCFWB4Z3015 | B4 Z3 :Epoxy Paint for Walls | 26327 | 2013-01-23 10:00 | 2013-02-05 10:00 | 13 | 1486 | 100 | 88 | -12 | 8307 | 8307 | 7310.16 | 9735.6835 | 0.88 | 0.75086 | TRUE | TRUE | TRUE | 185.75 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144685 | HCFWB4Z4002 | B4 Z4 :Trawelled smooth Concrete screed | 26371 | 2013-02-04 08:00 | 2013-02-12 16:00 | 8 | 140 | 100 | 93 | -7 | 8464 | 8464 | 7871.52 | 7371.776 | 0.93 | 1.0678 | FALSE | FALSE | FALSE | 17.5 | FALSE | 0 | Green | Continue normal monitoring.
144686 | HCFWB4Z4004 | B4 Z4 :Sealed Concrete | 26371 | 2013-03-23 10:00 | 2013-04-01 10:00 | 9 | 1158 | 100 | 80 | -20 | 4500 | 4500 | 3600 | 4112.3248 | 0.8 | 0.87542 | TRUE | TRUE | TRUE | 144.75 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144687 | HCFWB4Z4007 | B4 Z4 :Block Works | 26207 | 2012-10-23 08:00 | 2012-11-07 16:00 | 15 | 384 | 100 | 98 | -2 | 8835 | 8835 | 8658.3 | 8695.8426 | 0.98 | 0.99568 | FALSE | FALSE | FALSE | 48 | FALSE | 0 | Green | Continue normal monitoring.
144688 | HCFWB4Z4008 | B4 Z4 :Plaster First Layer | 26207 | 2012-12-15 12:00 | 2012-12-25 10:00 | 9 | 140 | 100 | 92 | -8 | 10377 | 10377 | 9546.84 | 9139.2623 | 0.92 | 1.0446 | FALSE | FALSE | FALSE | 17.5 | FALSE | 0 | Green | Continue normal monitoring.
144689 | HCFWB4Z4001 | B4 Z4 :Foam Concrete & Proofing Membrane Under Floorings | 26371 | 2013-01-15 08:00 | 2013-02-03 16:00 | 19 | 140 | 100 | 92 | -8 | 15561 | 15561 | 14316.12 | 14689.5484 | 0.92 | 0.97458 | FALSE | FALSE | FALSE | 17.5 | FALSE | 0 | Green | Continue normal monitoring.
144690 | HCFWB4Z4010 | B4 Z4 :Plaster Final Layer | 26207 | 2013-01-05 10:00 | 2013-01-14 16:00 | 9 | 140 | 100 | 83 | -17 | 5742 | 5742 | 4765.86 | 6787.3908 | 0.83 | 0.70216 | TRUE | TRUE | TRUE | 17.5 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144691 | HCFWB4Z4011 | B4 Z4 :Paint First Layer | 26207 | 2013-02-13 08:00 | 2013-02-21 16:00 | 8 | 384 | 100 | 100 | 0 | 10752 | 10752 | 10752 | 13217.4402 | 1 | 0.81347 | TRUE | FALSE | FALSE | 48 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144692 | HCFWB4Z4012 | B4 Z4 :Paint Final Layer | 26207 | 2013-02-23 08:00 | 2013-03-03 16:00 | 8 | 384 | 100 | 80 | -20 | 6064 | 6064 | 4851.2 | 5893.2435 | 0.8 | 0.82318 | TRUE | TRUE | TRUE | 48 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144693 | HCFWB4Z4003 | B4 Z4 :Epoxy Screed Finish Works | 26371 | 2013-03-23 10:00 | 2013-04-03 10:00 | 11 | 1158 | 100 | 96 | -4 | 15411 | 15411 | 14794.56 | 14729.9312 | 0.96 | 1.0044 | FALSE | FALSE | FALSE | 144.75 | FALSE | 0 | Green | Continue normal monitoring.
144694 | HCFWB4Z4013 | B4 Z4 :Plaster First Layer | 26133 | 2013-02-13 08:00 | 2013-02-23 14:00 | 10 | 140 | 100 | 87 | -13 | 11890 | 11890 | 10344.3 | 11437.6695 | 0.87 | 0.90441 | FALSE | TRUE | TRUE | 17.5 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144695 | HCFWB4Z4015 | B4 Z4 :Plaster Final Layer | 26133 | 2013-03-04 14:00 | 2013-03-23 10:00 | 18 | 140 | 100 | 81 | -19 | 9162 | 9162 | 7421.22 | 8805.4849 | 0.81 | 0.8428 | TRUE | TRUE | TRUE | 17.5 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144696 | HCFWB4Z4016 | B4 Z4 :Paint First Layer | 26133 | 2013-03-23 10:00 | 2013-04-03 10:00 | 11 | 174 | 100 | 100 | 0 | 8360 | 8360 | 8360 | 7226.1505 | 1 | 1.1569 | FALSE | FALSE | FALSE | 21.75 | FALSE | 0 | Green | Continue normal monitoring.
144697 | HCFWB4Z4017 | B4 Z4 :Paint Final Layer | 26133 | 2013-04-03 10:00 | 2013-04-15 10:00 | 12 | 174 | 100 | 100 | 0 | 8052 | 8052 | 8052 | 9829.6122 | 1 | 0.81916 | TRUE | FALSE | FALSE | 21.75 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144698 | HCFWB4Z4021 | B4 Z4 :Steel Fire Rated Doors | 26246 | 2013-08-24 08:00 | 2013-09-03 16:00 | 10 | 1064 | 100 | 87 | -13 | 13970 | 13970 | 12153.9 | 13068.6452 | 0.87 | 0.93 | FALSE | TRUE | TRUE | 133 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144699 | HCFWB4Z4005 | B4 Z4 :Rubber Flooring With Spicial Adhesive | 26371 | 2013-03-23 10:00 | 2013-04-03 10:00 | 11 | 1158 | 100 | 86 | -14 | 5632 | 5632 | 4843.52 | 5733.3852 | 0.86 | 0.84479 | TRUE | TRUE | TRUE | 144.75 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144700 | HCFWB4Z4006 | B4 Z4 :Rubber Skirting | 26371 | 2013-11-13 08:00 | 2013-11-14 16:00 | 1 | 208 | 100 | 100 | 0 | 1691 | 1691 | 1691 | 1443.9022 | 1 | 1.1711 | FALSE | FALSE | FALSE | 26 | FALSE | 0 | Green | Continue normal monitoring.
144701 | HCFWB4Z4020 | B4 Z4 :Steel Doors | 26246 | 2013-10-09 08:00 | 2013-10-24 16:00 | 15 | 744 | 100 | 100 | 0 | 12300 | 12300 | 12300 | 14676.139 | 1 | 0.8381 | TRUE | FALSE | FALSE | 93 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144702 | HCFWB4Z4022 | B4 Z4 :Wooden Doors | 26246 | 2013-10-09 08:00 | 2013-10-24 16:00 | 15 | 744 | 100 | 81 | -19 | 27630 | 27630 | 22380.3 | 31566.251 | 0.81 | 0.70899 | TRUE | TRUE | TRUE | 93 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144703 | HCFWB4Z4018 | B4 Z4 :Gybsum Board Ceiling | 26133 | 2013-10-02 08:00 | 2013-10-22 16:00 | 20 | 744 | 100 | 100 | 0 | 16560 | 16560 | 16560 | 20347.312 | 1 | 0.81387 | TRUE | FALSE | FALSE | 93 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144704 | HCFWB4Z4019 | B4 Z4 :Metal Works & Gutters | 26246 | 2013-10-09 08:00 | 2013-10-24 16:00 | 15 | 744 | 100 | 100 | 0 | 19260 | 19260 | 19260 | 22392.5657 | 1 | 0.86011 | TRUE | FALSE | FALSE | 93 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144705 | HCFWB4Z4023 | B4 Z4 :Handrails & Railling | 26246 | 2013-09-28 08:00 | 2013-10-14 16:00 | 16 | 744 | 100 | 82 | -18 | 20416 | 20416 | 16741.12 | 19915.4529 | 0.82 | 0.84061 | TRUE | TRUE | TRUE | 93 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144706 | HCFWB4Z4009 | B4 Z4 :Plaster Second Layer | 26207 | 2012-12-25 10:00 | 2013-01-05 10:00 | 11 | 140 | 100 | 100 | 0 | 15510 | 15510 | 15510 | 14721.3063 | 1 | 1.0536 | FALSE | FALSE | FALSE | 17.5 | FALSE | 0 | Green | Continue normal monitoring.
144707 | HCFWB4Z4014 | B4 Z4 :Plaster Second Layer | 26133 | 2013-02-23 14:00 | 2013-03-04 14:00 | 9 | 140 | 100 | 97 | -3 | 17478 | 17478 | 16953.66 | 19734.1742 | 0.97 | 0.8591 | TRUE | FALSE | FALSE | 17.5 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144708 | HCFWB4Z5002 | B4 Z4 :Trawelled smooth Concrete screed | 26365 | 2013-02-04 08:00 | 2013-02-12 16:00 | 8 | 156 | 100 | 91 | -9 | 12944 | 12944 | 11779.04 | 12887.6303 | 0.91 | 0.91398 | FALSE | FALSE | FALSE | 19.5 | FALSE | 0 | Green | Continue normal monitoring.
144709 | HCFWB4Z5004 | B4 Z4 :Sealed Concrete | 26365 | 2013-03-14 12:00 | 2013-03-24 12:00 | 10 | 244 | 100 | 80 | -20 | 8170 | 8170 | 6536 | 8794.8907 | 0.8 | 0.74316 | TRUE | TRUE | TRUE | 30.5 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144710 | HCFWB4Z5012 | B4 Z4 :Block Works | 26368 | 2012-11-28 08:00 | 2012-12-09 16:00 | 11 | 192 | 100 | 100 | 0 | 8085 | 8085 | 8085 | 6892.4867 | 1 | 1.173 | FALSE | FALSE | FALSE | 24 | FALSE | 0 | Green | Continue normal monitoring.
144711 | HCFWB4Z5007 | B4 Z4 :Plaster First Layer | 26368 | 2012-12-15 12:00 | 2012-12-25 10:00 | 9 | 156 | 100 | 91 | -9 | 7497 | 7497 | 6822.27 | 6558.0328 | 0.91 | 1.0403 | FALSE | FALSE | FALSE | 19.5 | FALSE | 0 | Green | Continue normal monitoring.
144712 | HCFWB4Z5001 | B4 Z4 :Foam Concrete & Proofing Membrane Under Floorings | 26365 | 2013-01-15 08:00 | 2013-02-03 16:00 | 19 | 156 | 100 | 84 | -16 | 16625 | 16625 | 13965 | 17691.4468 | 0.84 | 0.78936 | TRUE | TRUE | TRUE | 19.5 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144713 | HCFWB4Z5009 | B4 Z4 :Plaster Final Layer | 26368 | 2013-01-05 10:00 | 2013-01-14 16:00 | 9 | 156 | 100 | 100 | 0 | 17838 | 17838 | 17838 | 19201.3344 | 1 | 0.929 | FALSE | FALSE | FALSE | 19.5 | FALSE | 0 | Green | Continue normal monitoring.
144714 | HCFWB4Z5010 | B4 Z4 :Paint First Layer | 26368 | 2013-04-27 10:00 | 2013-05-12 10:00 | 15 | 2462 | 100 | 100 | 0 | 24900 | 24900 | 24900 | 28649.4713 | 1 | 0.86913 | TRUE | FALSE | FALSE | 307.75 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144715 | HCFWB4Z5011 | B4 Z4 :Paint Final Layer | 26368 | 2013-05-12 10:00 | 2013-05-27 10:00 | 15 | 2462 | 100 | 100 | 0 | 16305 | 16305 | 16305 | 14719.9278 | 1 | 1.1077 | FALSE | FALSE | FALSE | 307.75 | FALSE | 0 | Green | Continue normal monitoring.
144716 | HCFWB4Z5003 | B4 Z4 :Epoxy Screed Finish Works | 26365 | 2013-03-14 12:00 | 2013-03-26 12:00 | 12 | 244 | 100 | 100 | 0 | 12144 | 12144 | 12144 | 12815.2381 | 1 | 0.94762 | FALSE | FALSE | FALSE | 30.5 | FALSE | 0 | Green | Continue normal monitoring.
144717 | HCFWB4Z5013 | B4 Z4 :Plaster First Layer | 26314 | 2013-02-13 08:00 | 2013-02-23 14:00 | 10 | 156 | 100 | 96 | -4 | 18190 | 18190 | 17462.4 | 16876.3011 | 0.96 | 1.0347 | FALSE | FALSE | FALSE | 19.5 | FALSE | 0 | Green | Continue normal monitoring.
144718 | HCFWB4Z5015 | B4 Z4 :Plaster Final Layer | 26314 | 2013-03-04 14:00 | 2013-03-14 12:00 | 9 | 156 | 100 | 95 | -5 | 16587 | 16587 | 15757.65 | 14717.2876 | 0.95 | 1.0707 | FALSE | FALSE | FALSE | 19.5 | FALSE | 0 | Green | Continue normal monitoring.
144719 | HCFWB4Z5016 | B4 Z4 :Paint First Layer | 26314 | 2013-03-24 12:00 | 2013-04-04 12:00 | 11 | 244 | 100 | 100 | 0 | 15587 | 15587 | 15587 | 15808.3092 | 1 | 0.986 | FALSE | FALSE | FALSE | 30.5 | FALSE | 0 | Green | Continue normal monitoring.
144720 | HCFWB4Z5017 | B4 Z4 :Paint Final Layer | 26314 | 2013-04-15 10:00 | 2013-04-27 10:00 | 12 | 174 | 100 | 94 | -6 | 22464 | 22464 | 21116.16 | 20562.0778 | 0.94 | 1.0269 | FALSE | FALSE | FALSE | 21.75 | FALSE | 0 | Green | Continue normal monitoring.
144721 | HCFWB4Z5021 | B4 Z4 :Steel Fire Rated Doors | 26170 | 2013-08-24 08:00 | 2013-09-03 16:00 | 10 | 1240 | 100 | 100 | 0 | 13720 | 13720 | 13720 | 12879.1395 | 1 | 1.0653 | FALSE | FALSE | FALSE | 155 | FALSE | 0 | Green | Continue normal monitoring.
144722 | HCFWB4Z5005 | B4 Z4 :Rubber Flooring With Spicial Adhesive | 26365 | 2013-03-14 12:00 | 2013-03-26 12:00 | 12 | 1412 | 100 | 94 | -6 | 21024 | 21024 | 19762.56 | 20540.907 | 0.94 | 0.96211 | FALSE | FALSE | FALSE | 176.5 | FALSE | 0 | Green | Continue normal monitoring.
144723 | HCFWB4Z5006 | B4 Z4 :Rubber Skirting | 26365 | 2013-11-16 08:00 | 2013-11-17 16:00 | 1 | 208 | 100 | 84 | -16 | 769 | 769 | 645.96 | 733.4379 | 0.84 | 0.88073 | TRUE | TRUE | TRUE | 26 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144724 | HCFWB4Z5020 | B4 Z4 :Steel Doors | 26170 | 2013-10-26 08:00 | 2013-11-06 16:00 | 11 | 840 | 100 | 100 | 0 | 14267 | 14267 | 14267 | 12626.816 | 1 | 1.1299 | FALSE | FALSE | FALSE | 105 | FALSE | 0 | Green | Continue normal monitoring.
144725 | HCFWB4Z5022 | B4 Z4 :Wooden Doors | 26170 | 2013-10-26 08:00 | 2013-11-06 16:00 | 11 | 1400 | 100 | 93 | -7 | 19954 | 19954 | 18557.22 | 17678.5755 | 0.93 | 1.0497 | FALSE | FALSE | FALSE | 175 | FALSE | 0 | Green | Continue normal monitoring.
144726 | HCFWB4Z5019 | B4 Z4 :Metal Works & Gutters | 26170 | 2013-10-09 08:00 | 2013-10-24 16:00 | 15 | 520 | 100 | 81 | -19 | 18360 | 18360 | 14871.6 | 17025.2237 | 0.81 | 0.8735 | TRUE | TRUE | TRUE | 65 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144727 | HCFWB4Z5008 | B4 Z4 :Plaster Second Layer | 26368 | 2012-12-25 10:00 | 2013-01-05 10:00 | 11 | 156 | 100 | 90 | -10 | 18568 | 18568 | 16711.2 | 16158.3132 | 0.9 | 1.0342 | FALSE | FALSE | FALSE | 19.5 | FALSE | 0 | Green | Continue normal monitoring.
144728 | HCFWB4Z5014 | B4 Z4 :Plaster Second Layer | 26314 | 2013-02-23 14:00 | 2013-03-04 14:00 | 9 | 156 | 100 | 98 | -2 | 4536 | 4536 | 4445.28 | 4992.2436 | 0.98 | 0.89044 | TRUE | FALSE | FALSE | 19.5 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144729 | HCFWB4Z6002 | B4 Z6 :Trawelled smooth Concrete screed | 26213 | 2013-02-04 08:00 | 2013-02-12 16:00 | 8 | 270 | 100 | 86 | -14 | 10800 | 10800 | 9288 | 10421.2514 | 0.86 | 0.89126 | TRUE | TRUE | TRUE | 33.75 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144730 | HCFWB4Z6004 | B4 Z6 :Sealed Concrete | 26213 | 2013-03-23 10:00 | 2013-04-01 10:00 | 9 | 270 | 100 | 85 | -15 | 17118 | 17118 | 14550.3 | 16465.7766 | 0.85 | 0.88367 | TRUE | TRUE | TRUE | 33.75 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144731 | HCFWB4Z6007 | B4 Z6 :Block Works | 26235 | 2012-11-28 08:00 | 2012-12-09 16:00 | 11 | 306 | 100 | 100 | 0 | 6347 | 6347 | 6347 | 6237.8273 | 1 | 1.0175 | FALSE | FALSE | FALSE | 38.25 | FALSE | 0 | Green | Continue normal monitoring.
144732 | HCFWB4Z6008 | B4 Z6 :Plaster First Layer | 26235 | 2012-12-15 12:00 | 2012-12-25 10:00 | 9 | 270 | 100 | 81 | -19 | 17397 | 17397 | 14091.57 | 19399.7167 | 0.81 | 0.72638 | TRUE | TRUE | TRUE | 33.75 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144733 | HCFWB4Z6001 | B4 Z6 :Foam Concrete & Proofing Membrane Under Floorings | 26213 | 2013-01-15 08:00 | 2013-02-03 16:00 | 19 | 270 | 100 | 85 | -15 | 20387 | 20387 | 17328.95 | 24428.7952 | 0.85 | 0.70937 | TRUE | TRUE | TRUE | 33.75 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144734 | HCFWB4Z6010 | B4 Z6 :Plaster Final Layer | 26235 | 2013-01-05 10:00 | 2013-01-14 16:00 | 9 | 270 | 100 | 97 | -3 | 5679 | 5679 | 5508.63 | 6551.4919 | 0.97 | 0.84082 | TRUE | FALSE | FALSE | 33.75 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144735 | HCFWB4Z6011 | B4 Z6 :Paint First Layer | 26235 | 2013-04-01 10:00 | 2013-04-15 10:00 | 14 | 1998 | 100 | 81 | -19 | 15400 | 15400 | 12474 | 17571.5801 | 0.81 | 0.7099 | TRUE | TRUE | TRUE | 249.75 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144736 | HCFWB4Z6012 | B4 Z6 :Paint Final Layer | 26235 | 2013-04-15 10:00 | 2013-04-29 10:00 | 14 | 1998 | 100 | 97 | -3 | 21910 | 21910 | 21252.7 | 22868.7044 | 0.97 | 0.92934 | FALSE | FALSE | FALSE | 249.75 | FALSE | 0 | Green | Continue normal monitoring.
144737 | HCFWB4Z6003 | B4 Z6 :Epoxy Screed Finish Works | 26213 | 2013-03-23 10:00 | 2013-04-03 10:00 | 11 | 270 | 100 | 100 | 0 | 6468 | 6468 | 6468 | 7292.8137 | 1 | 0.8869 | TRUE | FALSE | FALSE | 33.75 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144738 | HCFWB4Z6013 | B4 Z6 :Plaster First Layer | 26132 | 2013-02-13 08:00 | 2013-02-23 14:00 | 10 | 270 | 100 | 94 | -6 | 9010 | 9010 | 8469.4 | 9650.6556 | 0.94 | 0.8776 | TRUE | FALSE | FALSE | 33.75 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144739 | HCFWB4Z6015 | B4 Z6 :Plaster Final Layer | 26132 | 2013-03-04 14:00 | 2013-03-23 10:00 | 18 | 270 | 100 | 100 | 0 | 14310 | 14310 | 14310 | 13401.318 | 1 | 1.0678 | FALSE | FALSE | FALSE | 33.75 | FALSE | 0 | Green | Continue normal monitoring.
144740 | HCFWB4Z6016 | B4 Z6 :Paint First Layer | 26132 | 2013-04-01 10:00 | 2013-04-13 10:00 | 12 | 270 | 100 | 98 | -2 | 21816 | 21816 | 21379.68 | 20363.8255 | 0.98 | 1.0499 | FALSE | FALSE | FALSE | 33.75 | FALSE | 0 | Green | Continue normal monitoring.
144741 | HCFWB4Z6017 | B4 Z6 :Paint Final Layer | 26132 | 2013-04-27 10:00 | 2013-05-07 10:00 | 10 | 174 | 100 | 100 | 0 | 11150 | 11150 | 11150 | 10799.4084 | 1 | 1.0325 | FALSE | FALSE | FALSE | 21.75 | FALSE | 0 | Green | Continue normal monitoring.
144742 | HCFWB4Z6020 | B4 Z6 :Steel Fire Rated Doors | 26193 | 2013-08-24 08:00 | 2013-09-03 16:00 | 10 | 920 | 100 | 81 | -19 | 12990 | 12990 | 10521.9 | 15774.0307 | 0.81 | 0.66704 | TRUE | TRUE | TRUE | 115 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144743 | HCFWB4Z6005 | B4 Z6 :Rubber Flooring With Spicial Adhesive | 26213 | 2013-03-23 10:00 | 2013-04-03 10:00 | 11 | 1358 | 100 | 99 | -1 | 10131 | 10131 | 10029.69 | 10829.6939 | 0.99 | 0.92613 | FALSE | FALSE | FALSE | 169.75 | FALSE | 0 | Green | Continue normal monitoring.
144744 | HCFWB4Z6006 | B4 Z6 :Rubber Skirting | 26213 | 2013-11-18 08:00 | 2013-11-19 16:00 | 1 | 208 | 100 | 100 | 0 | 1546 | 1546 | 1546 | 1767.9471 | 1 | 0.87446 | TRUE | FALSE | FALSE | 26 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144745 | HCFWB4Z6019 | B4 Z6 :Steel Doors | 26193 | 2013-10-09 08:00 | 2013-10-24 16:00 | 15 | 600 | 100 | 85 | -15 | 16110 | 16110 | 13693.5 | 15926.7246 | 0.85 | 0.85978 | TRUE | TRUE | TRUE | 75 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144746 | HCFWB4Z6021 | B4 Z6 :Wooden Doors | 26193 | 2013-10-09 08:00 | 2013-10-24 16:00 | 15 | 1480 | 100 | 80 | -20 | 9630 | 9630 | 7704 | 9756.0211 | 0.8 | 0.78967 | TRUE | TRUE | TRUE | 185 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144747 | HCFWB4Z6018 | B4 Z6 :Metal Works & Gutters | 26193 | 2013-10-09 08:00 | 2013-10-24 16:00 | 15 | 520 | 100 | 100 | 0 | 22380 | 22380 | 22380 | 20147.0631 | 1 | 1.1108 | FALSE | FALSE | FALSE | 65 | FALSE | 0 | Green | Continue normal monitoring.
144748 | HCFWB4Z6009 | B4 Z6 :Plaster Second Layer | 26235 | 2012-12-25 10:00 | 2013-01-05 10:00 | 11 | 270 | 100 | 94 | -6 | 12804 | 12804 | 12035.76 | 11760.7043 | 0.94 | 1.0234 | FALSE | FALSE | FALSE | 33.75 | FALSE | 0 | Green | Continue normal monitoring.
144749 | HCFWB4Z6014 | B4 Z6 :Plaster Second Layer | 26132 | 2013-02-23 14:00 | 2013-03-04 14:00 | 9 | 270 | 100 | 100 | 0 | 5796 | 5796 | 5796 | 6844.7434 | 1 | 0.84678 | TRUE | FALSE | FALSE | 33.75 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144750 | HCFWB20000 | Start Finishing Works B2 | 25853 | 2012-12-19 08:00 | 2012-12-19 08:00 | 1 | 328 | 100 | 100 | 0 | 1748 | 1748 | 1748 | 1894.7192 | 1 | 0.92256 | FALSE | FALSE | FALSE | 41 | FALSE | 0 | Green | Continue normal monitoring.
144751 | HCFWB20001 | End Finishing Works B2 | 25853 | 2014-05-22 16:00 | 2014-05-22 16:00 | 1 | 80 | 100 | 100 | 0 | 1506 | 1506 | 1506 | 1483.4296 | 1 | 1.0152 | FALSE | FALSE | FALSE | 10 | FALSE | 0 | Green | Continue normal monitoring.
144752 | HCFWB2Z1002 | B2 Z1 :Trawelled smooth Concrete screed | 26367 | 2013-03-28 14:00 | 2013-04-07 14:00 | 10 | 530 | 100 | 89 | -11 | 10020 | 10020 | 8917.8 | 11734.8276 | 0.89 | 0.75994 | TRUE | TRUE | TRUE | 66.25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144753 | HCFWB2Z1003 | B2 Z1 :Sealed Concrete | 26367 | 2013-07-14 08:00 | 2013-07-22 16:00 | 8 | 40 | 100 | 98 | -2 | 10560 | 10560 | 10348.8 | 10017.3001 | 0.98 | 1.0331 | FALSE | FALSE | FALSE | 5 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144754 | HCFWB2Z1012 | B2 Z1 :Block Works | 26178 | 2012-12-19 08:00 | 2012-12-30 16:00 | 11 | 248 | 100 | 96 | -4 | 6633 | 6633 | 6367.68 | 8227.66 | 0.96 | 0.77394 | TRUE | FALSE | FALSE | 31 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144755 | HCFWB2Z1007 | B2 Z1 :Plaster First Layer | 26178 | 2012-12-31 08:00 | 2013-01-10 14:00 | 10 | 248 | 100 | 84 | -16 | 15620 | 15620 | 13120.8 | 15431.4204 | 0.84 | 0.85027 | TRUE | TRUE | TRUE | 31 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144756 | HCFWB2Z1001 | B2 Z1 :Foam Concrete Under Floorings | 26367 | 2013-03-10 14:00 | 2013-03-28 14:00 | 18 | 530 | 100 | 100 | 0 | 12546 | 12546 | 12546 | 12356.8613 | 1 | 1.0153 | FALSE | FALSE | FALSE | 66.25 | FALSE | 0 | Green | Continue normal monitoring.
144757 | HCFWB2Z1009 | B2 Z1 :Plaster Final Layer | 26178 | 2013-01-20 14:00 | 2013-01-31 12:00 | 10 | 530 | 100 | 83 | -17 | 10780 | 10780 | 8947.4 | 10507.9641 | 0.83 | 0.85149 | TRUE | TRUE | TRUE | 66.25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144758 | HCFWB2Z1010 | B2 Z1 :Paint First Layer | 26178 | 2013-01-31 12:00 | 2013-02-14 12:00 | 14 | 948 | 100 | 89 | -11 | 12460 | 12460 | 11089.4 | 11199.6038 | 0.89 | 0.99016 | FALSE | TRUE | TRUE | 118.5 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144759 | HCFWB2Z1011 | B2 Z1 :Paint Final Layer | 26178 | 2013-06-30 08:00 | 2013-07-13 16:00 | 13 | 40 | 100 | 100 | 0 | 22126 | 22126 | 22126 | 19790.7082 | 1 | 1.118 | FALSE | FALSE | FALSE | 5 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144760 | HCFWB2Z1004 | B2 Z1 :Epoxy Screed Finish Works | 26367 | 2013-07-14 08:00 | 2013-07-24 16:00 | 10 | 40 | 100 | 96 | -4 | 10530 | 10530 | 10108.8 | 11680.3184 | 0.96 | 0.86546 | TRUE | FALSE | FALSE | 5 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144761 | HCFWB2Z1013 | B2 Z1 :Plaster First Layer | 26346 | 2013-01-31 12:00 | 2013-02-11 10:00 | 10 | 530 | 100 | 89 | -11 | 19710 | 19710 | 17541.9 | 23652.9307 | 0.89 | 0.74164 | TRUE | TRUE | TRUE | 66.25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144762 | HCFWB2Z1015 | B2 Z1 :Plaster Final Layer | 26346 | 2013-02-20 10:00 | 2013-03-10 14:00 | 18 | 530 | 100 | 96 | -4 | 27684 | 27684 | 26576.64 | 32285.3079 | 0.96 | 0.82318 | TRUE | FALSE | FALSE | 66.25 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144763 | HCFWB2Z1016 | B2 Z1 :Paint First Layer | 26346 | 2013-04-07 14:00 | 2013-04-18 14:00 | 11 | 530 | 100 | 100 | 0 | 19932 | 19932 | 19932 | 18067.2226 | 1 | 1.1032 | FALSE | FALSE | FALSE | 66.25 | FALSE | 0 | Green | Continue normal monitoring.
144764 | HCFWB2Z1017 | B2 Z1 :Paint Final Layer | 26346 | 2013-04-18 14:00 | 2013-04-30 14:00 | 12 | 530 | 100 | 99 | -1 | 11724 | 11724 | 11606.76 | 12523.9619 | 0.99 | 0.92676 | FALSE | FALSE | FALSE | 66.25 | FALSE | 0 | Green | Continue normal monitoring.
144765 | HCFWB2Z1021 | B2 Z1 :Steel Fire Rated Doors | 26135 | 2013-11-27 08:00 | 2013-12-08 16:00 | 11 | 424 | 100 | 100 | 0 | 19294 | 19294 | 19294 | 17214.8133 | 1 | 1.1208 | FALSE | FALSE | FALSE | 53 | FALSE | 0 | Green | Continue normal monitoring.
144766 | HCFWB2Z1005 | B2 Z1 :Rubber Flooring With Spicial Adhesive | 26367 | 2013-07-14 08:00 | 2013-07-24 16:00 | 10 | 40 | 100 | 84 | -16 | 14220 | 14220 | 11944.8 | 12344.6359 | 0.84 | 0.96761 | FALSE | TRUE | TRUE | 5 | TRUE | 4 | Orange | Develop recovery plan and review schedule and cost exposure.
144767 | HCFWB2Z1006 | B2 Z1 :Rubber Skirting | 26367 | 2013-12-04 08:00 | 2013-12-05 16:00 | 1 | 208 | 100 | 81 | -19 | 919 | 919 | 744.39 | 1022.4374 | 0.81 | 0.72805 | TRUE | TRUE | TRUE | 26 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144768 | HCFWB2Z1020 | B2 Z1 :Steel Doors | 26135 | 2013-11-27 08:00 | 2013-12-08 16:00 | 11 | 424 | 100 | 85 | -15 | 7216 | 7216 | 6133.6 | 7678.2637 | 0.85 | 0.79883 | TRUE | TRUE | TRUE | 53 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144769 | HCFWB2Z1022 | B2 Z1 :Wooden Doors | 26135 | 2013-11-27 08:00 | 2013-12-08 16:00 | 11 | 424 | 100 | 100 | 0 | 11539 | 11539 | 11539 | 10186.7385 | 1 | 1.1327 | FALSE | FALSE | FALSE | 53 | FALSE | 0 | Green | Continue normal monitoring.
144770 | HCFWB2Z1018 | B2 Z1 :Gybsum Board Ceiling | 26346 | 2013-11-11 08:00 | 2013-11-26 16:00 | 15 | 208 | 100 | 81 | -19 | 29460 | 29460 | 23862.6 | 25452.7241 | 0.81 | 0.93753 | FALSE | TRUE | TRUE | 26 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144771 | HCFWB2Z1019 | B2 Z1 :Metal Works & Gutters | 26135 | 2013-11-27 08:00 | 2013-12-08 16:00 | 11 | 208 | 100 | 92 | -8 | 17820 | 17820 | 16394.4 | 22201.9837 | 0.92 | 0.73842 | TRUE | FALSE | FALSE | 26 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144772 | HCFWB2Z1023 | B2 Z1 :Handrails & Railling | 26135 | 2013-11-27 08:00 | 2013-12-14 16:00 | 17 | 208 | 100 | 100 | 0 | 25840 | 25840 | 25840 | 22274.3005 | 1 | 1.1601 | FALSE | FALSE | FALSE | 26 | FALSE | 0 | Green | Continue normal monitoring.
144773 | HCFWB2Z1008 | B2 Z1 :Plaster Second Layer | 26178 | 2013-01-10 14:00 | 2013-01-20 14:00 | 10 | 530 | 100 | 90 | -10 | 14960 | 14960 | 13464 | 15376.0571 | 0.9 | 0.87565 | TRUE | FALSE | FALSE | 66.25 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144774 | HCFWB2Z1014 | B2 Z1 :Plaster Second Layer | 26346 | 2013-02-11 10:00 | 2013-02-20 10:00 | 9 | 530 | 100 | 90 | -10 | 17406 | 17406 | 15665.4 | 18308.4595 | 0.9 | 0.85564 | TRUE | FALSE | FALSE | 66.25 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144775 | HCFWB2Z2002 | B2 Z2 :Trawelled smooth Concrete screed | 26134 | 2013-03-24 12:00 | 2013-04-02 12:00 | 9 | 24 | 100 | 95 | -5 | 13050 | 13050 | 12397.5 | 11704.7024 | 0.95 | 1.0592 | FALSE | FALSE | FALSE | 3 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144776 | HCFWB2Z2003 | B2 Z2 :Sealed Concrete | 26134 | 2013-06-04 14:00 | 2013-06-13 14:00 | 9 | 306 | 100 | 90 | -10 | 7092 | 7092 | 6382.8 | 6507.7945 | 0.9 | 0.98079 | FALSE | FALSE | FALSE | 38.25 | FALSE | 0 | Green | Continue normal monitoring.
144777 | HCFWB2Z2013 | B2 Z2 :Block Works | 26129 | 2013-01-22 08:00 | 2013-02-03 16:00 | 12 | 24 | 100 | 98 | -2 | 21324 | 21324 | 20897.52 | 21126.156 | 0.98 | 0.98918 | FALSE | FALSE | FALSE | 3 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144778 | HCFWB2Z2007 | B2 Z2 :Plaster First Layer | 26129 | 2013-02-04 08:00 | 2013-02-13 14:00 | 9 | 24 | 100 | 94 | -6 | 6255 | 6255 | 5879.7 | 7222.463 | 0.94 | 0.81409 | TRUE | FALSE | FALSE | 3 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144779 | HCFWB2Z2001 | B2 Z2 :Foam Concrete Under Floorings | 26134 | 2013-03-05 12:00 | 2013-03-24 12:00 | 19 | 24 | 100 | 100 | 0 | 20843 | 20843 | 20843 | 21944.1976 | 1 | 0.94982 | FALSE | FALSE | FALSE | 3 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144780 | HCFWB2Z2010 | B2 Z2 :Plaster Final Layer | 26129 | 2013-02-23 14:00 | 2013-03-05 12:00 | 9 | 24 | 100 | 100 | 0 | 9144 | 9144 | 9144 | 10105.5899 | 1 | 0.90485 | FALSE | FALSE | FALSE | 3 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144781 | HCFWB2Z2011 | B2 Z2 :Paint First Layer | 26129 | 2013-03-05 12:00 | 2013-03-19 12:00 | 14 | 564 | 100 | 100 | 0 | 19096 | 19096 | 19096 | 23756.7573 | 1 | 0.80381 | TRUE | FALSE | FALSE | 70.5 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144782 | HCFWB2Z2012 | B2 Z2 :Paint Final Layer | 26129 | 2013-03-19 12:00 | 2013-04-02 12:00 | 14 | 564 | 100 | 95 | -5 | 22974 | 22974 | 21825.3 | 26585.5627 | 0.95 | 0.82095 | TRUE | FALSE | FALSE | 70.5 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144783 | HCFWB2Z2004 | B2 Z2 :Epoxy Screed Finish Works | 26134 | 2013-06-04 14:00 | 2013-06-16 14:00 | 12 | 306 | 100 | 100 | 0 | 15660 | 15660 | 15660 | 16031.8404 | 1 | 0.97681 | FALSE | FALSE | FALSE | 38.25 | FALSE | 0 | Green | Continue normal monitoring.
144784 | HCFWB2Z2014 | B2 Z2 :Plaster First Layer | 26351 | 2013-04-02 12:00 | 2013-04-13 10:00 | 10 | 24 | 100 | 90 | -10 | 16820 | 16820 | 15138 | 17300.6612 | 0.9 | 0.875 | TRUE | FALSE | FALSE | 3 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144785 | HCFWB2Z2016 | B2 Z2 :Plaster Final Layer | 26351 | 2013-04-22 10:00 | 2013-05-11 14:00 | 19 | 306 | 100 | 100 | 0 | 24966 | 24966 | 24966 | 27400.4055 | 1 | 0.91115 | FALSE | FALSE | FALSE | 38.25 | FALSE | 0 | Green | Continue normal monitoring.
144786 | HCFWB2Z2017 | B2 Z2 :Paint First Layer | 26351 | 2013-05-11 14:00 | 2013-05-22 14:00 | 11 | 306 | 100 | 95 | -5 | 7997 | 7997 | 7597.15 | 8925.8202 | 0.95 | 0.85114 | TRUE | FALSE | FALSE | 38.25 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144787 | HCFWB2Z2018 | B2 Z2 :Paint Final Layer | 26351 | 2013-05-22 14:00 | 2013-06-04 14:00 | 13 | 306 | 100 | 87 | -13 | 9295 | 9295 | 8086.65 | 9762.3932 | 0.87 | 0.82835 | TRUE | TRUE | TRUE | 38.25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144788 | HCFWB2Z2022 | B2 Z2 :Steel Fire Rated Doors | 26352 | 2013-11-13 08:00 | 2013-11-24 16:00 | 11 | 560 | 100 | 83 | -17 | 15917 | 15917 | 13211.11 | 17635.1524 | 0.83 | 0.74914 | TRUE | TRUE | TRUE | 70 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144789 | HCFWB2Z2005 | B2 Z2 :Rubber Flooring With Spicial Adhesive | 26134 | 2013-06-04 14:00 | 2013-06-16 14:00 | 12 | 306 | 100 | 87 | -13 | 6168 | 6168 | 5366.16 | 5300.8594 | 0.87 | 1.0123 | FALSE | TRUE | TRUE | 38.25 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144790 | HCFWB2Z2006 | B2 Z2 :Rubber Skirting | 26134 | 2013-12-07 08:00 | 2013-12-08 16:00 | 1 | 208 | 100 | 83 | -17 | 1680 | 1680 | 1394.4 | 1716.7066 | 0.83 | 0.81225 | TRUE | TRUE | TRUE | 26 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144791 | HCFWB2Z2021 | B2 Z2 :Steel Doors | 26352 | 2013-11-13 08:00 | 2013-11-24 16:00 | 11 | 560 | 100 | 100 | 0 | 19624 | 19624 | 19624 | 18869.9523 | 1 | 1.04 | FALSE | FALSE | FALSE | 70 | FALSE | 0 | Green | Continue normal monitoring.
144792 | HCFWB2Z2023 | B2 Z2 :Wooden Doors | 26352 | 2013-11-13 08:00 | 2013-11-24 16:00 | 11 | 640 | 100 | 100 | 0 | 18480 | 18480 | 18480 | 16662.8575 | 1 | 1.1091 | FALSE | FALSE | FALSE | 80 | FALSE | 0 | Green | Continue normal monitoring.
144793 | HCFWB2Z2019 | B2 Z2 :Gybsum Board Ceiling | 26351 | 2013-11-10 08:00 | 2013-11-25 16:00 | 15 | 296 | 100 | 82 | -18 | 8190 | 8190 | 6715.8 | 7287.6144 | 0.82 | 0.92154 | FALSE | TRUE | TRUE | 37 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144794 | HCFWB2Z2020 | B2 Z2 :Metal Works & Gutters | 26352 | 2013-11-07 08:00 | 2013-11-18 16:00 | 11 | 344 | 100 | 82 | -18 | 9053 | 9053 | 7423.46 | 9879.3295 | 0.82 | 0.75141 | TRUE | TRUE | TRUE | 43 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144795 | HCFWB2Z2024 | B2 Z2 :Handrails & Railling | 26352 | 2013-11-07 08:00 | 2013-11-24 16:00 | 17 | 344 | 100 | 100 | 0 | 22831 | 22831 | 22831 | 24188.0796 | 1 | 0.94389 | FALSE | FALSE | FALSE | 43 | FALSE | 0 | Green | Continue normal monitoring.
144796 | HCFWB2Z2008 | B2 Z2 :Plaster Second Layer | 26129 | 2013-02-13 14:00 | 2013-02-23 14:00 | 10 | 24 | 100 | 100 | 0 | 6290 | 6290 | 6290 | 5984.5176 | 1 | 1.051 | FALSE | FALSE | FALSE | 3 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144797 | HCFWB2Z2015 | B2 Z2 :Plaster Second Layer | 26351 | 2013-04-13 10:00 | 2013-04-22 10:00 | 9 | 306 | 100 | 97 | -3 | 17406 | 17406 | 16883.82 | 18074.0427 | 0.97 | 0.93415 | FALSE | FALSE | FALSE | 38.25 | FALSE | 0 | Green | Continue normal monitoring.
144798 | HCFWB2Z3002 | B2 Z3 :Trawelled smooth Concrete screed | 26173 | 2013-05-21 10:00 | 2013-06-01 10:00 | 11 | 658 | 100 | 100 | 0 | 6534 | 6534 | 6534 | 6840.3984 | 1 | 0.95521 | FALSE | FALSE | FALSE | 82.25 | FALSE | 0 | Green | Continue normal monitoring.
144799 | HCFWB2Z3003 | B2 Z3 :Sealed Concrete | 26173 | 2013-07-23 08:00 | 2013-07-31 16:00 | 8 | 1016 | 100 | 100 | 0 | 9008 | 9008 | 9008 | 8359.4564 | 1 | 1.0776 | FALSE | FALSE | FALSE | 127 | FALSE | 0 | Green | Continue normal monitoring.
144800 | HCFWB2Z3015 | B2 Z3 :Block Works | 26169 | 2013-01-05 08:00 | 2013-01-20 16:00 | 15 | 508 | 100 | 98 | -2 | 18810 | 18810 | 18433.8 | 20894.8482 | 0.98 | 0.88222 | TRUE | FALSE | FALSE | 63.5 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144801 | HCFWB2Z3009 | B2 Z3 :Plaster First Layer | 26169 | 2013-04-02 12:00 | 2013-04-13 10:00 | 10 | 24 | 100 | 98 | -2 | 18150 | 18150 | 17787 | 21096.9745 | 0.98 | 0.84311 | TRUE | FALSE | FALSE | 3 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144802 | HCFWB2Z3001 | B2 Z3 :Foam Concrete Under Floorings | 26173 | 2013-05-02 10:00 | 2013-05-21 10:00 | 19 | 658 | 100 | 100 | 0 | 24567 | 24567 | 24567 | 28659.5039 | 1 | 0.8572 | TRUE | FALSE | FALSE | 82.25 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144803 | HCFWB2Z3011 | B2 Z3 :Plaster Final Layer | 26169 | 2013-04-22 10:00 | 2013-05-02 10:00 | 10 | 658 | 100 | 84 | -16 | 18060 | 18060 | 15170.4 | 19703.2421 | 0.84 | 0.76994 | TRUE | TRUE | TRUE | 82.25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144804 | HCFWB2Z3012 | B2 Z3 :Paint First Layer | 26169 | 2013-05-02 10:00 | 2013-05-16 10:00 | 14 | 1078 | 100 | 97 | -3 | 7952 | 7952 | 7713.44 | 8386.62 | 0.97 | 0.91973 | FALSE | FALSE | FALSE | 134.75 | FALSE | 0 | Green | Continue normal monitoring.
144805 | HCFWB2Z3013 | B2 Z3 :Paint Final Layer | 26169 | 2013-05-16 10:00 | 2013-06-01 10:00 | 16 | 1078 | 100 | 100 | 0 | 8160 | 8160 | 8160 | 7135.1273 | 1 | 1.1436 | FALSE | FALSE | FALSE | 134.75 | FALSE | 0 | Green | Continue normal monitoring.
144806 | HCFWB2Z3004 | B2 Z3 :Epoxy Screed Finish Works | 26173 | 2013-07-23 08:00 | 2013-08-03 16:00 | 11 | 1016 | 100 | 89 | -11 | 19547 | 19547 | 17396.83 | 18865.4454 | 0.89 | 0.92215 | FALSE | TRUE | TRUE | 127 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144807 | HCFWB2Z3016 | B2 Z3 :Plaster First Layer | 26228 | 2013-06-01 10:00 | 2013-06-10 16:00 | 9 | 658 | 100 | 100 | 0 | 12339 | 12339 | 12339 | 10948.5006 | 1 | 1.127 | FALSE | FALSE | FALSE | 82.25 | FALSE | 0 | Green | Continue normal monitoring.
144808 | HCFWB2Z3018 | B2 Z3 :Plaster Final Layer | 26228 | 2013-06-20 08:00 | 2013-06-29 16:00 | 9 | 658 | 100 | 100 | 0 | 9441 | 9441 | 9441 | 11664.6318 | 1 | 0.80937 | TRUE | FALSE | FALSE | 82.25 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144809 | HCFWB2Z3019 | B2 Z3 :Paint First Layer | 26228 | 2013-06-30 08:00 | 2013-07-10 16:00 | 10 | 1016 | 100 | 100 | 0 | 16570 | 16570 | 16570 | 14979.8112 | 1 | 1.1062 | FALSE | FALSE | FALSE | 127 | FALSE | 0 | Green | Continue normal monitoring.
144810 | HCFWB2Z3020 | B2 Z3 :Paint Final Layer | 26228 | 2013-07-11 08:00 | 2013-07-22 16:00 | 11 | 1016 | 100 | 85 | -15 | 13321 | 13321 | 11322.85 | 12131.5701 | 0.85 | 0.93334 | FALSE | TRUE | TRUE | 127 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144811 | HCFWB2Z3025 | B2 Z3 :Steel Fire Rated Doors | 26366 | 2013-09-16 08:00 | 2013-09-26 16:00 | 10 | 760 | 100 | 80 | -20 | 5220 | 5220 | 4176 | 6294.436 | 0.8 | 0.66344 | TRUE | TRUE | TRUE | 95 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144812 | HCFWB2Z3005 | B2 Z3 :Rubber Flooring With Spicial Adhesive | 26173 | 2013-07-23 08:00 | 2013-08-03 16:00 | 11 | 1016 | 100 | 84 | -16 | 14454 | 14454 | 12141.36 | 17743.3158 | 0.84 | 0.68428 | TRUE | TRUE | TRUE | 127 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144813 | HCFWB2Z3006 | B2 Z3 :Rubber Skirting | 26173 | 2013-12-09 08:00 | 2013-12-10 16:00 | 1 | 208 | 100 | 88 | -12 | 845 | 845 | 743.6 | 977.1002 | 0.88 | 0.76103 | TRUE | TRUE | TRUE | 26 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144814 | HCFWB2Z3023 | B2 Z3 :Steel Doors | 26366 | 2013-11-07 08:00 | 2013-11-18 16:00 | 11 | 440 | 100 | 91 | -9 | 8811 | 8811 | 8018.01 | 7508.3991 | 0.91 | 1.0679 | FALSE | FALSE | FALSE | 55 | FALSE | 0 | Green | Continue normal monitoring.
144815 | HCFWB2Z3024 | B2 Z3 :Wooden Doors | 26366 | 2013-11-07 08:00 | 2013-11-18 16:00 | 11 | 440 | 100 | 100 | 0 | 9482 | 9482 | 9482 | 8064.8061 | 1 | 1.1757 | FALSE | FALSE | FALSE | 55 | FALSE | 0 | Green | Continue normal monitoring.
144816 | HCFWB2Z3021 | B2 Z3 :Gybsum Board Ceiling | 26228 | 2013-11-10 08:00 | 2013-11-25 16:00 | 15 | 328 | 100 | 93 | -7 | 13425 | 13425 | 12485.25 | 13441.6511 | 0.93 | 0.92885 | FALSE | FALSE | FALSE | 41 | FALSE | 0 | Green | Continue normal monitoring.
144817 | HCFWB2Z3022 | B2 Z3 :Metal Works & Gutters | 26366 | 2013-11-07 08:00 | 2013-11-18 16:00 | 11 | 400 | 100 | 81 | -19 | 7887 | 7887 | 6388.47 | 7156.3337 | 0.81 | 0.8927 | TRUE | TRUE | TRUE | 50 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144818 | HCFWB2Z3026 | B2 Z3 :Handrails & Railling | 26366 | 2013-11-07 08:00 | 2013-11-24 16:00 | 17 | 360 | 100 | 96 | -4 | 10880 | 10880 | 10444.8 | 9328.0165 | 0.96 | 1.1197 | FALSE | FALSE | FALSE | 45 | FALSE | 0 | Green | Continue normal monitoring.
144819 | HCFWB2Z3010 | B2 Z3 :Plaster Second Layer | 26169 | 2013-04-13 10:00 | 2013-04-22 10:00 | 9 | 658 | 100 | 93 | -7 | 13113 | 13113 | 12195.09 | 13580.1726 | 0.93 | 0.89801 | TRUE | FALSE | FALSE | 82.25 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144820 | HCFWB2Z3017 | B2 Z3 :Plaster Second Layer | 26228 | 2013-06-11 08:00 | 2013-06-19 16:00 | 8 | 658 | 100 | 100 | 0 | 13864 | 13864 | 13864 | 17014.2441 | 1 | 0.81485 | TRUE | FALSE | FALSE | 82.25 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144821 | HCFWB2Z3007 | B2 Z3 :Stone Flooring | 26173 | 2013-07-23 08:00 | 2013-08-05 16:00 | 13 | 1088 | 100 | 92 | -8 | 19292 | 19292 | 17748.64 | 18897.0509 | 0.92 | 0.93923 | FALSE | FALSE | FALSE | 136 | FALSE | 0 | Green | Continue normal monitoring.
144822 | HCFWB2Z3008 | B2 Z3 :Stone Skirting | 26173 | 2013-08-06 08:00 | 2013-08-20 16:00 | 14 | 1896 | 100 | 100 | 0 | 20888 | 20888 | 20888 | 23278.7626 | 1 | 0.8973 | TRUE | FALSE | FALSE | 237 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144823 | HCFWB2Z3014 | B2 Z3 :Epoxy Paint for Walls | 26169 | 2013-05-02 10:00 | 2013-05-14 10:00 | 12 | 1174 | 100 | 88 | -12 | 15924 | 15924 | 14013.12 | 17689.8783 | 0.88 | 0.79215 | TRUE | TRUE | TRUE | 146.75 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144824 | HCFWB2Z4002 | B2 Z4 :Trawelled smooth Concrete screed | 26231 | 2013-05-22 08:00 | 2013-06-01 16:00 | 10 | 24 | 100 | 100 | 0 | 11820 | 11820 | 11820 | 11234.1067 | 1 | 1.0522 | FALSE | FALSE | FALSE | 3 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144825 | HCFWB2Z4003 | B2 Z4 :Sealed Concrete | 26231 | 2013-07-09 10:00 | 2013-07-18 10:00 | 9 | 774 | 100 | 100 | 0 | 17847 | 17847 | 17847 | 19813.2058 | 1 | 0.90076 | FALSE | FALSE | FALSE | 96.75 | FALSE | 0 | Green | Continue normal monitoring.
144826 | HCFWB2Z4012 | B2 Z4 :Block Works | 26174 | 2013-01-26 08:00 | 2013-02-05 16:00 | 10 | 404 | 100 | 94 | -6 | 15030 | 15030 | 14128.2 | 14052.0519 | 0.94 | 1.0054 | FALSE | FALSE | FALSE | 50.5 | FALSE | 0 | Green | Continue normal monitoring.
144827 | HCFWB2Z4007 | B2 Z4 :Plaster First Layer | 26174 | 2013-04-02 12:00 | 2013-04-13 10:00 | 10 | 24 | 100 | 100 | 0 | 8550 | 8550 | 8550 | 7684.7654 | 1 | 1.1126 | FALSE | FALSE | FALSE | 3 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144828 | HCFWB2Z4001 | B2 Z4 :Foam Concrete Under Floorings | 26231 | 2013-05-04 08:00 | 2013-05-21 16:00 | 17 | 24 | 100 | 100 | 0 | 25619 | 25619 | 25619 | 28963.6454 | 1 | 0.88452 | TRUE | FALSE | FALSE | 3 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144829 | HCFWB2Z4009 | B2 Z4 :Plaster Final Layer | 26174 | 2013-04-22 10:00 | 2013-05-02 16:00 | 10 | 24 | 100 | 94 | -6 | 18470 | 18470 | 17361.8 | 16537.6008 | 0.94 | 1.0498 | FALSE | FALSE | FALSE | 3 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144830 | HCFWB2Z4010 | B2 Z4 :Paint First Layer | 26174 | 2013-06-02 08:00 | 2013-06-10 16:00 | 8 | 24 | 100 | 100 | 0 | 13248 | 13248 | 13248 | 16543.6213 | 1 | 0.80079 | TRUE | FALSE | FALSE | 3 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144831 | HCFWB2Z4011 | B2 Z4 :Paint Final Layer | 26174 | 2013-06-11 08:00 | 2013-06-19 16:00 | 8 | 24 | 100 | 100 | 0 | 11096 | 11096 | 11096 | 10245.8351 | 1 | 1.083 | FALSE | FALSE | FALSE | 3 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144832 | HCFWB2Z4004 | B2 Z4 :Epoxy Screed Finish Works | 26231 | 2013-07-09 10:00 | 2013-07-21 10:00 | 12 | 774 | 100 | 90 | -10 | 7512 | 7512 | 6760.8 | 8170.4775 | 0.9 | 0.82747 | TRUE | FALSE | FALSE | 96.75 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144833 | HCFWB2Z4013 | B2 Z4 :Plaster First Layer | 26342 | 2013-06-02 08:00 | 2013-06-11 14:00 | 9 | 312 | 100 | 100 | 0 | 14661 | 14661 | 14661 | 14874.315 | 1 | 0.98566 | FALSE | FALSE | FALSE | 39 | FALSE | 0 | Green | Continue normal monitoring.
144834 | HCFWB2Z4015 | B2 Z4 :Plaster Final Layer | 26342 | 2013-06-20 14:00 | 2013-07-09 10:00 | 18 | 312 | 100 | 95 | -5 | 27144 | 27144 | 25786.8 | 24444.6532 | 0.95 | 1.0549 | FALSE | FALSE | FALSE | 39 | FALSE | 0 | Green | Continue normal monitoring.
144835 | HCFWB2Z4016 | B2 Z4 :Paint First Layer | 26342 | 2013-07-09 10:00 | 2013-07-21 10:00 | 12 | 1430 | 100 | 100 | 0 | 13236 | 13236 | 13236 | 11398.0168 | 1 | 1.1613 | FALSE | FALSE | FALSE | 178.75 | FALSE | 0 | Green | Continue normal monitoring.
144836 | HCFWB2Z4017 | B2 Z4 :Paint Final Layer | 26342 | 2013-07-21 10:00 | 2013-08-01 10:00 | 11 | 2006 | 100 | 96 | -4 | 20911 | 20911 | 20074.56 | 22983.1319 | 0.96 | 0.87345 | TRUE | FALSE | FALSE | 250.75 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144837 | HCFWB2Z4021 | B2 Z4 :Steel Fire Rated Doors | 26370 | 2013-09-16 08:00 | 2013-09-26 16:00 | 10 | 1064 | 100 | 100 | 0 | 15130 | 15130 | 15130 | 17742.9968 | 1 | 0.85273 | TRUE | FALSE | FALSE | 133 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144838 | HCFWB2Z4005 | B2 Z4 :Rubber Flooring With Spicial Adhesive | 26231 | 2013-07-09 10:00 | 2013-07-21 10:00 | 12 | 774 | 100 | 83 | -17 | 6600 | 6600 | 5478 | 7832.9213 | 0.83 | 0.69936 | TRUE | TRUE | TRUE | 96.75 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144839 | HCFWB2Z4006 | B2 Z4 :Rubber Skirting | 26231 | 2013-12-11 08:00 | 2013-12-12 16:00 | 1 | 208 | 100 | 80 | -20 | 1552 | 1552 | 1241.6 | 1618.8685 | 0.8 | 0.76696 | TRUE | TRUE | TRUE | 26 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144840 | HCFWB2Z4020 | B2 Z4 :Steel Doors | 26370 | 2013-11-07 08:00 | 2013-11-18 16:00 | 11 | 744 | 100 | 87 | -13 | 21835 | 21835 | 18996.45 | 25350.0461 | 0.87 | 0.74937 | TRUE | TRUE | TRUE | 93 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144841 | HCFWB2Z4022 | B2 Z4 :Wooden Doors | 26370 | 2013-11-07 08:00 | 2013-11-18 16:00 | 11 | 744 | 100 | 96 | -4 | 20009 | 20009 | 19208.64 | 22392.8493 | 0.96 | 0.8578 | TRUE | FALSE | FALSE | 93 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144842 | HCFWB2Z4018 | B2 Z4 :Gybsum Board Ceiling | 26342 | 2013-11-10 08:00 | 2013-11-25 16:00 | 15 | 744 | 100 | 82 | -18 | 27300 | 27300 | 22386 | 31113.8594 | 0.82 | 0.71949 | TRUE | TRUE | TRUE | 93 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144843 | HCFWB2Z4019 | B2 Z4 :Metal Works & Gutters | 26370 | 2013-11-07 08:00 | 2013-11-18 16:00 | 11 | 744 | 100 | 100 | 0 | 14058 | 14058 | 14058 | 14719.2827 | 1 | 0.95507 | FALSE | FALSE | FALSE | 93 | FALSE | 0 | Green | Continue normal monitoring.
144844 | HCFWB2Z4023 | B2 Z4 :Handrails & Railling | 26370 | 2013-11-07 08:00 | 2013-11-24 16:00 | 17 | 744 | 100 | 99 | -1 | 32810 | 32810 | 32481.9 | 36201.3957 | 0.99 | 0.89726 | TRUE | FALSE | FALSE | 93 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144845 | HCFWB2Z4008 | B2 Z4 :Plaster Second Layer | 26174 | 2013-04-13 10:00 | 2013-04-22 10:00 | 9 | 24 | 100 | 94 | -6 | 11817 | 11817 | 11107.98 | 13852.0099 | 0.94 | 0.8019 | TRUE | FALSE | FALSE | 3 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144846 | HCFWB2Z4014 | B2 Z4 :Plaster Second Layer | 26342 | 2013-06-11 14:00 | 2013-06-20 14:00 | 9 | 312 | 100 | 94 | -6 | 17352 | 17352 | 16310.88 | 17510.8345 | 0.94 | 0.93147 | FALSE | FALSE | FALSE | 39 | FALSE | 0 | Green | Continue normal monitoring.
144847 | HCFWB2Z5002 | B2 Z5 :Trawelled smooth Concrete screed | 26179 | 2013-07-31 08:00 | 2013-08-12 16:00 | 12 | 156 | 100 | 100 | 0 | 22428 | 22428 | 22428 | 26294.3979 | 1 | 0.85296 | TRUE | FALSE | FALSE | 19.5 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144848 | HCFWB2Z5004 | B2 Z5 :Sealed Concrete | 26179 | 2013-09-11 12:00 | 2013-09-21 12:00 | 10 | 724 | 100 | 100 | 0 | 9190 | 9190 | 9190 | 9987.7539 | 1 | 0.92013 | FALSE | FALSE | FALSE | 90.5 | FALSE | 0 | Green | Continue normal monitoring.
144849 | HCFWB2Z5012 | B2 Z5 :Block Works | 26198 | 2013-01-14 08:00 | 2013-01-26 16:00 | 12 | 1080 | 100 | 100 | 0 | 20460 | 20460 | 20460 | 18748.734 | 1 | 1.0913 | FALSE | FALSE | FALSE | 135 | FALSE | 0 | Green | Continue normal monitoring.
144850 | HCFWB2Z5007 | B2 Z5 :Plaster First Layer | 26198 | 2013-06-12 12:00 | 2013-06-23 10:00 | 10 | 156 | 100 | 93 | -7 | 14820 | 14820 | 13782.6 | 12743.3277 | 0.93 | 1.0816 | FALSE | FALSE | FALSE | 19.5 | FALSE | 0 | Green | Continue normal monitoring.
144851 | HCFWB2Z5001 | B2 Z5 :Foam Concrete Under Floorings | 26179 | 2013-07-13 08:00 | 2013-07-30 16:00 | 17 | 156 | 100 | 100 | 0 | 22508 | 22508 | 22508 | 22397.7432 | 1 | 1.0049 | FALSE | FALSE | FALSE | 19.5 | FALSE | 0 | Green | Continue normal monitoring.
144852 | HCFWB2Z5009 | B2 Z5 :Plaster Final Layer | 26198 | 2013-07-02 10:00 | 2013-07-11 16:00 | 9 | 156 | 100 | 100 | 0 | 13716 | 13716 | 13716 | 14657.9947 | 1 | 0.93574 | FALSE | FALSE | FALSE | 19.5 | FALSE | 0 | Green | Continue normal monitoring.
144853 | HCFWB2Z5010 | B2 Z5 :Paint First Layer | 26198 | 2013-10-14 12:00 | 2013-11-02 12:00 | 19 | 1332 | 100 | 100 | 0 | 20254 | 20254 | 20254 | 24019.7886 | 1 | 0.84322 | TRUE | FALSE | FALSE | 166.5 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144854 | HCFWB2Z5011 | B2 Z5 :Paint Final Layer | 26198 | 2013-11-02 12:00 | 2013-11-17 12:00 | 15 | 1332 | 100 | 93 | -7 | 13050 | 13050 | 12136.5 | 11757.9753 | 0.93 | 1.0322 | FALSE | FALSE | FALSE | 166.5 | FALSE | 0 | Green | Continue normal monitoring.
144855 | HCFWB2Z5003 | B2 Z5 :Epoxy Screed Finish Works | 26179 | 2013-09-11 12:00 | 2013-09-23 12:00 | 12 | 724 | 100 | 100 | 0 | 17220 | 17220 | 17220 | 20148.8213 | 1 | 0.85464 | TRUE | FALSE | FALSE | 90.5 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144856 | HCFWB2Z5013 | B2 Z5 :Plaster First Layer | 26364 | 2013-08-13 08:00 | 2013-08-22 14:00 | 9 | 156 | 100 | 81 | -19 | 10440 | 10440 | 8456.4 | 12477.9258 | 0.81 | 0.67771 | TRUE | TRUE | TRUE | 19.5 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144857 | HCFWB2Z5015 | B2 Z5 :Plaster Final Layer | 26364 | 2013-09-01 14:00 | 2013-09-11 12:00 | 9 | 156 | 100 | 92 | -8 | 17586 | 17586 | 16179.12 | 16008.0961 | 0.92 | 1.0107 | FALSE | FALSE | FALSE | 19.5 | FALSE | 0 | Green | Continue normal monitoring.
144858 | HCFWB2Z5016 | B2 Z5 :Paint First Layer | 26364 | 2013-09-21 12:00 | 2013-10-02 12:00 | 11 | 724 | 100 | 100 | 0 | 16148 | 16148 | 16148 | 19226.418 | 1 | 0.83989 | TRUE | FALSE | FALSE | 90.5 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144859 | HCFWB2Z5017 | B2 Z5 :Paint Final Layer | 26364 | 2013-10-02 12:00 | 2013-10-14 12:00 | 12 | 1332 | 100 | 93 | -7 | 21984 | 21984 | 20445.12 | 27404.8461 | 0.93 | 0.74604 | TRUE | FALSE | FALSE | 166.5 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144860 | HCFWB2Z5020 | B2 Z5 :Steel Fire Rated Doors | 26387 | 2013-10-02 12:00 | 2013-10-14 12:00 | 12 | 1124 | 100 | 100 | 0 | 19920 | 19920 | 19920 | 22723.4518 | 1 | 0.87663 | TRUE | FALSE | FALSE | 140.5 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144861 | HCFWB2Z5005 | B2 Z5 :Rubber Flooring With Spicial Adhesive | 26179 | 2013-09-11 12:00 | 2013-09-23 12:00 | 12 | 588 | 100 | 100 | 0 | 8412 | 8412 | 8412 | 9790.793 | 1 | 0.85917 | TRUE | FALSE | FALSE | 73.5 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144862 | HCFWB2Z5006 | B2 Z5 :Rubber Skirting | 26179 | 2013-12-14 08:00 | 2013-12-15 16:00 | 1 | 208 | 100 | 98 | -2 | 1959 | 1959 | 1919.82 | 2444.3738 | 0.98 | 0.7854 | TRUE | FALSE | FALSE | 26 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144863 | HCFWB2Z5019 | B2 Z5 :Steel Doors | 26387 | 2013-11-19 08:00 | 2013-11-30 16:00 | 11 | 840 | 100 | 86 | -14 | 8932 | 8932 | 7681.52 | 9755.4634 | 0.86 | 0.78741 | TRUE | TRUE | TRUE | 105 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144864 | HCFWB2Z5021 | B2 Z5 :Wooden Doors | 26387 | 2013-11-19 08:00 | 2013-11-30 16:00 | 11 | 1240 | 100 | 82 | -18 | 6776 | 6776 | 5556.32 | 6594.0952 | 0.82 | 0.84262 | TRUE | TRUE | TRUE | 155 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144865 | HCFWB2Z5018 | B2 Z5 :Metal Works & Gutters | 26387 | 2013-11-07 08:00 | 2013-11-18 16:00 | 11 | 520 | 100 | 94 | -6 | 15796 | 15796 | 14848.24 | 18718.4548 | 0.94 | 0.79324 | TRUE | FALSE | FALSE | 65 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144866 | HCFWB2Z5008 | B2 Z5 :Plaster Second Layer | 26198 | 2013-06-23 10:00 | 2013-07-02 10:00 | 9 | 156 | 100 | 100 | 0 | 9666 | 9666 | 9666 | 10591.9478 | 1 | 0.91258 | FALSE | FALSE | FALSE | 19.5 | FALSE | 0 | Green | Continue normal monitoring.
144867 | HCFWB2Z5014 | B2 Z5 :Plaster Second Layer | 26364 | 2013-08-22 14:00 | 2013-09-01 14:00 | 10 | 156 | 100 | 93 | -7 | 7430 | 7430 | 6909.9 | 8042.8128 | 0.93 | 0.85914 | TRUE | FALSE | FALSE | 19.5 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144868 | HCFWB2Z6002 | B2 Z6 :Trawelled smooth Concrete screed | 26389 | 2013-07-31 08:00 | 2013-08-12 16:00 | 12 | 534 | 100 | 90 | -10 | 12432 | 12432 | 11188.8 | 11828.4789 | 0.9 | 0.94592 | FALSE | FALSE | FALSE | 66.75 | FALSE | 0 | Green | Continue normal monitoring.
144869 | HCFWB2Z6003 | B2 Z6 :Sealed Concrete | 26389 | 2013-09-19 10:00 | 2013-09-29 10:00 | 10 | 534 | 100 | 94 | -6 | 5740 | 5740 | 5395.6 | 6615.5435 | 0.94 | 0.81559 | TRUE | FALSE | FALSE | 66.75 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144870 | HCFWB2Z6012 | B2 Z6 :Block Works | 26167 | 2012-12-19 08:00 | 2012-12-30 16:00 | 11 | 1626 | 100 | 100 | 0 | 9735 | 9735 | 9735 | 8592.7624 | 1 | 1.1329 | FALSE | FALSE | FALSE | 203.25 | FALSE | 0 | Green | Continue normal monitoring.
144871 | HCFWB2Z6007 | B2 Z6 :Plaster First Layer | 26167 | 2013-06-12 12:00 | 2013-06-23 10:00 | 10 | 534 | 100 | 92 | -8 | 17330 | 17330 | 15943.6 | 21137.658 | 0.92 | 0.75427 | TRUE | FALSE | FALSE | 66.75 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144872 | HCFWB2Z6001 | B2 Z6 :Foam Concrete Under Floorings | 26389 | 2013-07-13 08:00 | 2013-07-30 16:00 | 17 | 534 | 100 | 97 | -3 | 16558 | 16558 | 16061.26 | 16232.2939 | 0.97 | 0.98946 | FALSE | FALSE | FALSE | 66.75 | FALSE | 0 | Green | Continue normal monitoring.
144873 | HCFWB2Z6009 | B2 Z6 :Plaster Final Layer | 26167 | 2013-07-02 10:00 | 2013-07-11 16:00 | 9 | 534 | 100 | 100 | 0 | 8253 | 8253 | 8253 | 7436.8597 | 1 | 1.1097 | FALSE | FALSE | FALSE | 66.75 | FALSE | 0 | Green | Continue normal monitoring.
144874 | HCFWB2Z6010 | B2 Z6 :Paint First Layer | 26167 | 2013-09-29 10:00 | 2013-10-13 10:00 | 14 | 1438 | 100 | 85 | -15 | 11844 | 11844 | 10067.4 | 12163.1557 | 0.85 | 0.8277 | TRUE | TRUE | TRUE | 179.75 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144875 | HCFWB2Z6011 | B2 Z6 :Paint Final Layer | 26167 | 2013-10-13 10:00 | 2013-10-31 10:00 | 18 | 1438 | 100 | 82 | -18 | 20502 | 20502 | 16811.64 | 17774.9872 | 0.82 | 0.9458 | FALSE | TRUE | TRUE | 179.75 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144876 | HCFWB2Z6004 | B2 Z6 :Epoxy Screed Finish Works | 26389 | 2013-09-19 10:00 | 2013-10-01 10:00 | 12 | 534 | 100 | 98 | -2 | 17256 | 17256 | 16910.88 | 19393.1638 | 0.98 | 0.872 | TRUE | FALSE | FALSE | 66.75 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144877 | HCFWB2Z6013 | B2 Z6 :Plaster First Layer | 26168 | 2013-08-13 08:00 | 2013-08-22 14:00 | 9 | 534 | 100 | 94 | -6 | 13086 | 13086 | 12300.84 | 15848.2217 | 0.94 | 0.77617 | TRUE | FALSE | FALSE | 66.75 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144878 | HCFWB2Z6015 | B2 Z6 :Plaster Final Layer | 26168 | 2013-09-01 14:00 | 2013-09-19 10:00 | 17 | 534 | 100 | 100 | 0 | 23375 | 23375 | 23375 | 27697.1591 | 1 | 0.84395 | TRUE | FALSE | FALSE | 66.75 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144879 | HCFWB2Z6016 | B2 Z6 :Paint First Layer | 26168 | 2013-09-29 10:00 | 2013-10-10 10:00 | 11 | 750 | 100 | 100 | 0 | 13882 | 13882 | 13882 | 12506.9572 | 1 | 1.1099 | FALSE | FALSE | FALSE | 93.75 | FALSE | 0 | Green | Continue normal monitoring.
144880 | HCFWB2Z6017 | B2 Z6 :Paint Final Layer | 26168 | 2013-10-10 10:00 | 2013-10-27 10:00 | 17 | 1390 | 100 | 84 | -16 | 28934 | 28934 | 24304.56 | 26055.3116 | 0.84 | 0.93281 | FALSE | TRUE | TRUE | 173.75 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144881 | HCFWB2Z6020 | B2 Z6 :Steel Fire Rated Doors | 26251 | 2013-10-10 10:00 | 2013-10-27 10:00 | 17 | 750 | 100 | 100 | 0 | 28985 | 28985 | 28985 | 34068.2094 | 1 | 0.85079 | TRUE | FALSE | FALSE | 93.75 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144882 | HCFWB2Z6005 | B2 Z6 :Rubber Flooring With Spicial Adhesive | 26389 | 2013-09-19 10:00 | 2013-10-01 10:00 | 12 | 534 | 100 | 89 | -11 | 13956 | 13956 | 12420.84 | 17022.1571 | 0.89 | 0.72969 | TRUE | TRUE | TRUE | 66.75 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144883 | HCFWB2Z6006 | B2 Z6 :Rubber Skirting | 26389 | 2013-12-16 08:00 | 2013-12-17 16:00 | 1 | 208 | 100 | 86 | -14 | 524 | 524 | 450.64 | 541.9564 | 0.86 | 0.83151 | TRUE | TRUE | TRUE | 26 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144884 | HCFWB2Z6019 | B2 Z6 :Steel Doors | 26251 | 2013-11-07 08:00 | 2013-11-18 16:00 | 11 | 600 | 100 | 100 | 0 | 18733 | 18733 | 18733 | 19661.9404 | 1 | 0.95275 | FALSE | FALSE | FALSE | 75 | FALSE | 0 | Green | Continue normal monitoring.
144885 | HCFWB2Z6021 | B2 Z6 :Wooden Doors | 26251 | 2013-11-07 08:00 | 2013-11-18 16:00 | 11 | 1320 | 100 | 96 | -4 | 13299 | 13299 | 12767.04 | 12997.1768 | 0.96 | 0.98229 | FALSE | FALSE | FALSE | 165 | FALSE | 0 | Green | Continue normal monitoring.
144886 | HCFWB2Z6018 | B2 Z6 :Metal Works & Gutters | 26251 | 2013-11-07 08:00 | 2013-11-18 16:00 | 11 | 520 | 100 | 86 | -14 | 18524 | 18524 | 15930.64 | 22371.5468 | 0.86 | 0.71209 | TRUE | TRUE | TRUE | 65 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144887 | HCFWB2Z6008 | B2 Z6 :Plaster Second Layer | 26167 | 2013-06-23 10:00 | 2013-07-02 10:00 | 9 | 534 | 100 | 100 | 0 | 6084 | 6084 | 6084 | 6740.8357 | 1 | 0.90256 | FALSE | FALSE | FALSE | 66.75 | FALSE | 0 | Green | Continue normal monitoring.
144888 | HCFWB2Z6014 | B2 Z6 :Plaster Second Layer | 26168 | 2013-08-22 14:00 | 2013-09-01 14:00 | 10 | 534 | 100 | 100 | 0 | 7840 | 7840 | 7840 | 7567.9569 | 1 | 1.0359 | FALSE | FALSE | FALSE | 66.75 | FALSE | 0 | Green | Continue normal monitoring.
144889 | HCFWB300010 | Start Finishing Works B3 | 25850 | 2012-11-06 08:00 | 2012-11-06 08:00 | 1 | 262 | 100 | 100 | 0 | 562 | 562 | 562 | 544.8664 | 1 | 1.0314 | FALSE | FALSE | FALSE | 32.75 | FALSE | 0 | Green | Continue normal monitoring.
144890 | HCFWB300011 | End Finishing Works B3 | 25850 | 2014-04-02 16:00 | 2014-04-02 16:00 | 1 | 416 | 100 | 91 | -9 | 1502 | 1502 | 1366.82 | 1812.133 | 0.91 | 0.75426 | TRUE | FALSE | FALSE | 52 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144891 | HCFWB3Z1002 | B3 Z1 :Trawelled smooth Concrete screed | 26172 | 2013-02-14 14:00 | 2013-02-24 14:00 | 10 | 626 | 100 | 100 | 0 | 11610 | 11610 | 11610 | 9931.8164 | 1 | 1.169 | FALSE | FALSE | FALSE | 78.25 | FALSE | 0 | Green | Continue normal monitoring.
144892 | HCFWB3Z1003 | B3 Z1 :Sealed Concrete | 26172 | 2013-06-18 08:00 | 2013-06-26 16:00 | 8 | 24 | 100 | 96 | -4 | 9320 | 9320 | 8947.2 | 9125.1247 | 0.96 | 0.9805 | FALSE | FALSE | FALSE | 3 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144893 | HCFWB3Z1012 | B3 Z1 :Block Works | 26244 | 2012-11-06 08:00 | 2012-11-18 16:00 | 12 | 182 | 100 | 92 | -8 | 7860 | 7860 | 7231.2 | 8423.8974 | 0.92 | 0.85842 | TRUE | FALSE | FALSE | 22.75 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144894 | HCFWB3Z1007 | B3 Z1 :Plaster First Layer | 26244 | 2012-11-19 08:00 | 2012-11-28 14:00 | 9 | 182 | 100 | 99 | -1 | 17928 | 17928 | 17748.72 | 16301.6971 | 0.99 | 1.0888 | FALSE | FALSE | FALSE | 22.75 | FALSE | 0 | Green | Continue normal monitoring.
144895 | HCFWB3Z1001 | B3 Z1 :Foam Concrete & Proofing Membrane Under Floorings | 26172 | 2013-01-27 14:00 | 2013-02-14 14:00 | 18 | 626 | 100 | 100 | 0 | 28296 | 28296 | 28296 | 25094.0105 | 1 | 1.1276 | FALSE | FALSE | FALSE | 78.25 | FALSE | 0 | Green | Continue normal monitoring.
144896 | HCFWB3Z1009 | B3 Z1 :Plaster Final Layer | 26244 | 2012-12-08 14:00 | 2012-12-18 12:00 | 9 | 626 | 100 | 83 | -17 | 13194 | 13194 | 10951.02 | 15517.6024 | 0.83 | 0.70572 | TRUE | TRUE | TRUE | 78.25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144897 | HCFWB3Z1010 | B3 Z1 :Paint First Layer | 26244 | 2012-12-18 12:00 | 2013-01-02 12:00 | 15 | 1188 | 100 | 89 | -11 | 20220 | 20220 | 17995.8 | 24420.9427 | 0.89 | 0.7369 | TRUE | TRUE | TRUE | 148.5 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144898 | HCFWB3Z1011 | B3 Z1 :Paint Final Layer | 26244 | 2013-06-25 08:00 | 2013-06-29 16:00 | 4 | 24 | 100 | 82 | -18 | 6428 | 6428 | 5270.96 | 7581.4568 | 0.82 | 0.69524 | TRUE | TRUE | TRUE | 3 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
144899 | HCFWB3Z1004 | B3 Z1 :Epoxy Screed Finish Works | 26172 | 2013-06-18 08:00 | 2013-06-29 16:00 | 11 | 24 | 100 | 88 | -12 | 20724 | 20724 | 18237.12 | 25065.9921 | 0.88 | 0.72756 | TRUE | TRUE | TRUE | 3 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
144900 | HCFWB3Z1013 | B3 Z1 :Plaster First Layer | 26390 | 2012-12-18 12:00 | 2012-12-29 10:00 | 10 | 626 | 100 | 92 | -8 | 11880 | 11880 | 10929.6 | 12726.3881 | 0.92 | 0.85881 | TRUE | FALSE | FALSE | 78.25 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144901 | HCFWB3Z1015 | B3 Z1 :Plaster Final Layer | 26390 | 2013-01-08 10:00 | 2013-01-27 14:00 | 19 | 626 | 100 | 97 | -3 | 12293 | 12293 | 11924.21 | 14443.0856 | 0.97 | 0.8256 | TRUE | FALSE | FALSE | 78.25 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144902 | HCFWB3Z1016 | B3 Z1 :Paint First Layer | 26390 | 2013-02-24 14:00 | 2013-03-07 14:00 | 11 | 626 | 100 | 94 | -6 | 9251 | 9251 | 8695.94 | 9284.4614 | 0.94 | 0.93661 | FALSE | FALSE | FALSE | 78.25 | FALSE | 0 | Green | Continue normal monitoring.
144903 | HCFWB3Z1017 | B3 Z1 :Paint Final Layer | 26390 | 2013-03-07 14:00 | 2013-03-19 14:00 | 12 | 626 | 100 | 83 | -17 | 11700 | 11700 | 9711 | 13063.1336 | 0.83 | 0.74339 | TRUE | TRUE | TRUE | 78.25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144904 | HCFWB3Z1021 | B3 Z1 :Steel Fire Rated Doors | 26233 | 2013-10-26 08:00 | 2013-11-06 16:00 | 11 | 560 | 100 | 94 | -6 | 17446 | 17446 | 16399.24 | 21729.5899 | 0.94 | 0.7547 | TRUE | FALSE | FALSE | 70 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144905 | HCFWB3Z1005 | B3 Z1 :Rubber Flooring With Spicial Adhesive | 26172 | 2013-06-18 08:00 | 2013-06-29 16:00 | 11 | 24 | 100 | 100 | 0 | 20713 | 20713 | 20713 | 19476.2493 | 1 | 1.0635 | FALSE | FALSE | FALSE | 3 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144906 | HCFWB3Z1006 | B3 Z1 :Rubber Skirting | 26172 | 2013-11-20 08:00 | 2013-11-21 16:00 | 1 | 208 | 100 | 81 | -19 | 1060 | 1060 | 858.6 | 1066.3175 | 0.81 | 0.8052 | TRUE | TRUE | TRUE | 26 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144907 | HCFWB3Z1020 | B3 Z1 :Steel Doors | 26233 | 2013-10-26 08:00 | 2013-11-06 16:00 | 11 | 560 | 100 | 94 | -6 | 9086 | 9086 | 8540.84 | 9467.7842 | 0.94 | 0.90209 | FALSE | FALSE | FALSE | 70 | FALSE | 0 | Green | Continue normal monitoring.
144908 | HCFWB3Z1022 | B3 Z1 :Wooden Doors | 26233 | 2013-11-07 08:00 | 2013-11-18 16:00 | 11 | 480 | 100 | 87 | -13 | 18304 | 18304 | 15924.48 | 16568.8942 | 0.87 | 0.96111 | FALSE | TRUE | TRUE | 60 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144909 | HCFWB3Z1018 | B3 Z1 :Gybsum Board Ceiling | 26390 | 2013-10-24 08:00 | 2013-11-10 16:00 | 17 | 208 | 100 | 87 | -13 | 25313 | 25313 | 22022.31 | 22336.5821 | 0.87 | 0.98593 | FALSE | TRUE | TRUE | 26 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144910 | HCFWB3Z1019 | B3 Z1 :Metal Works & Gutters | 26233 | 2013-10-20 08:00 | 2013-10-30 16:00 | 10 | 384 | 100 | 96 | -4 | 7140 | 7140 | 6854.4 | 8438.6885 | 0.96 | 0.81226 | TRUE | FALSE | FALSE | 48 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144911 | HCFWB3Z1023 | B3 Z1 :Handrails & Railling | 26233 | 2013-10-20 08:00 | 2013-11-06 16:00 | 17 | 344 | 100 | 91 | -9 | 15878 | 15878 | 14448.98 | 19700.1164 | 0.91 | 0.73345 | TRUE | FALSE | FALSE | 43 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144912 | HCFWB3Z1008 | B3 Z1 :Plaster Second Layer | 26244 | 2012-11-28 14:00 | 2012-12-08 14:00 | 10 | 626 | 100 | 98 | -2 | 14510 | 14510 | 14219.8 | 14682.5243 | 0.98 | 0.96848 | FALSE | FALSE | FALSE | 78.25 | FALSE | 0 | Green | Continue normal monitoring.
144913 | HCFWB3Z1014 | B3 Z1 :Plaster Second Layer | 26390 | 2012-12-29 10:00 | 2013-01-08 10:00 | 10 | 626 | 100 | 89 | -11 | 12220 | 12220 | 10875.8 | 10815.4324 | 0.89 | 1.0056 | FALSE | TRUE | TRUE | 78.25 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144914 | HCFWB3Z2002 | B3 Z2 :Trawelled smooth Concrete screed | 26340 | 2013-01-21 12:00 | 2013-01-31 12:00 | 10 | 86 | 100 | 88 | -12 | 18410 | 18410 | 16200.8 | 16133.1378 | 0.88 | 1.0042 | FALSE | TRUE | TRUE | 10.75 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144915 | HCFWB3Z2003 | B3 Z2 :Sealed Concrete | 26340 | 2013-03-26 08:00 | 2013-04-03 16:00 | 8 | 584 | 100 | 84 | -16 | 4248 | 4248 | 3568.32 | 5125.3279 | 0.84 | 0.69621 | TRUE | TRUE | TRUE | 73 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144916 | HCFWB3Z2012 | B3 Z2 :Block Works | 26140 | 2012-11-21 08:00 | 2012-12-02 16:00 | 11 | 86 | 100 | 85 | -15 | 12859 | 12859 | 10930.15 | 13315.825 | 0.85 | 0.82084 | TRUE | TRUE | TRUE | 10.75 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144917 | HCFWB3Z2007 | B3 Z2 :Plaster First Layer | 26140 | 2012-12-03 08:00 | 2012-12-12 14:00 | 9 | 86 | 100 | 99 | -1 | 7056 | 7056 | 6985.44 | 6900.8451 | 0.99 | 1.0123 | FALSE | FALSE | FALSE | 10.75 | FALSE | 0 | Green | Continue normal monitoring.
144918 | HCFWB3Z2001 | B3 Z2 :Foam Concrete & Proofing Membrane Under Floorings | 26340 | 2013-01-02 12:00 | 2013-01-21 12:00 | 19 | 86 | 100 | 100 | 0 | 34732 | 34732 | 34732 | 36141.5811 | 1 | 0.961 | FALSE | FALSE | FALSE | 10.75 | FALSE | 0 | Green | Continue normal monitoring.
144919 | HCFWB3Z2009 | B3 Z2 :Plaster Final Layer | 26140 | 2012-12-22 14:00 | 2013-01-02 12:00 | 10 | 86 | 100 | 81 | -19 | 9280 | 9280 | 7516.8 | 9069.5448 | 0.81 | 0.8288 | TRUE | TRUE | TRUE | 10.75 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144920 | HCFWB3Z2010 | B3 Z2 :Paint First Layer | 26140 | 2013-01-02 12:00 | 2013-01-16 12:00 | 14 | 788 | 100 | 100 | 0 | 10990 | 10990 | 10990 | 11491.3013 | 1 | 0.95638 | FALSE | FALSE | FALSE | 98.5 | FALSE | 0 | Green | Continue normal monitoring.
144921 | HCFWB3Z2011 | B3 Z2 :Paint Final Layer | 26140 | 2013-01-16 12:00 | 2013-01-31 12:00 | 15 | 788 | 100 | 100 | 0 | 25005 | 25005 | 25005 | 29851.5331 | 1 | 0.83765 | TRUE | FALSE | FALSE | 98.5 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144922 | HCFWB3Z2004 | B3 Z2 :Epoxy Screed Finish Works | 26340 | 2013-03-26 08:00 | 2013-04-06 16:00 | 11 | 584 | 100 | 100 | 0 | 21417 | 21417 | 21417 | 23278.5774 | 1 | 0.92003 | FALSE | FALSE | FALSE | 73 | FALSE | 0 | Green | Continue normal monitoring.
144923 | HCFWB3Z2013 | B3 Z2 :Plaster First Layer | 26196 | 2013-01-31 12:00 | 2013-02-11 10:00 | 10 | 86 | 100 | 92 | -8 | 15420 | 15420 | 14186.4 | 17391.6245 | 0.92 | 0.8157 | TRUE | FALSE | FALSE | 10.75 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144924 | HCFWB3Z2015 | B3 Z2 :Plaster Final Layer | 26196 | 2013-02-20 10:00 | 2013-03-02 16:00 | 10 | 584 | 100 | 85 | -15 | 5170 | 5170 | 4394.5 | 5148.639 | 0.85 | 0.85353 | TRUE | TRUE | TRUE | 73 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144925 | HCFWB3Z2016 | B3 Z2 :Paint First Layer | 26196 | 2013-03-03 08:00 | 2013-03-13 16:00 | 10 | 584 | 100 | 84 | -16 | 12680 | 12680 | 10651.2 | 14523.7018 | 0.84 | 0.73337 | TRUE | TRUE | TRUE | 73 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144926 | HCFWB3Z2017 | B3 Z2 :Paint Final Layer | 26196 | 2013-03-14 08:00 | 2013-03-25 16:00 | 11 | 584 | 100 | 100 | 0 | 11979 | 11979 | 11979 | 13376.3124 | 1 | 0.89554 | TRUE | FALSE | FALSE | 73 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144927 | HCFWB3Z2021 | B3 Z2 :Steel Fire Rated Doors | 26391 | 2013-10-31 08:00 | 2013-11-12 16:00 | 12 | 560 | 100 | 80 | -20 | 22728 | 22728 | 18182.4 | 20405.762 | 0.8 | 0.89104 | TRUE | TRUE | TRUE | 70 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144928 | HCFWB3Z2005 | B3 Z2 :Rubber Flooring With Spicial Adhesive | 26340 | 2013-03-26 08:00 | 2013-04-06 16:00 | 11 | 584 | 100 | 100 | 0 | 18678 | 18678 | 18678 | 20154.6293 | 1 | 0.92673 | FALSE | FALSE | FALSE | 73 | FALSE | 0 | Green | Continue normal monitoring.
144929 | HCFWB3Z2006 | B3 Z2 :Rubber Skirting | 26340 | 2013-11-23 08:00 | 2013-11-24 16:00 | 1 | 208 | 100 | 100 | 0 | 1509 | 1509 | 1509 | 1437.6204 | 1 | 1.0497 | FALSE | FALSE | FALSE | 26 | FALSE | 0 | Green | Continue normal monitoring.
144930 | HCFWB3Z2020 | B3 Z2 :Steel Doors | 26391 | 2013-10-31 08:00 | 2013-11-12 16:00 | 12 | 560 | 100 | 100 | 0 | 8316 | 8316 | 8316 | 9743.3438 | 1 | 0.85351 | TRUE | FALSE | FALSE | 70 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144931 | HCFWB3Z2022 | B3 Z2 :Wooden Doors | 26391 | 2013-10-31 08:00 | 2013-11-12 16:00 | 12 | 640 | 100 | 85 | -15 | 12012 | 12012 | 10210.2 | 12256.7455 | 0.85 | 0.83303 | TRUE | TRUE | TRUE | 80 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144932 | HCFWB3Z2018 | B3 Z2 :Gybsum Board Ceiling | 26196 | 2013-10-23 08:00 | 2013-11-09 16:00 | 17 | 296 | 100 | 85 | -15 | 25279 | 25279 | 21487.15 | 31544.9984 | 0.85 | 0.68116 | TRUE | TRUE | TRUE | 37 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144933 | HCFWB3Z2019 | B3 Z2 :Metal Works & Gutters | 26391 | 2013-10-20 08:00 | 2013-10-30 16:00 | 10 | 384 | 100 | 100 | 0 | 16360 | 16360 | 16360 | 14511.3229 | 1 | 1.1274 | FALSE | FALSE | FALSE | 48 | FALSE | 0 | Green | Continue normal monitoring.
144934 | HCFWB3Z2023 | B3 Z2 :Handrails & Railling | 26391 | 2013-10-20 08:00 | 2013-11-06 16:00 | 17 | 344 | 100 | 95 | -5 | 10421 | 10421 | 9899.95 | 12110.652 | 0.95 | 0.81746 | TRUE | FALSE | FALSE | 43 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144935 | HCFWB3Z2008 | B3 Z2 :Plaster Second Layer | 26140 | 2012-12-12 14:00 | 2012-12-22 14:00 | 10 | 86 | 100 | 83 | -17 | 17450 | 17450 | 14483.5 | 19534.9381 | 0.83 | 0.74142 | TRUE | TRUE | TRUE | 10.75 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144936 | HCFWB3Z2014 | B3 Z2 :Plaster Second Layer | 26196 | 2013-02-11 10:00 | 2013-02-20 10:00 | 9 | 584 | 100 | 100 | 0 | 13014 | 13014 | 13014 | 15057.1919 | 1 | 0.8643 | TRUE | FALSE | FALSE | 73 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144937 | HCFWB3Z3002 | B3 Z3 :B3 Z3 :Trawelled smooth Concrete screed | 26177 | 2013-03-20 10:00 | 2013-03-30 10:00 | 10 | 876 | 100 | 90 | -10 | 13300 | 13300 | 11970 | 12941.0585 | 0.9 | 0.92496 | FALSE | FALSE | FALSE | 109.5 | FALSE | 0 | Green | Continue normal monitoring.
144938 | HCFWB3Z3003 | B3 Z3 :B3 Z3 :Sealed Concrete | 26177 | 2013-05-22 08:00 | 2013-06-01 16:00 | 10 | 1336 | 100 | 100 | 0 | 17870 | 17870 | 17870 | 18706.7055 | 1 | 0.95527 | FALSE | FALSE | FALSE | 167 | FALSE | 0 | Green | Continue normal monitoring.
144939 | HCFWB3Z3015 | B3 Z3 :B3 Z3 :Block Works | 26145 | 2012-11-24 08:00 | 2012-12-09 16:00 | 15 | 434 | 100 | 100 | 0 | 21360 | 21360 | 21360 | 24961.3688 | 1 | 0.85572 | TRUE | FALSE | FALSE | 54.25 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144940 | HCFWB3Z3009 | B3 Z3 :B3 Z3 :Plaster First Layer | 26145 | 2013-01-31 12:00 | 2013-02-11 10:00 | 10 | 86 | 100 | 100 | 0 | 5540 | 5540 | 5540 | 5224.3116 | 1 | 1.0604 | FALSE | FALSE | FALSE | 10.75 | FALSE | 0 | Green | Continue normal monitoring.
144941 | HCFWB3Z3001 | B3 Z3 :B3 Z3 :Foam Concrete & Proofing Membrane Under Floorings | 26177 | 2013-03-02 10:00 | 2013-03-20 10:00 | 18 | 876 | 100 | 100 | 0 | 23382 | 23382 | 23382 | 21988.7433 | 1 | 1.0634 | FALSE | FALSE | FALSE | 109.5 | FALSE | 0 | Green | Continue normal monitoring.
144942 | HCFWB3Z3011 | B3 Z3 :B3 Z3 :Plaster Final Layer | 26145 | 2013-02-20 10:00 | 2013-03-02 10:00 | 10 | 242 | 100 | 100 | 0 | 12770 | 12770 | 12770 | 13669.2683 | 1 | 0.93421 | FALSE | FALSE | FALSE | 30.25 | FALSE | 0 | Green | Continue normal monitoring.
144943 | HCFWB3Z3012 | B3 Z3 :B3 Z3 :Paint First Layer | 26145 | 2013-03-02 10:00 | 2013-03-16 10:00 | 14 | 1302 | 100 | 100 | 0 | 27734 | 27734 | 27734 | 29382.1049 | 1 | 0.94391 | FALSE | FALSE | FALSE | 162.75 | FALSE | 0 | Green | Continue normal monitoring.
144944 | HCFWB3Z3013 | B3 Z3 :B3 Z3 :Paint Final Layer | 26145 | 2013-03-16 10:00 | 2013-03-30 10:00 | 14 | 1302 | 100 | 88 | -12 | 9254 | 9254 | 8143.52 | 8910.7228 | 0.88 | 0.9139 | FALSE | TRUE | TRUE | 162.75 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144945 | HCFWB3Z3004 | B3 Z3 :B3 Z3 :Epoxy Screed Finish Works | 26177 | 2013-05-22 08:00 | 2013-06-03 16:00 | 12 | 1336 | 100 | 100 | 0 | 22836 | 22836 | 22836 | 22133.3422 | 1 | 1.0317 | FALSE | FALSE | FALSE | 167 | FALSE | 0 | Green | Continue normal monitoring.
144946 | HCFWB3Z3016 | B3 Z3 :B3 Z3 :Plaster First Layer | 26220 | 2013-03-30 10:00 | 2013-04-08 16:00 | 9 | 876 | 100 | 82 | -18 | 5274 | 5274 | 4324.68 | 5069.0422 | 0.82 | 0.85316 | TRUE | TRUE | TRUE | 109.5 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144947 | HCFWB3Z3018 | B3 Z3 :B3 Z3 :Plaster Final Layer | 26220 | 2013-04-18 08:00 | 2013-04-27 16:00 | 9 | 876 | 100 | 98 | -2 | 4986 | 4986 | 4886.28 | 5776.8037 | 0.98 | 0.84584 | TRUE | FALSE | FALSE | 109.5 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144948 | HCFWB3Z3019 | B3 Z3 :B3 Z3 :Paint First Layer | 26220 | 2013-04-28 08:00 | 2013-05-09 16:00 | 11 | 1336 | 100 | 100 | 0 | 21989 | 21989 | 21989 | 24424.5093 | 1 | 0.90028 | FALSE | FALSE | FALSE | 167 | FALSE | 0 | Green | Continue normal monitoring.
144949 | HCFWB3Z3020 | B3 Z3 :B3 Z3 :Paint Final Layer | 26220 | 2013-05-11 08:00 | 2013-05-21 16:00 | 10 | 1336 | 100 | 87 | -13 | 17010 | 17010 | 14798.7 | 20122.2665 | 0.87 | 0.73544 | TRUE | TRUE | TRUE | 167 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144950 | HCFWB3Z3025 | B3 Z3 :B3 Z3 :Steel Fire Rated Doors | 26202 | 2013-09-04 08:00 | 2013-09-15 16:00 | 11 | 760 | 100 | 84 | -16 | 21054 | 21054 | 17685.36 | 26110.9437 | 0.84 | 0.67732 | TRUE | TRUE | TRUE | 95 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144951 | HCFWB3Z3005 | B3 Z3 :B3 Z3 :Rubber Flooring With Spicial Adhesive | 26177 | 2013-05-22 08:00 | 2013-06-03 16:00 | 12 | 1336 | 100 | 83 | -17 | 22464 | 22464 | 18645.12 | 23355.0507 | 0.83 | 0.79833 | TRUE | TRUE | TRUE | 167 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144952 | HCFWB3Z3006 | B3 Z3 :B3 Z3 :Rubber Skirting | 26177 | 2013-11-25 08:00 | 2013-11-26 16:00 | 1 | 208 | 100 | 100 | 0 | 1531 | 1531 | 1531 | 1342.1933 | 1 | 1.1407 | FALSE | FALSE | FALSE | 26 | FALSE | 0 | Green | Continue normal monitoring.
144953 | HCFWB3Z3023 | B3 Z3 :B3 Z3 :Steel Doors | 26202 | 2013-10-20 08:00 | 2013-10-30 16:00 | 10 | 480 | 100 | 100 | 0 | 13320 | 13320 | 13320 | 11578.2358 | 1 | 1.1504 | FALSE | FALSE | FALSE | 60 | FALSE | 0 | Green | Continue normal monitoring.
144954 | HCFWB3Z3024 | B3 Z3 :B3 Z3 :Wooden Doors | 26202 | 2013-10-20 08:00 | 2013-10-30 16:00 | 10 | 480 | 100 | 85 | -15 | 8120 | 8120 | 6902 | 7862.32 | 0.85 | 0.87786 | TRUE | TRUE | TRUE | 60 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144955 | HCFWB3Z3021 | B3 Z3 :B3 Z3 :Gybsum Board Ceiling | 26220 | 2013-10-23 08:00 | 2013-11-09 16:00 | 17 | 328 | 100 | 81 | -19 | 21386 | 21386 | 17322.66 | 26155.4594 | 0.81 | 0.6623 | TRUE | TRUE | TRUE | 41 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144956 | HCFWB3Z3022 | B3 Z3 :B3 Z3 :Metal Works & Gutters | 26202 | 2013-10-20 08:00 | 2013-10-30 16:00 | 10 | 440 | 100 | 99 | -1 | 9420 | 9420 | 9325.8 | 9978.4668 | 0.99 | 0.93459 | FALSE | FALSE | FALSE | 55 | FALSE | 0 | Green | Continue normal monitoring.
144957 | HCFWB3Z3026 | B3 Z3 :B3 Z3 :Handrails & Railling | 26202 | 2013-10-20 08:00 | 2013-11-06 16:00 | 17 | 360 | 100 | 100 | 0 | 14059 | 14059 | 14059 | 13478.5687 | 1 | 1.0431 | FALSE | FALSE | FALSE | 45 | FALSE | 0 | Green | Continue normal monitoring.
144958 | HCFWB3Z3010 | B3 Z3 :B3 Z3 :Plaster Second Layer | 26145 | 2013-02-11 10:00 | 2013-02-20 10:00 | 9 | 242 | 100 | 90 | -10 | 14193 | 14193 | 12773.7 | 14330.1997 | 0.9 | 0.89138 | TRUE | FALSE | FALSE | 30.25 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144959 | HCFWB3Z3017 | B3 Z3 :B3 Z3 :Plaster Second Layer | 26220 | 2013-04-09 08:00 | 2013-04-17 16:00 | 8 | 876 | 100 | 83 | -17 | 10080 | 10080 | 8366.4 | 10981.5355 | 0.83 | 0.76186 | TRUE | TRUE | TRUE | 109.5 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144960 | HCFWB3Z3007 | B3 Z3 :B3 Z3 :Stone Flooring | 26177 | 2013-05-22 08:00 | 2013-06-05 16:00 | 14 | 1440 | 100 | 94 | -6 | 24668 | 24668 | 23187.92 | 27410.5849 | 0.94 | 0.84595 | TRUE | FALSE | FALSE | 180 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144961 | HCFWB3Z3008 | B3 Z3 :B3 Z3 :Stone Skirting | 26177 | 2013-06-06 08:00 | 2013-06-17 16:00 | 11 | 2312 | 100 | 85 | -15 | 19272 | 19272 | 16381.2 | 17567.7347 | 0.85 | 0.93246 | FALSE | TRUE | TRUE | 289 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144962 | HCFWB3Z3014 | B3 Z3 :B3 Z3 :Epoxy Paint for Walls | 26145 | 2013-03-02 10:00 | 2013-03-13 10:00 | 11 | 1398 | 100 | 100 | 0 | 11858 | 11858 | 11858 | 14713.5566 | 1 | 0.80592 | TRUE | FALSE | FALSE | 174.75 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144963 | HCFWB3Z4002 | B3 Z4 :Trawelled smooth Concrete screed | 26182 | 2013-03-21 08:00 | 2013-03-30 16:00 | 9 | 86 | 100 | 96 | -4 | 14166 | 14166 | 13599.36 | 15127.9973 | 0.96 | 0.89895 | TRUE | FALSE | FALSE | 10.75 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144964 | HCFWB3Z4003 | B3 Z4 :Sealed Concrete | 26182 | 2013-05-08 10:00 | 2013-05-18 10:00 | 10 | 1006 | 100 | 100 | 0 | 15060 | 15060 | 15060 | 13618.3864 | 1 | 1.1059 | FALSE | FALSE | FALSE | 125.75 | FALSE | 0 | Green | Continue normal monitoring.
144965 | HCFWB3Z4012 | B3 Z4 :Block Works | 26146 | 2012-12-26 08:00 | 2013-01-07 16:00 | 12 | 242 | 100 | 100 | 0 | 21444 | 21444 | 21444 | 25892.6457 | 1 | 0.82819 | TRUE | FALSE | FALSE | 30.25 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144966 | HCFWB3Z4007 | B3 Z4 :Plaster First Layer | 26146 | 2013-01-31 12:00 | 2013-02-11 10:00 | 10 | 86 | 100 | 85 | -15 | 19410 | 19410 | 16498.5 | 17077.9928 | 0.85 | 0.96607 | FALSE | TRUE | TRUE | 10.75 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144967 | HCFWB3Z4001 | B3 Z4 :Foam Concrete & Proofing Membrane Under Floorings | 26182 | 2013-03-03 08:00 | 2013-03-20 16:00 | 17 | 86 | 100 | 98 | -2 | 10115 | 10115 | 9912.7 | 12270.4476 | 0.98 | 0.80785 | TRUE | FALSE | FALSE | 10.75 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144968 | HCFWB3Z4009 | B3 Z4 :Plaster Final Layer | 26146 | 2013-02-20 10:00 | 2013-03-02 16:00 | 10 | 86 | 100 | 100 | 0 | 16110 | 16110 | 16110 | 20115.3691 | 1 | 0.80088 | TRUE | FALSE | FALSE | 10.75 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144969 | HCFWB3Z4010 | B3 Z4 :Paint First Layer | 26146 | 2013-03-31 08:00 | 2013-04-08 16:00 | 8 | 312 | 100 | 100 | 0 | 12808 | 12808 | 12808 | 14475.2522 | 1 | 0.88482 | TRUE | FALSE | FALSE | 39 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144970 | HCFWB3Z4011 | B3 Z4 :Paint Final Layer | 26146 | 2013-04-09 08:00 | 2013-04-17 16:00 | 8 | 312 | 100 | 81 | -19 | 14488 | 14488 | 11735.28 | 16779.6957 | 0.81 | 0.69937 | TRUE | TRUE | TRUE | 39 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144971 | HCFWB3Z4005 | B3 Z4 :Epoxy Screed Finish Works | 26182 | 2013-05-08 10:00 | 2013-05-20 10:00 | 12 | 1006 | 100 | 94 | -6 | 19716 | 19716 | 18533.04 | 19418.7051 | 0.94 | 0.95439 | FALSE | FALSE | FALSE | 125.75 | FALSE | 0 | Green | Continue normal monitoring.
144972 | HCFWB3Z4013 | B3 Z4 :Plaster First Layer | 26184 | 2013-03-31 08:00 | 2013-04-09 14:00 | 9 | 86 | 100 | 90 | -10 | 11817 | 11817 | 10635.3 | 14495.0955 | 0.9 | 0.73372 | TRUE | FALSE | FALSE | 10.75 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144973 | HCFWB3Z4015 | B3 Z4 :Plaster Final Layer | 26184 | 2013-04-18 14:00 | 2013-05-08 10:00 | 19 | 86 | 100 | 87 | -13 | 18810 | 18810 | 16364.7 | 19974.0679 | 0.87 | 0.8193 | TRUE | TRUE | TRUE | 10.75 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144974 | HCFWB3Z4016 | B3 Z4 :Paint First Layer | 26184 | 2013-05-08 10:00 | 2013-05-20 10:00 | 12 | 86 | 100 | 100 | 0 | 11412 | 11412 | 11412 | 13043.4068 | 1 | 0.87492 | TRUE | FALSE | FALSE | 10.75 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144975 | HCFWB3Z4017 | B3 Z4 :Paint Final Layer | 26184 | 2013-05-20 10:00 | 2013-06-02 10:00 | 13 | 86 | 100 | 98 | -2 | 8632 | 8632 | 8459.36 | 10527.9591 | 0.98 | 0.80351 | TRUE | FALSE | FALSE | 10.75 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144976 | HCFWB3Z4021 | B3 Z4 :Steel Fire Rated Doors | 26166 | 2013-09-04 08:00 | 2013-09-15 16:00 | 11 | 1064 | 100 | 92 | -8 | 7491 | 7491 | 6891.72 | 9289.3793 | 0.92 | 0.74189 | TRUE | FALSE | FALSE | 133 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144977 | HCFWB3Z4004 | B3 Z4 :Rubber Flooring With Spicial Adhesive | 26182 | 2013-05-08 10:00 | 2013-05-20 10:00 | 12 | 1006 | 100 | 91 | -9 | 11616 | 11616 | 10570.56 | 13745.0007 | 0.91 | 0.76905 | TRUE | FALSE | FALSE | 125.75 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144978 | HCFWB3Z4006 | B3 Z4 :Rubber Skirting | 26182 | 2013-11-27 08:00 | 2013-11-28 16:00 | 1 | 208 | 100 | 84 | -16 | 1409 | 1409 | 1183.56 | 1368.4307 | 0.84 | 0.8649 | TRUE | TRUE | TRUE | 26 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144979 | HCFWB3Z4020 | B3 Z4 :Steel Doors | 26166 | 2013-10-26 08:00 | 2013-11-06 16:00 | 11 | 744 | 100 | 85 | -15 | 13574 | 13574 | 11537.9 | 16785.8664 | 0.85 | 0.68736 | TRUE | TRUE | TRUE | 93 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144980 | HCFWB3Z4022 | B3 Z4 :Wooden Doors | 26166 | 2013-10-26 08:00 | 2013-11-06 16:00 | 11 | 744 | 100 | 100 | 0 | 14542 | 14542 | 14542 | 16014.3457 | 1 | 0.90806 | FALSE | FALSE | FALSE | 93 | FALSE | 0 | Green | Continue normal monitoring.
144981 | HCFWB3Z4018 | B3 Z4 :Gybsum Board Ceiling | 26184 | 2013-10-23 08:00 | 2013-11-09 16:00 | 17 | 744 | 100 | 100 | 0 | 24531 | 24531 | 24531 | 29983.1862 | 1 | 0.81816 | TRUE | FALSE | FALSE | 93 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144982 | HCFWB3Z4019 | B3 Z4 :Metal Works & Gutters | 26166 | 2013-10-26 08:00 | 2013-11-06 16:00 | 11 | 744 | 100 | 83 | -17 | 5566 | 5566 | 4619.78 | 6236.3802 | 0.83 | 0.74078 | TRUE | TRUE | TRUE | 93 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144983 | HCFWB3Z4023 | B3 Z4 :Handrails & Railling | 26166 | 2013-10-20 08:00 | 2013-11-06 16:00 | 17 | 744 | 100 | 98 | -2 | 14093 | 14093 | 13811.14 | 13711.0175 | 0.98 | 1.0073 | FALSE | FALSE | FALSE | 93 | FALSE | 0 | Green | Continue normal monitoring.
144984 | HCFWB3Z4008 | B3 Z4 :Plaster Second Layer | 26146 | 2013-02-11 10:00 | 2013-02-20 10:00 | 9 | 86 | 100 | 99 | -1 | 11466 | 11466 | 11351.34 | 11443.1805 | 0.99 | 0.99197 | FALSE | FALSE | FALSE | 10.75 | FALSE | 0 | Green | Continue normal monitoring.
144985 | HCFWB3Z4014 | B3 Z4 :Plaster Second Layer | 26184 | 2013-04-09 14:00 | 2013-04-18 14:00 | 9 | 86 | 100 | 80 | -20 | 5850 | 5850 | 4680 | 6260.604 | 0.8 | 0.74753 | TRUE | TRUE | TRUE | 10.75 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144986 | HCFWB3Z5002 | B3 Z5 :Trawelled smooth Concrete screed | 26374 | 2013-05-04 08:00 | 2013-05-12 16:00 | 8 | 156 | 100 | 99 | -1 | 12864 | 12864 | 12735.36 | 14999.5004 | 0.99 | 0.84905 | TRUE | FALSE | FALSE | 19.5 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144987 | HCFWB3Z5004 | B3 Z5 :Sealed Concrete | 26374 | 2013-06-12 12:00 | 2013-06-22 12:00 | 10 | 1244 | 100 | 96 | -4 | 6460 | 6460 | 6201.6 | 6312.6669 | 0.96 | 0.98241 | FALSE | FALSE | FALSE | 155.5 | FALSE | 0 | Green | Continue normal monitoring.
144988 | HCFWB3Z5012 | B3 Z5 :Block Works | 26375 | 2012-12-10 08:00 | 2012-12-20 16:00 | 10 | 712 | 100 | 91 | -9 | 19040 | 19040 | 17326.4 | 20599.2326 | 0.91 | 0.84112 | TRUE | FALSE | FALSE | 89 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
144989 | HCFWB3Z5007 | B3 Z5 :Plaster First Layer | 26375 | 2013-03-14 12:00 | 2013-03-25 10:00 | 10 | 156 | 100 | 94 | -6 | 14140 | 14140 | 13291.6 | 13973.855 | 0.94 | 0.95118 | FALSE | FALSE | FALSE | 19.5 | FALSE | 0 | Green | Continue normal monitoring.
144990 | HCFWB3Z5001 | B3 Z5 :Foam Concrete & Proofing Membrane Under Floorings | 26374 | 2013-04-14 08:00 | 2013-05-02 16:00 | 18 | 156 | 100 | 80 | -20 | 32544 | 32544 | 26035.2 | 38281.7598 | 0.8 | 0.68009 | TRUE | TRUE | TRUE | 19.5 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144991 | HCFWB3Z5009 | B3 Z5 :Plaster Final Layer | 26375 | 2013-04-03 10:00 | 2013-04-13 16:00 | 10 | 156 | 100 | 100 | 0 | 11990 | 11990 | 11990 | 12429.9279 | 1 | 0.96461 | FALSE | FALSE | FALSE | 19.5 | FALSE | 0 | Green | Continue normal monitoring.
144992 | HCFWB3Z5010 | B3 Z5 :Paint First Layer | 26375 | 2013-07-15 12:00 | 2013-07-29 12:00 | 14 | 1932 | 100 | 93 | -7 | 8134 | 8134 | 7564.62 | 7163.5254 | 0.93 | 1.056 | FALSE | FALSE | FALSE | 241.5 | FALSE | 0 | Green | Continue normal monitoring.
144993 | HCFWB3Z5011 | B3 Z5 :Paint Final Layer | 26375 | 2013-07-29 12:00 | 2013-08-15 12:00 | 17 | 1932 | 100 | 85 | -15 | 17221 | 17221 | 14637.85 | 15781.6862 | 0.85 | 0.92752 | FALSE | TRUE | TRUE | 241.5 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144994 | HCFWB3Z5003 | B3 Z5 :Epoxy Screed Finish Works | 26374 | 2013-06-12 12:00 | 2013-06-24 12:00 | 12 | 1244 | 100 | 84 | -16 | 15768 | 15768 | 13245.12 | 13788.1994 | 0.84 | 0.96061 | FALSE | TRUE | TRUE | 155.5 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
144995 | HCFWB3Z5013 | B3 Z5 :Plaster First Layer | 26189 | 2013-05-13 08:00 | 2013-05-22 14:00 | 9 | 156 | 100 | 100 | 0 | 10872 | 10872 | 10872 | 11412.5687 | 1 | 0.95263 | FALSE | FALSE | FALSE | 19.5 | FALSE | 0 | Green | Continue normal monitoring.
144996 | HCFWB3Z5015 | B3 Z5 :Plaster Final Layer | 26189 | 2013-06-02 14:00 | 2013-06-12 12:00 | 9 | 156 | 100 | 90 | -10 | 11205 | 11205 | 10084.5 | 10000.8538 | 0.9 | 1.0084 | FALSE | FALSE | FALSE | 19.5 | FALSE | 0 | Green | Continue normal monitoring.
144997 | HCFWB3Z5016 | B3 Z5 :Paint First Layer | 26189 | 2013-06-22 12:00 | 2013-07-03 12:00 | 11 | 1244 | 100 | 100 | 0 | 16742 | 16742 | 16742 | 14995.0725 | 1 | 1.1165 | FALSE | FALSE | FALSE | 155.5 | FALSE | 0 | Green | Continue normal monitoring.
144998 | HCFWB3Z5017 | B3 Z5 :Paint Final Layer | 26189 | 2013-07-03 12:00 | 2013-07-15 12:00 | 12 | 1932 | 100 | 83 | -17 | 22908 | 22908 | 19013.64 | 28094.8134 | 0.83 | 0.67677 | TRUE | TRUE | TRUE | 241.5 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
144999 | HCFWB3Z5020 | B3 Z5 :Steel Fire Rated Doors | 26171 | 2013-09-04 08:00 | 2013-09-15 16:00 | 11 | 1240 | 100 | 92 | -8 | 13266 | 13266 | 12204.72 | 15906.7569 | 0.92 | 0.76727 | TRUE | FALSE | FALSE | 155 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145000 | HCFWB3Z5005 | B3 Z5 :Rubber Flooring With Spicial Adhesive | 26374 | 2013-06-12 12:00 | 2013-06-24 12:00 | 12 | 996 | 100 | 90 | -10 | 11640 | 11640 | 10476 | 11998.9152 | 0.9 | 0.87308 | TRUE | FALSE | FALSE | 124.5 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145001 | HCFWB3Z5006 | B3 Z5 :Rubber Skirting | 26374 | 2013-11-30 08:00 | 2013-12-01 16:00 | 1 | 208 | 100 | 82 | -18 | 1642 | 1642 | 1346.44 | 2043.1769 | 0.82 | 0.65899 | TRUE | TRUE | TRUE | 26 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145002 | HCFWB3Z5019 | B3 Z5 :Steel Doors | 26171 | 2013-11-07 08:00 | 2013-11-18 16:00 | 11 | 840 | 100 | 80 | -20 | 9845 | 9845 | 7876 | 8368.9845 | 0.8 | 0.94109 | FALSE | TRUE | TRUE | 105 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145003 | HCFWB3Z5021 | B3 Z5 :Wooden Doors | 26171 | 2013-11-07 08:00 | 2013-11-18 16:00 | 11 | 1320 | 100 | 85 | -15 | 8360 | 8360 | 7106 | 9159.1473 | 0.85 | 0.77584 | TRUE | TRUE | TRUE | 165 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145004 | HCFWB3Z5018 | B3 Z5 :Metal Works & Gutters | 26171 | 2013-10-26 08:00 | 2013-11-06 16:00 | 11 | 520 | 100 | 97 | -3 | 14344 | 14344 | 13913.68 | 15729.2183 | 0.97 | 0.88458 | TRUE | FALSE | FALSE | 65 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145005 | HCFWB3Z5008 | B3 Z5 :Plaster Second Layer | 26375 | 2013-03-25 10:00 | 2013-04-03 10:00 | 9 | 156 | 100 | 100 | 0 | 12897 | 12897 | 12897 | 13322.3072 | 1 | 0.96808 | FALSE | FALSE | FALSE | 19.5 | FALSE | 0 | Green | Continue normal monitoring.
145006 | HCFWB3Z5014 | B3 Z5 :Plaster Second Layer | 26189 | 2013-05-22 14:00 | 2013-06-02 14:00 | 11 | 156 | 100 | 89 | -11 | 19569 | 19569 | 17416.41 | 19740.8 | 0.89 | 0.88225 | TRUE | TRUE | TRUE | 19.5 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145007 | HCFWB3Z6002 | B3 Z6 :Trawelled smooth Concrete screed | 26136 | 2013-05-04 08:00 | 2013-05-12 16:00 | 8 | 942 | 100 | 84 | -16 | 11232 | 11232 | 9434.88 | 11593.1454 | 0.84 | 0.81383 | TRUE | TRUE | TRUE | 117.75 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145008 | HCFWB3Z6003 | B3 Z6 :Sealed Concrete | 26136 | 2013-06-20 10:00 | 2013-06-30 10:00 | 10 | 942 | 100 | 100 | 0 | 17490 | 17490 | 17490 | 17769.5632 | 1 | 0.98427 | FALSE | FALSE | FALSE | 117.75 | FALSE | 0 | Green | Continue normal monitoring.
145009 | HCFWB3Z6011 | B3 Z6 :Block Works | 26376 | 2012-12-29 08:00 | 2013-01-09 16:00 | 11 | 1370 | 100 | 89 | -11 | 17336 | 17336 | 15429.04 | 19801.127 | 0.89 | 0.7792 | TRUE | TRUE | TRUE | 171.25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145010 | HCFWB3Z6007 | B3 Z6 :Plaster First Layer | 26376 | 2013-03-14 12:00 | 2013-03-25 10:00 | 10 | 942 | 100 | 91 | -9 | 14390 | 14390 | 13094.9 | 13010.6059 | 0.91 | 1.0065 | FALSE | FALSE | FALSE | 117.75 | FALSE | 0 | Green | Continue normal monitoring.
145011 | HCFWB3Z6001 | B3 Z6 :Foam Concrete & Proofing Membrane Under Floorings | 26136 | 2013-04-14 08:00 | 2013-05-02 16:00 | 18 | 942 | 100 | 81 | -19 | 24354 | 24354 | 19726.74 | 22626.2222 | 0.81 | 0.87185 | TRUE | TRUE | TRUE | 117.75 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145012 | HCFWB3Z6009 | B3 Z6 :Plaster Final Layer | 26376 | 2013-04-03 10:00 | 2013-04-13 16:00 | 10 | 942 | 100 | 92 | -8 | 18870 | 18870 | 17360.4 | 17402.0516 | 0.92 | 0.99761 | FALSE | FALSE | FALSE | 117.75 | FALSE | 0 | Green | Continue normal monitoring.
145013 | HCFWB3Z6010 | B3 Z6 :Paint First Layer | 26376 | 2013-06-30 10:00 | 2013-07-14 10:00 | 14 | 2038 | 100 | 87 | -13 | 25242 | 25242 | 21960.54 | 24105.813 | 0.87 | 0.91101 | FALSE | TRUE | TRUE | 254.75 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145014 | HCFWB3Z6012 | B3 Z6 :Paint Final Layer | 26376 | 2013-07-14 10:00 | 2013-07-28 10:00 | 14 | 2038 | 100 | 81 | -19 | 15288 | 15288 | 12383.28 | 16206.8603 | 0.81 | 0.76408 | TRUE | TRUE | TRUE | 254.75 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145015 | HCFWB3Z6004 | B3 Z6 :Epoxy Screed Finish Works | 26136 | 2013-06-20 10:00 | 2013-07-02 10:00 | 12 | 942 | 100 | 99 | -1 | 14556 | 14556 | 14410.44 | 13020.1018 | 0.99 | 1.1068 | FALSE | FALSE | FALSE | 117.75 | FALSE | 0 | Green | Continue normal monitoring.
145016 | HCFWB3Z6013 | B3 Z6 :Plaster First Layer | 26175 | 2013-05-13 08:00 | 2013-05-22 14:00 | 9 | 942 | 100 | 80 | -20 | 15129 | 15129 | 12103.2 | 18113.4633 | 0.8 | 0.66819 | TRUE | TRUE | TRUE | 117.75 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145017 | HCFWB3Z6015 | B3 Z6 :Plaster Final Layer | 26175 | 2013-06-02 14:00 | 2013-06-20 10:00 | 17 | 942 | 100 | 100 | 0 | 19227 | 19227 | 19227 | 18629.8981 | 1 | 1.0321 | FALSE | FALSE | FALSE | 117.75 | FALSE | 0 | Green | Continue normal monitoring.
145018 | HCFWB3Z6016 | B3 Z6 :Paint First Layer | 26175 | 2013-06-30 10:00 | 2013-07-11 10:00 | 11 | 1190 | 100 | 84 | -16 | 6138 | 6138 | 5155.92 | 5616.3633 | 0.84 | 0.91802 | FALSE | TRUE | TRUE | 148.75 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145019 | HCFWB3Z6017 | B3 Z6 :Paint Final Layer | 26175 | 2013-07-11 10:00 | 2013-07-23 10:00 | 12 | 1990 | 100 | 88 | -12 | 7524 | 7524 | 6621.12 | 8428.7499 | 0.88 | 0.78554 | TRUE | TRUE | TRUE | 248.75 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145020 | HCFWB3Z6020 | B3 Z6 :Steel Fire Rated Doors | 26176 | 2013-09-04 08:00 | 2013-09-15 16:00 | 11 | 920 | 100 | 96 | -4 | 13585 | 13585 | 13041.6 | 11754.211 | 0.96 | 1.1095 | FALSE | FALSE | FALSE | 115 | FALSE | 0 | Green | Continue normal monitoring.
145021 | HCFWB3Z6005 | B3 Z6 :Rubber Flooring With Spicial Adhesive | 26136 | 2013-06-20 10:00 | 2013-07-02 10:00 | 12 | 942 | 100 | 88 | -12 | 14640 | 14640 | 12883.2 | 16074.5359 | 0.88 | 0.80147 | TRUE | TRUE | TRUE | 117.75 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145022 | HCFWB3Z6006 | B3 Z6 :Rubber Skirting | 26136 | 2013-12-02 08:00 | 2013-12-03 16:00 | 1 | 208 | 100 | 90 | -10 | 1638 | 1638 | 1474.2 | 1849.7596 | 0.9 | 0.79697 | TRUE | FALSE | FALSE | 26 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145023 | HCFWB3Z6019 | B3 Z6 :Steel Doors | 26176 | 2013-10-26 08:00 | 2013-11-06 16:00 | 11 | 600 | 100 | 94 | -6 | 19052 | 19052 | 17908.88 | 17832.0359 | 0.94 | 1.0043 | FALSE | FALSE | FALSE | 75 | FALSE | 0 | Green | Continue normal monitoring.
145024 | HCFWB3Z6021 | B3 Z6 :Wooden Doors | 26176 | 2013-10-26 08:00 | 2013-11-06 16:00 | 11 | 1400 | 100 | 100 | 0 | 11275 | 11275 | 11275 | 9773.008 | 1 | 1.1537 | FALSE | FALSE | FALSE | 175 | FALSE | 0 | Green | Continue normal monitoring.
145025 | HCFWB3Z6018 | B3 Z6 :Metal Works & Gutters | 26176 | 2013-10-26 08:00 | 2013-11-06 16:00 | 11 | 520 | 100 | 85 | -15 | 11220 | 11220 | 9537 | 11169.0404 | 0.85 | 0.85388 | TRUE | TRUE | TRUE | 65 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145026 | HCFWB3Z6008 | B3 Z6 :Plaster Second Layer | 26376 | 2013-03-25 10:00 | 2013-04-03 10:00 | 9 | 942 | 100 | 100 | 0 | 9459 | 9459 | 9459 | 8413.1911 | 1 | 1.1243 | FALSE | FALSE | FALSE | 117.75 | FALSE | 0 | Green | Continue normal monitoring.
145027 | HCFWB3Z6014 | B3 Z6 :Plaster Second Layer | 26175 | 2013-05-22 14:00 | 2013-06-02 14:00 | 11 | 942 | 100 | 82 | -18 | 8096 | 8096 | 6638.72 | 7258.8019 | 0.82 | 0.91458 | FALSE | TRUE | TRUE | 117.75 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145028 | HCFWB1Z1007 | B1 Z1 :Plaster Second Layer | 26249 | 2013-02-25 14:00 | 2013-03-06 14:00 | 9 | 554 | 100 | 100 | 0 | 16236 | 16236 | 16236 | 15451.8741 | 1 | 1.0507 | FALSE | FALSE | FALSE | 69.25 | FALSE | 0 | Green | Continue normal monitoring.
145029 | HCFWB1Z1013 | B1 Z1 :Plaster Second Layer | 26238 | 2013-04-24 10:00 | 2013-05-05 10:00 | 11 | 554 | 100 | 100 | 0 | 20702 | 20702 | 20702 | 20043.4108 | 1 | 1.0329 | FALSE | FALSE | FALSE | 69.25 | FALSE | 0 | Green | Continue normal monitoring.
145030 | HCFWB1Z2002 | B1 Z2 :Trawelled smooth Concrete screed | 26386 | 2013-04-28 12:00 | 2013-05-08 12:00 | 10 | 394 | 100 | 96 | -4 | 17240 | 17240 | 16550.4 | 18308.6755 | 0.96 | 0.90396 | FALSE | FALSE | FALSE | 49.25 | FALSE | 0 | Green | Continue normal monitoring.
145031 | HCFWB1Z2003 | B1 Z2 :Sealed Concrete | 26386 | 2013-06-16 14:00 | 2013-06-25 14:00 | 9 | 930 | 100 | 84 | -16 | 16209 | 16209 | 13615.56 | 18176.0716 | 0.84 | 0.74909 | TRUE | TRUE | TRUE | 116.25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145032 | HCFWB1Z2001 | B1 Z2 :Foam Concrete Under Floorings | 26386 | 2013-04-09 12:00 | 2013-04-28 12:00 | 19 | 394 | 100 | 100 | 0 | 33402 | 33402 | 33402 | 36311.594 | 1 | 0.91987 | FALSE | FALSE | FALSE | 49.25 | FALSE | 0 | Green | Continue normal monitoring.
145033 | HCFWB1Z2004 | B1 Z2 :Rubber Flooring | 26386 | 2013-06-16 14:00 | 2013-06-27 14:00 | 11 | 394 | 100 | 100 | 0 | 10923 | 10923 | 10923 | 9932.766 | 1 | 1.0997 | FALSE | FALSE | FALSE | 49.25 | FALSE | 0 | Green | Continue normal monitoring.
145034 | HCFWB1Z2005 | B1 Z2 :Rubber Skirting | 26386 | 2013-12-21 08:00 | 2013-12-22 16:00 | 1 | 208 | 100 | 91 | -9 | 503 | 503 | 457.73 | 462.1737 | 0.91 | 0.99039 | FALSE | FALSE | FALSE | 26 | FALSE | 0 | Green | Continue normal monitoring.
145035 | HCFWB1Z2011 | B1 Z2 :Block Works | 26234 | 2013-02-21 08:00 | 2013-03-04 16:00 | 11 | 434 | 100 | 97 | -3 | 12815 | 12815 | 12430.55 | 15397.3212 | 0.97 | 0.80732 | TRUE | FALSE | FALSE | 54.25 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145036 | HCFWB1Z2006 | B1 Z2 :Plaster First Layer | 26234 | 2013-03-11 08:00 | 2013-03-20 14:00 | 9 | 394 | 100 | 93 | -7 | 8469 | 8469 | 7876.17 | 9090.1243 | 0.93 | 0.86645 | TRUE | FALSE | FALSE | 49.25 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145037 | HCFWB1Z2008 | B1 Z2 :Plaster Final Layer | 26234 | 2013-03-30 14:00 | 2013-04-09 12:00 | 9 | 394 | 100 | 100 | 0 | 4752 | 4752 | 4752 | 5692.7778 | 1 | 0.83474 | TRUE | FALSE | FALSE | 49.25 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145038 | HCFWB1Z2009 | B1 Z2 :Paint First Layer | 26234 | 2013-06-25 14:00 | 2013-07-09 14:00 | 14 | 930 | 100 | 100 | 0 | 22848 | 22848 | 22848 | 22816.4379 | 1 | 1.0014 | FALSE | FALSE | FALSE | 116.25 | FALSE | 0 | Green | Continue normal monitoring.
145039 | HCFWB1Z2010 | B1 Z2 :Paint Final Layer | 26234 | 2013-07-09 14:00 | 2013-07-23 14:00 | 14 | 930 | 100 | 90 | -10 | 15526 | 15526 | 13973.4 | 17012.7698 | 0.9 | 0.82135 | TRUE | FALSE | FALSE | 116.25 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145040 | HCFWB1Z2007 | B1 Z2 :Plaster Second Layer | 26234 | 2013-03-20 14:00 | 2013-03-30 14:00 | 10 | 394 | 100 | 88 | -12 | 13040 | 13040 | 11475.2 | 13815.4284 | 0.88 | 0.83061 | TRUE | TRUE | TRUE | 49.25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145041 | HCFWB1Z2012 | B1 Z2 :Plaster First Layer | 26239 | 2013-05-08 12:00 | 2013-05-19 10:00 | 10 | 394 | 100 | 81 | -19 | 5740 | 5740 | 4649.4 | 5611.7075 | 0.81 | 0.82852 | TRUE | TRUE | TRUE | 49.25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145042 | HCFWB1Z2014 | B1 Z2 :Plaster Final Layer | 26239 | 2013-05-29 10:00 | 2013-06-16 14:00 | 18 | 394 | 100 | 91 | -9 | 24066 | 24066 | 21900.06 | 24979.6933 | 0.91 | 0.87671 | TRUE | FALSE | FALSE | 49.25 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145043 | HCFWB1Z2015 | B1 Z2 :Paint First Layer | 26239 | 2013-07-23 14:00 | 2013-08-04 14:00 | 12 | 930 | 100 | 82 | -18 | 20028 | 20028 | 16422.96 | 21049.3549 | 0.82 | 0.78021 | TRUE | TRUE | TRUE | 116.25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145044 | HCFWB1Z2016 | B1 Z2 :Paint Final Layer | 26239 | 2013-08-04 14:00 | 2013-08-19 14:00 | 15 | 930 | 100 | 82 | -18 | 9405 | 9405 | 7712.1 | 8749.5504 | 0.82 | 0.88143 | TRUE | TRUE | TRUE | 116.25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145045 | HCFWB1Z2017 | B1 Z2 :Gybsum Board Ceiling | 26239 | 2013-11-26 08:00 | 2013-12-11 16:00 | 15 | 296 | 100 | 80 | -20 | 8115 | 8115 | 6492 | 7920.2737 | 0.8 | 0.81967 | TRUE | TRUE | TRUE | 37 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145046 | HCFWB1Z2013 | B1 Z2 :Plaster Second Layer | 26239 | 2013-05-19 10:00 | 2013-05-29 10:00 | 10 | 394 | 100 | 87 | -13 | 18790 | 18790 | 16347.3 | 21919.7357 | 0.87 | 0.74578 | TRUE | TRUE | TRUE | 49.25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145047 | HCFWB1Z2020 | B1 Z2 :Steel Fire Rated Doors | 26131 | 2013-11-25 08:00 | 2013-12-05 16:00 | 10 | 560 | 100 | 100 | 0 | 5400 | 5400 | 5400 | 6568.1026 | 1 | 0.82216 | TRUE | FALSE | FALSE | 70 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145048 | HCFWB1Z2019 | B1 Z2 :Steel Doors | 26131 | 2014-01-04 08:00 | 2014-01-15 16:00 | 11 | 304 | 100 | 100 | 0 | 15763 | 15763 | 15763 | 15667.1237 | 1 | 1.0061 | FALSE | FALSE | FALSE | 38 | FALSE | 0 | Green | Continue normal monitoring.
145049 | HCFWB1Z2021 | B1 Z2 :Wooden Doors | 26131 | 2014-01-04 08:00 | 2014-01-15 16:00 | 11 | 384 | 100 | 100 | 0 | 5863 | 5863 | 5863 | 5703.4614 | 1 | 1.028 | FALSE | FALSE | FALSE | 48 | FALSE | 0 | Green | Continue normal monitoring.
145050 | HCFWB1Z2018 | B1 Z2 :Metal Works | 26131 | 2013-12-21 08:00 | 2014-01-02 16:00 | 12 | 208 | 100 | 87 | -13 | 18480 | 18480 | 16077.6 | 17150.8974 | 0.87 | 0.93742 | FALSE | TRUE | TRUE | 26 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145051 | HCFWB1Z2022 | B1 Z2 :Handrails & Railling | 26131 | 2013-12-21 08:00 | 2014-01-08 16:00 | 18 | 208 | 100 | 90 | -10 | 30168 | 30168 | 27151.2 | 33830.2886 | 0.9 | 0.80257 | TRUE | FALSE | FALSE | 26 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145052 | HCFWB1Z3002 | B1 Z3 :Trawelled smooth Concrete screed | 26212 | 2013-06-20 08:00 | 2013-06-29 16:00 | 9 | 658 | 100 | 88 | -12 | 13473 | 13473 | 11856.24 | 13193.2989 | 0.88 | 0.89866 | TRUE | TRUE | TRUE | 82.25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145053 | HCFWB1Z3004 | B1 Z3 :Sealed Concrete | 26212 | 2013-07-28 14:00 | 2013-08-06 14:00 | 9 | 658 | 100 | 84 | -16 | 17109 | 17109 | 14371.56 | 21302.4127 | 0.84 | 0.67464 | TRUE | TRUE | TRUE | 82.25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145054 | HCFWB1Z3001 | B1 Z3 :Foam Concrete Under Floorings | 26212 | 2013-06-02 08:00 | 2013-06-19 16:00 | 17 | 658 | 100 | 93 | -7 | 18479 | 18479 | 17185.47 | 18114.4818 | 0.93 | 0.94871 | FALSE | FALSE | FALSE | 82.25 | FALSE | 0 | Green | Continue normal monitoring.
145055 | HCFWB1Z3005 | B1 Z3 :Rubber Flooring | 26212 | 2013-07-28 14:00 | 2013-08-12 14:00 | 15 | 1074 | 100 | 100 | 0 | 12615 | 12615 | 12615 | 12711.5605 | 1 | 0.9924 | FALSE | FALSE | FALSE | 134.25 | FALSE | 0 | Green | Continue normal monitoring.
145056 | HCFWB1Z3009 | B1 Z3 :Rubber Skirting | 26212 | 2013-12-23 08:00 | 2013-12-24 16:00 | 1 | 208 | 100 | 100 | 0 | 526 | 526 | 526 | 574.0415 | 1 | 0.91631 | FALSE | FALSE | FALSE | 26 | FALSE | 0 | Green | Continue normal monitoring.
145057 | HCFWB1Z3013 | B1 Z3 :Block Works | 26219 | 2013-02-21 08:00 | 2013-03-09 16:00 | 16 | 664 | 100 | 82 | -18 | 28960 | 28960 | 23747.2 | 33902.7109 | 0.82 | 0.70045 | TRUE | TRUE | TRUE | 83 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145058 | HCFWB1Z3014 | B1 Z3 :Plaster First Layer | 26219 | 2013-05-02 10:00 | 2013-05-12 16:00 | 10 | 658 | 100 | 100 | 0 | 11450 | 11450 | 11450 | 11882.8955 | 1 | 0.96357 | FALSE | FALSE | FALSE | 82.25 | FALSE | 0 | Green | Continue normal monitoring.
145059 | HCFWB1Z3016 | B1 Z3 :Plaster Final Layer | 26219 | 2013-05-22 08:00 | 2013-06-01 16:00 | 10 | 658 | 100 | 84 | -16 | 12300 | 12300 | 10332 | 12534.4677 | 0.84 | 0.82429 | TRUE | TRUE | TRUE | 82.25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145060 | HCFWB1Z3017 | B1 Z3 :Paint First Layer | 26219 | 2013-08-06 14:00 | 2013-08-24 14:00 | 18 | 658 | 100 | 84 | -16 | 12006 | 12006 | 10085.04 | 14986.5511 | 0.84 | 0.67294 | TRUE | TRUE | TRUE | 82.25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145061 | HCFWB1Z3018 | B1 Z3 :Paint Final Layer | 26219 | 2013-08-24 14:00 | 2013-09-07 14:00 | 14 | 658 | 100 | 98 | -2 | 15526 | 15526 | 15215.48 | 13262.2697 | 0.98 | 1.1473 | FALSE | FALSE | FALSE | 82.25 | FALSE | 0 | Green | Continue normal monitoring.
145062 | HCFWB1Z3015 | B1 Z3 :Plaster Second Layer | 26219 | 2013-05-13 08:00 | 2013-05-21 16:00 | 8 | 658 | 100 | 100 | 0 | 6136 | 6136 | 6136 | 7412.4482 | 1 | 0.8278 | TRUE | FALSE | FALSE | 82.25 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145063 | HCFWB1Z3023 | B1 Z3 :Plaster First Layer | 26377 | 2013-06-30 08:00 | 2013-07-09 14:00 | 9 | 658 | 100 | 93 | -7 | 11880 | 11880 | 11048.4 | 10806.7172 | 0.93 | 1.0224 | FALSE | FALSE | FALSE | 82.25 | FALSE | 0 | Green | Continue normal monitoring.
145064 | HCFWB1Z3025 | B1 Z3 :Plaster Final Layer | 26377 | 2013-07-18 14:00 | 2013-07-28 14:00 | 10 | 658 | 100 | 100 | 0 | 9540 | 9540 | 9540 | 11108.0909 | 1 | 0.85883 | TRUE | FALSE | FALSE | 82.25 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145065 | HCFWB1Z3026 | B1 Z3 :Paint First Layer | 26377 | 2013-09-07 14:00 | 2013-09-18 14:00 | 11 | 674 | 100 | 100 | 0 | 15455 | 15455 | 15455 | 16956.8029 | 1 | 0.91143 | FALSE | FALSE | FALSE | 84.25 | FALSE | 0 | Green | Continue normal monitoring.
145066 | HCFWB1Z3027 | B1 Z3 :Paint Final Layer | 26377 | 2013-09-18 14:00 | 2013-09-30 14:00 | 12 | 674 | 100 | 83 | -17 | 23088 | 23088 | 19163.04 | 22781.8281 | 0.83 | 0.84115 | TRUE | TRUE | TRUE | 84.25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145067 | HCFWB1Z3028 | B1 Z3 :Gybsum Board Ceiling | 26377 | 2013-11-26 08:00 | 2013-12-11 16:00 | 15 | 328 | 100 | 100 | 0 | 21315 | 21315 | 21315 | 25568.4079 | 1 | 0.83365 | TRUE | FALSE | FALSE | 41 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145068 | HCFWB1Z3024 | B1 Z3 :Plaster Second Layer | 26377 | 2013-07-09 14:00 | 2013-07-18 14:00 | 9 | 658 | 100 | 92 | -8 | 13320 | 13320 | 12254.4 | 11390.7697 | 0.92 | 1.0758 | FALSE | FALSE | FALSE | 82.25 | FALSE | 0 | Green | Continue normal monitoring.
145069 | HCFWB1Z3032 | B1 Z3 :Steel Fire Rated Doors | 26215 | 2013-09-28 08:00 | 2013-10-08 16:00 | 10 | 920 | 100 | 89 | -11 | 19990 | 19990 | 17791.1 | 18804.1185 | 0.89 | 0.94613 | FALSE | TRUE | TRUE | 115 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145070 | HCFWB1Z3031 | B1 Z3 :Steel Doors | 26215 | 2013-12-01 08:00 | 2013-12-11 16:00 | 10 | 520 | 100 | 100 | 0 | 12010 | 12010 | 12010 | 12931.853 | 1 | 0.92871 | FALSE | FALSE | FALSE | 65 | FALSE | 0 | Green | Continue normal monitoring.
145071 | HCFWB1Z3033 | B1 Z3 :Wooden Doors | 26215 | 2014-01-19 08:00 | 2014-01-29 16:00 | 10 | 208 | 100 | 97 | -3 | 11330 | 11330 | 10990.1 | 11223.6895 | 0.97 | 0.97919 | FALSE | FALSE | FALSE | 26 | FALSE | 0 | Green | Continue normal monitoring.
145072 | HCFWB1Z3030 | B1 Z3 :Metal Works | 26215 | 2013-11-19 08:00 | 2013-11-30 16:00 | 11 | 400 | 100 | 87 | -13 | 6919 | 6919 | 6019.53 | 7570.4308 | 0.87 | 0.79514 | TRUE | TRUE | TRUE | 50 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145073 | HCFWB1Z3034 | B1 Z3 :Handrails & Railling | 26215 | 2013-11-25 08:00 | 2013-12-11 16:00 | 16 | 360 | 100 | 87 | -13 | 24304 | 24304 | 21144.48 | 20892.7897 | 0.87 | 1.012 | FALSE | TRUE | TRUE | 45 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145074 | HCFWB1Z3008 | B1 Z3 :Epoxy Screed Finish | 26212 | 2013-06-30 08:00 | 2013-07-10 16:00 | 10 | 1832 | 100 | 86 | -14 | 18860 | 18860 | 16219.6 | 16909.5662 | 0.86 | 0.9592 | FALSE | TRUE | TRUE | 229 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145075 | HCFWB1Z3019 | B1 Z3 :Epoxy Wall Paint | 26219 | 2013-08-24 14:00 | 2013-09-04 14:00 | 11 | 1474 | 100 | 87 | -13 | 14498 | 14498 | 12613.26 | 13060.3565 | 0.87 | 0.96577 | FALSE | TRUE | TRUE | 184.25 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145076 | HCFWB1Z3007 | B1 Z3 :Stone Flooring All types | 26212 | 2013-07-28 14:00 | 2013-08-14 14:00 | 17 | 1138 | 100 | 93 | -7 | 20264 | 20264 | 18845.52 | 18758.6575 | 0.93 | 1.0046 | FALSE | FALSE | FALSE | 142.25 | FALSE | 0 | Green | Continue normal monitoring.
145077 | HCFWB1Z3010 | B1 Z3 :Aluminum & Stainless Steel Skirting | 26212 | 2013-12-23 08:00 | 2014-01-05 16:00 | 13 | 688 | 100 | 98 | -2 | 23595 | 23595 | 23123.1 | 24390.9201 | 0.98 | 0.94802 | FALSE | FALSE | FALSE | 86 | FALSE | 0 | Green | Continue normal monitoring.
145078 | HCFWB1Z3020 | B1 Z3 :Stainless steel Wire Cloth Finish For Elev Lobby | 26219 | 2013-08-24 14:00 | 2013-09-04 14:00 | 11 | 1074 | 100 | 100 | 0 | 20834 | 20834 | 20834 | 23976.8397 | 1 | 0.86892 | TRUE | FALSE | FALSE | 134.25 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145079 | HCFWB1Z3035 | B1 Z3 :Stone Decoration For Benches | 26215 | 2013-11-25 08:00 | 2013-12-05 16:00 | 10 | 880 | 100 | 85 | -15 | 12930 | 12930 | 10990.5 | 15673.9469 | 0.85 | 0.7012 | TRUE | TRUE | TRUE | 110 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145080 | HCFWB1Z3021 | B1 Z3 :Glass Wall Tile & Laminated Taupe | 26219 | 2013-08-24 14:00 | 2013-09-04 14:00 | 11 | 1074 | 100 | 80 | -20 | 5808 | 5808 | 4646.4 | 6877.5375 | 0.8 | 0.67559 | TRUE | TRUE | TRUE | 134.25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145081 | HCFWB1Z3036 | B1 Z3 :Mirror | 26215 | 2013-11-25 08:00 | 2013-12-05 16:00 | 10 | 880 | 100 | 100 | 0 | 6480 | 6480 | 6480 | 6018.3334 | 1 | 1.0767 | FALSE | FALSE | FALSE | 110 | FALSE | 0 | Green | Continue normal monitoring.
145082 | HCFWB1Z3037 | B1 Z3 :Toilet & corian vanity tops | 26215 | 2013-11-25 08:00 | 2013-12-05 16:00 | 10 | 880 | 100 | 100 | 0 | 18190 | 18190 | 18190 | 18671.3114 | 1 | 0.97422 | FALSE | FALSE | FALSE | 110 | FALSE | 0 | Green | Continue normal monitoring.
145083 | HCFWB1Z3006 | B1 Z3 :Carpet Tile Flooring | 26212 | 2013-12-05 08:00 | 2013-12-16 16:00 | 11 | 808 | 100 | 94 | -6 | 5610 | 5610 | 5273.4 | 5215.9796 | 0.94 | 1.011 | FALSE | FALSE | FALSE | 101 | FALSE | 0 | Green | Continue normal monitoring.
145084 | HCFWB1Z3011 | B1 Z3 :Wooden Base Skirting | 26212 | 2013-12-23 08:00 | 2014-01-05 16:00 | 13 | 208 | 100 | 80 | -20 | 15275 | 15275 | 12220 | 14599.6728 | 0.8 | 0.83701 | TRUE | TRUE | TRUE | 26 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145085 | HCFWB1Z3022 | B1 Z3 :Wooden Wall Covering | 26219 | 2014-01-06 08:00 | 2014-01-18 16:00 | 12 | 208 | 100 | 100 | 0 | 19632 | 19632 | 19632 | 20641.4537 | 1 | 0.9511 | FALSE | FALSE | FALSE | 26 | FALSE | 0 | Green | Continue normal monitoring.
145086 | HCFWB1Z3029 | B1 Z3 :Acoustical Ceiling | 26377 | 2013-09-18 14:00 | 2013-09-30 14:00 | 12 | 754 | 100 | 96 | -4 | 8232 | 8232 | 7902.72 | 7221.4694 | 0.96 | 1.0943 | FALSE | FALSE | FALSE | 94.25 | FALSE | 0 | Green | Continue normal monitoring.
145087 | HCFWB1Z3012 | B1 Z3 :Stone Base Skirting | 26212 | 2013-12-23 08:00 | 2014-01-05 16:00 | 13 | 688 | 100 | 80 | -20 | 16978 | 16978 | 13582.4 | 15912.9655 | 0.8 | 0.85354 | TRUE | TRUE | TRUE | 86 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145088 | HCFWB1Z4002 | B1 Z4 :Trawelled smooth Concrete screed | 26181 | 2013-08-29 14:00 | 2013-09-08 14:00 | 10 | 312 | 100 | 94 | -6 | 12430 | 12430 | 11684.2 | 15216.2002 | 0.94 | 0.76788 | TRUE | FALSE | FALSE | 39 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145089 | HCFWB1Z4003 | B1 Z4 :Sealed Concrete | 26181 | 2013-10-21 08:00 | 2013-10-29 16:00 | 8 | 664 | 100 | 100 | 0 | 14000 | 14000 | 14000 | 14510.2512 | 1 | 0.96484 | FALSE | FALSE | FALSE | 83 | FALSE | 0 | Green | Continue normal monitoring.
145090 | HCFWB1Z4001 | B1 Z4 :Foam Concrete Under Floorings | 26181 | 2013-08-07 14:00 | 2013-08-29 14:00 | 22 | 312 | 100 | 81 | -19 | 40326 | 40326 | 32664.06 | 41461.3628 | 0.81 | 0.78782 | TRUE | TRUE | TRUE | 39 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145091 | HCFWB1Z4004 | B1 Z4 :Rubber Flooring | 26181 | 2013-10-21 08:00 | 2013-10-31 16:00 | 10 | 312 | 100 | 93 | -7 | 5970 | 5970 | 5552.1 | 5109.2864 | 0.93 | 1.0867 | FALSE | FALSE | FALSE | 39 | FALSE | 0 | Green | Continue normal monitoring.
145092 | HCFWB1Z4007 | B1 Z4 :Rubber Skirting | 26181 | 2013-12-26 08:00 | 2013-12-28 16:00 | 2 | 496 | 100 | 100 | 0 | 1108 | 1108 | 1108 | 1051.4476 | 1 | 1.0538 | FALSE | FALSE | FALSE | 62 | FALSE | 0 | Green | Continue normal monitoring.
145093 | HCFWB1Z4008 | B1 Z4 :Block Works | 26217 | 2013-03-16 08:00 | 2013-03-26 16:00 | 10 | 1010 | 100 | 87 | -13 | 11220 | 11220 | 9761.4 | 13424.9205 | 0.87 | 0.72711 | TRUE | TRUE | TRUE | 126.25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145094 | HCFWB1Z4009 | B1 Z4 :Plaster First Layer | 26217 | 2013-07-09 10:00 | 2013-07-18 16:00 | 9 | 312 | 100 | 87 | -13 | 10467 | 10467 | 9106.29 | 9586.2163 | 0.87 | 0.94994 | FALSE | TRUE | TRUE | 39 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145095 | HCFWB1Z4011 | B1 Z4 :Plaster Final Layer | 26217 | 2013-07-29 08:00 | 2013-08-07 14:00 | 9 | 312 | 100 | 98 | -2 | 11313 | 11313 | 11086.74 | 11494.5734 | 0.98 | 0.96452 | FALSE | FALSE | FALSE | 39 | FALSE | 0 | Green | Continue normal monitoring.
145096 | HCFWB1Z4012 | B1 Z4 :Paint First Layer | 26217 | 2013-10-30 08:00 | 2013-11-13 16:00 | 14 | 664 | 100 | 86 | -14 | 12670 | 12670 | 10896.2 | 10842.129 | 0.86 | 1.005 | FALSE | TRUE | TRUE | 83 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145097 | HCFWB1Z4013 | B1 Z4 :Paint Final Layer | 26217 | 2014-01-21 08:00 | 2014-02-03 16:00 | 13 | 496 | 100 | 98 | -2 | 7384 | 7384 | 7236.32 | 7689.2117 | 0.98 | 0.9411 | FALSE | FALSE | FALSE | 62 | FALSE | 0 | Green | Continue normal monitoring.
145098 | HCFWB1Z4010 | B1 Z4 :Plaster Second Layer | 26217 | 2013-07-20 08:00 | 2013-07-28 16:00 | 8 | 312 | 100 | 85 | -15 | 14680 | 14680 | 12478 | 12601.4359 | 0.85 | 0.9902 | FALSE | TRUE | TRUE | 39 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145099 | HCFWB1Z4016 | B1 Z4 :Plaster First Layer | 26183 | 2013-09-08 14:00 | 2013-09-18 12:00 | 9 | 312 | 100 | 85 | -15 | 16308 | 16308 | 13861.8 | 19208.277 | 0.85 | 0.72166 | TRUE | TRUE | TRUE | 39 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145100 | HCFWB1Z4018 | B1 Z4 :Plaster Final Layer | 26183 | 2013-09-28 12:00 | 2013-10-20 16:00 | 22 | 312 | 100 | 82 | -18 | 27500 | 27500 | 22550 | 32448.3914 | 0.82 | 0.69495 | TRUE | TRUE | TRUE | 39 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145101 | HCFWB1Z4019 | B1 Z4 :Paint First Layer | 26183 | 2013-11-14 08:00 | 2013-11-25 16:00 | 11 | 664 | 100 | 86 | -14 | 18381 | 18381 | 15807.66 | 21415.6457 | 0.86 | 0.73814 | TRUE | TRUE | TRUE | 83 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145102 | HCFWB1Z4020 | B1 Z4 :Paint Final Layer | 26183 | 2013-11-26 08:00 | 2013-12-07 16:00 | 11 | 664 | 100 | 98 | -2 | 21890 | 21890 | 21452.2 | 21087.6358 | 0.98 | 1.0173 | FALSE | FALSE | FALSE | 83 | FALSE | 0 | Green | Continue normal monitoring.
145103 | HCFWB1Z4021 | B1 Z4 :Gybsum Board Ceiling | 26183 | 2013-12-19 08:00 | 2014-01-06 16:00 | 18 | 584 | 100 | 87 | -13 | 31806 | 31806 | 27671.22 | 37686.7668 | 0.87 | 0.73424 | TRUE | TRUE | TRUE | 73 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145104 | HCFWB1Z4017 | B1 Z4 :Plaster Second Layer | 26183 | 2013-09-18 12:00 | 2013-09-28 12:00 | 10 | 312 | 100 | 89 | -11 | 14570 | 14570 | 12967.3 | 15549.0931 | 0.89 | 0.83396 | TRUE | TRUE | TRUE | 39 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145105 | HCFWB1Z4025 | B1 Z4 :Steel Fire Rated Doors | 26378 | 2013-11-26 08:00 | 2013-12-07 16:00 | 11 | 872 | 100 | 99 | -1 | 9504 | 9504 | 9408.96 | 9499.4689 | 0.99 | 0.99047 | FALSE | FALSE | FALSE | 109 | FALSE | 0 | Green | Continue normal monitoring.
145106 | HCFWB1Z4024 | B1 Z4 :Steel Doors | 26378 | 2013-12-08 08:00 | 2013-12-18 16:00 | 10 | 792 | 100 | 94 | -6 | 9810 | 9810 | 9221.4 | 10792.2948 | 0.94 | 0.85444 | TRUE | FALSE | FALSE | 99 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145107 | HCFWB1Z4026 | B1 Z4 :Wooden Doors | 26378 | 2014-01-21 08:00 | 2014-02-01 16:00 | 11 | 512 | 100 | 94 | -6 | 7700 | 7700 | 7238 | 6583.0104 | 0.94 | 1.0995 | FALSE | FALSE | FALSE | 64 | FALSE | 0 | Green | Continue normal monitoring.
145108 | HCFWB1Z4023 | B1 Z4 :Metal Works | 26378 | 2013-11-26 08:00 | 2013-12-07 16:00 | 11 | 792 | 100 | 100 | 0 | 7183 | 7183 | 7183 | 6516.3052 | 1 | 1.1023 | FALSE | FALSE | FALSE | 99 | FALSE | 0 | Green | Continue normal monitoring.
145109 | HCFWB1Z4027 | B1 Z4 :Handrails & Railling | 26378 | 2013-11-26 08:00 | 2013-12-12 16:00 | 16 | 872 | 100 | 80 | -20 | 31568 | 31568 | 25254.4 | 36205.889 | 0.8 | 0.69752 | TRUE | TRUE | TRUE | 109 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145110 | HCFWB1Z4030 | B1 Z4 :Stone Decoration For Benches | 26378 | 2013-11-26 08:00 | 2013-12-07 16:00 | 11 | 872 | 100 | 99 | -1 | 6292 | 6292 | 6229.08 | 5962.7059 | 0.99 | 1.0447 | FALSE | FALSE | FALSE | 109 | FALSE | 0 | Green | Continue normal monitoring.
145111 | HCFWB1Z4028 | B1 Z4 :Mirror | 26378 | 2013-11-26 08:00 | 2013-12-07 16:00 | 11 | 872 | 100 | 100 | 0 | 13332 | 13332 | 13332 | 14521.263 | 1 | 0.9181 | FALSE | FALSE | FALSE | 109 | FALSE | 0 | Green | Continue normal monitoring.
145112 | HCFWB1Z4029 | B1 Z4 :Toilet & corian vanity tops | 26378 | 2013-11-26 08:00 | 2013-12-07 16:00 | 11 | 872 | 100 | 86 | -14 | 8745 | 8745 | 7520.7 | 8780.3389 | 0.86 | 0.85654 | TRUE | TRUE | TRUE | 109 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145113 | HCFWB1Z4005 | B1 Z4 :Carpet Tile Flooring | 26181 | 2013-12-05 08:00 | 2013-12-16 16:00 | 11 | 552 | 100 | 100 | 0 | 16940 | 16940 | 16940 | 20191.164 | 1 | 0.83898 | TRUE | FALSE | FALSE | 69 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145114 | HCFWB1Z4006 | B1 Z4 :Wooden Base Skirting | 26181 | 2013-12-26 08:00 | 2014-01-07 16:00 | 12 | 496 | 100 | 83 | -17 | 20880 | 20880 | 17330.4 | 25702.5726 | 0.83 | 0.67427 | TRUE | TRUE | TRUE | 62 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145115 | HCFWB1Z4015 | B1 Z4 :Wooden Wall Covering | 26217 | 2014-01-08 08:00 | 2014-01-20 16:00 | 12 | 496 | 100 | 100 | 0 | 6720 | 6720 | 6720 | 8087.022 | 1 | 0.83096 | TRUE | FALSE | FALSE | 62 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145116 | HCFWB1Z4022 | B1 Z4 :Acoustical Ceiling | 26183 | 2013-11-26 08:00 | 2013-12-07 16:00 | 11 | 744 | 100 | 85 | -15 | 15818 | 15818 | 13445.3 | 15157.5668 | 0.85 | 0.88704 | TRUE | TRUE | TRUE | 93 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145117 | HCFWB1Z5002 | B1 Z5 :Trawelled smooth Concrete screed | 26185 | 2013-11-04 08:00 | 2013-11-13 16:00 | 9 | 156 | 100 | 100 | 0 | 4869 | 4869 | 4869 | 4516.8016 | 1 | 1.078 | FALSE | FALSE | FALSE | 19.5 | FALSE | 0 | Green | Continue normal monitoring.
145118 | HCFWB1Z5004 | B1 Z5 :Sealed Concrete | 26185 | 2013-12-14 12:00 | 2013-12-23 12:00 | 9 | 300 | 100 | 80 | -20 | 4716 | 4716 | 3772.8 | 4903.574 | 0.8 | 0.7694 | TRUE | TRUE | TRUE | 37.5 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145119 | HCFWB1Z5001 | B1 Z5 :Foam Concrete Under Floorings | 26185 | 2013-10-12 08:00 | 2013-11-03 16:00 | 22 | 156 | 100 | 100 | 0 | 34364 | 34364 | 34364 | 29310.2123 | 1 | 1.1724 | FALSE | FALSE | FALSE | 19.5 | FALSE | 0 | Green | Continue normal monitoring.
145120 | HCFWB1Z5005 | B1 Z5 :Rubber Flooring | 26185 | 2013-12-14 12:00 | 2013-12-26 12:00 | 12 | 156 | 100 | 84 | -16 | 7560 | 7560 | 6350.4 | 6504.0476 | 0.84 | 0.97638 | FALSE | TRUE | TRUE | 19.5 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145121 | HCFWB1Z5006 | B1 Z5 :Rubber Skirting | 26185 | 2013-12-29 08:00 | 2013-12-30 16:00 | 1 | 720 | 100 | 100 | 0 | 1752 | 1752 | 1752 | 1876.9461 | 1 | 0.93343 | FALSE | FALSE | FALSE | 90 | FALSE | 0 | Green | Continue normal monitoring.
145122 | HCFWB1Z5008 | B1 Z5 :Block Works | 26186 | 2013-02-25 08:00 | 2013-03-07 16:00 | 10 | 1400 | 100 | 100 | 0 | 6070 | 6070 | 6070 | 6423.1512 | 1 | 0.94502 | FALSE | FALSE | FALSE | 175 | FALSE | 0 | Green | Continue normal monitoring.
145123 | HCFWB1Z5009 | B1 Z5 :Plaster First Layer | 26186 | 2013-09-11 12:00 | 2013-09-22 10:00 | 10 | 156 | 100 | 80 | -20 | 6710 | 6710 | 5368 | 8372.9581 | 0.8 | 0.64111 | TRUE | TRUE | TRUE | 19.5 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145124 | HCFWB1Z5011 | B1 Z5 :Plaster Final Layer | 26186 | 2013-10-01 10:00 | 2013-10-10 16:00 | 9 | 156 | 100 | 100 | 0 | 17622 | 17622 | 17622 | 16401.4427 | 1 | 1.0744 | FALSE | FALSE | FALSE | 19.5 | FALSE | 0 | Green | Continue normal monitoring.
145125 | HCFWB1Z5012 | B1 Z5 :Paint First Layer | 26186 | 2013-12-23 12:00 | 2014-01-08 12:00 | 16 | 300 | 100 | 83 | -17 | 9616 | 9616 | 7981.28 | 9166.371 | 0.83 | 0.87071 | TRUE | TRUE | TRUE | 37.5 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145126 | HCFWB1Z5013 | B1 Z5 :Paint Final Layer | 26186 | 2014-01-08 12:00 | 2014-01-23 12:00 | 15 | 588 | 100 | 100 | 0 | 20475 | 20475 | 20475 | 18333.6479 | 1 | 1.1168 | FALSE | FALSE | FALSE | 73.5 | FALSE | 0 | Green | Continue normal monitoring.
145127 | HCFWB1Z5010 | B1 Z5 :Plaster Second Layer | 26186 | 2013-09-22 10:00 | 2013-10-01 10:00 | 9 | 156 | 100 | 81 | -19 | 9207 | 9207 | 7457.67 | 11205.0774 | 0.81 | 0.66556 | TRUE | TRUE | TRUE | 19.5 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145128 | HCFWB1Z5015 | B1 Z5 :Plaster First Layer | 26222 | 2013-11-14 08:00 | 2013-11-24 14:00 | 10 | 156 | 100 | 89 | -11 | 7740 | 7740 | 6888.6 | 8987.1036 | 0.89 | 0.7665 | TRUE | TRUE | TRUE | 19.5 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145129 | HCFWB1Z5017 | B1 Z5 :Plaster Final Layer | 26222 | 2013-12-03 14:00 | 2013-12-14 12:00 | 10 | 156 | 100 | 84 | -16 | 15670 | 15670 | 13162.8 | 18473.9216 | 0.84 | 0.71251 | TRUE | TRUE | TRUE | 19.5 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145130 | HCFWB1Z5018 | B1 Z5 :Paint First Layer | 26222 | 2014-01-08 12:00 | 2014-01-21 12:00 | 13 | 300 | 100 | 100 | 0 | 17108 | 17108 | 17108 | 20719.5932 | 1 | 0.82569 | TRUE | FALSE | FALSE | 37.5 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145131 | HCFWB1Z5019 | B1 Z5 :Paint Final Layer | 26222 | 2014-01-21 12:00 | 2014-02-02 12:00 | 12 | 300 | 100 | 89 | -11 | 17472 | 17472 | 15550.08 | 18519.621 | 0.89 | 0.83965 | TRUE | TRUE | TRUE | 37.5 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145132 | HCFWB1Z5020 | B1 Z5 :Gybsum Board Ceiling | 26222 | 2014-02-02 12:00 | 2014-02-18 12:00 | 16 | 300 | 100 | 80 | -20 | 24640 | 24640 | 19712 | 25390.9601 | 0.8 | 0.77634 | TRUE | TRUE | TRUE | 37.5 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145133 | HCFWB1Z5016 | B1 Z5 :Plaster Second Layer | 26222 | 2013-11-24 14:00 | 2013-12-03 14:00 | 9 | 156 | 100 | 100 | 0 | 7461 | 7461 | 7461 | 7327.8703 | 1 | 1.0182 | FALSE | FALSE | FALSE | 19.5 | FALSE | 0 | Green | Continue normal monitoring.
145134 | HCFWB1Z5023 | B1 Z5 :Steel Fire Rated Doors | 26188 | 2014-01-21 12:00 | 2014-02-02 12:00 | 12 | 508 | 100 | 85 | -15 | 6132 | 6132 | 5212.2 | 6657.4256 | 0.85 | 0.78292 | TRUE | TRUE | TRUE | 63.5 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145135 | HCFWB1Z5024 | B1 Z5 :Steel Doors | 26188 | 2014-02-02 12:00 | 2014-02-13 12:00 | 11 | 428 | 100 | 92 | -8 | 20251 | 20251 | 18630.92 | 20893.1867 | 0.92 | 0.89172 | TRUE | FALSE | FALSE | 53.5 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145136 | HCFWB1Z5026 | B1 Z5 :Wooden Doors | 26188 | 2014-02-02 12:00 | 2014-02-13 12:00 | 11 | 428 | 100 | 100 | 0 | 7865 | 7865 | 7865 | 8105.8753 | 1 | 0.97028 | FALSE | FALSE | FALSE | 53.5 | FALSE | 0 | Green | Continue normal monitoring.
145137 | HCFWB1Z5022 | B1 Z5 :Metal Works | 26188 | 2014-01-21 12:00 | 2014-02-02 12:00 | 12 | 428 | 100 | 94 | -6 | 10056 | 10056 | 9452.64 | 12316.2986 | 0.94 | 0.76749 | TRUE | FALSE | FALSE | 53.5 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145138 | HCFWB1Z5027 | B1 Z5 :Handrails & Railling | 26188 | 2014-01-21 12:00 | 2014-02-08 12:00 | 18 | 468 | 100 | 83 | -17 | 20880 | 20880 | 17330.4 | 25966.6312 | 0.83 | 0.66741 | TRUE | TRUE | TRUE | 58.5 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145139 | HCFWB1Z5025 | B1 Z5 :Stone Decoration For Benches | 26188 | 2014-01-21 12:00 | 2014-02-02 12:00 | 12 | 508 | 100 | 92 | -8 | 19248 | 19248 | 17708.16 | 22493.0926 | 0.92 | 0.78727 | TRUE | FALSE | FALSE | 63.5 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145140 | HCFWB1Z5028 | B1 Z5 :Mirror | 26188 | 2014-01-21 12:00 | 2014-02-02 12:00 | 12 | 508 | 100 | 100 | 0 | 10476 | 10476 | 10476 | 12075.7191 | 1 | 0.86753 | TRUE | FALSE | FALSE | 63.5 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145141 | HCFWB1Z5029 | B1 Z5 :Toilet & corian vanity tops | 26188 | 2014-01-21 12:00 | 2014-02-02 12:00 | 12 | 508 | 100 | 99 | -1 | 17700 | 17700 | 17523 | 19863.3518 | 0.99 | 0.88218 | TRUE | FALSE | FALSE | 63.5 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145142 | HCFWB1Z5007 | B1 Z5 :Carpet Tile Flooring | 26185 | 2013-12-14 12:00 | 2013-12-26 12:00 | 12 | 748 | 100 | 100 | 0 | 14508 | 14508 | 14508 | 13295.5656 | 1 | 1.0912 | FALSE | FALSE | FALSE | 93.5 | FALSE | 0 | Green | Continue normal monitoring.
145143 | HCFWB1Z5021 | B1 Z5 :Acoustical Ceiling | 26222 | 2014-01-21 12:00 | 2014-02-02 12:00 | 12 | 380 | 100 | 94 | -6 | 20676 | 20676 | 19435.44 | 18063.4288 | 0.94 | 1.076 | FALSE | FALSE | FALSE | 47.5 | FALSE | 0 | Green | Continue normal monitoring.
145144 | HCFWB1Z4014 | B1 Z4 :Glass Wall Tile & Laminated Taupe | 26217 | 2013-12-08 08:00 | 2013-12-18 16:00 | 10 | 584 | 100 | 100 | 0 | 9650 | 9650 | 9650 | 10868.7036 | 1 | 0.88787 | TRUE | FALSE | FALSE | 73 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145145 | HCFWB1Z4061 | B1 Z4 :Aluminum Base Skirting | 26181 | 2013-12-17 08:00 | 2013-12-29 16:00 | 12 | 552 | 100 | 87 | -13 | 19344 | 19344 | 16829.28 | 22081.4563 | 0.87 | 0.76215 | TRUE | TRUE | TRUE | 69 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145146 | HCFWB1Z5003 | B1 Z5 :Epoxy Screed Finish | 26185 | 2013-11-14 08:00 | 2013-11-25 16:00 | 11 | 504 | 100 | 84 | -16 | 19701 | 19701 | 16548.84 | 17116.016 | 0.84 | 0.96686 | FALSE | TRUE | TRUE | 63 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145147 | HCFWB1Z5014 | B1 Z5 :Epoxy Wall Paint | 26186 | 2014-01-08 12:00 | 2014-01-21 12:00 | 13 | 588 | 100 | 100 | 0 | 12844 | 12844 | 12844 | 15685.3587 | 1 | 0.81885 | TRUE | FALSE | FALSE | 73.5 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145148 | HCFWB1Z6002 | B1 Z6 :B1 Z6 :Trawelled smooth Concrete screed | 26379 | 2013-06-03 12:00 | 2013-06-12 12:00 | 9 | 1050 | 100 | 94 | -6 | 4914 | 4914 | 4619.16 | 4356.046 | 0.94 | 1.0604 | FALSE | FALSE | FALSE | 131.25 | FALSE | 0 | Green | Continue normal monitoring.
145149 | HCFWB1Z6003 | B1 Z6 :B1 Z6 :Sealed Concrete | 26379 | 2013-07-20 14:00 | 2013-07-29 14:00 | 9 | 1050 | 100 | 83 | -17 | 16299 | 16299 | 13528.17 | 15718.1071 | 0.83 | 0.86067 | TRUE | TRUE | TRUE | 131.25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145150 | HCFWB1Z6001 | B1 Z6 :B1 Z6 :Foam Concrete Under Floorings | 26379 | 2013-05-14 12:00 | 2013-06-03 12:00 | 20 | 1050 | 100 | 91 | -9 | 25540 | 25540 | 23241.4 | 28578.1343 | 0.91 | 0.81326 | TRUE | FALSE | FALSE | 131.25 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145151 | HCFWB1Z6006 | B1 Z6 :B1 Z6 :Wooden Base Skirting | 26379 | 2013-12-17 08:00 | 2013-12-29 16:00 | 12 | 728 | 100 | 92 | -8 | 18468 | 18468 | 16990.56 | 16952.6828 | 0.92 | 1.0022 | FALSE | FALSE | FALSE | 91 | FALSE | 0 | Green | Continue normal monitoring.
145152 | HCFWB1Z6008 | B1 Z6 :B1 Z6 :Block Works | 26190 | 2013-04-02 08:00 | 2013-04-13 16:00 | 11 | 1050 | 100 | 81 | -19 | 13310 | 13310 | 10781.1 | 11608.5342 | 0.81 | 0.92872 | FALSE | TRUE | TRUE | 131.25 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145153 | HCFWB1Z6009 | B1 Z6 :B1 Z6 :Plaster First Layer | 26190 | 2013-04-14 08:00 | 2013-04-23 14:00 | 9 | 1050 | 100 | 100 | 0 | 8100 | 8100 | 8100 | 7957.9146 | 1 | 1.0179 | FALSE | FALSE | FALSE | 131.25 | FALSE | 0 | Green | Continue normal monitoring.
145154 | HCFWB1Z6011 | B1 Z6 :B1 Z6 :Plaster Final Layer | 26190 | 2013-05-04 14:00 | 2013-05-14 12:00 | 9 | 1050 | 100 | 100 | 0 | 13320 | 13320 | 13320 | 15403.0966 | 1 | 0.86476 | TRUE | FALSE | FALSE | 131.25 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145155 | HCFWB1Z6012 | B1 Z6 :B1 Z6 :Paint First Layer | 26190 | 2013-07-29 14:00 | 2013-08-15 14:00 | 17 | 1050 | 100 | 98 | -2 | 27353 | 27353 | 26805.94 | 27776.1912 | 0.98 | 0.96507 | FALSE | FALSE | FALSE | 131.25 | FALSE | 0 | Green | Continue normal monitoring.
145156 | HCFWB1Z6013 | B1 Z6 :B1 Z6 :Paint Final Layer | 26190 | 2013-08-15 14:00 | 2013-08-29 14:00 | 14 | 1450 | 100 | 98 | -2 | 10486 | 10486 | 10276.28 | 11651.9296 | 0.98 | 0.88194 | TRUE | FALSE | FALSE | 181.25 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145157 | HCFWB1Z6010 | B1 Z6 :B1 Z6 :Plaster Second Layer | 26190 | 2013-04-23 14:00 | 2013-05-04 14:00 | 11 | 1050 | 100 | 83 | -17 | 9790 | 9790 | 8125.7 | 10591.2884 | 0.83 | 0.76721 | TRUE | TRUE | TRUE | 131.25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145158 | HCFWB1Z6017 | B1 Z6 :B1 Z6 :Plaster First Layer | 26232 | 2013-06-12 12:00 | 2013-06-23 10:00 | 10 | 1050 | 100 | 83 | -17 | 8340 | 8340 | 6922.2 | 7163.1209 | 0.83 | 0.96637 | FALSE | TRUE | TRUE | 131.25 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145159 | HCFWB1Z6019 | B1 Z6 :B1 Z6 :Plaster Final Layer | 26232 | 2013-07-02 10:00 | 2013-07-20 14:00 | 18 | 1050 | 100 | 100 | 0 | 20304 | 20304 | 20304 | 25286.9264 | 1 | 0.80294 | TRUE | FALSE | FALSE | 131.25 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145160 | HCFWB1Z6020 | B1 Z6 :B1 Z6 :Paint First Layer | 26232 | 2013-08-15 14:00 | 2013-08-27 14:00 | 12 | 1050 | 100 | 90 | -10 | 7632 | 7632 | 6868.8 | 6613.6717 | 0.9 | 1.0386 | FALSE | FALSE | FALSE | 131.25 | FALSE | 0 | Green | Continue normal monitoring.
145161 | HCFWB1Z6021 | B1 Z6 :B1 Z6 :Paint Final Layer | 26232 | 2013-08-27 14:00 | 2013-09-08 14:00 | 12 | 1354 | 100 | 100 | 0 | 16584 | 16584 | 16584 | 20516.4162 | 1 | 0.80833 | TRUE | FALSE | FALSE | 169.25 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145162 | HCFWB1Z6018 | B1 Z6 :B1 Z6 :Plaster Second Layer | 26232 | 2013-06-23 10:00 | 2013-07-02 10:00 | 9 | 1050 | 100 | 84 | -16 | 10683 | 10683 | 8973.72 | 11430.2296 | 0.84 | 0.78509 | TRUE | TRUE | TRUE | 131.25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145163 | HCFWB1Z6024 | B1 Z6 :B1 Z6 :Steel Fire Rated Doors | 26223 | 2013-10-27 10:00 | 2013-11-09 10:00 | 13 | 750 | 100 | 99 | -1 | 17238 | 17238 | 17065.62 | 21293.4741 | 0.99 | 0.80145 | TRUE | FALSE | FALSE | 93.75 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145164 | HCFWB1Z6025 | B1 Z6 :B1 Z6 :Steel Doors | 26223 | 2013-12-01 08:00 | 2013-12-11 16:00 | 10 | 520 | 100 | 90 | -10 | 12260 | 12260 | 11034 | 10983.7517 | 0.9 | 1.0046 | FALSE | FALSE | FALSE | 65 | FALSE | 0 | Green | Continue normal monitoring.
145165 | HCFWB1Z6026 | B1 Z6 :B1 Z6 :Wooden Doors | 26223 | 2013-12-01 08:00 | 2013-12-11 16:00 | 10 | 840 | 100 | 100 | 0 | 10930 | 10930 | 10930 | 11434.566 | 1 | 0.95587 | FALSE | FALSE | FALSE | 105 | FALSE | 0 | Green | Continue normal monitoring.
145166 | HCFWB1Z6023 | B1 Z6 :B1 Z6 :Metal Works | 26223 | 2013-11-19 08:00 | 2013-11-30 16:00 | 11 | 520 | 100 | 89 | -11 | 19206 | 19206 | 17093.34 | 17627.2982 | 0.89 | 0.96971 | FALSE | TRUE | TRUE | 65 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145167 | HCFWB1Z6027 | B1 Z6 :B1 Z6 :Handrails & Railling | 26223 | 2013-11-19 08:00 | 2013-12-05 16:00 | 16 | 880 | 100 | 87 | -13 | 23824 | 23824 | 20726.88 | 20736.1702 | 0.87 | 0.99955 | FALSE | TRUE | TRUE | 110 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145168 | HCFWB1Z6004 | B1 Z6 :B1 Z6 :Carpet Tile Flooring | 26379 | 2013-12-05 08:00 | 2013-12-16 16:00 | 11 | 728 | 100 | 85 | -15 | 9581 | 9581 | 8143.85 | 10510.4686 | 0.85 | 0.77483 | TRUE | TRUE | TRUE | 91 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145169 | HCFWB1Z6022 | B1 Z6 :B1 Z6 :Acoustical Ceiling | 26232 | 2013-08-27 14:00 | 2013-09-08 14:00 | 12 | 1354 | 100 | 85 | -15 | 17208 | 17208 | 14626.8 | 16057.0148 | 0.85 | 0.91093 | FALSE | TRUE | TRUE | 169.25 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145170 | HCFWB1Z6005 | B1 Z6 :B1 Z6 :Epoxy Screed Finish | 26379 | 2013-06-12 12:00 | 2013-06-24 12:00 | 12 | 1308 | 100 | 87 | -13 | 17928 | 17928 | 15597.36 | 19453.2929 | 0.87 | 0.80179 | TRUE | TRUE | TRUE | 163.5 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145171 | HCFWB1Z6014 | B1 Z6 :B1 Z6 :Epoxy Wall Paint | 26190 | 2013-08-15 14:00 | 2013-08-27 14:00 | 12 | 1450 | 100 | 100 | 0 | 10812 | 10812 | 10812 | 9676.1539 | 1 | 1.1174 | FALSE | FALSE | FALSE | 181.25 | FALSE | 0 | Green | Continue normal monitoring.
145172 | HCFWB1Z6007 | B1 Z6 :B1 Z6 :Aluminum & Stainless Steel Base Skirting | 26379 | 2013-12-17 08:00 | 2013-12-29 16:00 | 12 | 728 | 100 | 94 | -6 | 23592 | 23592 | 22176.48 | 23186.0899 | 0.94 | 0.95646 | FALSE | FALSE | FALSE | 91 | FALSE | 0 | Green | Continue normal monitoring.
145173 | HCFWB1Z6015 | B1 Z6 :B1 Z6 :Wire Cloth Stainless Steel Wall Cover | 26190 | 2013-08-15 14:00 | 2013-08-27 14:00 | 12 | 1450 | 100 | 100 | 0 | 13368 | 13368 | 13368 | 15542.3456 | 1 | 0.8601 | TRUE | FALSE | FALSE | 181.25 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145174 | HCFWB1Z6016 | B1 Z6 :B1 Z6 :Glass BackPainted Wall Tile | 26190 | 2013-08-27 14:00 | 2013-09-08 14:00 | 12 | 1450 | 100 | 93 | -7 | 21552 | 21552 | 20043.36 | 22086.9338 | 0.93 | 0.90748 | FALSE | FALSE | FALSE | 181.25 | FALSE | 0 | Green | Continue normal monitoring.
145175 | HCFWGFZ1002 | GF Z1 :Trawelled smooth Concrete screed | 26380 | 2013-04-16 12:00 | 2013-04-25 12:00 | 9 | 568 | 100 | 90 | -10 | 15138 | 15138 | 13624.2 | 16668.424 | 0.9 | 0.81737 | TRUE | FALSE | FALSE | 71 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145176 | HCFWGFZ1008 | GF Z1 :Block Works | 26236 | 2013-02-16 08:00 | 2013-02-26 16:00 | 10 | 400 | 100 | 91 | -9 | 16750 | 16750 | 15242.5 | 18575.4682 | 0.91 | 0.82057 | TRUE | FALSE | FALSE | 50 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145177 | HCFWGFZ1010 | GF Z1 :Plaster First Layer | 26236 | 2013-02-27 08:00 | 2013-03-09 14:00 | 10 | 568 | 100 | 100 | 0 | 14940 | 14940 | 14940 | 17741.2801 | 1 | 0.8421 | TRUE | FALSE | FALSE | 71 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145178 | HCFWGFZ1001 | GF Z1 :Foam Concrete Under Floorings | 26380 | 2013-03-28 12:00 | 2013-04-16 12:00 | 19 | 568 | 100 | 92 | -8 | 21261 | 21261 | 19560.12 | 20835.1234 | 0.92 | 0.93881 | FALSE | FALSE | FALSE | 71 | FALSE | 0 | Green | Continue normal monitoring.
145179 | HCFWGFZ1012 | GF Z1 :Plaster Final Layer | 26236 | 2013-03-18 14:00 | 2013-03-28 12:00 | 9 | 568 | 100 | 87 | -13 | 6183 | 6183 | 5379.21 | 6955.3694 | 0.87 | 0.77339 | TRUE | TRUE | TRUE | 71 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145180 | HCFWGFZ1013 | GF Z1 :Paint prime coat | 26236 | 2013-03-28 12:00 | 2013-04-11 12:00 | 14 | 1732 | 100 | 100 | 0 | 22694 | 22694 | 22694 | 28019.0637 | 1 | 0.80995 | TRUE | FALSE | FALSE | 216.5 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145181 | HCFWGFZ1014 | GF Z1 :Paint putty coat | 26236 | 2013-12-28 08:00 | 2014-01-11 16:00 | 14 | 360 | 100 | 97 | -3 | 8820 | 8820 | 8555.4 | 10073.2985 | 0.97 | 0.84931 | TRUE | FALSE | FALSE | 45 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145182 | HCFWGFZ1017 | GF Z1 :Plaster First Layer | 26227 | 2013-04-25 12:00 | 2013-05-07 10:00 | 11 | 568 | 100 | 100 | 0 | 14344 | 14344 | 14344 | 15003.0808 | 1 | 0.95607 | FALSE | FALSE | FALSE | 71 | FALSE | 0 | Green | Continue normal monitoring.
145183 | HCFWGFZ1019 | GF Z1 :Plaster Final Layer | 26227 | 2013-05-16 10:00 | 2013-05-27 16:00 | 11 | 568 | 100 | 80 | -20 | 18634 | 18634 | 14907.2 | 20540.0155 | 0.8 | 0.72576 | TRUE | TRUE | TRUE | 71 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145184 | HCFWGFZ1020 | GF Z1 :Paint prime coat | 26227 | 2013-05-28 08:00 | 2013-06-08 16:00 | 11 | 1432 | 100 | 94 | -6 | 15785 | 15785 | 14837.9 | 18087.6078 | 0.94 | 0.82034 | TRUE | FALSE | FALSE | 179 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145185 | HCFWGFZ1021 | GF Z1 :Paint putty coat | 26227 | 2013-06-09 08:00 | 2013-06-19 16:00 | 10 | 1432 | 100 | 87 | -13 | 14850 | 14850 | 12919.5 | 16259.418 | 0.87 | 0.79459 | TRUE | TRUE | TRUE | 179 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145186 | HCFWGFZ1024 | GF Z1 :Steel Fire Rated Doors | 26197 | 2013-12-21 08:00 | 2014-01-02 16:00 | 12 | 464 | 100 | 100 | 0 | 8184 | 8184 | 8184 | 7010.9899 | 1 | 1.1673 | FALSE | FALSE | FALSE | 58 | FALSE | 0 | Green | Continue normal monitoring.
145187 | HCFWGFZ1003 | GF Z1 :Rubber Flooring | 26380 | 2013-05-28 08:00 | 2013-06-08 16:00 | 11 | 704 | 100 | 90 | -10 | 16302 | 16302 | 14671.8 | 15126.779 | 0.9 | 0.96992 | FALSE | FALSE | FALSE | 88 | FALSE | 0 | Green | Continue normal monitoring.
145188 | HCFWGFZ1004 | GF Z1 :Rubber Skirting | 26380 | 2013-12-31 08:00 | 2014-01-02 16:00 | 2 | 784 | 100 | 91 | -9 | 1726 | 1726 | 1570.66 | 2026.6473 | 0.91 | 0.775 | TRUE | FALSE | FALSE | 98 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145189 | HCFWGFZ1025 | GF Z1 :Steel Doors | 26197 | 2014-01-04 08:00 | 2014-01-15 16:00 | 11 | 384 | 100 | 91 | -9 | 5918 | 5918 | 5385.38 | 5675.7186 | 0.91 | 0.94885 | FALSE | FALSE | FALSE | 48 | FALSE | 0 | Green | Continue normal monitoring.
145190 | HCFWGFZ1027 | GF Z1 :Wooden & Glass Doors Doors | 26197 | 2014-01-09 08:00 | 2014-01-21 16:00 | 12 | 344 | 100 | 83 | -17 | 11952 | 11952 | 9920.16 | 13656.6522 | 0.83 | 0.7264 | TRUE | TRUE | TRUE | 43 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145191 | HCFWGFZ1022 | GF Z1 :Gybsum Board Ceiling | 26227 | 2013-12-14 08:00 | 2013-12-30 16:00 | 16 | 288 | 100 | 95 | -5 | 29952 | 29952 | 28454.4 | 29917.4979 | 0.95 | 0.9511 | FALSE | FALSE | FALSE | 36 | FALSE | 0 | Green | Continue normal monitoring.
145192 | HCFWGFZ1023 | GF Z1 :Metal Works | 26197 | 2013-12-21 08:00 | 2014-01-02 16:00 | 12 | 248 | 100 | 83 | -17 | 17772 | 17772 | 14750.76 | 18816.1713 | 0.83 | 0.78394 | TRUE | TRUE | TRUE | 31 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145193 | HCFWGFZ1026 | GF Z1 :Handrails & Railling | 26197 | 2014-01-04 08:00 | 2014-01-21 16:00 | 17 | 224 | 100 | 84 | -16 | 24140 | 24140 | 20277.6 | 21175.3502 | 0.84 | 0.9576 | FALSE | TRUE | TRUE | 28 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145194 | HCFWGFZ1011 | GF Z1 :Plaster Second Layer | 26236 | 2013-03-09 14:00 | 2013-03-18 14:00 | 9 | 568 | 100 | 100 | 0 | 17280 | 17280 | 17280 | 15940.6311 | 1 | 1.084 | FALSE | FALSE | FALSE | 71 | FALSE | 0 | Green | Continue normal monitoring.
145195 | HCFWGFZ1018 | GF Z1 :Plaster Second Layer | 26227 | 2013-05-07 10:00 | 2013-05-16 10:00 | 9 | 568 | 100 | 84 | -16 | 10989 | 10989 | 9230.76 | 13548.105 | 0.84 | 0.68133 | TRUE | TRUE | TRUE | 71 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145196 | HCFWGFZ2002 | GF Z2 :Trawelled smooth Concrete screed | 26199 | 2013-05-04 08:00 | 2013-05-12 16:00 | 8 | 632 | 100 | 87 | -13 | 13472 | 13472 | 11720.64 | 16247.9759 | 0.87 | 0.72136 | TRUE | TRUE | TRUE | 79 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145197 | HCFWGFZ2001 | GF Z2 :Foam Concrete Under Floorings | 26199 | 2013-04-14 08:00 | 2013-05-02 16:00 | 18 | 632 | 100 | 100 | 0 | 9270 | 9270 | 9270 | 10298.1361 | 1 | 0.90016 | FALSE | FALSE | FALSE | 79 | FALSE | 0 | Green | Continue normal monitoring.
145198 | HCFWGFZ2004 | GF Z2 :Rubber Flooring | 26199 | 2013-06-11 08:00 | 2013-06-22 16:00 | 11 | 2040 | 100 | 89 | -11 | 10912 | 10912 | 9711.68 | 11281.4567 | 0.89 | 0.86085 | TRUE | TRUE | TRUE | 255 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145199 | HCFWGFZ2005 | GF Z2 :Rubber Skirting | 26199 | 2014-01-04 08:00 | 2014-01-05 16:00 | 1 | 784 | 100 | 96 | -4 | 1949 | 1949 | 1871.04 | 2183.4735 | 0.96 | 0.85691 | TRUE | FALSE | FALSE | 98 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145200 | HCFWGFZ2007 | GF Z2 :Block Works | 26200 | 2013-03-05 08:00 | 2013-03-16 16:00 | 11 | 632 | 100 | 100 | 0 | 17941 | 17941 | 17941 | 19689.2449 | 1 | 0.91121 | FALSE | FALSE | FALSE | 79 | FALSE | 0 | Green | Continue normal monitoring.
145201 | HCFWGFZ2009 | GF Z2 :Plaster First Layer | 26200 | 2013-03-17 08:00 | 2013-03-25 16:00 | 8 | 632 | 100 | 100 | 0 | 11144 | 11144 | 11144 | 12006.7785 | 1 | 0.92814 | FALSE | FALSE | FALSE | 79 | FALSE | 0 | Green | Continue normal monitoring.
145202 | HCFWGFZ2011 | GF Z2 :Plaster Final Layer | 26200 | 2013-04-04 08:00 | 2013-04-13 16:00 | 9 | 632 | 100 | 100 | 0 | 17757 | 17757 | 17757 | 15513.7729 | 1 | 1.1446 | FALSE | FALSE | FALSE | 79 | FALSE | 0 | Green | Continue normal monitoring.
145203 | HCFWGFZ2012 | GF Z2 :Paint prime coat | 26200 | 2013-07-23 14:00 | 2013-08-06 14:00 | 14 | 946 | 100 | 88 | -12 | 11340 | 11340 | 9979.2 | 12509.3926 | 0.88 | 0.79774 | TRUE | TRUE | TRUE | 118.25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145204 | HCFWGFZ2013 | GF Z2 :Paint putty coat | 26200 | 2013-08-06 14:00 | 2013-08-24 14:00 | 18 | 1010 | 100 | 100 | 0 | 22284 | 22284 | 22284 | 25795.2457 | 1 | 0.86388 | TRUE | FALSE | FALSE | 126.25 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145205 | HCFWGFZ2010 | GF Z2 :Plaster Second Layer | 26200 | 2013-03-26 08:00 | 2013-04-03 16:00 | 8 | 632 | 100 | 98 | -2 | 13544 | 13544 | 13273.12 | 16897.9368 | 0.98 | 0.78549 | TRUE | FALSE | FALSE | 79 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145206 | HCFWGFZ2015 | GF Z2 :Plaster First Layer | 26201 | 2013-05-13 08:00 | 2013-05-21 16:00 | 8 | 632 | 100 | 100 | 0 | 8360 | 8360 | 8360 | 7143.0467 | 1 | 1.1704 | FALSE | FALSE | FALSE | 79 | FALSE | 0 | Green | Continue normal monitoring.
145207 | HCFWGFZ2017 | GF Z2 :Plaster Final Layer | 26201 | 2013-06-02 08:00 | 2013-06-10 16:00 | 8 | 632 | 100 | 93 | -7 | 7304 | 7304 | 6792.72 | 8341.6748 | 0.93 | 0.81431 | TRUE | FALSE | FALSE | 79 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145208 | HCFWGFZ2018 | GF Z2 :Paint prime coat | 26201 | 2013-08-06 14:00 | 2013-08-21 14:00 | 15 | 946 | 100 | 87 | -13 | 11250 | 11250 | 9787.5 | 12135.5519 | 0.87 | 0.80651 | TRUE | TRUE | TRUE | 118.25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145209 | HCFWGFZ2019 | GF Z2 :Paint putty coat | 26201 | 2013-08-21 14:00 | 2013-09-02 14:00 | 12 | 946 | 100 | 88 | -12 | 15096 | 15096 | 13284.48 | 15452.5807 | 0.88 | 0.85969 | TRUE | TRUE | TRUE | 118.25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145210 | HCFWGFZ2020 | GF Z2 :Gybsum Board Ceiling | 26201 | 2013-12-12 08:00 | 2013-12-29 16:00 | 17 | 296 | 100 | 100 | 0 | 28288 | 28288 | 28288 | 25488.282 | 1 | 1.1098 | FALSE | FALSE | FALSE | 37 | FALSE | 0 | Green | Continue normal monitoring.
145211 | HCFWGFZ2016 | GF Z2 :Plaster Second Layer | 26201 | 2013-05-22 08:00 | 2013-06-01 16:00 | 10 | 632 | 100 | 90 | -10 | 17970 | 17970 | 16173 | 18215.004 | 0.9 | 0.88789 | TRUE | FALSE | FALSE | 79 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145212 | HCFWGFZ2023 | GF Z2 :Steel Fire Rated Doors | 26382 | 2013-12-07 08:00 | 2013-12-17 16:00 | 10 | 560 | 100 | 100 | 0 | 19390 | 19390 | 19390 | 19230.0494 | 1 | 1.0083 | FALSE | FALSE | FALSE | 70 | FALSE | 0 | Green | Continue normal monitoring.
145213 | HCFWGFZ2022 | GF Z2 :Steel Doors | 26382 | 2014-01-16 08:00 | 2014-01-27 16:00 | 11 | 304 | 100 | 80 | -20 | 17182 | 17182 | 13745.6 | 16685.9893 | 0.8 | 0.82378 | TRUE | TRUE | TRUE | 38 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145214 | HCFWGFZ2024 | GF Z2 :Wooden Doors | 26382 | 2014-01-16 08:00 | 2014-01-27 16:00 | 11 | 384 | 100 | 93 | -7 | 14443 | 14443 | 13431.99 | 16498.9878 | 0.93 | 0.81411 | TRUE | FALSE | FALSE | 48 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145215 | HCFWGFZ2021 | GF Z2 :Metal Works | 26382 | 2014-01-04 08:00 | 2014-01-15 16:00 | 11 | 248 | 100 | 84 | -16 | 5808 | 5808 | 4878.72 | 6564.7255 | 0.84 | 0.74317 | TRUE | TRUE | TRUE | 31 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145216 | HCFWGFZ2025 | GF Z2 :Handrails & Railling | 26382 | 2014-01-09 08:00 | 2014-01-27 16:00 | 18 | 208 | 100 | 100 | 0 | 26226 | 26226 | 26226 | 28471.1564 | 1 | 0.92114 | FALSE | FALSE | FALSE | 26 | FALSE | 0 | Green | Continue normal monitoring.
145217 | HCFWGFZ3002 | GF Z3 :Trawelled smooth Concrete screed | 26203 | 2013-08-18 08:00 | 2013-08-26 16:00 | 8 | 0 | 100 | 100 | 0 | 7808 | 7808 | 7808 | 9568.4379 | 1 | 0.81602 | TRUE | FALSE | FALSE | 0 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145218 | HCFWGFZ3001 | GF Z3 :Foam Concrete Under Floorings | 26203 | 2013-07-27 08:00 | 2013-08-17 16:00 | 21 | 0 | 100 | 93 | -7 | 17157 | 17157 | 15956.01 | 16984.4307 | 0.93 | 0.93945 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145219 | HCFWGFZ3003 | GF Z3 :Rubber Flooring | 26203 | 2013-09-24 08:00 | 2013-10-05 16:00 | 11 | 864 | 100 | 83 | -17 | 8184 | 8184 | 6792.72 | 7754.51 | 0.83 | 0.87597 | TRUE | TRUE | TRUE | 108 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145220 | HCFWGFZ3004 | GF Z3 :Rubber Skirting | 26203 | 2014-01-06 08:00 | 2014-01-07 16:00 | 1 | 784 | 100 | 100 | 0 | 1247 | 1247 | 1247 | 1387.1146 | 1 | 0.89899 | TRUE | FALSE | FALSE | 98 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145221 | HCFWGFZ3011 | GF Z3 :Block Works | 26204 | 2013-06-17 08:00 | 2013-06-27 16:00 | 10 | 0 | 100 | 100 | 0 | 11960 | 11960 | 11960 | 11117.1265 | 1 | 1.0758 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145222 | HCFWGFZ3012 | GF Z3 :Plaster First Layer | 26204 | 2013-06-29 08:00 | 2013-07-07 16:00 | 8 | 0 | 100 | 100 | 0 | 6168 | 6168 | 6168 | 6019.9939 | 1 | 1.0246 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145223 | HCFWGFZ3014 | GF Z3 :Plaster Final Layer | 26204 | 2013-07-17 08:00 | 2013-07-25 16:00 | 8 | 0 | 100 | 80 | -20 | 15704 | 15704 | 12563.2 | 14759.2627 | 0.8 | 0.85121 | TRUE | TRUE | TRUE | 0 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
145224 | HCFWGFZ3015 | GF Z3 :Paint prime coat | 26204 | 2013-09-07 14:00 | 2013-09-21 14:00 | 14 | 658 | 100 | 100 | 0 | 24668 | 24668 | 24668 | 21650.1521 | 1 | 1.1394 | FALSE | FALSE | FALSE | 82.25 | FALSE | 0 | Green | Continue normal monitoring.
145225 | HCFWGFZ3016 | GF Z3 :Paint putty coat | 26204 | 2013-09-21 14:00 | 2013-10-05 14:00 | 14 | 658 | 100 | 100 | 0 | 12264 | 12264 | 12264 | 14483.7778 | 1 | 0.84674 | TRUE | FALSE | FALSE | 82.25 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145226 | HCFWGFZ3013 | GF Z3 :Plaster Second Layer | 26204 | 2013-07-08 08:00 | 2013-07-16 16:00 | 8 | 0 | 100 | 100 | 0 | 6120 | 6120 | 6120 | 5825.1152 | 1 | 1.0506 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145227 | HCFWGFZ3020 | GF Z3 :Plaster First Layer | 26205 | 2013-08-27 08:00 | 2013-09-04 16:00 | 8 | 0 | 100 | 98 | -2 | 11400 | 11400 | 11172 | 11847.0054 | 0.98 | 0.94302 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145228 | HCFWGFZ3022 | GF Z3 :Plaster Final Layer | 26205 | 2013-09-15 08:00 | 2013-09-23 16:00 | 8 | 0 | 100 | 87 | -13 | 11360 | 11360 | 9883.2 | 9852.8246 | 0.87 | 1.0031 | FALSE | TRUE | TRUE | 0 | TRUE | 4 | Orange | Develop recovery plan and review schedule and cost exposure.
145229 | HCFWGFZ3023 | GF Z3 :Paint prime coat | 26205 | 2013-10-05 14:00 | 2013-10-21 14:00 | 16 | 674 | 100 | 94 | -6 | 30112 | 30112 | 28305.28 | 34018.604 | 0.94 | 0.83205 | TRUE | FALSE | FALSE | 84.25 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145230 | HCFWGFZ3024 | GF Z3 :Paint putty coat | 26205 | 2013-12-30 08:00 | 2014-01-11 16:00 | 12 | 968 | 100 | 100 | 0 | 10068 | 10068 | 10068 | 9889.0353 | 1 | 1.0181 | FALSE | FALSE | FALSE | 121 | FALSE | 0 | Green | Continue normal monitoring.
145231 | HCFWGFZ3025 | GF Z3 :Gybsum Board Ceiling | 26205 | 2013-12-12 08:00 | 2013-12-29 16:00 | 17 | 328 | 100 | 94 | -6 | 15096 | 15096 | 14190.24 | 17328.6183 | 0.94 | 0.81889 | TRUE | FALSE | FALSE | 41 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145232 | HCFWGFZ3021 | GF Z3 :Plaster Second Layer | 26205 | 2013-09-05 08:00 | 2013-09-14 16:00 | 9 | 0 | 100 | 88 | -12 | 9684 | 9684 | 8521.92 | 9828.8845 | 0.88 | 0.86703 | TRUE | TRUE | TRUE | 0 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
145233 | HCFWGFZ3038 | GF Z3 :Steel Fire Rated Doors | 26206 | 2013-10-21 14:00 | 2013-11-02 14:00 | 12 | 866 | 100 | 100 | 0 | 6024 | 6024 | 6024 | 5592.0927 | 1 | 1.0772 | FALSE | FALSE | FALSE | 108.25 | FALSE | 0 | Green | Continue normal monitoring.
145234 | HCFWGFZ3037 | GF Z3 :Steel Doors | 26206 | 2013-12-12 08:00 | 2013-12-23 16:00 | 11 | 520 | 100 | 88 | -12 | 21472 | 21472 | 18895.36 | 22658.7581 | 0.88 | 0.83391 | TRUE | TRUE | TRUE | 65 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145235 | HCFWGFZ3030 | GF Z3 :Wooden Doors | 26206 | 2014-01-30 08:00 | 2014-02-10 16:00 | 11 | 208 | 100 | 89 | -11 | 18315 | 18315 | 16300.35 | 16523.8264 | 0.89 | 0.98648 | FALSE | TRUE | TRUE | 26 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145236 | HCFWGFZ3036 | GF Z3 :Metal Works | 26206 | 2013-12-01 08:00 | 2013-12-11 16:00 | 10 | 440 | 100 | 99 | -1 | 8750 | 8750 | 8662.5 | 8979.3871 | 0.99 | 0.96471 | FALSE | FALSE | FALSE | 55 | FALSE | 0 | Green | Continue normal monitoring.
145237 | HCFWGFZ3031 | GF Z3 :Handrails & Railling | 26206 | 2013-12-12 08:00 | 2013-12-30 16:00 | 18 | 360 | 100 | 100 | 0 | 14814 | 14814 | 14814 | 14472.1253 | 1 | 1.0236 | FALSE | FALSE | FALSE | 45 | FALSE | 0 | Green | Continue normal monitoring.
145238 | HCFWGFZ3007 | GF Z3 :Epoxy Screed Finish | 26203 | 2013-08-27 08:00 | 2013-09-07 16:00 | 11 | 1776 | 100 | 100 | 0 | 7095 | 7095 | 7095 | 8618.8913 | 1 | 0.82319 | TRUE | FALSE | FALSE | 222 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145239 | HCFWGFZ3006 | GF Z3 :Stone Flooring All types | 26203 | 2013-09-24 08:00 | 2013-10-07 16:00 | 13 | 1488 | 100 | 100 | 0 | 10296 | 10296 | 10296 | 9002.5288 | 1 | 1.1437 | FALSE | FALSE | FALSE | 186 | FALSE | 0 | Green | Continue normal monitoring.
145240 | HCFWGFZ3005 | GF Z3 :Aluminum & Stainless Steel Skirting | 26203 | 2014-01-06 08:00 | 2014-01-18 16:00 | 12 | 928 | 100 | 88 | -12 | 11172 | 11172 | 9831.36 | 12597.625 | 0.88 | 0.78041 | TRUE | TRUE | TRUE | 116 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145241 | HCFWGFZ3018 | GF Z3 :Stainless steel Wire Cloth Finish For Elev Lobby | 26204 | 2013-09-21 14:00 | 2013-10-02 14:00 | 11 | 1602 | 100 | 82 | -18 | 13244 | 13244 | 10860.08 | 12225.5426 | 0.82 | 0.88831 | TRUE | TRUE | TRUE | 200.25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145242 | HCFWGFZ3034 | GF Z3 :Stone Decoration For Benches | 26206 | 2013-12-12 08:00 | 2013-12-23 16:00 | 11 | 1080 | 100 | 100 | 0 | 15928 | 15928 | 15928 | 15571.5 | 1 | 1.0229 | FALSE | FALSE | FALSE | 135 | FALSE | 0 | Green | Continue normal monitoring.
145243 | HCFWGFZ3032 | GF Z3 :Mirror | 26206 | 2014-02-11 08:00 | 2014-02-22 16:00 | 11 | 688 | 100 | 99 | -1 | 11924 | 11924 | 11804.76 | 12117.2359 | 0.99 | 0.97421 | FALSE | FALSE | FALSE | 86 | FALSE | 0 | Green | Continue normal monitoring.
145244 | HCFWGFZ3033 | GF Z3 :Toilet & corian vanity tops | 26206 | 2014-02-11 08:00 | 2014-02-22 16:00 | 11 | 688 | 100 | 100 | 0 | 9878 | 9878 | 9878 | 11984.0492 | 1 | 0.82426 | TRUE | FALSE | FALSE | 86 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145245 | HCFWGFZ3008 | GF Z3 :Carpet Tile Flooring | 26203 | 2013-12-17 08:00 | 2013-12-29 16:00 | 12 | 1048 | 100 | 100 | 0 | 15792 | 15792 | 15792 | 14955.5184 | 1 | 1.0559 | FALSE | FALSE | FALSE | 131 | FALSE | 0 | Green | Continue normal monitoring.
145246 | HCFWGFZ3026 | GF Z3 :Acoustical Ceiling | 26205 | 2013-10-21 14:00 | 2013-11-02 14:00 | 12 | 674 | 100 | 90 | -10 | 22404 | 22404 | 20163.6 | 19861.673 | 0.9 | 1.0152 | FALSE | FALSE | FALSE | 84.25 | FALSE | 0 | Green | Continue normal monitoring.
145247 | HCFWGFZ3009 | GF Z3 :Stone Base Skirting | 26203 | 2013-10-08 08:00 | 2013-10-23 16:00 | 15 | 1488 | 100 | 85 | -15 | 21945 | 21945 | 18653.25 | 21450.7073 | 0.85 | 0.86959 | TRUE | TRUE | TRUE | 186 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145248 | HCFWGF0000 | Start Finishing Works GF | 25771 | 2013-02-13 08:00 | 2013-02-13 08:00 | 1 | 416 | 100 | 81 | -19 | 1663 | 1663 | 1347.03 | 1483.1805 | 0.81 | 0.9082 | FALSE | TRUE | TRUE | 52 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145249 | HCFWGF0001 | End Finishing Works GF | 25771 | 2014-03-04 16:00 | 2014-03-04 16:00 | 1 | 616 | 100 | 86 | -14 | 686 | 686 | 589.96 | 618.3869 | 0.86 | 0.95403 | FALSE | TRUE | TRUE | 77 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145250 | HCFWGFZ1005 | GF Z1 :Carpet Floor Tiles | 26380 | 2013-12-17 08:00 | 2013-12-29 16:00 | 12 | 1048 | 100 | 97 | -3 | 6720 | 6720 | 6518.4 | 7254.5104 | 0.97 | 0.89853 | TRUE | FALSE | FALSE | 131 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145251 | HCFWGFZ1009 | GF Z1 :Gybsum Board Partitions | 26236 | 2013-02-16 08:00 | 2013-02-26 16:00 | 10 | 816 | 100 | 100 | 0 | 14380 | 14380 | 14380 | 12573.3079 | 1 | 1.1437 | FALSE | FALSE | FALSE | 102 | FALSE | 0 | Green | Continue normal monitoring.
145252 | HCFWGFZ1006 | GF Z1 :Stone Flooring | 26380 | 2013-05-28 08:00 | 2013-06-10 16:00 | 13 | 704 | 100 | 81 | -19 | 24739 | 24739 | 20038.59 | 21334.2296 | 0.81 | 0.93927 | FALSE | TRUE | TRUE | 88 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145253 | HCFWGFZ1015 | GF Z1 :Stone Cladding | 26236 | 2013-03-28 12:00 | 2013-04-09 12:00 | 12 | 1860 | 100 | 100 | 0 | 14508 | 14508 | 14508 | 16477.6879 | 1 | 0.88046 | TRUE | FALSE | FALSE | 232.5 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145254 | HCFWGFZ1016 | GF Z1 :Glass Wall Cladding | 26236 | 2013-12-08 08:00 | 2013-12-26 16:00 | 18 | 200 | 100 | 96 | -4 | 23508 | 23508 | 22567.68 | 23382.44 | 0.96 | 0.96516 | FALSE | FALSE | FALSE | 25 | FALSE | 0 | Green | Continue normal monitoring.
145255 | HCFWGFZ1028 | GF Z1 :Mirrors | 26197 | 2014-01-22 08:00 | 2014-02-02 16:00 | 11 | 824 | 100 | 90 | -10 | 21593 | 21593 | 19433.7 | 19436.942 | 0.9 | 0.99983 | FALSE | FALSE | FALSE | 103 | FALSE | 0 | Green | Continue normal monitoring.
145256 | HCFWGFZ1029 | GF Z1 :Toilet & corian vanity tops | 26197 | 2014-01-22 08:00 | 2014-02-02 16:00 | 11 | 824 | 100 | 100 | 0 | 20262 | 20262 | 20262 | 19278.1808 | 1 | 1.051 | FALSE | FALSE | FALSE | 103 | FALSE | 0 | Green | Continue normal monitoring.
145257 | HCFWGFZ1007 | GF Z1 :Epoxy Screed Finish | 26380 | 2013-04-25 12:00 | 2013-05-08 12:00 | 13 | 828 | 100 | 91 | -9 | 23725 | 23725 | 21589.75 | 26259.651 | 0.91 | 0.82216 | TRUE | FALSE | FALSE | 103.5 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145258 | HCFWGFZ2006 | GF Z2 :Carpet Tiles | 26199 | 2013-12-17 08:00 | 2013-12-29 16:00 | 12 | 1048 | 100 | 100 | 0 | 22404 | 22404 | 22404 | 21512.6485 | 1 | 1.0414 | FALSE | FALSE | FALSE | 131 | FALSE | 0 | Green | Continue normal monitoring.
145259 | HCFWGFZ2003 | GF Z2 :Stone Flooring | 26199 | 2013-05-04 08:00 | 2013-05-16 16:00 | 12 | 864 | 100 | 98 | -2 | 6120 | 6120 | 5997.6 | 6412.5877 | 0.98 | 0.93529 | FALSE | FALSE | FALSE | 108 | FALSE | 0 | Green | Continue normal monitoring.
145260 | HCFWGFZ2014 | GF Z2 :Glass Wall Cladding | 26200 | 2013-12-08 08:00 | 2013-12-26 16:00 | 18 | 296 | 100 | 100 | 0 | 28530 | 28530 | 28530 | 25639.2868 | 1 | 1.1127 | FALSE | FALSE | FALSE | 37 | FALSE | 0 | Green | Continue normal monitoring.
145261 | HCFWGFZ2008 | GF Z2 :Gybsum Board Partitions | 26200 | 2013-03-05 08:00 | 2013-03-16 16:00 | 11 | 696 | 100 | 100 | 0 | 7975 | 7975 | 7975 | 8654.7687 | 1 | 0.92146 | FALSE | FALSE | FALSE | 87 | FALSE | 0 | Green | Continue normal monitoring.
145262 | HCFWGFZ3017 | GF Z3 :Glass Wall Cladding | 26204 | 2013-12-08 08:00 | 2013-12-26 16:00 | 18 | 56 | 100 | 100 | 0 | 30168 | 30168 | 30168 | 29456.9726 | 1 | 1.0241 | FALSE | FALSE | FALSE | 7 | FALSE | 0 | Green | Continue normal monitoring.
145263 | HCFWGFZ3010 | GF Z3 :Gybsum Board Partitions | 26204 | 2013-06-17 08:00 | 2013-06-27 16:00 | 10 | 0 | 100 | 86 | -14 | 10630 | 10630 | 9141.8 | 11701.3698 | 0.86 | 0.78126 | TRUE | TRUE | TRUE | 0 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
145264 | HCFWGFZ3019 | GF Z3 :Stone Cladding | 26204 | 2013-12-08 08:00 | 2013-12-18 16:00 | 10 | 1112 | 100 | 99 | -1 | 12710 | 12710 | 12582.9 | 14913.3796 | 0.99 | 0.84373 | TRUE | FALSE | FALSE | 139 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145265 | HCFWGFZ3035 | GF Z3 :Glass Doors | 26206 | 2013-12-01 08:00 | 2013-12-11 16:00 | 10 | 1160 | 100 | 85 | -15 | 18330 | 18330 | 15580.5 | 20065.0915 | 0.85 | 0.7765 | TRUE | TRUE | TRUE | 145 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145266 | HCFWF1Z1032 | F1 Z1 :Trawelled smooth Concrete screed | 26208 | 2013-05-18 08:00 | 2013-05-27 16:00 | 9 | 568 | 100 | 100 | 0 | 12456 | 12456 | 12456 | 12061.1327 | 1 | 1.0327 | FALSE | FALSE | FALSE | 71 | FALSE | 0 | Green | Continue normal monitoring.
145267 | HCFWF1Z1033 | F1 Z1 :Block Works | 26209 | 2013-03-02 08:00 | 2013-03-12 16:00 | 10 | 488 | 100 | 100 | 0 | 17660 | 17660 | 17660 | 16817.5735 | 1 | 1.0501 | FALSE | FALSE | FALSE | 61 | FALSE | 0 | Green | Continue normal monitoring.
145268 | HCFWF1Z1031 | F1 Z1 :Foam Concrete Under Floorings | 26208 | 2013-04-28 08:00 | 2013-05-16 16:00 | 18 | 568 | 100 | 80 | -20 | 34002 | 34002 | 27201.6 | 33354.887 | 0.8 | 0.81552 | TRUE | TRUE | TRUE | 71 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145269 | HCFWF1Z1038 | F1 Z1 :Paint Prime coat | 26209 | 2013-04-11 12:00 | 2013-04-25 12:00 | 14 | 1780 | 100 | 96 | -4 | 25942 | 25942 | 24904.32 | 23758.9341 | 0.96 | 1.0482 | FALSE | FALSE | FALSE | 222.5 | FALSE | 0 | Green | Continue normal monitoring.
145270 | HCFWF1Z1034 | F1 Z1 :Paint putty coat | 26209 | 2014-01-12 08:00 | 2014-01-26 16:00 | 14 | 360 | 100 | 100 | 0 | 22820 | 22820 | 22820 | 21050.7367 | 1 | 1.084 | FALSE | FALSE | FALSE | 45 | FALSE | 0 | Green | Continue normal monitoring.
145271 | HCFWF1Z1042 | F1 Z1 :Plaster First Layer | 26210 | 2013-05-28 08:00 | 2013-06-06 14:00 | 9 | 568 | 100 | 100 | 0 | 6525 | 6525 | 6525 | 7609.9538 | 1 | 0.85743 | TRUE | FALSE | FALSE | 71 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145272 | HCFWF1Z1039 | F1 Z1 :Plaster Final Layer | 26210 | 2013-06-16 14:00 | 2013-06-26 12:00 | 9 | 568 | 100 | 90 | -10 | 11916 | 11916 | 10724.4 | 11962.3894 | 0.9 | 0.89651 | TRUE | FALSE | FALSE | 71 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145273 | HCFWF1Z1035 | F1 Z1 :Paint Prime coat | 26210 | 2013-06-26 12:00 | 2013-07-08 12:00 | 12 | 1436 | 100 | 100 | 0 | 8604 | 8604 | 8604 | 8813.921 | 1 | 0.97618 | FALSE | FALSE | FALSE | 179.5 | FALSE | 0 | Green | Continue normal monitoring.
145274 | HCFWF1Z1036 | F1 Z1 :Paint putty coat | 26210 | 2013-07-08 12:00 | 2013-07-20 12:00 | 12 | 2092 | 100 | 100 | 0 | 17232 | 17232 | 17232 | 18741.8642 | 1 | 0.91944 | FALSE | FALSE | FALSE | 261.5 | FALSE | 0 | Green | Continue normal monitoring.
145275 | HCFWF1Z1044 | F1 Z1 :Steel Fire Rated Doors | 26211 | 2014-01-04 08:00 | 2014-01-15 16:00 | 11 | 464 | 100 | 100 | 0 | 13772 | 13772 | 13772 | 14954.4832 | 1 | 0.92093 | FALSE | FALSE | FALSE | 58 | FALSE | 0 | Green | Continue normal monitoring.
145276 | HCFWF1Z1043 | F1 Z1 :Rubber Flooring | 26208 | 2013-06-26 12:00 | 2013-07-08 12:00 | 12 | 660 | 100 | 97 | -3 | 12060 | 12060 | 11698.2 | 10576.026 | 0.97 | 1.1061 | FALSE | FALSE | FALSE | 82.5 | FALSE | 0 | Green | Continue normal monitoring.
145277 | HCFWF1Z1040 | F1 Z1 :Steel Doors | 26211 | 2014-01-16 08:00 | 2014-01-27 16:00 | 11 | 384 | 100 | 100 | 0 | 8338 | 8338 | 8338 | 9860.6548 | 1 | 0.84558 | TRUE | FALSE | FALSE | 48 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145278 | HCFWF1Z1047 | F1 Z1 :Wooden Doors | 26211 | 2014-01-22 08:00 | 2014-02-02 16:00 | 11 | 344 | 100 | 96 | -4 | 6083 | 6083 | 5839.68 | 5602.021 | 0.96 | 1.0424 | FALSE | FALSE | FALSE | 43 | FALSE | 0 | Green | Continue normal monitoring.
145279 | HCFWF1Z1052 | F1 Z1 :Gybsum Board Ceiling | 26210 | 2013-12-31 08:00 | 2014-01-18 16:00 | 18 | 288 | 100 | 86 | -14 | 28260 | 28260 | 24303.6 | 32194.6018 | 0.86 | 0.7549 | TRUE | TRUE | TRUE | 36 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145280 | HCFWF1Z1048 | F1 Z1 :Metal Works | 26211 | 2014-01-04 08:00 | 2014-01-15 16:00 | 11 | 288 | 100 | 96 | -4 | 13486 | 13486 | 12946.56 | 15631.1964 | 0.96 | 0.82825 | TRUE | FALSE | FALSE | 36 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145281 | HCFWF1Z1041 | F1 Z1 :Handrails & Railling | 26211 | 2014-01-22 08:00 | 2014-02-08 16:00 | 17 | 224 | 100 | 99 | -1 | 20196 | 20196 | 19994.04 | 22941.8444 | 0.99 | 0.87151 | TRUE | FALSE | FALSE | 28 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145282 | HCFWF1Z1053 | F1 Z1 :Plaster Second Layer | 26210 | 2013-06-06 14:00 | 2013-06-16 14:00 | 10 | 568 | 100 | 88 | -12 | 16220 | 16220 | 14273.6 | 17543.407 | 0.88 | 0.81362 | TRUE | TRUE | TRUE | 71 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145283 | HCFWF1Z2027 | F1 Z2 :Trawelled smooth Concrete screed | 26362 | 2013-06-26 08:00 | 2013-07-04 16:00 | 8 | 464 | 100 | 96 | -4 | 12344 | 12344 | 11850.24 | 10564.5334 | 0.96 | 1.1217 | FALSE | FALSE | FALSE | 58 | FALSE | 0 | Green | Continue normal monitoring.
145284 | HCFWF1Z2026 | F1 Z2 :Foam Concrete Under Floorings | 26362 | 2013-06-08 08:00 | 2013-06-25 16:00 | 17 | 464 | 100 | 99 | -1 | 15606 | 15606 | 15449.94 | 15514.708 | 0.99 | 0.99583 | FALSE | FALSE | FALSE | 58 | FALSE | 0 | Green | Continue normal monitoring.
145285 | HCFWF1Z2029 | F1 Z2 :Rubber Flooring | 26362 | 2013-08-03 08:00 | 2013-08-17 16:00 | 14 | 1520 | 100 | 100 | 0 | 16646 | 16646 | 16646 | 18176.3629 | 1 | 0.9158 | FALSE | FALSE | FALSE | 190 | FALSE | 0 | Green | Continue normal monitoring.
145286 | HCFWF1Z2030 | F1 Z2 :Rubber Skirting | 26362 | 2013-08-18 08:00 | 2013-08-19 16:00 | 1 | 1520 | 100 | 100 | 0 | 1349 | 1349 | 1349 | 1355.7187 | 1 | 0.99504 | FALSE | FALSE | FALSE | 190 | FALSE | 0 | Green | Continue normal monitoring.
145287 | HCFWF1Z2032 | F1 Z2 :Block Works | 26214 | 2013-04-27 08:00 | 2013-05-08 16:00 | 11 | 448 | 100 | 100 | 0 | 6171 | 6171 | 6171 | 7376.7638 | 1 | 0.83655 | TRUE | FALSE | FALSE | 56 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145288 | HCFWF1Z2034 | F1 Z2 :Plaster First Layer | 26214 | 2013-05-09 08:00 | 2013-05-18 16:00 | 9 | 464 | 100 | 100 | 0 | 15012 | 15012 | 15012 | 14614.4959 | 1 | 1.0272 | FALSE | FALSE | FALSE | 58 | FALSE | 0 | Green | Continue normal monitoring.
145289 | HCFWF1Z2031 | F1 Z2 :Plaster Final Layer | 26214 | 2013-05-29 08:00 | 2013-06-06 16:00 | 8 | 464 | 100 | 100 | 0 | 5720 | 5720 | 5720 | 5533.6076 | 1 | 1.0337 | FALSE | FALSE | FALSE | 58 | FALSE | 0 | Green | Continue normal monitoring.
145290 | HCFWF1Z2037 | F1 Z2 :Paint Prime coat | 26214 | 2013-08-06 14:00 | 2013-08-24 14:00 | 18 | 946 | 100 | 87 | -13 | 9036 | 9036 | 7861.32 | 8642.0221 | 0.87 | 0.90966 | FALSE | TRUE | TRUE | 118.25 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145291 | HCFWF1Z2028 | F1 Z2 :Paint putty coat | 26214 | 2013-08-24 14:00 | 2013-09-07 14:00 | 14 | 1010 | 100 | 96 | -4 | 9226 | 9226 | 8856.96 | 9070.1945 | 0.96 | 0.97649 | FALSE | FALSE | FALSE | 126.25 | FALSE | 0 | Green | Continue normal monitoring.
145292 | HCFWF1Z2035 | F1 Z2 :Plaster Second Layer | 26214 | 2013-05-19 08:00 | 2013-05-28 16:00 | 9 | 464 | 100 | 86 | -14 | 11520 | 11520 | 9907.2 | 12360.5221 | 0.86 | 0.80152 | TRUE | TRUE | TRUE | 58 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145293 | HCFWF1Z2040 | F1 Z2 :Plaster First Layer | 26139 | 2013-07-06 08:00 | 2013-07-14 16:00 | 8 | 464 | 100 | 80 | -20 | 13144 | 13144 | 10515.2 | 14889.6036 | 0.8 | 0.70621 | TRUE | TRUE | TRUE | 58 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145294 | HCFWF1Z2042 | F1 Z2 :Plaster Final Layer | 26139 | 2013-07-24 08:00 | 2013-08-01 16:00 | 8 | 464 | 100 | 92 | -8 | 11136 | 11136 | 10245.12 | 12416.9425 | 0.92 | 0.82509 | TRUE | FALSE | FALSE | 58 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145295 | HCFWF1Z2033 | F1 Z2 :Paint Prime coat | 26139 | 2013-08-24 14:00 | 2013-09-04 14:00 | 11 | 962 | 100 | 100 | 0 | 17732 | 17732 | 17732 | 20801.181 | 1 | 0.85245 | TRUE | FALSE | FALSE | 120.25 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145296 | HCFWF1Z2039 | F1 Z2 :Paint putty coat | 26139 | 2013-09-04 14:00 | 2013-09-16 14:00 | 12 | 962 | 100 | 100 | 0 | 9936 | 9936 | 9936 | 11966.5766 | 1 | 0.83031 | TRUE | FALSE | FALSE | 120.25 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145297 | HCFWF1Z2045 | F1 Z2 :Gybsum Board Ceiling | 26139 | 2013-12-30 08:00 | 2014-01-16 16:00 | 17 | 296 | 100 | 98 | -2 | 18343 | 18343 | 17976.14 | 21579.2851 | 0.98 | 0.83303 | TRUE | FALSE | FALSE | 37 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145298 | HCFWF1Z2036 | F1 Z2 :Plaster Second Layer | 26139 | 2013-07-15 08:00 | 2013-07-23 16:00 | 8 | 464 | 100 | 100 | 0 | 15040 | 15040 | 15040 | 12897.9755 | 1 | 1.1661 | FALSE | FALSE | FALSE | 58 | FALSE | 0 | Green | Continue normal monitoring.
145299 | HCFWF1Z2038 | F1 Z2 :Steel Fire Rated Doors | 26216 | 2014-01-28 08:00 | 2014-02-08 16:00 | 11 | 304 | 100 | 100 | 0 | 19690 | 19690 | 19690 | 22532.5898 | 1 | 0.87385 | TRUE | FALSE | FALSE | 38 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145300 | HCFWF1Z2047 | F1 Z2 :Steel Doors | 26216 | 2014-01-28 08:00 | 2014-02-08 16:00 | 11 | 304 | 100 | 98 | -2 | 15961 | 15961 | 15641.78 | 14897.3562 | 0.98 | 1.05 | FALSE | FALSE | FALSE | 38 | FALSE | 0 | Green | Continue normal monitoring.
145301 | HCFWF1Z2044 | F1 Z2 :Wooden Doors | 26216 | 2014-01-28 08:00 | 2014-02-08 16:00 | 11 | 384 | 100 | 100 | 0 | 20306 | 20306 | 20306 | 18339.7947 | 1 | 1.1072 | FALSE | FALSE | FALSE | 48 | FALSE | 0 | Green | Continue normal monitoring.
145302 | HCFWF1Z2041 | F1 Z2 :Metal Works | 26216 | 2014-01-16 08:00 | 2014-01-27 16:00 | 11 | 288 | 100 | 100 | 0 | 12474 | 12474 | 12474 | 13788.7036 | 1 | 0.90465 | FALSE | FALSE | FALSE | 36 | FALSE | 0 | Green | Continue normal monitoring.
145303 | HCFWF1Z2050 | F1 Z2 :Handrails & Railling | 26216 | 2014-01-28 08:00 | 2014-02-13 16:00 | 16 | 208 | 100 | 100 | 0 | 23792 | 23792 | 23792 | 23266.132 | 1 | 1.0226 | FALSE | FALSE | FALSE | 26 | FALSE | 0 | Green | Continue normal monitoring.
145304 | HCFWF1Z3027 | F1 Z3 :Trawelled smooth Concrete screed | 26150 | 2013-09-15 08:00 | 2013-09-23 16:00 | 8 | 0 | 100 | 96 | -4 | 13744 | 13744 | 13194.24 | 11996.4073 | 0.96 | 1.0998 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145305 | HCFWF1Z3041 | F1 Z3 :Foam Concrete Under Floorings | 26150 | 2013-08-27 08:00 | 2013-09-14 16:00 | 18 | 0 | 100 | 92 | -8 | 25560 | 25560 | 23515.2 | 23133.1264 | 0.92 | 1.0165 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145306 | HCFWF1Z3028 | F1 Z3 :Rubber Flooring | 26150 | 2013-10-27 08:00 | 2013-11-07 16:00 | 11 | 368 | 100 | 100 | 0 | 13607 | 13607 | 13607 | 11571.0086 | 1 | 1.176 | FALSE | FALSE | FALSE | 46 | FALSE | 0 | Green | Continue normal monitoring.
145307 | HCFWF1Z3029 | F1 Z3 :Rubber Skirting | 26150 | 2013-11-09 08:00 | 2013-11-10 16:00 | 1 | 1008 | 100 | 100 | 0 | 1855 | 1855 | 1855 | 2246.9419 | 1 | 0.82557 | TRUE | FALSE | FALSE | 126 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145308 | HCFWF1Z3046 | F1 Z3 :Block Works | 26151 | 2013-06-29 08:00 | 2013-07-09 16:00 | 10 | 32 | 100 | 95 | -5 | 6690 | 6690 | 6355.5 | 5752.3777 | 0.95 | 1.1048 | FALSE | FALSE | FALSE | 4 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145309 | HCFWF1Z3042 | F1 Z3 :Plaster First Layer | 26151 | 2013-07-27 08:00 | 2013-08-04 16:00 | 8 | 0 | 100 | 87 | -13 | 8160 | 8160 | 7099.2 | 7619.6636 | 0.87 | 0.93169 | FALSE | TRUE | TRUE | 0 | TRUE | 4 | Orange | Develop recovery plan and review schedule and cost exposure.
145310 | HCFWF1Z3039 | F1 Z3 :Plaster Final Layer | 26151 | 2013-08-18 08:00 | 2013-08-26 16:00 | 8 | 0 | 100 | 98 | -2 | 15888 | 15888 | 15570.24 | 16150.2332 | 0.98 | 0.96409 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145311 | HCFWF1Z3040 | F1 Z3 :Paint Prime coat | 26151 | 2013-08-27 08:00 | 2013-09-09 16:00 | 13 | 832 | 100 | 97 | -3 | 7007 | 7007 | 6796.79 | 6955.3481 | 0.97 | 0.9772 | FALSE | FALSE | FALSE | 104 | FALSE | 0 | Green | Continue normal monitoring.
145312 | HCFWF1Z3051 | F1 Z3 :Paint putty coat | 26151 | 2014-01-09 08:00 | 2014-01-23 16:00 | 14 | 56 | 100 | 80 | -20 | 24976 | 24976 | 19980.8 | 30338.1062 | 0.8 | 0.6586 | TRUE | TRUE | TRUE | 7 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145313 | HCFWF1Z3043 | F1 Z3 :Plaster Second Layer | 26151 | 2013-08-05 08:00 | 2013-08-17 16:00 | 12 | 0 | 100 | 93 | -7 | 23016 | 23016 | 21404.88 | 19934.5162 | 0.93 | 1.0738 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145314 | HCFWF1Z3045 | F1 Z3 :Plaster First Layer | 26152 | 2013-09-24 08:00 | 2013-10-02 16:00 | 8 | 0 | 100 | 98 | -2 | 11632 | 11632 | 11399.36 | 12270.4326 | 0.98 | 0.92901 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145315 | HCFWF1Z3047 | F1 Z3 :Plaster Final Layer | 26152 | 2013-10-13 08:00 | 2013-10-26 16:00 | 13 | 0 | 100 | 94 | -6 | 22737 | 22737 | 21372.78 | 25515.2746 | 0.94 | 0.83765 | TRUE | FALSE | FALSE | 0 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145316 | HCFWF1Z3048 | F1 Z3 :Paint Prime coat | 26152 | 2014-01-25 08:00 | 2014-02-04 16:00 | 10 | 88 | 100 | 97 | -3 | 14830 | 14830 | 14385.1 | 18132.3324 | 0.97 | 0.79334 | TRUE | FALSE | FALSE | 11 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145317 | HCFWF1Z3044 | F1 Z3 :Paint putty coat | 26152 | 2014-02-22 08:00 | 2014-03-04 16:00 | 10 | 536 | 100 | 81 | -19 | 16470 | 16470 | 13340.7 | 18086.5058 | 0.81 | 0.73761 | TRUE | TRUE | TRUE | 67 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145318 | HCFWF1Z3050 | F1 Z3 :Gybsum Board Ceiling | 26152 | 2014-02-05 08:00 | 2014-02-20 16:00 | 15 | 88 | 100 | 100 | 0 | 22110 | 22110 | 22110 | 25901.9113 | 1 | 0.8536 | TRUE | FALSE | FALSE | 11 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145319 | HCFWF1Z3056 | F1 Z3 :Plaster Second Layer | 26152 | 2013-10-03 08:00 | 2013-10-12 16:00 | 9 | 0 | 100 | 100 | 0 | 4833 | 4833 | 4833 | 4269.907 | 1 | 1.1319 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145320 | HCFWF1Z3053 | F1 Z3 :Steel Fire Rated Doors | 26221 | 2014-02-05 08:00 | 2014-02-16 16:00 | 11 | 248 | 100 | 96 | -4 | 9097 | 9097 | 8733.12 | 9136.8067 | 0.96 | 0.95582 | FALSE | FALSE | FALSE | 31 | FALSE | 0 | Green | Continue normal monitoring.
145321 | HCFWF1Z3052 | F1 Z3 :Steel Doors | 26221 | 2014-02-17 08:00 | 2014-02-27 16:00 | 10 | 168 | 100 | 97 | -3 | 17740 | 17740 | 17207.8 | 17732.5289 | 0.97 | 0.97041 | FALSE | FALSE | FALSE | 21 | FALSE | 0 | Green | Continue normal monitoring.
145322 | HCFWF1Z3055 | F1 Z3 :Wooden Doors | 26221 | 2014-02-17 08:00 | 2014-02-27 16:00 | 10 | 168 | 100 | 100 | 0 | 16990 | 16990 | 16990 | 20464.7147 | 1 | 0.83021 | TRUE | FALSE | FALSE | 21 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145323 | HCFWF1Z3061 | F1 Z3 :Metal Works | 26221 | 2014-02-05 08:00 | 2014-02-16 16:00 | 11 | 128 | 100 | 85 | -15 | 15543 | 15543 | 13211.55 | 14152.6548 | 0.85 | 0.9335 | FALSE | TRUE | TRUE | 16 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145324 | HCFWF1Z3066 | F1 Z3 :Handrails & Railling | 26221 | 2014-02-05 08:00 | 2014-02-22 16:00 | 17 | 128 | 100 | 98 | -2 | 16201 | 16201 | 15876.98 | 14755.1332 | 0.98 | 1.076 | FALSE | FALSE | FALSE | 16 | FALSE | 0 | Green | Continue normal monitoring.
145325 | HCFWF1Z3057 | F1 Z3 :Epoxy Screed Finish | 26150 | 2013-09-24 08:00 | 2013-10-05 16:00 | 11 | 1584 | 100 | 100 | 0 | 5896 | 5896 | 5896 | 5786.4715 | 1 | 1.0189 | FALSE | FALSE | FALSE | 198 | FALSE | 0 | Green | Continue normal monitoring.
145326 | HCFWF1Z3071 | F1 Z3 :Stone Flooring All types | 26150 | 2013-10-27 08:00 | 2013-11-10 16:00 | 14 | 368 | 100 | 83 | -17 | 25746 | 25746 | 21369.18 | 22445.0131 | 0.83 | 0.95207 | FALSE | TRUE | TRUE | 46 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145327 | HCFWF1Z3060 | F1 Z3 :Aluminum & Stainless Steel Skirting | 26150 | 2013-11-09 08:00 | 2013-11-19 16:00 | 10 | 1312 | 100 | 80 | -20 | 14720 | 14720 | 11776 | 13586.3129 | 0.8 | 0.86675 | TRUE | TRUE | TRUE | 164 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145328 | HCFWF1Z3058 | F1 Z3 :Stainless steel Wire Cloth Finish For Elev Lobby | 26151 | 2014-01-09 08:00 | 2014-01-21 16:00 | 12 | 904 | 100 | 87 | -13 | 15540 | 15540 | 13519.8 | 19208.7431 | 0.87 | 0.70384 | TRUE | TRUE | TRUE | 113 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145329 | HCFWF1Z3049 | F1 Z3 :Stone Decoration For Benches | 26221 | 2014-03-05 08:00 | 2014-03-16 16:00 | 11 | 536 | 100 | 100 | 0 | 16192 | 16192 | 16192 | 16536.4617 | 1 | 0.97917 | FALSE | FALSE | FALSE | 67 | FALSE | 0 | Green | Continue normal monitoring.
145330 | HCFWF1Z3062 | F1 Z3 :Mirror | 26221 | 2014-03-01 08:00 | 2014-03-11 16:00 | 10 | 568 | 100 | 100 | 0 | 10920 | 10920 | 10920 | 12042.6599 | 1 | 0.90678 | FALSE | FALSE | FALSE | 71 | FALSE | 0 | Green | Continue normal monitoring.
145331 | HCFWF1Z3063 | F1 Z3 :Toilet & corian vanity tops | 26221 | 2014-03-01 08:00 | 2014-03-11 16:00 | 10 | 568 | 100 | 86 | -14 | 16370 | 16370 | 14078.2 | 18669.0765 | 0.86 | 0.75409 | TRUE | TRUE | TRUE | 71 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145332 | HCFWF1Z3068 | F1 Z3 :Carpet Tile Flooring | 26150 | 2013-12-17 08:00 | 2013-12-29 16:00 | 12 | 1048 | 100 | 82 | -18 | 18756 | 18756 | 15379.92 | 18695.6913 | 0.82 | 0.82265 | TRUE | TRUE | TRUE | 131 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145333 | HCFWF1Z3076 | F1 Z3 :Acoustical Ceiling | 26152 | 2014-02-05 08:00 | 2014-02-16 16:00 | 11 | 88 | 100 | 89 | -11 | 20064 | 20064 | 17856.96 | 18235.9856 | 0.89 | 0.97922 | FALSE | TRUE | TRUE | 11 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145334 | HCFWF1Z3054 | F1 Z3 :Stone Base Skirting | 26150 | 2013-11-11 08:00 | 2013-11-21 16:00 | 10 | 368 | 100 | 89 | -11 | 7230 | 7230 | 6434.7 | 6742.9323 | 0.89 | 0.95429 | FALSE | TRUE | TRUE | 46 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145335 | HCFWF1Z1045 | F1 Z1 :Carpet Floor Tiles | 26208 | 2013-12-17 08:00 | 2013-12-29 16:00 | 12 | 1048 | 100 | 98 | -2 | 9804 | 9804 | 9607.92 | 9561.9058 | 0.98 | 1.0048 | FALSE | FALSE | FALSE | 131 | FALSE | 0 | Green | Continue normal monitoring.
145336 | HCFWF1Z1054 | F1 Z1 :Gybsum Board Partitions | 26209 | 2013-03-02 08:00 | 2013-03-12 16:00 | 10 | 912 | 100 | 93 | -7 | 8480 | 8480 | 7886.4 | 9365.5441 | 0.93 | 0.84207 | TRUE | FALSE | FALSE | 114 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145337 | HCFWF1Z1051 | F1 Z1 :Stone Flooring | 26208 | 2013-06-26 12:00 | 2013-07-10 12:00 | 14 | 660 | 100 | 81 | -19 | 8596 | 8596 | 6962.76 | 8676.0478 | 0.81 | 0.80253 | TRUE | TRUE | TRUE | 82.5 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145338 | HCFWF1Z1056 | F1 Z1 :Glass Wall Cladding | 26209 | 2013-12-28 08:00 | 2014-01-16 16:00 | 19 | 200 | 100 | 100 | 0 | 22743 | 22743 | 22743 | 19393.5447 | 1 | 1.1727 | FALSE | FALSE | FALSE | 25 | FALSE | 0 | Green | Continue normal monitoring.
145339 | HCFWF1Z1058 | F1 Z1 :Mirrors | 26211 | 2014-02-03 08:00 | 2014-02-13 16:00 | 10 | 744 | 100 | 80 | -20 | 18460 | 18460 | 14768 | 19555.8387 | 0.8 | 0.75517 | TRUE | TRUE | TRUE | 93 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145340 | HCFWF1Z1059 | F1 Z1 :Toilet & corian vanity tops | 26211 | 2014-02-03 08:00 | 2014-02-13 16:00 | 10 | 744 | 100 | 100 | 0 | 15630 | 15630 | 15630 | 19046.8017 | 1 | 0.82061 | TRUE | FALSE | FALSE | 93 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145341 | HCFWF1Z2046 | F1 Z2 :Carpet Tiles | 26362 | 2013-12-17 08:00 | 2013-12-29 16:00 | 12 | 1048 | 100 | 100 | 0 | 6468 | 6468 | 6468 | 7598.8072 | 1 | 0.85119 | TRUE | FALSE | FALSE | 131 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145342 | HCFWF1Z2043 | F1 Z2 :Stone Flooring | 26362 | 2013-07-06 08:00 | 2013-07-18 16:00 | 12 | 600 | 100 | 100 | 0 | 21744 | 21744 | 21744 | 25659.7584 | 1 | 0.8474 | TRUE | FALSE | FALSE | 75 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145343 | HCFWF1Z2049 | F1 Z2 :Glass Wall Cladding | 26214 | 2013-12-28 08:00 | 2014-01-16 16:00 | 19 | 296 | 100 | 97 | -3 | 33915 | 33915 | 32897.55 | 39613.5071 | 0.97 | 0.83046 | TRUE | FALSE | FALSE | 37 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145344 | HCFWF1Z2048 | F1 Z2 :Gybsum Board Partitions | 26214 | 2013-04-27 08:00 | 2013-05-08 16:00 | 11 | 528 | 100 | 86 | -14 | 7865 | 7865 | 6763.9 | 7703.7072 | 0.86 | 0.87801 | TRUE | TRUE | TRUE | 66 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145345 | HCFWF1Z3067 | F1 Z3 :Glass Wall Cladding | 26151 | 2013-12-28 08:00 | 2014-01-16 16:00 | 19 | 56 | 100 | 100 | 0 | 31730 | 31730 | 31730 | 36682.3401 | 1 | 0.86499 | TRUE | FALSE | FALSE | 7 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145346 | HCFWF1Z3065 | F1 Z3 :Gybsum Board Partitions | 26151 | 2013-07-10 08:00 | 2013-07-21 16:00 | 11 | 32 | 100 | 87 | -13 | 9185 | 9185 | 7990.95 | 8333.2248 | 0.87 | 0.95893 | FALSE | TRUE | TRUE | 4 | TRUE | 4 | Orange | Develop recovery plan and review schedule and cost exposure.
145347 | HCFWF1Z3059 | F1 Z3 :Stone Cladding | 26151 | 2013-12-28 08:00 | 2014-01-08 16:00 | 11 | 56 | 100 | 80 | -20 | 18601 | 18601 | 14880.8 | 20704.5212 | 0.8 | 0.71872 | TRUE | TRUE | TRUE | 7 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145348 | HCFWF1Z3070 | F1 Z3 :Glass Doors | 26221 | 2014-02-05 08:00 | 2014-02-16 16:00 | 11 | 728 | 100 | 100 | 0 | 6501 | 6501 | 6501 | 7194.1849 | 1 | 0.90365 | FALSE | FALSE | FALSE | 91 | FALSE | 0 | Green | Continue normal monitoring.
145349 | HCFWF1Z1062 | F1 Z1 :Acoustical Ceiling | 26210 | 2013-12-31 08:00 | 2014-01-12 16:00 | 12 | 480 | 100 | 100 | 0 | 10224 | 10224 | 10224 | 8794.9703 | 1 | 1.1625 | FALSE | FALSE | FALSE | 60 | FALSE | 0 | Green | Continue normal monitoring.
145350 | HCFWF1Z1064 | F1 Z1 :Stone Base Skirting | 26208 | 2013-07-10 12:00 | 2013-07-22 12:00 | 12 | 2076 | 100 | 82 | -18 | 12840 | 12840 | 10528.8 | 14961.0146 | 0.82 | 0.70375 | TRUE | TRUE | TRUE | 259.5 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145351 | HCFWF2Z1057 | F2 Z1Trawelled smooth Concrete screed | 26224 | 2013-05-13 12:00 | 2013-05-22 12:00 | 9 | 800 | 100 | 100 | 0 | 11835 | 11835 | 11835 | 14335.7265 | 1 | 0.82556 | TRUE | FALSE | FALSE | 100 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145352 | HCFWF2Z1063 | F2 Z1Block Works | 26225 | 2013-03-13 08:00 | 2013-03-24 16:00 | 11 | 592 | 100 | 100 | 0 | 14080 | 14080 | 14080 | 13474.0828 | 1 | 1.045 | FALSE | FALSE | FALSE | 74 | FALSE | 0 | Green | Continue normal monitoring.
145353 | HCFWF2Z1055 | F2 Z1Plaster First Layer | 26225 | 2013-03-25 08:00 | 2013-04-03 14:00 | 9 | 800 | 100 | 100 | 0 | 7758 | 7758 | 7758 | 9115.3109 | 1 | 0.8511 | TRUE | FALSE | FALSE | 100 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145354 | HCFWF2Z1061 | F2 Z1Foam Concrete Under Floorings | 26224 | 2013-04-23 12:00 | 2013-05-13 12:00 | 20 | 800 | 100 | 100 | 0 | 21120 | 21120 | 21120 | 18648.1657 | 1 | 1.1326 | FALSE | FALSE | FALSE | 100 | FALSE | 0 | Green | Continue normal monitoring.
145355 | HCFWF2Z1067 | F2 Z1Plaster Final Layer | 26225 | 2013-04-13 14:00 | 2013-04-23 12:00 | 9 | 800 | 100 | 100 | 0 | 16812 | 16812 | 16812 | 18324.8639 | 1 | 0.91744 | FALSE | FALSE | FALSE | 100 | FALSE | 0 | Green | Continue normal monitoring.
145356 | HCFWF2Z1068 | F2 Z1Paint Prime coat | 26225 | 2013-04-25 12:00 | 2013-05-11 12:00 | 16 | 1780 | 100 | 87 | -13 | 27088 | 27088 | 23566.56 | 28286.8809 | 0.87 | 0.83313 | TRUE | TRUE | TRUE | 222.5 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145357 | HCFWF2Z1069 | F2 Z1Paint putty coat | 26225 | 2014-02-05 08:00 | 2014-02-23 16:00 | 18 | 296 | 100 | 100 | 0 | 15390 | 15390 | 15390 | 16442.2053 | 1 | 0.93601 | FALSE | FALSE | FALSE | 37 | FALSE | 0 | Green | Continue normal monitoring.
145358 | HCFWF2Z1072 | F2 Z1Plaster First Layer | 26226 | 2013-06-26 12:00 | 2013-07-07 10:00 | 10 | 568 | 100 | 100 | 0 | 6900 | 6900 | 6900 | 8421.3264 | 1 | 0.81935 | TRUE | FALSE | FALSE | 71 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145359 | HCFWF2Z1074 | F2 Z1Plaster Final Layer | 26226 | 2013-07-16 10:00 | 2013-07-25 16:00 | 9 | 568 | 100 | 94 | -6 | 8289 | 8289 | 7791.66 | 9934.5828 | 0.94 | 0.7843 | TRUE | FALSE | FALSE | 71 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145360 | HCFWF2Z1060 | F2 Z1Paint Prime coat | 26226 | 2013-07-27 08:00 | 2013-08-06 16:00 | 10 | 1328 | 100 | 84 | -16 | 11990 | 11990 | 10071.6 | 13956.7612 | 0.84 | 0.72163 | TRUE | TRUE | TRUE | 166 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145361 | HCFWF2Z1066 | F2 Z1Paint putty coat | 26226 | 2014-01-30 08:00 | 2014-02-10 16:00 | 11 | 768 | 100 | 82 | -18 | 5566 | 5566 | 4564.12 | 5340.4622 | 0.82 | 0.85463 | TRUE | TRUE | TRUE | 96 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145362 | HCFWF2Z1079 | F2 Z1Steel Fire Rated Doors | 26309 | 2014-01-16 08:00 | 2014-01-27 16:00 | 11 | 464 | 100 | 98 | -2 | 6952 | 6952 | 6812.96 | 8444.7852 | 0.98 | 0.80677 | TRUE | FALSE | FALSE | 58 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145363 | HCFWF2Z1073 | F2 Z1Rubber Flooring | 26224 | 2013-07-27 08:00 | 2013-08-06 16:00 | 10 | 640 | 100 | 80 | -20 | 10560 | 10560 | 8448 | 9387.8725 | 0.8 | 0.89988 | TRUE | TRUE | TRUE | 80 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145364 | HCFWF2Z1084 | F2 Z1Rubber Skirting | 26224 | 2013-11-11 08:00 | 2013-11-12 16:00 | 1 | 1008 | 100 | 100 | 0 | 1325 | 1325 | 1325 | 1578.5145 | 1 | 0.8394 | TRUE | FALSE | FALSE | 126 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145365 | HCFWF2Z1065 | F2 Z1Steel Doors | 26309 | 2014-01-28 08:00 | 2014-02-08 16:00 | 11 | 384 | 100 | 94 | -6 | 13860 | 13860 | 13028.4 | 13600.3194 | 0.94 | 0.95795 | FALSE | FALSE | FALSE | 48 | FALSE | 0 | Green | Continue normal monitoring.
145366 | HCFWF2Z1077 | F2 Z1Wooden Doors | 26309 | 2014-02-03 08:00 | 2014-02-13 16:00 | 10 | 344 | 100 | 87 | -13 | 15540 | 15540 | 13519.8 | 13543.2487 | 0.87 | 0.99827 | FALSE | TRUE | TRUE | 43 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145367 | HCFWF2Z1082 | F2 Z1Gybsum Board Ceiling | 26226 | 2014-01-19 08:00 | 2014-02-03 16:00 | 15 | 288 | 100 | 81 | -19 | 15510 | 15510 | 12563.1 | 17336.1907 | 0.81 | 0.72467 | TRUE | TRUE | TRUE | 36 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145368 | HCFWF2Z1078 | F2 Z1Metal Works | 26309 | 2014-01-16 08:00 | 2014-01-27 16:00 | 11 | 304 | 100 | 82 | -18 | 10175 | 10175 | 8343.5 | 9590.0593 | 0.82 | 0.87002 | TRUE | TRUE | TRUE | 38 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145369 | HCFWF2Z1071 | F2 Z1Handrails & Railling | 26309 | 2014-02-09 08:00 | 2014-02-25 16:00 | 16 | 224 | 100 | 100 | 0 | 30672 | 30672 | 30672 | 29059.5254 | 1 | 1.0555 | FALSE | FALSE | FALSE | 28 | FALSE | 0 | Green | Continue normal monitoring.
145370 | HCFWF2Z1076 | F2 Z1Plaster Second Layer | 26225 | 2013-04-03 14:00 | 2013-04-13 14:00 | 10 | 800 | 100 | 93 | -7 | 11710 | 11710 | 10890.3 | 11387.0249 | 0.93 | 0.95638 | FALSE | FALSE | FALSE | 100 | FALSE | 0 | Green | Continue normal monitoring.
145371 | HCFWF2Z1083 | F2 Z1Plaster Second Layer | 26226 | 2013-07-07 10:00 | 2013-07-16 10:00 | 9 | 568 | 100 | 100 | 0 | 7758 | 7758 | 7758 | 6791.9266 | 1 | 1.1422 | FALSE | FALSE | FALSE | 71 | FALSE | 0 | Green | Continue normal monitoring.
145372 | HCFWF2Z2052 | F2 Z2 :Trawelled smooth Concrete screed | 26229 | 2013-07-24 08:00 | 2013-08-01 16:00 | 8 | 464 | 100 | 93 | -7 | 15680 | 15680 | 14582.4 | 14438.9414 | 0.93 | 1.0099 | FALSE | FALSE | FALSE | 58 | FALSE | 0 | Green | Continue normal monitoring.
145373 | HCFWF2Z2051 | F2 Z2 :Foam Concrete Under Floorings | 26229 | 2013-07-06 08:00 | 2013-07-23 16:00 | 17 | 464 | 100 | 90 | -10 | 9877 | 9877 | 8889.3 | 8415.7556 | 0.9 | 1.0563 | FALSE | FALSE | FALSE | 58 | FALSE | 0 | Green | Continue normal monitoring.
145374 | HCFWF2Z2054 | F2 Z2 :Rubber Flooring | 26229 | 2013-09-03 08:00 | 2013-09-14 16:00 | 11 | 1376 | 100 | 95 | -5 | 9405 | 9405 | 8934.75 | 9669.8806 | 0.95 | 0.92398 | FALSE | FALSE | FALSE | 172 | FALSE | 0 | Green | Continue normal monitoring.
145375 | HCFWF2Z2055 | F2 Z2 :Rubber Skirting | 26229 | 2013-11-13 08:00 | 2013-11-14 16:00 | 1 | 1008 | 100 | 83 | -17 | 1781 | 1781 | 1478.23 | 1573.8735 | 0.83 | 0.93923 | FALSE | TRUE | TRUE | 126 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145376 | HCFWF2Z2057 | F2 Z2 :Block Works | 26230 | 2013-05-09 08:00 | 2013-05-20 16:00 | 11 | 576 | 100 | 99 | -1 | 11968 | 11968 | 11848.32 | 13440.7946 | 0.99 | 0.88152 | TRUE | FALSE | FALSE | 72 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145377 | HCFWF2Z2059 | F2 Z2 :Plaster First Layer | 26230 | 2013-06-08 08:00 | 2013-06-16 16:00 | 8 | 464 | 100 | 84 | -16 | 6352 | 6352 | 5335.68 | 5997.8705 | 0.84 | 0.8896 | TRUE | TRUE | TRUE | 58 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145378 | HCFWF2Z2056 | F2 Z2 :Plaster Final Layer | 26230 | 2013-06-26 08:00 | 2013-07-04 16:00 | 8 | 464 | 100 | 100 | 0 | 13976 | 13976 | 13976 | 17154.5569 | 1 | 0.81471 | TRUE | FALSE | FALSE | 58 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145379 | HCFWF2Z2062 | F2 Z2 :Paint Prime coat | 26230 | 2013-08-24 14:00 | 2013-09-07 14:00 | 14 | 946 | 100 | 100 | 0 | 21966 | 21966 | 21966 | 26326.2653 | 1 | 0.83438 | TRUE | FALSE | FALSE | 118.25 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145380 | HCFWF2Z2053 | F2 Z2 :Paint putty coat | 26230 | 2013-09-07 14:00 | 2013-09-25 14:00 | 18 | 1266 | 100 | 93 | -7 | 29448 | 29448 | 27386.64 | 28440.1822 | 0.93 | 0.96296 | FALSE | FALSE | FALSE | 158.25 | FALSE | 0 | Green | Continue normal monitoring.
145381 | HCFWF2Z2060 | F2 Z2 :Plaster Second Layer | 26230 | 2013-06-17 08:00 | 2013-06-25 16:00 | 8 | 464 | 100 | 100 | 0 | 14048 | 14048 | 14048 | 16341.8443 | 1 | 0.85963 | TRUE | FALSE | FALSE | 58 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145382 | HCFWF2Z2065 | F2 Z2 :Plaster First Layer | 26388 | 2013-08-03 08:00 | 2013-08-14 16:00 | 11 | 464 | 100 | 100 | 0 | 5676 | 5676 | 5676 | 6648.2872 | 1 | 0.85375 | TRUE | FALSE | FALSE | 58 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145383 | HCFWF2Z2067 | F2 Z2 :Plaster Final Layer | 26388 | 2013-08-25 08:00 | 2013-09-02 16:00 | 8 | 464 | 100 | 95 | -5 | 6872 | 6872 | 6528.4 | 8553.0647 | 0.95 | 0.76328 | TRUE | FALSE | FALSE | 58 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145384 | HCFWF2Z2058 | F2 Z2 :Paint Prime coat | 26388 | 2013-09-07 14:00 | 2013-09-18 14:00 | 11 | 1058 | 100 | 97 | -3 | 19206 | 19206 | 18629.82 | 20917.9459 | 0.97 | 0.89061 | TRUE | FALSE | FALSE | 132.25 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145385 | HCFWF2Z2064 | F2 Z2 :Paint putty coat | 26388 | 2014-02-03 08:00 | 2014-02-13 16:00 | 10 | 744 | 100 | 86 | -14 | 13650 | 13650 | 11739 | 12050.0329 | 0.86 | 0.97419 | FALSE | TRUE | TRUE | 93 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145386 | HCFWF2Z2070 | F2 Z2 :Gybsum Board Ceiling | 26388 | 2014-01-18 08:00 | 2014-02-02 16:00 | 15 | 296 | 100 | 89 | -11 | 17985 | 17985 | 16006.65 | 19940.597 | 0.89 | 0.80272 | TRUE | TRUE | TRUE | 37 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145387 | HCFWF2Z2061 | F2 Z2 :Plaster Second Layer | 26388 | 2013-08-15 08:00 | 2013-08-24 16:00 | 9 | 464 | 100 | 86 | -14 | 8523 | 8523 | 7329.78 | 9375.231 | 0.86 | 0.78182 | TRUE | TRUE | TRUE | 58 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145388 | HCFWF2Z2063 | F2 Z2 :Steel Fire Rated Doors | 26381 | 2014-02-09 08:00 | 2014-02-19 16:00 | 10 | 304 | 100 | 80 | -20 | 13550 | 13550 | 10840 | 14977.3601 | 0.8 | 0.72376 | TRUE | TRUE | TRUE | 38 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145389 | HCFWF2Z2072 | F2 Z2 :Steel Doors | 26381 | 2014-02-09 08:00 | 2014-02-19 16:00 | 10 | 304 | 100 | 100 | 0 | 8640 | 8640 | 8640 | 8405.4954 | 1 | 1.0279 | FALSE | FALSE | FALSE | 38 | FALSE | 0 | Green | Continue normal monitoring.
145390 | HCFWF2Z2069 | F2 Z2 :Wooden Doors | 26381 | 2014-02-09 08:00 | 2014-02-19 16:00 | 10 | 384 | 100 | 100 | 0 | 11740 | 11740 | 11740 | 14016.0553 | 1 | 0.83761 | TRUE | FALSE | FALSE | 48 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145391 | HCFWF2Z2066 | F2 Z2 :Metal Works | 26381 | 2014-01-28 08:00 | 2014-02-08 16:00 | 11 | 304 | 100 | 98 | -2 | 16577 | 16577 | 16245.46 | 20452.5182 | 0.98 | 0.7943 | TRUE | FALSE | FALSE | 38 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145392 | HCFWF2Z2075 | F2 Z2 :Handrails & Railling | 26381 | 2014-02-15 08:00 | 2014-03-03 16:00 | 16 | 208 | 100 | 95 | -5 | 29584 | 29584 | 28104.8 | 27722.7228 | 0.95 | 1.0138 | FALSE | FALSE | FALSE | 26 | FALSE | 0 | Green | Continue normal monitoring.
145393 | HCFWF2Z3072 | F2 Z3 :Trawelled smooth Concrete screed | 26383 | 2013-10-13 08:00 | 2013-10-26 16:00 | 13 | 0 | 100 | 100 | 0 | 12558 | 12558 | 12558 | 11117.1059 | 1 | 1.1296 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145394 | HCFWF2Z3081 | F2 Z3 :Foam Concrete Under Floorings | 26383 | 2013-09-24 08:00 | 2013-10-12 16:00 | 18 | 0 | 100 | 98 | -2 | 16434 | 16434 | 16105.32 | 15247.6955 | 0.98 | 1.0562 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145395 | HCFWF2Z3073 | F2 Z3 :Rubber Flooring | 26383 | 2013-11-25 08:00 | 2013-12-05 16:00 | 10 | 576 | 100 | 83 | -17 | 19780 | 19780 | 16417.4 | 23305.2085 | 0.83 | 0.70445 | TRUE | TRUE | TRUE | 72 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145396 | HCFWF2Z3064 | F2 Z3 :Rubber Skirting | 26383 | 2013-12-07 08:00 | 2013-12-08 16:00 | 1 | 864 | 100 | 100 | 0 | 1085 | 1085 | 1085 | 1215.9138 | 1 | 0.89233 | TRUE | FALSE | FALSE | 108 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145397 | HCFWF2Z3086 | F2 Z3 :Block Works | 26384 | 2013-07-10 08:00 | 2013-07-21 16:00 | 11 | 224 | 100 | 100 | 0 | 19316 | 19316 | 19316 | 21332.9562 | 1 | 0.90545 | FALSE | FALSE | FALSE | 28 | FALSE | 0 | Green | Continue normal monitoring.
145398 | HCFWF2Z3077 | F2 Z3 :Plaster First Layer | 26384 | 2013-08-27 08:00 | 2013-09-04 16:00 | 8 | 0 | 100 | 97 | -3 | 13976 | 13976 | 13556.72 | 14125.7843 | 0.97 | 0.95971 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145399 | HCFWF2Z3069 | F2 Z3 :Plaster Final Layer | 26384 | 2013-09-15 08:00 | 2013-09-23 16:00 | 8 | 0 | 100 | 81 | -19 | 11944 | 11944 | 9674.64 | 12913.0309 | 0.81 | 0.74922 | TRUE | TRUE | TRUE | 0 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
145400 | HCFWF2Z3075 | F2 Z3 :Paint Prime coat | 26384 | 2013-09-24 08:00 | 2013-10-05 16:00 | 11 | 752 | 100 | 80 | -20 | 21285 | 21285 | 17028 | 20713.4903 | 0.8 | 0.82207 | TRUE | TRUE | TRUE | 94 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145401 | HCFWF2Z3091 | F2 Z3 :Paint putty coat | 26384 | 2014-01-25 08:00 | 2014-02-04 16:00 | 10 | 56 | 100 | 94 | -6 | 10710 | 10710 | 10067.4 | 11147.8251 | 0.94 | 0.90308 | FALSE | FALSE | FALSE | 7 | FALSE | 0 | Green | Continue normal monitoring.
145402 | HCFWF2Z3078 | F2 Z3 :Plaster Second Layer | 26384 | 2013-09-05 08:00 | 2013-09-14 16:00 | 9 | 0 | 100 | 84 | -16 | 7506 | 7506 | 6305.04 | 8761.1924 | 0.84 | 0.71966 | TRUE | TRUE | TRUE | 0 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
145403 | HCFWF2Z3080 | F2 Z3 :Plaster First Layer | 26385 | 2013-10-27 08:00 | 2013-11-04 16:00 | 8 | 0 | 100 | 99 | -1 | 13960 | 13960 | 13820.4 | 17345.2531 | 0.99 | 0.79678 | TRUE | FALSE | FALSE | 0 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145404 | HCFWF2Z3082 | F2 Z3 :Plaster Final Layer | 26385 | 2013-11-16 08:00 | 2013-11-24 16:00 | 8 | 0 | 100 | 90 | -10 | 4288 | 4288 | 3859.2 | 5244.205 | 0.9 | 0.7359 | TRUE | FALSE | FALSE | 0 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145405 | HCFWF2Z3083 | F2 Z3 :Paint Prime coat | 26385 | 2014-02-05 08:00 | 2014-02-16 16:00 | 11 | 120 | 100 | 89 | -11 | 16368 | 16368 | 14567.52 | 20027.0071 | 0.89 | 0.72739 | TRUE | TRUE | TRUE | 15 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145406 | HCFWF2Z3074 | F2 Z3 :Paint putty coat | 26385 | 2014-02-17 08:00 | 2014-02-27 16:00 | 10 | 648 | 100 | 100 | 0 | 7770 | 7770 | 7770 | 7854.6114 | 1 | 0.98923 | FALSE | FALSE | FALSE | 81 | FALSE | 0 | Green | Continue normal monitoring.
145407 | HCFWF2Z3085 | F2 Z3 :Gybsum Board Ceiling | 26385 | 2014-02-22 08:00 | 2014-03-09 16:00 | 15 | 88 | 100 | 81 | -19 | 25785 | 25785 | 20885.85 | 26752.3488 | 0.81 | 0.78071 | TRUE | TRUE | TRUE | 11 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145408 | HCFWF2Z3096 | F2 Z3 :Plaster Second Layer | 26385 | 2013-11-06 08:00 | 2013-11-14 16:00 | 8 | 0 | 100 | 82 | -18 | 11320 | 11320 | 9282.4 | 12817.1171 | 0.82 | 0.72422 | TRUE | TRUE | TRUE | 0 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
145409 | HCFWF2Z3088 | F2 Z3 :Steel Fire Rated Doors | 26237 | 2014-02-17 08:00 | 2014-02-27 16:00 | 10 | 248 | 100 | 100 | 0 | 9830 | 9830 | 9830 | 11981.5587 | 1 | 0.82043 | TRUE | FALSE | FALSE | 31 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145410 | HCFWF2Z3087 | F2 Z3 :Steel Doors | 26237 | 2014-03-01 08:00 | 2014-03-11 16:00 | 10 | 168 | 100 | 100 | 0 | 17650 | 17650 | 17650 | 16004.9795 | 1 | 1.1028 | FALSE | FALSE | FALSE | 21 | FALSE | 0 | Green | Continue normal monitoring.
145411 | HCFWF2Z3090 | F2 Z3 :Wooden Doors | 26237 | 2014-03-01 08:00 | 2014-03-11 16:00 | 10 | 168 | 100 | 91 | -9 | 18470 | 18470 | 16807.7 | 17947.2389 | 0.91 | 0.93651 | FALSE | FALSE | FALSE | 21 | FALSE | 0 | Green | Continue normal monitoring.
145412 | HCFWF2Z3101 | F2 Z3 :Metal Works | 26237 | 2014-02-17 08:00 | 2014-02-27 16:00 | 10 | 168 | 100 | 99 | -1 | 12300 | 12300 | 12177 | 11140.0945 | 0.99 | 1.0931 | FALSE | FALSE | FALSE | 21 | FALSE | 0 | Green | Continue normal monitoring.
145413 | HCFWF2Z3106 | F2 Z3 :Handrails & Railling | 26237 | 2014-02-23 08:00 | 2014-03-11 16:00 | 16 | 128 | 100 | 84 | -16 | 11056 | 11056 | 9287.04 | 12104.1465 | 0.84 | 0.76726 | TRUE | TRUE | TRUE | 16 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145414 | HCFWF2Z3092 | F2 Z3 :Epoxy Screed Finish | 26383 | 2013-10-27 08:00 | 2013-11-07 16:00 | 11 | 1392 | 100 | 84 | -16 | 16940 | 16940 | 14229.6 | 16474.4956 | 0.84 | 0.86374 | TRUE | TRUE | TRUE | 174 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145415 | HCFWF2Z3111 | F2 Z3 :Stone Flooring All types | 26383 | 2013-11-25 08:00 | 2013-12-08 16:00 | 13 | 576 | 100 | 85 | -15 | 13299 | 13299 | 11304.15 | 13038.9133 | 0.85 | 0.86695 | TRUE | TRUE | TRUE | 72 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145416 | HCFWF2Z3095 | F2 Z3 :Aluminum & Stainless Steel Skirting | 26383 | 2013-12-07 08:00 | 2013-12-17 16:00 | 10 | 1120 | 100 | 100 | 0 | 14170 | 14170 | 14170 | 12446.4517 | 1 | 1.1385 | FALSE | FALSE | FALSE | 140 | FALSE | 0 | Green | Continue normal monitoring.
145417 | HCFWF2Z3093 | F2 Z3 :Stainless steel Wire Cloth Finish For Elev Lobby | 26384 | 2014-01-25 08:00 | 2014-02-11 16:00 | 17 | 760 | 100 | 88 | -12 | 15300 | 15300 | 13464 | 15145.7519 | 0.88 | 0.88896 | TRUE | TRUE | TRUE | 95 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145418 | HCFWF2Z3079 | F2 Z3 :Stone Decoration For Benches | 26237 | 2014-02-23 08:00 | 2014-03-05 16:00 | 10 | 608 | 100 | 81 | -19 | 13850 | 13850 | 11218.5 | 16550.7307 | 0.81 | 0.67783 | TRUE | TRUE | TRUE | 76 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145419 | HCFWF2Z3097 | F2 Z3 :Mirror | 26237 | 2014-03-12 08:00 | 2014-03-23 16:00 | 11 | 488 | 100 | 100 | 0 | 13244 | 13244 | 13244 | 12492.1265 | 1 | 1.0602 | FALSE | FALSE | FALSE | 61 | FALSE | 0 | Green | Continue normal monitoring.
145420 | HCFWF2Z3098 | F2 Z3 :Toilet & corian vanity tops | 26237 | 2014-03-12 08:00 | 2014-03-23 16:00 | 11 | 488 | 100 | 91 | -9 | 5731 | 5731 | 5215.21 | 6464.9977 | 0.91 | 0.80668 | TRUE | FALSE | FALSE | 61 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145421 | HCFWF2Z3103 | F2 Z3 :Carpet Tile Flooring | 26383 | 2013-12-17 08:00 | 2013-12-29 16:00 | 12 | 1048 | 100 | 82 | -18 | 11676 | 11676 | 9574.32 | 12865.2162 | 0.82 | 0.7442 | TRUE | TRUE | TRUE | 131 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145422 | HCFWF2Z3116 | F2 Z3 :Acoustical Ceiling | 26385 | 2014-02-17 08:00 | 2014-02-27 16:00 | 10 | 120 | 100 | 99 | -1 | 16430 | 16430 | 16265.7 | 19640.3208 | 0.99 | 0.82818 | TRUE | FALSE | FALSE | 15 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145423 | HCFWF2Z3084 | F2 Z3 :Stone Base Skirting | 26383 | 2013-12-09 08:00 | 2013-12-19 16:00 | 10 | 1104 | 100 | 100 | 0 | 7090 | 7090 | 7090 | 6401.6686 | 1 | 1.1075 | FALSE | FALSE | FALSE | 138 | FALSE | 0 | Green | Continue normal monitoring.
145424 | HCFWF2Z1070 | F2 Z1Carpet Floor Tiles | 26224 | 2013-12-17 08:00 | 2013-12-29 16:00 | 12 | 1048 | 100 | 100 | 0 | 9660 | 9660 | 9660 | 11988.4076 | 1 | 0.80578 | TRUE | FALSE | FALSE | 131 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145425 | HCFWF2Z1089 | F2 Z1Gybsum Board Partitions | 26225 | 2013-03-13 08:00 | 2013-03-24 16:00 | 11 | 1024 | 100 | 91 | -9 | 19723 | 19723 | 17947.93 | 21361.0239 | 0.91 | 0.84022 | TRUE | FALSE | FALSE | 128 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145426 | HCFWF2Z1081 | F2 Z1Stone Flooring | 26224 | 2013-07-27 08:00 | 2013-08-12 16:00 | 16 | 640 | 100 | 100 | 0 | 19248 | 19248 | 19248 | 24025.1546 | 1 | 0.80116 | TRUE | FALSE | FALSE | 80 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145427 | HCFWF2Z1075 | F2 Z1Stone Cladding | 26225 | 2013-04-23 12:00 | 2013-05-06 12:00 | 13 | 1940 | 100 | 96 | -4 | 15418 | 15418 | 14801.28 | 18726.7936 | 0.96 | 0.79038 | TRUE | FALSE | FALSE | 242.5 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145428 | HCFWF2Z1086 | F2 Z1Glass Wall Cladding | 26225 | 2014-01-18 08:00 | 2014-02-04 16:00 | 17 | 200 | 100 | 89 | -11 | 13328 | 13328 | 11861.92 | 12509.7529 | 0.89 | 0.94821 | FALSE | TRUE | TRUE | 25 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145429 | HCFWF2Z1088 | F2 Z1Mirrors | 26309 | 2014-02-15 08:00 | 2014-02-25 16:00 | 10 | 664 | 100 | 100 | 0 | 12150 | 12150 | 12150 | 10600.4474 | 1 | 1.1462 | FALSE | FALSE | FALSE | 83 | FALSE | 0 | Green | Continue normal monitoring.
145430 | HCFWF2Z1094 | F2 Z1Toilet & corian vanity tops | 26309 | 2014-02-15 08:00 | 2014-02-25 16:00 | 10 | 664 | 100 | 100 | 0 | 12620 | 12620 | 12620 | 12017.4661 | 1 | 1.0501 | FALSE | FALSE | FALSE | 83 | FALSE | 0 | Green | Continue normal monitoring.
145431 | HCFWF2Z2071 | F2 Z2 :Carpet Tiles | 26229 | 2013-12-17 08:00 | 2013-12-29 16:00 | 12 | 1048 | 100 | 100 | 0 | 21000 | 21000 | 21000 | 22281.5347 | 1 | 0.94248 | FALSE | FALSE | FALSE | 131 | FALSE | 0 | Green | Continue normal monitoring.
145432 | HCFWF2Z2068 | F2 Z2 :Stone Flooring | 26229 | 2013-08-03 08:00 | 2013-08-19 16:00 | 16 | 592 | 100 | 93 | -7 | 23152 | 23152 | 21531.36 | 21268.3196 | 0.93 | 1.0124 | FALSE | FALSE | FALSE | 74 | FALSE | 0 | Green | Continue normal monitoring.
145433 | HCFWF2Z2074 | F2 Z2 :Glass Wall Cladding | 26230 | 2014-01-18 08:00 | 2014-02-04 16:00 | 17 | 296 | 100 | 100 | 0 | 14960 | 14960 | 14960 | 13718.0791 | 1 | 1.0905 | FALSE | FALSE | FALSE | 37 | FALSE | 0 | Green | Continue normal monitoring.
145434 | HCFWF2Z2073 | F2 Z2 :Gybsum Board Partitions | 26230 | 2013-05-09 08:00 | 2013-05-20 16:00 | 11 | 640 | 100 | 96 | -4 | 10549 | 10549 | 10127.04 | 10918.6097 | 0.96 | 0.9275 | FALSE | FALSE | FALSE | 80 | FALSE | 0 | Green | Continue normal monitoring.
145435 | HCFWF2Z3102 | F2 Z3 :Glass Wall Cladding | 26384 | 2014-01-18 08:00 | 2014-02-04 16:00 | 17 | 344 | 100 | 97 | -3 | 26010 | 26010 | 25229.7 | 22454.62 | 0.97 | 1.1236 | FALSE | FALSE | FALSE | 43 | FALSE | 0 | Green | Continue normal monitoring.
145436 | HCFWF2Z3100 | F2 Z3 :Gybsum Board Partitions | 26384 | 2013-06-25 08:00 | 2013-07-06 16:00 | 11 | 328 | 100 | 98 | -2 | 5808 | 5808 | 5691.84 | 5219.9704 | 0.98 | 1.0904 | FALSE | FALSE | FALSE | 41 | FALSE | 0 | Green | Continue normal monitoring.
145437 | HCFWF2Z3089 | F2 Z3 :Stone Cladding | 26384 | 2014-01-18 08:00 | 2014-01-28 16:00 | 10 | 856 | 100 | 96 | -4 | 14060 | 14060 | 13497.6 | 14289.8042 | 0.96 | 0.94456 | FALSE | FALSE | FALSE | 107 | FALSE | 0 | Green | Continue normal monitoring.
145438 | HCFWF2Z3105 | F2 Z3 :Glass Doors | 26237 | 2014-02-17 08:00 | 2014-02-27 16:00 | 10 | 648 | 100 | 93 | -7 | 15560 | 15560 | 14470.8 | 13618.9206 | 0.93 | 1.0626 | FALSE | FALSE | FALSE | 81 | FALSE | 0 | Green | Continue normal monitoring.
145439 | HCFWF2Z1087 | F2 Z1Acoustical Ceiling | 26226 | 2014-01-19 08:00 | 2014-01-29 16:00 | 10 | 288 | 100 | 88 | -12 | 13780 | 13780 | 12126.4 | 13899.9139 | 0.88 | 0.87241 | TRUE | TRUE | TRUE | 36 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145440 | HCFWF2Z1099 | F2 Z1Stone Base Skirting | 26224 | 2013-08-13 08:00 | 2013-08-24 16:00 | 11 | 1584 | 100 | 87 | -13 | 6358 | 6358 | 5531.46 | 6609.7927 | 0.87 | 0.83686 | TRUE | TRUE | TRUE | 198 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145441 | HCFWF3Z1092 | F3 Z1 :Trawelled smooth Concrete screed | 26240 | 2013-06-13 08:00 | 2013-06-22 16:00 | 9 | 800 | 100 | 81 | -19 | 13014 | 13014 | 10541.34 | 13411.0135 | 0.81 | 0.78602 | TRUE | TRUE | TRUE | 100 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145442 | HCFWF3Z1093 | F3 Z1 :Block Works | 26241 | 2013-03-25 08:00 | 2013-04-04 16:00 | 10 | 704 | 100 | 92 | -8 | 9580 | 9580 | 8813.6 | 11473.6781 | 0.92 | 0.76816 | TRUE | FALSE | FALSE | 88 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145443 | HCFWF3Z1080 | F3 Z1 :Plaster First Layer | 26241 | 2013-04-23 12:00 | 2013-05-05 10:00 | 11 | 800 | 100 | 100 | 0 | 11759 | 11759 | 11759 | 12488.3518 | 1 | 0.9416 | FALSE | FALSE | FALSE | 100 | FALSE | 0 | Green | Continue normal monitoring.
145444 | HCFWF3Z1091 | F3 Z1 :Foam Concrete Under Floorings | 26240 | 2013-05-26 08:00 | 2013-06-12 16:00 | 17 | 800 | 100 | 86 | -14 | 33201 | 33201 | 28552.86 | 34435.8177 | 0.86 | 0.82916 | TRUE | TRUE | TRUE | 100 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145445 | HCFWF3Z1097 | F3 Z1 :Plaster Final Layer | 26241 | 2013-05-14 10:00 | 2013-05-23 16:00 | 9 | 800 | 100 | 88 | -12 | 11133 | 11133 | 9797.04 | 11292.0204 | 0.88 | 0.86761 | TRUE | TRUE | TRUE | 100 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145446 | HCFWF3Z1098 | F3 Z1 :Paint Prime coat | 26241 | 2013-05-26 08:00 | 2013-06-08 16:00 | 13 | 1688 | 100 | 100 | 0 | 23504 | 23504 | 23504 | 27665.368 | 1 | 0.84958 | TRUE | FALSE | FALSE | 211 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145447 | HCFWF3Z1104 | F3 Z1 :Paint putty coat | 26241 | 2014-02-24 08:00 | 2014-03-09 16:00 | 13 | 296 | 100 | 100 | 0 | 13195 | 13195 | 13195 | 15939.8588 | 1 | 0.8278 | TRUE | FALSE | FALSE | 37 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145448 | HCFWF3Z1102 | F3 Z1 :Plaster First Layer | 26242 | 2013-07-27 08:00 | 2013-08-05 14:00 | 9 | 568 | 100 | 90 | -10 | 14598 | 14598 | 13138.2 | 17390.5534 | 0.9 | 0.75548 | TRUE | FALSE | FALSE | 71 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145449 | HCFWF3Z1109 | F3 Z1 :Plaster Final Layer | 26242 | 2013-08-18 14:00 | 2013-08-28 12:00 | 9 | 568 | 100 | 93 | -7 | 8064 | 8064 | 7499.52 | 9026.9918 | 0.93 | 0.83079 | TRUE | FALSE | FALSE | 71 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145450 | HCFWF3Z1085 | F3 Z1 :Paint Prime coat | 26242 | 2013-08-28 12:00 | 2013-09-09 12:00 | 12 | 1156 | 100 | 83 | -17 | 6456 | 6456 | 5358.48 | 5842.323 | 0.83 | 0.91718 | FALSE | TRUE | TRUE | 144.5 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145451 | HCFWF3Z1096 | F3 Z1 :Paint putty coat | 26242 | 2013-09-09 12:00 | 2013-09-21 12:00 | 12 | 1156 | 100 | 100 | 0 | 21528 | 21528 | 21528 | 20682.9827 | 1 | 1.0409 | FALSE | FALSE | FALSE | 144.5 | FALSE | 0 | Green | Continue normal monitoring.
145452 | HCFWF3Z1114 | F3 Z1 :Steel Fire Rated Doors | 26243 | 2014-01-28 08:00 | 2014-02-08 16:00 | 11 | 464 | 100 | 100 | 0 | 15246 | 15246 | 15246 | 13240.011 | 1 | 1.1515 | FALSE | FALSE | FALSE | 58 | FALSE | 0 | Green | Continue normal monitoring.
145453 | HCFWF3Z1103 | F3 Z1 :Rubber Flooring | 26240 | 2013-08-28 12:00 | 2013-09-09 12:00 | 12 | 628 | 100 | 100 | 0 | 15552 | 15552 | 15552 | 19009.6704 | 1 | 0.81811 | TRUE | FALSE | FALSE | 78.5 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145454 | HCFWF3Z1119 | F3 Z1 :Rubber Skirting | 26240 | 2013-12-09 08:00 | 2013-12-10 16:00 | 1 | 864 | 100 | 92 | -8 | 656 | 656 | 603.52 | 730.9935 | 0.92 | 0.82562 | TRUE | FALSE | FALSE | 108 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145455 | HCFWF3Z1090 | F3 Z1 :Steel Doors | 26243 | 2014-02-09 08:00 | 2014-02-19 16:00 | 10 | 384 | 100 | 81 | -19 | 15980 | 15980 | 12943.8 | 18353.7516 | 0.81 | 0.70524 | TRUE | TRUE | TRUE | 48 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145456 | HCFWF3Z1107 | F3 Z1 :Wooden Doors | 26243 | 2014-02-15 08:00 | 2014-02-25 16:00 | 10 | 344 | 100 | 100 | 0 | 13830 | 13830 | 13830 | 13479.1149 | 1 | 1.026 | FALSE | FALSE | FALSE | 43 | FALSE | 0 | Green | Continue normal monitoring.
145457 | HCFWF3Z1112 | F3 Z1 :Gybsum Board Ceiling | 26242 | 2014-02-04 08:00 | 2014-02-19 16:00 | 15 | 288 | 100 | 84 | -16 | 24795 | 24795 | 20827.8 | 29462.9416 | 0.84 | 0.70692 | TRUE | TRUE | TRUE | 36 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145458 | HCFWF3Z1108 | F3 Z1 :Metal Works | 26243 | 2014-01-28 08:00 | 2014-02-08 16:00 | 11 | 304 | 100 | 90 | -10 | 16203 | 16203 | 14582.7 | 15455.0908 | 0.9 | 0.94355 | FALSE | FALSE | FALSE | 38 | FALSE | 0 | Green | Continue normal monitoring.
145459 | HCFWF3Z1101 | F3 Z1 :Handrails & Railling | 26243 | 2014-02-26 08:00 | 2014-03-15 16:00 | 17 | 224 | 100 | 85 | -15 | 27319 | 27319 | 23221.15 | 23239.1123 | 0.85 | 0.99923 | FALSE | TRUE | TRUE | 28 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145460 | HCFWF3Z1106 | F3 Z1 :Plaster Second Layer | 26241 | 2013-05-05 10:00 | 2013-05-14 10:00 | 9 | 800 | 100 | 97 | -3 | 13905 | 13905 | 13487.85 | 13912.87 | 0.97 | 0.96945 | FALSE | FALSE | FALSE | 100 | FALSE | 0 | Green | Continue normal monitoring.
145461 | HCFWF3Z1113 | F3 Z1 :Plaster Second Layer | 26242 | 2013-08-05 14:00 | 2013-08-18 14:00 | 13 | 568 | 100 | 100 | 0 | 25766 | 25766 | 25766 | 27783.5961 | 1 | 0.92738 | FALSE | FALSE | FALSE | 71 | FALSE | 0 | Green | Continue normal monitoring.
145462 | HCFWF3Z2077 | F3 Z2 :Trawelled smooth Concrete screed | 26245 | 2013-08-25 08:00 | 2013-09-02 16:00 | 8 | 464 | 100 | 89 | -11 | 10784 | 10784 | 9597.76 | 11231.3413 | 0.89 | 0.85455 | TRUE | TRUE | TRUE | 58 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145463 | HCFWF3Z2076 | F3 Z2 :Foam Concrete Under Floorings | 26245 | 2013-08-03 08:00 | 2013-08-24 16:00 | 21 | 464 | 100 | 83 | -17 | 40005 | 40005 | 33204.15 | 47799.1924 | 0.83 | 0.69466 | TRUE | TRUE | TRUE | 58 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145464 | HCFWF3Z2079 | F3 Z2 :Rubber Flooring | 26245 | 2013-10-01 08:00 | 2013-10-12 16:00 | 11 | 1232 | 100 | 88 | -12 | 13717 | 13717 | 12070.96 | 12237.7877 | 0.88 | 0.98637 | FALSE | TRUE | TRUE | 154 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145465 | HCFWF3Z2080 | F3 Z2 :Rubber Skirting | 26245 | 2013-12-11 08:00 | 2013-12-12 16:00 | 1 | 864 | 100 | 85 | -15 | 1963 | 1963 | 1668.55 | 2103.4122 | 0.85 | 0.79326 | TRUE | TRUE | TRUE | 108 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145466 | HCFWF3Z2082 | F3 Z2 :Block Works | 26137 | 2013-05-21 08:00 | 2013-06-02 16:00 | 12 | 688 | 100 | 81 | -19 | 17856 | 17856 | 14463.36 | 18841.5037 | 0.81 | 0.76763 | TRUE | TRUE | TRUE | 86 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145467 | HCFWF3Z2084 | F3 Z2 :Plaster First Layer | 26137 | 2013-07-06 08:00 | 2013-07-14 16:00 | 8 | 464 | 100 | 96 | -4 | 4160 | 4160 | 3993.6 | 4004.2379 | 0.96 | 0.99734 | FALSE | FALSE | FALSE | 58 | FALSE | 0 | Green | Continue normal monitoring.
145468 | HCFWF3Z2081 | F3 Z2 :Plaster Final Layer | 26137 | 2013-07-24 08:00 | 2013-08-01 16:00 | 8 | 464 | 100 | 84 | -16 | 6416 | 6416 | 5389.44 | 7563.7662 | 0.84 | 0.71253 | TRUE | TRUE | TRUE | 58 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145469 | HCFWF3Z2087 | F3 Z2 :Paint Prime coat | 26137 | 2013-09-07 14:00 | 2013-09-21 14:00 | 14 | 946 | 100 | 100 | 0 | 19152 | 19152 | 19152 | 22046.623 | 1 | 0.8687 | TRUE | FALSE | FALSE | 118.25 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145470 | HCFWF3Z2078 | F3 Z2 :Paint putty coat | 26137 | 2013-09-25 14:00 | 2013-10-09 14:00 | 14 | 1266 | 100 | 85 | -15 | 8162 | 8162 | 6937.7 | 9330.3387 | 0.85 | 0.74356 | TRUE | TRUE | TRUE | 158.25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145471 | HCFWF3Z2085 | F3 Z2 :Plaster Second Layer | 26137 | 2013-07-15 08:00 | 2013-07-23 16:00 | 8 | 464 | 100 | 100 | 0 | 15808 | 15808 | 15808 | 18977.1403 | 1 | 0.833 | TRUE | FALSE | FALSE | 58 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145472 | HCFWF3Z2090 | F3 Z2 :Plaster First Layer | 26138 | 2013-09-03 08:00 | 2013-09-11 16:00 | 8 | 464 | 100 | 91 | -9 | 15280 | 15280 | 13904.8 | 17405.6595 | 0.91 | 0.79887 | TRUE | FALSE | FALSE | 58 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145473 | HCFWF3Z2092 | F3 Z2 :Plaster Final Layer | 26138 | 2013-09-22 08:00 | 2013-09-30 16:00 | 8 | 464 | 100 | 100 | 0 | 14240 | 14240 | 14240 | 13424.568 | 1 | 1.0607 | FALSE | FALSE | FALSE | 58 | FALSE | 0 | Green | Continue normal monitoring.
145474 | HCFWF3Z2083 | F3 Z2 :Paint Prime coat | 26138 | 2013-10-01 08:00 | 2013-10-12 16:00 | 11 | 928 | 100 | 100 | 0 | 11759 | 11759 | 11759 | 13313.8348 | 1 | 0.88322 | TRUE | FALSE | FALSE | 116 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145475 | HCFWF3Z2089 | F3 Z2 :Paint putty coat | 26138 | 2013-10-13 08:00 | 2013-10-28 16:00 | 15 | 928 | 100 | 89 | -11 | 21495 | 21495 | 19130.55 | 20916.3788 | 0.89 | 0.91462 | FALSE | TRUE | TRUE | 116 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145476 | HCFWF3Z2095 | F3 Z2 :Gybsum Board Ceiling | 26138 | 2014-02-03 08:00 | 2014-02-18 16:00 | 15 | 296 | 100 | 100 | 0 | 25275 | 25275 | 25275 | 23932.1357 | 1 | 1.0561 | FALSE | FALSE | FALSE | 37 | FALSE | 0 | Green | Continue normal monitoring.
145477 | HCFWF3Z2086 | F3 Z2 :Plaster Second Layer | 26138 | 2013-09-12 08:00 | 2013-09-21 16:00 | 9 | 464 | 100 | 100 | 0 | 15174 | 15174 | 15174 | 13341.0026 | 1 | 1.1374 | FALSE | FALSE | FALSE | 58 | FALSE | 0 | Green | Continue normal monitoring.
145478 | HCFWF3Z2088 | F3 Z2 :Steel Fire Rated Doors | 26373 | 2014-02-20 08:00 | 2014-03-03 16:00 | 11 | 304 | 100 | 100 | 0 | 16588 | 16588 | 16588 | 19036.5784 | 1 | 0.87138 | TRUE | FALSE | FALSE | 38 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145479 | HCFWF3Z2097 | F3 Z2 :Steel Doors | 26373 | 2014-02-20 08:00 | 2014-03-03 16:00 | 11 | 304 | 100 | 100 | 0 | 14212 | 14212 | 14212 | 16122.0983 | 1 | 0.88152 | TRUE | FALSE | FALSE | 38 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145480 | HCFWF3Z2094 | F3 Z2 :Wooden Doors | 26373 | 2014-02-20 08:00 | 2014-03-03 16:00 | 11 | 384 | 100 | 100 | 0 | 14201 | 14201 | 14201 | 13402.9008 | 1 | 1.0595 | FALSE | FALSE | FALSE | 48 | FALSE | 0 | Green | Continue normal monitoring.
145481 | HCFWF3Z2091 | F3 Z2 :Metal Works | 26373 | 2014-02-09 08:00 | 2014-02-19 16:00 | 10 | 304 | 100 | 85 | -15 | 17940 | 17940 | 15249 | 20626.5438 | 0.85 | 0.73929 | TRUE | TRUE | TRUE | 38 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145482 | HCFWF3Z2100 | F3 Z2 :Handrails & Railling | 26373 | 2014-03-04 08:00 | 2014-03-20 16:00 | 16 | 208 | 100 | 100 | 0 | 15856 | 15856 | 15856 | 19298.914 | 1 | 0.8216 | TRUE | FALSE | FALSE | 26 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145483 | HCFWF3Z3107 | F3 Z3 :Trawelled smooth Concrete screed | 26141 | 2013-11-16 08:00 | 2013-11-24 16:00 | 8 | 0 | 100 | 87 | -13 | 5656 | 5656 | 4920.72 | 5052.0047 | 0.87 | 0.97401 | FALSE | TRUE | TRUE | 0 | TRUE | 4 | Orange | Develop recovery plan and review schedule and cost exposure.
145484 | HCFWF3Z3121 | F3 Z3 :Foam Concrete Under Floorings | 26141 | 2013-10-27 08:00 | 2013-11-14 16:00 | 18 | 0 | 100 | 81 | -19 | 28494 | 28494 | 23080.14 | 26871.3993 | 0.81 | 0.85891 | TRUE | TRUE | TRUE | 0 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
145485 | HCFWF3Z3108 | F3 Z3 :Rubber Flooring | 26141 | 2013-12-23 08:00 | 2014-01-05 16:00 | 13 | 440 | 100 | 91 | -9 | 12077 | 12077 | 10990.07 | 13889.8098 | 0.91 | 0.79123 | TRUE | FALSE | FALSE | 55 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145486 | HCFWF3Z3094 | F3 Z3 :Rubber Skirting | 26141 | 2014-01-06 08:00 | 2014-01-07 16:00 | 1 | 720 | 100 | 92 | -8 | 1484 | 1484 | 1365.28 | 1424.3472 | 0.92 | 0.95853 | FALSE | FALSE | FALSE | 90 | FALSE | 0 | Green | Continue normal monitoring.
145487 | HCFWF3Z3126 | F3 Z3 :Block Works | 26142 | 2013-07-22 08:00 | 2013-08-01 16:00 | 10 | 336 | 100 | 100 | 0 | 18320 | 18320 | 18320 | 20149.5376 | 1 | 0.9092 | FALSE | FALSE | FALSE | 42 | FALSE | 0 | Green | Continue normal monitoring.
145488 | HCFWF3Z3112 | F3 Z3 :Plaster First Layer | 26142 | 2013-09-24 08:00 | 2013-10-02 16:00 | 8 | 0 | 100 | 100 | 0 | 8152 | 8152 | 8152 | 7193.8603 | 1 | 1.1332 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145489 | HCFWF3Z3099 | F3 Z3 :Plaster Final Layer | 26142 | 2013-10-13 08:00 | 2013-10-26 16:00 | 13 | 0 | 100 | 86 | -14 | 14170 | 14170 | 12186.2 | 14607.5837 | 0.86 | 0.83424 | TRUE | TRUE | TRUE | 0 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
145490 | HCFWF3Z3110 | F3 Z3 :Paint Prime coat | 26142 | 2013-10-27 08:00 | 2013-11-10 16:00 | 14 | 624 | 100 | 89 | -11 | 21700 | 21700 | 19313 | 24860.3135 | 0.89 | 0.77686 | TRUE | TRUE | TRUE | 78 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145491 | HCFWF3Z3131 | F3 Z3 :Paint putty coat | 26142 | 2014-02-05 08:00 | 2014-02-18 16:00 | 13 | 56 | 100 | 92 | -8 | 9074 | 9074 | 8348.08 | 10204.671 | 0.92 | 0.81806 | TRUE | FALSE | FALSE | 7 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145492 | HCFWF3Z3113 | F3 Z3 :Plaster Second Layer | 26142 | 2013-10-03 08:00 | 2013-10-12 16:00 | 9 | 0 | 100 | 96 | -4 | 7974 | 7974 | 7655.04 | 9377.654 | 0.96 | 0.81631 | TRUE | FALSE | FALSE | 0 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145493 | HCFWF3Z3115 | F3 Z3 :Plaster First Layer | 26143 | 2013-11-25 08:00 | 2013-12-03 16:00 | 8 | 0 | 100 | 100 | 0 | 6784 | 6784 | 6784 | 8147.4541 | 1 | 0.83265 | TRUE | FALSE | FALSE | 0 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145494 | HCFWF3Z3117 | F3 Z3 :Plaster Final Layer | 26143 | 2013-12-14 08:00 | 2013-12-22 16:00 | 8 | 0 | 100 | 100 | 0 | 11672 | 11672 | 11672 | 13531.0391 | 1 | 0.86261 | TRUE | FALSE | FALSE | 0 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145495 | HCFWF3Z3118 | F3 Z3 :Paint Prime coat | 26143 | 2014-02-19 08:00 | 2014-03-02 16:00 | 11 | 56 | 100 | 100 | 0 | 13112 | 13112 | 13112 | 14667.5434 | 1 | 0.89395 | TRUE | FALSE | FALSE | 7 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145496 | HCFWF3Z3104 | F3 Z3 :Paint putty coat | 26143 | 2014-03-03 08:00 | 2014-03-13 16:00 | 10 | 56 | 100 | 100 | 0 | 8770 | 8770 | 8770 | 7565.7825 | 1 | 1.1592 | FALSE | FALSE | FALSE | 7 | FALSE | 0 | Green | Continue normal monitoring.
145497 | HCFWF3Z3120 | F3 Z3 :Gybsum Board Ceiling | 26143 | 2014-03-15 08:00 | 2014-03-30 16:00 | 15 | 56 | 100 | 100 | 0 | 20970 | 20970 | 20970 | 22311.8005 | 1 | 0.93986 | FALSE | FALSE | FALSE | 7 | FALSE | 0 | Green | Continue normal monitoring.
145498 | HCFWF3Z3136 | F3 Z3 :Plaster Second Layer | 26143 | 2013-12-04 08:00 | 2013-12-12 16:00 | 8 | 0 | 100 | 93 | -7 | 11320 | 11320 | 10527.6 | 9792.6953 | 0.93 | 1.075 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145499 | HCFWF3Z3123 | F3 Z3 :Steel Fire Rated Doors | 26144 | 2014-03-03 08:00 | 2014-03-13 16:00 | 10 | 232 | 100 | 81 | -19 | 10260 | 10260 | 8310.6 | 12037.3103 | 0.81 | 0.6904 | TRUE | TRUE | TRUE | 29 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145500 | HCFWF3Z3122 | F3 Z3 :Steel Doors | 26144 | 2014-03-15 08:00 | 2014-03-25 16:00 | 10 | 152 | 100 | 100 | 0 | 16760 | 16760 | 16760 | 16396.1372 | 1 | 1.0222 | FALSE | FALSE | FALSE | 19 | FALSE | 0 | Green | Continue normal monitoring.
145501 | HCFWF3Z3125 | F3 Z3 :Wooden Doors | 26144 | 2014-03-15 08:00 | 2014-03-25 16:00 | 10 | 152 | 100 | 100 | 0 | 12330 | 12330 | 12330 | 13254.4017 | 1 | 0.93026 | FALSE | FALSE | FALSE | 19 | FALSE | 0 | Green | Continue normal monitoring.
145502 | HCFWF3Z3141 | F3 Z3 :Metal Works | 26144 | 2014-03-03 08:00 | 2014-03-13 16:00 | 10 | 152 | 100 | 90 | -10 | 7050 | 7050 | 6345 | 6780.5358 | 0.9 | 0.93577 | FALSE | FALSE | FALSE | 19 | FALSE | 0 | Green | Continue normal monitoring.
145503 | HCFWF3Z3146 | F3 Z3 :Handrails & Railling | 26144 | 2014-03-12 08:00 | 2014-03-29 16:00 | 17 | 128 | 100 | 80 | -20 | 16218 | 16218 | 12974.4 | 18861.5349 | 0.8 | 0.68788 | TRUE | TRUE | TRUE | 16 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145504 | HCFWF3Z3127 | F3 Z3 :Epoxy Screed Finish | 26141 | 2013-11-25 08:00 | 2013-12-05 16:00 | 10 | 1200 | 100 | 98 | -2 | 17960 | 17960 | 17600.8 | 21634.6342 | 0.98 | 0.81355 | TRUE | FALSE | FALSE | 150 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145505 | HCFWF3Z3151 | F3 Z3 :Stone Flooring All types | 26141 | 2013-12-23 08:00 | 2014-01-07 16:00 | 15 | 440 | 100 | 100 | 0 | 26385 | 26385 | 26385 | 26634.5229 | 1 | 0.99063 | FALSE | FALSE | FALSE | 55 | FALSE | 0 | Green | Continue normal monitoring.
145506 | HCFWF3Z3130 | F3 Z3 :Aluminum & Stainless Steel Skirting | 26141 | 2014-01-06 08:00 | 2014-01-18 16:00 | 12 | 928 | 100 | 83 | -17 | 12240 | 12240 | 10159.2 | 14628.868 | 0.83 | 0.69446 | TRUE | TRUE | TRUE | 116 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145507 | HCFWF3Z3128 | F3 Z3 :Stainless steel Wire Cloth Finish For Elev Lobby | 26142 | 2014-02-05 08:00 | 2014-02-16 16:00 | 11 | 728 | 100 | 98 | -2 | 16676 | 16676 | 16342.48 | 15956.0971 | 0.98 | 1.0242 | FALSE | FALSE | FALSE | 91 | FALSE | 0 | Green | Continue normal monitoring.
145508 | HCFWF3Z3109 | F3 Z3 :Stone Decoration For Benches | 26144 | 2014-03-12 08:00 | 2014-03-23 16:00 | 11 | 488 | 100 | 100 | 0 | 16005 | 16005 | 16005 | 17027.1492 | 1 | 0.93997 | FALSE | FALSE | FALSE | 61 | FALSE | 0 | Green | Continue normal monitoring.
145509 | HCFWF3Z3132 | F3 Z3 :Mirror | 26144 | 2014-03-26 08:00 | 2014-04-06 16:00 | 11 | 392 | 100 | 100 | 0 | 13475 | 13475 | 13475 | 16082.4741 | 1 | 0.83787 | TRUE | FALSE | FALSE | 49 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145510 | HCFWF3Z3133 | F3 Z3 :Toilet & corian vanity tops | 26144 | 2014-03-26 08:00 | 2014-04-06 16:00 | 11 | 392 | 100 | 100 | 0 | 16643 | 16643 | 16643 | 16316.0073 | 1 | 1.02 | FALSE | FALSE | FALSE | 49 | FALSE | 0 | Green | Continue normal monitoring.
145511 | HCFWF3Z3138 | F3 Z3 :Carpet Tile Flooring | 26141 | 2013-12-23 08:00 | 2014-01-05 16:00 | 13 | 1008 | 100 | 90 | -10 | 13000 | 13000 | 11700 | 16011.0198 | 0.9 | 0.73075 | TRUE | FALSE | FALSE | 126 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145512 | HCFWF3Z3156 | F3 Z3 :Acoustical Ceiling | 26143 | 2014-03-03 08:00 | 2014-03-13 16:00 | 10 | 136 | 100 | 87 | -13 | 6160 | 6160 | 5359.2 | 5536.3111 | 0.87 | 0.96801 | FALSE | TRUE | TRUE | 17 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145513 | HCFWF3Z3114 | F3 Z3 :Stone Base Skirting | 26141 | 2014-01-08 08:00 | 2014-01-20 16:00 | 12 | 912 | 100 | 90 | -10 | 10620 | 10620 | 9558 | 9104.6325 | 0.9 | 1.0498 | FALSE | FALSE | FALSE | 114 | FALSE | 0 | Green | Continue normal monitoring.
145514 | HCFWF3Z1095 | F3 Z1 :Carpet Floor Tiles | 26240 | 2013-12-17 08:00 | 2013-12-29 16:00 | 12 | 1048 | 100 | 83 | -17 | 22404 | 22404 | 18595.32 | 27145.8994 | 0.83 | 0.68501 | TRUE | TRUE | TRUE | 131 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145515 | HCFWF3Z1124 | F3 Z1 :Gybsum Board Partitions | 26241 | 2013-03-25 08:00 | 2013-04-04 16:00 | 10 | 1136 | 100 | 96 | -4 | 10830 | 10830 | 10396.8 | 9502.886 | 0.96 | 1.0941 | FALSE | FALSE | FALSE | 142 | FALSE | 0 | Green | Continue normal monitoring.
145516 | HCFWF3Z1111 | F3 Z1 :Stone Flooring | 26240 | 2013-08-28 12:00 | 2013-09-11 12:00 | 14 | 628 | 100 | 100 | 0 | 12516 | 12516 | 12516 | 15604.3941 | 1 | 0.80208 | TRUE | FALSE | FALSE | 78.5 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145517 | HCFWF3Z1100 | F3 Z1 :Stone Cladding | 26241 | 2013-05-26 08:00 | 2013-06-05 16:00 | 10 | 1864 | 100 | 86 | -14 | 15870 | 15870 | 13648.2 | 19528.9673 | 0.86 | 0.69887 | TRUE | TRUE | TRUE | 233 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145518 | HCFWF3Z1116 | F3 Z1 :Glass Wall Cladding | 26241 | 2014-02-05 08:00 | 2014-02-23 16:00 | 18 | 200 | 100 | 87 | -13 | 21960 | 21960 | 19105.2 | 19869.5917 | 0.87 | 0.96153 | FALSE | TRUE | TRUE | 25 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145519 | HCFWF3Z1118 | F3 Z1 :Mirrors | 26243 | 2014-02-26 08:00 | 2014-03-09 16:00 | 11 | 584 | 100 | 82 | -18 | 6281 | 6281 | 5150.42 | 6689.4776 | 0.82 | 0.76993 | TRUE | TRUE | TRUE | 73 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145520 | HCFWF3Z1129 | F3 Z1 :Toilet & corian vanity tops | 26243 | 2014-02-26 08:00 | 2014-03-09 16:00 | 11 | 584 | 100 | 100 | 0 | 8503 | 8503 | 8503 | 7856.5009 | 1 | 1.0823 | FALSE | FALSE | FALSE | 73 | FALSE | 0 | Green | Continue normal monitoring.
145521 | HCFWF3Z2096 | F3 Z2 :Carpet Tiles | 26245 | 2013-12-17 08:00 | 2013-12-29 16:00 | 12 | 1048 | 100 | 81 | -19 | 22116 | 22116 | 17913.96 | 22586.2319 | 0.81 | 0.79314 | TRUE | TRUE | TRUE | 131 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145522 | HCFWF3Z2093 | F3 Z2 :Stone Flooring | 26245 | 2013-09-03 08:00 | 2013-09-16 16:00 | 13 | 592 | 100 | 100 | 0 | 10881 | 10881 | 10881 | 9516.1967 | 1 | 1.1434 | FALSE | FALSE | FALSE | 74 | FALSE | 0 | Green | Continue normal monitoring.
145523 | HCFWF3Z2099 | F3 Z2 :Glass Wall Cladding | 26137 | 2014-02-05 08:00 | 2014-02-23 16:00 | 18 | 296 | 100 | 94 | -6 | 34002 | 34002 | 31961.88 | 31947.2535 | 0.94 | 1.0005 | FALSE | FALSE | FALSE | 37 | FALSE | 0 | Green | Continue normal monitoring.
145524 | HCFWF3Z2098 | F3 Z2 :Gybsum Board Partitions | 26137 | 2013-05-21 08:00 | 2013-06-02 16:00 | 12 | 752 | 100 | 100 | 0 | 13272 | 13272 | 13272 | 13209.7426 | 1 | 1.0047 | FALSE | FALSE | FALSE | 94 | FALSE | 0 | Green | Continue normal monitoring.
145525 | HCFWF3Z3137 | F3 Z3 :Glass Wall Cladding | 26142 | 2014-02-05 08:00 | 2014-02-23 16:00 | 18 | 344 | 100 | 100 | 0 | 11970 | 11970 | 11970 | 12274.7442 | 1 | 0.97517 | FALSE | FALSE | FALSE | 43 | FALSE | 0 | Green | Continue normal monitoring.
145526 | HCFWF3Z3135 | F3 Z3 :Gybsum Board Partitions | 26142 | 2013-07-04 08:00 | 2013-07-15 16:00 | 11 | 456 | 100 | 100 | 0 | 5610 | 5610 | 5610 | 6962.0016 | 1 | 0.8058 | TRUE | FALSE | FALSE | 57 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145527 | HCFWF3Z3119 | F3 Z3 :Stone Cladding | 26142 | 2014-02-05 08:00 | 2014-02-16 16:00 | 11 | 728 | 100 | 84 | -16 | 20064 | 20064 | 16853.76 | 23538.0065 | 0.84 | 0.71602 | TRUE | TRUE | TRUE | 91 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145528 | HCFWF3Z3140 | F3 Z3 :Glass Doors | 26144 | 2014-03-03 08:00 | 2014-03-13 16:00 | 10 | 552 | 100 | 100 | 0 | 12280 | 12280 | 12280 | 14060.1576 | 1 | 0.87339 | TRUE | FALSE | FALSE | 69 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145529 | HCFWF3Z1117 | F3 Z1 :Acoustical Ceiling | 26242 | 2014-02-04 08:00 | 2014-02-15 16:00 | 11 | 368 | 100 | 80 | -20 | 14300 | 14300 | 11440 | 15226.8763 | 0.8 | 0.7513 | TRUE | TRUE | TRUE | 46 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145530 | HCFWF3Z1134 | F3 Z1 :Stone Base Skirting | 26240 | 2013-09-11 12:00 | 2013-09-23 12:00 | 12 | 1428 | 100 | 100 | 0 | 7212 | 7212 | 7212 | 8553.4255 | 1 | 0.84317 | TRUE | FALSE | FALSE | 178.5 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145531 | HCFWF4Z1122 | F4 Z1 :Trawelled smooth Concrete screed | 26147 | 2013-07-13 12:00 | 2013-07-22 12:00 | 9 | 800 | 100 | 83 | -17 | 17532 | 17532 | 14551.56 | 17281.8032 | 0.83 | 0.84202 | TRUE | TRUE | TRUE | 100 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145532 | HCFWF4Z1123 | F4 Z1 :Block Works | 26148 | 2013-04-06 08:00 | 2013-04-16 16:00 | 10 | 792 | 100 | 94 | -6 | 19150 | 19150 | 18001 | 21707.6672 | 0.94 | 0.82925 | TRUE | FALSE | FALSE | 99 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145533 | HCFWF4Z1105 | F4 Z1 :Plaster First Layer | 26148 | 2013-05-26 08:00 | 2013-06-04 14:00 | 9 | 800 | 100 | 99 | -1 | 11502 | 11502 | 11386.98 | 14348.9013 | 0.99 | 0.79358 | TRUE | FALSE | FALSE | 100 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145534 | HCFWF4Z1121 | F4 Z1 :Foam Concrete Under Floorings | 26147 | 2013-06-24 12:00 | 2013-07-13 12:00 | 19 | 800 | 100 | 98 | -2 | 13547 | 13547 | 13276.06 | 13219.8611 | 0.98 | 1.0043 | FALSE | FALSE | FALSE | 100 | FALSE | 0 | Green | Continue normal monitoring.
145535 | HCFWF4Z1127 | F4 Z1 :Plaster Final Layer | 26148 | 2013-06-13 14:00 | 2013-06-24 12:00 | 10 | 800 | 100 | 82 | -18 | 16110 | 16110 | 13210.2 | 18036.869 | 0.82 | 0.7324 | TRUE | TRUE | TRUE | 100 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145536 | HCFWF4Z1128 | F4 Z1 :Paint Prime coat | 26148 | 2013-06-24 12:00 | 2013-07-08 12:00 | 14 | 1580 | 100 | 99 | -1 | 12600 | 12600 | 12474 | 14965.3469 | 0.99 | 0.83353 | TRUE | FALSE | FALSE | 197.5 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145537 | HCFWF4Z1139 | F4 Z1 :Paint putty coat | 26148 | 2014-03-10 08:00 | 2014-03-23 16:00 | 13 | 296 | 100 | 90 | -10 | 14131 | 14131 | 12717.9 | 17187.8608 | 0.9 | 0.73994 | TRUE | FALSE | FALSE | 37 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145538 | HCFWF4Z1132 | F4 Z1 :Plaster First Layer | 26149 | 2013-08-28 12:00 | 2013-09-08 10:00 | 10 | 568 | 100 | 96 | -4 | 13880 | 13880 | 13324.8 | 15783.9623 | 0.96 | 0.8442 | TRUE | FALSE | FALSE | 71 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145539 | HCFWF4Z1144 | F4 Z1 :Plaster Final Layer | 26149 | 2013-09-17 10:00 | 2013-09-26 16:00 | 9 | 568 | 100 | 100 | 0 | 14121 | 14121 | 14121 | 13604.781 | 1 | 1.0379 | FALSE | FALSE | FALSE | 71 | FALSE | 0 | Green | Continue normal monitoring.
145540 | HCFWF4Z1110 | F4 Z1 :Paint Prime coat | 26149 | 2013-09-28 08:00 | 2013-10-08 16:00 | 10 | 1064 | 100 | 100 | 0 | 19860 | 19860 | 19860 | 19472.9854 | 1 | 1.0199 | FALSE | FALSE | FALSE | 133 | FALSE | 0 | Green | Continue normal monitoring.
145541 | HCFWF4Z1126 | F4 Z1 :Paint putty coat | 26149 | 2013-10-09 08:00 | 2013-10-24 16:00 | 15 | 1064 | 100 | 92 | -8 | 16365 | 16365 | 15055.8 | 14046.1321 | 0.92 | 1.0719 | FALSE | FALSE | FALSE | 133 | FALSE | 0 | Green | Continue normal monitoring.
145542 | HCFWF4Z1149 | F4 Z1 :Steel Fire Rated Doors | 26308 | 2014-02-09 08:00 | 2014-02-19 16:00 | 10 | 464 | 100 | 90 | -10 | 18330 | 18330 | 16497 | 21159.316 | 0.9 | 0.77966 | TRUE | FALSE | FALSE | 58 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145543 | HCFWF4Z1133 | F4 Z1 :Rubber Flooring | 26147 | 2013-09-28 08:00 | 2013-10-08 16:00 | 10 | 592 | 100 | 81 | -19 | 16090 | 16090 | 13032.9 | 13951.5721 | 0.81 | 0.93415 | FALSE | TRUE | TRUE | 74 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145544 | HCFWF4Z1154 | F4 Z1 :Rubber Skirting | 26147 | 2014-01-08 08:00 | 2014-01-09 16:00 | 1 | 720 | 100 | 88 | -12 | 591 | 591 | 520.08 | 706.7538 | 0.88 | 0.73587 | TRUE | TRUE | TRUE | 90 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145545 | HCFWF4Z1115 | F4 Z1 :Steel Doors | 26308 | 2014-02-20 08:00 | 2014-03-03 16:00 | 11 | 384 | 100 | 100 | 0 | 12892 | 12892 | 12892 | 11570.1091 | 1 | 1.1143 | FALSE | FALSE | FALSE | 48 | FALSE | 0 | Green | Continue normal monitoring.
145546 | HCFWF4Z1137 | F4 Z1 :Wooden Doors | 26308 | 2014-02-26 08:00 | 2014-03-09 16:00 | 11 | 344 | 100 | 81 | -19 | 13343 | 13343 | 10807.83 | 12258.8893 | 0.81 | 0.88163 | TRUE | TRUE | TRUE | 43 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145547 | HCFWF4Z1142 | F4 Z1 :Gybsum Board Ceiling | 26149 | 2014-02-20 08:00 | 2014-03-08 16:00 | 16 | 288 | 100 | 100 | 0 | 22960 | 22960 | 22960 | 23892.4191 | 1 | 0.96097 | FALSE | FALSE | FALSE | 36 | FALSE | 0 | Green | Continue normal monitoring.
145548 | HCFWF4Z1138 | F4 Z1 :Metal Works | 26308 | 2014-02-09 08:00 | 2014-02-19 16:00 | 10 | 304 | 100 | 88 | -12 | 7410 | 7410 | 6520.8 | 8485.5776 | 0.88 | 0.76846 | TRUE | TRUE | TRUE | 38 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145549 | HCFWF4Z1131 | F4 Z1 :Handrails & Railling | 26308 | 2014-03-16 08:00 | 2014-04-01 16:00 | 16 | 224 | 100 | 88 | -12 | 8016 | 8016 | 7054.08 | 7259.2967 | 0.88 | 0.97173 | FALSE | TRUE | TRUE | 28 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145550 | HCFWF4Z1136 | F4 Z1 :Plaster Second Layer | 26148 | 2013-06-04 14:00 | 2013-06-13 14:00 | 9 | 800 | 100 | 87 | -13 | 6516 | 6516 | 5668.92 | 6685.6013 | 0.87 | 0.84793 | TRUE | TRUE | TRUE | 100 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145551 | HCFWF4Z1143 | F4 Z1 :Plaster Second Layer | 26149 | 2013-09-08 10:00 | 2013-09-17 10:00 | 9 | 568 | 100 | 96 | -4 | 11700 | 11700 | 11232 | 12204.744 | 0.96 | 0.9203 | FALSE | FALSE | FALSE | 71 | FALSE | 0 | Green | Continue normal monitoring.
145552 | HCFWF4Z2102 | F4 Z2 :Trawelled smooth Concrete screed | 26311 | 2013-09-22 08:00 | 2013-09-30 16:00 | 8 | 464 | 100 | 80 | -20 | 8704 | 8704 | 6963.2 | 8137.4937 | 0.8 | 0.85569 | TRUE | TRUE | TRUE | 58 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145553 | HCFWF4Z2101 | F4 Z2 :Foam Concrete Under Floorings | 26311 | 2013-09-03 08:00 | 2013-09-21 16:00 | 18 | 464 | 100 | 100 | 0 | 11070 | 11070 | 11070 | 9921.1925 | 1 | 1.1158 | FALSE | FALSE | FALSE | 58 | FALSE | 0 | Green | Continue normal monitoring.
145554 | HCFWF4Z2104 | F4 Z2 :Rubber Flooring | 26311 | 2013-11-03 08:00 | 2013-11-14 16:00 | 11 | 1088 | 100 | 100 | 0 | 15587 | 15587 | 15587 | 18463.8672 | 1 | 0.84419 | TRUE | FALSE | FALSE | 136 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145555 | HCFWF4Z2105 | F4 Z2 :Rubber Skirting | 26311 | 2014-01-11 08:00 | 2014-01-12 16:00 | 1 | 720 | 100 | 90 | -10 | 1626 | 1626 | 1463.4 | 1708.9037 | 0.9 | 0.85634 | TRUE | FALSE | FALSE | 90 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145556 | HCFWF4Z2107 | F4 Z2 :Block Works | 26153 | 2013-06-03 08:00 | 2013-06-13 16:00 | 10 | 758 | 100 | 87 | -13 | 6930 | 6930 | 6029.1 | 5930.3648 | 0.87 | 1.0166 | FALSE | TRUE | TRUE | 94.75 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145557 | HCFWF4Z2109 | F4 Z2 :Plaster First Layer | 26153 | 2013-08-03 08:00 | 2013-08-14 16:00 | 11 | 464 | 100 | 89 | -11 | 18579 | 18579 | 16535.31 | 21759.5858 | 0.89 | 0.75991 | TRUE | TRUE | TRUE | 58 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145558 | HCFWF4Z2106 | F4 Z2 :Plaster Final Layer | 26153 | 2013-08-25 08:00 | 2013-09-02 16:00 | 8 | 464 | 100 | 100 | 0 | 10960 | 10960 | 10960 | 13615.8 | 1 | 0.80495 | TRUE | FALSE | FALSE | 58 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145559 | HCFWF4Z2112 | F4 Z2 :Paint Prime coat | 26153 | 2013-09-21 14:00 | 2013-10-05 14:00 | 14 | 946 | 100 | 86 | -14 | 8246 | 8246 | 7091.56 | 9007.687 | 0.86 | 0.78728 | TRUE | TRUE | TRUE | 118.25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145560 | HCFWF4Z2103 | F4 Z2 :Paint putty coat | 26153 | 2013-10-09 14:00 | 2013-10-28 14:00 | 19 | 1266 | 100 | 82 | -18 | 11799 | 11799 | 9675.18 | 12406.4521 | 0.82 | 0.77985 | TRUE | TRUE | TRUE | 158.25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145561 | HCFWF4Z2110 | F4 Z2 :Plaster Second Layer | 26153 | 2013-08-15 08:00 | 2013-08-24 16:00 | 9 | 464 | 100 | 82 | -18 | 5778 | 5778 | 4737.96 | 6941.4947 | 0.82 | 0.68256 | TRUE | TRUE | TRUE | 58 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145562 | HCFWF4Z2115 | F4 Z2 :Plaster First Layer | 26154 | 2013-10-01 08:00 | 2013-10-09 16:00 | 8 | 464 | 100 | 97 | -3 | 11944 | 11944 | 11585.68 | 14703.1442 | 0.97 | 0.78797 | TRUE | FALSE | FALSE | 58 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145563 | HCFWF4Z2117 | F4 Z2 :Plaster Final Layer | 26154 | 2013-10-24 08:00 | 2013-11-02 16:00 | 9 | 464 | 100 | 84 | -16 | 5445 | 5445 | 4573.8 | 6271.6314 | 0.84 | 0.72928 | TRUE | TRUE | TRUE | 58 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145564 | HCFWF4Z2108 | F4 Z2 :Paint Prime coat | 26154 | 2013-11-03 08:00 | 2013-11-14 16:00 | 11 | 848 | 100 | 91 | -9 | 15246 | 15246 | 13873.86 | 15675.6501 | 0.91 | 0.88506 | TRUE | FALSE | FALSE | 106 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145565 | HCFWF4Z2114 | F4 Z2 :Paint putty coat | 26154 | 2013-11-16 08:00 | 2013-11-26 16:00 | 10 | 848 | 100 | 91 | -9 | 9270 | 9270 | 8435.7 | 10075.4569 | 0.91 | 0.83725 | TRUE | FALSE | FALSE | 106 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145566 | HCFWF4Z2120 | F4 Z2 :Gybsum Board Ceiling | 26154 | 2014-02-19 08:00 | 2014-03-06 16:00 | 15 | 296 | 100 | 98 | -2 | 27420 | 27420 | 26871.6 | 30994.8591 | 0.98 | 0.86697 | TRUE | FALSE | FALSE | 37 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145567 | HCFWF4Z2111 | F4 Z2 :Plaster Second Layer | 26154 | 2013-10-10 08:00 | 2013-10-23 16:00 | 13 | 464 | 100 | 100 | 0 | 10608 | 10608 | 10608 | 9841.1416 | 1 | 1.0779 | FALSE | FALSE | FALSE | 58 | FALSE | 0 | Green | Continue normal monitoring.
145568 | HCFWF4Z2113 | F4 Z2 :Steel Fire Rated Doors | 26155 | 2014-03-04 08:00 | 2014-03-15 16:00 | 11 | 304 | 100 | 85 | -15 | 12474 | 12474 | 10602.9 | 12834.2543 | 0.85 | 0.82614 | TRUE | TRUE | TRUE | 38 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145569 | HCFWF4Z2122 | F4 Z2 :Steel Doors | 26155 | 2014-03-04 08:00 | 2014-03-15 16:00 | 11 | 304 | 100 | 81 | -19 | 5588 | 5588 | 4526.28 | 6604.6165 | 0.81 | 0.68532 | TRUE | TRUE | TRUE | 38 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145570 | HCFWF4Z2119 | F4 Z2 :Wooden Doors | 26155 | 2014-03-04 08:00 | 2014-03-15 16:00 | 11 | 384 | 100 | 91 | -9 | 14003 | 14003 | 12742.73 | 15569.7976 | 0.91 | 0.81843 | TRUE | FALSE | FALSE | 48 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145571 | HCFWF4Z2116 | F4 Z2 :Metal Works | 26155 | 2014-02-20 08:00 | 2014-03-03 16:00 | 11 | 304 | 100 | 98 | -2 | 17556 | 17556 | 17204.88 | 17810.2394 | 0.98 | 0.96601 | FALSE | FALSE | FALSE | 38 | FALSE | 0 | Green | Continue normal monitoring.
145572 | HCFWF4Z2125 | F4 Z2 :Handrails & Railling | 26155 | 2014-03-22 08:00 | 2014-04-05 16:00 | 14 | 208 | 100 | 84 | -16 | 26348 | 26348 | 22132.32 | 29387.1104 | 0.84 | 0.75313 | TRUE | TRUE | TRUE | 26 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145573 | HCFWF4Z3142 | F4 Z3 :Trawelled smooth Concrete screed | 26156 | 2013-12-14 08:00 | 2013-12-22 16:00 | 8 | 0 | 100 | 91 | -9 | 5776 | 5776 | 5256.16 | 5182.7411 | 0.91 | 1.0142 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145574 | HCFWF4Z3161 | F4 Z3 :Foam Concrete Under Floorings | 26156 | 2013-11-25 08:00 | 2013-12-12 16:00 | 17 | 0 | 100 | 100 | 0 | 32963 | 32963 | 32963 | 33312.3763 | 1 | 0.98951 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145575 | HCFWF4Z3143 | F4 Z3 :Rubber Flooring | 26156 | 2014-01-23 08:00 | 2014-02-03 16:00 | 11 | 296 | 100 | 100 | 0 | 11572 | 11572 | 11572 | 13507.4334 | 1 | 0.85671 | TRUE | FALSE | FALSE | 37 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145576 | HCFWF4Z3124 | F4 Z3 :Rubber Skirting | 26156 | 2014-02-04 08:00 | 2014-02-05 16:00 | 1 | 576 | 100 | 96 | -4 | 1893 | 1893 | 1817.28 | 1776.0193 | 0.96 | 1.0232 | FALSE | FALSE | FALSE | 72 | FALSE | 0 | Green | Continue normal monitoring.
145577 | HCFWF4Z3166 | F4 Z3 :Block Works | 26157 | 2013-08-03 08:00 | 2013-08-17 16:00 | 14 | 448 | 100 | 100 | 0 | 17010 | 17010 | 17010 | 15723.7821 | 1 | 1.0818 | FALSE | FALSE | FALSE | 56 | FALSE | 0 | Green | Continue normal monitoring.
145578 | HCFWF4Z3147 | F4 Z3 :Plaster First Layer | 26157 | 2013-10-27 08:00 | 2013-11-04 16:00 | 8 | 0 | 100 | 96 | -4 | 14296 | 14296 | 13724.16 | 17588.7614 | 0.96 | 0.78028 | TRUE | FALSE | FALSE | 0 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145579 | HCFWF4Z3129 | F4 Z3 :Plaster Final Layer | 26157 | 2013-11-16 08:00 | 2013-11-24 16:00 | 8 | 0 | 100 | 89 | -11 | 14728 | 14728 | 13107.92 | 13755.3489 | 0.89 | 0.95293 | FALSE | TRUE | TRUE | 0 | TRUE | 4 | Orange | Develop recovery plan and review schedule and cost exposure.
145580 | HCFWF4Z3145 | F4 Z3 :Paint Prime coat | 26157 | 2013-11-25 08:00 | 2013-12-08 16:00 | 13 | 560 | 100 | 100 | 0 | 20891 | 20891 | 20891 | 19937.69 | 1 | 1.0478 | FALSE | FALSE | FALSE | 70 | FALSE | 0 | Green | Continue normal monitoring.
145581 | HCFWF4Z3171 | F4 Z3 :Paint putty coat | 26157 | 2014-02-19 08:00 | 2014-03-04 16:00 | 13 | 88 | 100 | 100 | 0 | 23933 | 23933 | 23933 | 29625.3773 | 1 | 0.80785 | TRUE | FALSE | FALSE | 11 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145582 | HCFWF4Z3148 | F4 Z3 :Plaster Second Layer | 26157 | 2013-11-06 08:00 | 2013-11-14 16:00 | 8 | 0 | 100 | 96 | -4 | 4880 | 4880 | 4684.8 | 5582.1511 | 0.96 | 0.83925 | TRUE | FALSE | FALSE | 0 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145583 | HCFWF4Z3150 | F4 Z3 :Plaster First Layer | 26158 | 2013-12-23 08:00 | 2014-01-02 16:00 | 10 | 0 | 100 | 94 | -6 | 7500 | 7500 | 7050 | 8473.7896 | 0.94 | 0.83198 | TRUE | FALSE | FALSE | 0 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145584 | HCFWF4Z3152 | F4 Z3 :Plaster Final Layer | 26158 | 2014-01-13 08:00 | 2014-01-22 16:00 | 9 | 0 | 100 | 91 | -9 | 7938 | 7938 | 7223.58 | 9455.5119 | 0.91 | 0.76395 | TRUE | FALSE | FALSE | 0 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145585 | HCFWF4Z3153 | F4 Z3 :Paint Prime coat | 26158 | 2014-01-23 08:00 | 2014-02-03 16:00 | 11 | 352 | 100 | 100 | 0 | 5566 | 5566 | 5566 | 4988.9685 | 1 | 1.1157 | FALSE | FALSE | FALSE | 44 | FALSE | 0 | Green | Continue normal monitoring.
145586 | HCFWF4Z3134 | F4 Z3 :Paint putty coat | 26158 | 2014-02-04 08:00 | 2014-02-15 16:00 | 11 | 352 | 100 | 95 | -5 | 10538 | 10538 | 10011.1 | 11933.0467 | 0.95 | 0.83894 | TRUE | FALSE | FALSE | 44 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145587 | HCFWF4Z3155 | F4 Z3 :Gybsum Board Ceiling | 26158 | 2014-03-31 08:00 | 2014-04-15 16:00 | 15 | 56 | 100 | 100 | 0 | 24105 | 24105 | 24105 | 25345.8156 | 1 | 0.95104 | FALSE | FALSE | FALSE | 7 | FALSE | 0 | Green | Continue normal monitoring.
145588 | HCFWF4Z3176 | F4 Z3 :Plaster Second Layer | 26158 | 2014-01-04 08:00 | 2014-01-12 16:00 | 8 | 0 | 100 | 98 | -2 | 5656 | 5656 | 5542.88 | 6683.4704 | 0.98 | 0.82934 | TRUE | FALSE | FALSE | 0 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145589 | HCFWF4Z3158 | F4 Z3 :Steel Fire Rated Doors | 26159 | 2014-03-15 08:00 | 2014-03-25 16:00 | 10 | 232 | 100 | 87 | -13 | 13990 | 13990 | 12171.3 | 14735.0611 | 0.87 | 0.82601 | TRUE | TRUE | TRUE | 29 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145590 | HCFWF4Z3157 | F4 Z3 :Steel Doors | 26159 | 2014-03-26 08:00 | 2014-04-06 16:00 | 11 | 152 | 100 | 100 | 0 | 21043 | 21043 | 21043 | 23107.2455 | 1 | 0.91067 | FALSE | FALSE | FALSE | 19 | FALSE | 0 | Green | Continue normal monitoring.
145591 | HCFWF4Z3160 | F4 Z3 :Wooden Doors | 26159 | 2014-03-26 08:00 | 2014-04-06 16:00 | 11 | 152 | 100 | 100 | 0 | 20207 | 20207 | 20207 | 21037.4441 | 1 | 0.96053 | FALSE | FALSE | FALSE | 19 | FALSE | 0 | Green | Continue normal monitoring.
145592 | HCFWF4Z3181 | F4 Z3 :Metal Works | 26159 | 2014-03-15 08:00 | 2014-03-25 16:00 | 10 | 152 | 100 | 96 | -4 | 5210 | 5210 | 5001.6 | 5424.9832 | 0.96 | 0.92196 | FALSE | FALSE | FALSE | 19 | FALSE | 0 | Green | Continue normal monitoring.
145593 | HCFWF4Z3186 | F4 Z3 :Handrails & Railling | 26159 | 2014-03-30 08:00 | 2014-04-15 16:00 | 16 | 128 | 100 | 100 | 0 | 14544 | 14544 | 14544 | 16830.1421 | 1 | 0.86416 | TRUE | FALSE | FALSE | 16 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145594 | HCFWF4Z3162 | F4 Z3 :Epoxy Screed Finish | 26156 | 2013-12-23 08:00 | 2014-01-05 16:00 | 13 | 1008 | 100 | 84 | -16 | 18122 | 18122 | 15222.48 | 19960.0521 | 0.84 | 0.76265 | TRUE | TRUE | TRUE | 126 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145595 | HCFWF4Z3191 | F4 Z3 :Stone Flooring All types | 26156 | 2014-01-23 08:00 | 2014-02-05 16:00 | 13 | 296 | 100 | 100 | 0 | 13182 | 13182 | 13182 | 14543.7702 | 1 | 0.90637 | FALSE | FALSE | FALSE | 37 | FALSE | 0 | Green | Continue normal monitoring.
145596 | HCFWF4Z3165 | F4 Z3 :Aluminum & Stainless Steel Skirting | 26156 | 2014-02-04 08:00 | 2014-02-15 16:00 | 11 | 736 | 100 | 95 | -5 | 18150 | 18150 | 17242.5 | 18696.5508 | 0.95 | 0.92223 | FALSE | FALSE | FALSE | 92 | FALSE | 0 | Green | Continue normal monitoring.
145597 | HCFWF4Z3163 | F4 Z3 :Stainless steel Wire Cloth Finish For Elev Lobby | 26157 | 2014-02-19 08:00 | 2014-03-02 16:00 | 11 | 632 | 100 | 85 | -15 | 14388 | 14388 | 12229.8 | 15286.4414 | 0.85 | 0.80004 | TRUE | TRUE | TRUE | 79 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145598 | HCFWF4Z3139 | F4 Z3 :Stone Decoration For Benches | 26159 | 2014-03-30 08:00 | 2014-04-09 16:00 | 10 | 368 | 100 | 87 | -13 | 13730 | 13730 | 11945.1 | 15765.9814 | 0.87 | 0.75765 | TRUE | TRUE | TRUE | 46 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145599 | HCFWF4Z3167 | F4 Z3 :Mirror | 26159 | 2014-04-07 08:00 | 2014-04-17 16:00 | 10 | 312 | 100 | 100 | 0 | 5130 | 5130 | 5130 | 6055.3308 | 1 | 0.84719 | TRUE | FALSE | FALSE | 39 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145600 | HCFWF4Z3168 | F4 Z3 :Toilet & corian vanity tops | 26159 | 2014-04-07 08:00 | 2014-04-17 16:00 | 10 | 312 | 100 | 97 | -3 | 14700 | 14700 | 14259 | 16590.781 | 0.97 | 0.85945 | TRUE | FALSE | FALSE | 39 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145601 | HCFWF4Z3173 | F4 Z3 :Carpet Tile Flooring | 26156 | 2014-01-23 08:00 | 2014-02-03 16:00 | 11 | 816 | 100 | 100 | 0 | 16247 | 16247 | 16247 | 19815.3155 | 1 | 0.81992 | TRUE | FALSE | FALSE | 102 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145602 | HCFWF4Z3196 | F4 Z3 :Acoustical Ceiling | 26158 | 2014-02-04 08:00 | 2014-02-15 16:00 | 11 | 432 | 100 | 91 | -9 | 16643 | 16643 | 15145.13 | 19607.6115 | 0.91 | 0.77241 | TRUE | FALSE | FALSE | 54 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145603 | HCFWF4Z3144 | F4 Z3 :Stone Base Skirting | 26156 | 2014-02-06 08:00 | 2014-02-17 16:00 | 11 | 720 | 100 | 94 | -6 | 16885 | 16885 | 15871.9 | 18147.078 | 0.94 | 0.87463 | TRUE | FALSE | FALSE | 90 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145604 | HCFWF4Z5162 | F4 Z5 :Trawelled smooth Concrete screed | 26160 | 2013-10-23 12:00 | 2013-11-02 12:00 | 10 | 246 | 100 | 100 | 0 | 5860 | 5860 | 5860 | 6554.7758 | 1 | 0.894 | TRUE | FALSE | FALSE | 30.75 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145605 | HCFWF4Z5161 | F4 Z5 :Foam Concrete Under Floorings | 26160 | 2013-09-30 12:00 | 2013-10-23 12:00 | 23 | 246 | 100 | 100 | 0 | 32384 | 32384 | 32384 | 39525.4269 | 1 | 0.81932 | TRUE | FALSE | FALSE | 30.75 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145606 | HCFWF4Z5167 | F4 Z5 :Rubber Flooring | 26160 | 2013-12-10 14:00 | 2013-12-22 14:00 | 12 | 378 | 100 | 88 | -12 | 21888 | 21888 | 19261.44 | 24025.7401 | 0.88 | 0.8017 | TRUE | TRUE | TRUE | 47.25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145607 | HCFWF4Z5145 | F4 Z5 :Rubber Skirting | 26160 | 2014-02-09 08:00 | 2014-02-10 16:00 | 1 | 576 | 100 | 92 | -8 | 1766 | 1766 | 1624.72 | 2083.7436 | 0.92 | 0.77971 | TRUE | FALSE | FALSE | 72 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145608 | HCFWF4Z5163 | F4 Z5 :Block Works | 26161 | 2013-08-20 08:00 | 2013-08-31 16:00 | 11 | 246 | 100 | 100 | 0 | 6831 | 6831 | 6831 | 7688.4558 | 1 | 0.88847 | TRUE | FALSE | FALSE | 30.75 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145609 | HCFWF4Z5150 | F4 Z5 :Plaster First Layer | 26161 | 2013-09-01 08:00 | 2013-09-10 14:00 | 9 | 246 | 100 | 94 | -6 | 15030 | 15030 | 14128.2 | 16093.7414 | 0.94 | 0.87787 | TRUE | FALSE | FALSE | 30.75 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145610 | HCFWF4Z5172 | F4 Z5 :Plaster Final Layer | 26161 | 2013-09-19 14:00 | 2013-09-30 12:00 | 10 | 246 | 100 | 89 | -11 | 12490 | 12490 | 11116.1 | 11824.7236 | 0.89 | 0.94007 | FALSE | TRUE | TRUE | 30.75 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145611 | HCFWF4Z5168 | F4 Z5 :Paint Prime coat | 26161 | 2013-09-30 12:00 | 2013-10-14 12:00 | 14 | 980 | 100 | 95 | -5 | 26306 | 26306 | 24990.7 | 26842.6163 | 0.95 | 0.93101 | FALSE | FALSE | FALSE | 122.5 | FALSE | 0 | Green | Continue normal monitoring.
145612 | HCFWF4Z5144 | F4 Z5 :Paint putty coat | 26161 | 2013-10-14 12:00 | 2013-11-02 12:00 | 19 | 1428 | 100 | 86 | -14 | 22496 | 22496 | 19346.56 | 27829.737 | 0.86 | 0.69518 | TRUE | TRUE | TRUE | 178.5 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145613 | HCFWF4Z5166 | F4 Z5 :Plaster Second Layer | 26161 | 2013-09-10 14:00 | 2013-09-19 14:00 | 9 | 246 | 100 | 96 | -4 | 7272 | 7272 | 6981.12 | 8094.5079 | 0.96 | 0.86245 | TRUE | FALSE | FALSE | 30.75 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145614 | HCFWF4Z5149 | F4 Z5 :Plaster First Layer | 26162 | 2013-11-02 12:00 | 2013-11-13 10:00 | 10 | 246 | 100 | 100 | 0 | 11940 | 11940 | 11940 | 12844.5523 | 1 | 0.92958 | FALSE | FALSE | FALSE | 30.75 | FALSE | 0 | Green | Continue normal monitoring.
145615 | HCFWF4Z5171 | F4 Z5 :Plaster Final Layer | 26162 | 2013-11-23 10:00 | 2013-12-10 14:00 | 17 | 246 | 100 | 100 | 0 | 13379 | 13379 | 13379 | 16364.9607 | 1 | 0.81754 | TRUE | FALSE | FALSE | 30.75 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145616 | HCFWF4Z5177 | F4 Z5 :Paint Prime coat | 26162 | 2013-12-10 14:00 | 2013-12-22 14:00 | 12 | 626 | 100 | 100 | 0 | 9672 | 9672 | 9672 | 10490.2968 | 1 | 0.92199 | FALSE | FALSE | FALSE | 78.25 | FALSE | 0 | Green | Continue normal monitoring.
145617 | HCFWF4Z5173 | F4 Z5 :Paint putty coat | 26162 | 2013-12-22 14:00 | 2014-01-05 14:00 | 14 | 626 | 100 | 100 | 0 | 19782 | 19782 | 19782 | 20977.4858 | 1 | 0.94301 | FALSE | FALSE | FALSE | 78.25 | FALSE | 0 | Green | Continue normal monitoring.
145618 | HCFWF4Z5154 | F4 Z5 :Gybsum Board Ceiling | 26162 | 2014-02-18 12:00 | 2014-03-06 12:00 | 16 | 332 | 100 | 100 | 0 | 18576 | 18576 | 18576 | 21431.5834 | 1 | 0.86676 | TRUE | FALSE | FALSE | 41.5 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145619 | HCFWF4Z5155 | F4 Z5 :Plaster Second Layer | 26162 | 2013-11-13 10:00 | 2013-11-23 10:00 | 10 | 246 | 100 | 86 | -14 | 10480 | 10480 | 9012.8 | 11895.4943 | 0.86 | 0.75767 | TRUE | TRUE | TRUE | 30.75 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145620 | HCFWF4Z5182 | F4 Z5 :Steel Fire Rated Doors | 26163 | 2014-02-02 12:00 | 2014-02-13 12:00 | 11 | 508 | 100 | 93 | -7 | 20625 | 20625 | 19181.25 | 19124.8201 | 0.93 | 1.003 | FALSE | FALSE | FALSE | 63.5 | FALSE | 0 | Green | Continue normal monitoring.
145621 | HCFWF4Z5178 | F4 Z5 :Steel Doors | 26163 | 2014-02-13 12:00 | 2014-02-25 12:00 | 12 | 428 | 100 | 94 | -6 | 9732 | 9732 | 9148.08 | 10106.9089 | 0.94 | 0.90513 | FALSE | FALSE | FALSE | 53.5 | FALSE | 0 | Green | Continue normal monitoring.
145622 | HCFWF4Z5160 | F4 Z5 :Wooden Doors | 26163 | 2014-02-13 12:00 | 2014-02-25 12:00 | 12 | 588 | 100 | 100 | 0 | 16464 | 16464 | 16464 | 17106.1977 | 1 | 0.96246 | FALSE | FALSE | FALSE | 73.5 | FALSE | 0 | Green | Continue normal monitoring.
145623 | HCFWF4Z5176 | F4 Z5 :Metal Works | 26163 | 2014-02-02 12:00 | 2014-02-13 12:00 | 11 | 428 | 100 | 86 | -14 | 17402 | 17402 | 14965.72 | 17424.4452 | 0.86 | 0.85889 | TRUE | TRUE | TRUE | 53.5 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145624 | HCFWF4Z5181 | F4 Z5 :Handrails & Railling | 26163 | 2014-02-08 12:00 | 2014-02-25 12:00 | 17 | 468 | 100 | 88 | -12 | 24191 | 24191 | 21288.08 | 25567.8887 | 0.88 | 0.83261 | TRUE | TRUE | TRUE | 58.5 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145625 | HCFWF4Z5159 | F4 Z5 :Stone Decoration For Benches | 26163 | 2014-02-08 12:00 | 2014-02-19 12:00 | 11 | 708 | 100 | 98 | -2 | 13794 | 13794 | 13518.12 | 14004.2614 | 0.98 | 0.96529 | FALSE | FALSE | FALSE | 88.5 | FALSE | 0 | Green | Continue normal monitoring.
145626 | HCFWF4Z5187 | F4 Z5 :Mirror | 26163 | 2014-02-25 12:00 | 2014-03-09 12:00 | 12 | 588 | 100 | 95 | -5 | 6408 | 6408 | 6087.6 | 5957.7624 | 0.95 | 1.0218 | FALSE | FALSE | FALSE | 73.5 | FALSE | 0 | Green | Continue normal monitoring.
145627 | HCFWF4Z5183 | F4 Z5 :Toilet & corian vanity tops | 26163 | 2014-02-25 12:00 | 2014-03-09 12:00 | 12 | 588 | 100 | 87 | -13 | 11328 | 11328 | 9855.36 | 11497.315 | 0.87 | 0.85719 | TRUE | TRUE | TRUE | 73.5 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145628 | HCFWF4Z5192 | F4 Z5 :Carpet Tile Flooring | 26160 | 2013-12-17 08:00 | 2013-12-29 16:00 | 12 | 352 | 100 | 97 | -3 | 7104 | 7104 | 6890.88 | 6243.7822 | 0.97 | 1.1036 | FALSE | FALSE | FALSE | 44 | FALSE | 0 | Green | Continue normal monitoring.
145629 | HCFWF4Z5165 | F4 Z5 :Acoustical Ceiling | 26162 | 2013-12-22 14:00 | 2014-01-05 14:00 | 14 | 706 | 100 | 100 | 0 | 24220 | 24220 | 24220 | 26165.2134 | 1 | 0.92566 | FALSE | FALSE | FALSE | 88.25 | FALSE | 0 | Green | Continue normal monitoring.
145630 | HCFWF4Z5170 | F4 Z5 :Stone Wall Cladding | 26161 | 2013-10-14 12:00 | 2013-10-30 12:00 | 16 | 1444 | 100 | 100 | 0 | 13632 | 13632 | 13632 | 16242.0075 | 1 | 0.83931 | TRUE | FALSE | FALSE | 180.5 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145631 | HCFWF4Z1120 | F4 Z1 :Carpet Floor Tiles | 26147 | 2013-12-17 08:00 | 2013-12-29 16:00 | 12 | 1048 | 100 | 100 | 0 | 16824 | 16824 | 16824 | 19181.292 | 1 | 0.8771 | TRUE | FALSE | FALSE | 131 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145632 | HCFWF4Z1159 | F4 Z1 :Gybsum Board Partitions | 26148 | 2013-04-06 08:00 | 2013-04-16 16:00 | 10 | 1142 | 100 | 97 | -3 | 18550 | 18550 | 17993.5 | 18441.6238 | 0.97 | 0.9757 | FALSE | FALSE | FALSE | 142.75 | FALSE | 0 | Green | Continue normal monitoring.
145633 | HCFWF4Z1141 | F4 Z1 :Stone Flooring | 26147 | 2013-09-28 08:00 | 2013-10-10 16:00 | 12 | 592 | 100 | 100 | 0 | 16332 | 16332 | 16332 | 14451.0188 | 1 | 1.1302 | FALSE | FALSE | FALSE | 74 | FALSE | 0 | Green | Continue normal monitoring.
145634 | HCFWF4Z1125 | F4 Z1 :Stone Cladding | 26148 | 2013-06-24 12:00 | 2013-07-06 12:00 | 12 | 1788 | 100 | 100 | 0 | 7896 | 7896 | 7896 | 7350.0687 | 1 | 1.0743 | FALSE | FALSE | FALSE | 223.5 | FALSE | 0 | Green | Continue normal monitoring.
145635 | HCFWF4Z1146 | F4 Z1 :Glass Wall Cladding | 26148 | 2014-02-24 08:00 | 2014-03-13 16:00 | 17 | 200 | 100 | 99 | -1 | 24752 | 24752 | 24504.48 | 26439.9908 | 0.99 | 0.9268 | FALSE | FALSE | FALSE | 25 | FALSE | 0 | Green | Continue normal monitoring.
145636 | HCFWF4Z1148 | F4 Z1 :Mirrors | 26308 | 2014-03-16 08:00 | 2014-03-26 16:00 | 10 | 464 | 100 | 86 | -14 | 5230 | 5230 | 4497.8 | 4878.6634 | 0.86 | 0.92193 | FALSE | TRUE | TRUE | 58 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145637 | HCFWF4Z1164 | F4 Z1 :Toilet & corian vanity tops | 26308 | 2014-03-16 08:00 | 2014-03-26 16:00 | 10 | 464 | 100 | 82 | -18 | 9030 | 9030 | 7404.6 | 9640.3309 | 0.82 | 0.76809 | TRUE | TRUE | TRUE | 58 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145638 | HCFWF4Z2121 | F4 Z2 :Carpet Tiles | 26311 | 2013-12-17 08:00 | 2013-12-29 16:00 | 12 | 1048 | 100 | 97 | -3 | 15648 | 15648 | 15178.56 | 14750.4246 | 0.97 | 1.029 | FALSE | FALSE | FALSE | 131 | FALSE | 0 | Green | Continue normal monitoring.
145639 | HCFWF4Z2118 | F4 Z2 :Stone Flooring | 26311 | 2013-10-01 08:00 | 2013-10-14 16:00 | 13 | 568 | 100 | 100 | 0 | 13195 | 13195 | 13195 | 15696.3702 | 1 | 0.84064 | TRUE | FALSE | FALSE | 71 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145640 | HCFWF4Z2124 | F4 Z2 :Glass Wall Cladding | 26153 | 2014-02-24 08:00 | 2014-03-13 16:00 | 17 | 296 | 100 | 89 | -11 | 20927 | 20927 | 18625.03 | 21113.43 | 0.89 | 0.88214 | TRUE | TRUE | TRUE | 37 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145641 | HCFWF4Z2123 | F4 Z2 :Gybsum Board Partitions | 26153 | 2013-06-03 08:00 | 2013-06-13 16:00 | 10 | 758 | 100 | 86 | -14 | 18870 | 18870 | 16228.2 | 17892.9161 | 0.86 | 0.90696 | FALSE | TRUE | TRUE | 94.75 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145642 | HCFWF4Z3172 | F4 Z3 :Glass Wall Cladding | 26157 | 2014-02-24 08:00 | 2014-03-13 16:00 | 17 | 344 | 100 | 96 | -4 | 32385 | 32385 | 31089.6 | 38050.1233 | 0.96 | 0.81707 | TRUE | FALSE | FALSE | 43 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145643 | HCFWF4Z3170 | F4 Z3 :Gybsum Board Partitions | 26157 | 2013-07-14 08:00 | 2013-07-24 16:00 | 10 | 478 | 100 | 93 | -7 | 10310 | 10310 | 9588.3 | 10177.3679 | 0.93 | 0.94212 | FALSE | FALSE | FALSE | 59.75 | FALSE | 0 | Green | Continue normal monitoring.
145644 | HCFWF4Z3149 | F4 Z3 :Stone Cladding | 26157 | 2014-02-24 08:00 | 2014-03-06 16:00 | 10 | 600 | 100 | 100 | 0 | 14550 | 14550 | 14550 | 13016.3583 | 1 | 1.1178 | FALSE | FALSE | FALSE | 75 | FALSE | 0 | Green | Continue normal monitoring.
145645 | HCFWF4Z3175 | F4 Z3 :Glass Doors | 26159 | 2014-03-15 08:00 | 2014-03-25 16:00 | 10 | 472 | 100 | 100 | 0 | 6510 | 6510 | 6510 | 7018.8463 | 1 | 0.9275 | FALSE | FALSE | FALSE | 59 | FALSE | 0 | Green | Continue normal monitoring.
145646 | HCFWF4Z5186 | F4 Z5 :Stone Flooring All types | 26160 | 2013-12-10 14:00 | 2013-12-24 14:00 | 14 | 378 | 100 | 82 | -18 | 20244 | 20244 | 16600.08 | 21916.6743 | 0.82 | 0.75742 | TRUE | TRUE | TRUE | 47.25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145647 | HCFWF4Z5191 | F4 Z5 :Aluminum & Stainless Steel Skirting | 26160 | 2013-12-30 08:00 | 2014-01-11 16:00 | 12 | 760 | 100 | 91 | -9 | 13284 | 13284 | 12088.44 | 15089.0069 | 0.91 | 0.80114 | TRUE | FALSE | FALSE | 95 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145648 | HCFWF4Z5175 | F4 Z5 :Stone Base Skirting | 26160 | 2013-12-30 08:00 | 2014-01-11 16:00 | 12 | 760 | 100 | 100 | 0 | 11028 | 11028 | 11028 | 10433.456 | 1 | 1.057 | FALSE | FALSE | FALSE | 95 | FALSE | 0 | Green | Continue normal monitoring.
145649 | HCFWF4Z5164 | F4 Z5 :Epoxy Screed Finish | 26160 | 2013-11-02 12:00 | 2013-11-14 12:00 | 12 | 1348 | 100 | 92 | -8 | 21276 | 21276 | 19573.92 | 21861.2716 | 0.92 | 0.89537 | TRUE | FALSE | FALSE | 168.5 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145650 | HCFWF4Z5196 | F4 Z5 :Glass Wall Cladding | 26161 | 2013-12-08 08:00 | 2013-12-26 16:00 | 18 | 856 | 100 | 81 | -19 | 29520 | 29520 | 23911.2 | 28426.2004 | 0.81 | 0.84117 | TRUE | TRUE | TRUE | 107 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145651 | HCFWF4Z5169 | F4 Z5 :Gybsum Board Partitions | 26161 | 2013-08-20 08:00 | 2013-08-31 16:00 | 11 | 246 | 100 | 82 | -18 | 15015 | 15015 | 12312.3 | 13248.9581 | 0.82 | 0.9293 | FALSE | TRUE | TRUE | 30.75 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145652 | HCFWF4Z5188 | F4 Z5 :Quary Tiles | 26160 | 2013-12-17 08:00 | 2013-12-29 16:00 | 12 | 352 | 100 | 84 | -16 | 12924 | 12924 | 10856.16 | 15517.1428 | 0.84 | 0.69962 | TRUE | TRUE | TRUE | 44 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145653 | HCFWF4Z5193 | F4 Z5 :Stainless steel Wire Cloth Finish For Elev Lobby | 26161 | 2013-12-08 08:00 | 2013-12-18 16:00 | 10 | 1112 | 100 | 90 | -10 | 8340 | 8340 | 7506 | 9520.5097 | 0.9 | 0.7884 | TRUE | FALSE | FALSE | 139 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145654 | HCFWF4Z5174 | F4 Z5 :Aluminum Floor Tiles | 26160 | 2013-12-17 08:00 | 2013-12-29 16:00 | 12 | 760 | 100 | 87 | -13 | 23292 | 23292 | 20264.04 | 22606.871 | 0.87 | 0.89637 | TRUE | TRUE | TRUE | 95 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145655 | HCFWF4Z5198 | F4 Z5 :Wood Flooring | 26160 | 2013-12-17 08:00 | 2013-12-29 16:00 | 12 | 1048 | 100 | 100 | 0 | 17172 | 17172 | 17172 | 18713.1732 | 1 | 0.91764 | FALSE | FALSE | FALSE | 131 | FALSE | 0 | Green | Continue normal monitoring.
145656 | HCFWF4Z5197 | F4 Z5 :Acoustical Painted Walls | 26161 | 2013-09-01 08:00 | 2013-09-11 16:00 | 10 | 1488 | 100 | 100 | 0 | 7940 | 7940 | 7940 | 7388.2138 | 1 | 1.0747 | FALSE | FALSE | FALSE | 186 | FALSE | 0 | Green | Continue normal monitoring.
145657 | HCFWF4Z1147 | F4 Z1 :Acoustical Ceiling | 26149 | 2014-02-20 08:00 | 2014-03-03 16:00 | 11 | 368 | 100 | 100 | 0 | 13794 | 13794 | 13794 | 16636.8696 | 1 | 0.82912 | TRUE | FALSE | FALSE | 46 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145658 | HCFWF4Z1169 | F4 Z1 :Stone Base Skirting | 26147 | 2013-10-12 08:00 | 2013-10-27 16:00 | 15 | 1272 | 100 | 91 | -9 | 28410 | 28410 | 25853.1 | 25454.2957 | 0.91 | 1.0157 | FALSE | FALSE | FALSE | 159 | FALSE | 0 | Green | Continue normal monitoring.
145659 | HCFWF4Z4127 | F4 Z4 :Trawelled smooth Concrete screed | 26164 | 2013-07-18 12:00 | 2013-07-28 12:00 | 10 | 988 | 100 | 86 | -14 | 6850 | 6850 | 5891 | 5833.0138 | 0.86 | 1.0099 | FALSE | TRUE | TRUE | 123.5 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145660 | HCFWF4Z4126 | F4 Z4 :Foam Concrete Under Floorings | 26164 | 2013-06-30 12:00 | 2013-07-18 12:00 | 18 | 988 | 100 | 94 | -6 | 31842 | 31842 | 29931.48 | 33459.678 | 0.94 | 0.89455 | TRUE | FALSE | FALSE | 123.5 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145661 | HCFWF4Z4129 | F4 Z4 :Rubber Flooring | 26164 | 2013-08-29 10:00 | 2013-09-10 10:00 | 12 | 1534 | 100 | 100 | 0 | 13632 | 13632 | 13632 | 14766.8794 | 1 | 0.92315 | FALSE | FALSE | FALSE | 191.75 | FALSE | 0 | Green | Continue normal monitoring.
145662 | HCFWF4Z4130 | F4 Z4 :Rubber Skirting | 26164 | 2014-02-06 08:00 | 2014-02-08 16:00 | 2 | 576 | 100 | 96 | -4 | 3582 | 3582 | 3438.72 | 3874.2415 | 0.96 | 0.88759 | TRUE | FALSE | FALSE | 72 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145663 | HCFWF4Z4132 | F4 Z4 :Block Works | 26165 | 2013-05-19 08:00 | 2013-05-30 16:00 | 11 | 788 | 100 | 83 | -17 | 19360 | 19360 | 16068.8 | 16878.1404 | 0.83 | 0.95205 | FALSE | TRUE | TRUE | 98.5 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145664 | HCFWF4Z4134 | F4 Z4 :Plaster First Layer | 26165 | 2013-06-01 08:00 | 2013-06-10 14:00 | 9 | 788 | 100 | 100 | 0 | 9261 | 9261 | 9261 | 9035.1939 | 1 | 1.025 | FALSE | FALSE | FALSE | 98.5 | FALSE | 0 | Green | Continue normal monitoring.
145665 | HCFWF4Z4131 | F4 Z4 :Plaster Final Layer | 26165 | 2013-06-19 14:00 | 2013-06-30 12:00 | 10 | 788 | 100 | 100 | 0 | 5200 | 5200 | 5200 | 5458.3338 | 1 | 0.95267 | FALSE | FALSE | FALSE | 98.5 | FALSE | 0 | Green | Continue normal monitoring.
145666 | HCFWF4Z4137 | F4 Z4 :Paint Prime coat | 26165 | 2013-06-30 12:00 | 2013-07-14 12:00 | 14 | 1556 | 100 | 100 | 0 | 19740 | 19740 | 19740 | 18489.1092 | 1 | 1.0677 | FALSE | FALSE | FALSE | 194.5 | FALSE | 0 | Green | Continue normal monitoring.
145667 | HCFWF4Z4128 | F4 Z4 :Paint putty coat | 26165 | 2013-07-14 12:00 | 2013-07-28 12:00 | 14 | 1844 | 100 | 92 | -8 | 19124 | 19124 | 17594.08 | 22930.639 | 0.92 | 0.76727 | TRUE | FALSE | FALSE | 230.5 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145668 | HCFWF4Z4135 | F4 Z4 :Plaster Second Layer | 26165 | 2013-06-10 14:00 | 2013-06-19 14:00 | 9 | 788 | 100 | 97 | -3 | 11637 | 11637 | 11287.89 | 10296.9263 | 0.97 | 1.0962 | FALSE | FALSE | FALSE | 98.5 | FALSE | 0 | Green | Continue normal monitoring.
145669 | HCFWF4Z4140 | F4 Z4 :Plaster First Layer | 26310 | 2013-07-28 12:00 | 2013-08-07 10:00 | 9 | 1244 | 100 | 80 | -20 | 5391 | 5391 | 4312.8 | 5633.3458 | 0.8 | 0.76558 | TRUE | TRUE | TRUE | 155.5 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145670 | HCFWF4Z2142 | F4 Z4 :Plaster Final Layer | 26310 | 2013-08-20 10:00 | 2013-08-29 10:00 | 9 | 1262 | 100 | 95 | -5 | 11259 | 11259 | 10696.05 | 12684.0114 | 0.95 | 0.84327 | TRUE | FALSE | FALSE | 157.75 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145671 | HCFWF4Z2133 | F4 Z4 :Paint Prime coat | 26310 | 2013-08-29 10:00 | 2013-09-10 10:00 | 12 | 1262 | 100 | 92 | -8 | 11724 | 11724 | 10786.08 | 11192.908 | 0.92 | 0.96365 | FALSE | FALSE | FALSE | 157.75 | FALSE | 0 | Green | Continue normal monitoring.
145672 | HCFWF4Z2139 | F4 Z4 :Paint putty coat | 26310 | 2013-09-10 10:00 | 2013-09-22 10:00 | 12 | 1262 | 100 | 89 | -11 | 21852 | 21852 | 19448.28 | 24030.5634 | 0.89 | 0.80931 | TRUE | TRUE | TRUE | 157.75 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145673 | HCFWF4Z2145 | F4 Z4 :Gybsum Board Ceiling | 26310 | 2014-01-07 08:00 | 2014-01-23 16:00 | 16 | 584 | 100 | 91 | -9 | 23024 | 23024 | 20951.84 | 27208.7055 | 0.91 | 0.77004 | TRUE | FALSE | FALSE | 73 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145674 | HCFWF4Z4136 | F4 Z4 :Plaster Second Layer | 26310 | 2013-08-07 10:00 | 2013-08-20 10:00 | 13 | 1262 | 100 | 100 | 0 | 13325 | 13325 | 13325 | 12340.7461 | 1 | 1.0798 | FALSE | FALSE | FALSE | 157.75 | FALSE | 0 | Green | Continue normal monitoring.
145675 | HCFWF4Z2138 | F4 Z4 :Steel Fire Rated Doors | 26334 | 2013-12-08 08:00 | 2013-12-18 16:00 | 10 | 952 | 100 | 81 | -19 | 8330 | 8330 | 6747.3 | 10136.679 | 0.81 | 0.66563 | TRUE | TRUE | TRUE | 119 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145676 | HCFWF4Z4147 | F4 Z4 :Steel Doors | 26334 | 2013-12-19 08:00 | 2013-12-31 16:00 | 12 | 952 | 100 | 100 | 0 | 6012 | 6012 | 6012 | 6441.3976 | 1 | 0.93334 | FALSE | FALSE | FALSE | 119 | FALSE | 0 | Green | Continue normal monitoring.
145677 | HCFWF4Z2144 | F4 Z4 :Wooden Doors | 26334 | 2013-12-19 08:00 | 2013-12-31 16:00 | 12 | 952 | 100 | 82 | -18 | 10488 | 10488 | 8600.16 | 10170.1381 | 0.82 | 0.84563 | TRUE | TRUE | TRUE | 119 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145678 | HCFWF4Z4141 | F4 Z4 :Metal Works | 26334 | 2013-12-08 08:00 | 2013-12-18 16:00 | 10 | 872 | 100 | 89 | -11 | 7920 | 7920 | 7048.8 | 8096.959 | 0.89 | 0.87055 | TRUE | TRUE | TRUE | 109 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145679 | HCFWF4Z2150 | F4 Z4 :Handrails & Railling | 26334 | 2013-12-14 08:00 | 2013-12-31 16:00 | 17 | 1032 | 100 | 81 | -19 | 22712 | 22712 | 18396.72 | 22141.4008 | 0.81 | 0.83087 | TRUE | TRUE | TRUE | 129 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145680 | HCFWF4Z4146 | F4 Z4 :Carpet Tiles | 26164 | 2013-12-17 08:00 | 2013-12-29 16:00 | 12 | 1048 | 100 | 100 | 0 | 18048 | 18048 | 18048 | 20575.5225 | 1 | 0.87716 | TRUE | FALSE | FALSE | 131 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145681 | HCFWF4Z4143 | F4 Z4 :Stone Flooring | 26164 | 2013-07-28 12:00 | 2013-08-14 12:00 | 17 | 988 | 100 | 100 | 0 | 17884 | 17884 | 17884 | 20897.8164 | 1 | 0.85578 | TRUE | FALSE | FALSE | 123.5 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145682 | HCFWF4Z4249 | F4 Z4 :Glass Wall Cladding | 26165 | 2013-12-08 08:00 | 2013-12-26 16:00 | 18 | 808 | 100 | 100 | 0 | 14706 | 14706 | 14706 | 17399.7709 | 1 | 0.84518 | TRUE | FALSE | FALSE | 101 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145683 | HCFWF4Z4148 | F4 Z4 :Gybsum Board Partitions | 26165 | 2013-05-19 08:00 | 2013-05-30 16:00 | 11 | 788 | 100 | 92 | -8 | 9680 | 9680 | 8905.6 | 12044.8947 | 0.92 | 0.73937 | TRUE | FALSE | FALSE | 98.5 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145684 | HCFWF5Z1152 | F5 Z1 :Trawelled smooth Concrete screed | 26336 | 2013-08-15 08:00 | 2013-08-24 16:00 | 9 | 800 | 100 | 92 | -8 | 4617 | 4617 | 4247.64 | 5385.7938 | 0.92 | 0.78867 | TRUE | FALSE | FALSE | 100 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145685 | HCFWF5Z1153 | F5 Z1 :Block Works | 26337 | 2013-04-17 08:00 | 2013-04-28 16:00 | 11 | 904 | 100 | 97 | -3 | 11033 | 11033 | 10702.01 | 12032.0782 | 0.97 | 0.88946 | TRUE | FALSE | FALSE | 113 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145686 | HCFWF5Z1130 | F5 Z1 :Plaster First Layer | 26337 | 2013-06-24 12:00 | 2013-07-04 10:00 | 9 | 800 | 100 | 82 | -18 | 6570 | 6570 | 5387.4 | 6475.9709 | 0.82 | 0.83191 | TRUE | TRUE | TRUE | 100 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145687 | HCFWF5Z1151 | F5 Z1 :Foam Concrete Under Floorings | 26336 | 2013-07-24 08:00 | 2013-08-14 16:00 | 21 | 800 | 100 | 100 | 0 | 33747 | 33747 | 33747 | 36036.335 | 1 | 0.93647 | FALSE | FALSE | FALSE | 100 | FALSE | 0 | Green | Continue normal monitoring.
145688 | HCFWF5Z1157 | F5 Z1 :Plaster Final Layer | 26337 | 2013-07-14 10:00 | 2013-07-23 16:00 | 9 | 800 | 100 | 86 | -14 | 5661 | 5661 | 4868.46 | 4904.8448 | 0.86 | 0.99258 | FALSE | TRUE | TRUE | 100 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145689 | HCFWF5Z1158 | F5 Z1 :Paint Prime coat | 26337 | 2013-07-24 08:00 | 2013-08-06 16:00 | 13 | 1472 | 100 | 93 | -7 | 17381 | 17381 | 16164.33 | 19952.1719 | 0.93 | 0.81015 | TRUE | FALSE | FALSE | 184 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145690 | HCFWF5Z1174 | F5 Z1 :Paint putty coat | 26337 | 2014-03-24 08:00 | 2014-04-06 16:00 | 13 | 296 | 100 | 99 | -1 | 21684 | 21684 | 21467.16 | 22299.44 | 0.99 | 0.96268 | FALSE | FALSE | FALSE | 37 | FALSE | 0 | Green | Continue normal monitoring.
145691 | HCFWF5Z1162 | F5 Z1 :Plaster First Layer | 26338 | 2013-09-28 08:00 | 2013-10-07 14:00 | 9 | 568 | 100 | 100 | 0 | 12510 | 12510 | 12510 | 10733.6962 | 1 | 1.1655 | FALSE | FALSE | FALSE | 71 | FALSE | 0 | Green | Continue normal monitoring.
145692 | HCFWF5Z1179 | F5 Z1 :Plaster Final Layer | 26338 | 2013-10-21 14:00 | 2013-10-31 12:00 | 9 | 568 | 100 | 100 | 0 | 4743 | 4743 | 4743 | 4150.1382 | 1 | 1.1429 | FALSE | FALSE | FALSE | 71 | FALSE | 0 | Green | Continue normal monitoring.
145693 | HCFWF5Z1135 | F5 Z1 :Paint Prime coat | 26338 | 2013-10-31 12:00 | 2013-11-13 12:00 | 13 | 956 | 100 | 96 | -4 | 7345 | 7345 | 7051.2 | 7381.6265 | 0.96 | 0.95524 | FALSE | FALSE | FALSE | 119.5 | FALSE | 0 | Green | Continue normal monitoring.
145694 | HCFWF5Z1156 | F5 Z1 :Paint putty coat | 26338 | 2013-11-13 12:00 | 2013-11-25 12:00 | 12 | 972 | 100 | 100 | 0 | 20232 | 20232 | 20232 | 21918.7137 | 1 | 0.92305 | FALSE | FALSE | FALSE | 121.5 | FALSE | 0 | Green | Continue normal monitoring.
145695 | HCFWF5Z1184 | F5 Z1 :Steel Fire Rated Doors | 26339 | 2014-02-20 08:00 | 2014-03-03 16:00 | 11 | 464 | 100 | 100 | 0 | 19272 | 19272 | 19272 | 19959.6554 | 1 | 0.96555 | FALSE | FALSE | FALSE | 58 | FALSE | 0 | Green | Continue normal monitoring.
145696 | HCFWF5Z1163 | F5 Z1 :Rubber Flooring | 26336 | 2013-10-31 12:00 | 2013-11-13 12:00 | 13 | 580 | 100 | 100 | 0 | 9880 | 9880 | 9880 | 10845.0955 | 1 | 0.91101 | FALSE | FALSE | FALSE | 72.5 | FALSE | 0 | Green | Continue normal monitoring.
145697 | HCFWF5Z1189 | F5 Z1 :Rubber Skirting | 26336 | 2014-02-11 08:00 | 2014-02-12 16:00 | 1 | 576 | 100 | 91 | -9 | 1972 | 1972 | 1794.52 | 2055.0561 | 0.91 | 0.87322 | TRUE | FALSE | FALSE | 72 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145698 | HCFWF5Z1140 | F5 Z1 :Steel Doors | 26339 | 2014-03-04 08:00 | 2014-03-15 16:00 | 11 | 384 | 100 | 100 | 0 | 21417 | 21417 | 21417 | 23873.1345 | 1 | 0.89712 | TRUE | FALSE | FALSE | 48 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145699 | HCFWF5Z1167 | F5 Z1 :Wooden Doors | 26339 | 2014-03-10 08:00 | 2014-03-20 16:00 | 10 | 344 | 100 | 95 | -5 | 9590 | 9590 | 9110.5 | 8992.0676 | 0.95 | 1.0132 | FALSE | FALSE | FALSE | 43 | FALSE | 0 | Green | Continue normal monitoring.
145700 | HCFWF5Z1172 | F5 Z1 :Gybsum Board Ceiling | 26338 | 2014-03-09 08:00 | 2014-03-24 16:00 | 15 | 288 | 100 | 100 | 0 | 12000 | 12000 | 12000 | 10741.6473 | 1 | 1.1171 | FALSE | FALSE | FALSE | 36 | FALSE | 0 | Green | Continue normal monitoring.
145701 | HCFWF5Z1168 | F5 Z1 :Metal Works | 26339 | 2014-02-20 08:00 | 2014-03-03 16:00 | 11 | 304 | 100 | 91 | -9 | 15598 | 15598 | 14194.18 | 16979.5707 | 0.91 | 0.83596 | TRUE | FALSE | FALSE | 38 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145702 | HCFWF5Z1161 | F5 Z1 :Handrails & Railling | 26339 | 2014-04-02 08:00 | 2014-04-19 16:00 | 17 | 224 | 100 | 94 | -6 | 31042 | 31042 | 29179.48 | 32403.9928 | 0.94 | 0.90049 | FALSE | FALSE | FALSE | 28 | FALSE | 0 | Green | Continue normal monitoring.
145703 | HCFWF5Z1166 | F5 Z1 :Plaster Second Layer | 26337 | 2013-07-04 10:00 | 2013-07-14 10:00 | 10 | 800 | 100 | 100 | 0 | 7860 | 7860 | 7860 | 6765.4719 | 1 | 1.1618 | FALSE | FALSE | FALSE | 100 | FALSE | 0 | Green | Continue normal monitoring.
145704 | HCFWF5Z1173 | F5 Z1 :Plaster Second Layer | 26338 | 2013-10-07 14:00 | 2013-10-21 14:00 | 14 | 568 | 100 | 89 | -11 | 26852 | 26852 | 23898.28 | 26910.8798 | 0.89 | 0.88805 | TRUE | TRUE | TRUE | 71 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145705 | HCFWF5Z2152 | F5 Z2 :Trawelled smooth Concrete screed | 26322 | 2013-10-24 08:00 | 2013-11-02 16:00 | 9 | 464 | 100 | 100 | 0 | 13797 | 13797 | 13797 | 12313.1359 | 1 | 1.1205 | FALSE | FALSE | FALSE | 58 | FALSE | 0 | Green | Continue normal monitoring.
145706 | HCFWF5Z2151 | F5 Z2 :Foam Concrete Under Floorings | 26322 | 2013-10-01 08:00 | 2013-10-23 16:00 | 22 | 464 | 100 | 100 | 0 | 24838 | 24838 | 24838 | 26391.4364 | 1 | 0.94114 | FALSE | FALSE | FALSE | 58 | FALSE | 0 | Green | Continue normal monitoring.
145707 | HCFWF5Z2154 | F5 Z2 :Rubber Flooring | 26322 | 2013-12-02 08:00 | 2013-12-12 16:00 | 10 | 976 | 100 | 100 | 0 | 7690 | 7690 | 7690 | 7753.9121 | 1 | 0.99176 | FALSE | FALSE | FALSE | 122 | FALSE | 0 | Green | Continue normal monitoring.
145708 | HCFWF5Z2155 | F5 Z2 :Rubber Skirting | 26322 | 2014-02-13 08:00 | 2014-02-15 16:00 | 2 | 576 | 100 | 86 | -14 | 2182 | 2182 | 1876.52 | 2389.859 | 0.86 | 0.7852 | TRUE | TRUE | TRUE | 72 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145709 | HCFWF5Z2157 | F5 Z2 :Block Works | 26323 | 2013-06-15 08:00 | 2013-06-25 16:00 | 10 | 912 | 100 | 99 | -1 | 13430 | 13430 | 13295.7 | 15743.1951 | 0.99 | 0.84454 | TRUE | FALSE | FALSE | 114 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145710 | HCFWF5Z2159 | F5 Z2 :Plaster First Layer | 26323 | 2013-09-03 08:00 | 2013-09-11 16:00 | 8 | 464 | 100 | 84 | -16 | 10888 | 10888 | 9145.92 | 10559.9171 | 0.84 | 0.8661 | TRUE | TRUE | TRUE | 58 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145711 | HCFWF5Z2156 | F5 Z2 :Plaster Final Layer | 26323 | 2013-09-22 08:00 | 2013-09-30 16:00 | 8 | 464 | 100 | 80 | -20 | 15072 | 15072 | 12057.6 | 18611.5212 | 0.8 | 0.64786 | TRUE | TRUE | TRUE | 58 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145712 | HCFWF5Z2162 | F5 Z2 :Paint Prime coat | 26323 | 2013-10-05 14:00 | 2013-10-23 14:00 | 18 | 946 | 100 | 100 | 0 | 32040 | 32040 | 32040 | 34098.6918 | 1 | 0.93963 | FALSE | FALSE | FALSE | 118.25 | FALSE | 0 | Green | Continue normal monitoring.
145713 | HCFWF5Z2153 | F5 Z2 :Paint putty coat | 26323 | 2013-10-28 14:00 | 2013-11-12 14:00 | 15 | 1266 | 100 | 96 | -4 | 9480 | 9480 | 9100.8 | 10402.5587 | 0.96 | 0.87486 | TRUE | FALSE | FALSE | 158.25 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145714 | HCFWF5Z2160 | F5 Z2 :Plaster Second Layer | 26323 | 2013-09-12 08:00 | 2013-09-21 16:00 | 9 | 464 | 100 | 82 | -18 | 16191 | 16191 | 13276.62 | 18170.6566 | 0.82 | 0.73066 | TRUE | TRUE | TRUE | 58 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145715 | HCFWF5Z2165 | F5 Z2 :Plaster First Layer | 26324 | 2013-11-03 08:00 | 2013-11-12 16:00 | 9 | 464 | 100 | 92 | -8 | 13239 | 13239 | 12179.88 | 14783.8935 | 0.92 | 0.82386 | TRUE | FALSE | FALSE | 58 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145716 | HCFWF5Z2167 | F5 Z2 :Plaster Final Layer | 26324 | 2013-11-23 08:00 | 2013-12-01 16:00 | 8 | 464 | 100 | 93 | -7 | 8096 | 8096 | 7529.28 | 8536.3277 | 0.93 | 0.88203 | TRUE | FALSE | FALSE | 58 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145717 | HCFWF5Z2158 | F5 Z2 :Paint Prime coat | 26324 | 2013-12-02 08:00 | 2013-12-12 16:00 | 10 | 768 | 100 | 100 | 0 | 8120 | 8120 | 8120 | 8294.6264 | 1 | 0.97895 | FALSE | FALSE | FALSE | 96 | FALSE | 0 | Green | Continue normal monitoring.
145718 | HCFWF5Z2164 | F5 Z2 :Paint putty coat | 26324 | 2013-12-14 08:00 | 2013-12-24 16:00 | 10 | 768 | 100 | 100 | 0 | 10750 | 10750 | 10750 | 9368.7624 | 1 | 1.1474 | FALSE | FALSE | FALSE | 96 | FALSE | 0 | Green | Continue normal monitoring.
145719 | HCFWF5Z2170 | F5 Z2 :Gybsum Board Ceiling | 26324 | 2014-03-08 08:00 | 2014-03-23 16:00 | 15 | 296 | 100 | 97 | -3 | 20775 | 20775 | 20151.75 | 17842.2834 | 0.97 | 1.1294 | FALSE | FALSE | FALSE | 37 | FALSE | 0 | Green | Continue normal monitoring.
145720 | HCFWF5Z2161 | F5 Z2 :Plaster Second Layer | 26324 | 2013-11-13 08:00 | 2013-11-21 16:00 | 8 | 464 | 100 | 83 | -17 | 14456 | 14456 | 11998.48 | 14357.4748 | 0.83 | 0.8357 | TRUE | TRUE | TRUE | 58 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145721 | HCFWF5Z2163 | F5 Z2 :Steel Fire Rated Doors | 26325 | 2014-03-16 08:00 | 2014-03-26 16:00 | 10 | 304 | 100 | 97 | -3 | 16440 | 16440 | 15946.8 | 16168.154 | 0.97 | 0.98631 | FALSE | FALSE | FALSE | 38 | FALSE | 0 | Green | Continue normal monitoring.
145722 | HCFWF5Z2172 | F5 Z2 :Steel Doors | 26325 | 2014-03-16 08:00 | 2014-03-26 16:00 | 10 | 304 | 100 | 100 | 0 | 16300 | 16300 | 16300 | 16382.7724 | 1 | 0.99495 | FALSE | FALSE | FALSE | 38 | FALSE | 0 | Green | Continue normal monitoring.
145723 | HCFWF5Z2169 | F5 Z2 :Wooden Doors | 26325 | 2014-03-16 08:00 | 2014-03-26 16:00 | 10 | 384 | 100 | 84 | -16 | 11860 | 11860 | 9962.4 | 10737.4187 | 0.84 | 0.92782 | FALSE | TRUE | TRUE | 48 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145724 | HCFWF5Z2166 | F5 Z2 :Metal Works | 26325 | 2014-03-04 08:00 | 2014-03-15 16:00 | 11 | 304 | 100 | 100 | 0 | 18997 | 18997 | 18997 | 21756.6431 | 1 | 0.87316 | TRUE | FALSE | FALSE | 38 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145725 | HCFWF5Z2175 | F5 Z2 :Handrails & Railling | 26325 | 2014-04-06 08:00 | 2014-04-19 16:00 | 13 | 208 | 100 | 95 | -5 | 8632 | 8632 | 8200.4 | 10296.1267 | 0.95 | 0.79645 | TRUE | FALSE | FALSE | 26 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145726 | HCFWF5Z3177 | F5 Z3 :Trawelled smooth Concrete screed | 26328 | 2014-01-13 08:00 | 2014-01-22 16:00 | 9 | 0 | 100 | 80 | -20 | 7236 | 7236 | 5788.8 | 8867.6156 | 0.8 | 0.6528 | TRUE | TRUE | TRUE | 0 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
145727 | HCFWF5Z3201 | F5 Z3 :Foam Concrete Under Floorings | 26328 | 2013-12-23 08:00 | 2014-01-12 16:00 | 20 | 0 | 100 | 100 | 0 | 13100 | 13100 | 13100 | 13714.9785 | 1 | 0.95516 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145728 | HCFWF5Z3178 | F5 Z3 :Rubber Flooring | 26328 | 2014-02-20 08:00 | 2014-03-03 16:00 | 11 | 176 | 100 | 93 | -7 | 20790 | 20790 | 19334.7 | 23499.8992 | 0.93 | 0.82276 | TRUE | FALSE | FALSE | 22 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145729 | HCFWF5Z3154 | F5 Z3 :Rubber Skirting | 26328 | 2014-03-04 08:00 | 2014-03-05 16:00 | 1 | 464 | 100 | 94 | -6 | 1119 | 1119 | 1051.86 | 1334.0947 | 0.94 | 0.78844 | TRUE | FALSE | FALSE | 58 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145730 | HCFWF5Z3206 | F5 Z3 :Block Works | 26330 | 2013-08-18 08:00 | 2013-08-28 16:00 | 10 | 560 | 100 | 88 | -12 | 17740 | 17740 | 15611.2 | 18047.1937 | 0.88 | 0.86502 | TRUE | TRUE | TRUE | 70 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145731 | HCFWF5Z3182 | F5 Z3 :Plaster First Layer | 26330 | 2013-11-25 08:00 | 2013-12-03 16:00 | 8 | 0 | 100 | 94 | -6 | 11648 | 11648 | 10949.12 | 11342.4161 | 0.94 | 0.96533 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145732 | HCFWF5Z3159 | F5 Z3 :Plaster Final Layer | 26330 | 2013-12-14 08:00 | 2013-12-22 16:00 | 8 | 0 | 100 | 96 | -4 | 6664 | 6664 | 6397.44 | 8161.333 | 0.96 | 0.78387 | TRUE | FALSE | FALSE | 0 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145733 | HCFWF5Z3180 | F5 Z3 :Paint Prime coat | 26330 | 2013-12-23 08:00 | 2014-01-07 16:00 | 15 | 464 | 100 | 100 | 0 | 22020 | 22020 | 22020 | 23259.0791 | 1 | 0.94673 | FALSE | FALSE | FALSE | 58 | FALSE | 0 | Green | Continue normal monitoring.
145734 | HCFWF5Z3211 | F5 Z3 :Paint putty coat | 26330 | 2014-03-05 08:00 | 2014-03-18 16:00 | 13 | 88 | 100 | 100 | 0 | 13130 | 13130 | 13130 | 13772.0774 | 1 | 0.95338 | FALSE | FALSE | FALSE | 11 | FALSE | 0 | Green | Continue normal monitoring.
145735 | HCFWF5Z3183 | F5 Z3 :Plaster Second Layer | 26330 | 2013-12-04 08:00 | 2013-12-12 16:00 | 8 | 0 | 100 | 83 | -17 | 14528 | 14528 | 12058.24 | 13385.6116 | 0.83 | 0.90084 | FALSE | TRUE | TRUE | 0 | TRUE | 4 | Orange | Develop recovery plan and review schedule and cost exposure.
145736 | HCFWF5Z3185 | F5 Z3 :Plaster First Layer | 26332 | 2014-01-23 08:00 | 2014-02-01 16:00 | 9 | 0 | 100 | 91 | -9 | 13887 | 13887 | 12637.17 | 12404.7295 | 0.91 | 1.0187 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145737 | HCFWF5Z3187 | F5 Z3 :Plaster Final Layer | 26332 | 2014-02-11 08:00 | 2014-02-19 16:00 | 8 | 0 | 100 | 100 | 0 | 6248 | 6248 | 6248 | 7415.3935 | 1 | 0.84257 | TRUE | FALSE | FALSE | 0 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145738 | HCFWF5Z3188 | F5 Z3 :Paint Prime coat | 26332 | 2014-03-19 08:00 | 2014-03-30 16:00 | 11 | 88 | 100 | 100 | 0 | 14256 | 14256 | 14256 | 15619.633 | 1 | 0.9127 | FALSE | FALSE | FALSE | 11 | FALSE | 0 | Green | Continue normal monitoring.
145739 | HCFWF5Z3164 | F5 Z3 :Paint putty coat | 26332 | 2014-03-31 08:00 | 2014-04-10 16:00 | 10 | 88 | 100 | 84 | -16 | 15240 | 15240 | 12801.6 | 14940.2267 | 0.84 | 0.85685 | TRUE | TRUE | TRUE | 11 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145740 | HCFWF5Z3190 | F5 Z3 :Gybsum Board Ceiling | 26332 | 2014-04-16 08:00 | 2014-05-03 16:00 | 17 | 56 | 100 | 100 | 0 | 10506 | 10506 | 10506 | 9735.8523 | 1 | 1.0791 | FALSE | FALSE | FALSE | 7 | FALSE | 0 | Green | Continue normal monitoring.
145741 | HCFWF5Z3216 | F5 Z3 :Plaster Second Layer | 26332 | 2014-02-02 08:00 | 2014-02-10 16:00 | 8 | 0 | 100 | 84 | -16 | 12464 | 12464 | 10469.76 | 13363.8872 | 0.84 | 0.78344 | TRUE | TRUE | TRUE | 0 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
145742 | HCFWF5Z3193 | F5 Z3 :Steel Fire Rated Doors | 26312 | 2014-03-31 08:00 | 2014-04-10 16:00 | 10 | 200 | 100 | 90 | -10 | 6970 | 6970 | 6273 | 7552.467 | 0.9 | 0.83059 | TRUE | FALSE | FALSE | 25 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145743 | HCFWF5Z3192 | F5 Z3 :Steel Doors | 26312 | 2014-04-12 08:00 | 2014-04-22 16:00 | 10 | 120 | 100 | 100 | 0 | 9840 | 9840 | 9840 | 9178.7268 | 1 | 1.072 | FALSE | FALSE | FALSE | 15 | FALSE | 0 | Green | Continue normal monitoring.
145744 | HCFWF5Z3195 | F5 Z3 :Wooden Doors | 26312 | 2014-04-12 08:00 | 2014-04-22 16:00 | 10 | 120 | 100 | 85 | -15 | 15820 | 15820 | 13447 | 18834.6956 | 0.85 | 0.71395 | TRUE | TRUE | TRUE | 15 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145745 | HCFWF5Z3221 | F5 Z3 :Metal Works | 26312 | 2014-03-31 08:00 | 2014-04-10 16:00 | 10 | 120 | 100 | 86 | -14 | 13360 | 13360 | 11489.6 | 11806.3088 | 0.86 | 0.97317 | FALSE | TRUE | TRUE | 15 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145746 | HCFWF5Z3226 | F5 Z3 :Handrails & Railling | 26312 | 2014-04-16 08:00 | 2014-05-04 16:00 | 18 | 128 | 100 | 100 | 0 | 30312 | 30312 | 30312 | 30082.7574 | 1 | 1.0076 | FALSE | FALSE | FALSE | 16 | FALSE | 0 | Green | Continue normal monitoring.
145747 | HCFWF5Z3197 | F5 Z3 :Epoxy Screed Finish | 26328 | 2014-01-23 08:00 | 2014-02-03 16:00 | 11 | 816 | 100 | 100 | 0 | 16588 | 16588 | 16588 | 18614.2867 | 1 | 0.89114 | TRUE | FALSE | FALSE | 102 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145748 | HCFWF5Z3231 | F5 Z3 :Stone Flooring All types | 26328 | 2014-02-20 08:00 | 2014-03-05 16:00 | 13 | 176 | 100 | 93 | -7 | 15470 | 15470 | 14387.1 | 14845.7568 | 0.93 | 0.96911 | FALSE | FALSE | FALSE | 22 | FALSE | 0 | Green | Continue normal monitoring.
145749 | HCFWF5Z3200 | F5 Z3 :Aluminum & Stainless Steel Skirting | 26328 | 2014-03-04 08:00 | 2014-03-15 16:00 | 11 | 544 | 100 | 100 | 0 | 19019 | 19019 | 19019 | 22462.7718 | 1 | 0.84669 | TRUE | FALSE | FALSE | 68 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145750 | HCFWF5Z3198 | F5 Z3 :Stainless steel Wire Cloth Finish For Elev Lobby | 26330 | 2014-03-05 08:00 | 2014-03-16 16:00 | 11 | 536 | 100 | 90 | -10 | 16885 | 16885 | 15196.5 | 19349.3173 | 0.9 | 0.78538 | TRUE | FALSE | FALSE | 67 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145751 | HCFWF5Z3169 | F5 Z3 :Stone Decoration For Benches | 26312 | 2014-04-16 08:00 | 2014-04-27 16:00 | 11 | 248 | 100 | 100 | 0 | 10879 | 10879 | 10879 | 12680.6618 | 1 | 0.85792 | TRUE | FALSE | FALSE | 31 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145752 | HCFWF5Z3202 | F5 Z3 :Mirror | 26312 | 2014-04-23 08:00 | 2014-05-05 16:00 | 12 | 200 | 100 | 92 | -8 | 9300 | 9300 | 8556 | 8348.0763 | 0.92 | 1.0249 | FALSE | FALSE | FALSE | 25 | FALSE | 0 | Green | Continue normal monitoring.
145753 | HCFWF5Z3203 | F5 Z3 :Toilet & corian vanity tops | 26312 | 2014-04-23 08:00 | 2014-05-05 16:00 | 12 | 200 | 100 | 81 | -19 | 14304 | 14304 | 11586.24 | 12962.5544 | 0.81 | 0.89382 | TRUE | TRUE | TRUE | 25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145754 | HCFWF5Z3208 | F5 Z3 :Carpet Tile Flooring | 26328 | 2014-02-20 08:00 | 2014-03-03 16:00 | 11 | 624 | 100 | 100 | 0 | 8151 | 8151 | 8151 | 7862.369 | 1 | 1.0367 | FALSE | FALSE | FALSE | 78 | FALSE | 0 | Green | Continue normal monitoring.
145755 | HCFWF5Z3236 | F5 Z3 :Acoustical Ceiling | 26332 | 2014-03-31 08:00 | 2014-04-10 16:00 | 10 | 168 | 100 | 86 | -14 | 17390 | 17390 | 14955.4 | 18385.2448 | 0.86 | 0.81345 | TRUE | TRUE | TRUE | 21 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145756 | HCFWF5Z3174 | F5 Z3 :Stone Base Skirting | 26328 | 2014-03-06 08:00 | 2014-03-17 16:00 | 11 | 528 | 100 | 99 | -1 | 19514 | 19514 | 19318.86 | 22425.6143 | 0.99 | 0.86146 | TRUE | FALSE | FALSE | 66 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145757 | HCFWF5Z5202 | F5 Z5 :Trawelled smooth Concrete screed | 26315 | 2013-11-24 08:00 | 2013-12-02 16:00 | 8 | 300 | 100 | 83 | -17 | 5000 | 5000 | 4150 | 5923.0618 | 0.83 | 0.70065 | TRUE | TRUE | TRUE | 37.5 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145758 | HCFWF5Z5201 | F5 Z5 :Foam Concrete Under Floorings | 26315 | 2013-11-04 08:00 | 2013-11-23 16:00 | 19 | 300 | 100 | 100 | 0 | 13604 | 13604 | 13604 | 15396.1111 | 1 | 0.8836 | TRUE | FALSE | FALSE | 37.5 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145759 | HCFWF5Z5207 | F5 Z5 :Rubber Flooring | 26315 | 2014-01-21 08:00 | 2014-02-01 16:00 | 11 | 288 | 100 | 87 | -13 | 20119 | 20119 | 17503.53 | 24574.1263 | 0.87 | 0.71227 | TRUE | TRUE | TRUE | 36 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145760 | HCFWF5Z5180 | F5 Z5 :Rubber Skirting | 26315 | 2014-03-09 08:00 | 2014-03-10 16:00 | 1 | 464 | 100 | 99 | -1 | 1708 | 1708 | 1690.92 | 1956.5096 | 0.99 | 0.86425 | TRUE | FALSE | FALSE | 58 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145761 | HCFWF5Z5203 | F5 Z5 :Block Works | 26316 | 2013-09-01 08:00 | 2013-09-11 16:00 | 10 | 424 | 100 | 100 | 0 | 15620 | 15620 | 15620 | 15190.5618 | 1 | 1.0283 | FALSE | FALSE | FALSE | 53 | FALSE | 0 | Green | Continue normal monitoring.
145762 | HCFWF5Z5185 | F5 Z5 :Plaster First Layer | 26316 | 2013-09-30 12:00 | 2013-10-10 10:00 | 9 | 300 | 100 | 100 | 0 | 15714 | 15714 | 15714 | 15023.0949 | 1 | 1.046 | FALSE | FALSE | FALSE | 37.5 | FALSE | 0 | Green | Continue normal monitoring.
145763 | HCFWF5Z5212 | F5 Z5 :Plaster Final Layer | 26316 | 2013-10-24 10:00 | 2013-11-03 16:00 | 10 | 300 | 100 | 100 | 0 | 17070 | 17070 | 17070 | 19263.1021 | 1 | 0.88615 | TRUE | FALSE | FALSE | 37.5 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145764 | HCFWF5Z5208 | F5 Z5 :Paint Prime coat | 26316 | 2013-11-04 08:00 | 2013-11-18 16:00 | 14 | 888 | 100 | 100 | 0 | 13916 | 13916 | 13916 | 12902.1947 | 1 | 1.0786 | FALSE | FALSE | FALSE | 111 | FALSE | 0 | Green | Continue normal monitoring.
145765 | HCFWF5Z5179 | F5 Z5 :Paint putty coat | 26316 | 2013-11-19 08:00 | 2013-12-02 16:00 | 13 | 1224 | 100 | 98 | -2 | 12038 | 12038 | 11797.24 | 10678.7404 | 0.98 | 1.1047 | FALSE | FALSE | FALSE | 153 | FALSE | 0 | Green | Continue normal monitoring.
145766 | HCFWF5Z5206 | F5 Z5 :Plaster Second Layer | 26316 | 2013-10-10 10:00 | 2013-10-24 10:00 | 14 | 300 | 100 | 92 | -8 | 23814 | 23814 | 21908.88 | 25311.6422 | 0.92 | 0.86557 | TRUE | FALSE | FALSE | 37.5 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145767 | HCFWF5Z5184 | F5 Z5 :Plaster First Layer | 26317 | 2013-12-10 14:00 | 2013-12-21 12:00 | 10 | 246 | 100 | 93 | -7 | 14180 | 14180 | 13187.4 | 16713.351 | 0.93 | 0.78903 | TRUE | FALSE | FALSE | 30.75 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145768 | HCFWF5Z5211 | F5 Z5 :Plaster Final Layer | 26317 | 2013-12-31 12:00 | 2014-01-20 16:00 | 20 | 246 | 100 | 89 | -11 | 39020 | 39020 | 34727.8 | 34749.3366 | 0.89 | 0.99938 | FALSE | TRUE | TRUE | 30.75 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145769 | HCFWF5Z5217 | F5 Z5 :Paint Prime coat | 26317 | 2014-01-21 08:00 | 2014-02-01 16:00 | 11 | 480 | 100 | 90 | -10 | 19987 | 19987 | 17988.3 | 23319.9628 | 0.9 | 0.77137 | TRUE | FALSE | TRUE | 60 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145770 | HCFWF5Z5213 | F5 Z5 :Paint putty coat | 26317 | 2014-02-02 08:00 | 2014-02-12 16:00 | 10 | 480 | 100 | 81 | -19 | 6500 | 6500 | 5265 | 7635.0872 | 0.81 | 0.68958 | TRUE | TRUE | TRUE | 60 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145771 | HCFWF5Z5189 | F5 Z5 :Gybsum Board Ceiling | 26317 | 2014-03-06 12:00 | 2014-03-23 12:00 | 17 | 332 | 100 | 100 | 0 | 15011 | 15011 | 15011 | 15655.116 | 1 | 0.95886 | FALSE | FALSE | FALSE | 41.5 | FALSE | 0 | Green | Continue normal monitoring.
145772 | HCFWF5Z5190 | F5 Z5 :Plaster Second Layer | 26317 | 2013-12-21 12:00 | 2013-12-31 12:00 | 10 | 246 | 100 | 100 | 0 | 8070 | 8070 | 8070 | 7044.4977 | 1 | 1.1456 | FALSE | FALSE | FALSE | 30.75 | FALSE | 0 | Green | Continue normal monitoring.
145773 | HCFWF5Z5222 | F5 Z5 :Steel Fire Rated Doors | 26192 | 2014-02-13 12:00 | 2014-02-25 12:00 | 12 | 508 | 100 | 88 | -12 | 22308 | 22308 | 19631.04 | 20519.7002 | 0.88 | 0.95669 | FALSE | TRUE | TRUE | 63.5 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145774 | HCFWF5Z5218 | F5 Z5 :Steel Doors | 26192 | 2014-02-25 12:00 | 2014-03-09 12:00 | 12 | 428 | 100 | 96 | -4 | 14940 | 14940 | 14342.4 | 16926.5794 | 0.96 | 0.84733 | TRUE | FALSE | FALSE | 53.5 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145775 | HCFWF5Z5195 | F5 Z5 :Wooden Doors | 26192 | 2014-02-25 12:00 | 2014-03-09 12:00 | 12 | 508 | 100 | 100 | 0 | 16692 | 16692 | 16692 | 18940.599 | 1 | 0.88128 | TRUE | FALSE | FALSE | 63.5 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145776 | HCFWF5Z5216 | F5 Z5 :Metal Works | 26192 | 2014-02-13 12:00 | 2014-02-25 12:00 | 12 | 428 | 100 | 82 | -18 | 10488 | 10488 | 8600.16 | 12683.5801 | 0.82 | 0.67805 | TRUE | TRUE | TRUE | 53.5 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145777 | HCFWF5Z5221 | F5 Z5 :Handrails & Railling | 26192 | 2014-02-25 12:00 | 2014-03-15 12:00 | 18 | 468 | 100 | 100 | 0 | 27558 | 27558 | 27558 | 29847.3659 | 1 | 0.9233 | FALSE | FALSE | FALSE | 58.5 | FALSE | 0 | Green | Continue normal monitoring.
145778 | HCFWF5Z5194 | F5 Z5 :Stone Decoration For Benches | 26192 | 2014-02-25 12:00 | 2014-03-09 12:00 | 12 | 588 | 100 | 85 | -15 | 22368 | 22368 | 19012.8 | 20123.2134 | 0.85 | 0.94482 | FALSE | TRUE | TRUE | 73.5 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145779 | HCFWF5Z5227 | F5 Z5 :Mirror | 26192 | 2014-03-09 12:00 | 2014-03-20 12:00 | 11 | 508 | 100 | 84 | -16 | 6908 | 6908 | 5802.72 | 6207.2937 | 0.84 | 0.93482 | FALSE | TRUE | TRUE | 63.5 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145780 | HCFWF5Z5223 | F5 Z5 :Toilet & corian vanity tops | 26192 | 2014-03-09 12:00 | 2014-03-20 12:00 | 11 | 508 | 100 | 84 | -16 | 16654 | 16654 | 13989.36 | 18959.7953 | 0.84 | 0.73784 | TRUE | TRUE | TRUE | 63.5 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145781 | HCFWF5Z5232 | F5 Z5 :Carpet Tile Flooring | 26315 | 2014-01-21 08:00 | 2014-02-01 16:00 | 11 | 304 | 100 | 100 | 0 | 12848 | 12848 | 12848 | 11865.3062 | 1 | 1.0828 | FALSE | FALSE | FALSE | 38 | FALSE | 0 | Green | Continue normal monitoring.
145782 | HCFWF5Z5200 | F5 Z5 :Acoustical Ceiling | 26317 | 2014-02-02 08:00 | 2014-02-12 16:00 | 10 | 560 | 100 | 94 | -6 | 18750 | 18750 | 17625 | 18400.3912 | 0.94 | 0.95786 | FALSE | FALSE | FALSE | 70 | FALSE | 0 | Green | Continue normal monitoring.
145783 | HCFWF5Z5205 | F5 Z5 :Stone Wall Cladding | 26316 | 2013-11-19 08:00 | 2013-11-30 16:00 | 11 | 1240 | 100 | 100 | 0 | 20691 | 20691 | 20691 | 21619.7115 | 1 | 0.95704 | FALSE | FALSE | FALSE | 155 | FALSE | 0 | Green | Continue normal monitoring.
145784 | HCFWF5Z1145 | F5 Z1 :Carpet Floor Tiles | 26336 | 2013-12-17 08:00 | 2013-12-29 16:00 | 12 | 1048 | 100 | 96 | -4 | 12192 | 12192 | 11704.32 | 10483.9734 | 0.96 | 1.1164 | FALSE | FALSE | FALSE | 131 | FALSE | 0 | Green | Continue normal monitoring.
145785 | HCFWF5Z1194 | F5 Z1 :Gybsum Board Partitions | 26337 | 2013-04-17 08:00 | 2013-04-28 16:00 | 11 | 1320 | 100 | 88 | -12 | 6435 | 6435 | 5662.8 | 6110.2102 | 0.88 | 0.92678 | FALSE | TRUE | TRUE | 165 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145786 | HCFWF5Z1171 | F5 Z1 :Stone Flooring | 26336 | 2013-10-31 12:00 | 2013-11-16 12:00 | 16 | 580 | 100 | 82 | -18 | 27168 | 27168 | 22277.76 | 27525.418 | 0.82 | 0.80935 | TRUE | TRUE | TRUE | 72.5 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145787 | HCFWF5Z1150 | F5 Z1 :Stone Cladding | 26337 | 2013-07-24 08:00 | 2013-08-04 16:00 | 11 | 1712 | 100 | 99 | -1 | 18876 | 18876 | 18687.24 | 18155.9661 | 0.99 | 1.0293 | FALSE | FALSE | FALSE | 214 | FALSE | 0 | Green | Continue normal monitoring.
145788 | HCFWF5Z1176 | F5 Z1 :Glass Wall Cladding | 26337 | 2014-03-15 08:00 | 2014-04-01 16:00 | 17 | 200 | 100 | 100 | 0 | 13770 | 13770 | 13770 | 12455.6278 | 1 | 1.1055 | FALSE | FALSE | FALSE | 25 | FALSE | 0 | Green | Continue normal monitoring.
145789 | HCFWF5Z1178 | F5 Z1 :Mirrors | 26339 | 2014-04-02 08:00 | 2014-04-13 16:00 | 11 | 344 | 100 | 96 | -4 | 18062 | 18062 | 17339.52 | 20612.443 | 0.96 | 0.84122 | TRUE | FALSE | FALSE | 43 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145790 | HCFWF5Z1199 | F5 Z1 :Toilet & corian vanity tops | 26339 | 2014-04-02 08:00 | 2014-04-13 16:00 | 11 | 344 | 100 | 100 | 0 | 19151 | 19151 | 19151 | 22507.3863 | 1 | 0.85088 | TRUE | FALSE | FALSE | 43 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145791 | HCFWF5Z2171 | F5 Z2 :Carpet Tiles | 26322 | 2013-12-17 08:00 | 2013-12-29 16:00 | 12 | 1048 | 100 | 100 | 0 | 11112 | 11112 | 11112 | 10589.6426 | 1 | 1.0493 | FALSE | FALSE | FALSE | 131 | FALSE | 0 | Green | Continue normal monitoring.
145792 | HCFWF5Z2168 | F5 Z2 :Stone Flooring | 26322 | 2013-11-03 08:00 | 2013-11-17 16:00 | 14 | 568 | 100 | 89 | -11 | 27118 | 27118 | 24135.02 | 31450.5831 | 0.89 | 0.76739 | TRUE | TRUE | TRUE | 71 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145793 | HCFWF5Z2174 | F5 Z2 :Glass Wall Cladding | 26323 | 2014-03-15 08:00 | 2014-04-01 16:00 | 17 | 296 | 100 | 82 | -18 | 10421 | 10421 | 8545.22 | 10464.9915 | 0.82 | 0.81655 | TRUE | TRUE | TRUE | 37 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145794 | HCFWF5Z2173 | F5 Z2 :Gybsum Board Partitions | 26323 | 2013-06-15 08:00 | 2013-06-25 16:00 | 10 | 936 | 100 | 97 | -3 | 16680 | 16680 | 16179.6 | 17558.6076 | 0.97 | 0.92146 | FALSE | FALSE | FALSE | 117 | FALSE | 0 | Green | Continue normal monitoring.
145795 | HCFWF5Z3207 | F5 Z3 :Glass Wall Cladding | 26330 | 2014-03-15 08:00 | 2014-04-01 16:00 | 17 | 344 | 100 | 97 | -3 | 13634 | 13634 | 13224.98 | 16257.1875 | 0.97 | 0.81349 | TRUE | FALSE | FALSE | 43 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145796 | HCFWF5Z3205 | F5 Z3 :Gybsum Board Partitions | 26330 | 2013-07-23 08:00 | 2013-08-03 16:00 | 11 | 672 | 100 | 100 | 0 | 13673 | 13673 | 13673 | 15723.6967 | 1 | 0.86958 | TRUE | FALSE | FALSE | 84 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145797 | HCFWF5Z3179 | F5 Z3 :Stone Cladding | 26330 | 2014-03-15 08:00 | 2014-03-25 16:00 | 10 | 472 | 100 | 96 | -4 | 10870 | 10870 | 10435.2 | 12740.1481 | 0.96 | 0.81908 | TRUE | FALSE | FALSE | 59 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145798 | HCFWF5Z3210 | F5 Z3 :Glass Doors | 26312 | 2014-03-31 08:00 | 2014-04-10 16:00 | 10 | 360 | 100 | 100 | 0 | 14860 | 14860 | 14860 | 13444.4077 | 1 | 1.1053 | FALSE | FALSE | FALSE | 45 | FALSE | 0 | Green | Continue normal monitoring.
145799 | HCFWF5Z5226 | F5 Z5 :Stone Flooring All types | 26315 | 2014-01-21 08:00 | 2014-02-03 16:00 | 13 | 288 | 100 | 82 | -18 | 10972 | 10972 | 8997.04 | 9632.1846 | 0.82 | 0.93406 | FALSE | TRUE | TRUE | 36 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145800 | HCFWF5Z5231 | F5 Z5 :Aluminum & Stainless Steel Skirting | 26315 | 2014-02-02 08:00 | 2014-02-12 16:00 | 10 | 624 | 100 | 82 | -18 | 13130 | 13130 | 10766.6 | 15852.6616 | 0.82 | 0.67917 | TRUE | TRUE | TRUE | 78 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145801 | HCFWF5Z5210 | F5 Z5 :Stone Base Skirting | 26315 | 2014-02-04 08:00 | 2014-02-15 16:00 | 11 | 608 | 100 | 85 | -15 | 14300 | 14300 | 12155 | 14373.412 | 0.85 | 0.84566 | TRUE | TRUE | TRUE | 76 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145802 | HCFWF5Z5199 | F5 Z5 :Epoxy Screed Finish | 26315 | 2013-12-03 08:00 | 2013-12-14 16:00 | 11 | 1144 | 100 | 92 | -8 | 16764 | 16764 | 15422.88 | 16179.806 | 0.92 | 0.95322 | FALSE | FALSE | FALSE | 143 | FALSE | 0 | Green | Continue normal monitoring.
145803 | HCFWF5Z5236 | F5 Z5 :Glass Wall Cladding | 26316 | 2013-12-28 08:00 | 2014-01-16 16:00 | 19 | 856 | 100 | 100 | 0 | 31730 | 31730 | 31730 | 36168.3449 | 1 | 0.87729 | TRUE | FALSE | FALSE | 107 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145804 | HCFWF5Z5204 | F5 Z5 :Gybsum Board Partitions | 26316 | 2013-08-27 08:00 | 2013-09-07 16:00 | 11 | 456 | 100 | 100 | 0 | 19910 | 19910 | 19910 | 23584.7138 | 1 | 0.84419 | TRUE | FALSE | FALSE | 57 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145805 | HCFWF5Z5228 | F5 Z5 :Quary Tiles | 26315 | 2014-01-21 08:00 | 2014-02-01 16:00 | 11 | 304 | 100 | 94 | -6 | 17336 | 17336 | 16295.84 | 20716.448 | 0.94 | 0.78661 | TRUE | FALSE | FALSE | 38 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145806 | HCFWF5Z5233 | F5 Z5 :Stainless steel Wire Cloth Finish For Elev Lobby | 26316 | 2013-12-28 08:00 | 2014-01-08 16:00 | 11 | 984 | 100 | 100 | 0 | 20097 | 20097 | 20097 | 19622.6878 | 1 | 1.0242 | FALSE | FALSE | FALSE | 123 | FALSE | 0 | Green | Continue normal monitoring.
145807 | HCFWF5Z5209 | F5 Z5 :Aluminum Floor Tiles | 26315 | 2014-01-21 08:00 | 2014-02-01 16:00 | 11 | 624 | 100 | 88 | -12 | 17512 | 17512 | 15410.56 | 20854.7774 | 0.88 | 0.73895 | TRUE | TRUE | TRUE | 78 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145808 | HCFWF5Z5238 | F5 Z5 :Wood Flooring | 26315 | 2014-01-21 08:00 | 2014-02-01 16:00 | 11 | 832 | 100 | 83 | -17 | 9460 | 9460 | 7851.8 | 8195.894 | 0.83 | 0.95802 | FALSE | TRUE | TRUE | 104 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145809 | HCFWF5Z5237 | F5 Z5 :Acoustical Painted Walls | 26316 | 2013-09-12 08:00 | 2013-09-23 16:00 | 11 | 1536 | 100 | 93 | -7 | 19173 | 19173 | 17830.89 | 16677.9139 | 0.93 | 1.0691 | FALSE | FALSE | FALSE | 192 | FALSE | 0 | Green | Continue normal monitoring.
145810 | HCFWF5Z1177 | F5 Z1 :Acoustical Ceiling | 26338 | 2014-03-09 08:00 | 2014-03-19 16:00 | 10 | 368 | 100 | 84 | -16 | 15090 | 15090 | 12675.6 | 16590.0619 | 0.84 | 0.76405 | TRUE | TRUE | TRUE | 46 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145811 | HCFWF5Z1204 | F5 Z1 :Stone Base Skirting | 26336 | 2013-11-16 12:00 | 2013-11-27 12:00 | 11 | 1148 | 100 | 81 | -19 | 13233 | 13233 | 10718.73 | 11582.0846 | 0.81 | 0.92546 | FALSE | TRUE | TRUE | 143.5 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145812 | HCFWF5Z4277 | F5 Z4 :Trawelled smooth Concrete screed | 26329 | 2013-11-04 12:00 | 2013-11-14 12:00 | 10 | 492 | 100 | 90 | -10 | 10740 | 10740 | 9666 | 10523.521 | 0.9 | 0.91851 | FALSE | FALSE | FALSE | 61.5 | FALSE | 0 | Green | Continue normal monitoring.
145813 | HCFWF5Z4216 | F5 Z4 :Foam Concrete Under Floorings | 26329 | 2013-10-12 12:00 | 2013-11-04 12:00 | 23 | 492 | 100 | 88 | -12 | 38732 | 38732 | 34084.16 | 43345.0739 | 0.88 | 0.78634 | TRUE | TRUE | TRUE | 61.5 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145814 | HCFWF5Z2179 | F5 Z4 :Rubber Flooring | 26329 | 2013-12-22 14:00 | 2014-01-05 14:00 | 14 | 866 | 100 | 100 | 0 | 22568 | 22568 | 22568 | 22227.3757 | 1 | 1.0153 | FALSE | FALSE | FALSE | 108.25 | FALSE | 0 | Green | Continue normal monitoring.
145815 | HCFWF5Z4180 | F5 Z4 :Rubber Skirting | 26329 | 2014-03-06 08:00 | 2014-03-08 16:00 | 2 | 464 | 100 | 82 | -18 | 2374 | 2374 | 1946.68 | 2188.448 | 0.82 | 0.88953 | TRUE | TRUE | TRUE | 58 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145816 | HCFWF5Z4082 | F5 Z4 :Block Works | 26331 | 2013-09-01 08:00 | 2013-09-11 16:00 | 10 | 304 | 100 | 100 | 0 | 12800 | 12800 | 12800 | 12320.5152 | 1 | 1.0389 | FALSE | FALSE | FALSE | 38 | FALSE | 0 | Green | Continue normal monitoring.
145817 | HCFWF5Z4284 | F5 Z4 :Plaster First Layer | 26331 | 2013-09-12 08:00 | 2013-09-22 14:00 | 10 | 304 | 100 | 100 | 0 | 10840 | 10840 | 10840 | 11198.0466 | 1 | 0.96803 | FALSE | FALSE | FALSE | 38 | FALSE | 0 | Green | Continue normal monitoring.
145818 | HCFWF5Z4281 | F5 Z4 :Plaster Final Layer | 26331 | 2013-10-01 14:00 | 2013-10-12 12:00 | 10 | 304 | 100 | 100 | 0 | 10880 | 10880 | 10880 | 11316.8792 | 1 | 0.9614 | FALSE | FALSE | FALSE | 38 | FALSE | 0 | Green | Continue normal monitoring.
145819 | HCFWF5Z4287 | F5 Z4 :Paint Prime coat | 26331 | 2013-10-12 12:00 | 2013-10-30 12:00 | 18 | 980 | 100 | 88 | -12 | 30276 | 30276 | 26642.88 | 35217.046 | 0.88 | 0.75653 | TRUE | TRUE | TRUE | 122.5 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145820 | HCFWF5Z4278 | F5 Z4 :Paint putty coat | 26331 | 2013-10-30 12:00 | 2013-11-14 12:00 | 15 | 1252 | 100 | 82 | -18 | 14820 | 14820 | 12152.4 | 17043.9083 | 0.82 | 0.71301 | TRUE | TRUE | TRUE | 156.5 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145821 | HCFWF5Z4285 | F5 Z4 :Plaster Second Layer | 26331 | 2013-09-22 14:00 | 2013-10-01 14:00 | 9 | 304 | 100 | 100 | 0 | 13230 | 13230 | 13230 | 13662.9798 | 1 | 0.96831 | FALSE | FALSE | FALSE | 38 | FALSE | 0 | Green | Continue normal monitoring.
145822 | HCFWF5Z4290 | F5 Z4 :Plaster First Layer | 26333 | 2013-11-14 12:00 | 2013-11-25 10:00 | 10 | 626 | 100 | 81 | -19 | 18470 | 18470 | 14960.7 | 21947.2904 | 0.81 | 0.68167 | TRUE | TRUE | TRUE | 78.25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145823 | HCFWF5Z4292 | F5 Z4 :Plaster Final Layer | 26333 | 2013-12-04 10:00 | 2013-12-22 14:00 | 18 | 626 | 100 | 91 | -9 | 34272 | 34272 | 31187.52 | 30697.2541 | 0.91 | 1.016 | FALSE | FALSE | FALSE | 78.25 | FALSE | 0 | Green | Continue normal monitoring.
145824 | HCFWF5Z4283 | F5 Z4 :Paint Prime coat | 26333 | 2013-12-22 14:00 | 2014-01-05 14:00 | 14 | 626 | 100 | 89 | -11 | 22750 | 22750 | 20247.5 | 21661.2155 | 0.89 | 0.93474 | FALSE | TRUE | TRUE | 78.25 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145825 | HCFWF5Z4289 | F5 Z4 :Paint putty coat | 26333 | 2014-01-05 14:00 | 2014-01-18 14:00 | 13 | 626 | 100 | 88 | -12 | 12909 | 12909 | 11359.92 | 15247.9893 | 0.88 | 0.74501 | TRUE | TRUE | TRUE | 78.25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145826 | HCFWF5Z4295 | F5 Z4 :Gybsum Board Ceiling | 26333 | 2014-01-25 08:00 | 2014-02-09 16:00 | 15 | 584 | 100 | 94 | -6 | 7770 | 7770 | 7303.8 | 7779.3055 | 0.94 | 0.93888 | FALSE | FALSE | FALSE | 73 | FALSE | 0 | Green | Continue normal monitoring.
145827 | HCFWF5Z4286 | F5 Z4 :Plaster Second Layer | 26333 | 2013-11-25 10:00 | 2013-12-04 10:00 | 9 | 626 | 100 | 87 | -13 | 17793 | 17793 | 15479.91 | 22107.3154 | 0.87 | 0.70022 | TRUE | TRUE | TRUE | 78.25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145828 | HCFWF5Z4288 | F5 Z4 :Steel Fire Rated Doors | 26313 | 2014-01-05 14:00 | 2014-01-18 14:00 | 13 | 850 | 100 | 100 | 0 | 11648 | 11648 | 11648 | 12073.1673 | 1 | 0.96478 | FALSE | FALSE | FALSE | 106.25 | FALSE | 0 | Green | Continue normal monitoring.
145829 | HCFWF5Z4297 | F5 Z4 :Steel Doors | 26313 | 2014-01-18 14:00 | 2014-01-29 14:00 | 11 | 770 | 100 | 84 | -16 | 16500 | 16500 | 13860 | 19251.7751 | 0.84 | 0.71993 | TRUE | TRUE | TRUE | 96.25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145830 | HCFWF5Z4294 | F5 Z4 :Wooden Doors | 26313 | 2014-02-02 08:00 | 2014-02-12 16:00 | 10 | 672 | 100 | 90 | -10 | 18020 | 18020 | 16218 | 18216.8292 | 0.9 | 0.89028 | TRUE | FALSE | FALSE | 84 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145831 | HCFWF5Z4291 | F5 Z4 :Metal Works | 26313 | 2014-01-05 14:00 | 2014-01-18 14:00 | 13 | 770 | 100 | 100 | 0 | 17550 | 17550 | 17550 | 17900.6737 | 1 | 0.98041 | FALSE | FALSE | FALSE | 96.25 | FALSE | 0 | Green | Continue normal monitoring.
145832 | HCFWF5Z2200 | F5 Z4 :Handrails & Railling | 26313 | 2014-01-05 14:00 | 2014-01-23 14:00 | 18 | 890 | 100 | 81 | -19 | 33984 | 33984 | 27527.04 | 34091.1604 | 0.81 | 0.80745 | TRUE | TRUE | TRUE | 111.25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145833 | HCFWF5Z2196 | F5 Z4 :Carpet Tiles | 26329 | 2013-12-22 14:00 | 2014-01-05 14:00 | 14 | 1010 | 100 | 100 | 0 | 25956 | 25956 | 25956 | 29528.3307 | 1 | 0.87902 | TRUE | FALSE | FALSE | 126.25 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145834 | HCFWF5Z4293 | F5 Z4 :Stone Flooring | 26329 | 2013-11-14 12:00 | 2013-11-28 12:00 | 14 | 492 | 100 | 100 | 0 | 26138 | 26138 | 26138 | 27941.709 | 1 | 0.93545 | FALSE | FALSE | FALSE | 61.5 | FALSE | 0 | Green | Continue normal monitoring.
145835 | HCFWF5Z4299 | F5 Z4 :Glass Wall Cladding | 26331 | 2013-12-28 08:00 | 2014-01-16 16:00 | 19 | 808 | 100 | 94 | -6 | 25099 | 25099 | 23593.06 | 30809.3047 | 0.94 | 0.76578 | TRUE | FALSE | FALSE | 101 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145836 | HCFWF5Z4298 | F5 Z4 :Gybsum Board Partitions | 26331 | 2013-09-01 08:00 | 2013-09-11 16:00 | 10 | 1744 | 100 | 85 | -15 | 9540 | 9540 | 8109 | 9066.3974 | 0.85 | 0.8944 | TRUE | TRUE | TRUE | 218 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145837 | HCFWF6Z1182 | F6 Z1 :Trawelled smooth Concrete screed | 26194 | 2013-09-14 12:00 | 2013-09-23 12:00 | 9 | 800 | 100 | 87 | -13 | 11016 | 11016 | 9583.92 | 9806.7196 | 0.87 | 0.97728 | FALSE | TRUE | TRUE | 100 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145838 | HCFWF6Z1183 | F6 Z1 :Block Works | 26195 | 2013-04-29 08:00 | 2013-05-11 16:00 | 12 | 1016 | 100 | 100 | 0 | 19056 | 19056 | 19056 | 19195.1963 | 1 | 0.99275 | FALSE | FALSE | FALSE | 127 | FALSE | 0 | Green | Continue normal monitoring.
145839 | HCFWF6Z1155 | F6 Z1 :Plaster First Layer | 26195 | 2013-07-24 08:00 | 2013-08-03 14:00 | 10 | 800 | 100 | 84 | -16 | 15990 | 15990 | 13431.6 | 17535.9945 | 0.84 | 0.76594 | TRUE | TRUE | TRUE | 100 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145840 | HCFWF6Z1181 | F6 Z1 :Foam Concrete Under Floorings | 26194 | 2013-08-26 12:00 | 2013-09-14 12:00 | 19 | 800 | 100 | 95 | -5 | 22990 | 22990 | 21840.5 | 27457.407 | 0.95 | 0.79543 | TRUE | FALSE | FALSE | 100 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145841 | HCFWF6Z1187 | F6 Z1 :Plaster Final Layer | 26195 | 2013-08-15 14:00 | 2013-08-26 12:00 | 10 | 800 | 100 | 100 | 0 | 6420 | 6420 | 6420 | 6346.0336 | 1 | 1.0117 | FALSE | FALSE | FALSE | 100 | FALSE | 0 | Green | Continue normal monitoring.
145842 | HCFWF6Z1188 | F6 Z1 :Paint Prime coat | 26195 | 2013-08-26 12:00 | 2013-09-09 12:00 | 14 | 1364 | 100 | 97 | -3 | 19824 | 19824 | 19229.28 | 22034.6674 | 0.97 | 0.87268 | TRUE | FALSE | FALSE | 170.5 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145843 | HCFWF6Z1209 | F6 Z1 :Paint putty coat | 26195 | 2014-04-21 08:00 | 2014-05-05 16:00 | 14 | 200 | 100 | 85 | -15 | 18578 | 18578 | 15791.3 | 18393.6964 | 0.85 | 0.85852 | TRUE | TRUE | TRUE | 25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145844 | HCFWF6Z1192 | F6 Z1 :Plaster First Layer | 26344 | 2013-10-31 12:00 | 2013-11-12 10:00 | 11 | 568 | 100 | 84 | -16 | 12144 | 12144 | 10200.96 | 13320.6058 | 0.84 | 0.7658 | TRUE | TRUE | TRUE | 71 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145845 | HCFWF6Z1214 | F6 Z1 :Plaster Final Layer | 26344 | 2013-11-21 10:00 | 2013-12-01 16:00 | 10 | 568 | 100 | 100 | 0 | 19960 | 19960 | 19960 | 24030.3066 | 1 | 0.83062 | TRUE | FALSE | FALSE | 71 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145846 | HCFWF6Z1160 | F6 Z1 :Paint Prime coat | 26344 | 2013-12-02 08:00 | 2013-12-12 16:00 | 10 | 832 | 100 | 95 | -5 | 19400 | 19400 | 18430 | 18285.3353 | 0.95 | 1.0079 | FALSE | FALSE | FALSE | 104 | FALSE | 0 | Green | Continue normal monitoring.
145847 | HCFWF6Z1186 | F6 Z1 :Paint putty coat | 26344 | 2013-12-14 08:00 | 2013-12-24 16:00 | 10 | 880 | 100 | 92 | -8 | 8040 | 8040 | 7396.8 | 8134.0411 | 0.92 | 0.90936 | FALSE | FALSE | FALSE | 110 | FALSE | 0 | Green | Continue normal monitoring.
145848 | HCFWF6Z1219 | F6 Z1 :Steel Fire Rated Doors | 26345 | 2014-03-04 08:00 | 2014-03-15 16:00 | 11 | 464 | 100 | 100 | 0 | 13585 | 13585 | 13585 | 16944.6531 | 1 | 0.80173 | TRUE | FALSE | FALSE | 58 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145849 | HCFWF6Z1193 | F6 Z1 :Rubber Flooring | 26194 | 2013-12-02 08:00 | 2013-12-12 16:00 | 10 | 568 | 100 | 84 | -16 | 7900 | 7900 | 6636 | 9459.6402 | 0.84 | 0.70151 | TRUE | TRUE | TRUE | 71 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145850 | HCFWF6Z1224 | F6 Z1 :Rubber Skirting | 26194 | 2014-03-11 08:00 | 2014-03-12 16:00 | 1 | 464 | 100 | 92 | -8 | 601 | 601 | 552.92 | 646.5894 | 0.92 | 0.85513 | TRUE | FALSE | FALSE | 58 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145851 | HCFWF6Z1165 | F6 Z1 :Steel Doors | 26345 | 2014-03-16 08:00 | 2014-03-26 16:00 | 10 | 384 | 100 | 96 | -4 | 17900 | 17900 | 17184 | 18914.0536 | 0.96 | 0.90853 | FALSE | FALSE | FALSE | 48 | FALSE | 0 | Green | Continue normal monitoring.
145852 | HCFWF6Z1197 | F6 Z1 :Wooden Doors | 26345 | 2014-03-22 08:00 | 2014-04-01 16:00 | 10 | 344 | 100 | 97 | -3 | 13660 | 13660 | 13250.2 | 13166.0565 | 0.97 | 1.0064 | FALSE | FALSE | FALSE | 43 | FALSE | 0 | Green | Continue normal monitoring.
145853 | HCFWF6Z1202 | F6 Z1 :Gybsum Board Ceiling | 26344 | 2014-03-25 08:00 | 2014-04-09 16:00 | 15 | 288 | 100 | 87 | -13 | 22005 | 22005 | 19144.35 | 23256.7274 | 0.87 | 0.82317 | TRUE | TRUE | TRUE | 36 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145854 | HCFWF6Z1198 | F6 Z1 :Metal Works | 26345 | 2014-03-04 08:00 | 2014-03-15 16:00 | 11 | 304 | 100 | 92 | -8 | 16203 | 16203 | 14906.76 | 19269.7839 | 0.92 | 0.77358 | TRUE | FALSE | FALSE | 38 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145855 | HCFWF6Z1191 | F6 Z1 :Handrails & Railling | 26345 | 2014-04-20 08:00 | 2014-05-05 16:00 | 15 | 224 | 100 | 100 | 0 | 20115 | 20115 | 20115 | 22610.6641 | 1 | 0.88962 | TRUE | FALSE | FALSE | 28 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145856 | HCFWF6Z1196 | F6 Z1 :Plaster Second Layer | 26195 | 2013-08-03 14:00 | 2013-08-15 14:00 | 12 | 800 | 100 | 100 | 0 | 17532 | 17532 | 17532 | 16936.2208 | 1 | 1.0352 | FALSE | FALSE | FALSE | 100 | FALSE | 0 | Green | Continue normal monitoring.
145857 | HCFWF6Z1203 | F6 Z1 :Plaster Second Layer | 26344 | 2013-11-12 10:00 | 2013-11-21 10:00 | 9 | 568 | 100 | 98 | -2 | 12969 | 12969 | 12709.62 | 12068.7642 | 0.98 | 1.0531 | FALSE | FALSE | FALSE | 71 | FALSE | 0 | Green | Continue normal monitoring.
145858 | HCFWF6Z2202 | F6 Z2 :Trawelled smooth Concrete screed | 26347 | 2013-11-23 08:00 | 2013-12-01 16:00 | 8 | 464 | 100 | 100 | 0 | 12208 | 12208 | 12208 | 11671.8663 | 1 | 1.0459 | FALSE | FALSE | FALSE | 58 | FALSE | 0 | Green | Continue normal monitoring.
145859 | HCFWF6Z2201 | F6 Z2 :Foam Concrete Under Floorings | 26347 | 2013-11-03 08:00 | 2013-11-21 16:00 | 18 | 464 | 100 | 82 | -18 | 10512 | 10512 | 8619.84 | 9649.0035 | 0.82 | 0.89334 | TRUE | TRUE | TRUE | 58 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145860 | HCFWF6Z2204 | F6 Z2 :Rubber Flooring | 26347 | 2013-12-31 08:00 | 2014-01-12 16:00 | 12 | 464 | 100 | 100 | 0 | 9924 | 9924 | 9924 | 8815.0553 | 1 | 1.1258 | FALSE | FALSE | FALSE | 58 | FALSE | 0 | Green | Continue normal monitoring.
145861 | HCFWF6Z2205 | F6 Z2 :Rubber Skirting | 26347 | 2014-03-13 08:00 | 2014-03-15 16:00 | 2 | 464 | 100 | 87 | -13 | 2630 | 2630 | 2288.1 | 2676.4313 | 0.87 | 0.85491 | TRUE | TRUE | TRUE | 58 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145862 | HCFWF6Z2207 | F6 Z2 :Block Works | 26343 | 2013-06-26 08:00 | 2013-07-07 16:00 | 11 | 1024 | 100 | 81 | -19 | 21703 | 21703 | 17579.43 | 19431.1265 | 0.81 | 0.9047 | FALSE | TRUE | TRUE | 128 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145863 | HCFWF6Z2209 | F6 Z2 :Plaster First Layer | 26343 | 2013-10-01 08:00 | 2013-10-09 16:00 | 8 | 464 | 100 | 87 | -13 | 7624 | 7624 | 6632.88 | 7004.6645 | 0.87 | 0.94692 | FALSE | TRUE | TRUE | 58 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145864 | HCFWF6Z2206 | F6 Z2 :Plaster Final Layer | 26343 | 2013-10-24 08:00 | 2013-11-02 16:00 | 9 | 464 | 100 | 100 | 0 | 10152 | 10152 | 10152 | 10851.7761 | 1 | 0.93552 | FALSE | FALSE | FALSE | 58 | FALSE | 0 | Green | Continue normal monitoring.
145865 | HCFWF6Z2212 | F6 Z2 :Paint Prime coat | 26343 | 2013-11-03 08:00 | 2013-11-17 16:00 | 14 | 880 | 100 | 92 | -8 | 24416 | 24416 | 22462.72 | 22361.1423 | 0.92 | 1.0045 | FALSE | FALSE | FALSE | 110 | FALSE | 0 | Green | Continue normal monitoring.
145866 | HCFWF6Z2203 | F6 Z2 :Paint putty coat | 26343 | 2014-05-17 08:00 | 2014-06-01 16:00 | 15 | 32 | 100 | 92 | -8 | 25155 | 25155 | 23142.6 | 22024.5082 | 0.92 | 1.0508 | FALSE | FALSE | FALSE | 4 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145867 | HCFWF6Z2210 | F6 Z2 :Plaster Second Layer | 26343 | 2013-10-10 08:00 | 2013-10-23 16:00 | 13 | 464 | 100 | 80 | -20 | 15132 | 15132 | 12105.6 | 14783.2912 | 0.8 | 0.81887 | TRUE | TRUE | TRUE | 58 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145868 | HCFWF6Z2215 | F6 Z2 :Plaster First Layer | 26349 | 2013-12-02 08:00 | 2013-12-10 16:00 | 8 | 464 | 100 | 85 | -15 | 4088 | 4088 | 3474.8 | 3835.0658 | 0.85 | 0.90606 | FALSE | TRUE | TRUE | 58 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145869 | HCFWF6Z2217 | F6 Z2 :Plaster Final Layer | 26349 | 2013-12-21 08:00 | 2013-12-30 16:00 | 9 | 464 | 100 | 100 | 0 | 14904 | 14904 | 14904 | 15740.4434 | 1 | 0.94686 | FALSE | FALSE | FALSE | 58 | FALSE | 0 | Green | Continue normal monitoring.
145870 | HCFWF6Z2208 | F6 Z2 :Paint Prime coat | 26349 | 2013-11-18 08:00 | 2013-11-28 16:00 | 10 | 976 | 100 | 98 | -2 | 8030 | 8030 | 7869.4 | 7154.3031 | 0.98 | 1.1 | FALSE | FALSE | FALSE | 122 | FALSE | 0 | Green | Continue normal monitoring.
145871 | HCFWF6Z2214 | F6 Z2 :Paint putty coat | 26349 | 2013-11-30 08:00 | 2013-12-10 16:00 | 10 | 976 | 100 | 95 | -5 | 18160 | 18160 | 17252 | 20896.863 | 0.95 | 0.82558 | TRUE | FALSE | FALSE | 122 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145872 | HCFWF6Z2220 | F6 Z2 :Gybsum Board Ceiling | 26349 | 2014-03-24 08:00 | 2014-04-08 16:00 | 15 | 296 | 100 | 87 | -13 | 22110 | 22110 | 19235.7 | 26808.2292 | 0.87 | 0.71753 | TRUE | TRUE | TRUE | 37 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145873 | HCFWF6Z2211 | F6 Z2 :Plaster Second Layer | 26349 | 2013-12-11 08:00 | 2013-12-19 16:00 | 8 | 464 | 100 | 100 | 0 | 14584 | 14584 | 14584 | 16733.3034 | 1 | 0.87156 | TRUE | FALSE | FALSE | 58 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145874 | HCFWF6Z2213 | F6 Z2 :Steel Fire Rated Doors | 26350 | 2014-03-27 08:00 | 2014-04-07 16:00 | 11 | 304 | 100 | 80 | -20 | 14102 | 14102 | 11281.6 | 14992.2708 | 0.8 | 0.75249 | TRUE | TRUE | TRUE | 38 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145875 | HCFWF6Z2222 | F6 Z2 :Steel Doors | 26350 | 2014-03-27 08:00 | 2014-04-07 16:00 | 11 | 304 | 100 | 100 | 0 | 5962 | 5962 | 5962 | 7120.2206 | 1 | 0.83733 | TRUE | FALSE | FALSE | 38 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145876 | HCFWF6Z2219 | F6 Z2 :Wooden Doors | 26350 | 2014-03-27 08:00 | 2014-04-07 16:00 | 11 | 384 | 100 | 100 | 0 | 15873 | 15873 | 15873 | 17904.2258 | 1 | 0.88655 | TRUE | FALSE | FALSE | 48 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145877 | HCFWF6Z2216 | F6 Z2 :Metal Works | 26350 | 2014-03-16 08:00 | 2014-03-26 16:00 | 10 | 304 | 100 | 95 | -5 | 8420 | 8420 | 7999 | 7192.5362 | 0.95 | 1.1121 | FALSE | FALSE | FALSE | 38 | FALSE | 0 | Green | Continue normal monitoring.
145878 | HCFWF6Z2225 | F6 Z2 :Handrails & Railling | 26350 | 2014-04-20 08:00 | 2014-05-04 16:00 | 14 | 208 | 100 | 88 | -12 | 25886 | 25886 | 22779.68 | 26083.6671 | 0.88 | 0.87333 | TRUE | TRUE | TRUE | 26 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145879 | HCFWF6Z3212 | F6 Z3 :Trawelled smooth Concrete screed | 26348 | 2014-02-11 08:00 | 2014-02-19 16:00 | 8 | 0 | 100 | 92 | -8 | 7976 | 7976 | 7337.92 | 9494.4769 | 0.92 | 0.77286 | TRUE | FALSE | FALSE | 0 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145880 | HCFWF6Z3241 | F6 Z3 :Foam Concrete Under Floorings | 26348 | 2014-01-23 08:00 | 2014-02-10 16:00 | 18 | 0 | 100 | 90 | -10 | 15534 | 15534 | 13980.6 | 15352.9286 | 0.9 | 0.91061 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145881 | HCFWF6Z3213 | F6 Z3 :Rubber Flooring | 26348 | 2014-03-20 08:00 | 2014-03-31 16:00 | 11 | 0 | 100 | 92 | -8 | 15290 | 15290 | 14066.8 | 13211.876 | 0.92 | 1.0647 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145882 | HCFWF6Z3184 | F6 Z3 :Rubber Skirting | 26348 | 2014-04-01 08:00 | 2014-04-02 16:00 | 1 | 352 | 100 | 100 | 0 | 926 | 926 | 926 | 1063.4849 | 1 | 0.87072 | TRUE | FALSE | FALSE | 44 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145883 | HCFWF6Z3246 | F6 Z3 :Block Works | 26355 | 2013-08-29 08:00 | 2013-09-09 16:00 | 11 | 672 | 100 | 100 | 0 | 16544 | 16544 | 16544 | 19369.9685 | 1 | 0.85411 | TRUE | FALSE | FALSE | 84 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145884 | HCFWF6Z3217 | F6 Z3 :Plaster First Layer | 26355 | 2013-12-23 08:00 | 2014-01-02 16:00 | 10 | 0 | 100 | 89 | -11 | 5200 | 5200 | 4628 | 4754.0349 | 0.89 | 0.97349 | FALSE | TRUE | TRUE | 0 | TRUE | 4 | Orange | Develop recovery plan and review schedule and cost exposure.
145885 | HCFWF6Z3189 | F6 Z3 :Plaster Final Layer | 26355 | 2014-01-13 08:00 | 2014-01-22 16:00 | 9 | 0 | 100 | 83 | -17 | 8154 | 8154 | 6767.82 | 8683.4898 | 0.83 | 0.77939 | TRUE | TRUE | TRUE | 0 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
145886 | HCFWF6Z3215 | F6 Z3 :Paint Prime coat | 26355 | 2014-01-23 08:00 | 2014-02-05 16:00 | 13 | 384 | 100 | 100 | 0 | 14534 | 14534 | 14534 | 13469.8521 | 1 | 1.079 | FALSE | FALSE | FALSE | 48 | FALSE | 0 | Green | Continue normal monitoring.
145887 | HCFWF6Z3251 | F6 Z3 :Paint putty coat | 26355 | 2014-03-19 08:00 | 2014-04-01 16:00 | 13 | 104 | 100 | 100 | 0 | 19682 | 19682 | 19682 | 22392.0887 | 1 | 0.87897 | TRUE | FALSE | FALSE | 13 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145888 | HCFWF6Z3218 | F6 Z3 :Plaster Second Layer | 26355 | 2014-01-04 08:00 | 2014-01-12 16:00 | 8 | 0 | 100 | 85 | -15 | 6680 | 6680 | 5678 | 6403.5828 | 0.85 | 0.88669 | TRUE | TRUE | TRUE | 0 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
145889 | HCFWF6Z3220 | F6 Z3 :Plaster First Layer | 26357 | 2014-02-20 08:00 | 2014-03-01 16:00 | 9 | 0 | 100 | 100 | 0 | 14760 | 14760 | 14760 | 14412.9341 | 1 | 1.0241 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145890 | HCFWF6Z3222 | F6 Z3 :Plaster Final Layer | 26357 | 2014-03-11 08:00 | 2014-03-19 16:00 | 8 | 0 | 100 | 86 | -14 | 13176 | 13176 | 11331.36 | 15652.9344 | 0.86 | 0.72391 | TRUE | TRUE | TRUE | 0 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
145891 | HCFWF6Z3223 | F6 Z3 :Paint Prime coat | 26357 | 2014-04-02 08:00 | 2014-04-13 16:00 | 11 | 104 | 100 | 84 | -16 | 9878 | 9878 | 8297.52 | 10278.3449 | 0.84 | 0.80728 | TRUE | TRUE | TRUE | 13 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145892 | HCFWF6Z3194 | F6 Z3 :Paint putty coat | 26357 | 2014-04-14 08:00 | 2014-04-24 16:00 | 10 | 104 | 100 | 90 | -10 | 12920 | 12920 | 11628 | 14443.291 | 0.9 | 0.80508 | TRUE | FALSE | FALSE | 13 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145893 | HCFWF6Z3225 | F6 Z3 :Gybsum Board Ceiling | 26357 | 2014-05-04 08:00 | 2014-05-19 16:00 | 15 | 56 | 100 | 92 | -8 | 18210 | 18210 | 16753.2 | 18409.3853 | 0.92 | 0.91004 | FALSE | FALSE | FALSE | 7 | FALSE | 0 | Green | Continue normal monitoring.
145894 | HCFWF6Z3256 | F6 Z3 :Plaster Second Layer | 26357 | 2014-03-02 08:00 | 2014-03-10 16:00 | 8 | 0 | 100 | 100 | 0 | 4400 | 4400 | 4400 | 4264.4921 | 1 | 1.0318 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145895 | HCFWF6Z3228 | F6 Z3 :Steel Fire Rated Doors | 26358 | 2014-04-14 08:00 | 2014-04-24 16:00 | 10 | 184 | 100 | 100 | 0 | 8230 | 8230 | 8230 | 9054.5738 | 1 | 0.90893 | FALSE | FALSE | FALSE | 23 | FALSE | 0 | Green | Continue normal monitoring.
145896 | HCFWF6Z3227 | F6 Z3 :Steel Doors | 26358 | 2014-04-26 08:00 | 2014-05-07 16:00 | 11 | 104 | 100 | 98 | -2 | 14168 | 14168 | 13884.64 | 12920.4088 | 0.98 | 1.0746 | FALSE | FALSE | FALSE | 13 | FALSE | 0 | Green | Continue normal monitoring.
145897 | HCFWF6Z3230 | F6 Z3 :Wooden Doors | 26358 | 2014-04-26 08:00 | 2014-05-07 16:00 | 11 | 104 | 100 | 100 | 0 | 7040 | 7040 | 7040 | 7034.3675 | 1 | 1.0008 | FALSE | FALSE | FALSE | 13 | FALSE | 0 | Green | Continue normal monitoring.
145898 | HCFWF6Z3261 | F6 Z3 :Metal Works | 26358 | 2014-04-14 08:00 | 2014-04-24 16:00 | 10 | 104 | 100 | 100 | 0 | 9690 | 9690 | 9690 | 9046.7276 | 1 | 1.0711 | FALSE | FALSE | FALSE | 13 | FALSE | 0 | Green | Continue normal monitoring.
145899 | HCFWF6Z3266 | F6 Z3 :Handrails & Railling | 26358 | 2014-05-05 08:00 | 2014-05-21 16:00 | 16 | 128 | 100 | 89 | -11 | 20576 | 20576 | 18312.64 | 23216.2709 | 0.89 | 0.78878 | TRUE | TRUE | TRUE | 16 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145900 | HCFWF6Z3232 | F6 Z3 :Epoxy Screed Finish | 26348 | 2014-02-20 08:00 | 2014-03-03 16:00 | 11 | 624 | 100 | 89 | -11 | 20427 | 20427 | 18180.03 | 25077.8916 | 0.89 | 0.72494 | TRUE | TRUE | TRUE | 78 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145901 | HCFWF6Z3271 | F6 Z3 :Stone Flooring All types | 26348 | 2014-03-20 08:00 | 2014-04-02 16:00 | 13 | 96 | 100 | 90 | -10 | 19019 | 19019 | 17117.1 | 23739.5992 | 0.9 | 0.72104 | TRUE | FALSE | FALSE | 12 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145902 | HCFWF6Z3235 | F6 Z3 :Aluminum & Stainless Steel Skirting | 26348 | 2014-04-01 08:00 | 2014-04-12 16:00 | 11 | 352 | 100 | 100 | 0 | 16577 | 16577 | 16577 | 17076.1455 | 1 | 0.97077 | FALSE | FALSE | FALSE | 44 | FALSE | 0 | Green | Continue normal monitoring.
145903 | HCFWF6Z3233 | F6 Z3 :Stainless steel Wire Cloth Finish For Elev Lobby | 26355 | 2014-03-19 08:00 | 2014-03-30 16:00 | 11 | 440 | 100 | 100 | 0 | 9592 | 9592 | 9592 | 9122.1086 | 1 | 1.0515 | FALSE | FALSE | FALSE | 55 | FALSE | 0 | Green | Continue normal monitoring.
145904 | HCFWF6Z3199 | F6 Z3 :Stone Decoration For Benches | 26358 | 2014-05-05 08:00 | 2014-05-15 16:00 | 10 | 128 | 100 | 86 | -14 | 9930 | 9930 | 8539.8 | 10199.4183 | 0.86 | 0.83728 | TRUE | TRUE | TRUE | 16 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145905 | HCFWF6Z3237 | F6 Z3 :Mirror | 26358 | 2014-05-08 08:00 | 2014-05-19 16:00 | 11 | 104 | 100 | 100 | 0 | 13750 | 13750 | 13750 | 16347.4818 | 1 | 0.84111 | TRUE | FALSE | FALSE | 13 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145906 | HCFWF6Z3238 | F6 Z3 :Toilet & corian vanity tops | 26358 | 2014-05-08 08:00 | 2014-05-19 16:00 | 11 | 104 | 100 | 97 | -3 | 18469 | 18469 | 17914.93 | 17220.5376 | 0.97 | 1.0403 | FALSE | FALSE | FALSE | 13 | FALSE | 0 | Green | Continue normal monitoring.
145907 | HCFWF6Z3243 | F6 Z3 :Carpet Tile Flooring | 26348 | 2014-03-20 08:00 | 2014-03-29 16:00 | 9 | 0 | 100 | 83 | -17 | 7110 | 7110 | 5901.3 | 8751.26 | 0.83 | 0.67434 | TRUE | TRUE | TRUE | 0 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
145908 | HCFWF6Z3276 | F6 Z3 :Acoustical Ceiling | 26357 | 2014-04-14 08:00 | 2014-04-24 16:00 | 10 | 184 | 100 | 81 | -19 | 16670 | 16670 | 13502.7 | 16449.0609 | 0.81 | 0.82088 | TRUE | TRUE | TRUE | 23 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145909 | HCFWF6Z3204 | F6 Z3 :Stone Base Skirting | 26348 | 2014-04-03 08:00 | 2014-04-14 16:00 | 11 | 336 | 100 | 93 | -7 | 6655 | 6655 | 6189.15 | 8280.9593 | 0.93 | 0.7474 | TRUE | FALSE | FALSE | 42 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145910 | HCFWF6Z5242 | F6 Z5 :Trawelled smooth Concrete screed | 26363 | 2013-12-23 12:00 | 2014-01-04 12:00 | 12 | 354 | 100 | 92 | -8 | 23316 | 23316 | 21450.72 | 27639.8019 | 0.92 | 0.77608 | TRUE | FALSE | FALSE | 44.25 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145911 | HCFWF6Z5241 | F6 Z5 :Foam Concrete Under Floorings | 26363 | 2013-12-04 12:00 | 2013-12-23 12:00 | 19 | 354 | 100 | 100 | 0 | 22211 | 22211 | 22211 | 26063.0141 | 1 | 0.8522 | TRUE | FALSE | FALSE | 44.25 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145912 | HCFWF6Z5247 | F6 Z5 :Rubber Flooring | 26363 | 2014-02-27 10:00 | 2014-03-11 10:00 | 12 | 246 | 100 | 91 | -9 | 6012 | 6012 | 5470.92 | 5874.6972 | 0.91 | 0.93127 | FALSE | FALSE | FALSE | 30.75 | FALSE | 0 | Green | Continue normal monitoring.
145913 | HCFWF6Z5215 | F6 Z5 :Rubber Skirting | 26363 | 2014-05-03 08:00 | 2014-05-04 16:00 | 1 | 208 | 100 | 86 | -14 | 1088 | 1088 | 935.68 | 928.6198 | 0.86 | 1.0076 | FALSE | TRUE | TRUE | 26 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145914 | HCFWF6Z5243 | F6 Z5 :Block Works | 26359 | 2013-09-12 08:00 | 2013-09-23 16:00 | 11 | 600 | 100 | 81 | -19 | 12573 | 12573 | 10184.13 | 12608.8728 | 0.81 | 0.8077 | TRUE | TRUE | TRUE | 75 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145915 | HCFWF6Z5220 | F6 Z5 :Plaster First Layer | 26359 | 2013-11-04 08:00 | 2013-11-14 14:00 | 10 | 354 | 100 | 92 | -8 | 5890 | 5890 | 5418.8 | 5717.5629 | 0.92 | 0.94775 | FALSE | FALSE | FALSE | 44.25 | FALSE | 0 | Green | Continue normal monitoring.
145916 | HCFWF6Z5252 | F6 Z5 :Plaster Final Layer | 26359 | 2013-11-24 14:00 | 2013-12-04 12:00 | 9 | 354 | 100 | 93 | -7 | 16812 | 16812 | 15635.16 | 14541.6873 | 0.93 | 1.0752 | FALSE | FALSE | FALSE | 44.25 | FALSE | 0 | Green | Continue normal monitoring.
145917 | HCFWF6Z5248 | F6 Z5 :Paint Prime coat | 26359 | 2013-12-04 12:00 | 2013-12-18 12:00 | 14 | 796 | 100 | 100 | 0 | 11886 | 11886 | 11886 | 12505.8086 | 1 | 0.95044 | FALSE | FALSE | FALSE | 99.5 | FALSE | 0 | Green | Continue normal monitoring.
145918 | HCFWF6Z5214 | F6 Z5 :Paint putty coat | 26359 | 2013-12-18 12:00 | 2014-01-04 12:00 | 17 | 1020 | 100 | 96 | -4 | 33694 | 33694 | 32346.24 | 34071.7948 | 0.96 | 0.94936 | FALSE | FALSE | FALSE | 127.5 | FALSE | 0 | Green | Continue normal monitoring.
145919 | HCFWF6Z5246 | F6 Z5 :Plaster Second Layer | 26359 | 2013-11-14 14:00 | 2013-11-24 14:00 | 10 | 354 | 100 | 88 | -12 | 17860 | 17860 | 15716.8 | 19714.2714 | 0.88 | 0.79723 | TRUE | TRUE | TRUE | 44.25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145920 | HCFWF6Z5219 | F6 Z5 :Plaster First Layer | 26360 | 2014-01-21 08:00 | 2014-01-30 14:00 | 9 | 246 | 100 | 96 | -4 | 16866 | 16866 | 16191.36 | 18526.8714 | 0.96 | 0.87394 | TRUE | FALSE | FALSE | 30.75 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145921 | HCFWF6Z5251 | F6 Z5 :Plaster Final Layer | 26360 | 2014-02-09 14:00 | 2014-02-27 10:00 | 17 | 246 | 100 | 87 | -13 | 27727 | 27727 | 24122.49 | 24907.1268 | 0.87 | 0.9685 | FALSE | TRUE | TRUE | 30.75 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145922 | HCFWF6Z5257 | F6 Z5 :Paint Prime coat | 26360 | 2014-02-27 10:00 | 2014-03-11 10:00 | 12 | 334 | 100 | 100 | 0 | 18744 | 18744 | 18744 | 23257.2969 | 1 | 0.80594 | TRUE | FALSE | FALSE | 41.75 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145923 | HCFWF6Z5253 | F6 Z5 :Paint putty coat | 26360 | 2014-03-11 10:00 | 2014-03-23 10:00 | 12 | 334 | 100 | 81 | -19 | 16896 | 16896 | 13685.76 | 15624.9574 | 0.81 | 0.87589 | TRUE | TRUE | TRUE | 41.75 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145924 | HCFWF6Z5224 | F6 Z5 :Gybsum Board Ceiling | 26360 | 2014-03-23 12:00 | 2014-04-08 12:00 | 16 | 332 | 100 | 100 | 0 | 10528 | 10528 | 10528 | 10823.938 | 1 | 0.97266 | FALSE | FALSE | FALSE | 41.5 | FALSE | 0 | Green | Continue normal monitoring.
145925 | HCFWF6Z5225 | F6 Z5 :Plaster Second Layer | 26360 | 2014-01-30 14:00 | 2014-02-09 14:00 | 10 | 246 | 100 | 100 | 0 | 14580 | 14580 | 14580 | 15239.7015 | 1 | 0.95671 | FALSE | FALSE | FALSE | 30.75 | FALSE | 0 | Green | Continue normal monitoring.
145926 | HCFWF6Z5262 | F6 Z5 :Steel Fire Rated Doors | 26361 | 2014-03-11 10:00 | 2014-03-23 10:00 | 12 | 414 | 100 | 92 | -8 | 9732 | 9732 | 8953.44 | 11437.2909 | 0.92 | 0.78283 | TRUE | FALSE | FALSE | 51.75 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145927 | HCFWF6Z5258 | F6 Z5 :Steel Doors | 26361 | 2014-03-23 10:00 | 2014-04-03 10:00 | 11 | 334 | 100 | 82 | -18 | 19404 | 19404 | 15911.28 | 17263.5804 | 0.82 | 0.92167 | FALSE | TRUE | TRUE | 41.75 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
145928 | HCFWF6Z5230 | F6 Z5 :Wooden Doors | 26361 | 2014-03-23 10:00 | 2014-04-03 10:00 | 11 | 334 | 100 | 95 | -5 | 10384 | 10384 | 9864.8 | 10606.8169 | 0.95 | 0.93004 | FALSE | FALSE | FALSE | 41.75 | FALSE | 0 | Green | Continue normal monitoring.
145929 | HCFWF6Z5256 | F6 Z5 :Metal Works | 26361 | 2014-03-11 10:00 | 2014-03-23 10:00 | 12 | 334 | 100 | 85 | -15 | 9564 | 9564 | 8129.4 | 10533.7979 | 0.85 | 0.77174 | TRUE | TRUE | TRUE | 41.75 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145930 | HCFWF6Z5261 | F6 Z5 :Handrails & Railling | 26361 | 2014-03-15 12:00 | 2014-04-01 12:00 | 17 | 468 | 100 | 98 | -2 | 24667 | 24667 | 24173.66 | 23089.8475 | 0.98 | 1.0469 | FALSE | FALSE | FALSE | 58.5 | FALSE | 0 | Green | Continue normal monitoring.
145931 | HCFWF6Z5229 | F6 Z5 :Stone Decoration For Benches | 26361 | 2014-03-15 12:00 | 2014-03-26 12:00 | 11 | 468 | 100 | 100 | 0 | 5885 | 5885 | 5885 | 6479.3094 | 1 | 0.90828 | FALSE | FALSE | FALSE | 58.5 | FALSE | 0 | Green | Continue normal monitoring.
145932 | HCFWF6Z5267 | F6 Z5 :Mirror | 26361 | 2014-04-03 10:00 | 2014-04-15 10:00 | 12 | 334 | 100 | 86 | -14 | 19284 | 19284 | 16584.24 | 23516.1811 | 0.86 | 0.70523 | TRUE | TRUE | TRUE | 41.75 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145933 | HCFWF6Z5263 | F6 Z5 :Toilet & corian vanity tops | 26361 | 2014-04-03 10:00 | 2014-04-15 10:00 | 12 | 334 | 100 | 89 | -11 | 23700 | 23700 | 21093 | 29601.4719 | 0.89 | 0.71257 | TRUE | TRUE | TRUE | 41.75 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145934 | HCFWF6Z5272 | F6 Z5 :Carpet Tile Flooring | 26363 | 2014-04-08 08:00 | 2014-04-17 16:00 | 9 | 0 | 100 | 88 | -12 | 17172 | 17172 | 15111.36 | 14819.1 | 0.88 | 1.0197 | FALSE | TRUE | TRUE | 0 | TRUE | 4 | Orange | Develop recovery plan and review schedule and cost exposure.
145935 | HCFWF6Z5235 | F6 Z5 :Acoustical Ceiling | 26360 | 2014-03-11 10:00 | 2014-03-23 10:00 | 12 | 414 | 100 | 81 | -19 | 20340 | 20340 | 16475.4 | 19205.7458 | 0.81 | 0.85784 | TRUE | TRUE | TRUE | 51.75 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145936 | HCFWF6Z5240 | F6 Z5 :Stone Wall Cladding | 26359 | 2013-12-18 12:00 | 2013-12-31 12:00 | 13 | 1036 | 100 | 100 | 0 | 24687 | 24687 | 24687 | 24048.1707 | 1 | 1.0266 | FALSE | FALSE | FALSE | 129.5 | FALSE | 0 | Green | Continue normal monitoring.
145937 | HCFWF6Z1170 | F6 Z1 :Carpet Floor Tiles | 26194 | 2013-12-17 08:00 | 2013-12-26 16:00 | 9 | 488 | 100 | 100 | 0 | 16965 | 16965 | 16965 | 17128.7197 | 1 | 0.99044 | FALSE | FALSE | FALSE | 61 | FALSE | 0 | Green | Continue normal monitoring.
145938 | HCFWF6Z1229 | F6 Z1 :Gybsum Board Partitions | 26195 | 2013-04-29 08:00 | 2013-05-11 16:00 | 12 | 1472 | 100 | 100 | 0 | 12696 | 12696 | 12696 | 12021.8787 | 1 | 1.0561 | FALSE | FALSE | FALSE | 184 | FALSE | 0 | Green | Continue normal monitoring.
145939 | HCFWF6Z1201 | F6 Z1 :Stone Flooring | 26194 | 2013-12-02 08:00 | 2013-12-15 16:00 | 13 | 568 | 100 | 94 | -6 | 18070 | 18070 | 16985.8 | 16830.3112 | 0.94 | 1.0092 | FALSE | FALSE | FALSE | 71 | FALSE | 0 | Green | Continue normal monitoring.
145940 | HCFWF6Z1175 | F6 Z1 :Stone Cladding | 26195 | 2013-08-26 12:00 | 2013-09-07 12:00 | 12 | 1636 | 100 | 100 | 0 | 7680 | 7680 | 7680 | 9460.3894 | 1 | 0.81181 | TRUE | FALSE | FALSE | 204.5 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145941 | HCFWF6Z1206 | F6 Z1 :Glass Wall Cladding | 26195 | 2014-04-02 08:00 | 2014-04-20 16:00 | 18 | 200 | 100 | 84 | -16 | 24948 | 24948 | 20956.32 | 30371.9108 | 0.84 | 0.68999 | TRUE | TRUE | TRUE | 25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145942 | HCFWF6Z1208 | F6 Z1 :Mirrors | 26345 | 2014-04-20 08:00 | 2014-04-30 16:00 | 10 | 224 | 100 | 100 | 0 | 16410 | 16410 | 16410 | 14256.9588 | 1 | 1.151 | FALSE | FALSE | FALSE | 28 | FALSE | 0 | Green | Continue normal monitoring.
145943 | HCFWF6Z1234 | F6 Z1 :Toilet & corian vanity tops | 26345 | 2014-04-20 08:00 | 2014-04-30 16:00 | 10 | 224 | 100 | 100 | 0 | 18000 | 18000 | 18000 | 17739.4538 | 1 | 1.0147 | FALSE | FALSE | FALSE | 28 | FALSE | 0 | Green | Continue normal monitoring.
145944 | HCFWF6Z2221 | F6 Z2 :Carpet Tiles | 26347 | 2013-12-31 08:00 | 2014-01-09 16:00 | 9 | 464 | 100 | 83 | -17 | 11025 | 11025 | 9150.75 | 11157.9551 | 0.83 | 0.82011 | TRUE | TRUE | TRUE | 58 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145945 | HCFWF6Z2218 | F6 Z2 :Stone Flooring | 26347 | 2013-12-02 08:00 | 2013-12-15 16:00 | 13 | 568 | 100 | 99 | -1 | 22659 | 22659 | 22432.41 | 21426.4821 | 0.99 | 1.0469 | FALSE | FALSE | FALSE | 71 | FALSE | 0 | Green | Continue normal monitoring.
145946 | HCFWF6Z2224 | F6 Z2 :Glass Wall Cladding | 26343 | 2014-04-02 08:00 | 2014-04-20 16:00 | 18 | 296 | 100 | 83 | -17 | 27882 | 27882 | 23142.06 | 30713.3936 | 0.83 | 0.75348 | TRUE | TRUE | TRUE | 37 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145947 | HCFWF6Z2223 | F6 Z2 :Gybsum Board Partitions | 26343 | 2013-06-26 08:00 | 2013-07-07 16:00 | 11 | 1088 | 100 | 97 | -3 | 11220 | 11220 | 10883.4 | 12411.0288 | 0.97 | 0.87691 | TRUE | FALSE | FALSE | 136 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145948 | HCFWF6Z3242 | F6 Z3 :Glass Wall Cladding | 26355 | 2014-04-02 08:00 | 2014-04-20 16:00 | 18 | 344 | 100 | 83 | -17 | 9162 | 9162 | 7604.46 | 10904.6279 | 0.83 | 0.69736 | TRUE | TRUE | TRUE | 43 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145949 | HCFWF6Z3240 | F6 Z3 :Gybsum Board Partitions | 26355 | 2013-08-01 08:00 | 2013-08-15 16:00 | 14 | 840 | 100 | 100 | 0 | 20762 | 20762 | 20762 | 23800.4711 | 1 | 0.87234 | TRUE | FALSE | FALSE | 105 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145950 | HCFWF6Z3209 | F6 Z3 :Stone Cladding | 26355 | 2014-04-02 08:00 | 2014-04-13 16:00 | 11 | 344 | 100 | 96 | -4 | 9647 | 9647 | 9261.12 | 10293.632 | 0.96 | 0.89969 | TRUE | FALSE | FALSE | 43 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145951 | HCFWF6Z3245 | F6 Z3 :Glass Doors | 26358 | 2014-04-14 08:00 | 2014-04-24 16:00 | 10 | 264 | 100 | 91 | -9 | 11810 | 11810 | 10747.1 | 13126.0439 | 0.91 | 0.81876 | TRUE | FALSE | FALSE | 33 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145952 | HCFWF6Z5266 | F6 Z5 :Stone Flooring All types | 26363 | 2014-02-27 10:00 | 2014-03-13 10:00 | 14 | 246 | 100 | 100 | 0 | 15162 | 15162 | 15162 | 14549.3872 | 1 | 1.0421 | FALSE | FALSE | FALSE | 30.75 | FALSE | 0 | Green | Continue normal monitoring.
145953 | HCFWF6Z5271 | F6 Z5 :Aluminum & Stainless Steel Skirting | 26363 | 2014-04-20 08:00 | 2014-04-30 16:00 | 10 | 208 | 100 | 96 | -4 | 6510 | 6510 | 6249.6 | 7077.8183 | 0.96 | 0.88298 | TRUE | FALSE | FALSE | 26 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145954 | HCFWF6Z5245 | F6 Z5 :Stone Base Skirting | 26363 | 2014-04-20 08:00 | 2014-04-30 16:00 | 10 | 208 | 100 | 89 | -11 | 12190 | 12190 | 10849.1 | 12746.9721 | 0.89 | 0.85111 | TRUE | TRUE | TRUE | 26 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145955 | HCFWF6Z5234 | F6 Z5 :Epoxy Screed Finish | 26363 | 2014-01-04 12:00 | 2014-01-16 12:00 | 12 | 940 | 100 | 100 | 0 | 18864 | 18864 | 18864 | 17040.564 | 1 | 1.107 | FALSE | FALSE | FALSE | 117.5 | FALSE | 0 | Green | Continue normal monitoring.
145956 | HCFWF6Z5276 | F6 Z5 :Glass Wall Cladding | 26359 | 2014-01-18 08:00 | 2014-02-04 16:00 | 17 | 856 | 100 | 80 | -20 | 28509 | 28509 | 22807.2 | 26998.5279 | 0.8 | 0.84476 | TRUE | TRUE | TRUE | 107 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145957 | HCFWF6Z5239 | F6 Z5 :Gybsum Board Partitions | 26359 | 2013-09-03 08:00 | 2013-09-14 16:00 | 11 | 664 | 100 | 100 | 0 | 14938 | 14938 | 14938 | 14440.2267 | 1 | 1.0345 | FALSE | FALSE | FALSE | 83 | FALSE | 0 | Green | Continue normal monitoring.
145958 | HCFWF6Z5268 | F6 Z5 :Quary Tiles | 26363 | 2014-04-08 08:00 | 2014-04-17 16:00 | 9 | 0 | 100 | 100 | 0 | 16344 | 16344 | 16344 | 19935.1662 | 1 | 0.81986 | TRUE | FALSE | FALSE | 0 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145959 | HCFWF6Z5273 | F6 Z5 :Stainless steel Wire Cloth Finish For Elev Lobby | 26359 | 2014-01-18 08:00 | 2014-01-28 16:00 | 10 | 856 | 100 | 100 | 0 | 5490 | 5490 | 5490 | 5172.4291 | 1 | 1.0614 | FALSE | FALSE | FALSE | 107 | FALSE | 0 | Green | Continue normal monitoring.
145960 | HCFWF6Z5244 | F6 Z5 :Aluminum Floor Tiles | 26363 | 2014-04-08 08:00 | 2014-04-19 16:00 | 11 | 208 | 100 | 100 | 0 | 12793 | 12793 | 12793 | 12354.1689 | 1 | 1.0355 | FALSE | FALSE | FALSE | 26 | FALSE | 0 | Green | Continue normal monitoring.
145961 | HCFWF6Z5278 | F6 Z5 :Wood Flooring | 26363 | 2014-04-08 08:00 | 2014-04-19 16:00 | 11 | 304 | 100 | 97 | -3 | 11330 | 11330 | 10990.1 | 11304.4129 | 0.97 | 0.9722 | FALSE | FALSE | FALSE | 38 | FALSE | 0 | Green | Continue normal monitoring.
145962 | HCFWF6Z5277 | F6 Z5 :Acoustical Painted Walls | 26359 | 2013-09-24 08:00 | 2013-10-05 16:00 | 11 | 1584 | 100 | 97 | -3 | 17413 | 17413 | 16890.61 | 19424.1509 | 0.97 | 0.86957 | TRUE | FALSE | FALSE | 198 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145963 | HCFWF6Z1207 | F6 Z1 :Acoustical Ceiling | 26344 | 2014-03-25 08:00 | 2014-04-05 16:00 | 11 | 320 | 100 | 93 | -7 | 18590 | 18590 | 17288.7 | 16680.7207 | 0.93 | 1.0364 | FALSE | FALSE | FALSE | 40 | FALSE | 0 | Green | Continue normal monitoring.
145964 | HCFWF6Z1239 | F6 Z1 :Stone Base Skirting | 26194 | 2013-12-16 08:00 | 2013-12-28 16:00 | 12 | 1024 | 100 | 94 | -6 | 20700 | 20700 | 19458 | 25493.6664 | 0.94 | 0.76325 | TRUE | FALSE | FALSE | 128 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145965 | HCFWF6Z4227 | F6 Z4 :Trawelled smooth Concrete screed | 26354 | 2013-12-05 08:00 | 2013-12-14 16:00 | 9 | 304 | 100 | 100 | 0 | 12204 | 12204 | 12204 | 14598.7725 | 1 | 0.83596 | TRUE | FALSE | FALSE | 38 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145966 | HCFWF6Z4226 | F6 Z4 :Foam Concrete Under Floorings | 26354 | 2013-11-17 08:00 | 2013-12-04 16:00 | 17 | 304 | 100 | 91 | -9 | 10965 | 10965 | 9978.15 | 11851.9197 | 0.91 | 0.8419 | TRUE | FALSE | FALSE | 38 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145967 | HCFWF6Z4229 | F6 Z4 :Rubber Flooring | 26354 | 2014-01-15 08:00 | 2014-01-26 16:00 | 11 | 504 | 100 | 83 | -17 | 15554 | 15554 | 12909.82 | 17414.494 | 0.83 | 0.74133 | TRUE | TRUE | TRUE | 63 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145968 | HCFWF6Z4230 | F6 Z4 :Rubber Skirting | 26354 | 2014-04-03 08:00 | 2014-04-05 16:00 | 2 | 400 | 100 | 100 | 0 | 2984 | 2984 | 2984 | 2556.2859 | 1 | 1.1673 | FALSE | FALSE | FALSE | 50 | FALSE | 0 | Green | Continue normal monitoring.
145969 | HCFWF6Z4232 | F6 Z4 :Block Works | 26356 | 2013-09-12 08:00 | 2013-09-23 16:00 | 11 | 428 | 100 | 82 | -18 | 21582 | 21582 | 17697.24 | 21270.7425 | 0.82 | 0.832 | TRUE | TRUE | TRUE | 53.5 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145970 | HCFWF6Z4234 | F6 Z4 :Plaster First Layer | 26356 | 2013-10-12 12:00 | 2013-10-27 10:00 | 14 | 304 | 100 | 99 | -1 | 10374 | 10374 | 10270.26 | 12119.5717 | 0.99 | 0.84741 | TRUE | FALSE | FALSE | 38 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145971 | HCFWF6Z4231 | F6 Z4 :Plaster Final Layer | 26356 | 2013-11-06 10:00 | 2013-11-16 16:00 | 10 | 304 | 100 | 100 | 0 | 10800 | 10800 | 10800 | 9514.7264 | 1 | 1.1351 | FALSE | FALSE | FALSE | 38 | FALSE | 0 | Green | Continue normal monitoring.
145972 | HCFWF6Z2237 | F6 Z4 :Paint Prime coat | 26356 | 2013-11-18 08:00 | 2013-12-01 16:00 | 13 | 880 | 100 | 91 | -9 | 15418 | 15418 | 14030.38 | 14846.3859 | 0.91 | 0.94504 | FALSE | FALSE | FALSE | 110 | FALSE | 0 | Green | Continue normal monitoring.
145973 | HCFWF6Z4228 | F6 Z4 :Paint putty coat | 26356 | 2013-12-02 08:00 | 2013-12-15 16:00 | 13 | 1136 | 100 | 86 | -14 | 12766 | 12766 | 10978.76 | 13839.8597 | 0.86 | 0.79327 | TRUE | TRUE | TRUE | 142 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145974 | HCFWF6Z2235 | F6 Z4 :Plaster Second Layer | 26356 | 2013-10-27 10:00 | 2013-11-06 10:00 | 10 | 304 | 100 | 100 | 0 | 16310 | 16310 | 16310 | 15536.3386 | 1 | 1.0498 | FALSE | FALSE | FALSE | 38 | FALSE | 0 | Green | Continue normal monitoring.
145975 | HCFWF6Z2240 | F6 Z4 :Plaster First Layer | 26353 | 2013-12-15 08:00 | 2013-12-23 16:00 | 8 | 304 | 100 | 90 | -10 | 13992 | 13992 | 12592.8 | 17120.4879 | 0.9 | 0.73554 | TRUE | FALSE | FALSE | 38 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145976 | HCFWF6Z2242 | F6 Z4 :Plaster Final Layer | 26353 | 2014-01-05 08:00 | 2014-01-13 16:00 | 8 | 304 | 100 | 80 | -20 | 9376 | 9376 | 7500.8 | 8461.1223 | 0.8 | 0.8865 | TRUE | TRUE | TRUE | 38 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145977 | HCFWF6Z2233 | F6 Z4 :Paint Prime coat | 26353 | 2014-01-15 08:00 | 2014-01-26 16:00 | 11 | 600 | 100 | 85 | -15 | 12430 | 12430 | 10565.5 | 14530.1447 | 0.85 | 0.72714 | TRUE | TRUE | TRUE | 75 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145978 | HCFWF6Z2239 | F6 Z4 :Paint putty coat | 26353 | 2014-01-27 08:00 | 2014-02-06 16:00 | 10 | 600 | 100 | 94 | -6 | 11600 | 11600 | 10904 | 12216.8819 | 0.94 | 0.89254 | TRUE | FALSE | FALSE | 75 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145979 | HCFWF6Z2245 | F6 Z4 :Gybsum Board Ceiling | 26353 | 2014-02-10 08:00 | 2014-02-25 16:00 | 15 | 584 | 100 | 94 | -6 | 17415 | 17415 | 16370.1 | 20029.5542 | 0.94 | 0.8173 | TRUE | FALSE | FALSE | 73 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145980 | HCFWF6Z2236 | F6 Z4 :Plaster Second Layer | 26353 | 2013-12-24 08:00 | 2014-01-04 16:00 | 11 | 304 | 100 | 98 | -2 | 21505 | 21505 | 21074.9 | 20952.0233 | 0.98 | 1.0059 | FALSE | FALSE | FALSE | 38 | FALSE | 0 | Green | Continue normal monitoring.
145981 | HCFWF6Z2238 | F6 Z4 :Steel Fire Rated Doors | 26341 | 2014-01-27 08:00 | 2014-02-06 16:00 | 10 | 792 | 100 | 90 | -10 | 13040 | 13040 | 11736 | 13767.5778 | 0.9 | 0.85244 | TRUE | FALSE | FALSE | 99 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145982 | HCFWF6Z2247 | F6 Z4 :Steel Doors | 26341 | 2014-04-08 08:00 | 2014-04-19 16:00 | 11 | 304 | 100 | 100 | 0 | 10098 | 10098 | 10098 | 12044.2293 | 1 | 0.83841 | TRUE | FALSE | FALSE | 38 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145983 | HCFWF6Z2244 | F6 Z4 :Wooden Doors | 26341 | 2014-04-08 08:00 | 2014-04-19 16:00 | 11 | 304 | 100 | 100 | 0 | 16357 | 16357 | 16357 | 16958.14 | 1 | 0.96455 | FALSE | FALSE | FALSE | 38 | FALSE | 0 | Green | Continue normal monitoring.
145984 | HCFWF6Z2241 | F6 Z4 :Metal Works | 26341 | 2014-03-27 08:00 | 2014-04-07 16:00 | 11 | 304 | 100 | 100 | 0 | 21758 | 21758 | 21758 | 21625.0139 | 1 | 1.0061 | FALSE | FALSE | FALSE | 38 | FALSE | 0 | Green | Continue normal monitoring.
145985 | HCFWF6Z2250 | F6 Z4 :Handrails & Railling | 26341 | 2014-03-27 08:00 | 2014-04-13 16:00 | 17 | 344 | 100 | 81 | -19 | 28611 | 28611 | 23174.91 | 30455.3267 | 0.81 | 0.76095 | TRUE | TRUE | TRUE | 43 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145986 | HCFWF6Z4246 | F6 Z4 :Carpet Tiles | 26354 | 2014-03-30 08:00 | 2014-04-07 16:00 | 8 | 0 | 100 | 93 | -7 | 9192 | 9192 | 8548.56 | 10450.7994 | 0.93 | 0.81798 | TRUE | FALSE | FALSE | 0 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145987 | HCFWF6Z4243 | F6 Z4 :Stone Flooring | 26354 | 2013-12-15 08:00 | 2013-12-29 16:00 | 14 | 480 | 100 | 81 | -19 | 20552 | 20552 | 16647.12 | 21115.6456 | 0.81 | 0.78838 | TRUE | TRUE | TRUE | 60 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145988 | HCFWF6Z2249 | F6 Z4 :Glass Wall Cladding | 26356 | 2014-01-18 08:00 | 2014-02-04 16:00 | 17 | 808 | 100 | 100 | 0 | 18513 | 18513 | 18513 | 22688.6218 | 1 | 0.81596 | TRUE | FALSE | FALSE | 101 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145989 | HCFWF6Z2248 | F6 Z4 :Gybsum Board Partitions | 26356 | 2013-09-12 08:00 | 2013-09-23 16:00 | 11 | 1664 | 100 | 83 | -17 | 17600 | 17600 | 14608 | 17036.4186 | 0.83 | 0.85746 | TRUE | TRUE | TRUE | 208 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145990 | HCFWF7AZ050 | F7 :Decorative Stone Works | 26007 | 2014-01-06 08:00 | 2014-01-18 16:00 | 12 | 928 | 100 | 96 | -4 | 12096 | 12096 | 11612.16 | 12582.0831 | 0.96 | 0.92291 | FALSE | FALSE | FALSE | 116 | FALSE | 0 | Green | Continue normal monitoring.
145991 | HCFWF7AZ060 | F7 :Acoustic Wall Panels | 26007 | 2014-01-06 08:00 | 2014-01-18 16:00 | 12 | 808 | 100 | 82 | -18 | 11280 | 11280 | 9249.6 | 13003.2576 | 0.82 | 0.71133 | TRUE | TRUE | TRUE | 101 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145992 | HCFWF7AZ120 | F7 :Greean Area | 26007 | 2014-01-19 08:00 | 2014-02-04 16:00 | 16 | 808 | 100 | 92 | -8 | 28432 | 28432 | 26157.44 | 32004.4363 | 0.92 | 0.81731 | TRUE | FALSE | FALSE | 101 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145993 | HCFWF7AZ130 | F7 :Steel Post | 26007 | 2014-01-06 08:00 | 2014-01-23 16:00 | 17 | 888 | 100 | 88 | -12 | 24140 | 24140 | 21243.2 | 28858.318 | 0.88 | 0.73612 | TRUE | TRUE | TRUE | 111 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145994 | HCFWF10000 | Start Finishing Works First Floor | 25794 | 2013-03-02 08:00 | 2013-03-02 08:00 | 1 | 488 | 100 | 86 | -14 | 1269 | 1269 | 1091.34 | 1584.6303 | 0.86 | 0.6887 | TRUE | TRUE | TRUE | 61 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
145995 | HCFWF10001 | End Finishing Works First Floor | 25794 | 2014-03-18 16:00 | 2014-03-18 16:00 | 1 | 520 | 100 | 94 | -6 | 1843 | 1843 | 1732.42 | 1881.23 | 0.94 | 0.9209 | FALSE | FALSE | FALSE | 65 | FALSE | 0 | Green | Continue normal monitoring.
145996 | HCFWF20000 | Start Finishing Works Second Floor | 25816 | 2013-03-09 08:00 | 2013-03-09 08:00 | 1 | 624 | 100 | 100 | 0 | 762 | 762 | 762 | 681.5788 | 1 | 1.118 | FALSE | FALSE | FALSE | 78 | FALSE | 0 | Green | Continue normal monitoring.
145997 | HCFWF20001 | End Finishing Works Second Floor | 25816 | 2014-04-01 16:00 | 2014-04-01 16:00 | 1 | 424 | 100 | 100 | 0 | 1897 | 1897 | 1897 | 1635.5296 | 1 | 1.1599 | FALSE | FALSE | FALSE | 53 | FALSE | 0 | Green | Continue normal monitoring.
145998 | HCFWF30000 | Start Finishing Works Third Floor | 25814 | 2013-03-16 08:00 | 2013-03-16 08:00 | 1 | 768 | 100 | 100 | 0 | 1136 | 1136 | 1136 | 1295.8929 | 1 | 0.87662 | TRUE | FALSE | FALSE | 96 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
145999 | HCFWF30001 | End Finishing Works Third Floor | 25814 | 2014-04-15 16:00 | 2014-04-15 16:00 | 1 | 328 | 100 | 90 | -10 | 1690 | 1690 | 1521 | 2027.3332 | 0.9 | 0.75025 | TRUE | FALSE | FALSE | 41 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146000 | HCFWF40000 | Start Finishing Works Forth Floor | 25815 | 2013-03-23 08:00 | 2013-03-23 08:00 | 1 | 888 | 100 | 99 | -1 | 958 | 958 | 948.42 | 898.8771 | 0.99 | 1.0551 | FALSE | FALSE | FALSE | 111 | FALSE | 0 | Green | Continue normal monitoring.
146001 | HCFWF40001 | End Finishing Works Forth Floor | 25815 | 2014-04-29 16:00 | 2014-04-29 16:00 | 1 | 232 | 100 | 81 | -19 | 1498 | 1498 | 1213.38 | 1368.2421 | 0.81 | 0.88682 | TRUE | TRUE | TRUE | 29 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146002 | HCFWF50000 | Start Finishing Works Fifth Floor | 25768 | 2013-03-30 08:00 | 2013-03-30 08:00 | 1 | 1032 | 100 | 94 | -6 | 1803 | 1803 | 1694.82 | 1577.4123 | 0.94 | 1.0744 | FALSE | FALSE | FALSE | 129 | FALSE | 0 | Green | Continue normal monitoring.
146003 | HCFWF50001 | End Finishing Works Fifth Floor | 25768 | 2014-05-19 16:00 | 2014-05-19 16:00 | 1 | 104 | 100 | 93 | -7 | 1199 | 1199 | 1115.07 | 1413.7183 | 0.93 | 0.78875 | TRUE | FALSE | FALSE | 13 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146004 | HCFWF60000 | Start Finishing Works Sixth Floor | 25769 | 2013-04-06 08:00 | 2013-04-06 08:00 | 1 | 1176 | 100 | 99 | -1 | 801 | 801 | 792.99 | 780.6168 | 0.99 | 1.0159 | FALSE | FALSE | FALSE | 147 | FALSE | 0 | Green | Continue normal monitoring.
146005 | HCFWF60001 | End Finishing Works Sixth Floor | 25769 | 2014-06-04 16:00 | 2014-06-04 16:00 | 1 | 8 | 100 | 100 | 0 | 1741 | 1741 | 1741 | 1759.5917 | 1 | 0.98943 | FALSE | FALSE | FALSE | 1 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146006 | HCFWF70000 | F7 :Start Finishing Works Seventh Floor | 25775 | 2013-09-18 08:00 | 2013-09-18 08:00 | 1 | 1704 | 100 | 90 | -10 | 1625 | 1625 | 1462.5 | 1708.0376 | 0.9 | 0.85625 | TRUE | FALSE | FALSE | 213 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146007 | HCFWF70001 | F7 :End Finishing Works Seventh Floor | 25775 | 2014-04-21 16:00 | 2014-04-21 16:00 | 1 | 288 | 100 | 100 | 0 | 1053 | 1053 | 1053 | 1248.6277 | 1 | 0.84333 | TRUE | FALSE | FALSE | 36 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146008 | HMMOAZ050 | Removal of Tower crane # 1 | 25702 | 2014-05-14 08:00 | 2014-06-05 16:00 | 22 | 0 | 100 | 82 | -18 | 17314 | 17314 | 14197.48 | 19224.3106 | 0.82 | 0.73852 | TRUE | TRUE | TRUE | 0 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
146009 | HMMOAZ060 | Removal of Tower crane # 2 | 25702 | 2014-02-03 08:00 | 2014-02-18 16:00 | 15 | 104 | 100 | 96 | -4 | 25350 | 25350 | 24336 | 27784.2553 | 0.96 | 0.87589 | TRUE | FALSE | FALSE | 13 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146010 | HMMOAZ070 | Removal of Tower crane # 3 | 25702 | 2013-08-07 08:00 | 2013-08-26 16:00 | 19 | 0 | 100 | 100 | 0 | 21280 | 21280 | 21280 | 19583.3209 | 1 | 1.0866 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146011 | CIDEEL000 | PERMANENT POWER | 25789 | 2014-06-17 17:00 | 2014-06-17 17:00 | 1 | 0 | 100 | 91 | -9 | 1505 | 1505 | 1369.55 | 1588.1903 | 0.91 | 0.86233 | TRUE | FALSE | FALSE | 0 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146012 | ATWTPR000 | CONNECT THE PROJECT TO WATER NETWORK | 25858 | 2014-07-23 16:00 | 2014-07-23 16:00 | 1 | 1 | 100 | 100 | 0 | 535 | 535 | 535 | 607.8415 | 1 | 0.88016 | TRUE | FALSE | FALSE | 0.125 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146013 | HCMEB4Z1120 | B4 Z1 :Blocks Start Date for All Parts | 26414 | 2012-10-11 16:00 | 2012-10-11 16:00 | 1 | 560 | 100 | 100 | 0 | 1243 | 1243 | 1243 | 1540.4553 | 1 | 0.8069 | TRUE | FALSE | FALSE | 70 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146014 | HCMEB4Z1130 | B4 Z1 :Tiling Finish Date for All Parts | 26414 | 2013-02-27 14:00 | 2013-02-27 14:00 | 1 | 666 | 100 | 100 | 0 | 852 | 852 | 852 | 792.8393 | 1 | 1.0746 | FALSE | FALSE | FALSE | 83.25 | FALSE | 0 | Green | Continue normal monitoring.
146015 | HCMEB4Z1140 | B4 Z1 :Plastering Finish Date for All Parts | 26414 | 2012-11-17 12:00 | 2012-11-17 12:00 | 1 | 2035 | 100 | 100 | 0 | 572 | 572 | 572 | 488.3835 | 1 | 1.1712 | FALSE | FALSE | FALSE | 254.375 | FALSE | 0 | Green | Continue normal monitoring.
146016 | HCMEB4Z1150 | B4 Z1 :Gypsum Boards Finish Date for All Parts | 26414 | 2013-10-23 16:00 | 2013-10-23 16:00 | 1 | 1432 | 100 | 94 | -6 | 1147 | 1147 | 1078.18 | 1009.4983 | 0.94 | 1.068 | FALSE | FALSE | FALSE | 179 | FALSE | 0 | Green | Continue normal monitoring.
146017 | HCMEB4Z1180 | B4 Z1 :Electrical Coduits & Boards F.F for All Systems | 26414 | 2012-10-11 16:00 | 2012-10-29 16:00 | 18 | 1416 | 100 | 95 | -5 | 33768 | 33768 | 32079.6 | 33779.5144 | 0.95 | 0.94968 | FALSE | FALSE | FALSE | 177 | FALSE | 0 | Green | Continue normal monitoring.
146018 | HCMEB4Z1190 | B4 Z1 :Electrical Boards Seconed Fix | 26414 | 2013-03-28 16:00 | 2013-04-15 16:00 | 18 | 952 | 100 | 84 | -16 | 28674 | 28674 | 24086.16 | 33784.2189 | 0.84 | 0.71294 | TRUE | TRUE | TRUE | 119 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146019 | HCMEB4Z1200 | B4 Z1 :Cable Tray Installation | 26414 | 2013-09-25 16:00 | 2013-10-09 16:00 | 14 | 0 | 100 | 100 | 0 | 12936 | 12936 | 12936 | 11032.556 | 1 | 1.1725 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146020 | HCMEB4Z1210 | B4 Z1 :Electrcial Wiring | 26414 | 2013-04-29 08:00 | 2013-05-24 17:00 | 25 | 215 | 100 | 99 | -1 | 37450 | 37450 | 37075.5 | 38674.3243 | 0.99 | 0.95866 | FALSE | FALSE | FALSE | 26.875 | FALSE | 0 | Green | Continue normal monitoring.
146021 | HCMEB4Z1220 | B4 Z1 :Cable Laying | 26414 | 2013-10-09 16:00 | 2013-10-23 16:00 | 14 | 0 | 100 | 85 | -15 | 16898 | 16898 | 14363.3 | 16588.6356 | 0.85 | 0.86585 | TRUE | TRUE | TRUE | 0 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
146022 | HCMEB4Z1230 | B4 Z1 :Electrical Final Fix for All Systems & Boards (Vertical Elements) | 26414 | 2013-12-04 16:00 | 2013-12-18 16:00 | 14 | 888 | 100 | 98 | -2 | 14840 | 14840 | 14543.2 | 12925.5314 | 0.98 | 1.1252 | FALSE | FALSE | FALSE | 111 | FALSE | 0 | Green | Continue normal monitoring.
146023 | HCMEB4Z1240 | B4 Z1 :Electrical Final Fix for All Systems (Horizantel Elements) | 26414 | 2013-12-18 16:00 | 2014-01-01 16:00 | 14 | 888 | 100 | 100 | 0 | 18578 | 18578 | 18578 | 19137.0959 | 1 | 0.97078 | FALSE | FALSE | FALSE | 111 | FALSE | 0 | Green | Continue normal monitoring.
146024 | HCMEB4Z1030 | B4 Z1 :All Vertical Piping Works | 26612 | 2012-10-15 08:00 | 2012-10-26 17:00 | 11 | 471 | 100 | 84 | -16 | 16005 | 16005 | 13444.2 | 15235.1512 | 0.84 | 0.88245 | TRUE | TRUE | TRUE | 58.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146025 | HCMEB4Z1040 | B4 Z1 :All Horizantal Piping Works | 26612 | 2012-10-29 08:00 | 2012-12-07 17:00 | 39 | 471 | 100 | 82 | -18 | 39624 | 39624 | 32491.68 | 39257.6339 | 0.82 | 0.82765 | TRUE | TRUE | TRUE | 58.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146026 | HCMEB4Z1050 | B4 Z1 :Mechanical Final Fix | 26612 | 2013-04-15 08:00 | 2013-05-10 17:00 | 25 | 471 | 100 | 100 | 0 | 23175 | 23175 | 23175 | 26239.8039 | 1 | 0.8832 | TRUE | FALSE | FALSE | 58.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146027 | HCMEB4Z1060 | B4 Z1 :Horizontal F.F Piping Work | 26420 | 2012-10-15 08:00 | 2012-11-09 17:00 | 25 | 1671 | 100 | 80 | -20 | 16475 | 16475 | 13180 | 17440.771 | 0.8 | 0.7557 | TRUE | TRUE | TRUE | 208.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146028 | HCMEB4Z1070 | B4 Z1 :Fire Hose Cabinets | 26420 | 2012-11-12 08:00 | 2012-11-23 17:00 | 11 | 1671 | 100 | 100 | 0 | 7128 | 7128 | 7128 | 6414.1947 | 1 | 1.1113 | FALSE | FALSE | FALSE | 208.875 | FALSE | 0 | Green | Continue normal monitoring.
146029 | HCMEB4Z1080 | B4 Z1 :Sprinklers Final Fix | 26420 | 2013-11-04 16:00 | 2013-11-18 16:00 | 14 | 264 | 100 | 100 | 0 | 17850 | 17850 | 17850 | 22036.9998 | 1 | 0.81 | TRUE | FALSE | FALSE | 33 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146030 | HCMEB4Z1290 | B4 Z1 :Duct Installation& Dusct Accecories Installation, Fan coil Unit | 26614 | 2013-07-11 16:00 | 2013-07-23 16:00 | 12 | 96 | 100 | 85 | -15 | 21036 | 21036 | 17880.6 | 23231.4075 | 0.85 | 0.76967 | TRUE | TRUE | TRUE | 12 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146031 | HCMEB4Z1300 | B4 Z1 :Duct Insulation Work | 26614 | 2013-07-23 16:00 | 2013-08-13 16:00 | 21 | 96 | 100 | 94 | -6 | 11886 | 11886 | 11172.84 | 13744.3448 | 0.94 | 0.8129 | TRUE | FALSE | FALSE | 12 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146032 | HCMEB4Z1310 | B4 Z1 :Exhaust Fans | 26614 | 2013-08-13 16:00 | 2013-09-03 16:00 | 21 | 96 | 100 | 81 | -19 | 31773 | 31773 | 25736.13 | 28013.7858 | 0.81 | 0.9187 | FALSE | TRUE | TRUE | 12 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146033 | HCMEB4Z1320 | B4 Z1 :Grills & Diffusers | 26614 | 2013-11-28 16:00 | 2013-12-17 16:00 | 19 | 0 | 100 | 100 | 0 | 16720 | 16720 | 16720 | 14526.7264 | 1 | 1.151 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146034 | HCMEB4Z1330 | B4 Z1 :Mechanical final Fix | 26614 | 2013-12-17 16:00 | 2014-01-02 16:00 | 16 | 0 | 100 | 82 | -18 | 8912 | 8912 | 7307.84 | 7644.5284 | 0.82 | 0.95596 | FALSE | TRUE | TRUE | 0 | TRUE | 4 | Orange | Develop recovery plan and review schedule and cost exposure.
146035 | HCMERF00040 | RF :Duct Work, Fan coil Unit | 26252 | 2013-09-18 08:00 | 2013-10-16 17:00 | 28 | 1216 | 100 | 96 | -4 | 49896 | 49896 | 47900.16 | 46179.6267 | 0.96 | 1.0373 | FALSE | FALSE | FALSE | 152 | FALSE | 0 | Green | Continue normal monitoring.
146036 | HCMERF00050 | RF :Water Treatment Unit | 26252 | 2013-09-18 08:00 | 2013-10-10 17:00 | 22 | 1216 | 100 | 100 | 0 | 18502 | 18502 | 18502 | 18793.6537 | 1 | 0.98448 | FALSE | FALSE | FALSE | 152 | FALSE | 0 | Green | Continue normal monitoring.
146037 | HCMERF00070 | RF :Air Handing Unit | 26252 | 2013-10-12 08:00 | 2013-11-14 17:00 | 33 | 1216 | 100 | 100 | 0 | 54549 | 54549 | 54549 | 66786.0019 | 1 | 0.81677 | TRUE | FALSE | FALSE | 152 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146038 | HCMERF00080 | RF :Switch Boards | 26252 | 2013-11-16 08:00 | 2013-12-09 17:00 | 23 | 1216 | 100 | 91 | -9 | 28198 | 28198 | 25660.18 | 29123.5673 | 0.91 | 0.88108 | TRUE | FALSE | FALSE | 152 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146039 | HCMERF00060 | RF :Risers Works | 26252 | 2013-09-18 08:00 | 2014-04-17 17:00 | 211 | 336 | 100 | 97 | -3 | 357645 | 357645 | 346915.65 | 345521.5649 | 0.97 | 1.004 | FALSE | FALSE | FALSE | 42 | FALSE | 0 | Green | Continue normal monitoring.
146040 | HCMERF00010 | RF :All Vertical Piping Works | 26255 | 2013-10-28 08:00 | 2013-11-08 17:00 | 11 | 800 | 100 | 94 | -6 | 13959 | 13959 | 13121.46 | 15002.7717 | 0.94 | 0.8746 | TRUE | FALSE | FALSE | 100 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146041 | HCMERF00020 | RF :All Horizantal Piping Works | 26255 | 2013-11-11 08:00 | 2013-12-20 17:00 | 39 | 800 | 100 | 91 | -9 | 43407 | 43407 | 39500.37 | 38839.4477 | 0.91 | 1.017 | FALSE | FALSE | FALSE | 100 | FALSE | 0 | Green | Continue normal monitoring.
146042 | HCMERF00030 | RF :Mechanical Final Fix | 26255 | 2013-12-23 08:00 | 2014-01-17 17:00 | 25 | 800 | 100 | 95 | -5 | 43300 | 43300 | 41135 | 47361.642 | 0.95 | 0.86853 | TRUE | FALSE | FALSE | 100 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146043 | HCMERF00120 | RF :Electrical Conduits & Boards F.F | 26260 | 2013-09-18 08:00 | 2013-10-03 17:00 | 15 | 943 | 100 | 100 | 0 | 12795 | 12795 | 12795 | 13784.9847 | 1 | 0.92818 | FALSE | FALSE | FALSE | 117.875 | FALSE | 0 | Green | Continue normal monitoring.
146044 | HCMERF00150 | RF :Electrical Wiring Works | 26260 | 2013-10-04 08:00 | 2013-10-24 17:00 | 20 | 943 | 100 | 87 | -13 | 39880 | 39880 | 34695.6 | 46531.8729 | 0.87 | 0.74563 | TRUE | TRUE | TRUE | 117.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146045 | HCMERF00160 | RF :Electrical Boards Second Fix | 26260 | 2013-10-25 08:00 | 2013-11-11 17:00 | 17 | 943 | 100 | 100 | 0 | 10455 | 10455 | 10455 | 13013.0776 | 1 | 0.80342 | TRUE | FALSE | FALSE | 117.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146046 | HCMERF00170 | RF :Electrical Final Fix | 26260 | 2014-03-26 08:00 | 2014-04-15 17:00 | 20 | 295 | 100 | 93 | -7 | 35740 | 35740 | 33238.2 | 33965.4872 | 0.93 | 0.97859 | FALSE | FALSE | FALSE | 36.875 | FALSE | 0 | Green | Continue normal monitoring.
146047 | HCMERF00140 | RF :All Risers Works | 26260 | 2013-09-18 08:00 | 2014-04-15 17:00 | 209 | 280 | 100 | 100 | 0 | 242649 | 242649 | 242649 | 255718.7013 | 1 | 0.94889 | FALSE | FALSE | FALSE | 35 | FALSE | 0 | Green | Continue normal monitoring.
146048 | HCMERF00130 | RF :Earthing System Works | 26260 | 2014-03-19 08:00 | 2014-04-15 17:00 | 27 | 304 | 100 | 96 | -4 | 53055 | 53055 | 50932.8 | 64384.6917 | 0.96 | 0.79107 | TRUE | FALSE | FALSE | 38 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146049 | HCMEB4Z1340 | B4 Z1 :All Vertical Piping Works | 26400 | 2012-10-15 08:00 | 2012-10-26 17:00 | 11 | 471 | 100 | 100 | 0 | 10472 | 10472 | 10472 | 12190.2034 | 1 | 0.85905 | TRUE | FALSE | FALSE | 58.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146050 | HCMEB4Z1350 | B4 Z1 :All Horizantal Piping Works | 26400 | 2012-10-29 08:00 | 2012-12-07 17:00 | 39 | 471 | 100 | 100 | 0 | 30654 | 30654 | 30654 | 32032.2811 | 1 | 0.95697 | FALSE | FALSE | FALSE | 58.875 | FALSE | 0 | Green | Continue normal monitoring.
146051 | HCMEB4Z1360 | B4 Z1 :Mechanical Final Fix | 26400 | 2013-04-15 08:00 | 2013-05-10 17:00 | 25 | 471 | 100 | 87 | -13 | 45650 | 45650 | 39715.5 | 56064.9863 | 0.87 | 0.70838 | TRUE | TRUE | TRUE | 58.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146052 | HCMEB4Z2125 | B4 Z2 :Blocks Start Date for All Parts | 26431 | 2012-10-07 16:00 | 2012-10-07 16:00 | 1 | 1793 | 100 | 94 | -6 | 1516 | 1516 | 1425.04 | 1323.3083 | 0.94 | 1.0769 | FALSE | FALSE | FALSE | 224.125 | FALSE | 0 | Green | Continue normal monitoring.
146053 | HCMEB4Z2135 | B4 Z2 :Tiling Finish Date for All Parts | 26431 | 2013-02-27 14:00 | 2013-02-27 14:00 | 1 | 666 | 100 | 100 | 0 | 810 | 810 | 810 | 990.1436 | 1 | 0.81806 | TRUE | FALSE | FALSE | 83.25 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146054 | HCMEB4Z2145 | B4 Z2 :Plastering Finish Date for All Parts | 26431 | 2012-11-17 12:00 | 2012-11-17 12:00 | 1 | 2123 | 100 | 93 | -7 | 707 | 707 | 657.51 | 615.2335 | 0.93 | 1.0687 | FALSE | FALSE | FALSE | 265.375 | FALSE | 0 | Green | Continue normal monitoring.
146055 | HCMEB4Z2155 | B4 Z2 :Gypsum Boards Finish Date for All Parts | 26431 | 2013-10-22 16:00 | 2013-10-22 16:00 | 1 | 1440 | 100 | 97 | -3 | 1117 | 1117 | 1083.49 | 1193.9858 | 0.97 | 0.90746 | FALSE | FALSE | FALSE | 180 | FALSE | 0 | Green | Continue normal monitoring.
146056 | HCMEB4Z2185 | B4 Z2 :Electrical Coduits & Boards F.F for All Systems | 26431 | 2012-10-08 08:00 | 2012-10-23 17:00 | 15 | 1519 | 100 | 99 | -1 | 14175 | 14175 | 14033.25 | 17097.5502 | 0.99 | 0.82078 | TRUE | FALSE | FALSE | 189.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146057 | HCMEB4Z2195 | B4 Z2 :Electrical Boards Seconed Fix | 26431 | 2013-03-28 16:00 | 2013-04-15 16:00 | 18 | 1024 | 100 | 86 | -14 | 21042 | 21042 | 18096.12 | 20096.9696 | 0.86 | 0.90044 | FALSE | TRUE | TRUE | 128 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146058 | HCMEB4Z2205 | B4 Z2 :Cable Tray Installation | 26431 | 2013-09-25 16:00 | 2013-10-09 16:00 | 14 | 88 | 100 | 82 | -18 | 15848 | 15848 | 12995.36 | 16464.4777 | 0.82 | 0.7893 | TRUE | TRUE | TRUE | 11 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146059 | HCMEB4Z2215 | B4 Z2 :Electrcial Wiring | 26431 | 2013-04-29 08:00 | 2013-05-24 17:00 | 25 | 215 | 100 | 100 | 0 | 13850 | 13850 | 13850 | 13569.282 | 1 | 1.0207 | FALSE | FALSE | FALSE | 26.875 | FALSE | 0 | Green | Continue normal monitoring.
146060 | HCMEB4Z2225 | B4 Z2 :Cable Laying | 26431 | 2013-10-09 16:00 | 2013-10-23 16:00 | 14 | 88 | 100 | 91 | -9 | 19754 | 19754 | 17976.14 | 24314.3604 | 0.91 | 0.73932 | TRUE | FALSE | FALSE | 11 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146061 | HCMEB4Z2235 | B4 Z2 :Electrical Final Fix for All Systems & Boards (Vertical Elements) | 26431 | 2013-12-04 16:00 | 2013-12-18 16:00 | 14 | 888 | 100 | 100 | 0 | 21490 | 21490 | 21490 | 25346.5575 | 1 | 0.84785 | TRUE | FALSE | FALSE | 111 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146062 | HCMEB4Z2245 | B4 Z2 :Electrical Final Fix for All Systems (Horizantel Elements) | 26431 | 2013-12-18 16:00 | 2014-01-01 16:00 | 14 | 888 | 100 | 100 | 0 | 16184 | 16184 | 16184 | 18346.1922 | 1 | 0.88214 | TRUE | FALSE | FALSE | 111 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146063 | HCMEB4Z2035 | B4 Z2 :All Vertical Piping Works | 26399 | 2012-10-15 08:00 | 2012-10-26 17:00 | 11 | 631 | 100 | 100 | 0 | 21153 | 21153 | 21153 | 22952.0795 | 1 | 0.92162 | FALSE | FALSE | FALSE | 78.875 | FALSE | 0 | Green | Continue normal monitoring.
146064 | HCMEB4Z2045 | B4 Z2 :All Horizantal Piping Works | 26399 | 2012-10-29 08:00 | 2012-12-07 17:00 | 39 | 631 | 100 | 100 | 0 | 57681 | 57681 | 57681 | 67961.872 | 1 | 0.84873 | TRUE | FALSE | FALSE | 78.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146065 | HCMEB4Z2055 | B4 Z2 :Mechanical Final Fix | 26399 | 2013-04-15 08:00 | 2013-05-10 17:00 | 25 | 631 | 100 | 82 | -18 | 25350 | 25350 | 20787 | 25525.0878 | 0.82 | 0.81438 | TRUE | TRUE | TRUE | 78.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146066 | HCMEB4Z2065 | B4 Z2 :Horizontal F.F Piping Work | 26636 | 2012-10-08 08:00 | 2012-11-02 17:00 | 25 | 1791 | 100 | 99 | -1 | 18400 | 18400 | 18216 | 18933.9817 | 0.99 | 0.96208 | FALSE | FALSE | FALSE | 223.875 | FALSE | 0 | Green | Continue normal monitoring.
146067 | HCMEB4Z2075 | B4 Z2 :Fire Hose Cabinets | 26636 | 2012-11-05 08:00 | 2012-11-16 17:00 | 11 | 1791 | 100 | 93 | -7 | 19822 | 19822 | 18434.46 | 22636.7376 | 0.93 | 0.81436 | TRUE | FALSE | FALSE | 223.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146068 | HCMEB4Z2085 | B4 Z2 :Sprinklers Final Fix | 26636 | 2013-11-04 16:00 | 2013-11-18 16:00 | 14 | 344 | 100 | 94 | -6 | 11858 | 11858 | 11146.52 | 11776.2024 | 0.94 | 0.94653 | FALSE | FALSE | FALSE | 43 | FALSE | 0 | Green | Continue normal monitoring.
146069 | HCMEB4Z2295 | B4 Z2 :Duct Installation& Dusct Accecories Installation, Fan coil Unit | 26637 | 2013-07-11 16:00 | 2013-07-23 16:00 | 12 | 121 | 100 | 100 | 0 | 13512 | 13512 | 13512 | 11830.5718 | 1 | 1.1421 | FALSE | FALSE | FALSE | 15.125 | FALSE | 0 | Green | Continue normal monitoring.
146070 | HCMEB4Z2305 | B4 Z2 :Duct Insulation Work | 26637 | 2013-07-23 16:00 | 2013-08-13 16:00 | 21 | 121 | 100 | 100 | 0 | 34167 | 34167 | 34167 | 30057.8662 | 1 | 1.1367 | FALSE | FALSE | FALSE | 15.125 | FALSE | 0 | Green | Continue normal monitoring.
146071 | HCMEB4Z2315 | B4 Z2 :Exhaust Fans | 26637 | 2013-08-13 16:00 | 2013-09-03 16:00 | 21 | 121 | 100 | 93 | -7 | 23709 | 23709 | 22049.37 | 21246.7047 | 0.93 | 1.0378 | FALSE | FALSE | FALSE | 15.125 | FALSE | 0 | Green | Continue normal monitoring.
146072 | HCMEB4Z2325 | B4 Z2 :Grills & Diffusers | 26637 | 2013-11-28 16:00 | 2013-12-12 16:00 | 14 | 25 | 100 | 86 | -14 | 24794 | 24794 | 21322.84 | 29700.0515 | 0.86 | 0.71794 | TRUE | TRUE | TRUE | 3.125 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
146073 | HCMEB4Z2335 | B4 Z2 :Mechanical final Fix | 26637 | 2013-12-12 16:00 | 2013-12-26 16:00 | 14 | 25 | 100 | 96 | -4 | 12082 | 12082 | 11598.72 | 12551.8759 | 0.96 | 0.92406 | FALSE | FALSE | FALSE | 3.125 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146074 | HCMEB4Z2345 | B4 Z2 :All Vertical Piping Works | 26398 | 2012-10-15 08:00 | 2012-10-26 17:00 | 11 | 631 | 100 | 100 | 0 | 9020 | 9020 | 9020 | 10239.0796 | 1 | 0.88094 | TRUE | FALSE | FALSE | 78.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146075 | HCMEB4Z2355 | B4 Z2 :All Horizantal Piping Works | 26398 | 2012-10-29 08:00 | 2012-12-07 17:00 | 39 | 631 | 100 | 91 | -9 | 30615 | 30615 | 27859.65 | 30834.3177 | 0.91 | 0.90353 | FALSE | FALSE | FALSE | 78.875 | FALSE | 0 | Green | Continue normal monitoring.
146076 | HCMEB4Z2365 | B4 Z2 :Mechanical Final Fix | 26398 | 2013-04-15 08:00 | 2013-05-10 17:00 | 25 | 631 | 100 | 99 | -1 | 16200 | 16200 | 16038 | 15446.4469 | 0.99 | 1.0383 | FALSE | FALSE | FALSE | 78.875 | FALSE | 0 | Green | Continue normal monitoring.
146077 | HCMEB4Z3130 | B4 Z3 :Blocks Start Date for All Parts | 26638 | 2012-10-31 16:00 | 2012-10-31 16:00 | 1 | 1752 | 100 | 83 | -17 | 1607 | 1607 | 1333.81 | 1589.1251 | 0.83 | 0.83934 | TRUE | TRUE | TRUE | 219 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146078 | HCMEB4Z3140 | B4 Z3 :Tiling Finish Date for All Parts | 26638 | 2013-11-12 16:00 | 2013-11-12 16:00 | 1 | 336 | 100 | 88 | -12 | 905 | 905 | 796.4 | 1056.744 | 0.88 | 0.75364 | TRUE | TRUE | TRUE | 42 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146079 | HCMEB4Z3150 | B4 Z3 :Plastering Finish Date for All Parts | 26638 | 2013-01-14 10:00 | 2013-01-14 10:00 | 1 | 1853 | 100 | 85 | -15 | 1477 | 1477 | 1255.45 | 1624.8277 | 0.85 | 0.77267 | TRUE | TRUE | TRUE | 231.625 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146080 | HCMEB4Z3160 | B4 Z3 :Gypsum Boards Finish Date for All Parts | 26638 | 2013-10-22 16:00 | 2013-10-22 16:00 | 1 | 1440 | 100 | 95 | -5 | 955 | 955 | 907.25 | 1169.9284 | 0.95 | 0.77547 | TRUE | FALSE | FALSE | 180 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146081 | HCMEB4Z3190 | B4 Z3 :Electrical Coduits & Boards F.F for All Systems | 26638 | 2012-10-31 16:00 | 2012-11-16 16:00 | 16 | 1472 | 100 | 100 | 0 | 20784 | 20784 | 20784 | 23317.1936 | 1 | 0.89136 | TRUE | FALSE | FALSE | 184 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146082 | HCMEB4Z3200 | B4 Z3 :Electrical Boards Seconed Fix | 26638 | 2013-03-28 16:00 | 2013-04-15 16:00 | 18 | 1120 | 100 | 100 | 0 | 30312 | 30312 | 30312 | 32678.5382 | 1 | 0.92758 | FALSE | FALSE | FALSE | 140 | FALSE | 0 | Green | Continue normal monitoring.
146083 | HCMEB4Z3210 | B4 Z3 :Cable Tray Installation | 26638 | 2013-09-25 16:00 | 2013-10-09 16:00 | 14 | 168 | 100 | 100 | 0 | 21168 | 21168 | 21168 | 23159.4516 | 1 | 0.91401 | FALSE | FALSE | FALSE | 21 | FALSE | 0 | Green | Continue normal monitoring.
146084 | HCMEB4Z3220 | B4 Z3 :Electrcial Wiring | 26638 | 2013-11-12 16:00 | 2013-11-22 16:00 | 10 | 296 | 100 | 100 | 0 | 12830 | 12830 | 12830 | 15741.7502 | 1 | 0.81503 | TRUE | FALSE | FALSE | 37 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146085 | HCMEB4Z3230 | B4 Z3 :Cable Laying | 26638 | 2013-10-09 16:00 | 2013-10-23 16:00 | 14 | 168 | 100 | 100 | 0 | 13426 | 13426 | 13426 | 15645.0543 | 1 | 0.85816 | TRUE | FALSE | FALSE | 21 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146086 | HCMEB4Z3240 | B4 Z3 :Electrical Final Fix for All Systems & Boards (Vertical Elements) | 26638 | 2013-12-24 16:00 | 2014-01-07 16:00 | 14 | 776 | 100 | 100 | 0 | 17318 | 17318 | 17318 | 14886.8385 | 1 | 1.1633 | FALSE | FALSE | FALSE | 97 | FALSE | 0 | Green | Continue normal monitoring.
146087 | HCMEB4Z3250 | B4 Z3 :Electrical Final Fix for All Systems (Horizantel Elements) | 26638 | 2014-01-07 16:00 | 2014-01-21 16:00 | 14 | 776 | 100 | 100 | 0 | 14112 | 14112 | 14112 | 15010.3118 | 1 | 0.94015 | FALSE | FALSE | FALSE | 97 | FALSE | 0 | Green | Continue normal monitoring.
146088 | HCMEB4Z3040 | B4 Z3 :All Vertical Piping Works | 26436 | 2012-10-15 08:00 | 2012-10-26 17:00 | 11 | 631 | 100 | 81 | -19 | 10780 | 10780 | 8731.8 | 12131.1152 | 0.81 | 0.71979 | TRUE | TRUE | TRUE | 78.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146089 | HCMEB4Z3050 | B4 Z3 :All Horizantal Piping Works | 26436 | 2012-10-29 08:00 | 2012-12-07 17:00 | 39 | 631 | 100 | 100 | 0 | 23907 | 23907 | 23907 | 27480.6038 | 1 | 0.86996 | TRUE | FALSE | FALSE | 78.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146090 | HCMEB4Z3060 | B4 Z3 :Mechanical Final Fix | 26436 | 2013-04-15 08:00 | 2013-05-10 17:00 | 25 | 631 | 100 | 87 | -13 | 31200 | 31200 | 27144 | 29180.0136 | 0.87 | 0.93023 | FALSE | TRUE | TRUE | 78.875 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146091 | HCMEB4Z3070 | B4 Z3 :Horizontal F.F Piping Work | 26397 | 2012-10-31 16:00 | 2012-11-28 16:00 | 28 | 1648 | 100 | 90 | -10 | 24080 | 24080 | 21672 | 28820.6523 | 0.9 | 0.75196 | TRUE | FALSE | FALSE | 206 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146092 | HCMEB4Z3080 | B4 Z3 :Fire Hose Cabinets | 26397 | 2012-11-28 16:00 | 2012-12-12 16:00 | 14 | 1648 | 100 | 92 | -8 | 11760 | 11760 | 10819.2 | 14492.2862 | 0.92 | 0.74655 | TRUE | FALSE | FALSE | 206 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146093 | HCMEB4Z3090 | B4 Z3 :Sprinklers Final Fix | 26397 | 2013-11-04 16:00 | 2013-11-18 16:00 | 14 | 344 | 100 | 96 | -4 | 17766 | 17766 | 17055.36 | 16783.2936 | 0.96 | 1.0162 | FALSE | FALSE | FALSE | 43 | FALSE | 0 | Green | Continue normal monitoring.
146094 | HCMEB4Z3300 | B4 Z3 :Duct Installation& Dusct Accecories Installation, Fan coil Unit | 26393 | 2013-07-11 16:00 | 2013-07-25 16:00 | 14 | 200 | 100 | 87 | -13 | 17640 | 17640 | 15346.8 | 21221.7347 | 0.87 | 0.72316 | TRUE | TRUE | TRUE | 25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146095 | HCMEB4Z3310 | B4 Z3 :Duct Insulation Work | 26393 | 2013-07-25 16:00 | 2013-08-15 16:00 | 21 | 200 | 100 | 100 | 0 | 30828 | 30828 | 30828 | 27399.6645 | 1 | 1.1251 | FALSE | FALSE | FALSE | 25 | FALSE | 0 | Green | Continue normal monitoring.
146096 | HCMEB4Z3320 | B4 Z3 :Exhaust Fans | 26393 | 2013-08-15 16:00 | 2013-09-05 16:00 | 21 | 200 | 100 | 97 | -3 | 19908 | 19908 | 19310.76 | 17365.4047 | 0.97 | 1.112 | FALSE | FALSE | FALSE | 25 | FALSE | 0 | Green | Continue normal monitoring.
146097 | HCMEB4Z3330 | B4 Z3 :Grills & Diffusers | 26393 | 2013-11-28 16:00 | 2013-12-12 16:00 | 14 | 120 | 100 | 100 | 0 | 18676 | 18676 | 18676 | 16839.9535 | 1 | 1.109 | FALSE | FALSE | FALSE | 15 | FALSE | 0 | Green | Continue normal monitoring.
146098 | HCMEB4Z3340 | B4 Z3 :Mechanical final Fix | 26393 | 2013-12-12 16:00 | 2013-12-26 16:00 | 14 | 120 | 100 | 97 | -3 | 23842 | 23842 | 23126.74 | 20816.3651 | 0.97 | 1.111 | FALSE | FALSE | FALSE | 15 | FALSE | 0 | Green | Continue normal monitoring.
146099 | HCMEB4Z3350 | B4 Z3 :All Vertical Piping Works | 26568 | 2012-10-15 08:00 | 2012-10-26 17:00 | 11 | 631 | 100 | 93 | -7 | 21230 | 21230 | 19743.9 | 25221.3439 | 0.93 | 0.78283 | TRUE | FALSE | FALSE | 78.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146100 | HCMEB4Z3360 | B4 Z3 :All Horizantal Piping Works | 26568 | 2012-10-29 08:00 | 2012-12-07 17:00 | 39 | 631 | 100 | 94 | -6 | 67041 | 67041 | 63018.54 | 58568.3623 | 0.94 | 1.076 | FALSE | FALSE | FALSE | 78.875 | FALSE | 0 | Green | Continue normal monitoring.
146101 | HCMEB4Z3370 | B4 Z3 :Mechanical Final Fix | 26568 | 2013-04-15 08:00 | 2013-05-10 17:00 | 25 | 631 | 100 | 100 | 0 | 49725 | 49725 | 49725 | 47669.6508 | 1 | 1.0431 | FALSE | FALSE | FALSE | 78.875 | FALSE | 0 | Green | Continue normal monitoring.
146102 | HCMEB4Z4135 | B4 Z4 :Blocks Start Date for All Parts | 26413 | 2012-11-07 16:00 | 2012-11-07 16:00 | 1 | 2032 | 100 | 85 | -15 | 810 | 810 | 688.5 | 722.1171 | 0.85 | 0.95345 | FALSE | TRUE | TRUE | 254 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146103 | HCMEB4Z4145 | B4 Z4 :Tiling Finish Date for All Parts | 26413 | 2013-04-03 10:00 | 2013-04-03 10:00 | 1 | 1197 | 100 | 90 | -10 | 761 | 761 | 684.9 | 736.7765 | 0.9 | 0.92959 | FALSE | FALSE | FALSE | 149.625 | FALSE | 0 | Green | Continue normal monitoring.
146104 | HCMEB4Z4155 | B4 Z4 :Plastering Finish Date for All Parts | 26413 | 2013-01-14 16:00 | 2013-01-14 16:00 | 1 | 1736 | 100 | 92 | -8 | 1942 | 1942 | 1786.64 | 1721.0466 | 0.92 | 1.0381 | FALSE | FALSE | FALSE | 217 | FALSE | 0 | Green | Continue normal monitoring.
146105 | HCMEB4Z4165 | B4 Z4 :Gypsum Boards Finish Date for All Parts | 26413 | 2013-10-22 16:00 | 2013-10-22 16:00 | 1 | 1440 | 100 | 100 | 0 | 905 | 905 | 905 | 1011.0672 | 1 | 0.89509 | TRUE | FALSE | FALSE | 180 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146106 | HCMEB4Z4195 | B4 Z4 :Electrical Coduits & Boards F.F for All Systems | 26413 | 2012-11-07 16:00 | 2012-11-23 16:00 | 16 | 1720 | 100 | 80 | -20 | 10272 | 10272 | 8217.6 | 9279.0132 | 0.8 | 0.88561 | TRUE | TRUE | TRUE | 215 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146107 | HCMEB4Z4205 | B4 Z4 :Electrical Boards Seconed Fix | 26413 | 2013-03-28 16:00 | 2013-04-15 16:00 | 18 | 1408 | 100 | 100 | 0 | 15138 | 15138 | 15138 | 18025.3975 | 1 | 0.83982 | TRUE | FALSE | FALSE | 176 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146108 | HCMEB4Z4215 | B4 Z4 :Cable Tray Installation | 26413 | 2013-09-25 16:00 | 2013-10-09 16:00 | 14 | 360 | 100 | 85 | -15 | 25746 | 25746 | 21884.1 | 30299.8603 | 0.85 | 0.72225 | TRUE | TRUE | TRUE | 45 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146109 | HCMEB4Z4225 | B4 Z4 :Electrcial Wiring | 26413 | 2013-04-29 08:00 | 2013-05-24 17:00 | 25 | 855 | 100 | 88 | -12 | 40600 | 40600 | 35728 | 34731.8658 | 0.88 | 1.0287 | FALSE | TRUE | TRUE | 106.875 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146110 | HCMEB4Z4235 | B4 Z4 :Cable Laying | 26413 | 2013-10-09 16:00 | 2013-10-23 16:00 | 14 | 360 | 100 | 87 | -13 | 10402 | 10402 | 9049.74 | 12568.6382 | 0.87 | 0.72003 | TRUE | TRUE | TRUE | 45 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146111 | HCMEB4Z4245 | B4 Z4 :Electrical Final Fix for All Systems & Boards (Vertical Elements) | 26413 | 2013-12-04 16:00 | 2013-12-18 16:00 | 14 | 888 | 100 | 90 | -10 | 13846 | 13846 | 12461.4 | 11929.4052 | 0.9 | 1.0446 | FALSE | FALSE | FALSE | 111 | FALSE | 0 | Green | Continue normal monitoring.
146112 | HCMEB4Z4255 | B4 Z4 :Electrical Final Fix for All Systems (Horizantel Elements) | 26413 | 2013-12-18 16:00 | 2014-01-01 16:00 | 14 | 888 | 100 | 100 | 0 | 7154 | 7154 | 7154 | 6766.6704 | 1 | 1.0572 | FALSE | FALSE | FALSE | 111 | FALSE | 0 | Green | Continue normal monitoring.
146113 | HCMEB4Z4045 | B4 Z4 :All Vertical Piping Works | 26643 | 2012-10-15 08:00 | 2012-10-26 17:00 | 11 | 1111 | 100 | 98 | -2 | 19382 | 19382 | 18994.36 | 16725.8065 | 0.98 | 1.1356 | FALSE | FALSE | FALSE | 138.875 | FALSE | 0 | Green | Continue normal monitoring.
146114 | HCMEB4Z4055 | B4 Z4 :All Horizantal Piping Works | 26643 | 2012-10-29 08:00 | 2012-12-07 17:00 | 39 | 1271 | 100 | 100 | 0 | 41340 | 41340 | 41340 | 40692.5079 | 1 | 1.0159 | FALSE | FALSE | FALSE | 158.875 | FALSE | 0 | Green | Continue normal monitoring.
146115 | HCMEB4Z4065 | B4 Z4 :Mechanical Final Fix | 26643 | 2013-04-15 08:00 | 2013-05-10 17:00 | 25 | 1271 | 100 | 88 | -12 | 13525 | 13525 | 11902 | 14276.2679 | 0.88 | 0.83369 | TRUE | TRUE | TRUE | 158.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146116 | HCMEB4Z4075 | B4 Z4 :Horizontal F.F Piping Work | 26447 | 2012-11-07 16:00 | 2012-12-05 16:00 | 28 | 1928 | 100 | 96 | -4 | 32956 | 32956 | 31637.76 | 38514.2913 | 0.96 | 0.82146 | TRUE | FALSE | FALSE | 241 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146117 | HCMEB4Z4085 | B4 Z4 :Fire Hose Cabinets | 26447 | 2012-12-05 16:00 | 2012-12-19 16:00 | 14 | 1928 | 100 | 91 | -9 | 15302 | 15302 | 13924.82 | 15075.4175 | 0.91 | 0.92368 | FALSE | FALSE | FALSE | 241 | FALSE | 0 | Green | Continue normal monitoring.
146118 | HCMEB4Z4095 | B4 Z4 :Sprinklers Final Fix | 26447 | 2013-11-04 16:00 | 2013-11-18 16:00 | 14 | 664 | 100 | 100 | 0 | 27328 | 27328 | 27328 | 30940.6526 | 1 | 0.88324 | TRUE | FALSE | FALSE | 83 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146119 | HCMEB4Z4305 | B4 Z4 :Duct Installation& Dusct Accecories Installation, Fan coil Unit | 26448 | 2013-07-11 16:00 | 2013-07-31 16:00 | 20 | 296 | 100 | 93 | -7 | 33620 | 33620 | 31266.6 | 31098.5599 | 0.93 | 1.0054 | FALSE | FALSE | FALSE | 37 | FALSE | 0 | Green | Continue normal monitoring.
146120 | HCMEB4Z4315 | B4 Z4 :Duct Insulation Work | 26448 | 2013-07-31 16:00 | 2013-08-21 16:00 | 21 | 488 | 100 | 94 | -6 | 36519 | 36519 | 34327.86 | 42005.592 | 0.94 | 0.81722 | TRUE | FALSE | FALSE | 61 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146121 | HCMEB4Z4325 | B4 Z4 :Exhaust Fans | 26448 | 2013-08-21 16:00 | 2013-09-11 16:00 | 21 | 488 | 100 | 95 | -5 | 41685 | 41685 | 39600.75 | 39367.2574 | 0.95 | 1.0059 | FALSE | FALSE | FALSE | 61 | FALSE | 0 | Green | Continue normal monitoring.
146122 | HCMEB4Z4335 | B4 Z4 :Grills & Diffusers | 26448 | 2013-11-28 16:00 | 2013-12-12 16:00 | 14 | 440 | 100 | 100 | 0 | 8862 | 8862 | 8862 | 8041.5375 | 1 | 1.102 | FALSE | FALSE | FALSE | 55 | FALSE | 0 | Green | Continue normal monitoring.
146123 | HCMEB4Z4345 | B4 Z4 :Mechanical final Fix | 26448 | 2013-12-12 16:00 | 2013-12-26 16:00 | 14 | 440 | 100 | 100 | 0 | 22260 | 22260 | 22260 | 20571.8804 | 1 | 1.0821 | FALSE | FALSE | FALSE | 55 | FALSE | 0 | Green | Continue normal monitoring.
146124 | HCMEB4Z4355 | B4 Z4 :All Vertical Piping Works | 26649 | 2012-10-15 08:00 | 2012-10-26 17:00 | 11 | 1271 | 100 | 100 | 0 | 16830 | 16830 | 16830 | 15531.149 | 1 | 1.0836 | FALSE | FALSE | FALSE | 158.875 | FALSE | 0 | Green | Continue normal monitoring.
146125 | HCMEB4Z4365 | B4 Z4 :All Horizantal Piping Works | 26649 | 2012-10-29 08:00 | 2012-12-07 17:00 | 39 | 1271 | 100 | 99 | -1 | 56433 | 56433 | 55868.67 | 59545.0063 | 0.99 | 0.93826 | FALSE | FALSE | FALSE | 158.875 | FALSE | 0 | Green | Continue normal monitoring.
146126 | HCMEB4Z4375 | B4 Z4 :Mechanical Final Fix | 26649 | 2013-04-15 08:00 | 2013-05-10 17:00 | 25 | 1271 | 100 | 80 | -20 | 14300 | 14300 | 11440 | 16987.2422 | 0.8 | 0.67345 | TRUE | TRUE | TRUE | 158.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146127 | HCMEB4Z5290 | B4 Z4 :SOG Steel Work Finish Date | 26281 | 2012-09-24 16:00 | 2012-09-24 16:00 | 1 | 2304 | 100 | 89 | -11 | 898 | 898 | 799.22 | 791.8941 | 0.89 | 1.0093 | FALSE | TRUE | TRUE | 288 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146128 | HCMEB4Z5300 | B4 Z4 :Electrical First Fix (Conducting) | 26281 | 2012-09-24 16:00 | 2012-10-01 16:00 | 7 | 2304 | 100 | 87 | -13 | 13496 | 13496 | 11741.52 | 15288.033 | 0.87 | 0.76802 | TRUE | TRUE | TRUE | 288 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146129 | HCMEB4Z5140 | B4 Z4 :Blocks Start Date for All Parts | 26453 | 2012-12-09 16:00 | 2012-12-09 16:00 | 1 | 1824 | 100 | 97 | -3 | 1077 | 1077 | 1044.69 | 1197.3425 | 0.97 | 0.87251 | TRUE | FALSE | FALSE | 228 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146130 | HCMEB4Z5150 | B4 Z4 :Tiling Finish Date for All Parts | 26453 | 2013-03-26 12:00 | 2013-03-26 12:00 | 1 | 1483 | 100 | 100 | 0 | 1358 | 1358 | 1358 | 1628.2528 | 1 | 0.83402 | TRUE | FALSE | FALSE | 185.375 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146131 | HCMEB4Z5160 | B4 Z4 :Plastering Finish Date for All Parts | 26453 | 2013-01-14 16:00 | 2013-01-14 16:00 | 1 | 1968 | 100 | 80 | -20 | 629 | 629 | 503.2 | 596.0775 | 0.8 | 0.84419 | TRUE | TRUE | TRUE | 246 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146132 | HCMEB4Z5200 | B4 Z4 :Electrical Coduits & Boards F.F for All Systems | 26453 | 2012-12-10 08:00 | 2012-12-25 17:00 | 15 | 1543 | 100 | 81 | -19 | 21450 | 21450 | 17374.5 | 22094.4426 | 0.81 | 0.78637 | TRUE | TRUE | TRUE | 192.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146133 | HCMEB4Z5210 | B4 Z4 :Electrical Boards Seconed Fix | 26453 | 2013-03-28 16:00 | 2013-04-15 16:00 | 18 | 1408 | 100 | 80 | -20 | 35802 | 35802 | 28641.6 | 43690.2887 | 0.8 | 0.65556 | TRUE | TRUE | TRUE | 176 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146134 | HCMEB4Z5220 | B4 Z4 :Cable Tray Installation | 26453 | 2013-09-25 16:00 | 2013-10-09 16:00 | 14 | 360 | 100 | 80 | -20 | 24206 | 24206 | 19364.8 | 26965.4206 | 0.8 | 0.71813 | TRUE | TRUE | TRUE | 45 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146135 | HCMEB4Z5230 | B4 Z4 :Electrcial Wiring | 26453 | 2013-04-29 08:00 | 2013-05-24 17:00 | 25 | 1047 | 100 | 88 | -12 | 19125 | 19125 | 16830 | 19230.3284 | 0.88 | 0.87518 | TRUE | TRUE | TRUE | 130.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146136 | HCMEB4Z5240 | B4 Z4 :Cable Laying | 26453 | 2013-10-09 16:00 | 2013-10-23 16:00 | 14 | 360 | 100 | 92 | -8 | 18088 | 18088 | 16640.96 | 16325.5949 | 0.92 | 1.0193 | FALSE | FALSE | FALSE | 45 | FALSE | 0 | Green | Continue normal monitoring.
146137 | HCMEB4Z5250 | B4 Z4 :Electrical Final Fix for All Systems & Boards (Vertical Elements) | 26453 | 2013-12-04 16:00 | 2013-12-18 16:00 | 14 | 888 | 100 | 100 | 0 | 10528 | 10528 | 10528 | 10054.1769 | 1 | 1.0471 | FALSE | FALSE | FALSE | 111 | FALSE | 0 | Green | Continue normal monitoring.
146138 | HCMEB4Z5260 | B4 Z4 :Electrical Final Fix for All Systems (Horizantel Elements) | 26453 | 2013-12-18 16:00 | 2014-01-01 16:00 | 14 | 888 | 100 | 80 | -20 | 18494 | 18494 | 14795.2 | 20019.4996 | 0.8 | 0.73904 | TRUE | TRUE | TRUE | 111 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146139 | HCMEB4Z5050 | B4 Z4 :All Vertical Piping Works | 26392 | 2012-10-15 08:00 | 2012-10-26 17:00 | 11 | 1111 | 100 | 92 | -8 | 19932 | 19932 | 18337.44 | 22668.0094 | 0.92 | 0.80896 | TRUE | FALSE | FALSE | 138.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146140 | HCMEB4Z5060 | B4 Z4 :All Horizantal Piping Works | 26392 | 2012-10-29 08:00 | 2012-12-07 17:00 | 39 | 1176 | 100 | 99 | -1 | 25857 | 25857 | 25598.43 | 23265.3207 | 0.99 | 1.1003 | FALSE | FALSE | FALSE | 147 | FALSE | 0 | Green | Continue normal monitoring.
146141 | HCMEB4Z5070 | B4 Z4 :Mechanical Final Fix | 26392 | 2013-04-15 08:00 | 2013-05-10 17:00 | 25 | 1176 | 100 | 100 | 0 | 14850 | 14850 | 14850 | 16184.1077 | 1 | 0.91757 | FALSE | FALSE | FALSE | 147 | FALSE | 0 | Green | Continue normal monitoring.
146142 | HCMEB4Z5080 | B4 Z4 :Horizontal F.F Piping Work | 26655 | 2012-12-10 08:00 | 2013-01-04 17:00 | 25 | 1751 | 100 | 100 | 0 | 33300 | 33300 | 33300 | 35635.679 | 1 | 0.93446 | FALSE | FALSE | FALSE | 218.875 | FALSE | 0 | Green | Continue normal monitoring.
146143 | HCMEB4Z5090 | B4 Z4 :Fire Hose Cabinets | 26655 | 2013-01-07 08:00 | 2013-01-18 17:00 | 11 | 1751 | 100 | 86 | -14 | 17963 | 17963 | 15448.18 | 18961.4227 | 0.86 | 0.81472 | TRUE | TRUE | TRUE | 218.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146144 | HCMEB4Z5100 | B4 Z4 :Sprinklers Final Fix | 26655 | 2013-11-04 16:00 | 2013-11-18 16:00 | 14 | 664 | 100 | 81 | -19 | 11690 | 11690 | 9468.9 | 13163.5157 | 0.81 | 0.71933 | TRUE | TRUE | TRUE | 83 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146145 | HCMEB4Z5310 | B4 Z4 :Duct Installation& Dusct Accecories Installation, Fan coil Unit | 26395 | 2013-07-11 16:00 | 2013-07-31 16:00 | 20 | 296 | 100 | 85 | -15 | 26420 | 26420 | 22457 | 31307.1673 | 0.85 | 0.71731 | TRUE | TRUE | TRUE | 37 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146146 | HCMEB4Z5320 | B4 Z4 :Duct Insulation Work | 26395 | 2013-07-31 16:00 | 2013-08-21 16:00 | 21 | 488 | 100 | 86 | -14 | 15477 | 15477 | 13310.22 | 15155.0145 | 0.86 | 0.87827 | TRUE | TRUE | TRUE | 61 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146147 | HCMEB4Z5330 | B4 Z4 :Exhaust Fans | 26395 | 2013-08-21 16:00 | 2013-09-11 16:00 | 21 | 488 | 100 | 100 | 0 | 18480 | 18480 | 18480 | 22279.5781 | 1 | 0.82946 | TRUE | FALSE | FALSE | 61 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146148 | HCMEB4Z5340 | B4 Z4 :Grills & Diffusers | 26395 | 2013-11-28 16:00 | 2013-12-12 16:00 | 14 | 440 | 100 | 93 | -7 | 27426 | 27426 | 25506.18 | 25074.315 | 0.93 | 1.0172 | FALSE | FALSE | FALSE | 55 | FALSE | 0 | Green | Continue normal monitoring.
146149 | HCMEB4Z5350 | B4 Z4 :Mechanical final Fix | 26395 | 2013-12-12 16:00 | 2013-12-26 16:00 | 14 | 440 | 100 | 100 | 0 | 19572 | 19572 | 19572 | 17990.7693 | 1 | 1.0879 | FALSE | FALSE | FALSE | 55 | FALSE | 0 | Green | Continue normal monitoring.
146150 | HCMEB4Z5360 | B4 Z4 :All Vertical Piping Works | 26412 | 2012-10-15 08:00 | 2012-10-26 17:00 | 11 | 1111 | 100 | 97 | -3 | 10802 | 10802 | 10477.94 | 10334.3687 | 0.97 | 1.0139 | FALSE | FALSE | FALSE | 138.875 | FALSE | 0 | Green | Continue normal monitoring.
146151 | HCMEB4Z5370 | B4 Z4 :All Horizantal Piping Works | 26412 | 2012-10-29 08:00 | 2012-12-07 17:00 | 39 | 1111 | 100 | 94 | -6 | 54639 | 54639 | 51360.66 | 49055.5689 | 0.94 | 1.047 | FALSE | FALSE | FALSE | 138.875 | FALSE | 0 | Green | Continue normal monitoring.
146152 | HCMEB4Z5380 | B4 Z4 :Mechanical Final Fix | 26412 | 2013-04-15 08:00 | 2013-05-10 17:00 | 25 | 1111 | 100 | 81 | -19 | 38700 | 38700 | 31347 | 36460.3416 | 0.81 | 0.85976 | TRUE | TRUE | TRUE | 138.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146153 | HCMEB4Z6295 | B4 Z6 :SOG Steel Work Finish Date | 26285 | 2012-10-13 16:00 | 2012-10-13 16:00 | 1 | 2176 | 100 | 89 | -11 | 1640 | 1640 | 1459.6 | 1463.8061 | 0.89 | 0.99713 | FALSE | TRUE | TRUE | 272 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146154 | HCMEB4Z6315 | B4 Z6 :Electrical First Fix (Conducting) | 26285 | 2012-10-13 16:00 | 2012-10-20 16:00 | 7 | 2176 | 100 | 100 | 0 | 6867 | 6867 | 6867 | 8094.1395 | 1 | 0.84839 | TRUE | FALSE | FALSE | 272 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146155 | HCMEB4Z6145 | B4 Z6 :Blocks Start Date for All Parts | 26440 | 2012-12-09 16:00 | 2012-12-09 16:00 | 1 | 1824 | 100 | 91 | -9 | 1915 | 1915 | 1742.65 | 1734.2002 | 0.91 | 1.0049 | FALSE | FALSE | FALSE | 228 | FALSE | 0 | Green | Continue normal monitoring.
146156 | HCMEB4Z6155 | B4 Z6 :Tiling Finish Date for All Parts | 26440 | 2013-04-03 10:00 | 2013-04-03 10:00 | 1 | 1429 | 100 | 96 | -4 | 1416 | 1416 | 1359.36 | 1626.8693 | 0.96 | 0.83557 | TRUE | FALSE | FALSE | 178.625 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146157 | HCMEB4Z6165 | B4 Z6 :Plastering Finish Date for All Parts | 26440 | 2013-01-14 16:00 | 2013-01-14 16:00 | 1 | 1968 | 100 | 87 | -13 | 1493 | 1493 | 1298.91 | 1297.6642 | 0.87 | 1.001 | FALSE | TRUE | TRUE | 246 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146158 | HCMEB4Z6205 | B4 Z6 :Electrical Coduits & Boards F.F for All Systems | 26440 | 2012-12-10 08:00 | 2012-12-25 17:00 | 15 | 1543 | 100 | 90 | -10 | 21945 | 21945 | 19750.5 | 26979.3614 | 0.9 | 0.73206 | TRUE | FALSE | FALSE | 192.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146159 | HCMEB4Z6215 | B4 Z6 :Electrical Boards Seconed Fix | 26440 | 2013-03-28 16:00 | 2013-04-15 16:00 | 18 | 1408 | 100 | 100 | 0 | 18648 | 18648 | 18648 | 21155.4853 | 1 | 0.88147 | TRUE | FALSE | FALSE | 176 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146160 | HCMEB4Z6225 | B4 Z6 :Cable Tray Installation | 26440 | 2013-09-25 16:00 | 2013-10-09 16:00 | 14 | 360 | 100 | 82 | -18 | 22428 | 22428 | 18390.96 | 19124.7732 | 0.82 | 0.96163 | FALSE | TRUE | TRUE | 45 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146161 | HCMEB4Z6235 | B4 Z6 :Electrcial Wiring | 26440 | 2013-04-29 08:00 | 2013-05-24 17:00 | 25 | 1047 | 100 | 100 | 0 | 42400 | 42400 | 42400 | 48995.0062 | 1 | 0.86539 | TRUE | FALSE | FALSE | 130.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146162 | HCMEB4Z6245 | B4 Z6 :Cable Laying | 26440 | 2013-10-09 16:00 | 2013-10-23 16:00 | 14 | 360 | 100 | 85 | -15 | 21490 | 21490 | 18266.5 | 22685.5482 | 0.85 | 0.8052 | TRUE | TRUE | TRUE | 45 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146163 | HCMEB4Z6255 | B4 Z6 :Electrical Final Fix for All Systems & Boards (Vertical Elements) | 26440 | 2013-12-04 16:00 | 2013-12-18 16:00 | 14 | 888 | 100 | 88 | -12 | 8778 | 8778 | 7724.64 | 10197.807 | 0.88 | 0.75748 | TRUE | TRUE | TRUE | 111 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146164 | HCMEB4Z6265 | B4 Z6 :Electrical Final Fix for All Systems (Horizantel Elements) | 26440 | 2013-12-18 16:00 | 2014-01-01 16:00 | 14 | 888 | 100 | 85 | -15 | 8274 | 8274 | 7032.9 | 8762.1554 | 0.85 | 0.80264 | TRUE | TRUE | TRUE | 111 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146165 | HCMEB4Z6055 | B4 Z6 :All Vertical Piping Works | 26585 | 2012-10-15 08:00 | 2012-10-26 17:00 | 11 | 1511 | 100 | 88 | -12 | 11462 | 11462 | 10086.56 | 12681.6708 | 0.88 | 0.79537 | TRUE | TRUE | TRUE | 188.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146166 | HCMEB4Z6065 | B4 Z6 :All Horizantal Piping Works | 26585 | 2012-10-29 08:00 | 2012-12-07 17:00 | 39 | 1511 | 100 | 86 | -14 | 52455 | 52455 | 45111.3 | 61085.5608 | 0.86 | 0.73849 | TRUE | TRUE | TRUE | 188.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146167 | HCMEB4Z6075 | B4 Z6 :Mechanical Final Fix | 26585 | 2013-04-15 08:00 | 2013-05-10 17:00 | 25 | 1511 | 100 | 100 | 0 | 37200 | 37200 | 37200 | 37648.0079 | 1 | 0.9881 | FALSE | FALSE | FALSE | 188.875 | FALSE | 0 | Green | Continue normal monitoring.
146168 | HCMEB4Z6095 | B4 Z6 :Horizontal F.F Piping Work | 26411 | 2012-12-10 08:00 | 2013-01-04 17:00 | 25 | 1751 | 100 | 88 | -12 | 23650 | 23650 | 20812 | 20128.1191 | 0.88 | 1.034 | FALSE | TRUE | TRUE | 218.875 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146169 | HCMEB4Z6105 | B4 Z6 :Fire Hose Cabinets | 26411 | 2013-01-07 08:00 | 2013-01-18 17:00 | 11 | 1751 | 100 | 97 | -3 | 9779 | 9779 | 9485.63 | 11636.8007 | 0.97 | 0.81514 | TRUE | FALSE | FALSE | 218.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146170 | HCMEB4Z6325 | B4 Z6 :Sprinklers Final Fix | 26411 | 2013-11-04 16:00 | 2013-11-18 16:00 | 14 | 664 | 100 | 91 | -9 | 16394 | 16394 | 14918.54 | 16432.6266 | 0.91 | 0.90786 | FALSE | FALSE | FALSE | 83 | FALSE | 0 | Green | Continue normal monitoring.
146171 | HCMEB4Z6335 | B4 Z6 :Duct Installation& Dusct Accecories Installation, Fan coil Unit | 26442 | 2013-07-11 16:00 | 2013-07-31 16:00 | 20 | 296 | 100 | 87 | -13 | 10840 | 10840 | 9430.8 | 11364.8413 | 0.87 | 0.82982 | TRUE | TRUE | TRUE | 37 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146172 | HCMEB4Z6345 | B4 Z6 :Duct Insulation Work | 26442 | 2013-07-31 16:00 | 2013-08-21 16:00 | 21 | 488 | 100 | 87 | -13 | 15813 | 15813 | 13757.31 | 13490.1756 | 0.87 | 1.0198 | FALSE | TRUE | TRUE | 61 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146173 | HCMEB4Z6365 | B4 Z6 :Exhaust Fans | 26442 | 2013-08-21 16:00 | 2013-09-11 16:00 | 21 | 488 | 100 | 97 | -3 | 34713 | 34713 | 33671.61 | 36338.846 | 0.97 | 0.9266 | FALSE | FALSE | FALSE | 61 | FALSE | 0 | Green | Continue normal monitoring.
146174 | HCMEB4Z6375 | B4 Z6 :Grills & Diffusers | 26442 | 2013-11-28 16:00 | 2013-12-12 16:00 | 14 | 440 | 100 | 100 | 0 | 22162 | 22162 | 22162 | 27582.7135 | 1 | 0.80347 | TRUE | FALSE | FALSE | 55 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146175 | HCMEB4Z6385 | B4 Z6 :Mechanical final Fix | 26442 | 2013-12-12 16:00 | 2013-12-26 16:00 | 14 | 440 | 100 | 100 | 0 | 16268 | 16268 | 16268 | 15638.5433 | 1 | 1.0403 | FALSE | FALSE | FALSE | 55 | FALSE | 0 | Green | Continue normal monitoring.
146176 | HCMEB4Z6390 | B4 Z6 :All Vertical Piping Works | 26590 | 2012-10-15 08:00 | 2012-10-26 17:00 | 11 | 1591 | 100 | 99 | -1 | 10626 | 10626 | 10519.74 | 10712.7858 | 0.99 | 0.98198 | FALSE | FALSE | FALSE | 198.875 | FALSE | 0 | Green | Continue normal monitoring.
146177 | HCMEB4Z6395 | B4 Z6 :All Horizantal Piping Works | 26590 | 2012-10-29 08:00 | 2012-12-07 17:00 | 39 | 1591 | 100 | 100 | 0 | 30654 | 30654 | 30654 | 34481.9489 | 1 | 0.88899 | TRUE | FALSE | FALSE | 198.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146178 | HCMEB4Z6400 | B4 Z6 :Mechanical Final Fix | 26590 | 2013-04-15 08:00 | 2013-05-10 17:00 | 25 | 1591 | 100 | 94 | -6 | 37750 | 37750 | 35485 | 44390.8844 | 0.94 | 0.79938 | TRUE | FALSE | FALSE | 198.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146179 | HCMEB3Z1125 | B3 Z1 :Blocks Start Date for All Parts | 26407 | 2012-11-18 16:00 | 2012-11-18 16:00 | 1 | 496 | 100 | 100 | 0 | 1990 | 1990 | 1990 | 2023.7437 | 1 | 0.98333 | FALSE | FALSE | FALSE | 62 | FALSE | 0 | Green | Continue normal monitoring.
146180 | HCMEB3Z1135 | B3 Z1 :Tiling Finish Date for All Parts | 26407 | 2013-06-29 16:00 | 2013-06-29 16:00 | 1 | 24 | 100 | 100 | 0 | 1277 | 1277 | 1277 | 1243.6289 | 1 | 1.0268 | FALSE | FALSE | FALSE | 3 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146181 | HCMEB3Z1145 | B3 Z1 :Plastering Finish Date for All Parts | 26407 | 2012-12-18 12:00 | 2012-12-18 12:00 | 1 | 1932 | 100 | 86 | -14 | 844 | 844 | 725.84 | 1034.01 | 0.86 | 0.70197 | TRUE | TRUE | TRUE | 241.5 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146182 | HCMEB3Z1155 | B3 Z1 :Gypsum Boards Finish Date for All Parts | 26407 | 2013-11-10 16:00 | 2013-11-10 16:00 | 1 | 1312 | 100 | 90 | -10 | 1141 | 1141 | 1026.9 | 1278.899 | 0.9 | 0.80296 | TRUE | FALSE | FALSE | 164 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146183 | HCMEB3Z1185 | B3 Z1 :Electrical Coduits & Boards F.F for All Systems | 26407 | 2012-11-19 08:00 | 2012-12-04 17:00 | 15 | 1303 | 100 | 99 | -1 | 13215 | 13215 | 13082.85 | 11861.8966 | 0.99 | 1.1029 | FALSE | FALSE | FALSE | 162.875 | FALSE | 0 | Green | Continue normal monitoring.
146184 | HCMEB3Z1195 | B3 Z1 :Electrical Boards Seconed Fix | 26407 | 2013-04-15 16:00 | 2013-05-01 16:00 | 16 | 952 | 100 | 95 | -5 | 19024 | 19024 | 18072.8 | 16694.9136 | 0.95 | 1.0825 | FALSE | FALSE | FALSE | 119 | FALSE | 0 | Green | Continue normal monitoring.
146185 | HCMEB3Z1205 | B3 Z1 :Cable Tray Installation | 26407 | 2013-10-09 16:00 | 2013-10-23 16:00 | 14 | 0 | 100 | 83 | -17 | 24864 | 24864 | 20637.12 | 25943.5934 | 0.83 | 0.79546 | TRUE | TRUE | TRUE | 0 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
146186 | HCMEB3Z1215 | B3 Z1 :Electrcial Wiring | 26407 | 2013-07-01 08:00 | 2013-07-26 17:00 | 25 | 15 | 100 | 85 | -15 | 39475 | 39475 | 33553.75 | 37028.9721 | 0.85 | 0.90615 | FALSE | TRUE | TRUE | 1.875 | TRUE | 4 | Orange | Develop recovery plan and review schedule and cost exposure.
146187 | HCMEB3Z1225 | B3 Z1 :Cable Laying | 26407 | 2013-10-23 16:00 | 2013-11-06 16:00 | 14 | 0 | 100 | 100 | 0 | 27804 | 27804 | 27804 | 26458.1168 | 1 | 1.0509 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146188 | HCMEB3Z1235 | B3 Z1 :Electrical Final Fix for All Systems & Boards (Vertical Elements) | 26407 | 2013-12-18 16:00 | 2014-01-01 16:00 | 14 | 808 | 100 | 100 | 0 | 13384 | 13384 | 13384 | 16075.2128 | 1 | 0.83259 | TRUE | FALSE | FALSE | 101 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146189 | HCMEB3Z1245 | B3 Z1 :Electrical Final Fix for All Systems (Horizantel Elements) | 26407 | 2014-01-01 16:00 | 2014-01-15 16:00 | 14 | 808 | 100 | 100 | 0 | 20748 | 20748 | 20748 | 18379.1263 | 1 | 1.1289 | FALSE | FALSE | FALSE | 101 | FALSE | 0 | Green | Continue normal monitoring.
146190 | HCMEB3Z1035 | B3 Z1 :All Vertical Piping Works | 26656 | 2012-12-03 08:00 | 2012-12-14 17:00 | 11 | 351 | 100 | 100 | 0 | 6402 | 6402 | 6402 | 7273.6044 | 1 | 0.88017 | TRUE | FALSE | FALSE | 43.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146191 | HCMEB3Z1045 | B3 Z1 :All Horizantal Piping Works | 26656 | 2012-12-17 08:00 | 2013-01-25 17:00 | 39 | 351 | 100 | 82 | -18 | 63258 | 63258 | 51871.56 | 60630.0667 | 0.82 | 0.85554 | TRUE | TRUE | TRUE | 43.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146192 | HCMEB3Z1055 | B3 Z1 :Mechanical Final Fix | 26656 | 2013-06-03 08:00 | 2013-06-28 17:00 | 25 | 351 | 100 | 100 | 0 | 16200 | 16200 | 16200 | 18696.9269 | 1 | 0.86645 | TRUE | FALSE | FALSE | 43.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146193 | HCMEB3Z1065 | B3 Z1 :Horizontal F.F Piping Work | 26408 | 2012-11-19 08:00 | 2012-12-14 17:00 | 25 | 1551 | 100 | 88 | -12 | 46300 | 46300 | 40744 | 52734.0588 | 0.88 | 0.77263 | TRUE | TRUE | TRUE | 193.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146194 | HCMEB3Z1075 | B3 Z1 :Fire Hose Cabinets | 26408 | 2012-12-17 08:00 | 2012-12-28 17:00 | 11 | 1551 | 100 | 100 | 0 | 18469 | 18469 | 18469 | 15753.2584 | 1 | 1.1724 | FALSE | FALSE | FALSE | 193.875 | FALSE | 0 | Green | Continue normal monitoring.
146195 | HCMEB3Z1085 | B3 Z1 :Sprinklers Final Fix | 26408 | 2013-11-18 16:00 | 2013-12-02 16:00 | 14 | 264 | 100 | 89 | -11 | 9646 | 9646 | 8584.94 | 10163.5481 | 0.89 | 0.84468 | TRUE | TRUE | TRUE | 33 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146196 | HCMEB3Z1295 | B3 Z1 :Duct Installation& Dusct Accecories Installation, Fan coil Unit | 26406 | 2013-07-23 16:00 | 2013-08-02 16:00 | 10 | 152 | 100 | 93 | -7 | 13820 | 13820 | 12852.6 | 12517.1581 | 0.93 | 1.0268 | FALSE | FALSE | FALSE | 19 | FALSE | 0 | Green | Continue normal monitoring.
146197 | HCMEB3Z1305 | B3 Z1 :Duct Insulation Work | 26406 | 2013-08-02 16:00 | 2013-08-23 16:00 | 21 | 152 | 100 | 90 | -10 | 16002 | 16002 | 14401.8 | 19146.246 | 0.9 | 0.7522 | TRUE | FALSE | FALSE | 19 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146198 | HCMEB3Z1315 | B3 Z1 :Exhaust Fans | 26406 | 2013-08-23 16:00 | 2013-09-13 16:00 | 21 | 152 | 100 | 97 | -3 | 33663 | 33663 | 32653.11 | 40349.6282 | 0.97 | 0.80925 | TRUE | FALSE | FALSE | 19 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146199 | HCMEB3Z1325 | B3 Z1 :Grills & Diffusers | 26406 | 2013-12-17 16:00 | 2013-12-31 16:00 | 14 | 16 | 100 | 100 | 0 | 12586 | 12586 | 12586 | 12804.2201 | 1 | 0.98296 | FALSE | FALSE | FALSE | 2 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146200 | HCMEB3Z1335 | B3 Z1 :Mechanical final Fix | 26406 | 2014-01-02 16:00 | 2014-01-16 16:00 | 14 | 0 | 100 | 91 | -9 | 17682 | 17682 | 16090.62 | 18172.8213 | 0.91 | 0.88542 | TRUE | FALSE | FALSE | 0 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146201 | HCMEB3Z1345 | B3 Z1 :All Vertical Piping Works | 26596 | 2012-12-03 08:00 | 2012-12-14 17:00 | 11 | 351 | 100 | 100 | 0 | 12188 | 12188 | 12188 | 11838.365 | 1 | 1.0295 | FALSE | FALSE | FALSE | 43.875 | FALSE | 0 | Green | Continue normal monitoring.
146202 | HCMEB3Z1355 | B3 Z1 :All Horizantal Piping Works | 26596 | 2012-12-17 08:00 | 2013-01-25 17:00 | 39 | 351 | 100 | 91 | -9 | 69537 | 69537 | 63278.67 | 79038.7109 | 0.91 | 0.8006 | TRUE | FALSE | FALSE | 43.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146203 | HCMEB3Z1365 | B3 Z1 :Mechanical Final Fix | 26596 | 2013-06-03 08:00 | 2013-06-28 17:00 | 25 | 351 | 100 | 92 | -8 | 32100 | 32100 | 29532 | 31890.2119 | 0.92 | 0.92605 | FALSE | FALSE | FALSE | 43.875 | FALSE | 0 | Green | Continue normal monitoring.
146204 | HCMEB3Z2130 | B3 Z2 :Blocks Start Date for All Parts | 26403 | 2012-12-02 16:00 | 2012-12-02 16:00 | 1 | 400 | 100 | 100 | 0 | 600 | 600 | 600 | 574.2702 | 1 | 1.0448 | FALSE | FALSE | FALSE | 50 | FALSE | 0 | Green | Continue normal monitoring.
146205 | HCMEB3Z2140 | B3 Z2 :Tiling Finish Date for All Parts | 26403 | 2013-04-06 16:00 | 2013-04-06 16:00 | 1 | 600 | 100 | 92 | -8 | 1882 | 1882 | 1731.44 | 1925.0835 | 0.92 | 0.89941 | TRUE | FALSE | FALSE | 75 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146206 | HCMEB3Z2150 | B3 Z2 :Plastering Finish Date for All Parts | 26403 | 2013-01-02 12:00 | 2013-01-02 12:00 | 1 | 1931 | 100 | 98 | -2 | 1903 | 1903 | 1864.94 | 1687.1903 | 0.98 | 1.1054 | FALSE | FALSE | FALSE | 241.375 | FALSE | 0 | Green | Continue normal monitoring.
146207 | HCMEB3Z2160 | B3 Z2 :Gypsum Boards Finish Date for All Parts | 26403 | 2013-11-09 16:00 | 2013-11-09 16:00 | 1 | 1320 | 100 | 100 | 0 | 1319 | 1319 | 1319 | 1515.0579 | 1 | 0.87059 | TRUE | FALSE | FALSE | 165 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146208 | HCMEB3Z2190 | B3 Z2 :Electrical Coduits & Boards F.F for All Systems | 26403 | 2012-12-03 08:00 | 2012-12-18 17:00 | 15 | 1295 | 100 | 98 | -2 | 26160 | 26160 | 25636.8 | 22367.8087 | 0.98 | 1.1461 | FALSE | FALSE | FALSE | 161.875 | FALSE | 0 | Green | Continue normal monitoring.
146209 | HCMEB3Z2200 | B3 Z2 :Electrical Boards Seconed Fix | 26403 | 2013-04-15 16:00 | 2013-05-01 16:00 | 16 | 1024 | 100 | 100 | 0 | 21104 | 21104 | 21104 | 23378.8851 | 1 | 0.90269 | FALSE | FALSE | FALSE | 128 | FALSE | 0 | Green | Continue normal monitoring.
146210 | HCMEB3Z2210 | B3 Z2 :Cable Tray Installation | 26403 | 2013-10-09 16:00 | 2013-10-23 16:00 | 14 | 88 | 100 | 93 | -7 | 12866 | 12866 | 11965.38 | 11877.194 | 0.93 | 1.0074 | FALSE | FALSE | FALSE | 11 | FALSE | 0 | Green | Continue normal monitoring.
146211 | HCMEB3Z2220 | B3 Z2 :Electrcial Wiring | 26403 | 2013-05-27 08:00 | 2013-06-21 17:00 | 25 | 215 | 100 | 83 | -17 | 15575 | 15575 | 12927.25 | 14686.6272 | 0.83 | 0.88021 | TRUE | TRUE | TRUE | 26.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146212 | HCMEB3Z2230 | B3 Z2 :Cable Laying | 26403 | 2013-10-23 16:00 | 2013-11-06 16:00 | 14 | 88 | 100 | 92 | -8 | 12894 | 12894 | 11862.48 | 14238.2356 | 0.92 | 0.83314 | TRUE | FALSE | FALSE | 11 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146213 | HCMEB3Z2240 | B3 Z2 :Electrical Final Fix for All Systems & Boards (Vertical Elements) | 26403 | 2013-12-18 16:00 | 2014-01-01 16:00 | 14 | 808 | 100 | 87 | -13 | 24556 | 24556 | 21363.72 | 30625.6879 | 0.87 | 0.69758 | TRUE | TRUE | TRUE | 101 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146214 | HCMEB3Z2250 | B3 Z2 :Electrical Final Fix for All Systems (Horizantel Elements) | 26403 | 2014-01-01 16:00 | 2014-01-15 16:00 | 14 | 808 | 100 | 100 | 0 | 22204 | 22204 | 22204 | 25780.7757 | 1 | 0.86126 | TRUE | FALSE | FALSE | 101 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146215 | HCMEB3Z2040 | B3 Z2 :All Vertical Piping Works | 26657 | 2012-12-03 08:00 | 2012-12-14 17:00 | 11 | 511 | 100 | 100 | 0 | 13937 | 13937 | 13937 | 13105.4608 | 1 | 1.0634 | FALSE | FALSE | FALSE | 63.875 | FALSE | 0 | Green | Continue normal monitoring.
146216 | HCMEB3Z2050 | B3 Z2 :All Horizantal Piping Works | 26657 | 2012-12-17 08:00 | 2013-01-25 17:00 | 39 | 511 | 100 | 100 | 0 | 38298 | 38298 | 38298 | 35249.8584 | 1 | 1.0865 | FALSE | FALSE | FALSE | 63.875 | FALSE | 0 | Green | Continue normal monitoring.
146217 | HCMEB3Z2060 | B3 Z2 :Mechanical Final Fix | 26657 | 2013-06-03 08:00 | 2013-06-28 17:00 | 25 | 511 | 100 | 100 | 0 | 25450 | 25450 | 25450 | 30450.7506 | 1 | 0.83578 | TRUE | FALSE | FALSE | 63.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146218 | HCMEB3Z2070 | B3 Z2 :Horizontal F.F Piping Work | 26401 | 2012-12-03 08:00 | 2012-12-28 17:00 | 25 | 1551 | 100 | 98 | -2 | 16350 | 16350 | 16023 | 16802.463 | 0.98 | 0.95361 | FALSE | FALSE | FALSE | 193.875 | FALSE | 0 | Green | Continue normal monitoring.
146219 | HCMEB3Z2080 | B3 Z2 :Fire Hose Cabinets | 26401 | 2012-12-31 08:00 | 2013-01-11 17:00 | 11 | 1551 | 100 | 91 | -9 | 6501 | 6501 | 5915.91 | 5882.2421 | 0.91 | 1.0057 | FALSE | FALSE | FALSE | 193.875 | FALSE | 0 | Green | Continue normal monitoring.
146220 | HCMEB3Z2090 | B3 Z2 :Sprinklers Final Fix | 26401 | 2013-11-18 16:00 | 2013-12-02 16:00 | 14 | 344 | 100 | 97 | -3 | 20734 | 20734 | 20111.98 | 24774.7367 | 0.97 | 0.81179 | TRUE | FALSE | FALSE | 43 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146221 | HCMEB3Z2300 | B3 Z2 :Duct Installation& Dusct Accecories Installation, Fan coil Unit | 26402 | 2013-07-23 16:00 | 2013-08-02 16:00 | 10 | 137 | 100 | 85 | -15 | 9540 | 9540 | 8109 | 11223.2084 | 0.85 | 0.72252 | TRUE | TRUE | TRUE | 17.125 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146222 | HCMEB3Z2310 | B3 Z2 :Duct Insulation Work | 26402 | 2013-08-02 16:00 | 2013-08-23 16:00 | 21 | 137 | 100 | 97 | -3 | 23037 | 23037 | 22345.89 | 28647.9504 | 0.97 | 0.78002 | TRUE | FALSE | FALSE | 17.125 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146223 | HCMEB3Z2320 | B3 Z2 :Exhaust Fans | 26402 | 2013-08-23 16:00 | 2013-09-13 16:00 | 21 | 137 | 100 | 98 | -2 | 21189 | 21189 | 20765.22 | 25721.2736 | 0.98 | 0.80732 | TRUE | FALSE | FALSE | 17.125 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146224 | HCMEB3Z2330 | B3 Z2 :Grills & Diffusers | 26402 | 2013-12-12 16:00 | 2013-12-26 16:00 | 14 | 25 | 100 | 100 | 0 | 23884 | 23884 | 23884 | 28439.0642 | 1 | 0.83983 | TRUE | FALSE | FALSE | 3.125 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146225 | HCMEB3Z2340 | B3 Z2 :Mechanical final Fix | 26402 | 2013-12-26 16:00 | 2014-01-09 16:00 | 14 | 25 | 100 | 84 | -16 | 12390 | 12390 | 10407.6 | 10792.0587 | 0.84 | 0.96438 | FALSE | TRUE | TRUE | 3.125 | TRUE | 4 | Orange | Develop recovery plan and review schedule and cost exposure.
146226 | HCMEB3Z2350 | B3 Z2 :All Vertical Piping Works | 26602 | 2012-12-03 08:00 | 2012-12-14 17:00 | 11 | 511 | 100 | 100 | 0 | 9944 | 9944 | 9944 | 8867.7226 | 1 | 1.1214 | FALSE | FALSE | FALSE | 63.875 | FALSE | 0 | Green | Continue normal monitoring.
146227 | HCMEB3Z2360 | B3 Z2 :All Horizantal Piping Works | 26602 | 2012-12-17 08:00 | 2013-01-25 17:00 | 39 | 511 | 100 | 88 | -12 | 29055 | 29055 | 25568.4 | 31309.4727 | 0.88 | 0.81663 | TRUE | TRUE | TRUE | 63.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146228 | HCMEB3Z2370 | B3 Z2 :Mechanical Final Fix | 26602 | 2013-06-03 08:00 | 2013-06-28 17:00 | 25 | 511 | 100 | 100 | 0 | 31025 | 31025 | 31025 | 32966.9074 | 1 | 0.9411 | FALSE | FALSE | FALSE | 63.875 | FALSE | 0 | Green | Continue normal monitoring.
146229 | HCMEB3Z3135 | B3 Z3 :B3 Z3 :Blocks Start Date for All Parts | 26415 | 2012-12-09 16:00 | 2012-12-09 16:00 | 1 | 1608 | 100 | 82 | -18 | 1160 | 1160 | 951.2 | 1198.4949 | 0.82 | 0.79366 | TRUE | TRUE | TRUE | 201 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146230 | HCMEB3Z3145 | B3 Z3 :B3 Z3 :Tiling Finish Date for All Parts | 26415 | 2013-06-05 16:00 | 2013-06-05 16:00 | 1 | 1512 | 100 | 100 | 0 | 1149 | 1149 | 1149 | 1159.0144 | 1 | 0.99136 | FALSE | FALSE | FALSE | 189 | FALSE | 0 | Green | Continue normal monitoring.
146231 | HCMEB3Z3155 | B3 Z3 :B3 Z3 :Plastering Finish Date for All Parts | 26415 | 2013-03-02 10:00 | 2013-03-02 10:00 | 1 | 1653 | 100 | 89 | -11 | 1994 | 1994 | 1774.66 | 2038.8335 | 0.89 | 0.87043 | TRUE | TRUE | TRUE | 206.625 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146232 | HCMEB3Z3165 | B3 Z3 :B3 Z3 :Gypsum Boards Finish Date for All Parts | 26415 | 2013-11-09 16:00 | 2013-11-09 16:00 | 1 | 1320 | 100 | 98 | -2 | 1946 | 1946 | 1907.08 | 2097.2415 | 0.98 | 0.90933 | FALSE | FALSE | FALSE | 165 | FALSE | 0 | Green | Continue normal monitoring.
146233 | HCMEB3Z3195 | B3 Z3 :B3 Z3 :Electrical Coduits & Boards F.F for All Systems | 26415 | 2012-12-10 08:00 | 2012-12-25 17:00 | 15 | 1351 | 100 | 82 | -18 | 21000 | 21000 | 17220 | 17867.4427 | 0.82 | 0.96376 | FALSE | TRUE | TRUE | 168.875 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146234 | HCMEB3Z3205 | B3 Z3 :B3 Z3 :Electrical Boards Seconed Fix | 26415 | 2013-04-15 16:00 | 2013-05-01 16:00 | 16 | 1120 | 100 | 100 | 0 | 9024 | 9024 | 9024 | 8611.4544 | 1 | 1.0479 | FALSE | FALSE | FALSE | 140 | FALSE | 0 | Green | Continue normal monitoring.
146235 | HCMEB3Z3215 | B3 Z3 :B3 Z3 :Cable Tray Installation | 26415 | 2013-10-09 16:00 | 2013-10-23 16:00 | 14 | 168 | 100 | 100 | 0 | 21504 | 21504 | 21504 | 22736.4348 | 1 | 0.94579 | FALSE | FALSE | FALSE | 21 | FALSE | 0 | Green | Continue normal monitoring.
146236 | HCMEB3Z3225 | B3 Z3 :B3 Z3 :Electrcial Wiring | 26415 | 2013-11-22 16:00 | 2013-12-04 16:00 | 12 | 296 | 100 | 100 | 0 | 8544 | 8544 | 8544 | 9730.6457 | 1 | 0.87805 | TRUE | FALSE | FALSE | 37 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146237 | HCMEB3Z3235 | B3 Z3 :B3 Z3 :Cable Laying | 26415 | 2013-10-23 16:00 | 2013-11-06 16:00 | 14 | 168 | 100 | 100 | 0 | 10374 | 10374 | 10374 | 9540.5806 | 1 | 1.0874 | FALSE | FALSE | FALSE | 21 | FALSE | 0 | Green | Continue normal monitoring.
146238 | HCMEB3Z3245 | B3 Z3 :B3 Z3 :Electrical Final Fix for All Systems & Boards (Vertical Elements) | 26415 | 2014-01-03 16:00 | 2014-01-17 16:00 | 14 | 712 | 100 | 94 | -6 | 13888 | 13888 | 13054.72 | 14842.8343 | 0.94 | 0.87953 | TRUE | FALSE | FALSE | 89 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146239 | HCMEB3Z3255 | B3 Z3 :B3 Z3 :Electrical Final Fix for All Systems (Horizantel Elements) | 26415 | 2014-01-17 16:00 | 2014-01-31 16:00 | 14 | 712 | 100 | 80 | -20 | 24304 | 24304 | 19443.2 | 27604.0913 | 0.8 | 0.70436 | TRUE | TRUE | TRUE | 89 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146240 | HCMEB3Z3045 | B3 Z3 :B3 Z3 :All Vertical Piping Works | 26663 | 2012-12-03 08:00 | 2012-12-14 17:00 | 11 | 511 | 100 | 86 | -14 | 9207 | 9207 | 7918.02 | 9463.4247 | 0.86 | 0.8367 | TRUE | TRUE | TRUE | 63.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146241 | HCMEB3Z3055 | B3 Z3 :B3 Z3 :All Horizantal Piping Works | 26663 | 2012-12-17 08:00 | 2013-01-25 17:00 | 39 | 511 | 100 | 91 | -9 | 26208 | 26208 | 23849.28 | 22560.6969 | 0.91 | 1.0571 | FALSE | FALSE | FALSE | 63.875 | FALSE | 0 | Green | Continue normal monitoring.
146242 | HCMEB3Z3065 | B3 Z3 :B3 Z3 :Mechanical Final Fix | 26663 | 2013-06-03 08:00 | 2013-06-28 17:00 | 25 | 511 | 100 | 96 | -4 | 29275 | 29275 | 28104 | 30144.6801 | 0.96 | 0.9323 | FALSE | FALSE | FALSE | 63.875 | FALSE | 0 | Green | Continue normal monitoring.
146243 | HCMEB3Z3075 | B3 Z3 :B3 Z3 :Horizontal F.F Piping Work | 26410 | 2012-12-10 08:00 | 2013-01-04 17:00 | 25 | 1511 | 100 | 100 | 0 | 16575 | 16575 | 16575 | 16054.1796 | 1 | 1.0324 | FALSE | FALSE | FALSE | 188.875 | FALSE | 0 | Green | Continue normal monitoring.
146244 | HCMEB3Z3085 | B3 Z3 :B3 Z3 :Fire Hose Cabinets | 26410 | 2013-01-07 08:00 | 2013-01-18 17:00 | 11 | 1511 | 100 | 100 | 0 | 10604 | 10604 | 10604 | 12956.6018 | 1 | 0.81842 | TRUE | FALSE | FALSE | 188.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146245 | HCMEB3Z3095 | B3 Z3 :B3 Z3 :Sprinklers Final Fix | 26410 | 2013-11-18 16:00 | 2013-12-02 16:00 | 14 | 344 | 100 | 100 | 0 | 20916 | 20916 | 20916 | 18821.1654 | 1 | 1.1113 | FALSE | FALSE | FALSE | 43 | FALSE | 0 | Green | Continue normal monitoring.
146246 | HCMEB3Z3305 | B3 Z3 :B3 Z3 :Duct Installation& Dusct Accecories Installation, Fan coil Unit | 26394 | 2013-07-25 16:00 | 2013-08-08 16:00 | 14 | 200 | 100 | 100 | 0 | 13944 | 13944 | 13944 | 15491.6499 | 1 | 0.9001 | FALSE | FALSE | FALSE | 25 | FALSE | 0 | Green | Continue normal monitoring.
146247 | HCMEB3Z3315 | B3 Z3 :B3 Z3 :Duct Insulation Work | 26394 | 2013-08-08 16:00 | 2013-08-29 16:00 | 21 | 200 | 100 | 100 | 0 | 25179 | 25179 | 25179 | 21933.1224 | 1 | 1.148 | FALSE | FALSE | FALSE | 25 | FALSE | 0 | Green | Continue normal monitoring.
146248 | HCMEB3Z3325 | B3 Z3 :B3 Z3 :Exhaust Fans | 26394 | 2013-08-29 16:00 | 2013-09-19 16:00 | 21 | 200 | 100 | 100 | 0 | 18774 | 18774 | 18774 | 19308.4615 | 1 | 0.97232 | FALSE | FALSE | FALSE | 25 | FALSE | 0 | Green | Continue normal monitoring.
146249 | HCMEB3Z3335 | B3 Z3 :B3 Z3 :Grills & Diffusers | 26394 | 2013-12-12 16:00 | 2013-12-26 16:00 | 14 | 120 | 100 | 99 | -1 | 16828 | 16828 | 16659.72 | 18032.7467 | 0.99 | 0.92386 | FALSE | FALSE | FALSE | 15 | FALSE | 0 | Green | Continue normal monitoring.
146250 | HCMEB3Z3345 | B3 Z3 :B3 Z3 :Mechanical final Fix | 26394 | 2013-12-26 16:00 | 2014-01-09 16:00 | 14 | 120 | 100 | 84 | -16 | 11298 | 11298 | 9490.32 | 10949.8179 | 0.84 | 0.86671 | TRUE | TRUE | TRUE | 15 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146251 | HCMEB3Z3355 | B3 Z3 :B3 Z3 :All Vertical Piping Works | 26608 | 2012-12-03 08:00 | 2012-12-14 17:00 | 11 | 511 | 100 | 83 | -17 | 7502 | 7502 | 6226.66 | 7742.291 | 0.83 | 0.80424 | TRUE | TRUE | TRUE | 63.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146252 | HCMEB3Z3365 | B3 Z3 :B3 Z3 :All Horizantal Piping Works | 26608 | 2012-12-17 08:00 | 2013-01-25 17:00 | 39 | 511 | 100 | 100 | 0 | 43992 | 43992 | 43992 | 40271.2234 | 1 | 1.0924 | FALSE | FALSE | FALSE | 63.875 | FALSE | 0 | Green | Continue normal monitoring.
146253 | HCMEB3Z3375 | B3 Z3 :B3 Z3 :Mechanical Final Fix | 26608 | 2013-06-03 08:00 | 2013-06-28 17:00 | 25 | 511 | 100 | 91 | -9 | 25225 | 25225 | 22954.75 | 24509.8596 | 0.91 | 0.93655 | FALSE | FALSE | FALSE | 63.875 | FALSE | 0 | Green | Continue normal monitoring.
146254 | HCMEB3Z4140 | B3 Z4 :Blocks Start Date for All Parts | 26421 | 2013-01-07 16:00 | 2013-01-07 16:00 | 1 | 1753 | 100 | 100 | 0 | 1045 | 1045 | 1045 | 1147.8724 | 1 | 0.91038 | FALSE | FALSE | FALSE | 219.125 | FALSE | 0 | Green | Continue normal monitoring.
146255 | HCMEB3Z4150 | B3 Z4 :Tiling Finish Date for All Parts | 26421 | 2013-05-20 10:00 | 2013-05-20 10:00 | 1 | 1069 | 100 | 99 | -1 | 1123 | 1123 | 1111.77 | 1090.1186 | 0.99 | 1.0199 | FALSE | FALSE | FALSE | 133.625 | FALSE | 0 | Green | Continue normal monitoring.
146256 | HCMEB3Z4160 | B3 Z4 :Plastering Finish Date for All Parts | 26421 | 2013-03-02 16:00 | 2013-03-02 16:00 | 1 | 1944 | 100 | 100 | 0 | 1093 | 1093 | 1093 | 1322.4177 | 1 | 0.82652 | TRUE | FALSE | FALSE | 243 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146257 | HCMEB3Z4170 | B3 Z4 :Gypsum Boards Finish Date for All Parts | 26421 | 2013-11-09 16:00 | 2013-11-09 16:00 | 1 | 1320 | 100 | 100 | 0 | 1243 | 1243 | 1243 | 1368.9939 | 1 | 0.90797 | FALSE | FALSE | FALSE | 165 | FALSE | 0 | Green | Continue normal monitoring.
146258 | HCMEB3Z4200 | B3 Z4 :Electrical Coduits & Boards F.F for All Systems | 26421 | 2013-01-07 16:00 | 2013-01-23 16:00 | 16 | 1472 | 100 | 97 | -3 | 28000 | 28000 | 27160 | 28712.869 | 0.97 | 0.94592 | FALSE | FALSE | FALSE | 184 | FALSE | 0 | Green | Continue normal monitoring.
146259 | HCMEB3Z4210 | B3 Z4 :Electrical Boards Seconed Fix | 26421 | 2013-04-15 16:00 | 2013-05-01 16:00 | 16 | 1408 | 100 | 96 | -4 | 31344 | 31344 | 30090.24 | 27128.319 | 0.96 | 1.1092 | FALSE | FALSE | FALSE | 176 | FALSE | 0 | Green | Continue normal monitoring.
146260 | HCMEB3Z4220 | B3 Z4 :Cable Tray Installation | 26421 | 2013-10-09 16:00 | 2013-10-23 16:00 | 14 | 360 | 100 | 98 | -2 | 27230 | 27230 | 26685.4 | 28586.5805 | 0.98 | 0.93349 | FALSE | FALSE | FALSE | 45 | FALSE | 0 | Green | Continue normal monitoring.
146261 | HCMEB3Z4230 | B3 Z4 :Electrcial Wiring | 26421 | 2013-05-27 08:00 | 2013-06-21 17:00 | 25 | 855 | 100 | 88 | -12 | 26325 | 26325 | 23166 | 30429.3438 | 0.88 | 0.7613 | TRUE | TRUE | TRUE | 106.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146262 | HCMEB3Z4240 | B3 Z4 :Cable Laying | 26421 | 2013-10-23 16:00 | 2013-11-06 16:00 | 14 | 360 | 100 | 83 | -17 | 7280 | 7280 | 6042.4 | 6961.3037 | 0.83 | 0.868 | TRUE | TRUE | TRUE | 45 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146263 | HCMEB3Z4250 | B3 Z4 :Electrical Final Fix for All Systems & Boards (Vertical Elements) | 26421 | 2013-12-18 16:00 | 2014-01-01 16:00 | 14 | 808 | 100 | 100 | 0 | 14742 | 14742 | 14742 | 17288.0824 | 1 | 0.85273 | TRUE | FALSE | FALSE | 101 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146264 | HCMEB3Z4260 | B3 Z4 :Electrical Final Fix for All Systems (Horizantel Elements) | 26421 | 2014-01-01 16:00 | 2014-01-15 16:00 | 14 | 808 | 100 | 100 | 0 | 12544 | 12544 | 12544 | 11925.8656 | 1 | 1.0518 | FALSE | FALSE | FALSE | 101 | FALSE | 0 | Green | Continue normal monitoring.
146265 | HCMEB3Z4050 | B3 Z4 :All Vertical Piping Works | 26460 | 2012-12-03 08:00 | 2012-12-14 17:00 | 11 | 1056 | 100 | 81 | -19 | 12364 | 12364 | 10014.84 | 14583.3201 | 0.81 | 0.68673 | TRUE | TRUE | TRUE | 132 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146266 | HCMEB3Z4060 | B3 Z4 :All Horizantal Piping Works | 26460 | 2012-12-17 08:00 | 2013-01-25 17:00 | 39 | 1151 | 100 | 83 | -17 | 23556 | 23556 | 19551.48 | 20826.0324 | 0.83 | 0.9388 | FALSE | TRUE | TRUE | 143.875 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146267 | HCMEB3Z4070 | B3 Z4 :Mechanical Final Fix | 26460 | 2013-06-03 08:00 | 2013-06-28 17:00 | 25 | 1151 | 100 | 81 | -19 | 17275 | 17275 | 13992.75 | 20669.0794 | 0.81 | 0.67699 | TRUE | TRUE | TRUE | 143.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146268 | HCMEB3Z4080 | B3 Z4 :Horizontal F.F Piping Work | 26419 | 2013-01-07 16:00 | 2013-02-04 16:00 | 28 | 1664 | 100 | 94 | -6 | 14448 | 14448 | 13581.12 | 15165.6983 | 0.94 | 0.89552 | TRUE | FALSE | FALSE | 208 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146269 | HCMEB3Z4090 | B3 Z4 :Fire Hose Cabinets | 26419 | 2013-02-04 16:00 | 2013-02-18 16:00 | 14 | 1664 | 100 | 81 | -19 | 23002 | 23002 | 18631.62 | 22280.0831 | 0.81 | 0.83625 | TRUE | TRUE | TRUE | 208 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146270 | HCMEB3Z4100 | B3 Z4 :Sprinklers Final Fix | 26419 | 2013-11-18 16:00 | 2013-12-02 16:00 | 14 | 664 | 100 | 83 | -17 | 12488 | 12488 | 10365.04 | 11939.0937 | 0.83 | 0.86816 | TRUE | TRUE | TRUE | 83 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146271 | HCMEB3Z4310 | B3 Z4 :Duct Installation& Dusct Accecories Installation, Fan coil Unit | 26423 | 2013-07-31 16:00 | 2013-08-20 16:00 | 20 | 296 | 100 | 85 | -15 | 18480 | 18480 | 15708 | 18901.4221 | 0.85 | 0.83105 | TRUE | TRUE | TRUE | 37 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146272 | HCMEB3Z4320 | B3 Z4 :Duct Insulation Work | 26423 | 2013-08-20 16:00 | 2013-09-10 16:00 | 21 | 456 | 100 | 86 | -14 | 13188 | 13188 | 11341.68 | 16479.9859 | 0.86 | 0.68821 | TRUE | TRUE | TRUE | 57 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146273 | HCMEB3Z4330 | B3 Z4 :Exhaust Fans | 26423 | 2013-09-10 16:00 | 2013-10-01 16:00 | 21 | 456 | 100 | 89 | -11 | 34713 | 34713 | 30894.57 | 32565.3399 | 0.89 | 0.94869 | FALSE | TRUE | TRUE | 57 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146274 | HCMEB3Z4340 | B3 Z4 :Grills & Diffusers | 26423 | 2013-12-12 16:00 | 2013-12-26 16:00 | 14 | 440 | 100 | 98 | -2 | 14994 | 14994 | 14694.12 | 13363.9522 | 0.98 | 1.0995 | FALSE | FALSE | FALSE | 55 | FALSE | 0 | Green | Continue normal monitoring.
146275 | HCMEB3Z4350 | B3 Z4 :Mechanical final Fix | 26423 | 2013-12-26 16:00 | 2014-01-09 16:00 | 14 | 440 | 100 | 98 | -2 | 7392 | 7392 | 7244.16 | 8013.032 | 0.98 | 0.90405 | FALSE | FALSE | FALSE | 55 | FALSE | 0 | Green | Continue normal monitoring.
146276 | HCMEB3Z4360 | B3 Z4 :All Vertical Piping Works | 26611 | 2012-12-03 08:00 | 2012-12-14 17:00 | 11 | 1151 | 100 | 100 | 0 | 17820 | 17820 | 17820 | 18629.3307 | 1 | 0.95656 | FALSE | FALSE | FALSE | 143.875 | FALSE | 0 | Green | Continue normal monitoring.
146277 | HCMEB3Z4370 | B3 Z4 :All Horizantal Piping Works | 26611 | 2012-12-17 08:00 | 2013-01-25 17:00 | 39 | 1151 | 100 | 100 | 0 | 59787 | 59787 | 59787 | 63354.999 | 1 | 0.94368 | FALSE | FALSE | FALSE | 143.875 | FALSE | 0 | Green | Continue normal monitoring.
146278 | HCMEB3Z4380 | B3 Z4 :Mechanical Final Fix | 26611 | 2013-06-03 08:00 | 2013-06-28 17:00 | 25 | 1151 | 100 | 100 | 0 | 18525 | 18525 | 18525 | 20688.2414 | 1 | 0.89544 | TRUE | FALSE | FALSE | 143.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146279 | HCMEB3Z5145 | B3 Z5 :Blocks Start Date for All Parts | 26426 | 2012-12-20 16:00 | 2012-12-20 16:00 | 1 | 1865 | 100 | 91 | -9 | 731 | 731 | 665.21 | 699.4629 | 0.91 | 0.95103 | FALSE | FALSE | FALSE | 233.125 | FALSE | 0 | Green | Continue normal monitoring.
146280 | HCMEB3Z5155 | B3 Z5 :Tiling Finish Date for All Parts | 26426 | 2013-06-24 12:00 | 2013-06-24 12:00 | 1 | 1059 | 100 | 82 | -18 | 1288 | 1288 | 1056.16 | 1563.9746 | 0.82 | 0.67531 | TRUE | TRUE | TRUE | 132.375 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146281 | HCMEB3Z5165 | B3 Z5 :Plastering Finish Date for All Parts | 26426 | 2013-04-13 16:00 | 2013-04-13 16:00 | 1 | 1656 | 100 | 92 | -8 | 1807 | 1807 | 1662.44 | 1850.8538 | 0.92 | 0.8982 | TRUE | FALSE | FALSE | 207 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146282 | HCMEB3Z5175 | B3 Z5 :Gypsum Boards Finish Date for All Parts | 26426 | 2013-07-15 12:00 | 2013-07-15 12:00 | 1 | 2123 | 100 | 97 | -3 | 1214 | 1214 | 1177.58 | 1094.5843 | 0.97 | 1.0758 | FALSE | FALSE | FALSE | 265.375 | FALSE | 0 | Green | Continue normal monitoring.
146283 | HCMEB3Z5205 | B3 Z5 :Electrical Coduits & Boards F.F for All Systems | 26426 | 2012-12-20 16:00 | 2013-01-07 16:00 | 18 | 1568 | 100 | 87 | -13 | 22644 | 22644 | 19700.28 | 25970.8452 | 0.87 | 0.75855 | TRUE | TRUE | TRUE | 196 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146284 | HCMEB3Z5215 | B3 Z5 :Electrical Boards Seconed Fix | 26426 | 2013-04-15 16:00 | 2013-05-01 16:00 | 16 | 1408 | 100 | 100 | 0 | 20816 | 20816 | 20816 | 23048.3441 | 1 | 0.90315 | FALSE | FALSE | FALSE | 176 | FALSE | 0 | Green | Continue normal monitoring.
146285 | HCMEB3Z5225 | B3 Z5 :Cable Tray Installation | 26426 | 2013-10-09 16:00 | 2013-10-23 16:00 | 14 | 360 | 100 | 94 | -6 | 17850 | 17850 | 16779 | 17426.9079 | 0.94 | 0.96282 | FALSE | FALSE | FALSE | 45 | FALSE | 0 | Green | Continue normal monitoring.
146286 | HCMEB3Z5235 | B3 Z5 :Electrcial Wiring | 26426 | 2013-06-24 13:00 | 2013-07-22 12:00 | 27 | 883 | 100 | 80 | -20 | 33075 | 33075 | 26460 | 36336.4427 | 0.8 | 0.72819 | TRUE | TRUE | TRUE | 110.375 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146287 | HCMEB3Z5245 | B3 Z5 :Cable Laying | 26426 | 2013-10-23 16:00 | 2013-11-06 16:00 | 14 | 360 | 100 | 82 | -18 | 9786 | 9786 | 8024.52 | 9178.7276 | 0.82 | 0.87425 | TRUE | TRUE | TRUE | 45 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146288 | HCMEB3Z5255 | B3 Z5 :Electrical Final Fix for All Systems & Boards (Vertical Elements) | 26426 | 2013-12-18 16:00 | 2014-01-01 16:00 | 14 | 808 | 100 | 100 | 0 | 20216 | 20216 | 20216 | 20780.749 | 1 | 0.97282 | FALSE | FALSE | FALSE | 101 | FALSE | 0 | Green | Continue normal monitoring.
146289 | HCMEB3Z5265 | B3 Z5 :Electrical Final Fix for All Systems (Horizantel Elements) | 26426 | 2014-01-01 16:00 | 2014-01-15 16:00 | 14 | 808 | 100 | 87 | -13 | 8092 | 8092 | 7040.04 | 9789.4185 | 0.87 | 0.71915 | TRUE | TRUE | TRUE | 101 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146290 | HCMEB3Z5055 | B3 Z5 :All Vertical Piping Works | 26466 | 2012-12-03 08:00 | 2012-12-14 17:00 | 11 | 1056 | 100 | 83 | -17 | 16005 | 16005 | 13284.15 | 14459.1362 | 0.83 | 0.91874 | FALSE | TRUE | TRUE | 132 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146291 | HCMEB3Z5065 | B3 Z5 :All Horizantal Piping Works | 26466 | 2012-12-17 08:00 | 2013-01-25 17:00 | 39 | 1056 | 100 | 95 | -5 | 52845 | 52845 | 50202.75 | 53092.2396 | 0.95 | 0.94558 | FALSE | FALSE | FALSE | 132 | FALSE | 0 | Green | Continue normal monitoring.
146292 | HCMEB3Z5075 | B3 Z5 :Mechanical Final Fix | 26466 | 2013-06-03 08:00 | 2013-06-28 17:00 | 25 | 1056 | 100 | 100 | 0 | 42400 | 42400 | 42400 | 49966.5755 | 1 | 0.84857 | TRUE | FALSE | FALSE | 132 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146293 | HCMEB3Z5085 | B3 Z5 :Horizontal F.F Piping Work | 26427 | 2012-12-20 16:00 | 2013-01-17 16:00 | 28 | 1760 | 100 | 100 | 0 | 27048 | 27048 | 27048 | 33479.9159 | 1 | 0.80789 | TRUE | FALSE | FALSE | 220 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146294 | HCMEB3Z5095 | B3 Z5 :Fire Hose Cabinets | 26427 | 2013-01-17 16:00 | 2013-01-31 16:00 | 14 | 1760 | 100 | 89 | -11 | 15120 | 15120 | 13456.8 | 15597.3453 | 0.89 | 0.86276 | TRUE | TRUE | TRUE | 220 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146295 | HCMEB3Z5105 | B3 Z5 :Sprinklers Final Fix | 26427 | 2013-11-18 16:00 | 2013-12-02 16:00 | 14 | 664 | 100 | 91 | -9 | 27146 | 27146 | 24702.86 | 28579.3047 | 0.91 | 0.86436 | TRUE | FALSE | FALSE | 83 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146296 | HCMEB3Z5315 | B3 Z5 :Duct Installation& Dusct Accecories Installation, Fan coil Unit | 26428 | 2013-07-31 16:00 | 2013-08-20 16:00 | 20 | 296 | 100 | 93 | -7 | 28780 | 28780 | 26765.4 | 31049.8436 | 0.93 | 0.86201 | TRUE | FALSE | FALSE | 37 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146297 | HCMEB3Z5325 | B3 Z5 :Duct Insulation Work | 26428 | 2013-08-20 16:00 | 2013-09-10 16:00 | 21 | 456 | 100 | 93 | -7 | 19908 | 19908 | 18514.44 | 24346.2747 | 0.93 | 0.76046 | TRUE | FALSE | FALSE | 57 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146298 | HCMEB3Z5335 | B3 Z5 :Exhaust Fans | 26428 | 2013-09-10 16:00 | 2013-10-01 16:00 | 21 | 456 | 100 | 81 | -19 | 12306 | 12306 | 9967.86 | 14684.5371 | 0.81 | 0.6788 | TRUE | TRUE | TRUE | 57 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146299 | HCMEB3Z5345 | B3 Z5 :Grills & Diffusers | 26428 | 2013-12-12 16:00 | 2013-12-26 16:00 | 14 | 440 | 100 | 100 | 0 | 8400 | 8400 | 8400 | 7713.2198 | 1 | 1.089 | FALSE | FALSE | FALSE | 55 | FALSE | 0 | Green | Continue normal monitoring.
146300 | HCMEB3Z5355 | B3 Z5 :Mechanical final Fix | 26428 | 2013-12-26 16:00 | 2014-01-09 16:00 | 14 | 440 | 100 | 84 | -16 | 21434 | 21434 | 18004.56 | 21963.4868 | 0.84 | 0.81975 | TRUE | TRUE | TRUE | 55 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146301 | HCMEB3Z5365 | B3 Z5 :All Vertical Piping Works | 26613 | 2012-12-03 08:00 | 2012-12-14 17:00 | 11 | 1951 | 100 | 84 | -16 | 14784 | 14784 | 12418.56 | 15310.3129 | 0.84 | 0.81112 | TRUE | TRUE | TRUE | 243.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146302 | HCMEB3Z5375 | B3 Z5 :All Horizantal Piping Works | 26613 | 2012-12-17 08:00 | 2013-01-25 17:00 | 39 | 1951 | 100 | 85 | -15 | 67197 | 67197 | 57117.45 | 78327.4066 | 0.85 | 0.72921 | TRUE | TRUE | TRUE | 243.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146303 | HCMEB3Z5385 | B3 Z5 :Mechanical Final Fix | 26613 | 2013-06-03 08:00 | 2013-06-28 17:00 | 25 | 1951 | 100 | 92 | -8 | 14650 | 14650 | 13478 | 15985.4523 | 0.92 | 0.84314 | TRUE | FALSE | FALSE | 243.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146304 | HCMEB3Z6150 | B3 Z6 :Blocks Start Date for All Parts | 26396 | 2013-01-09 16:00 | 2013-01-09 16:00 | 1 | 1737 | 100 | 88 | -12 | 542 | 542 | 476.96 | 602.535 | 0.88 | 0.79159 | TRUE | TRUE | TRUE | 217.125 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146305 | HCMEB3Z6160 | B3 Z6 :Tiling Finish Date for All Parts | 26396 | 2013-07-02 10:00 | 2013-07-02 10:00 | 1 | 1005 | 100 | 100 | 0 | 1908 | 1908 | 1908 | 2383.6262 | 1 | 0.80046 | TRUE | FALSE | FALSE | 125.625 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146306 | HCMEB3Z6170 | B3 Z6 :Plastering Finish Date for All Parts | 26396 | 2013-04-13 16:00 | 2013-04-13 16:00 | 1 | 1656 | 100 | 100 | 0 | 1958 | 1958 | 1958 | 1723.0087 | 1 | 1.1364 | FALSE | FALSE | FALSE | 207 | FALSE | 0 | Green | Continue normal monitoring.
146307 | HCMEB3Z6180 | B3 Z6 :Gypsum Boards Finish Date for All Parts | 26396 | 2013-07-23 10:00 | 2013-07-23 10:00 | 1 | 2069 | 100 | 100 | 0 | 907 | 907 | 907 | 851.858 | 1 | 1.0647 | FALSE | FALSE | FALSE | 258.625 | FALSE | 0 | Green | Continue normal monitoring.
146308 | HCMEB3Z6210 | B3 Z6 :Electrical Coduits & Boards F.F for All Systems | 26396 | 2013-01-09 16:00 | 2013-01-25 16:00 | 16 | 1456 | 100 | 100 | 0 | 18608 | 18608 | 18608 | 18852.851 | 1 | 0.98701 | FALSE | FALSE | FALSE | 182 | FALSE | 0 | Green | Continue normal monitoring.
146309 | HCMEB3Z6220 | B3 Z6 :Electrical Boards Seconed Fix | 26396 | 2013-04-15 16:00 | 2013-05-01 16:00 | 16 | 1408 | 100 | 94 | -6 | 24640 | 24640 | 23161.6 | 24371.7434 | 0.94 | 0.95035 | FALSE | FALSE | FALSE | 176 | FALSE | 0 | Green | Continue normal monitoring.
146310 | HCMEB3Z6230 | B3 Z6 :Cable Tray Installation | 26396 | 2013-10-09 16:00 | 2013-10-23 16:00 | 14 | 360 | 100 | 93 | -7 | 9058 | 9058 | 8423.94 | 7777.7262 | 0.93 | 1.0831 | FALSE | FALSE | FALSE | 45 | FALSE | 0 | Green | Continue normal monitoring.
146311 | HCMEB3Z6240 | B3 Z6 :Electrcial Wiring | 26396 | 2013-07-02 10:00 | 2013-07-30 10:00 | 28 | 837 | 100 | 100 | 0 | 21728 | 21728 | 21728 | 19266.4575 | 1 | 1.1278 | FALSE | FALSE | FALSE | 104.625 | FALSE | 0 | Green | Continue normal monitoring.
146312 | HCMEB3Z6250 | B3 Z6 :Cable Laying | 26396 | 2013-10-23 16:00 | 2013-11-06 16:00 | 14 | 360 | 100 | 86 | -14 | 10234 | 10234 | 8801.24 | 11486.4504 | 0.86 | 0.76623 | TRUE | TRUE | TRUE | 45 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146313 | HCMEB3Z6260 | B3 Z6 :Electrical Final Fix for All Systems & Boards (Vertical Elements) | 26396 | 2013-12-18 16:00 | 2014-01-01 16:00 | 14 | 808 | 100 | 100 | 0 | 12110 | 12110 | 12110 | 14552.9477 | 1 | 0.83213 | TRUE | FALSE | FALSE | 101 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146314 | HCMEB3Z6270 | B3 Z6 :Electrical Final Fix for All Systems (Horizantel Elements) | 26396 | 2014-01-01 16:00 | 2014-01-15 16:00 | 14 | 808 | 100 | 99 | -1 | 24514 | 24514 | 24268.86 | 25879.2044 | 0.99 | 0.93777 | FALSE | FALSE | FALSE | 101 | FALSE | 0 | Green | Continue normal monitoring.
146315 | HCMEB3Z6060 | B3 Z6 :All Vertical Piping Works | 26467 | 2012-12-03 08:00 | 2012-12-14 17:00 | 11 | 1391 | 100 | 81 | -19 | 10285 | 10285 | 8330.85 | 10960.4821 | 0.81 | 0.76008 | TRUE | TRUE | TRUE | 173.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146316 | HCMEB3Z6070 | B3 Z6 :All Horizantal Piping Works | 26467 | 2012-12-17 08:00 | 2013-01-25 17:00 | 39 | 1391 | 100 | 86 | -14 | 35022 | 35022 | 30118.92 | 33342.2529 | 0.86 | 0.90333 | FALSE | TRUE | TRUE | 173.875 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146317 | HCMEB3Z6080 | B3 Z6 :Mechanical Final Fix | 26467 | 2013-06-03 08:00 | 2013-06-28 17:00 | 25 | 1391 | 100 | 85 | -15 | 43350 | 43350 | 36847.5 | 50162.4761 | 0.85 | 0.73456 | TRUE | TRUE | TRUE | 173.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146318 | HCMEB3Z6100 | B3 Z6 :Horizontal F.F Piping Work | 26432 | 2013-01-09 16:00 | 2013-02-06 16:00 | 28 | 1648 | 100 | 96 | -4 | 53592 | 53592 | 51448.32 | 61669.2702 | 0.96 | 0.83426 | TRUE | FALSE | FALSE | 206 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146319 | HCMEB3Z6110 | B3 Z6 :Fire Hose Cabinets | 26432 | 2013-02-06 16:00 | 2013-02-20 16:00 | 14 | 1648 | 100 | 100 | 0 | 13972 | 13972 | 13972 | 15164.4582 | 1 | 0.92136 | FALSE | FALSE | FALSE | 206 | FALSE | 0 | Green | Continue normal monitoring.
146320 | HCMEB3Z6330 | B3 Z6 :Sprinklers Final Fix | 26432 | 2013-11-18 16:00 | 2013-12-02 16:00 | 14 | 664 | 100 | 100 | 0 | 14546 | 14546 | 14546 | 13601.4659 | 1 | 1.0694 | FALSE | FALSE | FALSE | 83 | FALSE | 0 | Green | Continue normal monitoring.
146321 | HCMEB3Z6340 | B3 Z6 :Duct Installation& Dusct Accecories Installation, Fan coil Unit | 26433 | 2013-07-31 16:00 | 2013-08-20 16:00 | 20 | 296 | 100 | 100 | 0 | 21240 | 21240 | 21240 | 18878.2668 | 1 | 1.1251 | FALSE | FALSE | FALSE | 37 | FALSE | 0 | Green | Continue normal monitoring.
146322 | HCMEB3Z6350 | B3 Z6 :Duct Insulation Work | 26433 | 2013-08-20 16:00 | 2013-09-10 16:00 | 21 | 456 | 100 | 100 | 0 | 19761 | 19761 | 19761 | 17304.6174 | 1 | 1.1419 | FALSE | FALSE | FALSE | 57 | FALSE | 0 | Green | Continue normal monitoring.
146323 | HCMEB3Z6370 | B3 Z6 :Exhaust Fans | 26433 | 2013-09-10 16:00 | 2013-10-01 16:00 | 21 | 456 | 100 | 81 | -19 | 37464 | 37464 | 30345.84 | 40726.3062 | 0.81 | 0.74512 | TRUE | TRUE | TRUE | 57 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146324 | HCMEB3Z6380 | B3 Z6 :Grills & Diffusers | 26433 | 2013-12-12 16:00 | 2013-12-26 16:00 | 14 | 440 | 100 | 82 | -18 | 17808 | 17808 | 14602.56 | 21013.6916 | 0.82 | 0.69491 | TRUE | TRUE | TRUE | 55 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146325 | HCMEB3Z6405 | B3 Z6 :Mechanical final Fix | 26433 | 2013-12-26 16:00 | 2014-01-09 16:00 | 14 | 440 | 100 | 84 | -16 | 11886 | 11886 | 9984.24 | 14183.9462 | 0.84 | 0.70391 | TRUE | TRUE | TRUE | 55 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146326 | HCMEB3Z6410 | B3 Z6 :All Vertical Piping Works | 26615 | 2012-12-03 08:00 | 2012-12-14 17:00 | 11 | 1471 | 100 | 84 | -16 | 20625 | 20625 | 17325 | 21356.1321 | 0.84 | 0.81124 | TRUE | TRUE | TRUE | 183.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146327 | HCMEB3Z6415 | B3 Z6 :All Horizantal Piping Works | 26615 | 2012-12-17 08:00 | 2013-01-25 17:00 | 39 | 1471 | 100 | 100 | 0 | 39741 | 39741 | 39741 | 46246.9403 | 1 | 0.85932 | TRUE | FALSE | FALSE | 183.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146328 | HCMEB3Z6420 | B3 Z6 :Mechanical Final Fix | 26615 | 2013-06-03 08:00 | 2013-06-28 17:00 | 25 | 1471 | 100 | 80 | -20 | 46075 | 46075 | 36860 | 56614.752 | 0.8 | 0.65107 | TRUE | TRUE | TRUE | 183.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146329 | HCMEB2Z1130 | B2 Z1 :Blocks Start Date for All Parts | 26441 | 2012-12-30 16:00 | 2012-12-30 16:00 | 1 | 408 | 100 | 87 | -13 | 637 | 637 | 554.19 | 611.5633 | 0.87 | 0.90619 | FALSE | TRUE | TRUE | 51 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146330 | HCMEB2Z1140 | B2 Z1 :Tiling Finish Date for All Parts | 26441 | 2013-07-24 16:00 | 2013-07-24 16:00 | 1 | 40 | 100 | 91 | -9 | 1491 | 1491 | 1356.81 | 1504.6936 | 0.91 | 0.90172 | FALSE | FALSE | FALSE | 5 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146331 | HCMEB2Z1150 | B2 Z1 :Plastering Finish Date for All Parts | 26441 | 2013-01-31 12:00 | 2013-01-31 12:00 | 1 | 1763 | 100 | 100 | 0 | 867 | 867 | 867 | 1059.9869 | 1 | 0.81793 | TRUE | FALSE | FALSE | 220.375 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146332 | HCMEB2Z1160 | B2 Z1 :Gypsum Boards Finish Date for All Parts | 26441 | 2013-11-26 16:00 | 2013-11-26 16:00 | 1 | 1200 | 100 | 83 | -17 | 1743 | 1743 | 1446.69 | 1717.3646 | 0.83 | 0.84239 | TRUE | TRUE | TRUE | 150 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146333 | HCMEB2Z1190 | B2 Z1 :Electrical Coduits & Boards F.F for All Systems | 26441 | 2012-12-31 08:00 | 2013-01-15 17:00 | 15 | 1159 | 100 | 92 | -8 | 27900 | 27900 | 25668 | 33913.8594 | 0.92 | 0.75686 | TRUE | FALSE | FALSE | 144.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146334 | HCMEB2Z1200 | B2 Z1 :Electrical Boards Seconed Fix | 26441 | 2013-05-01 16:00 | 2013-05-17 16:00 | 16 | 952 | 100 | 100 | 0 | 27936 | 27936 | 27936 | 34708.1877 | 1 | 0.80488 | TRUE | FALSE | FALSE | 119 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146335 | HCMEB2Z1210 | B2 Z1 :Cable Tray Installation | 26441 | 2013-10-23 16:00 | 2013-11-06 16:00 | 14 | 0 | 100 | 94 | -6 | 12026 | 12026 | 11304.44 | 13405.6743 | 0.94 | 0.84326 | TRUE | FALSE | FALSE | 0 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146336 | HCMEB2Z1220 | B2 Z1 :Electrcial Wiring | 26441 | 2013-07-29 08:00 | 2013-08-23 17:00 | 25 | 15 | 100 | 100 | 0 | 35500 | 35500 | 35500 | 41774.8421 | 1 | 0.84979 | TRUE | FALSE | FALSE | 1.875 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146337 | HCMEB2Z1230 | B2 Z1 :Cable Laying | 26441 | 2013-11-06 16:00 | 2013-11-20 16:00 | 14 | 0 | 100 | 90 | -10 | 11592 | 11592 | 10432.8 | 13328.6929 | 0.9 | 0.78273 | TRUE | FALSE | FALSE | 0 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146338 | HCMEB2Z1240 | B2 Z1 :Electrical Final Fix for All Systems & Boards (Vertical Elements) | 26441 | 2014-01-01 16:00 | 2014-01-15 16:00 | 14 | 728 | 100 | 89 | -11 | 20454 | 20454 | 18204.06 | 23109.2095 | 0.89 | 0.78774 | TRUE | TRUE | TRUE | 91 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146339 | HCMEB2Z1250 | B2 Z1 :Electrical Final Fix for All Systems (Horizantel Elements) | 26441 | 2014-01-15 16:00 | 2014-01-29 16:00 | 14 | 728 | 100 | 82 | -18 | 13468 | 13468 | 11043.76 | 13101.2991 | 0.82 | 0.84295 | TRUE | TRUE | TRUE | 91 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146340 | HCMEB2Z1040 | B2 Z1 :All Vertical Piping Works | 26468 | 2012-12-31 08:00 | 2013-01-11 17:00 | 11 | 351 | 100 | 100 | 0 | 15895 | 15895 | 15895 | 13873.7558 | 1 | 1.1457 | FALSE | FALSE | FALSE | 43.875 | FALSE | 0 | Green | Continue normal monitoring.
146341 | HCMEB2Z1050 | B2 Z1 :All Horizantal Piping Works | 26468 | 2013-01-14 08:00 | 2013-02-22 17:00 | 39 | 351 | 100 | 93 | -7 | 57018 | 57018 | 53026.74 | 56289.3495 | 0.93 | 0.94204 | FALSE | FALSE | FALSE | 43.875 | FALSE | 0 | Green | Continue normal monitoring.
146342 | HCMEB2Z1060 | B2 Z1 :Mechanical Final Fix | 26468 | 2013-07-01 08:00 | 2013-07-26 17:00 | 25 | 351 | 100 | 95 | -5 | 47625 | 47625 | 45243.75 | 53186.3805 | 0.95 | 0.85066 | TRUE | FALSE | FALSE | 43.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146343 | HCMEB2Z1070 | B2 Z1 :Horizontal F.F Piping Work | 26437 | 2012-12-31 08:00 | 2013-01-25 17:00 | 25 | 1391 | 100 | 89 | -11 | 33375 | 33375 | 29703.75 | 29737.5148 | 0.89 | 0.99886 | FALSE | TRUE | TRUE | 173.875 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146344 | HCMEB2Z1080 | B2 Z1 :Fire Hose Cabinets | 26437 | 2013-01-28 08:00 | 2013-02-08 17:00 | 11 | 1391 | 100 | 100 | 0 | 7348 | 7348 | 7348 | 6280.8293 | 1 | 1.1699 | FALSE | FALSE | FALSE | 173.875 | FALSE | 0 | Green | Continue normal monitoring.
146345 | HCMEB2Z1090 | B2 Z1 :Sprinklers Final Fix | 26437 | 2013-12-02 16:00 | 2013-12-16 16:00 | 14 | 264 | 100 | 89 | -11 | 10024 | 10024 | 8921.36 | 9080.5105 | 0.89 | 0.98247 | FALSE | TRUE | TRUE | 33 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146346 | HCMEB2Z1300 | B2 Z1 :Duct Installation& Dusct Accecories Installation, Fan coil Unit | 26438 | 2013-08-02 16:00 | 2013-08-14 16:00 | 12 | 168 | 100 | 91 | -9 | 10524 | 10524 | 9576.84 | 11958.362 | 0.91 | 0.80085 | TRUE | FALSE | FALSE | 21 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146347 | HCMEB2Z1310 | B2 Z1 :Duct Insulation Work | 26438 | 2013-08-14 16:00 | 2013-09-04 16:00 | 21 | 168 | 100 | 100 | 0 | 12978 | 12978 | 12978 | 16081.2667 | 1 | 0.80703 | TRUE | FALSE | FALSE | 21 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146348 | HCMEB2Z1320 | B2 Z1 :Exhaust Fans | 26438 | 2013-09-04 16:00 | 2013-09-25 16:00 | 21 | 168 | 100 | 88 | -12 | 14469 | 14469 | 12732.72 | 17988.2353 | 0.88 | 0.70784 | TRUE | TRUE | TRUE | 21 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146349 | HCMEB2Z1330 | B2 Z1 :Grills & Diffusers | 26438 | 2013-12-31 16:00 | 2014-01-14 16:00 | 14 | 16 | 100 | 80 | -20 | 17724 | 17724 | 14179.2 | 18567.5146 | 0.8 | 0.76366 | TRUE | TRUE | TRUE | 2 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
146350 | HCMEB2Z1340 | B2 Z1 :Mechanical final Fix | 26438 | 2014-01-16 16:00 | 2014-01-30 16:00 | 14 | 0 | 100 | 84 | -16 | 12166 | 12166 | 10219.44 | 14571.716 | 0.84 | 0.70132 | TRUE | TRUE | TRUE | 0 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
146351 | HCMEB2Z1350 | B2 Z1 :All Vertical Piping Works | 26621 | 2012-12-31 08:00 | 2013-01-11 17:00 | 11 | 351 | 100 | 99 | -1 | 7128 | 7128 | 7056.72 | 8159.6396 | 0.99 | 0.86483 | TRUE | FALSE | FALSE | 43.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146352 | HCMEB2Z1360 | B2 Z1 :All Horizantal Piping Works | 26621 | 2013-01-14 08:00 | 2013-02-22 17:00 | 39 | 351 | 100 | 87 | -13 | 44889 | 44889 | 39053.43 | 47152.1281 | 0.87 | 0.82824 | TRUE | TRUE | TRUE | 43.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146353 | HCMEB2Z1370 | B2 Z1 :Mechanical Final Fix | 26621 | 2013-07-01 08:00 | 2013-07-26 17:00 | 25 | 351 | 100 | 90 | -10 | 31725 | 31725 | 28552.5 | 34234.5812 | 0.9 | 0.83403 | TRUE | FALSE | FALSE | 43.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146354 | HCMEB2Z2135 | B2 Z2 :Blocks Start Date for All Parts | 26569 | 2013-02-03 16:00 | 2013-02-03 16:00 | 1 | 1232 | 100 | 91 | -9 | 873 | 873 | 794.43 | 789.9697 | 0.91 | 1.0056 | FALSE | FALSE | FALSE | 154 | FALSE | 0 | Green | Continue normal monitoring.
146355 | HCMEB2Z2145 | B2 Z2 :Tiling Finish Date for All Parts | 26569 | 2013-06-16 14:00 | 2013-06-16 14:00 | 1 | 306 | 100 | 80 | -20 | 1280 | 1280 | 1024 | 1568.0827 | 0.8 | 0.65303 | TRUE | TRUE | TRUE | 38.25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146356 | HCMEB2Z2155 | B2 Z2 :Plastering Finish Date for All Parts | 26569 | 2013-03-05 12:00 | 2013-03-05 12:00 | 1 | 1627 | 100 | 100 | 0 | 659 | 659 | 659 | 652.9187 | 1 | 1.0093 | FALSE | FALSE | FALSE | 203.375 | FALSE | 0 | Green | Continue normal monitoring.
146357 | HCMEB2Z2165 | B2 Z2 :Gypsum Boards Finish Date for All Parts | 26569 | 2013-11-25 16:00 | 2013-11-25 16:00 | 1 | 1208 | 100 | 100 | 0 | 850 | 850 | 850 | 874.1907 | 1 | 0.97233 | FALSE | FALSE | FALSE | 151 | FALSE | 0 | Green | Continue normal monitoring.
146358 | HCMEB2Z2195 | B2 Z2 :Electrical Coduits & Boards F.F for All Systems | 26569 | 2013-02-04 08:00 | 2013-02-19 17:00 | 15 | 1031 | 100 | 99 | -1 | 27165 | 27165 | 26893.35 | 30388.5101 | 0.99 | 0.88498 | TRUE | FALSE | FALSE | 128.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146359 | HCMEB2Z2205 | B2 Z2 :Electrical Boards Seconed Fix | 26569 | 2013-05-01 16:00 | 2013-05-17 16:00 | 16 | 1024 | 100 | 100 | 0 | 28976 | 28976 | 28976 | 28499.6632 | 1 | 1.0167 | FALSE | FALSE | FALSE | 128 | FALSE | 0 | Green | Continue normal monitoring.
146360 | HCMEB2Z2215 | B2 Z2 :Cable Tray Installation | 26569 | 2013-10-23 16:00 | 2013-11-06 16:00 | 14 | 88 | 100 | 100 | 0 | 19474 | 19474 | 19474 | 18533.4772 | 1 | 1.0507 | FALSE | FALSE | FALSE | 11 | FALSE | 0 | Green | Continue normal monitoring.
146361 | HCMEB2Z2225 | B2 Z2 :Electrcial Wiring | 26569 | 2013-06-24 08:00 | 2013-07-19 17:00 | 25 | 215 | 100 | 90 | -10 | 43725 | 43725 | 39352.5 | 48203.3039 | 0.9 | 0.81639 | TRUE | FALSE | FALSE | 26.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146362 | HCMEB2Z2235 | B2 Z2 :Cable Laying | 26569 | 2013-11-06 16:00 | 2013-11-20 16:00 | 14 | 88 | 100 | 84 | -16 | 14308 | 14308 | 12018.72 | 12304.7889 | 0.84 | 0.97675 | FALSE | TRUE | TRUE | 11 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146363 | HCMEB2Z2245 | B2 Z2 :Electrical Final Fix for All Systems & Boards (Vertical Elements) | 26569 | 2014-01-01 16:00 | 2014-01-15 16:00 | 14 | 728 | 100 | 94 | -6 | 14294 | 14294 | 13436.36 | 16270.7179 | 0.94 | 0.8258 | TRUE | FALSE | FALSE | 91 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146364 | HCMEB2Z2255 | B2 Z2 :Electrical Final Fix for All Systems (Horizantel Elements) | 26569 | 2014-01-15 16:00 | 2014-01-29 16:00 | 14 | 728 | 100 | 84 | -16 | 17948 | 17948 | 15076.32 | 18946.0766 | 0.84 | 0.79575 | TRUE | TRUE | TRUE | 91 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146365 | HCMEB2Z2045 | B2 Z2 :All Vertical Piping Works | 26469 | 2012-12-31 08:00 | 2013-01-11 17:00 | 11 | 511 | 100 | 91 | -9 | 8492 | 8492 | 7727.72 | 9275.8243 | 0.91 | 0.8331 | TRUE | FALSE | FALSE | 63.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146366 | HCMEB2Z2055 | B2 Z2 :All Horizantal Piping Works | 26469 | 2013-01-14 08:00 | 2013-02-22 17:00 | 39 | 511 | 100 | 84 | -16 | 55965 | 55965 | 47010.6 | 61715.5192 | 0.84 | 0.76173 | TRUE | TRUE | TRUE | 63.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146367 | HCMEB2Z2065 | B2 Z2 :Mechanical Final Fix | 26469 | 2013-07-01 08:00 | 2013-07-26 17:00 | 25 | 511 | 100 | 96 | -4 | 48125 | 48125 | 46200 | 51051.9655 | 0.96 | 0.90496 | FALSE | FALSE | FALSE | 63.875 | FALSE | 0 | Green | Continue normal monitoring.
146368 | HCMEB2Z2075 | B2 Z2 :Horizontal F.F Piping Work | 26443 | 2013-02-04 08:00 | 2013-03-01 17:00 | 25 | 1271 | 100 | 96 | -4 | 17050 | 17050 | 16368 | 18465.3804 | 0.96 | 0.88642 | TRUE | FALSE | FALSE | 158.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146369 | HCMEB2Z2085 | B2 Z2 :Fire Hose Cabinets | 26443 | 2013-03-04 08:00 | 2013-03-15 17:00 | 11 | 1271 | 100 | 100 | 0 | 10857 | 10857 | 10857 | 12198.0054 | 1 | 0.89006 | TRUE | FALSE | FALSE | 158.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146370 | HCMEB2Z2095 | B2 Z2 :Sprinklers Final Fix | 26443 | 2013-12-02 16:00 | 2013-12-16 16:00 | 14 | 344 | 100 | 91 | -9 | 18830 | 18830 | 17135.3 | 21677.9912 | 0.91 | 0.79045 | TRUE | FALSE | FALSE | 43 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146371 | HCMEB2Z2305 | B2 Z2 :Duct Installation& Dusct Accecories Installation, Fan coil Unit | 26444 | 2013-08-02 16:00 | 2013-08-14 16:00 | 12 | 153 | 100 | 100 | 0 | 7476 | 7476 | 7476 | 8529.9736 | 1 | 0.87644 | TRUE | FALSE | FALSE | 19.125 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146372 | HCMEB2Z2315 | B2 Z2 :Duct Insulation Work | 26444 | 2013-08-14 16:00 | 2013-09-04 16:00 | 21 | 153 | 100 | 100 | 0 | 31164 | 31164 | 31164 | 37329.6909 | 1 | 0.83483 | TRUE | FALSE | FALSE | 19.125 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146373 | HCMEB2Z2325 | B2 Z2 :Exhaust Fans | 26444 | 2013-09-04 16:00 | 2013-09-25 16:00 | 21 | 153 | 100 | 94 | -6 | 27069 | 27069 | 25444.86 | 25059.8677 | 0.94 | 1.0154 | FALSE | FALSE | FALSE | 19.125 | FALSE | 0 | Green | Continue normal monitoring.
146374 | HCMEB2Z2335 | B2 Z2 :Grills & Diffusers | 26444 | 2013-12-26 16:00 | 2014-01-09 16:00 | 14 | 25 | 100 | 94 | -6 | 12782 | 12782 | 12015.08 | 12915.6893 | 0.94 | 0.93027 | FALSE | FALSE | FALSE | 3.125 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146375 | HCMEB2Z2345 | B2 Z2 :Mechanical final Fix | 26444 | 2014-01-09 16:00 | 2014-01-23 16:00 | 14 | 25 | 100 | 85 | -15 | 23730 | 23730 | 20170.5 | 29166.9803 | 0.85 | 0.69155 | TRUE | TRUE | TRUE | 3.125 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
146376 | HCMEB2Z2355 | B2 Z2 :All Vertical Piping Works | 26627 | 2012-12-31 08:00 | 2013-01-11 17:00 | 11 | 511 | 100 | 91 | -9 | 19921 | 19921 | 18128.11 | 20093.0423 | 0.91 | 0.90221 | FALSE | FALSE | FALSE | 63.875 | FALSE | 0 | Green | Continue normal monitoring.
146377 | HCMEB2Z2365 | B2 Z2 :All Horizantal Piping Works | 26627 | 2013-01-14 08:00 | 2013-02-22 17:00 | 39 | 511 | 100 | 100 | 0 | 76362 | 76362 | 76362 | 68721.8315 | 1 | 1.1112 | FALSE | FALSE | FALSE | 63.875 | FALSE | 0 | Green | Continue normal monitoring.
146378 | HCMEB2Z2375 | B2 Z2 :Mechanical Final Fix | 26627 | 2013-07-01 08:00 | 2013-07-26 17:00 | 25 | 511 | 100 | 100 | 0 | 29625 | 29625 | 29625 | 31407.7747 | 1 | 0.94324 | FALSE | FALSE | FALSE | 63.875 | FALSE | 0 | Green | Continue normal monitoring.
146379 | HCMEB2Z3140 | B2 Z3 :Blocks Start Date for All Parts | 26404 | 2013-01-20 16:00 | 2013-01-20 16:00 | 1 | 1448 | 100 | 99 | -1 | 612 | 612 | 605.88 | 547.0034 | 0.99 | 1.1076 | FALSE | FALSE | FALSE | 181 | FALSE | 0 | Green | Continue normal monitoring.
146380 | HCMEB2Z3150 | B2 Z3 :Tiling Finish Date for All Parts | 26404 | 2013-08-05 16:00 | 2013-08-05 16:00 | 1 | 1161 | 100 | 97 | -3 | 1387 | 1387 | 1345.39 | 1291.493 | 0.97 | 1.0417 | FALSE | FALSE | FALSE | 145.125 | FALSE | 0 | Green | Continue normal monitoring.
146381 | HCMEB2Z3160 | B2 Z3 :Plastering Finish Date for All Parts | 26404 | 2013-06-01 10:00 | 2013-06-01 10:00 | 1 | 1141 | 100 | 93 | -7 | 621 | 621 | 577.53 | 775.8324 | 0.93 | 0.7444 | TRUE | FALSE | FALSE | 142.625 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146382 | HCMEB2Z3170 | B2 Z3 :Gypsum Boards Finish Date for All Parts | 26404 | 2013-11-25 16:00 | 2013-11-25 16:00 | 1 | 1208 | 100 | 81 | -19 | 1745 | 1745 | 1413.45 | 1861.1211 | 0.81 | 0.75946 | TRUE | TRUE | TRUE | 151 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146383 | HCMEB2Z3200 | B2 Z3 :Electrical Coduits & Boards F.F for All Systems | 26404 | 2013-01-21 08:00 | 2013-02-05 17:00 | 15 | 1207 | 100 | 88 | -12 | 8070 | 8070 | 7101.6 | 7776.4405 | 0.88 | 0.91322 | FALSE | TRUE | TRUE | 150.875 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146384 | HCMEB2Z3210 | B2 Z3 :Electrical Boards Seconed Fix | 26404 | 2013-06-03 08:00 | 2013-06-18 17:00 | 15 | 943 | 100 | 100 | 0 | 14940 | 14940 | 14940 | 18643.7751 | 1 | 0.80134 | TRUE | FALSE | FALSE | 117.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146385 | HCMEB2Z3220 | B2 Z3 :Cable Tray Installation | 26404 | 2013-10-23 16:00 | 2013-11-06 16:00 | 14 | 168 | 100 | 84 | -16 | 17906 | 17906 | 15041.04 | 22142.9816 | 0.84 | 0.67927 | TRUE | TRUE | TRUE | 21 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146386 | HCMEB2Z3230 | B2 Z3 :Electrcial Wiring | 26404 | 2013-12-04 16:00 | 2013-12-16 16:00 | 12 | 296 | 100 | 99 | -1 | 21072 | 21072 | 20861.28 | 21626.1012 | 0.99 | 0.96463 | FALSE | FALSE | FALSE | 37 | FALSE | 0 | Green | Continue normal monitoring.
146387 | HCMEB2Z3240 | B2 Z3 :Cable Laying | 26404 | 2013-11-06 16:00 | 2013-11-20 16:00 | 14 | 168 | 100 | 100 | 0 | 20188 | 20188 | 20188 | 19262.6072 | 1 | 1.048 | FALSE | FALSE | FALSE | 21 | FALSE | 0 | Green | Continue normal monitoring.
146388 | HCMEB2Z3250 | B2 Z3 :Electrical Final Fix for All Systems & Boards (Vertical Elements) | 26404 | 2014-01-15 16:00 | 2014-01-29 16:00 | 14 | 648 | 100 | 100 | 0 | 9072 | 9072 | 9072 | 10753.5846 | 1 | 0.84363 | TRUE | FALSE | FALSE | 81 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146389 | HCMEB2Z3260 | B2 Z3 :Electrical Final Fix for All Systems (Horizantel Elements) | 26404 | 2014-01-29 16:00 | 2014-02-12 16:00 | 14 | 648 | 100 | 80 | -20 | 26880 | 26880 | 21504 | 30542.3539 | 0.8 | 0.70407 | TRUE | TRUE | TRUE | 81 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146390 | HCMEB2Z3050 | B2 Z3 :All Vertical Piping Works | 26475 | 2012-12-31 08:00 | 2013-01-11 17:00 | 11 | 511 | 100 | 100 | 0 | 16731 | 16731 | 16731 | 18818.6369 | 1 | 0.88907 | TRUE | FALSE | FALSE | 63.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146391 | HCMEB2Z3060 | B2 Z3 :All Horizantal Piping Works | 26475 | 2013-01-14 08:00 | 2013-02-22 17:00 | 39 | 511 | 100 | 82 | -18 | 45240 | 45240 | 37096.8 | 54615.7863 | 0.82 | 0.67923 | TRUE | TRUE | TRUE | 63.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146392 | HCMEB2Z3070 | B2 Z3 :Mechanical Final Fix | 26475 | 2013-07-01 08:00 | 2013-07-26 17:00 | 25 | 511 | 100 | 85 | -15 | 20025 | 20025 | 17021.25 | 22543.4812 | 0.85 | 0.75504 | TRUE | TRUE | TRUE | 63.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146393 | HCMEB2Z3080 | B2 Z3 :Horizontal F.F Piping Work | 26405 | 2013-01-21 08:00 | 2013-02-15 17:00 | 25 | 1351 | 100 | 84 | -16 | 47075 | 47075 | 39543 | 45357.6653 | 0.84 | 0.8718 | TRUE | TRUE | TRUE | 168.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146394 | HCMEB2Z3090 | B2 Z3 :Fire Hose Cabinets | 26405 | 2013-02-18 08:00 | 2013-03-01 17:00 | 11 | 1351 | 100 | 100 | 0 | 8107 | 8107 | 8107 | 9141.0095 | 1 | 0.88688 | TRUE | FALSE | FALSE | 168.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146395 | HCMEB2Z3100 | B2 Z3 :Sprinklers Final Fix | 26405 | 2013-12-02 16:00 | 2013-12-16 16:00 | 14 | 344 | 100 | 100 | 0 | 16044 | 16044 | 16044 | 15599.9888 | 1 | 1.0285 | FALSE | FALSE | FALSE | 43 | FALSE | 0 | Green | Continue normal monitoring.
146396 | HCMEB2Z3310 | B2 Z3 :Duct Installation& Dusct Accecories Installation, Fan coil Unit | 26409 | 2013-08-08 16:00 | 2013-08-22 16:00 | 14 | 200 | 100 | 84 | -16 | 16268 | 16268 | 13665.12 | 18768.3199 | 0.84 | 0.7281 | TRUE | TRUE | TRUE | 25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146397 | HCMEB2Z3320 | B2 Z3 :Duct Insulation Work | 26409 | 2013-08-22 16:00 | 2013-09-12 16:00 | 21 | 200 | 100 | 80 | -20 | 15435 | 15435 | 12348 | 16946.0733 | 0.8 | 0.72866 | TRUE | TRUE | TRUE | 25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146398 | HCMEB2Z3330 | B2 Z3 :Exhaust Fans | 26409 | 2013-09-12 16:00 | 2013-10-03 16:00 | 21 | 200 | 100 | 96 | -4 | 14742 | 14742 | 14152.32 | 12987.1804 | 0.96 | 1.0897 | FALSE | FALSE | FALSE | 25 | FALSE | 0 | Green | Continue normal monitoring.
146399 | HCMEB2Z3340 | B2 Z3 :Grills & Diffusers | 26409 | 2013-12-26 16:00 | 2014-01-09 16:00 | 14 | 120 | 100 | 98 | -2 | 10570 | 10570 | 10358.6 | 11152.7679 | 0.98 | 0.92879 | FALSE | FALSE | FALSE | 15 | FALSE | 0 | Green | Continue normal monitoring.
146400 | HCMEB2Z3350 | B2 Z3 :Mechanical final Fix | 26409 | 2014-01-09 16:00 | 2014-01-23 16:00 | 14 | 120 | 100 | 93 | -7 | 15358 | 15358 | 14282.94 | 15163.2665 | 0.93 | 0.94194 | FALSE | FALSE | FALSE | 15 | FALSE | 0 | Green | Continue normal monitoring.
146401 | HCMEB2Z3360 | B2 Z3 :All Vertical Piping Works | 26633 | 2012-12-31 08:00 | 2013-01-11 17:00 | 11 | 511 | 100 | 91 | -9 | 12771 | 12771 | 11621.61 | 12533.8202 | 0.91 | 0.92722 | FALSE | FALSE | FALSE | 63.875 | FALSE | 0 | Green | Continue normal monitoring.
146402 | HCMEB2Z3370 | B2 Z3 :All Horizantal Piping Works | 26633 | 2013-01-14 08:00 | 2013-02-22 17:00 | 39 | 511 | 100 | 89 | -11 | 28626 | 28626 | 25477.14 | 31228.1756 | 0.89 | 0.81584 | TRUE | TRUE | TRUE | 63.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146403 | HCMEB2Z3380 | B2 Z3 :Mechanical Final Fix | 26633 | 2013-07-01 08:00 | 2013-07-26 17:00 | 25 | 511 | 100 | 99 | -1 | 46700 | 46700 | 46233 | 45716.0277 | 0.99 | 1.0113 | FALSE | FALSE | FALSE | 63.875 | FALSE | 0 | Green | Continue normal monitoring.
146404 | HCMEB2Z4145 | B2 Z4 :Blocks Start Date for All Parts | 26416 | 2013-02-05 16:00 | 2013-02-05 16:00 | 1 | 1680 | 100 | 100 | 0 | 1033 | 1033 | 1033 | 1199.0625 | 1 | 0.86151 | TRUE | FALSE | FALSE | 210 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146405 | HCMEB2Z4155 | B2 Z4 :Tiling Finish Date for All Parts | 26416 | 2013-07-21 10:00 | 2013-07-21 10:00 | 1 | 837 | 100 | 97 | -3 | 1359 | 1359 | 1318.23 | 1193.6322 | 0.97 | 1.1044 | FALSE | FALSE | FALSE | 104.625 | FALSE | 0 | Green | Continue normal monitoring.
146406 | HCMEB2Z4165 | B2 Z4 :Plastering Finish Date for All Parts | 26416 | 2013-05-02 16:00 | 2013-05-02 16:00 | 1 | 1616 | 100 | 100 | 0 | 1989 | 1989 | 1989 | 2216.0549 | 1 | 0.89754 | TRUE | FALSE | FALSE | 202 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146407 | HCMEB2Z4175 | B2 Z4 :Gypsum Boards Finish Date for All Parts | 26416 | 2013-11-25 16:00 | 2013-11-25 16:00 | 1 | 1208 | 100 | 100 | 0 | 1269 | 1269 | 1269 | 1489.3973 | 1 | 0.85202 | TRUE | FALSE | FALSE | 151 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146408 | HCMEB2Z4205 | B2 Z4 :Electrical Coduits & Boards F.F for All Systems | 26416 | 2013-02-05 16:00 | 2013-02-21 16:00 | 16 | 1400 | 100 | 90 | -10 | 16640 | 16640 | 14976 | 18622.3677 | 0.9 | 0.80419 | TRUE | FALSE | FALSE | 175 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146409 | HCMEB2Z4215 | B2 Z4 :Electrical Boards Seconed Fix | 26416 | 2013-05-02 16:00 | 2013-05-20 16:00 | 18 | 1400 | 100 | 100 | 0 | 12816 | 12816 | 12816 | 13442.5957 | 1 | 0.95339 | FALSE | FALSE | FALSE | 175 | FALSE | 0 | Green | Continue normal monitoring.
146410 | HCMEB2Z4225 | B2 Z4 :Cable Tray Installation | 26416 | 2013-10-23 16:00 | 2013-11-06 16:00 | 14 | 360 | 100 | 81 | -19 | 13468 | 13468 | 10909.08 | 16567.2939 | 0.81 | 0.65847 | TRUE | TRUE | TRUE | 45 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146411 | HCMEB2Z4235 | B2 Z4 :Electrcial Wiring | 26416 | 2013-07-22 08:00 | 2013-08-16 17:00 | 25 | 695 | 100 | 100 | 0 | 23375 | 23375 | 23375 | 22673.1749 | 1 | 1.031 | FALSE | FALSE | FALSE | 86.875 | FALSE | 0 | Green | Continue normal monitoring.
146412 | HCMEB2Z4245 | B2 Z4 :Cable Laying | 26416 | 2013-11-06 16:00 | 2013-11-20 16:00 | 14 | 360 | 100 | 97 | -3 | 10948 | 10948 | 10619.56 | 9389.74 | 0.97 | 1.131 | FALSE | FALSE | FALSE | 45 | FALSE | 0 | Green | Continue normal monitoring.
146413 | HCMEB2Z4255 | B2 Z4 :Electrical Final Fix for All Systems & Boards (Vertical Elements) | 26416 | 2014-01-01 16:00 | 2014-01-15 16:00 | 14 | 728 | 100 | 100 | 0 | 27804 | 27804 | 27804 | 28437.813 | 1 | 0.97771 | FALSE | FALSE | FALSE | 91 | FALSE | 0 | Green | Continue normal monitoring.
146414 | HCMEB2Z4265 | B2 Z4 :Electrical Final Fix for All Systems (Horizantel Elements) | 26416 | 2014-01-15 16:00 | 2014-01-29 16:00 | 14 | 728 | 100 | 100 | 0 | 27020 | 27020 | 27020 | 23323.793 | 1 | 1.1585 | FALSE | FALSE | FALSE | 91 | FALSE | 0 | Green | Continue normal monitoring.
146415 | HCMEB2Z4055 | B2 Z4 :All Vertical Piping Works | 26481 | 2012-12-31 08:00 | 2013-01-11 17:00 | 11 | 1056 | 100 | 86 | -14 | 6457 | 6457 | 5553.02 | 7952.2778 | 0.86 | 0.69829 | TRUE | TRUE | TRUE | 132 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146416 | HCMEB2Z4065 | B2 Z4 :All Horizantal Piping Works | 26481 | 2013-01-14 08:00 | 2013-02-22 17:00 | 39 | 1151 | 100 | 100 | 0 | 61113 | 61113 | 61113 | 57077.5386 | 1 | 1.0707 | FALSE | FALSE | FALSE | 143.875 | FALSE | 0 | Green | Continue normal monitoring.
146417 | HCMEB2Z4075 | B2 Z4 :Mechanical Final Fix | 26481 | 2013-07-01 08:00 | 2013-07-26 17:00 | 25 | 1151 | 100 | 100 | 0 | 24000 | 24000 | 24000 | 27973.6994 | 1 | 0.85795 | TRUE | FALSE | FALSE | 143.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146418 | HCMEB2Z4085 | B2 Z4 :Horizontal F.F Piping Work | 26417 | 2013-02-05 16:00 | 2013-03-05 16:00 | 28 | 1576 | 100 | 94 | -6 | 21756 | 21756 | 20450.64 | 25233.2361 | 0.94 | 0.81046 | TRUE | FALSE | FALSE | 197 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146419 | HCMEB2Z4095 | B2 Z4 :Fire Hose Cabinets | 26417 | 2013-03-05 16:00 | 2013-03-19 16:00 | 14 | 1576 | 100 | 90 | -10 | 12880 | 12880 | 11592 | 12069.7393 | 0.9 | 0.96042 | FALSE | FALSE | FALSE | 197 | FALSE | 0 | Green | Continue normal monitoring.
146420 | HCMEB2Z4105 | B2 Z4 :Sprinklers Final Fix | 26417 | 2013-12-02 16:00 | 2013-12-16 16:00 | 14 | 664 | 100 | 97 | -3 | 26264 | 26264 | 25476.08 | 28850.7574 | 0.97 | 0.88303 | TRUE | FALSE | FALSE | 83 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146421 | HCMEB2Z4315 | B2 Z4 :Duct Installation& Dusct Accecories Installation, Fan coil Unit | 26418 | 2013-08-20 16:00 | 2013-09-09 16:00 | 20 | 296 | 100 | 100 | 0 | 23900 | 23900 | 23900 | 20774.6349 | 1 | 1.1504 | FALSE | FALSE | FALSE | 37 | FALSE | 0 | Green | Continue normal monitoring.
146422 | HCMEB2Z4325 | B2 Z4 :Duct Insulation Work | 26418 | 2013-09-09 16:00 | 2013-09-30 16:00 | 21 | 424 | 100 | 91 | -9 | 21294 | 21294 | 19377.54 | 22218.7949 | 0.91 | 0.87212 | TRUE | FALSE | FALSE | 53 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146423 | HCMEB2Z4335 | B2 Z4 :Exhaust Fans | 26418 | 2013-09-30 16:00 | 2013-10-21 16:00 | 21 | 424 | 100 | 85 | -15 | 25242 | 25242 | 21455.7 | 21603.5891 | 0.85 | 0.99315 | FALSE | TRUE | TRUE | 53 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146424 | HCMEB2Z4345 | B2 Z4 :Grills & Diffusers | 26418 | 2013-12-30 16:00 | 2014-01-13 16:00 | 14 | 424 | 100 | 99 | -1 | 7252 | 7252 | 7179.48 | 8836.2542 | 0.99 | 0.8125 | TRUE | FALSE | FALSE | 53 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146425 | HCMEB2Z4355 | B2 Z4 :Mechanical final Fix | 26418 | 2014-01-13 16:00 | 2014-01-27 16:00 | 14 | 424 | 100 | 100 | 0 | 7308 | 7308 | 7308 | 9065.0947 | 1 | 0.80617 | TRUE | FALSE | FALSE | 53 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146426 | HCMEB2Z4365 | B2 Z4 :All Vertical Piping Works | 26635 | 2012-12-31 08:00 | 2013-01-11 17:00 | 11 | 1151 | 100 | 100 | 0 | 10032 | 10032 | 10032 | 9419.1763 | 1 | 1.0651 | FALSE | FALSE | FALSE | 143.875 | FALSE | 0 | Green | Continue normal monitoring.
146427 | HCMEB2Z4375 | B2 Z4 :All Horizantal Piping Works | 26635 | 2013-01-14 08:00 | 2013-02-22 17:00 | 39 | 1151 | 100 | 92 | -8 | 60567 | 60567 | 55721.64 | 56523.6933 | 0.92 | 0.98581 | FALSE | FALSE | FALSE | 143.875 | FALSE | 0 | Green | Continue normal monitoring.
146428 | HCMEB2Z4385 | B2 Z4 :Mechanical Final Fix | 26635 | 2013-07-01 08:00 | 2013-07-26 17:00 | 25 | 1151 | 100 | 99 | -1 | 15175 | 15175 | 15023.25 | 17473.8315 | 0.99 | 0.85976 | TRUE | FALSE | FALSE | 143.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146429 | HCMEB2Z5150 | B2 Z5 :Blocks Start Date for All Parts | 26422 | 2013-01-26 16:00 | 2013-01-26 16:00 | 1 | 1752 | 100 | 95 | -5 | 1890 | 1890 | 1795.5 | 1798.0548 | 0.95 | 0.99858 | FALSE | FALSE | FALSE | 219 | FALSE | 0 | Green | Continue normal monitoring.
146430 | HCMEB2Z5160 | B2 Z5 :Tiling Finish Date for All Parts | 26422 | 2013-09-23 12:00 | 2013-09-23 12:00 | 1 | 619 | 100 | 97 | -3 | 1804 | 1804 | 1749.88 | 2179.2872 | 0.97 | 0.80296 | TRUE | FALSE | FALSE | 77.375 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146431 | HCMEB2Z5170 | B2 Z5 :Plastering Finish Date for All Parts | 26422 | 2013-07-11 16:00 | 2013-07-11 16:00 | 1 | 1136 | 100 | 89 | -11 | 1651 | 1651 | 1469.39 | 1782.3728 | 0.89 | 0.8244 | TRUE | TRUE | TRUE | 142 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146432 | HCMEB2Z5180 | B2 Z5 :Gypsum Boards Finish Date for All Parts | 26422 | 2013-10-14 12:00 | 2013-10-14 12:00 | 1 | 1499 | 100 | 100 | 0 | 1752 | 1752 | 1752 | 1735.025 | 1 | 1.0098 | FALSE | FALSE | FALSE | 187.375 | FALSE | 0 | Green | Continue normal monitoring.
146433 | HCMEB2Z5210 | B2 Z5 :Electrical Coduits & Boards F.F for All Systems | 26422 | 2013-01-28 08:00 | 2013-02-12 17:00 | 15 | 1455 | 100 | 100 | 0 | 24510 | 24510 | 24510 | 28997.2295 | 1 | 0.84525 | TRUE | FALSE | FALSE | 181.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146434 | HCMEB2Z5220 | B2 Z5 :Electrical Boards Seconed Fix | 26422 | 2013-07-11 16:00 | 2013-07-29 16:00 | 18 | 1000 | 100 | 87 | -13 | 11430 | 11430 | 9944.1 | 11971.3554 | 0.87 | 0.83066 | TRUE | TRUE | TRUE | 125 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146435 | HCMEB2Z5230 | B2 Z5 :Cable Tray Installation | 26422 | 2013-10-23 16:00 | 2013-11-06 16:00 | 14 | 360 | 100 | 97 | -3 | 12054 | 12054 | 11692.38 | 14641.4293 | 0.97 | 0.79858 | TRUE | FALSE | FALSE | 45 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146436 | HCMEB2Z5240 | B2 Z5 :Electrcial Wiring | 26422 | 2013-09-23 13:00 | 2013-10-21 12:00 | 27 | 523 | 100 | 100 | 0 | 46143 | 46143 | 46143 | 56350.0944 | 1 | 0.81886 | TRUE | FALSE | FALSE | 65.375 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146437 | HCMEB2Z5250 | B2 Z5 :Cable Laying | 26422 | 2013-11-06 16:00 | 2013-11-20 16:00 | 14 | 360 | 100 | 80 | -20 | 8792 | 8792 | 7033.6 | 8054.9496 | 0.8 | 0.8732 | TRUE | TRUE | TRUE | 45 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146438 | HCMEB2Z5260 | B2 Z5 :Electrical Final Fix for All Systems & Boards (Vertical Elements) | 26422 | 2014-01-01 16:00 | 2014-01-15 16:00 | 14 | 728 | 100 | 100 | 0 | 24976 | 24976 | 24976 | 21252.8118 | 1 | 1.1752 | FALSE | FALSE | FALSE | 91 | FALSE | 0 | Green | Continue normal monitoring.
146439 | HCMEB2Z5270 | B2 Z5 :Electrical Final Fix for All Systems (Horizantel Elements) | 26422 | 2014-01-15 16:00 | 2014-01-29 16:00 | 14 | 728 | 100 | 87 | -13 | 14196 | 14196 | 12350.52 | 17653.7535 | 0.87 | 0.6996 | TRUE | TRUE | TRUE | 91 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146440 | HCMEB2Z5060 | B2 Z5 :All Vertical Piping Works | 26487 | 2012-12-31 08:00 | 2013-01-11 17:00 | 11 | 1056 | 100 | 100 | 0 | 10428 | 10428 | 10428 | 12643.4809 | 1 | 0.82477 | TRUE | FALSE | FALSE | 132 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146441 | HCMEB2Z5070 | B2 Z5 :All Horizantal Piping Works | 26487 | 2013-01-14 08:00 | 2013-02-22 17:00 | 39 | 1056 | 100 | 85 | -15 | 63453 | 63453 | 53935.05 | 55342.3166 | 0.85 | 0.97457 | FALSE | TRUE | TRUE | 132 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146442 | HCMEB2Z5080 | B2 Z5 :Mechanical Final Fix | 26487 | 2013-07-01 08:00 | 2013-07-26 17:00 | 25 | 1056 | 100 | 84 | -16 | 43675 | 43675 | 36687 | 51676.8586 | 0.84 | 0.70993 | TRUE | TRUE | TRUE | 132 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146443 | HCMEB2Z5090 | B2 Z5 :Horizontal F.F Piping Work | 26586 | 2013-01-28 08:00 | 2013-02-22 17:00 | 25 | 1631 | 100 | 94 | -6 | 34325 | 34325 | 32265.5 | 35461.9117 | 0.94 | 0.90986 | FALSE | FALSE | FALSE | 203.875 | FALSE | 0 | Green | Continue normal monitoring.
146444 | HCMEB2Z5100 | B2 Z5 :Fire Hose Cabinets | 26586 | 2013-02-25 08:00 | 2013-03-08 17:00 | 11 | 1631 | 100 | 100 | 0 | 10692 | 10692 | 10692 | 10195.727 | 1 | 1.0487 | FALSE | FALSE | FALSE | 203.875 | FALSE | 0 | Green | Continue normal monitoring.
146445 | HCMEB2Z5110 | B2 Z5 :Sprinklers Final Fix | 26586 | 2013-12-02 16:00 | 2013-12-16 16:00 | 14 | 664 | 100 | 94 | -6 | 21462 | 21462 | 20174.28 | 25786.5632 | 0.94 | 0.78236 | TRUE | FALSE | FALSE | 83 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146446 | HCMEB2Z5320 | B2 Z5 :Duct Installation& Dusct Accecories Installation, Fan coil Unit | 26424 | 2013-08-20 16:00 | 2013-09-09 16:00 | 20 | 296 | 100 | 81 | -19 | 38560 | 38560 | 31233.6 | 35809.3954 | 0.81 | 0.87222 | TRUE | TRUE | TRUE | 37 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146447 | HCMEB2Z5330 | B2 Z5 :Duct Insulation Work | 26424 | 2013-09-09 16:00 | 2013-09-30 16:00 | 21 | 424 | 100 | 80 | -20 | 16821 | 16821 | 13456.8 | 20671.6633 | 0.8 | 0.65098 | TRUE | TRUE | TRUE | 53 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146448 | HCMEB2Z5340 | B2 Z5 :Exhaust Fans | 26424 | 2013-09-30 16:00 | 2013-10-21 16:00 | 21 | 424 | 100 | 100 | 0 | 15330 | 15330 | 15330 | 14291.371 | 1 | 1.0727 | FALSE | FALSE | FALSE | 53 | FALSE | 0 | Green | Continue normal monitoring.
146449 | HCMEB2Z5350 | B2 Z5 :Grills & Diffusers | 26424 | 2013-12-30 16:00 | 2014-01-13 16:00 | 14 | 424 | 100 | 100 | 0 | 19908 | 19908 | 19908 | 21808.682 | 1 | 0.91285 | FALSE | FALSE | FALSE | 53 | FALSE | 0 | Green | Continue normal monitoring.
146450 | HCMEB2Z5360 | B2 Z5 :Mechanical final Fix | 26424 | 2014-01-13 16:00 | 2014-01-27 16:00 | 14 | 424 | 100 | 100 | 0 | 22246 | 22246 | 22246 | 20894.2114 | 1 | 1.0647 | FALSE | FALSE | FALSE | 53 | FALSE | 0 | Green | Continue normal monitoring.
146451 | HCMEB2Z5370 | B2 Z5 :All Vertical Piping Works | 26425 | 2012-12-31 08:00 | 2013-01-11 17:00 | 11 | 1791 | 100 | 90 | -10 | 15796 | 15796 | 14216.4 | 16874.3529 | 0.9 | 0.84249 | TRUE | FALSE | FALSE | 223.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146452 | HCMEB2Z5380 | B2 Z5 :All Horizantal Piping Works | 26425 | 2013-01-14 08:00 | 2013-02-22 17:00 | 39 | 1791 | 100 | 89 | -11 | 23829 | 23829 | 21207.81 | 26774.0273 | 0.89 | 0.7921 | TRUE | TRUE | TRUE | 223.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146453 | HCMEB2Z5390 | B2 Z5 :Mechanical Final Fix | 26425 | 2013-07-01 08:00 | 2013-07-26 17:00 | 25 | 1791 | 100 | 100 | 0 | 38400 | 38400 | 38400 | 35561.901 | 1 | 1.0798 | FALSE | FALSE | FALSE | 223.875 | FALSE | 0 | Green | Continue normal monitoring.
146454 | HCMEB2Z6155 | B2 Z6 :Blocks Start Date for All Parts | 26591 | 2012-12-30 16:00 | 2012-12-30 16:00 | 1 | 1928 | 100 | 97 | -3 | 1916 | 1916 | 1858.52 | 2027.8069 | 0.97 | 0.91652 | FALSE | FALSE | FALSE | 241 | FALSE | 0 | Green | Continue normal monitoring.
146455 | HCMEB2Z6165 | B2 Z6 :Tiling Finish Date for All Parts | 26591 | 2013-10-01 10:00 | 2013-10-01 10:00 | 1 | 565 | 100 | 97 | -3 | 999 | 999 | 969.03 | 1036.5863 | 0.97 | 0.93483 | FALSE | FALSE | FALSE | 70.625 | FALSE | 0 | Green | Continue normal monitoring.
146456 | HCMEB2Z6175 | B2 Z6 :Plastering Finish Date for All Parts | 26591 | 2013-07-11 16:00 | 2013-07-11 16:00 | 1 | 1136 | 100 | 96 | -4 | 1431 | 1431 | 1373.76 | 1257.0118 | 0.96 | 1.0929 | FALSE | FALSE | FALSE | 142 | FALSE | 0 | Green | Continue normal monitoring.
146457 | HCMEB2Z6185 | B2 Z6 :Gypsum Boards Finish Date for All Parts | 26591 | 2013-10-27 10:00 | 2013-10-27 10:00 | 1 | 1413 | 100 | 100 | 0 | 1097 | 1097 | 1097 | 1291.5235 | 1 | 0.84938 | TRUE | FALSE | FALSE | 176.625 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146458 | HCMEB2Z6215 | B2 Z6 :Electrical Coduits & Boards F.F for All Systems | 26591 | 2012-12-31 08:00 | 2013-01-15 17:00 | 15 | 1615 | 100 | 87 | -13 | 10995 | 10995 | 9565.65 | 10822.0812 | 0.87 | 0.8839 | TRUE | TRUE | TRUE | 201.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146459 | HCMEB2Z6225 | B2 Z6 :Electrical Boards Seconed Fix | 26591 | 2013-07-11 16:00 | 2013-07-29 16:00 | 18 | 1000 | 100 | 94 | -6 | 19818 | 19818 | 18628.92 | 21400.128 | 0.94 | 0.87051 | TRUE | FALSE | FALSE | 125 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146460 | HCMEB2Z6235 | B2 Z6 :Cable Tray Installation | 26591 | 2013-10-23 16:00 | 2013-11-06 16:00 | 14 | 360 | 100 | 87 | -13 | 11382 | 11382 | 9902.34 | 12018.4097 | 0.87 | 0.82393 | TRUE | TRUE | TRUE | 45 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146461 | HCMEB2Z6245 | B2 Z6 :Electrcial Wiring | 26591 | 2013-10-01 10:00 | 2013-10-29 10:00 | 28 | 477 | 100 | 96 | -4 | 29820 | 29820 | 28627.2 | 31469.1713 | 0.96 | 0.90969 | FALSE | FALSE | FALSE | 59.625 | FALSE | 0 | Green | Continue normal monitoring.
146462 | HCMEB2Z6255 | B2 Z6 :Cable Laying | 26591 | 2013-11-06 16:00 | 2013-11-20 16:00 | 14 | 360 | 100 | 91 | -9 | 21490 | 21490 | 19555.9 | 19188.1837 | 0.91 | 1.0192 | FALSE | FALSE | FALSE | 45 | FALSE | 0 | Green | Continue normal monitoring.
146463 | HCMEB2Z6265 | B2 Z6 :Electrical Final Fix for All Systems & Boards (Vertical Elements) | 26591 | 2014-01-01 16:00 | 2014-01-15 16:00 | 14 | 728 | 100 | 100 | 0 | 9912 | 9912 | 9912 | 10104.2215 | 1 | 0.98098 | FALSE | FALSE | FALSE | 91 | FALSE | 0 | Green | Continue normal monitoring.
146464 | HCMEB2Z6275 | B2 Z6 :Electrical Final Fix for All Systems (Horizantel Elements) | 26591 | 2014-01-15 16:00 | 2014-01-29 16:00 | 14 | 728 | 100 | 87 | -13 | 21518 | 21518 | 18720.66 | 22183.9112 | 0.87 | 0.84388 | TRUE | TRUE | TRUE | 91 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146465 | HCMEB2Z6065 | B2 Z6 :All Vertical Piping Works | 26493 | 2012-12-31 08:00 | 2013-01-11 17:00 | 11 | 1391 | 100 | 100 | 0 | 21351 | 21351 | 21351 | 24413.9533 | 1 | 0.87454 | TRUE | FALSE | FALSE | 173.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146466 | HCMEB2Z6075 | B2 Z6 :All Horizantal Piping Works | 26493 | 2013-01-14 08:00 | 2013-02-22 17:00 | 39 | 1391 | 100 | 93 | -7 | 76440 | 76440 | 71089.2 | 90658.4158 | 0.93 | 0.78414 | TRUE | FALSE | FALSE | 173.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146467 | HCMEB2Z6085 | B2 Z6 :Mechanical Final Fix | 26493 | 2013-07-01 08:00 | 2013-07-26 17:00 | 25 | 1391 | 100 | 83 | -17 | 47500 | 47500 | 39425 | 50729.6633 | 0.83 | 0.77716 | TRUE | TRUE | TRUE | 173.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146468 | HCMEB2Z6105 | B2 Z6 :Horizontal F.F Piping Work | 26592 | 2012-12-31 08:00 | 2013-01-25 17:00 | 25 | 1791 | 100 | 80 | -20 | 38575 | 38575 | 30860 | 34127.811 | 0.8 | 0.90425 | FALSE | TRUE | TRUE | 223.875 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146469 | HCMEB2Z6115 | B2 Z6 :Fire Hose Cabinets | 26592 | 2013-01-28 08:00 | 2013-02-08 17:00 | 11 | 1791 | 100 | 80 | -20 | 11946 | 11946 | 9556.8 | 11285.8615 | 0.8 | 0.84679 | TRUE | TRUE | TRUE | 223.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146470 | HCMEB2Z6335 | B2 Z6 :Sprinklers Final Fix | 26592 | 2013-12-02 16:00 | 2013-12-16 16:00 | 14 | 664 | 100 | 98 | -2 | 21196 | 21196 | 20772.08 | 19414.9767 | 0.98 | 1.0699 | FALSE | FALSE | FALSE | 83 | FALSE | 0 | Green | Continue normal monitoring.
146471 | HCMEB2Z6345 | B2 Z6 :Duct Installation& Dusct Accecories Installation, Fan coil Unit | 26429 | 2013-08-20 16:00 | 2013-09-09 16:00 | 20 | 296 | 100 | 100 | 0 | 31860 | 31860 | 31860 | 28669.0944 | 1 | 1.1113 | FALSE | FALSE | FALSE | 37 | FALSE | 0 | Green | Continue normal monitoring.
146472 | HCMEB2Z6355 | B2 Z6 :Duct Insulation Work | 26429 | 2013-09-09 16:00 | 2013-09-30 16:00 | 21 | 424 | 100 | 95 | -5 | 36414 | 36414 | 34593.3 | 36281.4428 | 0.95 | 0.95347 | FALSE | FALSE | FALSE | 53 | FALSE | 0 | Green | Continue normal monitoring.
146473 | HCMEB2Z6375 | B2 Z6 :Exhaust Fans | 26429 | 2013-09-30 16:00 | 2013-10-21 16:00 | 21 | 424 | 100 | 93 | -7 | 34104 | 34104 | 31716.72 | 32117.6944 | 0.93 | 0.98752 | FALSE | FALSE | FALSE | 53 | FALSE | 0 | Green | Continue normal monitoring.
146474 | HCMEB2Z6385 | B2 Z6 :Grills & Diffusers | 26429 | 2013-12-30 16:00 | 2014-01-13 16:00 | 14 | 424 | 100 | 100 | 0 | 16758 | 16758 | 16758 | 15707.6294 | 1 | 1.0669 | FALSE | FALSE | FALSE | 53 | FALSE | 0 | Green | Continue normal monitoring.
146475 | HCMEB2Z6425 | B2 Z6 :Mechanical final Fix | 26429 | 2014-01-13 16:00 | 2014-01-27 16:00 | 14 | 424 | 100 | 95 | -5 | 8834 | 8834 | 8392.3 | 7702.1638 | 0.95 | 1.0896 | FALSE | FALSE | FALSE | 53 | FALSE | 0 | Green | Continue normal monitoring.
146476 | HCMEB2Z6430 | B2 Z6 :All Vertical Piping Works | 26430 | 2012-12-31 08:00 | 2013-01-11 17:00 | 11 | 1471 | 100 | 84 | -16 | 20944 | 20944 | 17592.96 | 17950.4326 | 0.84 | 0.98009 | FALSE | TRUE | TRUE | 183.875 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146477 | HCMEB2Z6435 | B2 Z6 :All Horizantal Piping Works | 26430 | 2013-01-14 08:00 | 2013-02-22 17:00 | 39 | 1471 | 100 | 88 | -12 | 64545 | 64545 | 56799.6 | 57516.5205 | 0.88 | 0.98754 | FALSE | TRUE | TRUE | 183.875 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146478 | HCMEB2Z6440 | B2 Z6 :Mechanical Final Fix | 26430 | 2013-07-01 08:00 | 2013-07-26 17:00 | 25 | 1471 | 100 | 100 | 0 | 38575 | 38575 | 38575 | 35445.7571 | 1 | 1.0883 | FALSE | FALSE | FALSE | 183.875 | FALSE | 0 | Green | Continue normal monitoring.
146479 | HCMEB1Z1135 | B1 Z1 :Blocks Start Date for All Parts | 26597 | 2013-02-14 16:00 | 2013-02-14 16:00 | 1 | 288 | 100 | 100 | 0 | 1035 | 1035 | 1035 | 1058.1773 | 1 | 0.9781 | FALSE | FALSE | FALSE | 36 | FALSE | 0 | Green | Continue normal monitoring.
146480 | HCMEB1Z1145 | B1 Z1 :Tiling Finish Date for All Parts | 26597 | 2013-06-04 14:00 | 2013-06-04 14:00 | 1 | 578 | 100 | 100 | 0 | 1513 | 1513 | 1513 | 1595.0169 | 1 | 0.94858 | FALSE | FALSE | FALSE | 72.25 | FALSE | 0 | Green | Continue normal monitoring.
146481 | HCMEB1Z1155 | B1 Z1 :Plastering Finish Date for All Parts | 26597 | 2013-03-17 12:00 | 2013-03-17 12:00 | 1 | 1571 | 100 | 81 | -19 | 726 | 726 | 588.06 | 657.9279 | 0.81 | 0.89381 | TRUE | TRUE | TRUE | 196.375 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146482 | HCMEB1Z1165 | B1 Z1 :Gypsum Boards Finish Date for All Parts | 26597 | 2013-12-12 16:00 | 2013-12-12 16:00 | 1 | 752 | 100 | 97 | -3 | 1677 | 1677 | 1626.69 | 1710.3947 | 0.97 | 0.95106 | FALSE | FALSE | FALSE | 94 | FALSE | 0 | Green | Continue normal monitoring.
146483 | HCMEB1Z1195 | B1 Z1 :Electrical Coduits & Boards F.F for All Systems | 26597 | 2013-02-14 16:00 | 2013-03-04 16:00 | 18 | 984 | 100 | 85 | -15 | 35856 | 35856 | 30477.6 | 35379.0986 | 0.85 | 0.86146 | TRUE | TRUE | TRUE | 123 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146484 | HCMEB1Z1205 | B1 Z1 :Electrical Boards Seconed Fix | 26597 | 2013-05-17 16:00 | 2013-06-04 16:00 | 18 | 952 | 100 | 100 | 0 | 23778 | 23778 | 23778 | 21955.879 | 1 | 1.083 | FALSE | FALSE | FALSE | 119 | FALSE | 0 | Green | Continue normal monitoring.
146485 | HCMEB1Z1215 | B1 Z1 :Cable Tray Installation | 26597 | 2013-11-06 16:00 | 2013-11-20 16:00 | 14 | 0 | 100 | 88 | -12 | 19180 | 19180 | 16878.4 | 16355.4822 | 0.88 | 1.032 | FALSE | TRUE | TRUE | 0 | TRUE | 4 | Orange | Develop recovery plan and review schedule and cost exposure.
146486 | HCMEB1Z1225 | B1 Z1 :Electrcial Wiring | 26597 | 2013-08-26 08:00 | 2013-09-20 17:00 | 25 | 15 | 100 | 80 | -20 | 22600 | 22600 | 18080 | 23431.8415 | 0.8 | 0.7716 | TRUE | TRUE | TRUE | 1.875 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
146487 | HCMEB1Z1235 | B1 Z1 :Cable Laying | 26597 | 2013-11-20 16:00 | 2013-12-04 16:00 | 14 | 0 | 100 | 88 | -12 | 9814 | 9814 | 8636.32 | 11033.4945 | 0.88 | 0.78274 | TRUE | TRUE | TRUE | 0 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
146488 | HCMEB1Z1245 | B1 Z1 :Electrical Final Fix for All Systems & Boards (Vertical Elements) | 26597 | 2014-01-15 16:00 | 2014-01-29 16:00 | 14 | 360 | 100 | 100 | 0 | 7518 | 7518 | 7518 | 7070.7612 | 1 | 1.0633 | FALSE | FALSE | FALSE | 45 | FALSE | 0 | Green | Continue normal monitoring.
146489 | HCMEB1Z1255 | B1 Z1 :Electrical Final Fix for All Systems (Horizantel Elements) | 26597 | 2014-01-29 16:00 | 2014-02-12 16:00 | 14 | 360 | 100 | 95 | -5 | 20174 | 20174 | 19165.3 | 18211.5284 | 0.95 | 1.0524 | FALSE | FALSE | FALSE | 45 | FALSE | 0 | Green | Continue normal monitoring.
146490 | HCMEB1Z1045 | B1 Z1 :All Vertical Piping Works | 26499 | 2013-02-18 08:00 | 2013-03-01 17:00 | 11 | 231 | 100 | 92 | -8 | 7557 | 7557 | 6952.44 | 9104.8028 | 0.92 | 0.7636 | TRUE | FALSE | FALSE | 28.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146491 | HCMEB1Z1055 | B1 Z1 :All Horizantal Piping Works | 26499 | 2013-03-04 08:00 | 2013-04-12 17:00 | 39 | 231 | 100 | 88 | -12 | 61620 | 61620 | 54225.6 | 59155.8106 | 0.88 | 0.91666 | FALSE | TRUE | TRUE | 28.875 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146492 | HCMEB1Z1065 | B1 Z1 :Mechanical Final Fix | 26499 | 2013-08-19 08:00 | 2013-09-13 17:00 | 25 | 231 | 100 | 100 | 0 | 36000 | 36000 | 36000 | 33820.0217 | 1 | 1.0645 | FALSE | FALSE | FALSE | 28.875 | FALSE | 0 | Green | Continue normal monitoring.
146493 | HCMEB1Z1075 | B1 Z1 :Horizontal F.F Piping Work | 26598 | 2013-02-14 16:00 | 2013-03-14 16:00 | 28 | 1200 | 100 | 92 | -8 | 43204 | 43204 | 39747.68 | 51535.4065 | 0.92 | 0.77127 | TRUE | FALSE | FALSE | 150 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146494 | HCMEB1Z1085 | B1 Z1 :Fire Hose Cabinets | 26598 | 2013-03-14 16:00 | 2013-03-28 16:00 | 14 | 1200 | 100 | 100 | 0 | 10808 | 10808 | 10808 | 12719.3174 | 1 | 0.84973 | TRUE | FALSE | FALSE | 150 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146495 | HCMEB1Z1095 | B1 Z1 :Sprinklers Final Fix | 26598 | 2013-12-16 16:00 | 2013-12-30 16:00 | 14 | 264 | 100 | 88 | -12 | 22988 | 22988 | 20229.44 | 23662.4355 | 0.88 | 0.85492 | TRUE | TRUE | TRUE | 33 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146496 | HCMEB1Z1305 | B1 Z1 :Duct Installation& Dusct Accecories Installation, Fan coil Unit | 26434 | 2013-08-14 16:00 | 2013-08-26 16:00 | 12 | 184 | 100 | 90 | -10 | 12984 | 12984 | 11685.6 | 13577.311 | 0.9 | 0.86067 | TRUE | FALSE | FALSE | 23 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146497 | HCMEB1Z1315 | B1 Z1 :Duct Insulation Work | 26434 | 2013-08-26 16:00 | 2013-09-16 16:00 | 21 | 184 | 100 | 83 | -17 | 21315 | 21315 | 17691.45 | 19974.2755 | 0.83 | 0.88571 | TRUE | TRUE | TRUE | 23 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146498 | HCMEB1Z1325 | B1 Z1 :Exhaust Fans | 26434 | 2013-09-16 16:00 | 2013-10-07 16:00 | 21 | 184 | 100 | 81 | -19 | 36624 | 36624 | 29665.44 | 32277.4882 | 0.81 | 0.91908 | FALSE | TRUE | TRUE | 23 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146499 | HCMEB1Z1335 | B1 Z1 :Grills & Diffusers | 26434 | 2014-01-14 16:00 | 2014-01-28 16:00 | 14 | 16 | 100 | 100 | 0 | 14350 | 14350 | 14350 | 15488.9987 | 1 | 0.92646 | FALSE | FALSE | FALSE | 2 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146500 | HCMEB1Z1345 | B1 Z1 :Mechanical final Fix | 26434 | 2014-01-30 16:00 | 2014-02-13 16:00 | 14 | 0 | 100 | 85 | -15 | 11690 | 11690 | 9936.5 | 10396.3609 | 0.85 | 0.95577 | FALSE | TRUE | TRUE | 0 | TRUE | 4 | Orange | Develop recovery plan and review schedule and cost exposure.
146501 | HCMEB1Z1355 | B1 Z1 :All Vertical Piping Works | 26435 | 2013-02-18 08:00 | 2013-03-01 17:00 | 11 | 231 | 100 | 93 | -7 | 13167 | 13167 | 12245.31 | 13558.1892 | 0.93 | 0.90317 | FALSE | FALSE | FALSE | 28.875 | FALSE | 0 | Green | Continue normal monitoring.
146502 | HCMEB1Z1365 | B1 Z1 :All Horizantal Piping Works | 26435 | 2013-03-04 08:00 | 2013-04-12 17:00 | 39 | 231 | 100 | 83 | -17 | 61542 | 61542 | 51079.86 | 75462.7314 | 0.83 | 0.67689 | TRUE | TRUE | TRUE | 28.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146503 | HCMEB1Z1375 | B1 Z1 :Mechanical Final Fix | 26435 | 2013-08-19 08:00 | 2013-09-13 17:00 | 25 | 231 | 100 | 85 | -15 | 24975 | 24975 | 21228.75 | 30747.5655 | 0.85 | 0.69042 | TRUE | TRUE | TRUE | 28.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146504 | HCMEB1Z2140 | B1 Z2 :Blocks Start Date for All Parts | 26603 | 2013-03-04 16:00 | 2013-03-04 16:00 | 1 | 1152 | 100 | 98 | -2 | 1399 | 1399 | 1371.02 | 1323.0803 | 0.98 | 1.0362 | FALSE | FALSE | FALSE | 144 | FALSE | 0 | Green | Continue normal monitoring.
146505 | HCMEB1Z2150 | B1 Z2 :Tiling Finish Date for All Parts | 26603 | 2013-06-27 14:00 | 2013-06-27 14:00 | 1 | 418 | 100 | 85 | -15 | 1265 | 1265 | 1075.25 | 1391.0514 | 0.85 | 0.77298 | TRUE | TRUE | TRUE | 52.25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146506 | HCMEB1Z2160 | B1 Z2 :Plastering Finish Date for All Parts | 26603 | 2013-04-09 12:00 | 2013-04-09 12:00 | 1 | 1499 | 100 | 81 | -19 | 1035 | 1035 | 838.35 | 1076.0176 | 0.81 | 0.77912 | TRUE | TRUE | TRUE | 187.375 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146507 | HCMEB1Z2170 | B1 Z2 :Gypsum Boards Finish Date for All Parts | 26603 | 2013-12-11 16:00 | 2013-12-11 16:00 | 1 | 760 | 100 | 97 | -3 | 661 | 661 | 641.17 | 793.3811 | 0.97 | 0.80815 | TRUE | FALSE | FALSE | 95 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146508 | HCMEB1Z2200 | B1 Z2 :Electrical Coduits & Boards F.F for All Systems | 26603 | 2013-03-04 16:00 | 2013-03-20 16:00 | 16 | 960 | 100 | 92 | -8 | 17488 | 17488 | 16088.96 | 16763.5132 | 0.92 | 0.95976 | FALSE | FALSE | FALSE | 120 | FALSE | 0 | Green | Continue normal monitoring.
146509 | HCMEB1Z2210 | B1 Z2 :Electrical Boards Seconed Fix | 26603 | 2013-05-29 16:00 | 2013-06-14 16:00 | 16 | 960 | 100 | 88 | -12 | 10528 | 10528 | 9264.64 | 8964.3916 | 0.88 | 1.0335 | FALSE | TRUE | TRUE | 120 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146510 | HCMEB1Z2220 | B1 Z2 :Cable Tray Installation | 26603 | 2013-11-06 16:00 | 2013-11-20 16:00 | 14 | 88 | 100 | 100 | 0 | 23954 | 23954 | 23954 | 21918.4965 | 1 | 1.0929 | FALSE | FALSE | FALSE | 11 | FALSE | 0 | Green | Continue normal monitoring.
146511 | HCMEB1Z2230 | B1 Z2 :Electrcial Wiring | 26603 | 2013-07-22 08:00 | 2013-08-16 17:00 | 25 | 215 | 100 | 98 | -2 | 13975 | 13975 | 13695.5 | 13832.5825 | 0.98 | 0.99009 | FALSE | FALSE | FALSE | 26.875 | FALSE | 0 | Green | Continue normal monitoring.
146512 | HCMEB1Z2240 | B1 Z2 :Cable Laying | 26603 | 2013-11-20 16:00 | 2013-12-04 16:00 | 14 | 88 | 100 | 92 | -8 | 19796 | 19796 | 18212.32 | 19326.6062 | 0.92 | 0.94234 | FALSE | FALSE | FALSE | 11 | FALSE | 0 | Green | Continue normal monitoring.
146513 | HCMEB1Z2250 | B1 Z2 :Electrical Final Fix for All Systems & Boards (Vertical Elements) | 26603 | 2014-01-15 16:00 | 2014-01-29 16:00 | 14 | 360 | 100 | 90 | -10 | 25788 | 25788 | 23209.2 | 30082.8668 | 0.9 | 0.77151 | TRUE | FALSE | FALSE | 45 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146514 | HCMEB1Z2260 | B1 Z2 :Electrical Final Fix for All Systems (Horizantel Elements) | 26603 | 2014-01-29 16:00 | 2014-02-12 16:00 | 14 | 360 | 100 | 80 | -20 | 9940 | 9940 | 7952 | 11154.9092 | 0.8 | 0.71287 | TRUE | TRUE | TRUE | 45 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146515 | HCMEB1Z2050 | B1 Z2 :All Vertical Piping Works | 26500 | 2013-02-18 08:00 | 2013-03-01 17:00 | 11 | 391 | 100 | 100 | 0 | 9955 | 9955 | 9955 | 9654.5833 | 1 | 1.0311 | FALSE | FALSE | FALSE | 48.875 | FALSE | 0 | Green | Continue normal monitoring.
146516 | HCMEB1Z2060 | B1 Z2 :All Horizantal Piping Works | 26500 | 2013-03-04 08:00 | 2013-04-12 17:00 | 39 | 391 | 100 | 100 | 0 | 45357 | 45357 | 45357 | 46858.2045 | 1 | 0.96796 | FALSE | FALSE | FALSE | 48.875 | FALSE | 0 | Green | Continue normal monitoring.
146517 | HCMEB1Z2070 | B1 Z2 :Mechanical Final Fix | 26500 | 2013-08-19 08:00 | 2013-09-13 17:00 | 25 | 391 | 100 | 100 | 0 | 40800 | 40800 | 40800 | 36239.5246 | 1 | 1.1258 | FALSE | FALSE | FALSE | 48.875 | FALSE | 0 | Green | Continue normal monitoring.
146518 | HCMEB1Z2080 | B1 Z2 :Horizontal F.F Piping Work | 26604 | 2013-03-04 16:00 | 2013-04-01 16:00 | 28 | 1184 | 100 | 86 | -14 | 44772 | 44772 | 38503.92 | 54140.9251 | 0.86 | 0.71118 | TRUE | TRUE | TRUE | 148 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146519 | HCMEB1Z2090 | B1 Z2 :Fire Hose Cabinets | 26604 | 2013-04-01 16:00 | 2013-04-15 16:00 | 14 | 1184 | 100 | 100 | 0 | 14574 | 14574 | 14574 | 17841.0526 | 1 | 0.81688 | TRUE | FALSE | FALSE | 148 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146520 | HCMEB1Z2100 | B1 Z2 :Sprinklers Final Fix | 26604 | 2013-12-16 16:00 | 2013-12-30 16:00 | 14 | 344 | 100 | 100 | 0 | 25718 | 25718 | 25718 | 31939.7349 | 1 | 0.8052 | TRUE | FALSE | FALSE | 43 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146521 | HCMEB1Z2310 | B1 Z2 :Duct Installation& Dusct Accecories Installation, Fan coil Unit | 26439 | 2013-08-14 16:00 | 2013-08-26 16:00 | 12 | 169 | 100 | 94 | -6 | 17964 | 17964 | 16886.16 | 21510.4732 | 0.94 | 0.78502 | TRUE | FALSE | FALSE | 21.125 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146522 | HCMEB1Z2320 | B1 Z2 :Duct Insulation Work | 26439 | 2013-08-26 16:00 | 2013-09-16 16:00 | 21 | 169 | 100 | 80 | -20 | 34440 | 34440 | 27552 | 31670.4852 | 0.8 | 0.86996 | TRUE | TRUE | TRUE | 21.125 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146523 | HCMEB1Z2330 | B1 Z2 :Exhaust Fans | 26439 | 2013-09-16 16:00 | 2013-10-07 16:00 | 21 | 169 | 100 | 91 | -9 | 29946 | 29946 | 27250.86 | 26007.46 | 0.91 | 1.0478 | FALSE | FALSE | FALSE | 21.125 | FALSE | 0 | Green | Continue normal monitoring.
146524 | HCMEB1Z2340 | B1 Z2 :Grills & Diffusers | 26439 | 2014-01-09 16:00 | 2014-01-23 16:00 | 14 | 25 | 100 | 100 | 0 | 19138 | 19138 | 19138 | 20704.2289 | 1 | 0.92435 | FALSE | FALSE | FALSE | 3.125 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146525 | HCMEB1Z2350 | B1 Z2 :Mechanical final Fix | 26439 | 2014-01-23 16:00 | 2014-02-06 16:00 | 14 | 25 | 100 | 86 | -14 | 7252 | 7252 | 6236.72 | 8811.4847 | 0.86 | 0.70779 | TRUE | TRUE | TRUE | 3.125 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
146526 | HCMEB1Z2360 | B1 Z2 :All Vertical Piping Works | 26567 | 2013-02-18 08:00 | 2013-03-01 17:00 | 11 | 391 | 100 | 94 | -6 | 10241 | 10241 | 9626.54 | 9431.3521 | 0.94 | 1.0207 | FALSE | FALSE | FALSE | 48.875 | FALSE | 0 | Green | Continue normal monitoring.
146527 | HCMEB1Z2370 | B1 Z2 :All Horizantal Piping Works | 26567 | 2013-03-04 08:00 | 2013-04-12 17:00 | 39 | 391 | 100 | 100 | 0 | 48321 | 48321 | 48321 | 41208.9783 | 1 | 1.1726 | FALSE | FALSE | FALSE | 48.875 | FALSE | 0 | Green | Continue normal monitoring.
146528 | HCMEB1Z2380 | B1 Z2 :Mechanical Final Fix | 26567 | 2013-08-19 08:00 | 2013-09-13 17:00 | 25 | 391 | 100 | 98 | -2 | 46825 | 46825 | 45888.5 | 54888.1909 | 0.98 | 0.83604 | TRUE | FALSE | FALSE | 48.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146529 | HCMEB1Z3145 | B1 Z3 :Blocks Start Date for All Parts | 26609 | 2013-03-09 16:00 | 2013-03-09 16:00 | 1 | 1232 | 100 | 100 | 0 | 682 | 682 | 682 | 600.6499 | 1 | 1.1354 | FALSE | FALSE | FALSE | 154 | FALSE | 0 | Green | Continue normal monitoring.
146530 | HCMEB1Z3155 | B1 Z3 :Tiling Finish Date for All Parts | 26609 | 2013-08-14 14:00 | 2013-08-14 14:00 | 1 | 1186 | 100 | 100 | 0 | 612 | 612 | 612 | 621.4752 | 1 | 0.98475 | FALSE | FALSE | FALSE | 148.25 | FALSE | 0 | Green | Continue normal monitoring.
146531 | HCMEB1Z3165 | B1 Z3 :Plastering Finish Date for All Parts | 26609 | 2013-06-01 16:00 | 2013-06-01 16:00 | 1 | 1241 | 100 | 100 | 0 | 1706 | 1706 | 1706 | 1913.3727 | 1 | 0.89162 | TRUE | FALSE | FALSE | 155.125 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146532 | HCMEB1Z3175 | B1 Z3 :Gypsum Boards Finish Date for All Parts | 26609 | 2013-12-11 16:00 | 2013-12-11 16:00 | 1 | 760 | 100 | 80 | -20 | 980 | 980 | 784 | 925.8247 | 0.8 | 0.84681 | TRUE | TRUE | TRUE | 95 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146533 | HCMEB1Z3205 | B1 Z3 :Electrical Coduits & Boards F.F for All Systems | 26609 | 2013-03-11 08:00 | 2013-03-26 17:00 | 15 | 1023 | 100 | 96 | -4 | 25035 | 25035 | 24033.6 | 22120.5511 | 0.96 | 1.0865 | FALSE | FALSE | FALSE | 127.875 | FALSE | 0 | Green | Continue normal monitoring.
146534 | HCMEB1Z3215 | B1 Z3 :Electrical Boards Seconed Fix | 26609 | 2013-06-19 08:00 | 2013-07-04 17:00 | 15 | 943 | 100 | 96 | -4 | 19950 | 19950 | 19152 | 23102.2694 | 0.96 | 0.82901 | TRUE | FALSE | FALSE | 117.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146535 | HCMEB1Z3225 | B1 Z3 :Cable Tray Installation | 26609 | 2013-11-06 16:00 | 2013-11-20 16:00 | 14 | 168 | 100 | 82 | -18 | 22904 | 22904 | 18781.28 | 25241.8121 | 0.82 | 0.74405 | TRUE | TRUE | TRUE | 21 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146536 | HCMEB1Z3235 | B1 Z3 :Electrcial Wiring | 26609 | 2013-12-16 16:00 | 2013-12-26 16:00 | 10 | 296 | 100 | 91 | -9 | 12620 | 12620 | 11484.2 | 15716.9 | 0.91 | 0.73069 | TRUE | FALSE | FALSE | 37 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146537 | HCMEB1Z3245 | B1 Z3 :Cable Laying | 26609 | 2013-11-20 16:00 | 2013-12-04 16:00 | 14 | 168 | 100 | 85 | -15 | 13650 | 13650 | 11602.5 | 13482.4219 | 0.85 | 0.86056 | TRUE | TRUE | TRUE | 21 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146538 | HCMEB1Z3255 | B1 Z3 :Electrical Final Fix for All Systems & Boards (Vertical Elements) | 26609 | 2014-01-27 16:00 | 2014-02-10 16:00 | 14 | 296 | 100 | 100 | 0 | 17668 | 17668 | 17668 | 15454.2871 | 1 | 1.1432 | FALSE | FALSE | FALSE | 37 | FALSE | 0 | Green | Continue normal monitoring.
146539 | HCMEB1Z3265 | B1 Z3 :Electrical Final Fix for All Systems (Horizantel Elements) | 26609 | 2014-02-10 16:00 | 2014-02-24 16:00 | 14 | 296 | 100 | 90 | -10 | 25564 | 25564 | 23007.6 | 29238.5697 | 0.9 | 0.78689 | TRUE | FALSE | FALSE | 37 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146540 | HCMEB1Z3055 | B1 Z3 :All Vertical Piping Works | 26506 | 2013-02-18 08:00 | 2013-03-01 17:00 | 11 | 391 | 100 | 82 | -18 | 16170 | 16170 | 13259.4 | 17119.0718 | 0.82 | 0.77454 | TRUE | TRUE | TRUE | 48.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146541 | HCMEB1Z3065 | B1 Z3 :All Horizantal Piping Works | 26506 | 2013-03-04 08:00 | 2013-04-12 17:00 | 39 | 391 | 100 | 87 | -13 | 59241 | 59241 | 51539.67 | 55407.0156 | 0.87 | 0.9302 | FALSE | TRUE | TRUE | 48.875 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146542 | HCMEB1Z3075 | B1 Z3 :Mechanical Final Fix | 26506 | 2013-08-19 08:00 | 2013-09-13 17:00 | 25 | 391 | 100 | 93 | -7 | 41025 | 41025 | 38153.25 | 47699.4227 | 0.93 | 0.79987 | TRUE | FALSE | FALSE | 48.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146543 | HCMEB1Z3085 | B1 Z3 :Horizontal F.F Piping Work | 26610 | 2013-03-11 08:00 | 2013-04-05 17:00 | 25 | 1151 | 100 | 93 | -7 | 16500 | 16500 | 15345 | 15369.7862 | 0.93 | 0.99839 | FALSE | FALSE | FALSE | 143.875 | FALSE | 0 | Green | Continue normal monitoring.
146544 | HCMEB1Z3095 | B1 Z3 :Fire Hose Cabinets | 26610 | 2013-04-08 08:00 | 2013-04-19 17:00 | 11 | 1151 | 100 | 89 | -11 | 9900 | 9900 | 8811 | 9447.2202 | 0.89 | 0.93266 | FALSE | TRUE | TRUE | 143.875 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146545 | HCMEB1Z3105 | B1 Z3 :Sprinklers Final Fix | 26610 | 2013-12-16 16:00 | 2013-12-30 16:00 | 14 | 344 | 100 | 81 | -19 | 9758 | 9758 | 7903.98 | 8655.4575 | 0.81 | 0.91318 | FALSE | TRUE | TRUE | 43 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146546 | HCMEB1Z3315 | B1 Z3 :Duct Installation& Dusct Accecories Installation, Fan coil Unit | 26445 | 2013-08-22 16:00 | 2013-09-05 16:00 | 14 | 200 | 100 | 93 | -7 | 24962 | 24962 | 23214.66 | 25205.9514 | 0.93 | 0.921 | FALSE | FALSE | FALSE | 25 | FALSE | 0 | Green | Continue normal monitoring.
146547 | HCMEB1Z3325 | B1 Z3 :Duct Insulation Work | 26445 | 2013-09-05 16:00 | 2013-09-26 16:00 | 21 | 200 | 100 | 88 | -12 | 24339 | 24339 | 21418.32 | 24766.6774 | 0.88 | 0.8648 | TRUE | TRUE | TRUE | 25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146548 | HCMEB1Z3335 | B1 Z3 :Exhaust Fans | 26445 | 2013-09-26 16:00 | 2013-10-17 16:00 | 21 | 200 | 100 | 82 | -18 | 32970 | 32970 | 27035.4 | 34810.5409 | 0.82 | 0.77664 | TRUE | TRUE | TRUE | 25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146549 | HCMEB1Z3345 | B1 Z3 :Grills & Diffusers | 26445 | 2014-01-09 16:00 | 2014-01-23 16:00 | 14 | 120 | 100 | 100 | 0 | 12572 | 12572 | 12572 | 14251.4395 | 1 | 0.88216 | TRUE | FALSE | FALSE | 15 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146550 | HCMEB1Z3355 | B1 Z3 :Mechanical final Fix | 26445 | 2014-01-23 16:00 | 2014-02-06 16:00 | 14 | 120 | 100 | 100 | 0 | 8078 | 8078 | 8078 | 9794.0933 | 1 | 0.82478 | TRUE | FALSE | FALSE | 15 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146551 | HCMEB1Z3365 | B1 Z3 :All Vertical Piping Works | 26446 | 2013-02-18 08:00 | 2013-03-01 17:00 | 11 | 391 | 100 | 87 | -13 | 6853 | 6853 | 5962.11 | 6202.6067 | 0.87 | 0.96123 | FALSE | TRUE | TRUE | 48.875 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146552 | HCMEB1Z3375 | B1 Z3 :All Horizantal Piping Works | 26446 | 2013-03-04 08:00 | 2013-04-12 17:00 | 39 | 391 | 100 | 95 | -5 | 22386 | 22386 | 21266.7 | 19514.7546 | 0.95 | 1.0898 | FALSE | FALSE | FALSE | 48.875 | FALSE | 0 | Green | Continue normal monitoring.
146553 | HCMEB1Z3385 | B1 Z3 :Mechanical Final Fix | 26446 | 2013-08-19 08:00 | 2013-09-13 17:00 | 25 | 391 | 100 | 81 | -19 | 15900 | 15900 | 12879 | 13632.8586 | 0.81 | 0.9447 | FALSE | TRUE | TRUE | 48.875 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146554 | HCMEB1Z4150 | B1 Z4 :Blocks Start Date for All Parts | 26449 | 2013-03-26 16:00 | 2013-03-26 16:00 | 1 | 1456 | 100 | 85 | -15 | 1101 | 1101 | 935.85 | 999.1009 | 0.85 | 0.93669 | FALSE | TRUE | TRUE | 182 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146555 | HCMEB1Z4160 | B1 Z4 :Tiling Finish Date for All Parts | 26449 | 2013-10-31 16:00 | 2013-10-31 16:00 | 1 | 312 | 100 | 100 | 0 | 1923 | 1923 | 1923 | 2140.6447 | 1 | 0.89833 | TRUE | FALSE | FALSE | 39 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146556 | HCMEB1Z4170 | B1 Z4 :Plastering Finish Date for All Parts | 26449 | 2013-08-07 14:00 | 2013-08-07 14:00 | 1 | 1042 | 100 | 100 | 0 | 1336 | 1336 | 1336 | 1524.3638 | 1 | 0.87643 | TRUE | FALSE | FALSE | 130.25 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146557 | HCMEB1Z4180 | B1 Z4 :Gypsum Boards Finish Date for All Parts | 26449 | 2014-01-06 16:00 | 2014-01-06 16:00 | 1 | 592 | 100 | 100 | 0 | 999 | 999 | 999 | 1163.4377 | 1 | 0.85866 | TRUE | FALSE | FALSE | 74 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146558 | HCMEB1Z4210 | B1 Z4 :Electrical Coduits & Boards F.F for All Systems | 26449 | 2013-03-26 16:00 | 2013-04-11 16:00 | 16 | 1216 | 100 | 100 | 0 | 10192 | 10192 | 10192 | 9656.7496 | 1 | 1.0554 | FALSE | FALSE | FALSE | 152 | FALSE | 0 | Green | Continue normal monitoring.
146559 | HCMEB1Z4220 | B1 Z4 :Electrical Boards Seconed Fix | 26449 | 2013-08-07 14:00 | 2013-08-23 14:00 | 16 | 946 | 100 | 100 | 0 | 8784 | 8784 | 8784 | 8541.192 | 1 | 1.0284 | FALSE | FALSE | FALSE | 118.25 | FALSE | 0 | Green | Continue normal monitoring.
146560 | HCMEB1Z4230 | B1 Z4 :Cable Tray Installation | 26449 | 2013-11-06 16:00 | 2013-11-20 16:00 | 14 | 360 | 100 | 91 | -9 | 20608 | 20608 | 18753.28 | 21499.3755 | 0.91 | 0.87227 | TRUE | FALSE | FALSE | 45 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146561 | HCMEB1Z4240 | B1 Z4 :Electrcial Wiring | 26449 | 2013-10-31 16:00 | 2013-11-28 16:00 | 28 | 264 | 100 | 84 | -16 | 21084 | 21084 | 17710.56 | 18454.261 | 0.84 | 0.9597 | FALSE | TRUE | TRUE | 33 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146562 | HCMEB1Z4250 | B1 Z4 :Cable Laying | 26449 | 2013-11-20 16:00 | 2013-12-04 16:00 | 14 | 360 | 100 | 81 | -19 | 16926 | 16926 | 13710.06 | 18524.7726 | 0.81 | 0.74009 | TRUE | TRUE | TRUE | 45 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146563 | HCMEB1Z4260 | B1 Z4 :Electrical Final Fix for All Systems & Boards (Vertical Elements) | 26449 | 2014-01-15 16:00 | 2014-01-29 16:00 | 14 | 360 | 100 | 95 | -5 | 14868 | 14868 | 14124.6 | 18488.269 | 0.95 | 0.76398 | TRUE | FALSE | FALSE | 45 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146564 | HCMEB1Z4270 | B1 Z4 :Electrical Final Fix for All Systems (Horizantel Elements) | 26449 | 2014-01-29 16:00 | 2014-02-12 16:00 | 14 | 360 | 100 | 84 | -16 | 17584 | 17584 | 14770.56 | 17484.1673 | 0.84 | 0.8448 | TRUE | TRUE | TRUE | 45 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146565 | HCMEB1Z4060 | B1 Z4 :All Vertical Piping Works | 26512 | 2013-02-18 08:00 | 2013-03-01 17:00 | 11 | 936 | 100 | 94 | -6 | 21439 | 21439 | 20152.66 | 24679.2688 | 0.94 | 0.81658 | TRUE | FALSE | FALSE | 117 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146566 | HCMEB1Z4070 | B1 Z4 :All Horizantal Piping Works | 26512 | 2013-03-04 08:00 | 2013-04-12 17:00 | 39 | 1031 | 100 | 91 | -9 | 40794 | 40794 | 37122.54 | 42834.2534 | 0.91 | 0.86666 | TRUE | FALSE | FALSE | 128.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146567 | HCMEB1Z4080 | B1 Z4 :Mechanical Final Fix | 26512 | 2013-08-19 08:00 | 2013-09-13 17:00 | 25 | 1031 | 100 | 83 | -17 | 45625 | 45625 | 37868.75 | 41113.8162 | 0.83 | 0.92107 | FALSE | TRUE | TRUE | 128.875 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146568 | HCMEB1Z4090 | B1 Z4 :Horizontal F.F Piping Work | 26450 | 2013-03-26 16:00 | 2013-04-23 16:00 | 28 | 1376 | 100 | 94 | -6 | 39788 | 39788 | 37400.72 | 43086.2254 | 0.94 | 0.86804 | TRUE | FALSE | FALSE | 172 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146569 | HCMEB1Z4100 | B1 Z4 :Fire Hose Cabinets | 26450 | 2013-04-23 16:00 | 2013-05-07 16:00 | 14 | 1376 | 100 | 90 | -10 | 15120 | 15120 | 13608 | 14665.6396 | 0.9 | 0.92788 | FALSE | FALSE | FALSE | 172 | FALSE | 0 | Green | Continue normal monitoring.
146570 | HCMEB1Z4110 | B1 Z4 :Sprinklers Final Fix | 26450 | 2013-12-16 16:00 | 2013-12-30 16:00 | 14 | 664 | 100 | 95 | -5 | 26208 | 26208 | 24897.6 | 22637.4557 | 0.95 | 1.0998 | FALSE | FALSE | FALSE | 83 | FALSE | 0 | Green | Continue normal monitoring.
146571 | HCMEB1Z4320 | B1 Z4 :Duct Installation& Dusct Accecories Installation, Fan coil Unit | 26451 | 2013-09-09 16:00 | 2013-09-27 16:00 | 18 | 296 | 100 | 100 | 0 | 9864 | 9864 | 9864 | 10889.5787 | 1 | 0.90582 | FALSE | FALSE | FALSE | 37 | FALSE | 0 | Green | Continue normal monitoring.
146572 | HCMEB1Z4330 | B1 Z4 :Duct Insulation Work | 26451 | 2013-09-27 16:00 | 2013-10-18 16:00 | 21 | 392 | 100 | 85 | -15 | 29736 | 29736 | 25275.6 | 35492.0849 | 0.85 | 0.71215 | TRUE | TRUE | TRUE | 49 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146573 | HCMEB1Z4340 | B1 Z4 :Exhaust Fans | 26451 | 2013-10-18 16:00 | 2013-11-08 16:00 | 21 | 392 | 100 | 93 | -7 | 33537 | 33537 | 31189.41 | 33131.4675 | 0.93 | 0.94138 | FALSE | FALSE | FALSE | 49 | FALSE | 0 | Green | Continue normal monitoring.
146574 | HCMEB1Z4350 | B1 Z4 :Grills & Diffusers | 26451 | 2014-01-17 16:00 | 2014-01-31 16:00 | 14 | 392 | 100 | 97 | -3 | 16842 | 16842 | 16336.74 | 16945.043 | 0.97 | 0.9641 | FALSE | FALSE | FALSE | 49 | FALSE | 0 | Green | Continue normal monitoring.
146575 | HCMEB1Z4360 | B1 Z4 :Mechanical final Fix | 26451 | 2014-01-31 16:00 | 2014-02-14 16:00 | 14 | 392 | 100 | 91 | -9 | 10640 | 10640 | 9682.4 | 12836.1883 | 0.91 | 0.7543 | TRUE | FALSE | FALSE | 49 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146576 | HCMEB1Z4370 | B1 Z4 :All Vertical Piping Works | 26452 | 2013-02-18 08:00 | 2013-03-01 17:00 | 11 | 1031 | 100 | 100 | 0 | 9405 | 9405 | 9405 | 11055.0464 | 1 | 0.85074 | TRUE | FALSE | FALSE | 128.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146577 | HCMEB1Z4380 | B1 Z4 :All Horizantal Piping Works | 26452 | 2013-03-04 08:00 | 2013-04-12 17:00 | 39 | 1031 | 100 | 90 | -10 | 69537 | 69537 | 62583.3 | 78992.7198 | 0.9 | 0.79227 | TRUE | FALSE | FALSE | 128.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146578 | HCMEB1Z4390 | B1 Z4 :Mechanical Final Fix | 26452 | 2013-08-19 08:00 | 2013-09-13 17:00 | 25 | 1031 | 100 | 92 | -8 | 28425 | 28425 | 26151 | 26990.0726 | 0.92 | 0.96891 | FALSE | FALSE | FALSE | 128.875 | FALSE | 0 | Green | Continue normal monitoring.
146579 | HCMEB1Z5155 | B1 Z5 :Blocks Start Date for All Parts | 26454 | 2013-03-07 16:00 | 2013-03-07 16:00 | 1 | 1584 | 100 | 100 | 0 | 1242 | 1242 | 1242 | 1507.8956 | 1 | 0.82366 | TRUE | FALSE | FALSE | 198 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146580 | HCMEB1Z5165 | B1 Z5 :Tiling Finish Date for All Parts | 26454 | 2013-12-26 12:00 | 2013-12-26 12:00 | 1 | 163 | 100 | 100 | 0 | 1818 | 1818 | 1818 | 1657.5911 | 1 | 1.0968 | FALSE | FALSE | FALSE | 20.375 | FALSE | 0 | Green | Continue normal monitoring.
146581 | HCMEB1Z5175 | B1 Z5 :Plastering Finish Date for All Parts | 26454 | 2013-10-10 16:00 | 2013-10-10 16:00 | 1 | 600 | 100 | 90 | -10 | 1509 | 1509 | 1358.1 | 1660.9687 | 0.9 | 0.81766 | TRUE | FALSE | FALSE | 75 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146582 | HCMEB1Z5185 | B1 Z5 :Gypsum Boards Finish Date for All Parts | 26454 | 2014-02-18 12:00 | 2014-02-18 12:00 | 1 | 299 | 100 | 100 | 0 | 1430 | 1430 | 1430 | 1231.9743 | 1 | 1.1607 | FALSE | FALSE | FALSE | 37.375 | FALSE | 0 | Green | Continue normal monitoring.
146583 | HCMEB1Z5215 | B1 Z5 :Electrical Coduits & Boards F.F for All Systems | 26454 | 2013-03-07 16:00 | 2013-03-25 16:00 | 18 | 1320 | 100 | 95 | -5 | 20520 | 20520 | 19494 | 22725.6522 | 0.95 | 0.8578 | TRUE | FALSE | FALSE | 165 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146584 | HCMEB1Z5225 | B1 Z5 :Electrical Boards Seconed Fix | 26454 | 2013-10-10 16:00 | 2013-10-28 16:00 | 18 | 576 | 100 | 94 | -6 | 23238 | 23238 | 21843.72 | 22328.4122 | 0.94 | 0.97829 | FALSE | FALSE | FALSE | 72 | FALSE | 0 | Green | Continue normal monitoring.
146585 | HCMEB1Z5235 | B1 Z5 :Cable Tray Installation | 26454 | 2013-11-06 16:00 | 2013-11-20 16:00 | 14 | 360 | 100 | 100 | 0 | 25704 | 25704 | 25704 | 26471.7988 | 1 | 0.971 | FALSE | FALSE | FALSE | 45 | FALSE | 0 | Green | Continue normal monitoring.
146586 | HCMEB1Z5245 | B1 Z5 :Electrcial Wiring | 26454 | 2013-12-26 13:00 | 2014-01-23 12:00 | 27 | 139 | 100 | 100 | 0 | 29997 | 29997 | 29997 | 29640.2103 | 1 | 1.012 | FALSE | FALSE | FALSE | 17.375 | FALSE | 0 | Green | Continue normal monitoring.
146587 | HCMEB1Z5255 | B1 Z5 :Cable Laying | 26454 | 2013-11-20 16:00 | 2013-12-04 16:00 | 14 | 360 | 100 | 94 | -6 | 18312 | 18312 | 17213.28 | 16830.6087 | 0.94 | 1.0227 | FALSE | FALSE | FALSE | 45 | FALSE | 0 | Green | Continue normal monitoring.
146588 | HCMEB1Z5265 | B1 Z5 :Electrical Final Fix for All Systems & Boards (Vertical Elements) | 26454 | 2014-02-24 13:00 | 2014-03-10 12:00 | 13 | 139 | 100 | 100 | 0 | 22165 | 22165 | 22165 | 24354.7317 | 1 | 0.91009 | FALSE | FALSE | FALSE | 17.375 | FALSE | 0 | Green | Continue normal monitoring.
146589 | HCMEB1Z5275 | B1 Z5 :Electrical Final Fix for All Systems (Horizantel Elements) | 26454 | 2014-03-10 13:00 | 2014-03-24 12:00 | 13 | 139 | 100 | 83 | -17 | 15405 | 15405 | 12786.15 | 18528.9834 | 0.83 | 0.69006 | TRUE | TRUE | TRUE | 17.375 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146590 | HCMEB1Z5065 | B1 Z5 :All Vertical Piping Works | 26518 | 2013-02-18 08:00 | 2013-03-01 17:00 | 11 | 936 | 100 | 90 | -10 | 20757 | 20757 | 18681.3 | 25606.5346 | 0.9 | 0.72955 | TRUE | FALSE | TRUE | 117 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146591 | HCMEB1Z5075 | B1 Z5 :All Horizantal Piping Works | 26518 | 2013-03-04 08:00 | 2013-04-12 17:00 | 39 | 936 | 100 | 98 | -2 | 26793 | 26793 | 26257.14 | 24835.4644 | 0.98 | 1.0572 | FALSE | FALSE | FALSE | 117 | FALSE | 0 | Green | Continue normal monitoring.
146592 | HCMEB1Z5085 | B1 Z5 :Mechanical Final Fix | 26518 | 2013-08-19 08:00 | 2013-09-13 17:00 | 25 | 936 | 100 | 94 | -6 | 37100 | 37100 | 34874 | 42180.812 | 0.94 | 0.82677 | TRUE | FALSE | FALSE | 117 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146593 | HCMEB1Z5095 | B1 Z5 :Horizontal F.F Piping Work | 26582 | 2013-03-07 16:00 | 2013-04-04 16:00 | 28 | 1480 | 100 | 83 | -17 | 29316 | 29316 | 24332.28 | 32708.9091 | 0.83 | 0.7439 | TRUE | TRUE | TRUE | 185 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146594 | HCMEB1Z5105 | B1 Z5 :Fire Hose Cabinets | 26582 | 2013-04-04 16:00 | 2013-04-18 16:00 | 14 | 1480 | 100 | 100 | 0 | 17136 | 17136 | 17136 | 16919.2487 | 1 | 1.0128 | FALSE | FALSE | FALSE | 185 | FALSE | 0 | Green | Continue normal monitoring.
146595 | HCMEB1Z5115 | B1 Z5 :Sprinklers Final Fix | 26582 | 2013-12-16 16:00 | 2013-12-30 16:00 | 14 | 664 | 100 | 92 | -8 | 19950 | 19950 | 18354 | 17109.9116 | 0.92 | 1.0727 | FALSE | FALSE | FALSE | 83 | FALSE | 0 | Green | Continue normal monitoring.
146596 | HCMEB1Z5325 | B1 Z5 :Duct Installation& Dusct Accecories Installation, Fan coil Unit | 26583 | 2013-09-09 16:00 | 2013-09-27 16:00 | 18 | 296 | 100 | 100 | 0 | 34758 | 34758 | 34758 | 39134.6057 | 1 | 0.88817 | TRUE | FALSE | FALSE | 37 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146597 | HCMEB1Z5335 | B1 Z5 :Duct Insulation Work | 26583 | 2013-09-27 16:00 | 2013-10-18 16:00 | 21 | 392 | 100 | 98 | -2 | 28875 | 28875 | 28297.5 | 35464.2156 | 0.98 | 0.79792 | TRUE | FALSE | FALSE | 49 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146598 | HCMEB1Z5345 | B1 Z5 :Exhaust Fans | 26583 | 2013-10-18 16:00 | 2013-11-08 16:00 | 21 | 392 | 100 | 81 | -19 | 23457 | 23457 | 19000.17 | 25869.5067 | 0.81 | 0.73446 | TRUE | TRUE | TRUE | 49 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146599 | HCMEB1Z5355 | B1 Z5 :Grills & Diffusers | 26583 | 2014-01-17 16:00 | 2014-01-31 16:00 | 14 | 392 | 100 | 93 | -7 | 12782 | 12782 | 11887.26 | 13090.2646 | 0.93 | 0.9081 | FALSE | FALSE | FALSE | 49 | FALSE | 0 | Green | Continue normal monitoring.
146600 | HCMEB1Z5365 | B1 Z5 :Mechanical final Fix | 26583 | 2014-01-31 16:00 | 2014-02-14 16:00 | 14 | 392 | 100 | 100 | 0 | 26110 | 26110 | 26110 | 27678.2073 | 1 | 0.94334 | FALSE | FALSE | FALSE | 49 | FALSE | 0 | Green | Continue normal monitoring.
146601 | HCMEB1Z5375 | B1 Z5 :All Vertical Piping Works | 26584 | 2013-02-18 08:00 | 2013-03-01 17:00 | 11 | 1223 | 100 | 83 | -17 | 19173 | 19173 | 15913.59 | 17828.0433 | 0.83 | 0.89262 | TRUE | TRUE | TRUE | 152.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146602 | HCMEB1Z5385 | B1 Z5 :All Horizantal Piping Works | 26584 | 2013-03-04 08:00 | 2013-04-12 17:00 | 39 | 1223 | 100 | 95 | -5 | 54678 | 54678 | 51944.1 | 62891.6015 | 0.95 | 0.82593 | TRUE | FALSE | FALSE | 152.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146603 | HCMEB1Z5395 | B1 Z5 :Mechanical Final Fix | 26584 | 2013-08-19 08:00 | 2013-09-13 17:00 | 25 | 1223 | 100 | 100 | 0 | 16550 | 16550 | 16550 | 19008.7993 | 1 | 0.87065 | TRUE | FALSE | FALSE | 152.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146604 | HCMEB1Z6160 | B1 Z6 :B1 Z6 :Blocks Start Date for All Parts | 26616 | 2013-04-13 16:00 | 2013-04-13 16:00 | 1 | 1336 | 100 | 99 | -1 | 1743 | 1743 | 1725.57 | 1583.0047 | 0.99 | 1.0901 | FALSE | FALSE | FALSE | 167 | FALSE | 0 | Green | Continue normal monitoring.
146605 | HCMEB1Z6170 | B1 Z6 :B1 Z6 :Tiling Finish Date for All Parts | 26616 | 2013-06-24 12:00 | 2013-06-24 12:00 | 1 | 1427 | 100 | 93 | -7 | 769 | 769 | 715.17 | 923.7162 | 0.93 | 0.77423 | TRUE | FALSE | FALSE | 178.375 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146606 | HCMEB1Z6180 | B1 Z6 :B1 Z6 :Plastering Finish Date for All Parts | 26616 | 2013-05-14 12:00 | 2013-05-14 12:00 | 1 | 1627 | 100 | 100 | 0 | 1131 | 1131 | 1131 | 1083.1314 | 1 | 1.0442 | FALSE | FALSE | FALSE | 203.375 | FALSE | 0 | Green | Continue normal monitoring.
146607 | HCMEB1Z6190 | B1 Z6 :B1 Z6 :Gypsum Boards Finish Date for All Parts | 26616 | 2013-09-08 14:00 | 2013-09-08 14:00 | 1 | 1402 | 100 | 100 | 0 | 1405 | 1405 | 1405 | 1746.2779 | 1 | 0.80457 | TRUE | FALSE | FALSE | 175.25 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146608 | HCMEB1Z6220 | B1 Z6 :B1 Z6 :Electrical Coduits & Boards F.F for All Systems | 26616 | 2013-04-15 08:00 | 2013-04-30 17:00 | 15 | 1111 | 100 | 94 | -6 | 28845 | 28845 | 27114.3 | 28936.185 | 0.94 | 0.93704 | FALSE | FALSE | FALSE | 138.875 | FALSE | 0 | Green | Continue normal monitoring.
146609 | HCMEB1Z6230 | B1 Z6 :B1 Z6 :Electrical Boards Seconed Fix | 26616 | 2013-07-29 16:00 | 2013-08-14 16:00 | 16 | 1000 | 100 | 100 | 0 | 27280 | 27280 | 27280 | 25129.0708 | 1 | 1.0856 | FALSE | FALSE | FALSE | 125 | FALSE | 0 | Green | Continue normal monitoring.
146610 | HCMEB1Z6240 | B1 Z6 :B1 Z6 :Cable Tray Installation | 26616 | 2013-11-06 16:00 | 2013-11-20 16:00 | 14 | 360 | 100 | 82 | -18 | 9856 | 9856 | 8081.92 | 9764.2214 | 0.82 | 0.82771 | TRUE | TRUE | TRUE | 45 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146611 | HCMEB1Z6250 | B1 Z6 :B1 Z6 :Electrcial Wiring | 26616 | 2013-10-29 10:00 | 2013-11-26 10:00 | 28 | 477 | 100 | 87 | -13 | 30268 | 30268 | 26333.16 | 31057.1513 | 0.87 | 0.84789 | TRUE | TRUE | TRUE | 59.625 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146612 | HCMEB1Z6260 | B1 Z6 :B1 Z6 :Cable Laying | 26616 | 2013-11-20 16:00 | 2013-12-04 16:00 | 14 | 360 | 100 | 95 | -5 | 18760 | 18760 | 17822 | 16466.0855 | 0.95 | 1.0823 | FALSE | FALSE | FALSE | 45 | FALSE | 0 | Green | Continue normal monitoring.
146613 | HCMEB1Z6270 | B1 Z6 :B1 Z6 :Electrical Final Fix for All Systems & Boards (Vertical Elements) | 26616 | 2014-01-15 16:00 | 2014-01-29 16:00 | 14 | 360 | 100 | 89 | -11 | 24514 | 24514 | 21817.46 | 26506.6782 | 0.89 | 0.82309 | TRUE | TRUE | TRUE | 45 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146614 | HCMEB1Z6280 | B1 Z6 :B1 Z6 :Electrical Final Fix for All Systems (Horizantel Elements) | 26616 | 2014-01-29 16:00 | 2014-02-12 16:00 | 14 | 360 | 100 | 83 | -17 | 15330 | 15330 | 12723.9 | 16695.1821 | 0.83 | 0.76213 | TRUE | TRUE | TRUE | 45 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146615 | HCMEB1Z6070 | B1 Z6 :B1 Z6 :All Vertical Piping Works | 26524 | 2013-02-18 08:00 | 2013-03-01 17:00 | 11 | 1271 | 100 | 100 | 0 | 8239 | 8239 | 8239 | 9438.3692 | 1 | 0.87293 | TRUE | FALSE | FALSE | 158.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146616 | HCMEB1Z6080 | B1 Z6 :B1 Z6 :All Horizantal Piping Works | 26524 | 2013-03-04 08:00 | 2013-04-12 17:00 | 39 | 1271 | 100 | 97 | -3 | 53586 | 53586 | 51978.42 | 46173.3391 | 0.97 | 1.1257 | FALSE | FALSE | FALSE | 158.875 | FALSE | 0 | Green | Continue normal monitoring.
146617 | HCMEB1Z6090 | B1 Z6 :B1 Z6 :Mechanical Final Fix | 26524 | 2013-08-19 08:00 | 2013-09-13 17:00 | 25 | 1271 | 100 | 81 | -19 | 49100 | 49100 | 39771 | 52364.9185 | 0.81 | 0.7595 | TRUE | TRUE | TRUE | 158.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146618 | HCMEB1Z6110 | B1 Z6 :B1 Z6 :Horizontal F.F Piping Work | 26587 | 2013-04-15 08:00 | 2013-05-10 17:00 | 25 | 1271 | 100 | 96 | -4 | 17375 | 17375 | 16680 | 15136.4567 | 0.96 | 1.102 | FALSE | FALSE | FALSE | 158.875 | FALSE | 0 | Green | Continue normal monitoring.
146619 | HCMEB1Z6120 | B1 Z6 :B1 Z6 :Fire Hose Cabinets | 26587 | 2013-05-13 08:00 | 2013-05-24 17:00 | 11 | 1271 | 100 | 92 | -8 | 13079 | 13079 | 12032.68 | 14785.2561 | 0.92 | 0.81383 | TRUE | FALSE | FALSE | 158.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146620 | HCMEB1Z6340 | B1 Z6 :B1 Z6 :Sprinklers Final Fix | 26587 | 2013-12-16 16:00 | 2013-12-30 16:00 | 14 | 664 | 100 | 83 | -17 | 22302 | 22302 | 18510.66 | 19453.8382 | 0.83 | 0.95152 | FALSE | TRUE | TRUE | 83 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146621 | HCMEB1Z6350 | B1 Z6 :B1 Z6 :Duct Installation& Dusct Accecories Installation, Fan coil Unit | 26588 | 2013-09-09 16:00 | 2013-09-27 16:00 | 18 | 296 | 100 | 100 | 0 | 20484 | 20484 | 20484 | 24881.7333 | 1 | 0.82325 | TRUE | FALSE | FALSE | 37 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146622 | HCMEB1Z6360 | B1 Z6 :B1 Z6 :Duct Insulation Work | 26588 | 2013-09-27 16:00 | 2013-10-18 16:00 | 21 | 392 | 100 | 100 | 0 | 40362 | 40362 | 40362 | 45642.6826 | 1 | 0.8843 | TRUE | FALSE | FALSE | 49 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146623 | HCMEB1Z6380 | B1 Z6 :B1 Z6 :Exhaust Fans | 26588 | 2013-10-18 16:00 | 2013-11-08 16:00 | 21 | 392 | 100 | 100 | 0 | 24591 | 24591 | 24591 | 25893.2387 | 1 | 0.94971 | FALSE | FALSE | FALSE | 49 | FALSE | 0 | Green | Continue normal monitoring.
146624 | HCMEB1Z6390 | B1 Z6 :B1 Z6 :Grills & Diffusers | 26588 | 2014-01-17 16:00 | 2014-01-31 16:00 | 14 | 392 | 100 | 90 | -10 | 24164 | 24164 | 21747.6 | 24806.8003 | 0.9 | 0.87668 | TRUE | FALSE | FALSE | 49 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146625 | HCMEB1Z6445 | B1 Z6 :B1 Z6 :Mechanical final Fix | 26588 | 2014-01-31 16:00 | 2014-02-14 16:00 | 14 | 392 | 100 | 86 | -14 | 23394 | 23394 | 20118.84 | 21107.6822 | 0.86 | 0.95315 | FALSE | TRUE | TRUE | 49 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146626 | HCMEB1Z6450 | B1 Z6 :B1 Z6 :All Vertical Piping Works | 26589 | 2013-02-18 08:00 | 2013-03-01 17:00 | 11 | 1351 | 100 | 100 | 0 | 21945 | 21945 | 21945 | 21207.6426 | 1 | 1.0348 | FALSE | FALSE | FALSE | 168.875 | FALSE | 0 | Green | Continue normal monitoring.
146627 | HCMEB2Z6455 | B2 Z6 :All Horizantal Piping Works | 26589 | 2013-03-04 08:00 | 2013-04-12 17:00 | 39 | 1351 | 100 | 91 | -9 | 56277 | 56277 | 51212.07 | 67396.4146 | 0.91 | 0.75986 | TRUE | FALSE | FALSE | 168.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146628 | HCMEB2Z6460 | B2 Z6 :Mechanical Final Fix | 26589 | 2013-08-19 08:00 | 2013-09-13 17:00 | 25 | 1351 | 100 | 89 | -11 | 17450 | 17450 | 15530.5 | 21145.5806 | 0.89 | 0.73446 | TRUE | TRUE | TRUE | 168.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146629 | HCMEGFZ1140 | GF Z1 :Blocks Start Date for All Parts | 26622 | 2013-02-26 16:00 | 2013-02-26 16:00 | 1 | 1216 | 100 | 86 | -14 | 1949 | 1949 | 1676.14 | 1657.2329 | 0.86 | 1.0114 | FALSE | TRUE | TRUE | 152 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146630 | HCMEGFZ1150 | GF Z1 :Tiling Finish Date for All Parts | 26622 | 2013-06-10 16:00 | 2013-06-10 16:00 | 1 | 728 | 100 | 92 | -8 | 991 | 991 | 911.72 | 1077.8657 | 0.92 | 0.84586 | TRUE | FALSE | FALSE | 91 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146631 | HCMEGFZ1160 | GF Z1 :Plastering Finish Date for All Parts | 26622 | 2013-05-27 16:00 | 2013-05-27 16:00 | 1 | 1200 | 100 | 100 | 0 | 1395 | 1395 | 1395 | 1587.1197 | 1 | 0.87895 | TRUE | FALSE | FALSE | 150 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146632 | HCMEGFZ1170 | GF Z1 :Gypsum Boards Finish Date for All Parts | 26622 | 2013-12-30 16:00 | 2013-12-30 16:00 | 1 | 976 | 100 | 86 | -14 | 641 | 641 | 551.26 | 703.4967 | 0.86 | 0.7836 | TRUE | TRUE | TRUE | 122 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146633 | HCMEGFZ1200 | GF Z1 :Electrical Coduits & Boards F.F for All Systems | 26622 | 2013-02-26 16:00 | 2013-03-14 16:00 | 16 | 1016 | 100 | 100 | 0 | 29376 | 29376 | 29376 | 25929.3699 | 1 | 1.1329 | FALSE | FALSE | FALSE | 127 | FALSE | 0 | Green | Continue normal monitoring.
146634 | HCMEGFZ1210 | GF Z1 :Electrical Boards Seconed Fix | 26622 | 2013-06-04 16:00 | 2013-06-20 16:00 | 16 | 952 | 100 | 100 | 0 | 10624 | 10624 | 10624 | 9955.6437 | 1 | 1.0671 | FALSE | FALSE | FALSE | 119 | FALSE | 0 | Green | Continue normal monitoring.
146635 | HCMEGFZ1220 | GF Z1 :Cable Tray Installation | 26622 | 2013-11-20 16:00 | 2013-12-04 16:00 | 14 | 0 | 100 | 96 | -4 | 11382 | 11382 | 10926.72 | 10814.4492 | 0.96 | 1.0104 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146636 | HCMEGFZ1230 | GF Z1 :Electrcial Wiring | 26622 | 2013-09-23 08:00 | 2013-10-18 17:00 | 25 | 15 | 100 | 89 | -11 | 13000 | 13000 | 11570 | 15374.9681 | 0.89 | 0.75252 | TRUE | TRUE | TRUE | 1.875 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
146637 | HCMEGFZ1240 | GF Z1 :Cable Laying | 26622 | 2013-12-04 16:00 | 2013-12-24 16:00 | 20 | 0 | 100 | 100 | 0 | 32100 | 32100 | 32100 | 33232.4808 | 1 | 0.96592 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146638 | HCMEGFZ1250 | GF Z1 :Electrical Final Fix for All Systems & Boards (Vertical Elements) | 26622 | 2014-02-04 16:00 | 2014-02-18 16:00 | 14 | 536 | 100 | 89 | -11 | 23156 | 23156 | 20608.84 | 24191.7976 | 0.89 | 0.85189 | TRUE | TRUE | TRUE | 67 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146639 | HCMEGFZ1260 | GF Z1 :Electrical Final Fix for All Systems (Horizantel Elements) | 26622 | 2014-02-18 16:00 | 2014-03-04 16:00 | 14 | 536 | 100 | 100 | 0 | 20762 | 20762 | 20762 | 25411.7998 | 1 | 0.81702 | TRUE | FALSE | FALSE | 67 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146640 | HCMEGFZ1050 | GF Z1 :All Vertical Piping Works | 26530 | 2013-02-27 08:00 | 2013-03-12 17:00 | 13 | 335 | 100 | 83 | -17 | 10452 | 10452 | 8675.16 | 11547.7287 | 0.83 | 0.75124 | TRUE | TRUE | TRUE | 41.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146641 | HCMEGFZ1060 | GF Z1 :All Horizantal Piping Works | 26530 | 2013-03-13 08:00 | 2013-04-23 17:00 | 41 | 335 | 100 | 99 | -1 | 35670 | 35670 | 35313.3 | 43141.6908 | 0.99 | 0.81854 | TRUE | FALSE | FALSE | 41.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146642 | HCMEGFZ1070 | GF Z1 :Mechanical Final Fix | 26530 | 2013-09-16 08:00 | 2013-10-11 17:00 | 25 | 231 | 100 | 83 | -17 | 33800 | 33800 | 28054 | 34901.9997 | 0.83 | 0.80379 | TRUE | TRUE | TRUE | 28.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146643 | HCMEGFZ1080 | GF Z1 :Horizontal F.F Piping Work | 26593 | 2013-02-26 16:00 | 2013-03-26 16:00 | 28 | 1216 | 100 | 100 | 0 | 24724 | 24724 | 24724 | 22493.2648 | 1 | 1.0992 | FALSE | FALSE | FALSE | 152 | FALSE | 0 | Green | Continue normal monitoring.
146644 | HCMEGFZ1090 | GF Z1 :Fire Hose Cabinets | 26593 | 2013-03-26 16:00 | 2013-04-09 16:00 | 14 | 1216 | 100 | 86 | -14 | 13216 | 13216 | 11365.76 | 16149.6115 | 0.86 | 0.70378 | TRUE | TRUE | TRUE | 152 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146645 | HCMEGFZ1100 | GF Z1 :Sprinklers Final Fix | 26593 | 2013-12-30 16:00 | 2014-01-13 16:00 | 14 | 264 | 100 | 100 | 0 | 12936 | 12936 | 12936 | 13369.1238 | 1 | 0.9676 | FALSE | FALSE | FALSE | 33 | FALSE | 0 | Green | Continue normal monitoring.
146646 | HCMEGFZ1310 | GF Z1 :Duct Installation& Dusct Accecories Installation, Fan coil Unit | 26594 | 2013-08-26 16:00 | 2013-09-09 16:00 | 14 | 184 | 100 | 80 | -20 | 9240 | 9240 | 7392 | 8525.3097 | 0.8 | 0.86707 | TRUE | TRUE | TRUE | 23 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146647 | HCMEGFZ1320 | GF Z1 :Duct Insulation Work | 26594 | 2013-09-09 16:00 | 2013-09-30 16:00 | 21 | 184 | 100 | 91 | -9 | 35721 | 35721 | 32506.11 | 34683.6013 | 0.91 | 0.93722 | FALSE | FALSE | FALSE | 23 | FALSE | 0 | Green | Continue normal monitoring.
146648 | HCMEGFZ1330 | GF Z1 :Exhaust Fans | 26594 | 2013-09-30 16:00 | 2013-10-21 16:00 | 21 | 184 | 100 | 100 | 0 | 23688 | 23688 | 23688 | 20616.1647 | 1 | 1.149 | FALSE | FALSE | FALSE | 23 | FALSE | 0 | Green | Continue normal monitoring.
146649 | HCMEGFZ1340 | GF Z1 :Grills & Diffusers | 26594 | 2014-01-28 16:00 | 2014-02-11 16:00 | 14 | 16 | 100 | 92 | -8 | 19516 | 19516 | 17954.72 | 20244.3417 | 0.92 | 0.8869 | TRUE | FALSE | FALSE | 2 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146650 | HCMEGFZ1350 | GF Z1 :Mechanical final Fix | 26594 | 2014-02-13 16:00 | 2014-02-27 16:00 | 14 | 0 | 100 | 89 | -11 | 13846 | 13846 | 12322.94 | 16494.0651 | 0.89 | 0.74711 | TRUE | TRUE | TRUE | 0 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
146651 | HCMEGFZ1360 | GF Z1 :All Vertical Piping Works | 26595 | 2013-02-27 08:00 | 2013-03-12 17:00 | 13 | 335 | 100 | 94 | -6 | 19708 | 19708 | 18525.52 | 24111.4015 | 0.94 | 0.76833 | TRUE | FALSE | FALSE | 41.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146652 | HCMEGFZ1370 | GF Z1 :All Horizantal Piping Works | 26595 | 2013-03-13 08:00 | 2013-04-23 17:00 | 41 | 335 | 100 | 100 | 0 | 33866 | 33866 | 33866 | 41419.5025 | 1 | 0.81763 | TRUE | FALSE | FALSE | 41.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146653 | HCMEGFZ1380 | GF Z1 :Mechanical Final Fix | 26595 | 2013-09-16 08:00 | 2013-10-11 17:00 | 25 | 231 | 100 | 92 | -8 | 27425 | 27425 | 25231 | 24685.0234 | 0.92 | 1.0221 | FALSE | FALSE | FALSE | 28.875 | FALSE | 0 | Green | Continue normal monitoring.
146654 | HCMEGFZ2145 | GF Z2 :Blocks Start Date for All Parts | 26628 | 2013-03-16 16:00 | 2013-03-16 16:00 | 1 | 1184 | 100 | 100 | 0 | 1514 | 1514 | 1514 | 1518.2718 | 1 | 0.99719 | FALSE | FALSE | FALSE | 148 | FALSE | 0 | Green | Continue normal monitoring.
146655 | HCMEGFZ2155 | GF Z2 :Tiling Finish Date for All Parts | 26628 | 2013-05-16 16:00 | 2013-05-16 16:00 | 1 | 896 | 100 | 100 | 0 | 788 | 788 | 788 | 678.6977 | 1 | 1.161 | FALSE | FALSE | FALSE | 112 | FALSE | 0 | Green | Continue normal monitoring.
146656 | HCMEGFZ2165 | GF Z2 :Plastering Finish Date for All Parts | 26628 | 2013-04-13 16:00 | 2013-04-13 16:00 | 1 | 1577 | 100 | 100 | 0 | 1092 | 1092 | 1092 | 1301.7362 | 1 | 0.83888 | TRUE | FALSE | FALSE | 197.125 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146657 | HCMEGFZ2175 | GF Z2 :Gypsum Boards Finish Date for All Parts | 26628 | 2013-12-29 16:00 | 2013-12-29 16:00 | 1 | 984 | 100 | 100 | 0 | 1072 | 1072 | 1072 | 1065.0345 | 1 | 1.0065 | FALSE | FALSE | FALSE | 123 | FALSE | 0 | Green | Continue normal monitoring.
146658 | HCMEGFZ2205 | GF Z2 :Electrical Coduits & Boards F.F for All Systems | 26628 | 2013-03-18 08:00 | 2013-04-02 17:00 | 15 | 983 | 100 | 100 | 0 | 28155 | 28155 | 28155 | 31039.39 | 1 | 0.90707 | FALSE | FALSE | FALSE | 122.875 | FALSE | 0 | Green | Continue normal monitoring.
146659 | HCMEGFZ2215 | GF Z2 :Electrical Boards Seconed Fix | 26628 | 2013-06-14 16:00 | 2013-07-02 16:00 | 18 | 960 | 100 | 100 | 0 | 9486 | 9486 | 9486 | 10775.7106 | 1 | 0.88031 | TRUE | FALSE | FALSE | 120 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146660 | HCMEGFZ2225 | GF Z2 :Cable Tray Installation | 26628 | 2013-11-20 16:00 | 2013-12-04 16:00 | 14 | 88 | 100 | 88 | -12 | 20342 | 20342 | 17900.96 | 20788.2601 | 0.88 | 0.86111 | TRUE | TRUE | TRUE | 11 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146661 | HCMEGFZ2235 | GF Z2 :Electrcial Wiring | 26628 | 2013-08-19 08:00 | 2013-09-13 17:00 | 25 | 215 | 100 | 100 | 0 | 13550 | 13550 | 13550 | 13178.4175 | 1 | 1.0282 | FALSE | FALSE | FALSE | 26.875 | FALSE | 0 | Green | Continue normal monitoring.
146662 | HCMEGFZ2245 | GF Z2 :Cable Laying | 26628 | 2013-12-04 16:00 | 2013-12-18 16:00 | 14 | 88 | 100 | 88 | -12 | 12908 | 12908 | 11359.04 | 15939.8977 | 0.88 | 0.71262 | TRUE | TRUE | TRUE | 11 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146663 | HCMEGFZ2255 | GF Z2 :Electrical Final Fix for All Systems & Boards (Vertical Elements) | 26628 | 2014-01-29 16:00 | 2014-02-12 16:00 | 14 | 568 | 100 | 94 | -6 | 9464 | 9464 | 8896.16 | 11695.5666 | 0.94 | 0.76064 | TRUE | FALSE | FALSE | 71 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146664 | HCMEGFZ2265 | GF Z2 :Electrical Final Fix for All Systems (Horizantel Elements) | 26628 | 2014-02-12 16:00 | 2014-02-26 16:00 | 14 | 568 | 100 | 89 | -11 | 14392 | 14392 | 12808.88 | 13899.4273 | 0.89 | 0.92154 | FALSE | TRUE | TRUE | 71 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146665 | HCMEGFZ2055 | GF Z2 :All Vertical Piping Works | 26531 | 2013-02-27 08:00 | 2013-03-12 17:00 | 13 | 495 | 100 | 100 | 0 | 19045 | 19045 | 19045 | 19842.034 | 1 | 0.95983 | FALSE | FALSE | FALSE | 61.875 | FALSE | 0 | Green | Continue normal monitoring.
146666 | HCMEGFZ2065 | GF Z2 :All Horizantal Piping Works | 26531 | 2013-03-13 08:00 | 2013-04-23 17:00 | 41 | 495 | 100 | 100 | 0 | 28577 | 28577 | 28577 | 35410.837 | 1 | 0.80701 | TRUE | FALSE | FALSE | 61.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146667 | HCMEGFZ2075 | GF Z2 :Mechanical Final Fix | 26531 | 2013-09-16 08:00 | 2013-10-11 17:00 | 25 | 391 | 100 | 100 | 0 | 27725 | 27725 | 27725 | 23620.2406 | 1 | 1.1738 | FALSE | FALSE | FALSE | 48.875 | FALSE | 0 | Green | Continue normal monitoring.
146668 | HCMEGFZ2085 | GF Z2 :Horizontal F.F Piping Work | 26599 | 2013-03-18 08:00 | 2013-04-12 17:00 | 25 | 1191 | 100 | 100 | 0 | 33525 | 33525 | 33525 | 34030.2653 | 1 | 0.98515 | FALSE | FALSE | FALSE | 148.875 | FALSE | 0 | Green | Continue normal monitoring.
146669 | HCMEGFZ2095 | GF Z2 :Fire Hose Cabinets | 26599 | 2013-04-15 08:00 | 2013-04-26 17:00 | 11 | 1191 | 100 | 89 | -11 | 14872 | 14872 | 13236.08 | 13238.8019 | 0.89 | 0.99979 | FALSE | TRUE | TRUE | 148.875 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146670 | HCMEGFZ2105 | GF Z2 :Sprinklers Final Fix | 26599 | 2013-12-30 16:00 | 2014-01-13 16:00 | 14 | 344 | 100 | 87 | -13 | 7294 | 7294 | 6345.78 | 7685.4193 | 0.87 | 0.82569 | TRUE | TRUE | TRUE | 43 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146671 | HCMEGFZ2315 | GF Z2 :Duct Installation& Dusct Accecories Installation, Fan coil Unit | 26600 | 2013-08-26 16:00 | 2013-09-05 16:00 | 10 | 185 | 100 | 100 | 0 | 16350 | 16350 | 16350 | 14058.8415 | 1 | 1.163 | FALSE | FALSE | FALSE | 23.125 | FALSE | 0 | Green | Continue normal monitoring.
146672 | HCMEGFZ2325 | GF Z2 :Duct Insulation Work | 26600 | 2013-09-05 16:00 | 2013-09-26 16:00 | 21 | 185 | 100 | 95 | -5 | 33180 | 33180 | 31521 | 33603.356 | 0.95 | 0.93803 | FALSE | FALSE | FALSE | 23.125 | FALSE | 0 | Green | Continue normal monitoring.
146673 | HCMEGFZ2335 | GF Z2 :Exhaust Fans | 26600 | 2013-09-26 16:00 | 2013-10-17 16:00 | 21 | 185 | 100 | 96 | -4 | 33369 | 33369 | 32034.24 | 31309.453 | 0.96 | 1.0231 | FALSE | FALSE | FALSE | 23.125 | FALSE | 0 | Green | Continue normal monitoring.
146674 | HCMEGFZ2345 | GF Z2 :Grills & Diffusers | 26600 | 2014-01-23 16:00 | 2014-02-06 16:00 | 14 | 25 | 100 | 100 | 0 | 18774 | 18774 | 18774 | 19962.8325 | 1 | 0.94045 | FALSE | FALSE | FALSE | 3.125 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146675 | HCMEGFZ2355 | GF Z2 :Mechanical final Fix | 26600 | 2014-02-06 16:00 | 2014-02-20 16:00 | 14 | 25 | 100 | 100 | 0 | 8358 | 8358 | 8358 | 10434.106 | 1 | 0.80103 | TRUE | FALSE | FALSE | 3.125 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146676 | HCMEGFZ2365 | GF Z2 :All Vertical Piping Works | 26601 | 2013-02-27 08:00 | 2013-03-12 17:00 | 13 | 495 | 100 | 84 | -16 | 21671 | 21671 | 18203.64 | 25359.7172 | 0.84 | 0.71782 | TRUE | TRUE | TRUE | 61.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146677 | HCMEGFZ2375 | GF Z2 :All Horizantal Piping Works | 26601 | 2013-03-13 08:00 | 2013-04-23 17:00 | 41 | 495 | 100 | 83 | -17 | 38294 | 38294 | 31784.02 | 45503.1073 | 0.83 | 0.6985 | TRUE | TRUE | TRUE | 61.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146678 | HCMEGFZ2385 | GF Z2 :Mechanical Final Fix | 26601 | 2013-09-16 08:00 | 2013-10-11 17:00 | 25 | 391 | 100 | 97 | -3 | 28400 | 28400 | 27548 | 31356.6103 | 0.97 | 0.87854 | TRUE | FALSE | FALSE | 48.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146679 | HCMEGFZ3150 | GF Z3 :Blocks Start Date for All Parts | 26634 | 2013-06-27 16:00 | 2013-06-27 16:00 | 1 | 577 | 100 | 100 | 0 | 1609 | 1609 | 1609 | 1394.3979 | 1 | 1.1539 | FALSE | FALSE | FALSE | 72.125 | FALSE | 0 | Green | Continue normal monitoring.
146680 | HCMEGFZ3160 | GF Z3 :Tiling Finish Date for All Parts | 26634 | 2013-10-05 16:00 | 2013-10-05 16:00 | 1 | 912 | 100 | 98 | -2 | 1087 | 1087 | 1065.26 | 1013.8656 | 0.98 | 1.0507 | FALSE | FALSE | FALSE | 114 | FALSE | 0 | Green | Continue normal monitoring.
146681 | HCMEGFZ3170 | GF Z3 :Plastering Finish Date for All Parts | 26634 | 2013-07-25 16:00 | 2013-07-25 16:00 | 1 | 984 | 100 | 83 | -17 | 843 | 843 | 699.69 | 1028.4818 | 0.83 | 0.68031 | TRUE | TRUE | TRUE | 123 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146682 | HCMEGFZ3180 | GF Z3 :Gypsum Boards Finish Date for All Parts | 26634 | 2013-12-29 16:00 | 2013-12-29 16:00 | 1 | 984 | 100 | 100 | 0 | 1817 | 1817 | 1817 | 1810.541 | 1 | 1.0036 | FALSE | FALSE | FALSE | 123 | FALSE | 0 | Green | Continue normal monitoring.
146683 | HCMEGFZ3210 | GF Z3 :Electrical Coduits & Boards F.F for All Systems | 26634 | 2013-06-27 16:00 | 2013-07-15 16:00 | 18 | 488 | 100 | 86 | -14 | 19260 | 19260 | 16563.6 | 17169.4173 | 0.86 | 0.96472 | FALSE | TRUE | TRUE | 61 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146684 | HCMEGFZ3220 | GF Z3 :Electrical Boards Seconed Fix | 26634 | 2013-09-23 16:00 | 2013-10-09 16:00 | 16 | 488 | 100 | 89 | -11 | 17760 | 17760 | 15806.4 | 20085.8877 | 0.89 | 0.78694 | TRUE | TRUE | TRUE | 61 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146685 | HCMEGFZ3230 | GF Z3 :Cable Tray Installation | 26634 | 2013-11-20 16:00 | 2013-12-04 16:00 | 14 | 168 | 100 | 100 | 0 | 10388 | 10388 | 10388 | 10074.1067 | 1 | 1.0312 | FALSE | FALSE | FALSE | 21 | FALSE | 0 | Green | Continue normal monitoring.
146686 | HCMEGFZ3240 | GF Z3 :Electrcial Wiring | 26634 | 2013-12-26 16:00 | 2014-01-03 16:00 | 8 | 296 | 100 | 97 | -3 | 8480 | 8480 | 8225.6 | 8119.9626 | 0.97 | 1.013 | FALSE | FALSE | FALSE | 37 | FALSE | 0 | Green | Continue normal monitoring.
146687 | HCMEGFZ3250 | GF Z3 :Cable Laying | 26634 | 2013-12-04 16:00 | 2013-12-18 16:00 | 14 | 168 | 100 | 98 | -2 | 20426 | 20426 | 20017.48 | 25515.975 | 0.98 | 0.78451 | TRUE | FALSE | FALSE | 21 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146688 | HCMEGFZ3260 | GF Z3 :Electrical Final Fix for All Systems & Boards (Vertical Elements) | 26634 | 2014-02-04 16:00 | 2014-02-18 16:00 | 14 | 536 | 100 | 83 | -17 | 7434 | 7434 | 6170.22 | 8870.6619 | 0.83 | 0.69558 | TRUE | TRUE | TRUE | 67 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146689 | HCMEGFZ3270 | GF Z3 :Electrical Final Fix for All Systems (Horizantel Elements) | 26634 | 2014-02-18 16:00 | 2014-03-04 16:00 | 14 | 536 | 100 | 89 | -11 | 12460 | 12460 | 11089.4 | 12624.1621 | 0.89 | 0.87843 | TRUE | TRUE | TRUE | 67 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146690 | HCMEGFZ3060 | GF Z3 :All Vertical Piping Works | 26537 | 2013-02-27 08:00 | 2013-03-12 17:00 | 13 | 495 | 100 | 80 | -20 | 10088 | 10088 | 8070.4 | 12530.35 | 0.8 | 0.64407 | TRUE | TRUE | TRUE | 61.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146691 | HCMEGFZ3070 | GF Z3 :All Horizantal Piping Works | 26537 | 2013-03-13 08:00 | 2013-04-23 17:00 | 41 | 495 | 100 | 100 | 0 | 42271 | 42271 | 42271 | 46922.7244 | 1 | 0.90086 | FALSE | FALSE | FALSE | 61.875 | FALSE | 0 | Green | Continue normal monitoring.
146692 | HCMEGFZ3080 | GF Z3 :Mechanical Final Fix | 26537 | 2013-09-16 08:00 | 2013-10-11 17:00 | 25 | 391 | 100 | 97 | -3 | 41925 | 41925 | 40667.25 | 48079.9665 | 0.97 | 0.84583 | TRUE | FALSE | FALSE | 48.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146693 | HCMEGFZ3090 | GF Z3 :Horizontal F.F Piping Work | 26605 | 2013-06-27 16:00 | 2013-07-25 16:00 | 28 | 600 | 100 | 84 | -16 | 24696 | 24696 | 20744.64 | 21302.8984 | 0.84 | 0.97379 | FALSE | TRUE | TRUE | 75 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146694 | HCMEGFZ3100 | GF Z3 :Fire Hose Cabinets | 26605 | 2013-07-25 16:00 | 2013-08-08 16:00 | 14 | 600 | 100 | 94 | -6 | 22274 | 22274 | 20937.56 | 20016.3542 | 0.94 | 1.046 | FALSE | FALSE | FALSE | 75 | FALSE | 0 | Green | Continue normal monitoring.
146695 | HCMEGFZ3110 | GF Z3 :Sprinklers Final Fix | 26605 | 2013-12-30 16:00 | 2014-01-13 16:00 | 14 | 344 | 100 | 96 | -4 | 19362 | 19362 | 18587.52 | 21360.8177 | 0.96 | 0.87017 | TRUE | FALSE | FALSE | 43 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146696 | HCMEGFZ3320 | GF Z3 :Duct Installation& Dusct Accecories Installation, Fan coil Unit | 26606 | 2013-09-05 16:00 | 2013-09-17 16:00 | 12 | 216 | 100 | 82 | -18 | 8556 | 8556 | 7015.92 | 10349.4197 | 0.82 | 0.6779 | TRUE | TRUE | TRUE | 27 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146697 | HCMEGFZ3330 | GF Z3 :Duct Insulation Work | 26606 | 2013-09-17 16:00 | 2013-10-08 16:00 | 21 | 216 | 100 | 91 | -9 | 18375 | 18375 | 16721.25 | 20203.2664 | 0.91 | 0.82765 | TRUE | FALSE | FALSE | 27 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146698 | HCMEGFZ3340 | GF Z3 :Exhaust Fans | 26606 | 2013-10-08 16:00 | 2013-10-29 16:00 | 21 | 216 | 100 | 81 | -19 | 26103 | 26103 | 21143.43 | 23586.9307 | 0.81 | 0.8964 | TRUE | TRUE | TRUE | 27 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146699 | HCMEGFZ3350 | GF Z3 :Grills & Diffusers | 26606 | 2014-01-23 16:00 | 2014-02-06 16:00 | 14 | 120 | 100 | 80 | -20 | 9968 | 9968 | 7974.4 | 8934.3585 | 0.8 | 0.89255 | TRUE | TRUE | TRUE | 15 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146700 | HCMEGFZ3360 | GF Z3 :Mechanical final Fix | 26606 | 2014-02-06 16:00 | 2014-02-20 16:00 | 14 | 120 | 100 | 100 | 0 | 8092 | 8092 | 8092 | 9610.6609 | 1 | 0.84198 | TRUE | FALSE | FALSE | 15 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146701 | HCMEGFZ3370 | GF Z3 :All Vertical Piping Works | 26607 | 2013-02-27 08:00 | 2013-03-12 17:00 | 13 | 495 | 100 | 100 | 0 | 14651 | 14651 | 14651 | 13269.7174 | 1 | 1.1041 | FALSE | FALSE | FALSE | 61.875 | FALSE | 0 | Green | Continue normal monitoring.
146702 | HCMEGFZ3380 | GF Z3 :All Horizantal Piping Works | 26607 | 2013-03-13 08:00 | 2013-04-23 17:00 | 41 | 495 | 100 | 96 | -4 | 45223 | 45223 | 43414.08 | 47850.13 | 0.96 | 0.90729 | FALSE | FALSE | FALSE | 61.875 | FALSE | 0 | Green | Continue normal monitoring.
146703 | HCMEGFZ3390 | GF Z3 :Mechanical Final Fix | 26607 | 2013-09-16 08:00 | 2013-10-11 17:00 | 25 | 391 | 100 | 100 | 0 | 32025 | 32025 | 32025 | 27696.6716 | 1 | 1.1563 | FALSE | FALSE | FALSE | 48.875 | FALSE | 0 | Green | Continue normal monitoring.
146704 | HCMEF1Z1145 | F1 Z1 :Blocks Start Date for All Parts | 26617 | 2013-03-12 16:00 | 2013-03-12 16:00 | 1 | 1240 | 100 | 95 | -5 | 1904 | 1904 | 1808.8 | 1679.8381 | 0.95 | 1.0768 | FALSE | FALSE | FALSE | 155 | FALSE | 0 | Green | Continue normal monitoring.
146705 | HCMEF1Z1155 | F1 Z1 :Tiling Finish Date for All Parts | 26617 | 2013-07-10 12:00 | 2013-07-10 12:00 | 1 | 715 | 100 | 84 | -16 | 1500 | 1500 | 1260 | 1678.409 | 0.84 | 0.75071 | TRUE | TRUE | TRUE | 89.375 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146706 | HCMEF1Z1165 | F1 Z1 :Plastering Finish Date for All Parts | 26617 | 2013-04-27 16:00 | 2013-04-27 16:00 | 1 | 1512 | 100 | 94 | -6 | 1179 | 1179 | 1108.26 | 1327.168 | 0.94 | 0.83506 | TRUE | FALSE | FALSE | 189 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146707 | HCMEF1Z1175 | F1 Z1 :Gypsum Boards Finish Date for All Parts | 26617 | 2014-01-18 16:00 | 2014-01-18 16:00 | 1 | 856 | 100 | 82 | -18 | 557 | 557 | 456.74 | 549.5294 | 0.82 | 0.83115 | TRUE | TRUE | TRUE | 107 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146708 | HCMEF1Z1205 | F1 Z1 :Electrical Coduits & Boards F.F for All Systems | 26617 | 2013-03-12 16:00 | 2013-03-28 16:00 | 16 | 1032 | 100 | 100 | 0 | 24784 | 24784 | 24784 | 23203.869 | 1 | 1.0681 | FALSE | FALSE | FALSE | 129 | FALSE | 0 | Green | Continue normal monitoring.
146709 | HCMEF1Z1215 | F1 Z1 :Electrical Boards Seconed Fix | 26617 | 2013-06-20 16:00 | 2013-07-08 16:00 | 18 | 952 | 100 | 86 | -14 | 24840 | 24840 | 21362.4 | 29199.0253 | 0.86 | 0.73161 | TRUE | TRUE | TRUE | 119 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146710 | HCMEF1Z1225 | F1 Z1 :Cable Tray Installation | 26617 | 2013-12-04 16:00 | 2013-12-18 16:00 | 14 | 0 | 100 | 90 | -10 | 13244 | 13244 | 11919.6 | 12407.5261 | 0.9 | 0.96067 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146711 | HCMEF1Z1235 | F1 Z1 :Electrcial Wiring | 26617 | 2013-10-21 08:00 | 2013-11-15 17:00 | 25 | 15 | 100 | 89 | -11 | 14125 | 14125 | 12571.25 | 15068.7029 | 0.89 | 0.83426 | TRUE | TRUE | TRUE | 1.875 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
146712 | HCMEF1Z1245 | F1 Z1 :Cable Laying | 26617 | 2013-12-24 16:00 | 2014-01-07 16:00 | 14 | 0 | 100 | 88 | -12 | 24878 | 24878 | 21892.64 | 30781.1398 | 0.88 | 0.71124 | TRUE | TRUE | TRUE | 0 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
146713 | HCMEF1Z1255 | F1 Z1 :Electrical Final Fix for All Systems & Boards (Vertical Elements) | 26617 | 2014-02-18 16:00 | 2014-03-04 16:00 | 14 | 456 | 100 | 93 | -7 | 21938 | 21938 | 20402.34 | 19944.7347 | 0.93 | 1.0229 | FALSE | FALSE | FALSE | 57 | FALSE | 0 | Green | Continue normal monitoring.
146714 | HCMEF1Z1265 | F1 Z1 :Electrical Final Fix for All Systems (Horizantel Elements) | 26617 | 2014-03-04 16:00 | 2014-03-18 16:00 | 14 | 456 | 100 | 92 | -8 | 22680 | 22680 | 20865.6 | 27813.6295 | 0.92 | 0.75019 | TRUE | FALSE | FALSE | 57 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146715 | HCMEF1Z1055 | F1 Z1 :All Vertical Piping Works | 26558 | 2013-03-13 08:00 | 2013-03-26 17:00 | 13 | 415 | 100 | 100 | 0 | 19643 | 19643 | 19643 | 18133.5773 | 1 | 1.0832 | FALSE | FALSE | FALSE | 51.875 | FALSE | 0 | Green | Continue normal monitoring.
146716 | HCMEF1Z1065 | F1 Z1 :All Horizantal Piping Works | 26558 | 2013-03-27 08:00 | 2013-05-07 17:00 | 41 | 415 | 100 | 100 | 0 | 29766 | 29766 | 29766 | 32057.3058 | 1 | 0.92852 | FALSE | FALSE | FALSE | 51.875 | FALSE | 0 | Green | Continue normal monitoring.
146717 | HCMEF1Z1075 | F1 Z1 :Mechanical Final Fix | 26558 | 2013-10-14 08:00 | 2013-11-08 17:00 | 25 | 231 | 100 | 100 | 0 | 31825 | 31825 | 31825 | 31850.5582 | 1 | 0.9992 | FALSE | FALSE | FALSE | 28.875 | FALSE | 0 | Green | Continue normal monitoring.
146718 | HCMEF1Z1085 | F1 Z1 :Horizontal F.F Piping Work | 26618 | 2013-03-12 16:00 | 2013-04-09 16:00 | 28 | 1216 | 100 | 100 | 0 | 32984 | 32984 | 32984 | 40767.282 | 1 | 0.80908 | TRUE | FALSE | FALSE | 152 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146719 | HCMEF1Z1095 | F1 Z1 :Fire Hose Cabinets | 26618 | 2013-04-09 16:00 | 2013-04-23 16:00 | 14 | 1216 | 100 | 81 | -19 | 27426 | 27426 | 22215.06 | 26312.9655 | 0.81 | 0.84426 | TRUE | TRUE | TRUE | 152 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146720 | HCMEF1Z1105 | F1 Z1 :Sprinklers Final Fix | 26618 | 2014-01-13 16:00 | 2014-01-27 16:00 | 14 | 264 | 100 | 82 | -18 | 15400 | 15400 | 12628 | 15551.8933 | 0.82 | 0.81199 | TRUE | TRUE | TRUE | 33 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146721 | HCMEF1Z1315 | F1 Z1 :Duct Installation& Dusct Accecories Installation, Fan coil Unit | 26619 | 2013-09-09 16:00 | 2013-09-23 16:00 | 14 | 184 | 100 | 86 | -14 | 12292 | 12292 | 10571.12 | 15280.7266 | 0.86 | 0.69179 | TRUE | TRUE | TRUE | 23 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146722 | HCMEF1Z1325 | F1 Z1 :Duct Insulation Work | 26619 | 2013-09-23 16:00 | 2013-10-14 16:00 | 21 | 184 | 100 | 100 | 0 | 35721 | 35721 | 35721 | 38028.1535 | 1 | 0.93933 | FALSE | FALSE | FALSE | 23 | FALSE | 0 | Green | Continue normal monitoring.
146723 | HCMEF1Z1335 | F1 Z1 :Exhaust Fans | 26619 | 2013-10-14 16:00 | 2013-11-04 16:00 | 21 | 184 | 100 | 97 | -3 | 40950 | 40950 | 39721.5 | 43040.5813 | 0.97 | 0.92288 | FALSE | FALSE | FALSE | 23 | FALSE | 0 | Green | Continue normal monitoring.
146724 | HCMEF1Z1345 | F1 Z1 :Grills & Diffusers | 26619 | 2014-02-11 16:00 | 2014-02-25 16:00 | 14 | 16 | 100 | 82 | -18 | 16912 | 16912 | 13867.84 | 16119.0199 | 0.82 | 0.86034 | TRUE | TRUE | TRUE | 2 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
146725 | HCMEF1Z1355 | F1 Z1 :Mechanical final Fix | 26619 | 2014-02-27 16:00 | 2014-03-13 16:00 | 14 | 0 | 100 | 89 | -11 | 11284 | 11284 | 10042.76 | 12757.0746 | 0.89 | 0.78723 | TRUE | TRUE | TRUE | 0 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
146726 | HCMEF1Z1365 | F1 Z1 :All Vertical Piping Works | 26620 | 2013-03-13 08:00 | 2013-03-26 17:00 | 13 | 415 | 100 | 100 | 0 | 16614 | 16614 | 16614 | 14217.4169 | 1 | 1.1686 | FALSE | FALSE | FALSE | 51.875 | FALSE | 0 | Green | Continue normal monitoring.
146727 | HCMEF1Z1375 | F1 Z1 :All Horizantal Piping Works | 26620 | 2013-03-27 08:00 | 2013-05-07 17:00 | 41 | 415 | 100 | 100 | 0 | 41123 | 41123 | 41123 | 35768.9931 | 1 | 1.1497 | FALSE | FALSE | FALSE | 51.875 | FALSE | 0 | Green | Continue normal monitoring.
146728 | HCMEF1Z1385 | F1 Z1 :Mechanical Final Fix | 26620 | 2013-10-14 08:00 | 2013-11-08 17:00 | 25 | 231 | 100 | 86 | -14 | 19175 | 19175 | 16490.5 | 20895.8304 | 0.86 | 0.78918 | TRUE | TRUE | TRUE | 28.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146729 | HCMEF1Z2150 | F1 Z2 :Blocks Start Date for All Parts | 26623 | 2013-05-08 16:00 | 2013-05-08 16:00 | 1 | 921 | 100 | 88 | -12 | 507 | 507 | 446.16 | 500.2416 | 0.88 | 0.89189 | TRUE | TRUE | TRUE | 115.125 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146730 | HCMEF1Z2160 | F1 Z2 :Tiling Finish Date for All Parts | 26623 | 2013-07-18 16:00 | 2013-07-18 16:00 | 1 | 656 | 100 | 96 | -4 | 1007 | 1007 | 966.72 | 1239.9458 | 0.96 | 0.77965 | TRUE | FALSE | FALSE | 82 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146731 | HCMEF1Z2170 | F1 Z2 :Plastering Finish Date for All Parts | 26623 | 2013-06-06 16:00 | 2013-06-06 16:00 | 1 | 1320 | 100 | 90 | -10 | 975 | 975 | 877.5 | 1180.9944 | 0.9 | 0.74302 | TRUE | FALSE | FALSE | 165 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146732 | HCMEF1Z2180 | F1 Z2 :Gypsum Boards Finish Date for All Parts | 26623 | 2014-01-16 16:00 | 2014-01-16 16:00 | 1 | 864 | 100 | 86 | -14 | 1820 | 1820 | 1565.2 | 2066.5782 | 0.86 | 0.75739 | TRUE | TRUE | TRUE | 108 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146733 | HCMEF1Z2210 | F1 Z2 :Electrical Coduits & Boards F.F for All Systems | 26623 | 2013-05-08 16:00 | 2013-05-24 16:00 | 16 | 776 | 100 | 100 | 0 | 10608 | 10608 | 10608 | 12488.3553 | 1 | 0.84943 | TRUE | FALSE | FALSE | 97 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146734 | HCMEF1Z2220 | F1 Z2 :Electrical Boards Seconed Fix | 26623 | 2013-08-02 16:00 | 2013-08-20 16:00 | 18 | 776 | 100 | 100 | 0 | 17712 | 17712 | 17712 | 19783.1127 | 1 | 0.89531 | TRUE | FALSE | FALSE | 97 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146735 | HCMEF1Z2230 | F1 Z2 :Cable Tray Installation | 26623 | 2013-12-04 16:00 | 2013-12-18 16:00 | 14 | 88 | 100 | 93 | -7 | 22330 | 22330 | 20766.9 | 20102.1993 | 0.93 | 1.0331 | FALSE | FALSE | FALSE | 11 | FALSE | 0 | Green | Continue normal monitoring.
146736 | HCMEF1Z2240 | F1 Z2 :Electrcial Wiring | 26623 | 2013-09-16 08:00 | 2013-10-11 17:00 | 25 | 215 | 100 | 98 | -2 | 26650 | 26650 | 26117 | 30813.1923 | 0.98 | 0.84759 | TRUE | FALSE | FALSE | 26.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146737 | HCMEF1Z2250 | F1 Z2 :Cable Laying | 26623 | 2013-12-18 16:00 | 2014-01-01 16:00 | 14 | 88 | 100 | 83 | -17 | 19656 | 19656 | 16314.48 | 18360.2133 | 0.83 | 0.88858 | TRUE | TRUE | TRUE | 11 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146738 | HCMEF1Z2260 | F1 Z2 :Electrical Final Fix for All Systems & Boards (Vertical Elements) | 26623 | 2014-02-12 16:00 | 2014-02-26 16:00 | 14 | 488 | 100 | 100 | 0 | 14812 | 14812 | 14812 | 14506.5342 | 1 | 1.0211 | FALSE | FALSE | FALSE | 61 | FALSE | 0 | Green | Continue normal monitoring.
146739 | HCMEF1Z2270 | F1 Z2 :Electrical Final Fix for All Systems (Horizantel Elements) | 26623 | 2014-02-26 16:00 | 2014-03-12 16:00 | 14 | 488 | 100 | 85 | -15 | 10318 | 10318 | 8770.3 | 12151.4434 | 0.85 | 0.72175 | TRUE | TRUE | TRUE | 61 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146740 | HCMEF1Z2060 | F1 Z2 :All Vertical Piping Works | 26559 | 2013-03-13 08:00 | 2013-03-26 17:00 | 13 | 575 | 100 | 89 | -11 | 21151 | 21151 | 18824.39 | 22517.5713 | 0.89 | 0.83599 | TRUE | TRUE | TRUE | 71.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146741 | HCMEF1Z2070 | F1 Z2 :All Horizantal Piping Works | 26559 | 2013-03-27 08:00 | 2013-05-07 17:00 | 41 | 575 | 100 | 86 | -14 | 71053 | 71053 | 61105.58 | 84835.597 | 0.86 | 0.72028 | TRUE | TRUE | TRUE | 71.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146742 | HCMEF1Z2080 | F1 Z2 :Mechanical Final Fix | 26559 | 2013-10-14 08:00 | 2013-11-08 17:00 | 25 | 391 | 100 | 92 | -8 | 26325 | 26325 | 24219 | 24619.5119 | 0.92 | 0.98373 | FALSE | FALSE | FALSE | 48.875 | FALSE | 0 | Green | Continue normal monitoring.
146743 | HCMEF1Z2090 | F1 Z2 :Horizontal F.F Piping Work | 26624 | 2013-05-08 16:00 | 2013-06-05 16:00 | 28 | 968 | 100 | 93 | -7 | 37156 | 37156 | 34555.08 | 40615.6463 | 0.93 | 0.85078 | TRUE | FALSE | FALSE | 121 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146744 | HCMEF1Z2100 | F1 Z2 :Fire Hose Cabinets | 26624 | 2013-06-05 16:00 | 2013-06-19 16:00 | 14 | 968 | 100 | 83 | -17 | 13538 | 13538 | 11236.54 | 11961.0449 | 0.83 | 0.93943 | FALSE | TRUE | TRUE | 121 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146745 | HCMEF1Z2110 | F1 Z2 :Sprinklers Final Fix | 26624 | 2014-01-13 16:00 | 2014-01-27 16:00 | 14 | 344 | 100 | 87 | -13 | 27678 | 27678 | 24079.86 | 30645.7569 | 0.87 | 0.78575 | TRUE | TRUE | TRUE | 43 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146746 | HCMEF1Z2320 | F1 Z2 :Duct Installation& Dusct Accecories Installation, Fan coil Unit | 26625 | 2013-09-05 16:00 | 2013-09-17 16:00 | 12 | 201 | 100 | 84 | -16 | 21492 | 21492 | 18053.28 | 24823.5526 | 0.84 | 0.72726 | TRUE | TRUE | TRUE | 25.125 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146747 | HCMEF1Z2330 | F1 Z2 :Duct Insulation Work | 26625 | 2013-09-17 16:00 | 2013-10-08 16:00 | 21 | 201 | 100 | 80 | -20 | 18585 | 18585 | 14868 | 20145.6263 | 0.8 | 0.73803 | TRUE | TRUE | TRUE | 25.125 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146748 | HCMEF1Z2340 | F1 Z2 :Exhaust Fans | 26625 | 2013-10-08 16:00 | 2013-10-29 16:00 | 21 | 201 | 100 | 83 | -17 | 26754 | 26754 | 22205.82 | 25590.003 | 0.83 | 0.86775 | TRUE | TRUE | TRUE | 25.125 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146749 | HCMEF1Z2350 | F1 Z2 :Grills & Diffusers | 26625 | 2014-02-06 16:00 | 2014-02-20 16:00 | 14 | 25 | 100 | 82 | -18 | 18858 | 18858 | 15463.56 | 16265.724 | 0.82 | 0.95068 | FALSE | TRUE | TRUE | 3.125 | TRUE | 4 | Orange | Develop recovery plan and review schedule and cost exposure.
146750 | HCMEF1Z2360 | F1 Z2 :Mechanical final Fix | 26625 | 2014-02-20 16:00 | 2014-03-06 16:00 | 14 | 25 | 100 | 88 | -12 | 12404 | 12404 | 10915.52 | 11136.0576 | 0.88 | 0.9802 | FALSE | TRUE | TRUE | 3.125 | TRUE | 4 | Orange | Develop recovery plan and review schedule and cost exposure.
146751 | HCMEF1Z2370 | F1 Z2 :All Vertical Piping Works | 26626 | 2013-03-13 08:00 | 2013-03-26 17:00 | 13 | 575 | 100 | 87 | -13 | 17888 | 17888 | 15562.56 | 19657.5023 | 0.87 | 0.79169 | TRUE | TRUE | TRUE | 71.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146752 | HCMEF1Z2380 | F1 Z2 :All Horizantal Piping Works | 26626 | 2013-03-27 08:00 | 2013-05-07 17:00 | 41 | 575 | 100 | 80 | -20 | 31078 | 31078 | 24862.4 | 38032.2646 | 0.8 | 0.65372 | TRUE | TRUE | TRUE | 71.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146753 | HCMEF1Z2390 | F1 Z2 :Mechanical Final Fix | 26626 | 2013-10-14 08:00 | 2013-11-08 17:00 | 25 | 391 | 100 | 100 | 0 | 19550 | 19550 | 19550 | 18232.599 | 1 | 1.0723 | FALSE | FALSE | FALSE | 48.875 | FALSE | 0 | Green | Continue normal monitoring.
146754 | HCMEF1Z3155 | F1 Z3 :Blocks Start Date for All Parts | 26629 | 2013-07-09 16:00 | 2013-07-09 16:00 | 1 | 624 | 100 | 85 | -15 | 539 | 539 | 458.15 | 616.6216 | 0.85 | 0.743 | TRUE | TRUE | TRUE | 78 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146755 | HCMEF1Z3165 | F1 Z3 :Tiling Finish Date for All Parts | 26629 | 2013-11-10 16:00 | 2013-11-10 16:00 | 1 | 720 | 100 | 88 | -12 | 985 | 985 | 866.8 | 1178.6317 | 0.88 | 0.73543 | TRUE | TRUE | TRUE | 90 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146756 | HCMEF1Z3175 | F1 Z3 :Plastering Finish Date for All Parts | 26629 | 2013-08-26 16:00 | 2013-08-26 16:00 | 1 | 872 | 100 | 86 | -14 | 1428 | 1428 | 1228.08 | 1511.3279 | 0.86 | 0.81258 | TRUE | TRUE | TRUE | 109 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146757 | HCMEF1Z3185 | F1 Z3 :Gypsum Boards Finish Date for All Parts | 26629 | 2014-02-20 16:00 | 2014-02-20 16:00 | 1 | 624 | 100 | 83 | -17 | 719 | 719 | 596.77 | 803.6308 | 0.83 | 0.74259 | TRUE | TRUE | TRUE | 78 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146758 | HCMEF1Z3215 | F1 Z3 :Electrical Coduits & Boards F.F for All Systems | 26629 | 2013-07-09 16:00 | 2013-07-25 16:00 | 16 | 520 | 100 | 92 | -8 | 26432 | 26432 | 24317.44 | 31084.1939 | 0.92 | 0.78231 | TRUE | FALSE | FALSE | 65 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146759 | HCMEF1Z3225 | F1 Z3 :Electrical Boards Seconed Fix | 26629 | 2013-10-09 16:00 | 2013-10-25 16:00 | 16 | 488 | 100 | 96 | -4 | 24224 | 24224 | 23255.04 | 23116.238 | 0.96 | 1.006 | FALSE | FALSE | FALSE | 61 | FALSE | 0 | Green | Continue normal monitoring.
146760 | HCMEF1Z3235 | F1 Z3 :Cable Tray Installation | 26629 | 2013-12-04 16:00 | 2013-12-18 16:00 | 14 | 168 | 100 | 100 | 0 | 21322 | 21322 | 21322 | 20655.8638 | 1 | 1.0322 | FALSE | FALSE | FALSE | 21 | FALSE | 0 | Green | Continue normal monitoring.
146761 | HCMEF1Z3245 | F1 Z3 :Electrcial Wiring | 26629 | 2014-01-03 16:00 | 2014-01-13 16:00 | 10 | 296 | 100 | 81 | -19 | 11120 | 11120 | 9007.2 | 9454.7912 | 0.81 | 0.95266 | FALSE | TRUE | TRUE | 37 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146762 | HCMEF1Z3255 | F1 Z3 :Cable Laying | 26629 | 2013-12-18 16:00 | 2014-01-01 16:00 | 14 | 168 | 100 | 100 | 0 | 19978 | 19978 | 19978 | 24677.5778 | 1 | 0.80956 | TRUE | FALSE | FALSE | 21 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146763 | HCMEF1Z3265 | F1 Z3 :Electrical Final Fix for All Systems & Boards (Vertical Elements) | 26629 | 2014-02-12 16:00 | 2014-02-26 16:00 | 14 | 488 | 100 | 84 | -16 | 16618 | 16618 | 13959.12 | 20224.4044 | 0.84 | 0.69021 | TRUE | TRUE | TRUE | 61 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146764 | HCMEF1Z3275 | F1 Z3 :Electrical Final Fix for All Systems (Horizantel Elements) | 26629 | 2014-02-26 16:00 | 2014-03-12 16:00 | 14 | 488 | 100 | 91 | -9 | 15568 | 15568 | 14166.88 | 17993.9195 | 0.91 | 0.78731 | TRUE | FALSE | FALSE | 61 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146765 | HCMEF1Z3065 | F1 Z3 :All Vertical Piping Works | 26565 | 2013-03-13 08:00 | 2013-03-26 17:00 | 13 | 575 | 100 | 100 | 0 | 9867 | 9867 | 9867 | 8699.0472 | 1 | 1.1343 | FALSE | FALSE | FALSE | 71.875 | FALSE | 0 | Green | Continue normal monitoring.
146766 | HCMEF1Z3075 | F1 Z3 :All Horizantal Piping Works | 26565 | 2013-03-27 08:00 | 2013-05-07 17:00 | 41 | 575 | 100 | 100 | 0 | 61049 | 61049 | 61049 | 62819.4916 | 1 | 0.97182 | FALSE | FALSE | FALSE | 71.875 | FALSE | 0 | Green | Continue normal monitoring.
146767 | HCMEF1Z3085 | F1 Z3 :Mechanical Final Fix | 26565 | 2013-10-14 08:00 | 2013-11-08 17:00 | 25 | 391 | 100 | 87 | -13 | 36625 | 36625 | 31863.75 | 32623.9642 | 0.87 | 0.9767 | FALSE | TRUE | TRUE | 48.875 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146768 | HCMEF1Z3095 | F1 Z3 :Horizontal F.F Piping Work | 26630 | 2013-07-09 16:00 | 2013-08-06 16:00 | 28 | 616 | 100 | 85 | -15 | 24220 | 24220 | 20587 | 20741.2355 | 0.85 | 0.99256 | FALSE | TRUE | TRUE | 77 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146769 | HCMEF1Z3105 | F1 Z3 :Fire Hose Cabinets | 26630 | 2013-08-06 16:00 | 2013-08-20 16:00 | 14 | 616 | 100 | 87 | -13 | 14602 | 14602 | 12703.74 | 16010.7015 | 0.87 | 0.79345 | TRUE | TRUE | TRUE | 77 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146770 | HCMEF1Z3115 | F1 Z3 :Sprinklers Final Fix | 26630 | 2014-01-13 16:00 | 2014-01-27 16:00 | 14 | 344 | 100 | 97 | -3 | 16072 | 16072 | 15589.84 | 19838.1802 | 0.97 | 0.78585 | TRUE | FALSE | FALSE | 43 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146771 | HCMEF1Z3325 | F1 Z3 :Duct Installation& Dusct Accecories Installation, Fan coil Unit | 26631 | 2013-09-17 16:00 | 2013-09-27 16:00 | 10 | 232 | 100 | 82 | -18 | 13130 | 13130 | 10766.6 | 15902.3629 | 0.82 | 0.67704 | TRUE | TRUE | TRUE | 29 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146772 | HCMEF1Z3335 | F1 Z3 :Duct Insulation Work | 26631 | 2013-09-27 16:00 | 2013-10-18 16:00 | 21 | 232 | 100 | 100 | 0 | 32319 | 32319 | 32319 | 36478.5175 | 1 | 0.88597 | TRUE | FALSE | FALSE | 29 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146773 | HCMEF1Z3345 | F1 Z3 :Exhaust Fans | 26631 | 2013-10-18 16:00 | 2013-11-08 16:00 | 21 | 232 | 100 | 91 | -9 | 34692 | 34692 | 31569.72 | 30829.2621 | 0.91 | 1.024 | FALSE | FALSE | FALSE | 29 | FALSE | 0 | Green | Continue normal monitoring.
146774 | HCMEF1Z3355 | F1 Z3 :Grills & Diffusers | 26631 | 2014-02-06 16:00 | 2014-02-20 16:00 | 14 | 120 | 100 | 100 | 0 | 15036 | 15036 | 15036 | 14429.5322 | 1 | 1.042 | FALSE | FALSE | FALSE | 15 | FALSE | 0 | Green | Continue normal monitoring.
146775 | HCMEF1Z3365 | F1 Z3 :Mechanical final Fix | 26631 | 2014-02-20 16:00 | 2014-03-06 16:00 | 14 | 120 | 100 | 100 | 0 | 22848 | 22848 | 22848 | 22345.8624 | 1 | 1.0225 | FALSE | FALSE | FALSE | 15 | FALSE | 0 | Green | Continue normal monitoring.
146776 | HCMEF1Z3375 | F1 Z3 :All Vertical Piping Works | 26632 | 2013-03-13 08:00 | 2013-03-26 17:00 | 13 | 575 | 100 | 82 | -18 | 19656 | 19656 | 16117.92 | 22707.791 | 0.82 | 0.7098 | TRUE | TRUE | TRUE | 71.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146777 | HCMEF1Z3385 | F1 Z3 :All Horizantal Piping Works | 26632 | 2013-03-27 08:00 | 2013-05-07 17:00 | 41 | 575 | 100 | 100 | 0 | 47929 | 47929 | 47929 | 56120.0504 | 1 | 0.85404 | TRUE | FALSE | FALSE | 71.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146778 | HCMEF1Z3395 | F1 Z3 :Mechanical Final Fix | 26632 | 2013-10-14 08:00 | 2013-11-08 17:00 | 25 | 391 | 100 | 85 | -15 | 19200 | 19200 | 16320 | 19277.615 | 0.85 | 0.84658 | TRUE | TRUE | TRUE | 48.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146779 | HCMEF2Z1150 | F2 Z1 :Blocks Start Date for All Parts | 26639 | 2013-03-24 16:00 | 2013-03-24 16:00 | 1 | 1272 | 100 | 81 | -19 | 1685 | 1685 | 1364.85 | 1713.9038 | 0.81 | 0.79634 | TRUE | TRUE | TRUE | 159 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146780 | HCMEF2Z1160 | F2 Z1 :Tiling Finish Date for All Parts | 26639 | 2013-08-12 16:00 | 2013-08-12 16:00 | 1 | 680 | 100 | 100 | 0 | 1783 | 1783 | 1783 | 1547.2938 | 1 | 1.1523 | FALSE | FALSE | FALSE | 85 | FALSE | 0 | Green | Continue normal monitoring.
146781 | HCMEF2Z1170 | F2 Z1 :Plastering Finish Date for All Parts | 26639 | 2013-04-23 12:00 | 2013-04-23 12:00 | 1 | 1635 | 100 | 91 | -9 | 1423 | 1423 | 1294.93 | 1374.1266 | 0.91 | 0.94237 | FALSE | FALSE | FALSE | 204.375 | FALSE | 0 | Green | Continue normal monitoring.
146782 | HCMEF2Z1180 | F2 Z1 :Gypsum Boards Finish Date for All Parts | 26639 | 2014-02-03 16:00 | 2014-02-03 16:00 | 1 | 744 | 100 | 81 | -19 | 1625 | 1625 | 1316.25 | 1674.5854 | 0.81 | 0.78602 | TRUE | TRUE | TRUE | 93 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146783 | HCMEF2Z1210 | F2 Z1 :Electrical Coduits & Boards F.F for All Systems | 26639 | 2013-03-25 08:00 | 2013-04-09 17:00 | 15 | 1063 | 100 | 85 | -15 | 11190 | 11190 | 9511.5 | 10035.1161 | 0.85 | 0.94782 | FALSE | TRUE | TRUE | 132.875 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146784 | HCMEF2Z1220 | F2 Z1 :Electrical Boards Seconed Fix | 26639 | 2013-07-08 16:00 | 2013-07-24 16:00 | 16 | 952 | 100 | 96 | -4 | 10080 | 10080 | 9676.8 | 10395.5744 | 0.96 | 0.93086 | FALSE | FALSE | FALSE | 119 | FALSE | 0 | Green | Continue normal monitoring.
146785 | HCMEF2Z1230 | F2 Z1 :Cable Tray Installation | 26639 | 2013-12-18 16:00 | 2014-01-01 16:00 | 14 | 0 | 100 | 82 | -18 | 11928 | 11928 | 9780.96 | 14209.4724 | 0.82 | 0.68834 | TRUE | TRUE | TRUE | 0 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
146786 | HCMEF2Z1240 | F2 Z1 :Electrcial Wiring | 26639 | 2013-11-18 08:00 | 2013-12-13 17:00 | 25 | 15 | 100 | 81 | -19 | 17375 | 17375 | 14073.75 | 18808.9311 | 0.81 | 0.74825 | TRUE | TRUE | TRUE | 1.875 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
146787 | HCMEF2Z1250 | F2 Z1 :Cable Laying | 26639 | 2014-01-07 16:00 | 2014-01-21 16:00 | 14 | 0 | 100 | 100 | 0 | 20006 | 20006 | 20006 | 17636.7283 | 1 | 1.1343 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146788 | HCMEF2Z1260 | F2 Z1 :Electrical Final Fix for All Systems & Boards (Vertical Elements) | 26639 | 2014-03-04 16:00 | 2014-03-18 16:00 | 14 | 376 | 100 | 100 | 0 | 26670 | 26670 | 26670 | 24714.2496 | 1 | 1.0791 | FALSE | FALSE | FALSE | 47 | FALSE | 0 | Green | Continue normal monitoring.
146789 | HCMEF2Z1270 | F2 Z1 :Electrical Final Fix for All Systems (Horizantel Elements) | 26639 | 2014-03-18 16:00 | 2014-04-01 16:00 | 14 | 376 | 100 | 99 | -1 | 21294 | 21294 | 21081.06 | 22141.879 | 0.99 | 0.95209 | FALSE | FALSE | FALSE | 47 | FALSE | 0 | Green | Continue normal monitoring.
146790 | HCMEF2Z1060 | F2 Z1 :All Vertical Piping Works | 26566 | 2013-03-25 08:00 | 2013-04-05 17:00 | 11 | 511 | 100 | 87 | -13 | 12584 | 12584 | 10948.08 | 12515.9817 | 0.87 | 0.87473 | TRUE | TRUE | TRUE | 63.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146791 | HCMEF2Z1070 | F2 Z1 :All Horizantal Piping Works | 26566 | 2013-04-08 08:00 | 2013-05-17 17:00 | 39 | 511 | 100 | 100 | 0 | 28314 | 28314 | 28314 | 28129.6987 | 1 | 1.0066 | FALSE | FALSE | FALSE | 63.875 | FALSE | 0 | Green | Continue normal monitoring.
146792 | HCMEF2Z1080 | F2 Z1 :Mechanical Final Fix | 26566 | 2013-11-11 08:00 | 2013-12-06 17:00 | 25 | 231 | 100 | 91 | -9 | 30000 | 30000 | 27300 | 31851.2094 | 0.91 | 0.85711 | TRUE | FALSE | FALSE | 28.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146793 | HCMEF2Z1090 | F2 Z1 :Horizontal F.F Piping Work | 26640 | 2013-03-25 08:00 | 2013-04-19 17:00 | 25 | 1231 | 100 | 100 | 0 | 49975 | 49975 | 49975 | 54160.8245 | 1 | 0.92271 | FALSE | FALSE | FALSE | 153.875 | FALSE | 0 | Green | Continue normal monitoring.
146794 | HCMEF2Z1100 | F2 Z1 :Fire Hose Cabinets | 26640 | 2013-04-22 08:00 | 2013-05-03 17:00 | 11 | 1231 | 100 | 83 | -17 | 8404 | 8404 | 6975.32 | 9822.1299 | 0.83 | 0.71016 | TRUE | TRUE | TRUE | 153.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146795 | HCMEF2Z1110 | F2 Z1 :Sprinklers Final Fix | 26640 | 2014-01-27 16:00 | 2014-02-10 16:00 | 14 | 264 | 100 | 84 | -16 | 26530 | 26530 | 22285.2 | 26168.8372 | 0.84 | 0.85159 | TRUE | TRUE | TRUE | 33 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146796 | HCMEF2Z1320 | F2 Z1 :Duct Installation& Dusct Accecories Installation, Fan coil Unit | 26641 | 2013-09-23 16:00 | 2013-10-07 16:00 | 14 | 184 | 100 | 92 | -8 | 27398 | 27398 | 25206.16 | 32115.5661 | 0.92 | 0.78486 | TRUE | FALSE | FALSE | 23 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146797 | HCMEF2Z1330 | F2 Z1 :Duct Insulation Work | 26641 | 2013-10-07 16:00 | 2013-10-28 16:00 | 21 | 184 | 100 | 100 | 0 | 24045 | 24045 | 24045 | 23695.0128 | 1 | 1.0148 | FALSE | FALSE | FALSE | 23 | FALSE | 0 | Green | Continue normal monitoring.
146798 | HCMEF2Z1340 | F2 Z1 :Exhaust Fans | 26641 | 2013-10-28 16:00 | 2013-11-18 16:00 | 21 | 184 | 100 | 100 | 0 | 14910 | 14910 | 14910 | 13004.1023 | 1 | 1.1466 | FALSE | FALSE | FALSE | 23 | FALSE | 0 | Green | Continue normal monitoring.
146799 | HCMEF2Z1350 | F2 Z1 :Grills & Diffusers | 26641 | 2014-02-25 16:00 | 2014-03-11 16:00 | 14 | 16 | 100 | 94 | -6 | 26600 | 26600 | 25004 | 28506.5566 | 0.94 | 0.87713 | TRUE | FALSE | FALSE | 2 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146800 | HCMEF2Z1360 | F2 Z1 :Mechanical final Fix | 26641 | 2014-03-13 16:00 | 2014-03-27 16:00 | 14 | 0 | 100 | 100 | 0 | 26852 | 26852 | 26852 | 29138.7413 | 1 | 0.92152 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146801 | HCMEF2Z1370 | F2 Z1 :All Vertical Piping Works | 26642 | 2013-03-25 08:00 | 2013-04-05 17:00 | 11 | 511 | 100 | 100 | 0 | 21703 | 21703 | 21703 | 26560.4808 | 1 | 0.81712 | TRUE | FALSE | FALSE | 63.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146802 | HCMEF2Z1380 | F2 Z1 :All Horizantal Piping Works | 26642 | 2013-04-08 08:00 | 2013-05-17 17:00 | 39 | 511 | 100 | 95 | -5 | 56238 | 56238 | 53426.1 | 64135.1947 | 0.95 | 0.83302 | TRUE | FALSE | FALSE | 63.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146803 | HCMEF2Z1390 | F2 Z1 :Mechanical Final Fix | 26642 | 2013-11-11 08:00 | 2013-12-06 17:00 | 25 | 231 | 100 | 89 | -11 | 47175 | 47175 | 41985.75 | 57417.12 | 0.89 | 0.73124 | TRUE | TRUE | TRUE | 28.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146804 | HCMEF2Z2155 | F2 Z2 :Blocks Start Date for All Parts | 26645 | 2013-05-20 16:00 | 2013-05-20 16:00 | 1 | 968 | 100 | 100 | 0 | 956 | 956 | 956 | 1159.952 | 1 | 0.82417 | TRUE | FALSE | FALSE | 121 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146805 | HCMEF2Z2165 | F2 Z2 :Tiling Finish Date for All Parts | 26645 | 2013-08-19 16:00 | 2013-08-19 16:00 | 1 | 632 | 100 | 100 | 0 | 1224 | 1224 | 1224 | 1336.3995 | 1 | 0.91589 | FALSE | FALSE | FALSE | 79 | FALSE | 0 | Green | Continue normal monitoring.
146806 | HCMEF2Z2175 | F2 Z2 :Plastering Finish Date for All Parts | 26645 | 2013-07-04 16:00 | 2013-07-04 16:00 | 1 | 1232 | 100 | 100 | 0 | 1749 | 1749 | 1749 | 1855.8723 | 1 | 0.94241 | FALSE | FALSE | FALSE | 154 | FALSE | 0 | Green | Continue normal monitoring.
146807 | HCMEF2Z2185 | F2 Z2 :Gypsum Boards Finish Date for All Parts | 26645 | 2014-02-02 16:00 | 2014-02-02 16:00 | 1 | 752 | 100 | 100 | 0 | 1481 | 1481 | 1481 | 1589.078 | 1 | 0.93199 | FALSE | FALSE | FALSE | 94 | FALSE | 0 | Green | Continue normal monitoring.
146808 | HCMEF2Z2215 | F2 Z2 :Electrical Coduits & Boards F.F for All Systems | 26645 | 2013-05-20 16:00 | 2013-06-05 16:00 | 16 | 808 | 100 | 95 | -5 | 26464 | 26464 | 25140.8 | 32850.6186 | 0.95 | 0.76531 | TRUE | FALSE | FALSE | 101 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146809 | HCMEF2Z2225 | F2 Z2 :Electrical Boards Seconed Fix | 26645 | 2013-08-20 16:00 | 2013-09-05 16:00 | 16 | 776 | 100 | 91 | -9 | 17392 | 17392 | 15826.72 | 20161.973 | 0.91 | 0.78498 | TRUE | FALSE | FALSE | 97 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146810 | HCMEF2Z2235 | F2 Z2 :Cable Tray Installation | 26645 | 2013-12-18 16:00 | 2014-01-01 16:00 | 14 | 88 | 100 | 96 | -4 | 13650 | 13650 | 13104 | 12182.7118 | 0.96 | 1.0756 | FALSE | FALSE | FALSE | 11 | FALSE | 0 | Green | Continue normal monitoring.
146811 | HCMEF2Z2245 | F2 Z2 :Electrcial Wiring | 26645 | 2013-10-14 08:00 | 2013-11-08 17:00 | 25 | 215 | 100 | 95 | -5 | 37125 | 37125 | 35268.75 | 43115.9118 | 0.95 | 0.818 | TRUE | FALSE | FALSE | 26.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146812 | HCMEF2Z2255 | F2 Z2 :Cable Laying | 26645 | 2014-01-01 16:00 | 2014-01-15 16:00 | 14 | 88 | 100 | 91 | -9 | 25200 | 25200 | 22932 | 23139.0235 | 0.91 | 0.99105 | FALSE | FALSE | FALSE | 11 | FALSE | 0 | Green | Continue normal monitoring.
146813 | HCMEF2Z2265 | F2 Z2 :Electrical Final Fix for All Systems & Boards (Vertical Elements) | 26645 | 2014-02-26 16:00 | 2014-03-12 16:00 | 14 | 408 | 100 | 87 | -13 | 9170 | 9170 | 7977.9 | 9435.3818 | 0.87 | 0.84553 | TRUE | TRUE | TRUE | 51 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146814 | HCMEF2Z2275 | F2 Z2 :Electrical Final Fix for All Systems (Horizantel Elements) | 26645 | 2014-03-12 16:00 | 2014-03-26 16:00 | 14 | 408 | 100 | 99 | -1 | 24374 | 24374 | 24130.26 | 22769.7976 | 0.99 | 1.0597 | FALSE | FALSE | FALSE | 51 | FALSE | 0 | Green | Continue normal monitoring.
146815 | HCMEF2Z2065 | F2 Z2 :All Vertical Piping Works | 26644 | 2013-03-25 08:00 | 2013-04-05 17:00 | 11 | 671 | 100 | 82 | -18 | 7579 | 7579 | 6214.78 | 8532.69 | 0.82 | 0.72835 | TRUE | TRUE | TRUE | 83.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146816 | HCMEF2Z2075 | F2 Z2 :All Horizantal Piping Works | 26644 | 2013-04-08 08:00 | 2013-05-17 17:00 | 39 | 671 | 100 | 95 | -5 | 75660 | 75660 | 71877 | 90861.9019 | 0.95 | 0.79106 | TRUE | FALSE | FALSE | 83.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146817 | HCMEF2Z2085 | F2 Z2 :Mechanical Final Fix | 26644 | 2013-11-11 08:00 | 2013-12-06 17:00 | 25 | 391 | 100 | 100 | 0 | 37000 | 37000 | 37000 | 35747.3559 | 1 | 1.035 | FALSE | FALSE | FALSE | 48.875 | FALSE | 0 | Green | Continue normal monitoring.
146818 | HCMEF2Z2095 | F2 Z2 :Horizontal F.F Piping Work | 26646 | 2013-05-20 16:00 | 2013-06-17 16:00 | 28 | 984 | 100 | 92 | -8 | 29260 | 29260 | 26919.2 | 25830.8537 | 0.92 | 1.0421 | FALSE | FALSE | FALSE | 123 | FALSE | 0 | Green | Continue normal monitoring.
146819 | HCMEF2Z2105 | F2 Z2 :Fire Hose Cabinets | 26646 | 2013-06-17 16:00 | 2013-07-01 16:00 | 14 | 984 | 100 | 100 | 0 | 7560 | 7560 | 7560 | 7328.6431 | 1 | 1.0316 | FALSE | FALSE | FALSE | 123 | FALSE | 0 | Green | Continue normal monitoring.
146820 | HCMEF2Z2115 | F2 Z2 :Sprinklers Final Fix | 26646 | 2014-01-27 16:00 | 2014-02-10 16:00 | 14 | 344 | 100 | 100 | 0 | 11284 | 11284 | 11284 | 12626.1725 | 1 | 0.8937 | TRUE | FALSE | FALSE | 43 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146821 | HCMEF2Z2325 | F2 Z2 :Duct Installation& Dusct Accecories Installation, Fan coil Unit | 26647 | 2013-09-17 16:00 | 2013-09-27 16:00 | 10 | 217 | 100 | 98 | -2 | 14420 | 14420 | 14131.6 | 14153.2884 | 0.98 | 0.99847 | FALSE | FALSE | FALSE | 27.125 | FALSE | 0 | Green | Continue normal monitoring.
146822 | HCMEF2Z2335 | F2 Z2 :Duct Insulation Work | 26647 | 2013-09-27 16:00 | 2013-10-18 16:00 | 21 | 217 | 100 | 87 | -13 | 17577 | 17577 | 15291.99 | 16895.801 | 0.87 | 0.90508 | FALSE | TRUE | TRUE | 27.125 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146823 | HCMEF2Z2345 | F2 Z2 :Exhaust Fans | 26647 | 2013-10-18 16:00 | 2013-11-08 16:00 | 21 | 217 | 100 | 100 | 0 | 38577 | 38577 | 38577 | 35636.4325 | 1 | 1.0825 | FALSE | FALSE | FALSE | 27.125 | FALSE | 0 | Green | Continue normal monitoring.
146824 | HCMEF2Z2355 | F2 Z2 :Grills & Diffusers | 26647 | 2014-02-20 16:00 | 2014-03-06 16:00 | 14 | 25 | 100 | 84 | -16 | 22372 | 22372 | 18792.48 | 23468.375 | 0.84 | 0.80076 | TRUE | TRUE | TRUE | 3.125 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
146825 | HCMEF2Z2365 | F2 Z2 :Mechanical final Fix | 26647 | 2014-03-06 16:00 | 2014-03-20 16:00 | 14 | 25 | 100 | 99 | -1 | 20328 | 20328 | 20124.72 | 19522.5951 | 0.99 | 1.0308 | FALSE | FALSE | FALSE | 3.125 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146826 | HCMEF2Z2375 | F2 Z2 :All Vertical Piping Works | 26648 | 2013-03-25 08:00 | 2013-04-05 17:00 | 11 | 671 | 100 | 87 | -13 | 8558 | 8558 | 7445.46 | 9776.6946 | 0.87 | 0.76155 | TRUE | TRUE | TRUE | 83.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146827 | HCMEF2Z2385 | F2 Z2 :All Horizantal Piping Works | 26648 | 2013-04-08 08:00 | 2013-05-17 17:00 | 39 | 671 | 100 | 100 | 0 | 66261 | 66261 | 66261 | 58352.6808 | 1 | 1.1355 | FALSE | FALSE | FALSE | 83.875 | FALSE | 0 | Green | Continue normal monitoring.
146828 | HCMEF2Z2395 | F2 Z2 :Mechanical Final Fix | 26648 | 2013-11-11 08:00 | 2013-12-06 17:00 | 25 | 391 | 100 | 91 | -9 | 34875 | 34875 | 31736.25 | 38907.0108 | 0.91 | 0.81569 | TRUE | FALSE | FALSE | 48.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146829 | HCMEF2Z3160 | F2 Z3 :Blocks Start Date for All Parts | 26651 | 2013-07-21 16:00 | 2013-07-21 16:00 | 1 | 656 | 100 | 80 | -20 | 772 | 772 | 617.6 | 729.5585 | 0.8 | 0.84654 | TRUE | TRUE | TRUE | 82 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146830 | HCMEF2Z3170 | F2 Z3 :Tiling Finish Date for All Parts | 26651 | 2013-12-08 16:00 | 2013-12-08 16:00 | 1 | 592 | 100 | 100 | 0 | 1336 | 1336 | 1336 | 1397.0708 | 1 | 0.95629 | FALSE | FALSE | FALSE | 74 | FALSE | 0 | Green | Continue normal monitoring.
146831 | HCMEF2Z3180 | F2 Z3 :Plastering Finish Date for All Parts | 26651 | 2013-09-04 16:00 | 2013-09-04 16:00 | 1 | 904 | 100 | 100 | 0 | 1119 | 1119 | 1119 | 1079.2038 | 1 | 1.0369 | FALSE | FALSE | FALSE | 113 | FALSE | 0 | Green | Continue normal monitoring.
146832 | HCMEF2Z3190 | F2 Z3 :Gypsum Boards Finish Date for All Parts | 26651 | 2014-03-09 16:00 | 2014-03-09 16:00 | 1 | 512 | 100 | 100 | 0 | 1361 | 1361 | 1361 | 1550.3253 | 1 | 0.87788 | TRUE | FALSE | FALSE | 64 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146833 | HCMEF2Z3220 | F2 Z3 :Electrical Coduits & Boards F.F for All Systems | 26651 | 2013-07-22 08:00 | 2013-08-06 17:00 | 15 | 551 | 100 | 99 | -1 | 21450 | 21450 | 21235.5 | 26343.2344 | 0.99 | 0.80611 | TRUE | FALSE | FALSE | 68.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146834 | HCMEF2Z3230 | F2 Z3 :Electrical Boards Seconed Fix | 26651 | 2013-10-25 16:00 | 2013-11-12 16:00 | 18 | 488 | 100 | 85 | -15 | 14184 | 14184 | 12056.4 | 17259.5268 | 0.85 | 0.69854 | TRUE | TRUE | TRUE | 61 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146835 | HCMEF2Z3240 | F2 Z3 :Cable Tray Installation | 26651 | 2013-12-18 16:00 | 2014-01-01 16:00 | 14 | 168 | 100 | 100 | 0 | 17122 | 17122 | 17122 | 18549.4695 | 1 | 0.92305 | FALSE | FALSE | FALSE | 21 | FALSE | 0 | Green | Continue normal monitoring.
146836 | HCMEF2Z3250 | F2 Z3 :Electrcial Wiring | 26651 | 2014-01-13 16:00 | 2014-01-21 16:00 | 8 | 296 | 100 | 97 | -3 | 11136 | 11136 | 10801.92 | 11526.2513 | 0.97 | 0.93716 | FALSE | FALSE | FALSE | 37 | FALSE | 0 | Green | Continue normal monitoring.
146837 | HCMEF2Z3260 | F2 Z3 :Cable Laying | 26651 | 2014-01-01 16:00 | 2014-01-15 16:00 | 14 | 168 | 100 | 87 | -13 | 10794 | 10794 | 9390.78 | 12707.9943 | 0.87 | 0.73897 | TRUE | TRUE | TRUE | 21 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146838 | HCMEF2Z3270 | F2 Z3 :Electrical Final Fix for All Systems & Boards (Vertical Elements) | 26651 | 2014-02-26 16:00 | 2014-03-12 16:00 | 14 | 408 | 100 | 86 | -14 | 22246 | 22246 | 19131.56 | 24989.6113 | 0.86 | 0.76558 | TRUE | TRUE | TRUE | 51 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146839 | HCMEF2Z3280 | F2 Z3 :Electrical Final Fix for All Systems (Horizantel Elements) | 26651 | 2014-03-12 16:00 | 2014-03-26 16:00 | 14 | 408 | 100 | 80 | -20 | 13748 | 13748 | 10998.4 | 12695.2558 | 0.8 | 0.86634 | TRUE | TRUE | TRUE | 51 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146840 | HCMEF2Z3070 | F2 Z3 :All Vertical Piping Works | 26650 | 2013-03-25 08:00 | 2013-04-05 17:00 | 11 | 671 | 100 | 100 | 0 | 15785 | 15785 | 15785 | 18600.5339 | 1 | 0.84863 | TRUE | FALSE | FALSE | 83.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146841 | HCMEF2Z3080 | F2 Z3 :All Horizantal Piping Works | 26650 | 2013-04-08 08:00 | 2013-05-17 17:00 | 39 | 671 | 100 | 95 | -5 | 29133 | 29133 | 27676.35 | 29760.9256 | 0.95 | 0.92996 | FALSE | FALSE | FALSE | 83.875 | FALSE | 0 | Green | Continue normal monitoring.
146842 | HCMEF2Z3090 | F2 Z3 :Mechanical Final Fix | 26650 | 2013-11-11 08:00 | 2013-12-06 17:00 | 25 | 391 | 100 | 91 | -9 | 16375 | 16375 | 14901.25 | 15156.6061 | 0.91 | 0.98315 | FALSE | FALSE | FALSE | 48.875 | FALSE | 0 | Green | Continue normal monitoring.
146843 | HCMEF2Z3100 | F2 Z3 :Horizontal F.F Piping Work | 26652 | 2013-07-22 08:00 | 2013-08-16 17:00 | 25 | 631 | 100 | 85 | -15 | 39250 | 39250 | 33362.5 | 37786.7184 | 0.85 | 0.88292 | TRUE | TRUE | TRUE | 78.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146844 | HCMEF2Z3110 | F2 Z3 :Fire Hose Cabinets | 26652 | 2013-08-19 08:00 | 2013-08-30 17:00 | 11 | 631 | 100 | 99 | -1 | 10483 | 10483 | 10378.17 | 10032.3443 | 0.99 | 1.0345 | FALSE | FALSE | FALSE | 78.875 | FALSE | 0 | Green | Continue normal monitoring.
146845 | HCMEF2Z3120 | F2 Z3 :Sprinklers Final Fix | 26652 | 2014-01-27 16:00 | 2014-02-10 16:00 | 14 | 344 | 100 | 81 | -19 | 9800 | 9800 | 7938 | 10365.2913 | 0.81 | 0.76583 | TRUE | TRUE | TRUE | 43 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146846 | HCMEF2Z3330 | F2 Z3 :Duct Installation& Dusct Accecories Installation, Fan coil Unit | 26653 | 2013-09-27 16:00 | 2013-10-09 16:00 | 12 | 248 | 100 | 100 | 0 | 7476 | 7476 | 7476 | 7055.4603 | 1 | 1.0596 | FALSE | FALSE | FALSE | 31 | FALSE | 0 | Green | Continue normal monitoring.
146847 | HCMEF2Z3340 | F2 Z3 :Duct Insulation Work | 26653 | 2013-10-09 16:00 | 2013-10-30 16:00 | 21 | 248 | 100 | 93 | -7 | 10500 | 10500 | 9765 | 9443.9792 | 0.93 | 1.034 | FALSE | FALSE | FALSE | 31 | FALSE | 0 | Green | Continue normal monitoring.
146848 | HCMEF2Z3350 | F2 Z3 :Exhaust Fans | 26653 | 2013-10-30 16:00 | 2013-11-20 16:00 | 21 | 248 | 100 | 83 | -17 | 30807 | 30807 | 25569.81 | 27710.1676 | 0.83 | 0.92276 | FALSE | TRUE | TRUE | 31 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146849 | HCMEF2Z3360 | F2 Z3 :Grills & Diffusers | 26653 | 2014-02-20 16:00 | 2014-03-06 16:00 | 14 | 120 | 100 | 80 | -20 | 18956 | 18956 | 15164.8 | 20535.2334 | 0.8 | 0.73848 | TRUE | TRUE | TRUE | 15 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146850 | HCMEF2Z3370 | F2 Z3 :Mechanical final Fix | 26653 | 2014-03-06 16:00 | 2014-03-20 16:00 | 14 | 120 | 100 | 100 | 0 | 15946 | 15946 | 15946 | 18240.6886 | 1 | 0.8742 | TRUE | FALSE | FALSE | 15 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146851 | HCMEF2Z3380 | F2 Z3 :All Vertical Piping Works | 26654 | 2013-03-25 08:00 | 2013-04-05 17:00 | 11 | 671 | 100 | 97 | -3 | 7590 | 7590 | 7362.3 | 7427.6742 | 0.97 | 0.9912 | FALSE | FALSE | FALSE | 83.875 | FALSE | 0 | Green | Continue normal monitoring.
146852 | HCMEF2Z3390 | F2 Z3 :All Horizantal Piping Works | 26654 | 2013-04-08 08:00 | 2013-05-17 17:00 | 39 | 671 | 100 | 92 | -8 | 39585 | 39585 | 36418.2 | 34195.9093 | 0.92 | 1.065 | FALSE | FALSE | FALSE | 83.875 | FALSE | 0 | Green | Continue normal monitoring.
146853 | HCMEF2Z3400 | F2 Z3 :Mechanical Final Fix | 26654 | 2013-11-11 08:00 | 2013-12-06 17:00 | 25 | 391 | 100 | 81 | -19 | 23525 | 23525 | 19055.25 | 21193.4362 | 0.81 | 0.89911 | TRUE | TRUE | TRUE | 48.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146854 | HCMEF3Z1155 | F3 Z1 :Blocks Start Date for All Parts | 26659 | 2013-04-04 16:00 | 2013-04-04 16:00 | 1 | 1297 | 100 | 88 | -12 | 642 | 642 | 564.96 | 780.5936 | 0.88 | 0.72376 | TRUE | TRUE | TRUE | 162.125 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146855 | HCMEF3Z1165 | F3 Z1 :Tiling Finish Date for All Parts | 26659 | 2013-09-11 12:00 | 2013-09-11 12:00 | 1 | 659 | 100 | 100 | 0 | 1714 | 1714 | 1714 | 1795.2735 | 1 | 0.95473 | FALSE | FALSE | FALSE | 82.375 | FALSE | 0 | Green | Continue normal monitoring.
146856 | HCMEF3Z1175 | F3 Z1 :Plastering Finish Date for All Parts | 26659 | 2013-05-23 16:00 | 2013-05-23 16:00 | 1 | 1513 | 100 | 81 | -19 | 1032 | 1032 | 835.92 | 1064.4349 | 0.81 | 0.78532 | TRUE | TRUE | TRUE | 189.125 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146857 | HCMEF3Z1185 | F3 Z1 :Gypsum Boards Finish Date for All Parts | 26659 | 2014-02-19 16:00 | 2014-02-19 16:00 | 1 | 632 | 100 | 100 | 0 | 726 | 726 | 726 | 628.1495 | 1 | 1.1558 | FALSE | FALSE | FALSE | 79 | FALSE | 0 | Green | Continue normal monitoring.
146858 | HCMEF3Z1215 | F3 Z1 :Electrical Coduits & Boards F.F for All Systems | 26659 | 2013-04-04 16:00 | 2013-04-22 16:00 | 18 | 1088 | 100 | 100 | 0 | 33048 | 33048 | 33048 | 37722.7985 | 1 | 0.87607 | TRUE | FALSE | FALSE | 136 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146859 | HCMEF3Z1225 | F3 Z1 :Electrical Boards Seconed Fix | 26659 | 2013-07-24 16:00 | 2013-08-09 16:00 | 16 | 952 | 100 | 88 | -12 | 23168 | 23168 | 20387.84 | 24586.5125 | 0.88 | 0.82923 | TRUE | TRUE | TRUE | 119 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146860 | HCMEF3Z1235 | F3 Z1 :Cable Tray Installation | 26659 | 2014-01-01 16:00 | 2014-01-15 16:00 | 14 | 0 | 100 | 80 | -20 | 25550 | 25550 | 20440 | 23782.7672 | 0.8 | 0.85945 | TRUE | TRUE | TRUE | 0 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
146861 | HCMEF3Z1245 | F3 Z1 :Electrcial Wiring | 26659 | 2013-12-16 08:00 | 2014-01-10 17:00 | 25 | 15 | 100 | 90 | -10 | 23975 | 23975 | 21577.5 | 21434.3574 | 0.9 | 1.0067 | FALSE | FALSE | FALSE | 1.875 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146862 | HCMEF3Z1255 | F3 Z1 :Cable Laying | 26659 | 2014-01-21 16:00 | 2014-02-04 16:00 | 14 | 0 | 100 | 82 | -18 | 26936 | 26936 | 22087.52 | 27026.3742 | 0.82 | 0.81726 | TRUE | TRUE | TRUE | 0 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
146863 | HCMEF3Z1265 | F3 Z1 :Electrical Final Fix for All Systems & Boards (Vertical Elements) | 26659 | 2014-03-18 16:00 | 2014-04-01 16:00 | 14 | 296 | 100 | 99 | -1 | 14700 | 14700 | 14553 | 17417.5123 | 0.99 | 0.83554 | TRUE | FALSE | FALSE | 37 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146864 | HCMEF3Z1275 | F3 Z1 :Electrical Final Fix for All Systems (Horizantel Elements) | 26659 | 2014-04-01 16:00 | 2014-04-15 16:00 | 14 | 296 | 100 | 100 | 0 | 12488 | 12488 | 12488 | 14937.1194 | 1 | 0.83604 | TRUE | FALSE | FALSE | 37 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146865 | HCMEF3Z1065 | F3 Z1 :All Vertical Piping Works | 26658 | 2013-04-08 08:00 | 2013-04-19 17:00 | 11 | 591 | 100 | 100 | 0 | 14784 | 14784 | 14784 | 16131.3924 | 1 | 0.91647 | FALSE | FALSE | FALSE | 73.875 | FALSE | 0 | Green | Continue normal monitoring.
146866 | HCMEF3Z1075 | F3 Z1 :All Horizantal Piping Works | 26658 | 2013-04-22 08:00 | 2013-05-31 17:00 | 39 | 591 | 100 | 100 | 0 | 67470 | 67470 | 67470 | 76984.2531 | 1 | 0.87641 | TRUE | FALSE | FALSE | 73.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146867 | HCMEF3Z1085 | F3 Z1 :Mechanical Final Fix | 26658 | 2013-12-09 08:00 | 2014-01-03 17:00 | 25 | 231 | 100 | 83 | -17 | 17725 | 17725 | 14711.75 | 15882.7045 | 0.83 | 0.92627 | FALSE | TRUE | TRUE | 28.875 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146868 | HCMEF3Z1095 | F3 Z1 :Horizontal F.F Piping Work | 26660 | 2013-04-04 16:00 | 2013-05-02 16:00 | 28 | 1240 | 100 | 97 | -3 | 45864 | 45864 | 44488.08 | 49773.9255 | 0.97 | 0.8938 | TRUE | FALSE | FALSE | 155 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146869 | HCMEF3Z1105 | F3 Z1 :Fire Hose Cabinets | 26660 | 2013-05-02 16:00 | 2013-05-16 16:00 | 14 | 1240 | 100 | 100 | 0 | 16030 | 16030 | 16030 | 17902.0841 | 1 | 0.89543 | TRUE | FALSE | FALSE | 155 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146870 | HCMEF3Z1115 | F3 Z1 :Sprinklers Final Fix | 26660 | 2014-02-10 16:00 | 2014-02-24 16:00 | 14 | 264 | 100 | 85 | -15 | 24836 | 24836 | 21110.6 | 23104.5617 | 0.85 | 0.9137 | FALSE | TRUE | TRUE | 33 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146871 | HCMEF3Z1325 | F3 Z1 :Duct Installation& Dusct Accecories Installation, Fan coil Unit | 26661 | 2013-10-07 16:00 | 2013-10-21 16:00 | 14 | 184 | 100 | 82 | -18 | 10052 | 10052 | 8242.64 | 12083.1262 | 0.82 | 0.68216 | TRUE | TRUE | TRUE | 23 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146872 | HCMEF3Z1335 | F3 Z1 :Duct Insulation Work | 26661 | 2013-10-21 16:00 | 2013-11-11 16:00 | 21 | 184 | 100 | 100 | 0 | 19026 | 19026 | 19026 | 17656.1032 | 1 | 1.0776 | FALSE | FALSE | FALSE | 23 | FALSE | 0 | Green | Continue normal monitoring.
146873 | HCMEF3Z1345 | F3 Z1 :Exhaust Fans | 26661 | 2013-11-11 16:00 | 2013-12-02 16:00 | 21 | 184 | 100 | 90 | -10 | 41286 | 41286 | 37157.4 | 40269.9905 | 0.9 | 0.92271 | FALSE | FALSE | FALSE | 23 | FALSE | 0 | Green | Continue normal monitoring.
146874 | HCMEF3Z1355 | F3 Z1 :Grills & Diffusers | 26661 | 2014-03-11 16:00 | 2014-03-25 16:00 | 14 | 16 | 100 | 94 | -6 | 26278 | 26278 | 24701.32 | 28859.0971 | 0.94 | 0.85593 | TRUE | FALSE | FALSE | 2 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146875 | HCMEF3Z1365 | F3 Z1 :Mechanical final Fix | 26661 | 2014-03-27 16:00 | 2014-04-10 16:00 | 14 | 0 | 100 | 100 | 0 | 19418 | 19418 | 19418 | 21463.4926 | 1 | 0.9047 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146876 | HCMEF3Z1375 | F3 Z1 :All Vertical Piping Works | 26662 | 2013-04-08 08:00 | 2013-04-19 17:00 | 11 | 591 | 100 | 100 | 0 | 11627 | 11627 | 11627 | 13135.6486 | 1 | 0.88515 | TRUE | FALSE | FALSE | 73.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146877 | HCMEF3Z1385 | F3 Z1 :All Horizantal Piping Works | 26662 | 2013-04-22 08:00 | 2013-05-31 17:00 | 39 | 591 | 100 | 84 | -16 | 40911 | 40911 | 34365.24 | 36607.3545 | 0.84 | 0.93875 | FALSE | TRUE | TRUE | 73.875 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146878 | HCMEF3Z1395 | F3 Z1 :Mechanical Final Fix | 26662 | 2013-12-09 08:00 | 2014-01-03 17:00 | 25 | 231 | 100 | 99 | -1 | 16025 | 16025 | 15864.75 | 19066.317 | 0.99 | 0.83208 | TRUE | FALSE | FALSE | 28.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146879 | HCMEF3Z2160 | F3 Z2 :Blocks Start Date for All Parts | 26456 | 2013-06-02 16:00 | 2013-06-02 16:00 | 1 | 992 | 100 | 89 | -11 | 1111 | 1111 | 988.79 | 1181.1473 | 0.89 | 0.83714 | TRUE | TRUE | TRUE | 124 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146880 | HCMEF3Z2170 | F3 Z2 :Tiling Finish Date for All Parts | 26456 | 2013-09-16 16:00 | 2013-09-16 16:00 | 1 | 624 | 100 | 91 | -9 | 1000 | 1000 | 910 | 1038.5287 | 0.91 | 0.87624 | TRUE | FALSE | FALSE | 78 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146881 | HCMEF3Z2180 | F3 Z2 :Plastering Finish Date for All Parts | 26456 | 2013-08-01 16:00 | 2013-08-01 16:00 | 1 | 1136 | 100 | 94 | -6 | 1339 | 1339 | 1258.66 | 1663.6259 | 0.94 | 0.75658 | TRUE | FALSE | FALSE | 142 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146882 | HCMEF3Z2190 | F3 Z2 :Gypsum Boards Finish Date for All Parts | 26456 | 2014-02-18 16:00 | 2014-02-18 16:00 | 1 | 640 | 100 | 96 | -4 | 1201 | 1201 | 1152.96 | 1376.5277 | 0.96 | 0.83759 | TRUE | FALSE | FALSE | 80 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146883 | HCMEF3Z2220 | F3 Z2 :Electrical Coduits & Boards F.F for All Systems | 26456 | 2013-06-03 08:00 | 2013-06-18 17:00 | 15 | 831 | 100 | 89 | -11 | 16425 | 16425 | 14618.25 | 14736.5496 | 0.89 | 0.99197 | FALSE | TRUE | TRUE | 103.875 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146884 | HCMEF3Z2230 | F3 Z2 :Electrical Boards Seconed Fix | 26456 | 2013-09-05 16:00 | 2013-09-23 16:00 | 18 | 776 | 100 | 85 | -15 | 14040 | 14040 | 11934 | 16182.724 | 0.85 | 0.73745 | TRUE | TRUE | TRUE | 97 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146885 | HCMEF3Z2240 | F3 Z2 :Cable Tray Installation | 26456 | 2014-01-01 16:00 | 2014-01-15 16:00 | 14 | 88 | 100 | 97 | -3 | 12922 | 12922 | 12534.34 | 11476.0227 | 0.97 | 1.0922 | FALSE | FALSE | FALSE | 11 | FALSE | 0 | Green | Continue normal monitoring.
146886 | HCMEF3Z2250 | F3 Z2 :Electrcial Wiring | 26456 | 2013-11-11 08:00 | 2013-12-06 17:00 | 25 | 215 | 100 | 92 | -8 | 33875 | 33875 | 31165 | 29165.9761 | 0.92 | 1.0685 | FALSE | FALSE | FALSE | 26.875 | FALSE | 0 | Green | Continue normal monitoring.
146887 | HCMEF3Z2260 | F3 Z2 :Cable Laying | 26456 | 2014-01-15 16:00 | 2014-01-29 16:00 | 14 | 88 | 100 | 82 | -18 | 10766 | 10766 | 8828.12 | 10889.2746 | 0.82 | 0.81072 | TRUE | TRUE | TRUE | 11 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146888 | HCMEF3Z2270 | F3 Z2 :Electrical Final Fix for All Systems & Boards (Vertical Elements) | 26456 | 2014-03-12 16:00 | 2014-03-26 16:00 | 14 | 328 | 100 | 100 | 0 | 9142 | 9142 | 9142 | 11404.0167 | 1 | 0.80165 | TRUE | FALSE | FALSE | 41 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146889 | HCMEF3Z2280 | F3 Z2 :Electrical Final Fix for All Systems (Horizantel Elements) | 26456 | 2014-03-26 16:00 | 2014-04-09 16:00 | 14 | 328 | 100 | 100 | 0 | 15582 | 15582 | 15582 | 14334.7166 | 1 | 1.087 | FALSE | FALSE | FALSE | 41 | FALSE | 0 | Green | Continue normal monitoring.
146890 | HCMEF3Z2070 | F3 Z2 :All Vertical Piping Works | 26455 | 2013-04-08 08:00 | 2013-04-19 17:00 | 11 | 751 | 100 | 89 | -11 | 12771 | 12771 | 11366.19 | 14291.4864 | 0.89 | 0.79531 | TRUE | TRUE | TRUE | 93.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146891 | HCMEF3Z2080 | F3 Z2 :All Horizantal Piping Works | 26455 | 2013-04-22 08:00 | 2013-05-31 17:00 | 39 | 751 | 100 | 100 | 0 | 22698 | 22698 | 22698 | 20867.5976 | 1 | 1.0877 | FALSE | FALSE | FALSE | 93.875 | FALSE | 0 | Green | Continue normal monitoring.
146892 | HCMEF3Z2090 | F3 Z2 :Mechanical Final Fix | 26455 | 2013-12-09 08:00 | 2014-01-03 17:00 | 25 | 391 | 100 | 93 | -7 | 36150 | 36150 | 33619.5 | 41207.9197 | 0.93 | 0.81585 | TRUE | FALSE | FALSE | 48.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146893 | HCMEF3Z2100 | F3 Z2 :Horizontal F.F Piping Work | 26457 | 2013-06-03 08:00 | 2013-06-28 17:00 | 25 | 991 | 100 | 85 | -15 | 34950 | 34950 | 29707.5 | 36772.3443 | 0.85 | 0.80788 | TRUE | TRUE | TRUE | 123.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146894 | HCMEF3Z2110 | F3 Z2 :Fire Hose Cabinets | 26457 | 2013-07-01 08:00 | 2013-07-12 17:00 | 11 | 991 | 100 | 82 | -18 | 21439 | 21439 | 17579.98 | 24054.3154 | 0.82 | 0.73085 | TRUE | TRUE | TRUE | 123.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146895 | HCMEF3Z2120 | F3 Z2 :Sprinklers Final Fix | 26457 | 2014-02-10 16:00 | 2014-02-24 16:00 | 14 | 344 | 100 | 95 | -5 | 25172 | 25172 | 23913.4 | 23438.8894 | 0.95 | 1.0202 | FALSE | FALSE | FALSE | 43 | FALSE | 0 | Green | Continue normal monitoring.
146896 | HCMEF3Z2330 | F3 Z2 :Duct Installation& Dusct Accecories Installation, Fan coil Unit | 26458 | 2013-09-27 16:00 | 2013-10-09 16:00 | 12 | 233 | 100 | 86 | -14 | 9396 | 9396 | 8080.56 | 10788.9695 | 0.86 | 0.74896 | TRUE | TRUE | TRUE | 29.125 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146897 | HCMEF3Z2340 | F3 Z2 :Duct Insulation Work | 26458 | 2013-10-09 16:00 | 2013-10-30 16:00 | 21 | 233 | 100 | 99 | -1 | 31059 | 31059 | 30748.41 | 38769.3229 | 0.99 | 0.79311 | TRUE | FALSE | FALSE | 29.125 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146898 | HCMEF3Z2350 | F3 Z2 :Exhaust Fans | 26458 | 2013-10-30 16:00 | 2013-11-20 16:00 | 21 | 233 | 100 | 93 | -7 | 14112 | 14112 | 13124.16 | 15752.6639 | 0.93 | 0.83314 | TRUE | FALSE | FALSE | 29.125 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146899 | HCMEF3Z2360 | F3 Z2 :Grills & Diffusers | 26458 | 2014-03-06 16:00 | 2014-03-20 16:00 | 14 | 25 | 100 | 88 | -12 | 25900 | 25900 | 22792 | 27127.4528 | 0.88 | 0.84018 | TRUE | TRUE | TRUE | 3.125 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
146900 | HCMEF3Z2370 | F3 Z2 :Mechanical final Fix | 26458 | 2014-03-20 16:00 | 2014-04-03 16:00 | 14 | 25 | 100 | 94 | -6 | 22204 | 22204 | 20871.76 | 27072.6621 | 0.94 | 0.77095 | TRUE | FALSE | FALSE | 3.125 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146901 | HCMEF3Z2380 | F3 Z2 :All Vertical Piping Works | 26459 | 2013-04-08 08:00 | 2013-04-19 17:00 | 11 | 751 | 100 | 100 | 0 | 17556 | 17556 | 17556 | 15033.918 | 1 | 1.1678 | FALSE | FALSE | FALSE | 93.875 | FALSE | 0 | Green | Continue normal monitoring.
146902 | HCMEF3Z2390 | F3 Z2 :All Horizantal Piping Works | 26459 | 2013-04-22 08:00 | 2013-05-31 17:00 | 39 | 751 | 100 | 82 | -18 | 49218 | 49218 | 40358.76 | 56205.4503 | 0.82 | 0.71806 | TRUE | TRUE | TRUE | 93.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146903 | HCMEF3Z2400 | F3 Z2 :Mechanical Final Fix | 26459 | 2013-12-09 08:00 | 2014-01-03 17:00 | 25 | 391 | 100 | 81 | -19 | 47450 | 47450 | 38434.5 | 57200.9089 | 0.81 | 0.67192 | TRUE | TRUE | TRUE | 48.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146904 | HCMEF3Z3165 | F3 Z3 :Blocks Start Date for All Parts | 26462 | 2013-08-01 16:00 | 2013-08-01 16:00 | 1 | 696 | 100 | 100 | 0 | 1132 | 1132 | 1132 | 990.1263 | 1 | 1.1433 | FALSE | FALSE | FALSE | 87 | FALSE | 0 | Green | Continue normal monitoring.
146905 | HCMEF3Z3175 | F3 Z3 :Tiling Finish Date for All Parts | 26462 | 2014-01-07 16:00 | 2014-01-07 16:00 | 1 | 448 | 100 | 81 | -19 | 1286 | 1286 | 1041.66 | 1324.613 | 0.81 | 0.78639 | TRUE | TRUE | TRUE | 56 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146906 | HCMEF3Z3185 | F3 Z3 :Plastering Finish Date for All Parts | 26462 | 2013-10-26 16:00 | 2013-10-26 16:00 | 1 | 648 | 100 | 82 | -18 | 1442 | 1442 | 1182.44 | 1343.7822 | 0.82 | 0.87993 | TRUE | TRUE | TRUE | 81 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146907 | HCMEF3Z3195 | F3 Z3 :Gypsum Boards Finish Date for All Parts | 26462 | 2014-03-30 16:00 | 2014-03-30 16:00 | 1 | 368 | 100 | 97 | -3 | 1511 | 1511 | 1465.67 | 1626.7536 | 0.97 | 0.90098 | FALSE | FALSE | FALSE | 46 | FALSE | 0 | Green | Continue normal monitoring.
146908 | HCMEF3Z3225 | F3 Z3 :Electrical Coduits & Boards F.F for All Systems | 26462 | 2013-08-01 16:00 | 2013-08-19 16:00 | 18 | 576 | 100 | 93 | -7 | 16146 | 16146 | 15015.78 | 17919.1082 | 0.93 | 0.83798 | TRUE | FALSE | FALSE | 72 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146909 | HCMEF3Z3235 | F3 Z3 :Electrical Boards Seconed Fix | 26462 | 2013-11-12 16:00 | 2013-11-28 16:00 | 16 | 488 | 100 | 99 | -1 | 26288 | 26288 | 26025.12 | 25526.9433 | 0.99 | 1.0195 | FALSE | FALSE | FALSE | 61 | FALSE | 0 | Green | Continue normal monitoring.
146910 | HCMEF3Z3245 | F3 Z3 :Cable Tray Installation | 26462 | 2014-01-01 16:00 | 2014-01-15 16:00 | 14 | 168 | 100 | 97 | -3 | 20062 | 20062 | 19460.14 | 20743.9609 | 0.97 | 0.93811 | FALSE | FALSE | FALSE | 21 | FALSE | 0 | Green | Continue normal monitoring.
146911 | HCMEF3Z3255 | F3 Z3 :Electrcial Wiring | 26462 | 2014-01-21 16:00 | 2014-01-29 16:00 | 8 | 296 | 100 | 89 | -11 | 15680 | 15680 | 13955.2 | 15080.0173 | 0.89 | 0.92541 | FALSE | TRUE | TRUE | 37 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146912 | HCMEF3Z3265 | F3 Z3 :Cable Laying | 26462 | 2014-01-15 16:00 | 2014-01-29 16:00 | 14 | 168 | 100 | 100 | 0 | 16450 | 16450 | 16450 | 16413.0939 | 1 | 1.0022 | FALSE | FALSE | FALSE | 21 | FALSE | 0 | Green | Continue normal monitoring.
146913 | HCMEF3Z3275 | F3 Z3 :Electrical Final Fix for All Systems & Boards (Vertical Elements) | 26462 | 2014-03-12 16:00 | 2014-03-26 16:00 | 14 | 328 | 100 | 81 | -19 | 20090 | 20090 | 16272.9 | 18358.5631 | 0.81 | 0.88639 | TRUE | TRUE | TRUE | 41 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146914 | HCMEF3Z3285 | F3 Z3 :Electrical Final Fix for All Systems (Horizantel Elements) | 26462 | 2014-03-31 08:00 | 2014-04-11 17:00 | 11 | 311 | 100 | 100 | 0 | 10604 | 10604 | 10604 | 12769.5889 | 1 | 0.83041 | TRUE | FALSE | FALSE | 38.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146915 | HCMEF3Z3075 | F3 Z3 :All Vertical Piping Works | 26461 | 2013-04-08 08:00 | 2013-04-19 17:00 | 11 | 751 | 100 | 100 | 0 | 8635 | 8635 | 8635 | 7374.326 | 1 | 1.171 | FALSE | FALSE | FALSE | 93.875 | FALSE | 0 | Green | Continue normal monitoring.
146916 | HCMEF3Z3085 | F3 Z3 :All Horizantal Piping Works | 26461 | 2013-04-22 08:00 | 2013-05-31 17:00 | 39 | 751 | 100 | 100 | 0 | 29796 | 29796 | 29796 | 35843.5056 | 1 | 0.83128 | TRUE | FALSE | FALSE | 93.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146917 | HCMEF3Z3095 | F3 Z3 :Mechanical Final Fix | 26461 | 2013-12-09 08:00 | 2014-01-03 17:00 | 25 | 391 | 100 | 80 | -20 | 20475 | 20475 | 16380 | 22085.8 | 0.8 | 0.74165 | TRUE | TRUE | TRUE | 48.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146918 | HCMEF3Z3105 | F3 Z3 :Horizontal F.F Piping Work | 26463 | 2013-08-01 16:00 | 2013-08-29 16:00 | 28 | 640 | 100 | 83 | -17 | 32816 | 32816 | 27237.28 | 32247.0735 | 0.83 | 0.84464 | TRUE | TRUE | TRUE | 80 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146919 | HCMEF3Z3115 | F3 Z3 :Fire Hose Cabinets | 26463 | 2013-08-29 16:00 | 2013-09-12 16:00 | 14 | 640 | 100 | 100 | 0 | 26586 | 26586 | 26586 | 30287.3787 | 1 | 0.87779 | TRUE | FALSE | FALSE | 80 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146920 | HCMEF3Z3125 | F3 Z3 :Sprinklers Final Fix | 26463 | 2014-02-10 16:00 | 2014-02-24 16:00 | 14 | 344 | 100 | 93 | -7 | 18466 | 18466 | 17173.38 | 19446.5605 | 0.93 | 0.88311 | TRUE | FALSE | FALSE | 43 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146921 | HCMEF3Z3335 | F3 Z3 :Duct Installation& Dusct Accecories Installation, Fan coil Unit | 26464 | 2013-10-09 16:00 | 2013-10-21 16:00 | 12 | 264 | 100 | 80 | -20 | 7056 | 7056 | 5644.8 | 7406.2843 | 0.8 | 0.76216 | TRUE | TRUE | TRUE | 33 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146922 | HCMEF3Z3345 | F3 Z3 :Duct Insulation Work | 26464 | 2013-10-21 16:00 | 2013-11-11 16:00 | 21 | 264 | 100 | 93 | -7 | 36246 | 36246 | 33708.78 | 32405.9869 | 0.93 | 1.0402 | FALSE | FALSE | FALSE | 33 | FALSE | 0 | Green | Continue normal monitoring.
146923 | HCMEF3Z3355 | F3 Z3 :Exhaust Fans | 26464 | 2013-11-11 16:00 | 2013-12-02 16:00 | 21 | 264 | 100 | 95 | -5 | 27720 | 27720 | 26334 | 27880.9537 | 0.95 | 0.94452 | FALSE | FALSE | FALSE | 33 | FALSE | 0 | Green | Continue normal monitoring.
146924 | HCMEF3Z3365 | F3 Z3 :Grills & Diffusers | 26464 | 2014-03-06 16:00 | 2014-03-20 16:00 | 14 | 120 | 100 | 100 | 0 | 21000 | 21000 | 21000 | 19874.9405 | 1 | 1.0566 | FALSE | FALSE | FALSE | 15 | FALSE | 0 | Green | Continue normal monitoring.
146925 | HCMEF3Z3375 | F3 Z3 :Mechanical final Fix | 26464 | 2014-03-20 16:00 | 2014-04-03 16:00 | 14 | 120 | 100 | 93 | -7 | 11662 | 11662 | 10845.66 | 9985.9183 | 0.93 | 1.0861 | FALSE | FALSE | FALSE | 15 | FALSE | 0 | Green | Continue normal monitoring.
146926 | HCMEF3Z3385 | F3 Z3 :All Vertical Piping Works | 26465 | 2013-04-08 08:00 | 2013-04-19 17:00 | 11 | 751 | 100 | 100 | 0 | 7931 | 7931 | 7931 | 7883.7301 | 1 | 1.006 | FALSE | FALSE | FALSE | 93.875 | FALSE | 0 | Green | Continue normal monitoring.
146927 | HCMEF3Z3395 | F3 Z3 :All Horizantal Piping Works | 26465 | 2013-04-22 08:00 | 2013-05-31 17:00 | 39 | 751 | 100 | 99 | -1 | 21060 | 21060 | 20849.4 | 18657.6616 | 0.99 | 1.1175 | FALSE | FALSE | FALSE | 93.875 | FALSE | 0 | Green | Continue normal monitoring.
146928 | HCMEF3Z3405 | F3 Z3 :Mechanical Final Fix | 26465 | 2013-12-09 08:00 | 2014-01-03 17:00 | 25 | 391 | 100 | 82 | -18 | 14175 | 14175 | 11623.5 | 13504.9763 | 0.82 | 0.86068 | TRUE | TRUE | TRUE | 48.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146929 | HCMEF4Z1160 | F4 Z1 :Blocks Start Date for All Parts | 26471 | 2013-04-16 16:00 | 2013-04-16 16:00 | 1 | 1344 | 100 | 82 | -18 | 1487 | 1487 | 1219.34 | 1318.9789 | 0.82 | 0.92446 | FALSE | TRUE | TRUE | 168 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146930 | HCMEF4Z1170 | F4 Z1 :Tiling Finish Date for All Parts | 26471 | 2013-10-10 16:00 | 2013-10-10 16:00 | 1 | 640 | 100 | 88 | -12 | 1013 | 1013 | 891.44 | 901.9515 | 0.88 | 0.98835 | FALSE | TRUE | TRUE | 80 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146931 | HCMEF4Z1180 | F4 Z1 :Plastering Finish Date for All Parts | 26471 | 2013-06-24 12:00 | 2013-06-24 12:00 | 1 | 1395 | 100 | 85 | -15 | 1650 | 1650 | 1402.5 | 1533.8475 | 0.85 | 0.91437 | FALSE | TRUE | TRUE | 174.375 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146932 | HCMEF4Z1190 | F4 Z1 :Gypsum Boards Finish Date for All Parts | 26471 | 2014-03-08 16:00 | 2014-03-08 16:00 | 1 | 520 | 100 | 100 | 0 | 1778 | 1778 | 1778 | 2222.3928 | 1 | 0.80004 | TRUE | FALSE | FALSE | 65 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146933 | HCMEF4Z1220 | F4 Z1 :Electrical Coduits & Boards F.F for All Systems | 26471 | 2013-04-16 16:00 | 2013-05-02 16:00 | 16 | 1120 | 100 | 92 | -8 | 19104 | 19104 | 17575.68 | 16255.0903 | 0.92 | 1.0812 | FALSE | FALSE | FALSE | 140 | FALSE | 0 | Green | Continue normal monitoring.
146934 | HCMEF4Z1230 | F4 Z1 :Electrical Boards Seconed Fix | 26471 | 2013-08-09 16:00 | 2013-08-27 16:00 | 18 | 952 | 100 | 100 | 0 | 27702 | 27702 | 27702 | 30623.7037 | 1 | 0.90459 | FALSE | FALSE | FALSE | 119 | FALSE | 0 | Green | Continue normal monitoring.
146935 | HCMEF4Z1240 | F4 Z1 :Cable Tray Installation | 26471 | 2014-01-15 16:00 | 2014-01-29 16:00 | 14 | 0 | 100 | 81 | -19 | 13664 | 13664 | 11067.84 | 12386.3816 | 0.81 | 0.89355 | TRUE | TRUE | TRUE | 0 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
146936 | HCMEF4Z1250 | F4 Z1 :Electrcial Wiring | 26471 | 2014-01-13 08:00 | 2014-02-07 17:00 | 25 | 15 | 100 | 87 | -13 | 39625 | 39625 | 34473.75 | 48273.206 | 0.87 | 0.71414 | TRUE | TRUE | TRUE | 1.875 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
146937 | HCMEF4Z1260 | F4 Z1 :Cable Laying | 26471 | 2014-02-04 16:00 | 2014-02-18 16:00 | 14 | 0 | 100 | 100 | 0 | 19320 | 19320 | 19320 | 17145.595 | 1 | 1.1268 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146938 | HCMEF4Z1270 | F4 Z1 :Electrical Final Fix for All Systems & Boards (Vertical Elements) | 26471 | 2014-04-01 16:00 | 2014-04-15 16:00 | 14 | 216 | 100 | 81 | -19 | 13034 | 13034 | 10557.54 | 16058.2174 | 0.81 | 0.65745 | TRUE | TRUE | TRUE | 27 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146939 | HCMEF4Z1280 | F4 Z1 :Electrical Final Fix for All Systems (Horizantel Elements) | 26471 | 2014-04-15 16:00 | 2014-04-29 16:00 | 14 | 216 | 100 | 83 | -17 | 10738 | 10738 | 8912.54 | 11751.351 | 0.83 | 0.75843 | TRUE | TRUE | TRUE | 27 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146940 | HCMEF4Z1070 | F4 Z1 :All Vertical Piping Works | 26470 | 2013-04-17 08:00 | 2013-04-30 17:00 | 13 | 695 | 100 | 100 | 0 | 20254 | 20254 | 20254 | 17226.1735 | 1 | 1.1758 | FALSE | FALSE | FALSE | 86.875 | FALSE | 0 | Green | Continue normal monitoring.
146941 | HCMEF4Z1080 | F4 Z1 :All Horizantal Piping Works | 26470 | 2013-05-01 08:00 | 2013-06-11 17:00 | 41 | 695 | 100 | 94 | -6 | 52398 | 52398 | 49254.12 | 63275.9757 | 0.94 | 0.7784 | TRUE | FALSE | FALSE | 86.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146942 | HCMEF4Z1090 | F4 Z1 :Mechanical Final Fix | 26470 | 2014-01-06 08:00 | 2014-01-31 17:00 | 25 | 231 | 100 | 83 | -17 | 24825 | 24825 | 20604.75 | 26281.8482 | 0.83 | 0.78399 | TRUE | TRUE | TRUE | 28.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146943 | HCMEF4Z1100 | F4 Z1 :Horizontal F.F Piping Work | 26472 | 2013-04-16 16:00 | 2013-05-14 16:00 | 28 | 1256 | 100 | 92 | -8 | 55776 | 55776 | 51313.92 | 53269.8669 | 0.92 | 0.96328 | FALSE | FALSE | FALSE | 157 | FALSE | 0 | Green | Continue normal monitoring.
146944 | HCMEF4Z1110 | F4 Z1 :Fire Hose Cabinets | 26472 | 2013-05-14 16:00 | 2013-05-28 16:00 | 14 | 1256 | 100 | 100 | 0 | 16240 | 16240 | 16240 | 18788.2455 | 1 | 0.86437 | TRUE | FALSE | FALSE | 157 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146945 | HCMEF4Z1120 | F4 Z1 :Sprinklers Final Fix | 26472 | 2014-02-24 16:00 | 2014-03-10 16:00 | 14 | 264 | 100 | 91 | -9 | 25872 | 25872 | 23543.52 | 31581.0765 | 0.91 | 0.74549 | TRUE | FALSE | FALSE | 33 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146946 | HCMEF4Z1330 | F4 Z1 :Duct Installation& Dusct Accecories Installation, Fan coil Unit | 26473 | 2013-10-21 16:00 | 2013-11-04 16:00 | 14 | 184 | 100 | 100 | 0 | 25578 | 25578 | 25578 | 26690.0375 | 1 | 0.95834 | FALSE | FALSE | FALSE | 23 | FALSE | 0 | Green | Continue normal monitoring.
146947 | HCMEF4Z1340 | F4 Z1 :Duct Insulation Work | 26473 | 2013-11-04 16:00 | 2013-11-25 16:00 | 21 | 184 | 100 | 92 | -8 | 37779 | 37779 | 34756.68 | 36880.6679 | 0.92 | 0.94241 | FALSE | FALSE | FALSE | 23 | FALSE | 0 | Green | Continue normal monitoring.
146948 | HCMEF4Z1350 | F4 Z1 :Exhaust Fans | 26473 | 2013-11-25 16:00 | 2013-12-16 16:00 | 21 | 184 | 100 | 100 | 0 | 31752 | 31752 | 31752 | 37009.4342 | 1 | 0.85794 | TRUE | FALSE | FALSE | 23 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146949 | HCMEF4Z1360 | F4 Z1 :Grills & Diffusers | 26473 | 2014-03-25 16:00 | 2014-04-08 16:00 | 14 | 16 | 100 | 93 | -7 | 24136 | 24136 | 22446.48 | 27097.8299 | 0.93 | 0.82835 | TRUE | FALSE | FALSE | 2 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146950 | HCMEF4Z1370 | F4 Z1 :Mechanical final Fix | 26473 | 2014-04-10 16:00 | 2014-04-24 16:00 | 14 | 0 | 100 | 99 | -1 | 27552 | 27552 | 27276.48 | 33213.9634 | 0.99 | 0.82124 | TRUE | FALSE | FALSE | 0 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146951 | HCMEF4Z1380 | F4 Z1 :All Vertical Piping Works | 26474 | 2013-04-17 08:00 | 2013-04-30 17:00 | 13 | 695 | 100 | 97 | -3 | 24011 | 24011 | 23290.67 | 27060.5316 | 0.97 | 0.86069 | TRUE | FALSE | FALSE | 86.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146952 | HCMEF4Z1390 | F4 Z1 :All Horizantal Piping Works | 26474 | 2013-05-01 08:00 | 2013-06-11 17:00 | 41 | 695 | 100 | 100 | 0 | 63878 | 63878 | 63878 | 60518.7413 | 1 | 1.0555 | FALSE | FALSE | FALSE | 86.875 | FALSE | 0 | Green | Continue normal monitoring.
146953 | HCMEF4Z1400 | F4 Z1 :Mechanical Final Fix | 26474 | 2014-01-06 08:00 | 2014-01-31 17:00 | 25 | 231 | 100 | 100 | 0 | 36900 | 36900 | 36900 | 45116.2905 | 1 | 0.81789 | TRUE | FALSE | FALSE | 28.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146954 | HCMEF4Z2165 | F4 Z2 :Blocks Start Date for All Parts | 26477 | 2013-06-13 16:00 | 2013-06-13 16:00 | 1 | 1032 | 100 | 100 | 0 | 981 | 981 | 981 | 874.9875 | 1 | 1.1212 | FALSE | FALSE | FALSE | 129 | FALSE | 0 | Green | Continue normal monitoring.
146955 | HCMEF4Z2175 | F4 Z2 :Tiling Finish Date for All Parts | 26477 | 2013-10-14 16:00 | 2013-10-14 16:00 | 1 | 616 | 100 | 85 | -15 | 1227 | 1227 | 1042.95 | 1174.4563 | 0.85 | 0.88803 | TRUE | TRUE | TRUE | 77 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146956 | HCMEF4Z2185 | F4 Z2 :Plastering Finish Date for All Parts | 26477 | 2013-09-02 16:00 | 2013-09-02 16:00 | 1 | 1016 | 100 | 100 | 0 | 979 | 979 | 979 | 1035.8582 | 1 | 0.94511 | FALSE | FALSE | FALSE | 127 | FALSE | 0 | Green | Continue normal monitoring.
146957 | HCMEF4Z2195 | F4 Z2 :Gypsum Boards Finish Date for All Parts | 26477 | 2014-03-06 16:00 | 2014-03-06 16:00 | 1 | 528 | 100 | 90 | -10 | 1588 | 1588 | 1429.2 | 1709.1593 | 0.9 | 0.8362 | TRUE | FALSE | FALSE | 66 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146958 | HCMEF4Z2225 | F4 Z2 :Electrical Coduits & Boards F.F for All Systems | 26477 | 2013-06-13 16:00 | 2013-07-01 16:00 | 18 | 856 | 100 | 100 | 0 | 27558 | 27558 | 27558 | 23593.0717 | 1 | 1.1681 | FALSE | FALSE | FALSE | 107 | FALSE | 0 | Green | Continue normal monitoring.
146959 | HCMEF4Z2235 | F4 Z2 :Electrical Boards Seconed Fix | 26477 | 2013-09-23 16:00 | 2013-10-09 16:00 | 16 | 776 | 100 | 81 | -19 | 29184 | 29184 | 23639.04 | 33918.4938 | 0.81 | 0.69694 | TRUE | TRUE | TRUE | 97 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146960 | HCMEF4Z2245 | F4 Z2 :Cable Tray Installation | 26477 | 2014-01-15 16:00 | 2014-01-29 16:00 | 14 | 88 | 100 | 100 | 0 | 11788 | 11788 | 11788 | 11724.8508 | 1 | 1.0054 | FALSE | FALSE | FALSE | 11 | FALSE | 0 | Green | Continue normal monitoring.
146961 | HCMEF4Z2255 | F4 Z2 :Electrcial Wiring | 26477 | 2013-12-09 08:00 | 2014-01-03 17:00 | 25 | 215 | 100 | 100 | 0 | 48850 | 48850 | 48850 | 49463.9183 | 1 | 0.98759 | FALSE | FALSE | FALSE | 26.875 | FALSE | 0 | Green | Continue normal monitoring.
146962 | HCMEF4Z2265 | F4 Z2 :Cable Laying | 26477 | 2014-01-29 16:00 | 2014-02-12 16:00 | 14 | 88 | 100 | 98 | -2 | 27258 | 27258 | 26712.84 | 31994.018 | 0.98 | 0.83493 | TRUE | FALSE | FALSE | 11 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146963 | HCMEF4Z2275 | F4 Z2 :Electrical Final Fix for All Systems & Boards (Vertical Elements) | 26477 | 2014-03-26 16:00 | 2014-04-09 16:00 | 14 | 248 | 100 | 100 | 0 | 11634 | 11634 | 11634 | 11653.9332 | 1 | 0.99829 | FALSE | FALSE | FALSE | 31 | FALSE | 0 | Green | Continue normal monitoring.
146964 | HCMEF4Z2285 | F4 Z2 :Electrical Final Fix for All Systems (Horizantel Elements) | 26477 | 2014-04-09 16:00 | 2014-04-23 16:00 | 14 | 248 | 100 | 98 | -2 | 13118 | 13118 | 12855.64 | 11398.0984 | 0.98 | 1.1279 | FALSE | FALSE | FALSE | 31 | FALSE | 0 | Green | Continue normal monitoring.
146965 | HCMEF4Z2075 | F4 Z2 :All Vertical Piping Works | 26476 | 2013-04-17 08:00 | 2013-04-30 17:00 | 13 | 760 | 100 | 84 | -16 | 8749 | 8749 | 7349.16 | 8054.1186 | 0.84 | 0.91247 | FALSE | TRUE | TRUE | 95 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146966 | HCMEF4Z2085 | F4 Z2 :All Horizantal Piping Works | 26476 | 2013-05-01 08:00 | 2013-06-11 17:00 | 41 | 855 | 100 | 98 | -2 | 43378 | 43378 | 42510.44 | 53457.3671 | 0.98 | 0.79522 | TRUE | FALSE | FALSE | 106.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146967 | HCMEF4Z2095 | F4 Z2 :Mechanical Final Fix | 26476 | 2014-01-06 08:00 | 2014-01-31 17:00 | 25 | 391 | 100 | 81 | -19 | 25650 | 25650 | 20776.5 | 22524.859 | 0.81 | 0.92238 | FALSE | TRUE | TRUE | 48.875 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146968 | HCMEF4Z2105 | F4 Z2 :Horizontal F.F Piping Work | 26478 | 2013-06-13 16:00 | 2013-07-11 16:00 | 28 | 1000 | 100 | 89 | -11 | 32424 | 32424 | 28857.36 | 32163.7157 | 0.89 | 0.8972 | TRUE | TRUE | TRUE | 125 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146969 | HCMEF4Z2115 | F4 Z2 :Fire Hose Cabinets | 26478 | 2013-07-11 16:00 | 2013-07-25 16:00 | 14 | 1000 | 100 | 100 | 0 | 7350 | 7350 | 7350 | 7726.8468 | 1 | 0.95123 | FALSE | FALSE | FALSE | 125 | FALSE | 0 | Green | Continue normal monitoring.
146970 | HCMEF4Z2125 | F4 Z2 :Sprinklers Final Fix | 26478 | 2014-02-24 16:00 | 2014-03-10 16:00 | 14 | 344 | 100 | 81 | -19 | 18466 | 18466 | 14957.46 | 19339.6695 | 0.81 | 0.77341 | TRUE | TRUE | TRUE | 43 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146971 | HCMEF4Z2335 | F4 Z2 :Duct Installation& Dusct Accecories Installation, Fan coil Unit | 26479 | 2013-10-09 16:00 | 2013-10-21 16:00 | 12 | 249 | 100 | 100 | 0 | 13248 | 13248 | 13248 | 11281.7845 | 1 | 1.1743 | FALSE | FALSE | FALSE | 31.125 | FALSE | 0 | Green | Continue normal monitoring.
146972 | HCMEF4Z2345 | F4 Z2 :Duct Insulation Work | 26479 | 2013-10-21 16:00 | 2013-11-11 16:00 | 21 | 249 | 100 | 90 | -10 | 19005 | 19005 | 17104.5 | 19964.0891 | 0.9 | 0.85676 | TRUE | FALSE | FALSE | 31.125 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146973 | HCMEF4Z2355 | F4 Z2 :Exhaust Fans | 26479 | 2013-11-11 16:00 | 2013-12-02 16:00 | 21 | 249 | 100 | 97 | -3 | 15351 | 15351 | 14890.47 | 15404.8664 | 0.97 | 0.96661 | FALSE | FALSE | FALSE | 31.125 | FALSE | 0 | Green | Continue normal monitoring.
146974 | HCMEF4Z2365 | F4 Z2 :Grills & Diffusers | 26479 | 2014-03-20 16:00 | 2014-04-03 16:00 | 14 | 25 | 100 | 100 | 0 | 14448 | 14448 | 14448 | 17898.6409 | 1 | 0.80721 | TRUE | FALSE | FALSE | 3.125 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146975 | HCMEF4Z2375 | F4 Z2 :Mechanical final Fix | 26479 | 2014-04-03 16:00 | 2014-04-17 16:00 | 14 | 25 | 100 | 100 | 0 | 14056 | 14056 | 14056 | 12842.456 | 1 | 1.0945 | FALSE | FALSE | FALSE | 3.125 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146976 | HCMEF4Z2385 | F4 Z2 :All Vertical Piping Works | 26480 | 2013-04-17 08:00 | 2013-04-30 17:00 | 13 | 855 | 100 | 100 | 0 | 8814 | 8814 | 8814 | 8740.506 | 1 | 1.0084 | FALSE | FALSE | FALSE | 106.875 | FALSE | 0 | Green | Continue normal monitoring.
146977 | HCMEF4Z2395 | F4 Z2 :All Horizantal Piping Works | 26480 | 2013-05-01 08:00 | 2013-06-11 17:00 | 41 | 855 | 100 | 94 | -6 | 25871 | 25871 | 24318.74 | 26331.3122 | 0.94 | 0.92357 | FALSE | FALSE | FALSE | 106.875 | FALSE | 0 | Green | Continue normal monitoring.
146978 | HCMEF4Z2405 | F4 Z2 :Mechanical Final Fix | 26480 | 2014-01-06 08:00 | 2014-01-31 17:00 | 25 | 391 | 100 | 88 | -12 | 49450 | 49450 | 43516 | 49760.4182 | 0.88 | 0.87451 | TRUE | TRUE | TRUE | 48.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146979 | HCMEF4Z3170 | F4 Z3 :Blocks Start Date for All Parts | 26483 | 2013-08-17 16:00 | 2013-08-17 16:00 | 1 | 704 | 100 | 100 | 0 | 847 | 847 | 847 | 945.5335 | 1 | 0.89579 | TRUE | FALSE | FALSE | 88 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146980 | HCMEF4Z3180 | F4 Z3 :Tiling Finish Date for All Parts | 26483 | 2014-02-05 16:00 | 2014-02-05 16:00 | 1 | 297 | 100 | 98 | -2 | 1039 | 1039 | 1018.22 | 972.7171 | 0.98 | 1.0468 | FALSE | FALSE | FALSE | 37.125 | FALSE | 0 | Green | Continue normal monitoring.
146981 | HCMEF4Z3190 | F4 Z3 :Plastering Finish Date for All Parts | 26483 | 2013-11-24 16:00 | 2013-11-24 16:00 | 1 | 544 | 100 | 88 | -12 | 1271 | 1271 | 1118.48 | 1192.7428 | 0.88 | 0.93774 | FALSE | TRUE | TRUE | 68 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146982 | HCMEF4Z3200 | F4 Z3 :Gypsum Boards Finish Date for All Parts | 26483 | 2014-04-15 16:00 | 2014-04-15 16:00 | 1 | 256 | 100 | 82 | -18 | 1929 | 1929 | 1581.78 | 2202.3092 | 0.82 | 0.71824 | TRUE | TRUE | TRUE | 32 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146983 | HCMEF4Z3230 | F4 Z3 :Electrical Coduits & Boards F.F for All Systems | 26483 | 2013-08-19 08:00 | 2013-09-03 17:00 | 15 | 583 | 100 | 100 | 0 | 8625 | 8625 | 8625 | 9057.2523 | 1 | 0.95228 | FALSE | FALSE | FALSE | 72.875 | FALSE | 0 | Green | Continue normal monitoring.
146984 | HCMEF4Z3240 | F4 Z3 :Electrical Boards Seconed Fix | 26483 | 2013-11-28 16:00 | 2013-12-16 16:00 | 18 | 488 | 100 | 88 | -12 | 19404 | 19404 | 17075.52 | 19715.6723 | 0.88 | 0.86609 | TRUE | TRUE | TRUE | 61 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146985 | HCMEF4Z3250 | F4 Z3 :Cable Tray Installation | 26483 | 2014-01-15 16:00 | 2014-01-29 16:00 | 14 | 168 | 100 | 100 | 0 | 18942 | 18942 | 18942 | 17382.7177 | 1 | 1.0897 | FALSE | FALSE | FALSE | 21 | FALSE | 0 | Green | Continue normal monitoring.
146986 | HCMEF4Z3260 | F4 Z3 :Electrcial Wiring | 26483 | 2014-02-05 16:00 | 2014-02-13 16:00 | 8 | 256 | 100 | 100 | 0 | 5544 | 5544 | 5544 | 5128.2604 | 1 | 1.0811 | FALSE | FALSE | FALSE | 32 | FALSE | 0 | Green | Continue normal monitoring.
146987 | HCMEF4Z3270 | F4 Z3 :Cable Laying | 26483 | 2014-01-29 16:00 | 2014-02-12 16:00 | 14 | 168 | 100 | 93 | -7 | 23590 | 23590 | 21938.7 | 20151.0652 | 0.93 | 1.0887 | FALSE | FALSE | FALSE | 21 | FALSE | 0 | Green | Continue normal monitoring.
146988 | HCMEF4Z3280 | F4 Z3 :Electrical Final Fix for All Systems & Boards (Vertical Elements) | 26483 | 2014-03-26 16:00 | 2014-04-09 16:00 | 14 | 248 | 100 | 98 | -2 | 11844 | 11844 | 11607.12 | 10500.5411 | 0.98 | 1.1054 | FALSE | FALSE | FALSE | 31 | FALSE | 0 | Green | Continue normal monitoring.
146989 | HCMEF4Z3290 | F4 Z3 :Electrical Final Fix for All Systems (Horizantel Elements) | 26483 | 2014-04-15 16:00 | 2014-04-29 16:00 | 14 | 216 | 100 | 86 | -14 | 20300 | 20300 | 17458 | 21776.5302 | 0.86 | 0.80169 | TRUE | TRUE | TRUE | 27 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146990 | HCMEF4Z3080 | F4 Z3 :All Vertical Piping Works | 26482 | 2013-04-17 08:00 | 2013-04-30 17:00 | 13 | 760 | 100 | 95 | -5 | 24492 | 24492 | 23267.4 | 29555.7027 | 0.95 | 0.78724 | TRUE | FALSE | FALSE | 95 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146991 | HCMEF4Z3090 | F4 Z3 :All Horizantal Piping Works | 26482 | 2013-05-01 08:00 | 2013-06-11 17:00 | 41 | 855 | 100 | 95 | -5 | 66010 | 66010 | 62709.5 | 63690.7985 | 0.95 | 0.98459 | FALSE | FALSE | FALSE | 106.875 | FALSE | 0 | Green | Continue normal monitoring.
146992 | HCMEF4Z3100 | F4 Z3 :Mechanical Final Fix | 26482 | 2014-01-06 08:00 | 2014-01-31 17:00 | 25 | 391 | 100 | 100 | 0 | 44625 | 44625 | 44625 | 43781.538 | 1 | 1.0193 | FALSE | FALSE | FALSE | 48.875 | FALSE | 0 | Green | Continue normal monitoring.
146993 | HCMEF4Z3110 | F4 Z3 :Horizontal F.F Piping Work | 26484 | 2013-08-19 08:00 | 2013-09-13 17:00 | 25 | 631 | 100 | 80 | -20 | 17825 | 17825 | 14260 | 15975.518 | 0.8 | 0.89262 | TRUE | TRUE | TRUE | 78.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146994 | HCMEF4Z3120 | F4 Z3 :Fire Hose Cabinets | 26484 | 2013-09-16 08:00 | 2013-09-27 17:00 | 11 | 631 | 100 | 83 | -17 | 11792 | 11792 | 9787.36 | 11856.2944 | 0.83 | 0.8255 | TRUE | TRUE | TRUE | 78.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146995 | HCMEF4Z3130 | F4 Z3 :Sprinklers Final Fix | 26484 | 2014-02-24 16:00 | 2014-03-10 16:00 | 14 | 344 | 100 | 83 | -17 | 17906 | 17906 | 14861.98 | 15486.6967 | 0.83 | 0.95966 | FALSE | TRUE | TRUE | 43 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
146996 | HCMEF4Z3340 | F4 Z3 :Duct Installation& Dusct Accecories Installation, Fan coil Unit | 26485 | 2013-10-21 16:00 | 2013-10-31 16:00 | 10 | 280 | 100 | 86 | -14 | 7610 | 7610 | 6544.6 | 9261.6765 | 0.86 | 0.70663 | TRUE | TRUE | TRUE | 35 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146997 | HCMEF4Z3350 | F4 Z3 :Duct Insulation Work | 26485 | 2013-10-31 16:00 | 2013-11-21 16:00 | 21 | 280 | 100 | 87 | -13 | 25809 | 25809 | 22453.83 | 28886.5823 | 0.87 | 0.77731 | TRUE | TRUE | TRUE | 35 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
146998 | HCMEF4Z3360 | F4 Z3 :Exhaust Fans | 26485 | 2013-11-21 16:00 | 2013-12-12 16:00 | 21 | 280 | 100 | 96 | -4 | 16422 | 16422 | 15765.12 | 20466.7308 | 0.96 | 0.77028 | TRUE | FALSE | FALSE | 35 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
146999 | HCMEF4Z3370 | F4 Z3 :Grills & Diffusers | 26485 | 2014-03-20 16:00 | 2014-04-03 16:00 | 14 | 120 | 100 | 84 | -16 | 27860 | 27860 | 23402.4 | 33519.1813 | 0.84 | 0.69818 | TRUE | TRUE | TRUE | 15 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147000 | HCMEF4Z3380 | F4 Z3 :Mechanical final Fix | 26485 | 2014-04-03 16:00 | 2014-04-17 16:00 | 14 | 120 | 100 | 86 | -14 | 26642 | 26642 | 22912.12 | 27686.2662 | 0.86 | 0.82756 | TRUE | TRUE | TRUE | 15 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147001 | HCMEF4Z3390 | F4 Z3 :All Vertical Piping Works | 26486 | 2013-04-17 08:00 | 2013-04-30 17:00 | 13 | 855 | 100 | 100 | 0 | 11193 | 11193 | 11193 | 11840.7838 | 1 | 0.94529 | FALSE | FALSE | FALSE | 106.875 | FALSE | 0 | Green | Continue normal monitoring.
147002 | HCMEF4Z3400 | F4 Z3 :All Horizantal Piping Works | 26486 | 2013-05-01 08:00 | 2013-06-11 17:00 | 41 | 855 | 100 | 99 | -1 | 80852 | 80852 | 80043.48 | 74887.5818 | 0.99 | 1.0688 | FALSE | FALSE | FALSE | 106.875 | FALSE | 0 | Green | Continue normal monitoring.
147003 | HCMEF4Z3410 | F4 Z3 :Mechanical Final Fix | 26486 | 2014-01-06 08:00 | 2014-01-31 17:00 | 25 | 391 | 100 | 100 | 0 | 23500 | 23500 | 23500 | 24318.1698 | 1 | 0.96636 | FALSE | FALSE | FALSE | 48.875 | FALSE | 0 | Green | Continue normal monitoring.
147004 | HCMEF4Z4175 | F4 Z4 :Blocks Start Date for All Parts | 26489 | 2013-05-30 16:00 | 2013-05-30 16:00 | 1 | 1128 | 100 | 99 | -1 | 592 | 592 | 586.08 | 717.037 | 0.99 | 0.81736 | TRUE | FALSE | FALSE | 141 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147005 | HCMEF4Z4185 | F4 Z4 :Tiling Finish Date for All Parts | 26489 | 2013-08-14 12:00 | 2013-08-14 12:00 | 1 | 1035 | 100 | 83 | -17 | 1252 | 1252 | 1039.16 | 1089.6674 | 0.83 | 0.95365 | FALSE | TRUE | TRUE | 129.375 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147006 | HCMEF4Z4195 | F4 Z4 :Plastering Finish Date for All Parts | 26489 | 2013-06-30 12:00 | 2013-06-30 12:00 | 1 | 1459 | 100 | 100 | 0 | 1366 | 1366 | 1366 | 1632.9474 | 1 | 0.83652 | TRUE | FALSE | FALSE | 182.375 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147007 | HCMEF4Z4205 | F4 Z4 :Gypsum Boards Finish Date for All Parts | 26489 | 2014-01-23 16:00 | 2014-01-23 16:00 | 1 | 816 | 100 | 85 | -15 | 1947 | 1947 | 1654.95 | 1920.4801 | 0.85 | 0.86174 | TRUE | TRUE | TRUE | 102 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147008 | HCMEF4Z4235 | F4 Z4 :Electrical Coduits & Boards F.F for All Systems | 26489 | 2013-05-30 16:00 | 2013-06-17 16:00 | 18 | 936 | 100 | 86 | -14 | 11538 | 11538 | 9922.68 | 13958.7313 | 0.86 | 0.71086 | TRUE | TRUE | TRUE | 117 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147009 | HCMEF4Z4245 | F4 Z4 :Electrical Boards Seconed Fix | 26489 | 2013-08-26 16:00 | 2013-09-11 16:00 | 16 | 936 | 100 | 97 | -3 | 29024 | 29024 | 28153.28 | 35593.6394 | 0.97 | 0.79096 | TRUE | FALSE | FALSE | 117 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147010 | HCMEF4Z4255 | F4 Z4 :Cable Tray Installation | 26489 | 2013-11-20 16:00 | 2013-12-04 16:00 | 14 | 408 | 100 | 100 | 0 | 27370 | 27370 | 27370 | 30609.1288 | 1 | 0.89418 | TRUE | FALSE | FALSE | 51 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147011 | HCMEF4Z4265 | F4 Z4 :Electrcial Wiring | 26489 | 2013-11-28 16:00 | 2013-12-26 16:00 | 28 | 264 | 100 | 84 | -16 | 34944 | 34944 | 29352.96 | 38989.4499 | 0.84 | 0.75284 | TRUE | TRUE | TRUE | 33 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147012 | HCMEF4Z4275 | F4 Z4 :Cable Laying | 26489 | 2013-12-04 16:00 | 2013-12-18 16:00 | 14 | 408 | 100 | 99 | -1 | 16128 | 16128 | 15966.72 | 16629.6088 | 0.99 | 0.96014 | FALSE | FALSE | FALSE | 51 | FALSE | 0 | Green | Continue normal monitoring.
147013 | HCMEF4Z4285 | F4 Z4 :Electrical Final Fix for All Systems & Boards (Vertical Elements) | 26489 | 2014-01-29 16:00 | 2014-02-12 16:00 | 14 | 568 | 100 | 100 | 0 | 16800 | 16800 | 16800 | 19894.8303 | 1 | 0.84444 | TRUE | FALSE | FALSE | 71 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147014 | HCMEF4Z4295 | F4 Z4 :Electrical Final Fix for All Systems (Horizantel Elements) | 26489 | 2014-02-12 16:00 | 2014-02-26 16:00 | 14 | 568 | 100 | 100 | 0 | 20958 | 20958 | 20958 | 25875.6921 | 1 | 0.80995 | TRUE | FALSE | FALSE | 71 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147015 | HCMEF4Z4085 | F4 Z4 :All Vertical Piping Works | 26488 | 2013-04-17 08:00 | 2013-04-30 17:00 | 13 | 760 | 100 | 100 | 0 | 7124 | 7124 | 7124 | 8264.0731 | 1 | 0.86204 | TRUE | FALSE | FALSE | 95 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147016 | HCMEF4Z4095 | F4 Z4 :All Horizantal Piping Works | 26488 | 2013-05-01 08:00 | 2013-06-11 17:00 | 41 | 855 | 100 | 82 | -18 | 74825 | 74825 | 61356.5 | 82215.8164 | 0.82 | 0.74629 | TRUE | TRUE | TRUE | 106.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147017 | HCMEF4Z4105 | F4 Z4 :Mechanical Final Fix | 26488 | 2013-10-16 08:00 | 2013-11-12 17:00 | 27 | 855 | 100 | 86 | -14 | 37260 | 37260 | 32043.6 | 40714.6413 | 0.86 | 0.78703 | TRUE | TRUE | TRUE | 106.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147018 | HCMEF4Z4115 | F4 Z4 :Horizontal F.F Piping Work | 26490 | 2013-05-30 16:00 | 2013-06-27 16:00 | 28 | 1080 | 100 | 100 | 0 | 47964 | 47964 | 47964 | 57066.9897 | 1 | 0.84049 | TRUE | FALSE | FALSE | 135 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147019 | HCMEF4Z4125 | F4 Z4 :Fire Hose Cabinets | 26490 | 2013-06-27 16:00 | 2013-07-11 16:00 | 14 | 1080 | 100 | 100 | 0 | 23226 | 23226 | 23226 | 24770.0995 | 1 | 0.93766 | FALSE | FALSE | FALSE | 135 | FALSE | 0 | Green | Continue normal monitoring.
147020 | HCMEF4Z4135 | F4 Z4 :Sprinklers Final Fix | 26490 | 2013-12-30 16:00 | 2014-01-13 16:00 | 14 | 664 | 100 | 100 | 0 | 14756 | 14756 | 14756 | 17287.3026 | 1 | 0.85357 | TRUE | FALSE | FALSE | 83 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147021 | HCMEF4Z4345 | F4 Z4 :Duct Installation& Dusct Accecories Installation, Fan coil Unit | 26491 | 2013-09-27 16:00 | 2013-10-17 16:00 | 20 | 296 | 100 | 93 | -7 | 18060 | 18060 | 16795.8 | 19027.1871 | 0.93 | 0.88273 | TRUE | FALSE | FALSE | 37 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147022 | HCMEF4Z4355 | F4 Z4 :Duct Insulation Work | 26491 | 2013-10-17 16:00 | 2013-11-07 16:00 | 21 | 360 | 100 | 86 | -14 | 29211 | 29211 | 25121.46 | 25558.9739 | 0.86 | 0.98288 | FALSE | TRUE | TRUE | 45 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147023 | HCMEF4Z4365 | F4 Z4 :Exhaust Fans | 26491 | 2013-11-07 16:00 | 2013-11-28 16:00 | 21 | 360 | 100 | 84 | -16 | 28644 | 28644 | 24060.96 | 28746.5112 | 0.84 | 0.837 | TRUE | TRUE | TRUE | 45 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147024 | HCMEF4Z4375 | F4 Z4 :Grills & Diffusers | 26491 | 2014-02-06 16:00 | 2014-02-20 16:00 | 14 | 360 | 100 | 100 | 0 | 15414 | 15414 | 15414 | 15842.1452 | 1 | 0.97297 | FALSE | FALSE | FALSE | 45 | FALSE | 0 | Green | Continue normal monitoring.
147025 | HCMEF4Z4385 | F4 Z4 :Mechanical final Fix | 26491 | 2014-02-20 16:00 | 2014-03-06 16:00 | 14 | 360 | 100 | 100 | 0 | 11760 | 11760 | 11760 | 10662.1675 | 1 | 1.103 | FALSE | FALSE | FALSE | 45 | FALSE | 0 | Green | Continue normal monitoring.
147026 | HCMEF4Z4395 | F4 Z4 :All Vertical Piping Works | 26492 | 2013-04-17 08:00 | 2013-04-30 17:00 | 13 | 855 | 100 | 84 | -16 | 15639 | 15639 | 13136.76 | 13934.326 | 0.84 | 0.94276 | FALSE | TRUE | TRUE | 106.875 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147027 | HCMEF4Z4405 | F4 Z4 :All Horizantal Piping Works | 26492 | 2013-05-01 08:00 | 2013-06-11 17:00 | 41 | 855 | 100 | 100 | 0 | 33497 | 33497 | 33497 | 35647.0378 | 1 | 0.93969 | FALSE | FALSE | FALSE | 106.875 | FALSE | 0 | Green | Continue normal monitoring.
147028 | HCMEF4Z4415 | F4 Z4 :Mechanical Final Fix | 26492 | 2013-10-16 08:00 | 2013-11-12 17:00 | 27 | 855 | 100 | 100 | 0 | 30159 | 30159 | 30159 | 26662.2888 | 1 | 1.1311 | FALSE | FALSE | FALSE | 106.875 | FALSE | 0 | Green | Continue normal monitoring.
147029 | HCMEF4Z5180 | F4 Z5 :Blocks Start Date for All Parts | 26495 | 2013-08-31 16:00 | 2013-08-31 16:00 | 1 | 552 | 100 | 81 | -19 | 1886 | 1886 | 1527.66 | 1831.6418 | 0.81 | 0.83404 | TRUE | TRUE | TRUE | 69 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147030 | HCMEF4Z5190 | F4 Z5 :Tiling Finish Date for All Parts | 26495 | 2013-12-29 16:00 | 2013-12-29 16:00 | 1 | 361 | 100 | 100 | 0 | 881 | 881 | 881 | 1011.246 | 1 | 0.8712 | TRUE | FALSE | FALSE | 45.125 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147031 | HCMEF4Z5200 | F4 Z5 :Plastering Finish Date for All Parts | 26495 | 2013-09-30 12:00 | 2013-09-30 12:00 | 1 | 923 | 100 | 100 | 0 | 732 | 732 | 732 | 904.5857 | 1 | 0.80921 | TRUE | FALSE | FALSE | 115.375 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147032 | HCMEF4Z5210 | F4 Z5 :Gypsum Boards Finish Date for All Parts | 26495 | 2014-03-06 12:00 | 2014-03-06 12:00 | 1 | 531 | 100 | 100 | 0 | 1867 | 1867 | 1867 | 2123.0557 | 1 | 0.87939 | TRUE | FALSE | FALSE | 66.375 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147033 | HCMEF4Z5240 | F4 Z5 :Electrical Coduits & Boards F.F for All Systems | 26495 | 2013-09-02 08:00 | 2013-09-17 17:00 | 15 | 503 | 100 | 100 | 0 | 19740 | 19740 | 19740 | 24616.7713 | 1 | 0.80189 | TRUE | FALSE | FALSE | 62.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147034 | HCMEF4Z5250 | F4 Z5 :Electrical Boards Seconed Fix | 26495 | 2013-11-27 08:00 | 2013-12-12 17:00 | 15 | 503 | 100 | 85 | -15 | 15780 | 15780 | 13413 | 17820.9093 | 0.85 | 0.75266 | TRUE | TRUE | TRUE | 62.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147035 | HCMEF4Z5260 | F4 Z5 :Cable Tray Installation | 26495 | 2013-11-20 16:00 | 2013-12-04 16:00 | 14 | 488 | 100 | 94 | -6 | 18970 | 18970 | 17831.8 | 18353.8124 | 0.94 | 0.97156 | FALSE | FALSE | FALSE | 61 | FALSE | 0 | Green | Continue normal monitoring.
147036 | HCMEF4Z5270 | F4 Z5 :Electrcial Wiring | 26495 | 2014-01-23 13:00 | 2014-02-14 12:00 | 21 | 171 | 100 | 100 | 0 | 27678 | 27678 | 27678 | 30966.7281 | 1 | 0.8938 | TRUE | FALSE | FALSE | 21.375 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147037 | HCMEF4Z5280 | F4 Z5 :Cable Laying | 26495 | 2013-12-04 16:00 | 2013-12-18 16:00 | 14 | 488 | 100 | 89 | -11 | 9548 | 9548 | 8497.72 | 10797.4771 | 0.89 | 0.78701 | TRUE | TRUE | TRUE | 61 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147038 | HCMEF4Z5290 | F4 Z5 :Electrical Final Fix for All Systems & Boards (Vertical Elements) | 26495 | 2014-03-18 13:00 | 2014-04-01 12:00 | 13 | 299 | 100 | 100 | 0 | 20332 | 20332 | 20332 | 20305.3812 | 1 | 1.0013 | FALSE | FALSE | FALSE | 37.375 | FALSE | 0 | Green | Continue normal monitoring.
147039 | HCMEF4Z5300 | F4 Z5 :Electrical Final Fix for All Systems (Horizantel Elements) | 26495 | 2014-04-01 13:00 | 2014-04-15 12:00 | 13 | 299 | 100 | 100 | 0 | 11648 | 11648 | 11648 | 9983.3324 | 1 | 1.1667 | FALSE | FALSE | FALSE | 37.375 | FALSE | 0 | Green | Continue normal monitoring.
147040 | HCMEF4Z5090 | F4 Z5 :All Vertical Piping Works | 26494 | 2013-04-17 08:00 | 2013-04-30 17:00 | 13 | 760 | 100 | 100 | 0 | 16614 | 16614 | 16614 | 18795.0845 | 1 | 0.88395 | TRUE | FALSE | FALSE | 95 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147041 | HCMEF4Z5100 | F4 Z5 :All Horizantal Piping Works | 26494 | 2013-05-01 08:00 | 2013-06-11 17:00 | 41 | 760 | 100 | 86 | -14 | 57646 | 57646 | 49575.56 | 49499.4695 | 0.86 | 1.0015 | FALSE | TRUE | TRUE | 95 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147042 | HCMEF4Z5110 | F4 Z5 :Mechanical Final Fix | 26494 | 2013-10-16 08:00 | 2013-11-12 17:00 | 27 | 760 | 100 | 84 | -16 | 50112 | 50112 | 42094.08 | 55247.2388 | 0.84 | 0.76192 | TRUE | TRUE | TRUE | 95 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147043 | HCMEF4Z5120 | F4 Z5 :Horizontal F.F Piping Work | 26496 | 2013-09-02 08:00 | 2013-09-27 17:00 | 25 | 551 | 100 | 80 | -20 | 15650 | 15650 | 12520 | 14326.7392 | 0.8 | 0.87389 | TRUE | TRUE | TRUE | 68.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147044 | HCMEF4Z5130 | F4 Z5 :Fire Hose Cabinets | 26496 | 2013-09-30 08:00 | 2013-10-11 17:00 | 11 | 551 | 100 | 92 | -8 | 5500 | 5500 | 5060 | 5919.3278 | 0.92 | 0.85483 | TRUE | FALSE | FALSE | 68.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147045 | HCMEF4Z5140 | F4 Z5 :Sprinklers Final Fix | 26496 | 2014-01-20 08:00 | 2014-01-31 17:00 | 11 | 551 | 100 | 100 | 0 | 18601 | 18601 | 18601 | 19560.1645 | 1 | 0.95096 | FALSE | FALSE | FALSE | 68.875 | FALSE | 0 | Green | Continue normal monitoring.
147046 | HCMEF4Z5350 | F4 Z5 :Duct Installation& Dusct Accecories Installation, Fan coil Unit | 26497 | 2013-09-27 16:00 | 2013-10-17 16:00 | 20 | 296 | 100 | 100 | 0 | 10360 | 10360 | 10360 | 8862.0005 | 1 | 1.169 | FALSE | FALSE | FALSE | 37 | FALSE | 0 | Green | Continue normal monitoring.
147047 | HCMEF4Z5360 | F4 Z5 :Duct Insulation Work | 26497 | 2013-10-17 16:00 | 2013-11-07 16:00 | 21 | 360 | 100 | 97 | -3 | 38955 | 38955 | 37786.35 | 38765.9252 | 0.97 | 0.97473 | FALSE | FALSE | FALSE | 45 | FALSE | 0 | Green | Continue normal monitoring.
147048 | HCMEF4Z5370 | F4 Z5 :Exhaust Fans | 26497 | 2013-11-07 16:00 | 2013-11-28 16:00 | 21 | 360 | 100 | 92 | -8 | 22743 | 22743 | 20923.56 | 24799.7966 | 0.92 | 0.8437 | TRUE | FALSE | FALSE | 45 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147049 | HCMEF4Z5380 | F4 Z5 :Grills & Diffusers | 26497 | 2014-02-06 16:00 | 2014-02-20 16:00 | 14 | 360 | 100 | 100 | 0 | 13370 | 13370 | 13370 | 15902.8478 | 1 | 0.84073 | TRUE | FALSE | FALSE | 45 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147050 | HCMEF4Z5390 | F4 Z5 :Mechanical final Fix | 26497 | 2014-02-20 16:00 | 2014-03-06 16:00 | 14 | 360 | 100 | 100 | 0 | 20384 | 20384 | 20384 | 24572.0323 | 1 | 0.82956 | TRUE | FALSE | FALSE | 45 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147051 | HCMEF4Z5400 | F4 Z5 :All Vertical Piping Works | 26498 | 2013-04-17 08:00 | 2013-04-30 17:00 | 13 | 1175 | 100 | 97 | -3 | 21216 | 21216 | 20579.52 | 22139.7444 | 0.97 | 0.92953 | FALSE | FALSE | FALSE | 146.875 | FALSE | 0 | Green | Continue normal monitoring.
147052 | HCMEF4Z5410 | F4 Z5 :All Horizantal Piping Works | 26498 | 2013-05-01 08:00 | 2013-06-11 17:00 | 41 | 1175 | 100 | 84 | -16 | 73431 | 73431 | 61682.04 | 83811.8667 | 0.84 | 0.73596 | TRUE | TRUE | TRUE | 146.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147053 | HCMEF4Z5420 | F4 Z5 :Mechanical Final Fix | 26498 | 2013-10-16 08:00 | 2013-11-12 17:00 | 27 | 1175 | 100 | 92 | -8 | 25488 | 25488 | 23448.96 | 24891.1177 | 0.92 | 0.94206 | FALSE | FALSE | FALSE | 146.875 | FALSE | 0 | Green | Continue normal monitoring.
147054 | HCMEF5Z1310 | F5 Z1 :Blocks Start Date for All Parts | 26502 | 2013-04-28 16:00 | 2013-04-28 16:00 | 1 | 1376 | 100 | 83 | -17 | 1763 | 1763 | 1463.29 | 1739.8599 | 0.83 | 0.84104 | TRUE | TRUE | TRUE | 172 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147055 | HCMEF5Z1315 | F5 Z1 :Tiling Finish Date for All Parts | 26502 | 2013-11-16 12:00 | 2013-11-16 12:00 | 1 | 587 | 100 | 96 | -4 | 1824 | 1824 | 1751.04 | 1692.2806 | 0.96 | 1.0347 | FALSE | FALSE | FALSE | 73.375 | FALSE | 0 | Green | Continue normal monitoring.
147056 | HCMEF5Z1320 | F5 Z1 :Plastering Finish Date for All Parts | 26502 | 2013-07-23 16:00 | 2013-07-23 16:00 | 1 | 1288 | 100 | 82 | -18 | 1101 | 1101 | 902.82 | 1183.3319 | 0.82 | 0.76295 | TRUE | TRUE | TRUE | 161 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147057 | HCMEF5Z1405 | F5 Z1 :Gypsum Boards Finish Date for All Parts | 26502 | 2014-03-24 16:00 | 2014-03-24 16:00 | 1 | 408 | 100 | 96 | -4 | 602 | 602 | 577.92 | 587.447 | 0.96 | 0.98378 | FALSE | FALSE | FALSE | 51 | FALSE | 0 | Green | Continue normal monitoring.
147058 | HCMEF5Z1420 | F5 Z1 :Electrical Coduits & Boards F.F for All Systems | 26502 | 2013-04-29 08:00 | 2013-05-14 17:00 | 15 | 1151 | 100 | 100 | 0 | 22305 | 22305 | 22305 | 19712.0071 | 1 | 1.1315 | FALSE | FALSE | FALSE | 143.875 | FALSE | 0 | Green | Continue normal monitoring.
147059 | HCMEF5Z1425 | F5 Z1 :Electrical Boards Seconed Fix | 26502 | 2013-08-27 16:00 | 2013-09-12 16:00 | 16 | 952 | 100 | 90 | -10 | 28368 | 28368 | 25531.2 | 31885.7011 | 0.9 | 0.80071 | TRUE | FALSE | FALSE | 119 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147060 | HCMEF5Z1430 | F5 Z1 :Cable Tray Installation | 26502 | 2014-01-29 16:00 | 2014-02-12 16:00 | 14 | 0 | 100 | 100 | 0 | 27664 | 27664 | 27664 | 31346.1139 | 1 | 0.88253 | TRUE | FALSE | FALSE | 0 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147061 | HCMEF5Z1435 | F5 Z1 :Electrcial Wiring | 26502 | 2014-02-10 08:00 | 2014-03-07 17:00 | 25 | 15 | 100 | 100 | 0 | 25475 | 25475 | 25475 | 25322.0727 | 1 | 1.006 | FALSE | FALSE | FALSE | 1.875 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147062 | HCMEF5Z1440 | F5 Z1 :Cable Laying | 26502 | 2014-02-18 16:00 | 2014-03-04 16:00 | 14 | 0 | 100 | 99 | -1 | 23464 | 23464 | 23229.36 | 20664.4951 | 0.99 | 1.1241 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147063 | HCMEF5Z1445 | F5 Z1 :Electrical Final Fix for All Systems & Boards (Vertical Elements) | 26502 | 2014-04-15 16:00 | 2014-04-29 16:00 | 14 | 136 | 100 | 100 | 0 | 19012 | 19012 | 19012 | 19402.1089 | 1 | 0.97989 | FALSE | FALSE | FALSE | 17 | FALSE | 0 | Green | Continue normal monitoring.
147064 | HCMEF5Z1450 | F5 Z1 :Electrical Final Fix for All Systems (Horizantel Elements) | 26502 | 2014-04-29 16:00 | 2014-05-13 16:00 | 14 | 136 | 100 | 100 | 0 | 9422 | 9422 | 9422 | 9675.7739 | 1 | 0.97377 | FALSE | FALSE | FALSE | 17 | FALSE | 0 | Green | Continue normal monitoring.
147065 | HCMEF5Z1460 | F5 Z1 :All Vertical Piping Works | 26501 | 2013-04-29 08:00 | 2013-05-10 17:00 | 11 | 791 | 100 | 100 | 0 | 20526 | 20526 | 20526 | 22937.1554 | 1 | 0.89488 | TRUE | FALSE | FALSE | 98.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147066 | HCMEF5Z1465 | F5 Z1 :All Horizantal Piping Works | 26501 | 2013-05-13 08:00 | 2013-06-21 17:00 | 39 | 791 | 100 | 100 | 0 | 58656 | 58656 | 58656 | 57258.0255 | 1 | 1.0244 | FALSE | FALSE | FALSE | 98.875 | FALSE | 0 | Green | Continue normal monitoring.
147067 | HCMEF5Z1470 | F5 Z1 :Mechanical Final Fix | 26501 | 2014-02-03 08:00 | 2014-02-28 17:00 | 25 | 231 | 100 | 83 | -17 | 23250 | 23250 | 19297.5 | 26110.6733 | 0.83 | 0.73907 | TRUE | TRUE | TRUE | 28.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147068 | HCMEF5Z1475 | F5 Z1 :Horizontal F.F Piping Work | 26503 | 2013-04-29 08:00 | 2013-05-24 17:00 | 25 | 1271 | 100 | 81 | -19 | 30650 | 30650 | 24826.5 | 36736.9495 | 0.81 | 0.67579 | TRUE | TRUE | TRUE | 158.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147069 | HCMEF5Z1480 | F5 Z1 :Fire Hose Cabinets | 26503 | 2013-05-27 08:00 | 2013-06-07 17:00 | 11 | 1271 | 100 | 99 | -1 | 14839 | 14839 | 14690.61 | 14022.7722 | 0.99 | 1.0476 | FALSE | FALSE | FALSE | 158.875 | FALSE | 0 | Green | Continue normal monitoring.
147070 | HCMEF5Z1485 | F5 Z1 :Sprinklers Final Fix | 26503 | 2014-03-10 16:00 | 2014-03-24 16:00 | 14 | 264 | 100 | 95 | -5 | 25858 | 25858 | 24565.1 | 32104.4608 | 0.95 | 0.76516 | TRUE | FALSE | FALSE | 33 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147071 | HCMEF5Z1490 | F5 Z1 :Duct Installation& Dusct Accecories Installation, Fan coil Unit | 26504 | 2013-11-04 16:00 | 2013-11-18 16:00 | 14 | 184 | 100 | 100 | 0 | 20846 | 20846 | 20846 | 20940.7921 | 1 | 0.99547 | FALSE | FALSE | FALSE | 23 | FALSE | 0 | Green | Continue normal monitoring.
147072 | HCMEF5Z1495 | F5 Z1 :Duct Insulation Work | 26504 | 2013-11-18 16:00 | 2013-12-09 16:00 | 21 | 184 | 100 | 97 | -3 | 23898 | 23898 | 23181.06 | 22868.0792 | 0.97 | 1.0137 | FALSE | FALSE | FALSE | 23 | FALSE | 0 | Green | Continue normal monitoring.
147073 | HCMEF5Z1500 | F5 Z1 :Exhaust Fans | 26504 | 2013-12-09 16:00 | 2013-12-30 16:00 | 21 | 184 | 100 | 87 | -13 | 19299 | 19299 | 16790.13 | 19658.0477 | 0.87 | 0.85411 | TRUE | TRUE | TRUE | 23 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147074 | HCMEF5Z1505 | F5 Z1 :Grills & Diffusers | 26504 | 2014-04-08 16:00 | 2014-04-22 16:00 | 14 | 16 | 100 | 82 | -18 | 15302 | 15302 | 12547.64 | 13584.4881 | 0.82 | 0.92367 | FALSE | TRUE | TRUE | 2 | TRUE | 4 | Orange | Develop recovery plan and review schedule and cost exposure.
147075 | HCMEF5Z1510 | F5 Z1 :Mechanical final Fix | 26504 | 2014-04-24 16:00 | 2014-05-08 16:00 | 14 | 0 | 100 | 88 | -12 | 13776 | 13776 | 12122.88 | 12402.2898 | 0.88 | 0.97747 | FALSE | TRUE | TRUE | 0 | TRUE | 4 | Orange | Develop recovery plan and review schedule and cost exposure.
147076 | HCMEF5Z1515 | F5 Z1 :All Vertical Piping Works | 26505 | 2013-04-29 08:00 | 2013-05-10 17:00 | 11 | 791 | 100 | 100 | 0 | 10021 | 10021 | 10021 | 10179.0674 | 1 | 0.98447 | FALSE | FALSE | FALSE | 98.875 | FALSE | 0 | Green | Continue normal monitoring.
147077 | HCMEF5Z1520 | F5 Z1 :All Horizantal Piping Works | 26505 | 2013-05-13 08:00 | 2013-06-21 17:00 | 39 | 791 | 100 | 99 | -1 | 55965 | 55965 | 55405.35 | 64638.3331 | 0.99 | 0.85716 | TRUE | FALSE | FALSE | 98.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147078 | HCMEF5Z1525 | F5 Z1 :Mechanical Final Fix | 26505 | 2014-02-03 08:00 | 2014-02-28 17:00 | 25 | 231 | 100 | 100 | 0 | 40175 | 40175 | 40175 | 48616.7677 | 1 | 0.82636 | TRUE | FALSE | FALSE | 28.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147079 | HCMEF5Z2315 | F5 Z2 :Blocks Start Date for All Parts | 26508 | 2013-06-25 16:00 | 2013-06-25 16:00 | 1 | 1064 | 100 | 85 | -15 | 1636 | 1636 | 1390.6 | 1825.6569 | 0.85 | 0.7617 | TRUE | TRUE | TRUE | 133 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147080 | HCMEF5Z2320 | F5 Z2 :Tiling Finish Date for All Parts | 26508 | 2013-11-17 16:00 | 2013-11-17 16:00 | 1 | 576 | 100 | 89 | -11 | 831 | 831 | 739.59 | 741.325 | 0.89 | 0.99766 | FALSE | TRUE | TRUE | 72 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147081 | HCMEF5Z2325 | F5 Z2 :Plastering Finish Date for All Parts | 26508 | 2013-09-30 16:00 | 2013-09-30 16:00 | 1 | 920 | 100 | 100 | 0 | 1901 | 1901 | 1901 | 2126.8538 | 1 | 0.89381 | TRUE | FALSE | FALSE | 115 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147082 | HCMEF5Z2410 | F5 Z2 :Gypsum Boards Finish Date for All Parts | 26508 | 2014-03-23 16:00 | 2014-03-23 16:00 | 1 | 416 | 100 | 89 | -11 | 1154 | 1154 | 1027.06 | 1274.2135 | 0.89 | 0.80603 | TRUE | TRUE | TRUE | 52 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147083 | HCMEF5Z2425 | F5 Z2 :Electrical Coduits & Boards F.F for All Systems | 26508 | 2013-06-25 16:00 | 2013-07-11 16:00 | 16 | 888 | 100 | 92 | -8 | 8640 | 8640 | 7948.8 | 10128.7201 | 0.92 | 0.78478 | TRUE | FALSE | FALSE | 111 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147084 | HCMEF5Z2430 | F5 Z2 :Electrical Boards Seconed Fix | 26508 | 2013-10-09 16:00 | 2013-10-25 16:00 | 16 | 776 | 100 | 96 | -4 | 23328 | 23328 | 22394.88 | 27529.3604 | 0.96 | 0.81349 | TRUE | FALSE | FALSE | 97 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147085 | HCMEF5Z2435 | F5 Z2 :Cable Tray Installation | 26508 | 2014-01-29 16:00 | 2014-02-12 16:00 | 14 | 88 | 100 | 88 | -12 | 8456 | 8456 | 7441.28 | 10124.2101 | 0.88 | 0.735 | TRUE | TRUE | TRUE | 11 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147086 | HCMEF5Z2440 | F5 Z2 :Electrcial Wiring | 26508 | 2014-01-06 08:00 | 2014-01-31 17:00 | 25 | 215 | 100 | 96 | -4 | 17525 | 17525 | 16824 | 17799.3119 | 0.96 | 0.94521 | FALSE | FALSE | FALSE | 26.875 | FALSE | 0 | Green | Continue normal monitoring.
147087 | HCMEF5Z2445 | F5 Z2 :Cable Laying | 26508 | 2014-02-12 16:00 | 2014-02-26 16:00 | 14 | 88 | 100 | 100 | 0 | 13286 | 13286 | 13286 | 15001.8305 | 1 | 0.88563 | TRUE | FALSE | FALSE | 11 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147088 | HCMEF5Z2450 | F5 Z2 :Electrical Final Fix for All Systems & Boards (Vertical Elements) | 26508 | 2014-04-09 16:00 | 2014-04-23 16:00 | 14 | 168 | 100 | 88 | -12 | 25046 | 25046 | 22040.48 | 23976.5394 | 0.88 | 0.91925 | FALSE | TRUE | TRUE | 21 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147089 | HCMEF5Z2455 | F5 Z2 :Electrical Final Fix for All Systems (Horizantel Elements) | 26508 | 2014-04-23 16:00 | 2014-05-07 16:00 | 14 | 168 | 100 | 88 | -12 | 19726 | 19726 | 17358.88 | 24652.263 | 0.88 | 0.70415 | TRUE | TRUE | TRUE | 21 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147090 | HCMEF5Z2465 | F5 Z2 :All Vertical Piping Works | 26507 | 2013-04-29 08:00 | 2013-05-10 17:00 | 11 | 856 | 100 | 80 | -20 | 7799 | 7799 | 6239.2 | 7176.1227 | 0.8 | 0.86944 | TRUE | TRUE | TRUE | 107 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147091 | HCMEF5Z2470 | F5 Z2 :All Horizantal Piping Works | 26507 | 2013-05-13 08:00 | 2013-06-21 17:00 | 39 | 951 | 100 | 81 | -19 | 41418 | 41418 | 33548.58 | 35372.8678 | 0.81 | 0.94843 | FALSE | TRUE | TRUE | 118.875 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147092 | HCMEF5Z2475 | F5 Z2 :Mechanical Final Fix | 26507 | 2014-02-03 08:00 | 2014-02-28 17:00 | 25 | 391 | 100 | 100 | 0 | 41025 | 41025 | 41025 | 37313.201 | 1 | 1.0995 | FALSE | FALSE | FALSE | 48.875 | FALSE | 0 | Green | Continue normal monitoring.
147093 | HCMEF5Z2480 | F5 Z2 :Horizontal F.F Piping Work | 26509 | 2013-06-25 16:00 | 2013-07-23 16:00 | 28 | 1016 | 100 | 95 | -5 | 33936 | 33936 | 32239.2 | 39377.6008 | 0.95 | 0.81872 | TRUE | FALSE | FALSE | 127 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147094 | HCMEF5Z2485 | F5 Z2 :Fire Hose Cabinets | 26509 | 2013-07-23 16:00 | 2013-08-06 16:00 | 14 | 1016 | 100 | 100 | 0 | 26600 | 26600 | 26600 | 27363.7783 | 1 | 0.97209 | FALSE | FALSE | FALSE | 127 | FALSE | 0 | Green | Continue normal monitoring.
147095 | HCMEF5Z2490 | F5 Z2 :Sprinklers Final Fix | 26509 | 2014-03-10 16:00 | 2014-03-24 16:00 | 14 | 344 | 100 | 80 | -20 | 17780 | 17780 | 14224 | 18295.6218 | 0.8 | 0.77745 | TRUE | TRUE | TRUE | 43 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147096 | HCMEF5Z2495 | F5 Z2 :Duct Installation& Dusct Accecories Installation, Fan coil Unit | 26510 | 2013-10-21 16:00 | 2013-10-31 16:00 | 10 | 265 | 100 | 89 | -11 | 16070 | 16070 | 14302.3 | 19798.3873 | 0.89 | 0.7224 | TRUE | TRUE | TRUE | 33.125 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147097 | HCMEF5Z2500 | F5 Z2 :Duct Insulation Work | 26510 | 2013-10-31 16:00 | 2013-11-21 16:00 | 21 | 265 | 100 | 97 | -3 | 20013 | 20013 | 19412.61 | 24372.9114 | 0.97 | 0.79648 | TRUE | FALSE | FALSE | 33.125 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147098 | HCMEF5Z2505 | F5 Z2 :Exhaust Fans | 26510 | 2013-11-21 16:00 | 2013-12-12 16:00 | 21 | 265 | 100 | 100 | 0 | 24486 | 24486 | 24486 | 23861.0657 | 1 | 1.0262 | FALSE | FALSE | FALSE | 33.125 | FALSE | 0 | Green | Continue normal monitoring.
147099 | HCMEF5Z2510 | F5 Z2 :Grills & Diffusers | 26510 | 2014-04-03 16:00 | 2014-04-17 16:00 | 14 | 25 | 100 | 100 | 0 | 15792 | 15792 | 15792 | 14743.7784 | 1 | 1.0711 | FALSE | FALSE | FALSE | 3.125 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147100 | HCMEF5Z2515 | F5 Z2 :Mechanical final Fix | 26510 | 2014-04-17 16:00 | 2014-05-01 16:00 | 14 | 25 | 100 | 87 | -13 | 12404 | 12404 | 10791.48 | 14753.2293 | 0.87 | 0.73147 | TRUE | TRUE | TRUE | 3.125 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
147101 | HCMEF5Z2520 | F5 Z2 :All Vertical Piping Works | 26511 | 2013-04-29 08:00 | 2013-05-10 17:00 | 11 | 951 | 100 | 100 | 0 | 20603 | 20603 | 20603 | 24979.2344 | 1 | 0.82481 | TRUE | FALSE | FALSE | 118.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147102 | HCMEF5Z2525 | F5 Z2 :All Horizantal Piping Works | 26511 | 2013-05-13 08:00 | 2013-06-21 17:00 | 39 | 951 | 100 | 100 | 0 | 31005 | 31005 | 31005 | 33071.135 | 1 | 0.93752 | FALSE | FALSE | FALSE | 118.875 | FALSE | 0 | Green | Continue normal monitoring.
147103 | HCMEF5Z2530 | F5 Z2 :Mechanical Final Fix | 26511 | 2014-02-03 08:00 | 2014-02-28 17:00 | 25 | 391 | 100 | 90 | -10 | 18925 | 18925 | 17032.5 | 20850.9875 | 0.9 | 0.81687 | TRUE | FALSE | FALSE | 48.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147104 | HCMEF5Z3320 | F5 Z3 :Blocks Start Date for All Parts | 26514 | 2013-08-28 16:00 | 2013-08-28 16:00 | 1 | 721 | 100 | 100 | 0 | 1604 | 1604 | 1604 | 1528.2362 | 1 | 1.0496 | FALSE | FALSE | FALSE | 90.125 | FALSE | 0 | Green | Continue normal monitoring.
147105 | HCMEF5Z3325 | F5 Z3 :Tiling Finish Date for All Parts | 26514 | 2014-03-05 16:00 | 2014-03-05 16:00 | 1 | 176 | 100 | 81 | -19 | 767 | 767 | 621.27 | 897.6363 | 0.81 | 0.69212 | TRUE | TRUE | TRUE | 22 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147106 | HCMEF5Z3330 | F5 Z3 :Plastering Finish Date for All Parts | 26514 | 2013-12-22 16:00 | 2013-12-22 16:00 | 1 | 456 | 100 | 87 | -13 | 918 | 918 | 798.66 | 1012.4154 | 0.87 | 0.78887 | TRUE | TRUE | TRUE | 57 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147107 | HCMEF5Z3415 | F5 Z3 :Gypsum Boards Finish Date for All Parts | 26514 | 2014-05-03 16:00 | 2014-05-03 16:00 | 1 | 136 | 100 | 100 | 0 | 734 | 734 | 734 | 771.7316 | 1 | 0.95111 | FALSE | FALSE | FALSE | 17 | FALSE | 0 | Green | Continue normal monitoring.
147108 | HCMEF5Z3430 | F5 Z3 :Electrical Coduits & Boards F.F for All Systems | 26514 | 2013-08-28 16:00 | 2013-09-13 16:00 | 16 | 616 | 100 | 100 | 0 | 29344 | 29344 | 29344 | 25647.9302 | 1 | 1.1441 | FALSE | FALSE | FALSE | 77 | FALSE | 0 | Green | Continue normal monitoring.
147109 | HCMEF5Z3435 | F5 Z3 :Electrical Boards Seconed Fix | 26514 | 2013-12-23 08:00 | 2014-01-07 17:00 | 15 | 455 | 100 | 87 | -13 | 22275 | 22275 | 19379.25 | 27094.7305 | 0.87 | 0.71524 | TRUE | TRUE | TRUE | 56.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147110 | HCMEF5Z3440 | F5 Z3 :Cable Tray Installation | 26514 | 2014-01-29 16:00 | 2014-02-12 16:00 | 14 | 168 | 100 | 96 | -4 | 26320 | 26320 | 25267.2 | 28851.4726 | 0.96 | 0.87577 | TRUE | FALSE | FALSE | 21 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147111 | HCMEF5Z3445 | F5 Z3 :Electrcial Wiring | 26514 | 2014-03-05 16:00 | 2014-03-13 16:00 | 8 | 144 | 100 | 94 | -6 | 13888 | 13888 | 13054.72 | 12875.2376 | 0.94 | 1.0139 | FALSE | FALSE | FALSE | 18 | FALSE | 0 | Green | Continue normal monitoring.
147112 | HCMEF5Z3450 | F5 Z3 :Cable Laying | 26514 | 2014-02-12 16:00 | 2014-02-26 16:00 | 14 | 168 | 100 | 96 | -4 | 15022 | 15022 | 14421.12 | 16412.3529 | 0.96 | 0.87867 | TRUE | FALSE | FALSE | 21 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147113 | HCMEF5Z3455 | F5 Z3 :Electrical Final Fix for All Systems & Boards (Vertical Elements) | 26514 | 2014-04-14 16:00 | 2014-04-28 16:00 | 14 | 144 | 100 | 100 | 0 | 7672 | 7672 | 7672 | 8600.1995 | 1 | 0.89207 | TRUE | FALSE | FALSE | 18 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147114 | HCMEF5Z3460 | F5 Z3 :Electrical Final Fix for All Systems (Horizantel Elements) | 26514 | 2014-05-05 08:00 | 2014-05-16 17:00 | 11 | 111 | 100 | 100 | 0 | 18150 | 18150 | 18150 | 19244.5926 | 1 | 0.94312 | FALSE | FALSE | FALSE | 13.875 | FALSE | 0 | Green | Continue normal monitoring.
147115 | HCMEF5Z3470 | F5 Z3 :All Vertical Piping Works | 26513 | 2013-04-29 08:00 | 2013-05-10 17:00 | 11 | 856 | 100 | 100 | 0 | 7942 | 7942 | 7942 | 9031.9656 | 1 | 0.87932 | TRUE | FALSE | FALSE | 107 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147116 | HCMEF5Z3475 | F5 Z3 :All Horizantal Piping Works | 26513 | 2013-05-13 08:00 | 2013-06-21 17:00 | 39 | 951 | 100 | 92 | -8 | 55380 | 55380 | 50949.6 | 59953.3679 | 0.92 | 0.84982 | TRUE | FALSE | FALSE | 118.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147117 | HCMEF5Z3480 | F5 Z3 :Mechanical Final Fix | 26513 | 2014-02-03 08:00 | 2014-02-28 17:00 | 25 | 391 | 100 | 98 | -2 | 45050 | 45050 | 44149 | 55371.3079 | 0.98 | 0.79733 | TRUE | FALSE | FALSE | 48.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147118 | HCMEF5Z3485 | F5 Z3 :Horizontal F.F Piping Work | 26515 | 2013-08-28 16:00 | 2013-09-25 16:00 | 28 | 648 | 100 | 84 | -16 | 54068 | 54068 | 45417.12 | 47119.1175 | 0.84 | 0.96388 | FALSE | TRUE | TRUE | 81 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147119 | HCMEF5Z3490 | F5 Z3 :Fire Hose Cabinets | 26515 | 2013-09-25 16:00 | 2013-10-09 16:00 | 14 | 648 | 100 | 91 | -9 | 25438 | 25438 | 23148.58 | 22703.3713 | 0.91 | 1.0196 | FALSE | FALSE | FALSE | 81 | FALSE | 0 | Green | Continue normal monitoring.
147120 | HCMEF5Z3495 | F5 Z3 :Sprinklers Final Fix | 26515 | 2014-03-10 16:00 | 2014-03-24 16:00 | 14 | 344 | 100 | 80 | -20 | 10864 | 10864 | 8691.2 | 9989.1075 | 0.8 | 0.87007 | TRUE | TRUE | TRUE | 43 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147121 | HCMEF5Z3500 | F5 Z3 :Duct Installation& Dusct Accecories Installation, Fan coil Unit | 26516 | 2013-10-31 16:00 | 2013-11-12 16:00 | 12 | 296 | 100 | 100 | 0 | 23532 | 23532 | 23532 | 26498.6423 | 1 | 0.88805 | TRUE | FALSE | FALSE | 37 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147122 | HCMEF5Z3505 | F5 Z3 :Duct Insulation Work | 26516 | 2013-11-12 16:00 | 2013-12-03 16:00 | 21 | 296 | 100 | 84 | -16 | 34230 | 34230 | 28753.2 | 37934.9987 | 0.84 | 0.75796 | TRUE | TRUE | TRUE | 37 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147123 | HCMEF5Z3510 | F5 Z3 :Exhaust Fans | 26516 | 2013-12-03 16:00 | 2013-12-24 16:00 | 21 | 296 | 100 | 87 | -13 | 19299 | 19299 | 16790.13 | 23290.4876 | 0.87 | 0.7209 | TRUE | TRUE | TRUE | 37 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147124 | HCMEF5Z3515 | F5 Z3 :Grills & Diffusers | 26516 | 2014-04-03 16:00 | 2014-04-17 16:00 | 14 | 120 | 100 | 92 | -8 | 15540 | 15540 | 14296.8 | 17764.5662 | 0.92 | 0.80479 | TRUE | FALSE | FALSE | 15 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147125 | HCMEF5Z3520 | F5 Z3 :Mechanical final Fix | 26516 | 2014-04-17 16:00 | 2014-05-01 16:00 | 14 | 120 | 100 | 87 | -13 | 27328 | 27328 | 23775.36 | 28785.7355 | 0.87 | 0.82594 | TRUE | TRUE | TRUE | 15 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147126 | HCMEF5Z3525 | F5 Z3 :All Vertical Piping Works | 26517 | 2013-04-29 08:00 | 2013-05-10 17:00 | 11 | 951 | 100 | 100 | 0 | 9614 | 9614 | 9614 | 11986.0883 | 1 | 0.8021 | TRUE | FALSE | FALSE | 118.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147127 | HCMEF5Z3530 | F5 Z3 :All Horizantal Piping Works | 26517 | 2013-05-13 08:00 | 2013-06-21 17:00 | 39 | 951 | 100 | 100 | 0 | 22308 | 22308 | 22308 | 21336.3345 | 1 | 1.0455 | FALSE | FALSE | FALSE | 118.875 | FALSE | 0 | Green | Continue normal monitoring.
147128 | HCMEF5Z3535 | F5 Z3 :Mechanical Final Fix | 26517 | 2014-02-03 08:00 | 2014-02-28 17:00 | 25 | 391 | 100 | 90 | -10 | 38825 | 38825 | 34942.5 | 45940.7165 | 0.9 | 0.7606 | TRUE | FALSE | FALSE | 48.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147129 | HCMEF5Z4325 | F5 Z4 :Blocks Start Date for All Parts | 26520 | 2013-09-11 16:00 | 2013-09-11 16:00 | 1 | 528 | 100 | 80 | -20 | 1711 | 1711 | 1368.8 | 1746.4453 | 0.8 | 0.78376 | TRUE | TRUE | TRUE | 66 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147130 | HCMEF5Z4330 | F5 Z4 :Tiling Finish Date for All Parts | 26520 | 2013-11-28 12:00 | 2013-11-28 12:00 | 1 | 499 | 100 | 92 | -8 | 1887 | 1887 | 1736.04 | 2093.6153 | 0.92 | 0.82921 | TRUE | FALSE | FALSE | 62.375 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147131 | HCMEF5Z4335 | F5 Z4 :Plastering Finish Date for All Parts | 26520 | 2013-10-12 12:00 | 2013-10-12 12:00 | 1 | 843 | 100 | 98 | -2 | 1974 | 1974 | 1934.52 | 2252.1512 | 0.98 | 0.85897 | TRUE | FALSE | FALSE | 105.375 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147132 | HCMEF5Z4420 | F5 Z4 :Gypsum Boards Finish Date for All Parts | 26520 | 2014-02-09 16:00 | 2014-02-09 16:00 | 1 | 704 | 100 | 100 | 0 | 694 | 694 | 694 | 765.8301 | 1 | 0.90621 | FALSE | FALSE | FALSE | 88 | FALSE | 0 | Green | Continue normal monitoring.
147133 | HCMEF5Z4435 | F5 Z4 :Electrical Coduits & Boards F.F for All Systems | 26520 | 2013-09-11 16:00 | 2013-09-27 16:00 | 16 | 440 | 100 | 82 | -18 | 26864 | 26864 | 22028.48 | 24344.2353 | 0.82 | 0.90487 | FALSE | TRUE | TRUE | 55 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147134 | HCMEF5Z4440 | F5 Z4 :Electrical Boards Seconed Fix | 26520 | 2013-12-06 16:00 | 2013-12-24 16:00 | 18 | 440 | 100 | 100 | 0 | 30510 | 30510 | 30510 | 31339.2741 | 1 | 0.97354 | FALSE | FALSE | FALSE | 55 | FALSE | 0 | Green | Continue normal monitoring.
147135 | HCMEF5Z4445 | F5 Z4 :Cable Tray Installation | 26520 | 2013-12-04 16:00 | 2013-12-18 16:00 | 14 | 408 | 100 | 96 | -4 | 18844 | 18844 | 18090.24 | 20249.2979 | 0.96 | 0.89338 | TRUE | FALSE | FALSE | 51 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147136 | HCMEF5Z4450 | F5 Z4 :Electrcial Wiring | 26520 | 2013-12-26 16:00 | 2014-01-23 16:00 | 28 | 264 | 100 | 84 | -16 | 43792 | 43792 | 36785.28 | 52095.7297 | 0.84 | 0.70611 | TRUE | TRUE | TRUE | 33 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147137 | HCMEF5Z4455 | F5 Z4 :Cable Laying | 26520 | 2013-12-18 16:00 | 2014-01-01 16:00 | 14 | 408 | 100 | 99 | -1 | 22204 | 22204 | 21981.96 | 22813.6841 | 0.99 | 0.96354 | FALSE | FALSE | FALSE | 51 | FALSE | 0 | Green | Continue normal monitoring.
147138 | HCMEF5Z4460 | F5 Z4 :Electrical Final Fix for All Systems & Boards (Vertical Elements) | 26520 | 2014-02-24 16:00 | 2014-03-10 16:00 | 14 | 424 | 100 | 100 | 0 | 7308 | 7308 | 7308 | 8897.4821 | 1 | 0.82136 | TRUE | FALSE | FALSE | 53 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147139 | HCMEF5Z4465 | F5 Z4 :Electrical Final Fix for All Systems (Horizantel Elements) | 26520 | 2014-03-10 16:00 | 2014-03-24 16:00 | 14 | 424 | 100 | 87 | -13 | 12026 | 12026 | 10462.62 | 12340.4762 | 0.87 | 0.84783 | TRUE | TRUE | TRUE | 53 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147140 | HCMEF5Z4475 | F5 Z4 :All Vertical Piping Works | 26519 | 2013-04-29 08:00 | 2013-05-10 17:00 | 11 | 856 | 100 | 100 | 0 | 17578 | 17578 | 17578 | 18799.8809 | 1 | 0.93501 | FALSE | FALSE | FALSE | 107 | FALSE | 0 | Green | Continue normal monitoring.
147141 | HCMEF5Z4480 | F5 Z4 :All Horizantal Piping Works | 26519 | 2013-05-13 08:00 | 2013-06-21 17:00 | 39 | 951 | 100 | 100 | 0 | 41301 | 41301 | 41301 | 48260.808 | 1 | 0.85579 | TRUE | FALSE | FALSE | 118.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147142 | HCMEF5Z4485 | F5 Z4 :Mechanical Final Fix | 26519 | 2013-11-13 08:00 | 2013-12-10 17:00 | 27 | 855 | 100 | 93 | -7 | 31617 | 31617 | 29403.81 | 34248.3904 | 0.93 | 0.85855 | TRUE | FALSE | FALSE | 106.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147143 | HCMEF5Z4490 | F5 Z4 :Horizontal F.F Piping Work | 26521 | 2013-09-11 16:00 | 2013-10-09 16:00 | 28 | 568 | 100 | 83 | -17 | 45948 | 45948 | 38136.84 | 56703.84 | 0.83 | 0.67256 | TRUE | TRUE | TRUE | 71 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147144 | HCMEF5Z4495 | F5 Z4 :Fire Hose Cabinets | 26521 | 2013-10-09 16:00 | 2013-10-23 16:00 | 14 | 568 | 100 | 90 | -10 | 26642 | 26642 | 23977.8 | 29682.7669 | 0.9 | 0.8078 | TRUE | FALSE | FALSE | 71 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147145 | HCMEF5Z4500 | F5 Z4 :Sprinklers Final Fix | 26521 | 2014-01-29 16:00 | 2014-02-12 16:00 | 14 | 568 | 100 | 99 | -1 | 16492 | 16492 | 16327.08 | 17466.4097 | 0.99 | 0.93477 | FALSE | FALSE | FALSE | 71 | FALSE | 0 | Green | Continue normal monitoring.
147146 | HCMEF5Z4505 | F5 Z4 :Duct Installation& Dusct Accecories Installation, Fan coil Unit | 26522 | 2013-10-17 16:00 | 2013-11-06 16:00 | 20 | 296 | 100 | 94 | -6 | 36260 | 36260 | 34084.4 | 31163.1779 | 0.94 | 1.0937 | FALSE | FALSE | FALSE | 37 | FALSE | 0 | Green | Continue normal monitoring.
147147 | HCMEF5Z4510 | F5 Z4 :Duct Insulation Work | 26522 | 2013-11-06 16:00 | 2013-11-27 16:00 | 21 | 328 | 100 | 98 | -2 | 19719 | 19719 | 19324.62 | 20024.5096 | 0.98 | 0.96505 | FALSE | FALSE | FALSE | 41 | FALSE | 0 | Green | Continue normal monitoring.
147148 | HCMEF5Z4515 | F5 Z4 :Exhaust Fans | 26522 | 2013-11-27 16:00 | 2013-12-18 16:00 | 21 | 328 | 100 | 86 | -14 | 30072 | 30072 | 25861.92 | 29160.7994 | 0.86 | 0.88687 | TRUE | TRUE | TRUE | 41 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147149 | HCMEF5Z4520 | F5 Z4 :Grills & Diffusers | 26522 | 2014-02-26 16:00 | 2014-03-12 16:00 | 14 | 328 | 100 | 98 | -2 | 7084 | 7084 | 6942.32 | 8141.2322 | 0.98 | 0.85274 | TRUE | FALSE | FALSE | 41 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147150 | HCMEF5Z4525 | F5 Z4 :Mechanical final Fix | 26522 | 2014-03-12 16:00 | 2014-03-26 16:00 | 14 | 328 | 100 | 100 | 0 | 24066 | 24066 | 24066 | 22461.0642 | 1 | 1.0715 | FALSE | FALSE | FALSE | 41 | FALSE | 0 | Green | Continue normal monitoring.
147151 | HCMEF5Z4530 | F5 Z4 :All Vertical Piping Works | 26523 | 2013-04-29 08:00 | 2013-05-10 17:00 | 11 | 951 | 100 | 98 | -2 | 10120 | 10120 | 9917.6 | 9432.7309 | 0.98 | 1.0514 | FALSE | FALSE | FALSE | 118.875 | FALSE | 0 | Green | Continue normal monitoring.
147152 | HCMEF5Z4535 | F5 Z4 :All Horizantal Piping Works | 26523 | 2013-05-13 08:00 | 2013-06-21 17:00 | 39 | 951 | 100 | 90 | -10 | 51948 | 51948 | 46753.2 | 48093.8541 | 0.9 | 0.97212 | FALSE | FALSE | FALSE | 118.875 | FALSE | 0 | Green | Continue normal monitoring.
147153 | HCMEF5Z4540 | F5 Z4 :Mechanical Final Fix | 26523 | 2013-11-13 08:00 | 2013-12-10 17:00 | 27 | 855 | 100 | 100 | 0 | 46332 | 46332 | 46332 | 41710.209 | 1 | 1.1108 | FALSE | FALSE | FALSE | 106.875 | FALSE | 0 | Green | Continue normal monitoring.
147154 | HCMEF5Z5330 | F5 Z5 :Blocks Start Date for All Parts | 26526 | 2013-09-11 16:00 | 2013-09-11 16:00 | 1 | 600 | 100 | 84 | -16 | 1058 | 1058 | 888.72 | 1030.9182 | 0.84 | 0.86207 | TRUE | TRUE | TRUE | 75 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147155 | HCMEF5Z5335 | F5 Z5 :Tiling Finish Date for All Parts | 26526 | 2014-02-03 16:00 | 2014-02-03 16:00 | 1 | 288 | 100 | 84 | -16 | 1671 | 1671 | 1403.64 | 2012.5003 | 0.84 | 0.69746 | TRUE | TRUE | TRUE | 36 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147156 | HCMEF5Z5340 | F5 Z5 :Plastering Finish Date for All Parts | 26526 | 2013-11-03 16:00 | 2013-11-03 16:00 | 1 | 784 | 100 | 100 | 0 | 1725 | 1725 | 1725 | 2000.9506 | 1 | 0.86209 | TRUE | FALSE | FALSE | 98 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147157 | HCMEF5Z5425 | F5 Z5 :Gypsum Boards Finish Date for All Parts | 26526 | 2014-03-23 12:00 | 2014-03-23 12:00 | 1 | 419 | 100 | 100 | 0 | 1967 | 1967 | 1967 | 2250.4457 | 1 | 0.87405 | TRUE | FALSE | FALSE | 52.375 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147158 | HCMEF5Z5440 | F5 Z5 :Electrical Coduits & Boards F.F for All Systems | 26526 | 2013-09-11 16:00 | 2013-09-27 16:00 | 16 | 536 | 100 | 87 | -13 | 22608 | 22608 | 19668.96 | 26427.2762 | 0.87 | 0.74427 | TRUE | TRUE | TRUE | 67 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147159 | HCMEF5Z5445 | F5 Z5 :Electrical Boards Seconed Fix | 26526 | 2013-12-13 08:00 | 2013-12-30 17:00 | 17 | 503 | 100 | 89 | -11 | 33014 | 33014 | 29382.46 | 31619.7249 | 0.89 | 0.92924 | FALSE | TRUE | TRUE | 62.875 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147160 | HCMEF5Z5450 | F5 Z5 :Cable Tray Installation | 26526 | 2013-12-04 16:00 | 2013-12-18 16:00 | 14 | 488 | 100 | 85 | -15 | 27300 | 27300 | 23205 | 32895.8633 | 0.85 | 0.70541 | TRUE | TRUE | TRUE | 61 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147161 | HCMEF5Z5455 | F5 Z5 :Electrcial Wiring | 26526 | 2014-02-14 13:00 | 2014-03-10 12:00 | 23 | 171 | 100 | 94 | -6 | 34638 | 34638 | 32559.72 | 31344.6657 | 0.94 | 1.0388 | FALSE | FALSE | FALSE | 21.375 | FALSE | 0 | Green | Continue normal monitoring.
147162 | HCMEF5Z5460 | F5 Z5 :Cable Laying | 26526 | 2013-12-18 16:00 | 2014-01-01 16:00 | 14 | 488 | 100 | 95 | -5 | 27972 | 27972 | 26573.4 | 27539.5051 | 0.95 | 0.96492 | FALSE | FALSE | FALSE | 61 | FALSE | 0 | Green | Continue normal monitoring.
147163 | HCMEF5Z5465 | F5 Z5 :Electrical Final Fix for All Systems & Boards (Vertical Elements) | 26526 | 2014-04-09 13:00 | 2014-04-23 12:00 | 13 | 171 | 100 | 100 | 0 | 8125 | 8125 | 8125 | 8813.1814 | 1 | 0.92191 | FALSE | FALSE | FALSE | 21.375 | FALSE | 0 | Green | Continue normal monitoring.
147164 | HCMEF5Z5470 | F5 Z5 :Electrical Final Fix for All Systems (Horizantel Elements) | 26526 | 2014-04-23 13:00 | 2014-05-07 12:00 | 13 | 171 | 100 | 96 | -4 | 11622 | 11622 | 11157.12 | 10357.0852 | 0.96 | 1.0772 | FALSE | FALSE | FALSE | 21.375 | FALSE | 0 | Green | Continue normal monitoring.
147165 | HCMEF5Z5480 | F5 Z5 :All Vertical Piping Works | 26525 | 2013-04-29 08:00 | 2013-05-10 17:00 | 11 | 856 | 100 | 100 | 0 | 14476 | 14476 | 14476 | 16532.3458 | 1 | 0.87562 | TRUE | FALSE | FALSE | 107 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147166 | HCMEF5Z5485 | F5 Z5 :All Horizantal Piping Works | 26525 | 2013-05-13 08:00 | 2013-06-21 17:00 | 39 | 856 | 100 | 87 | -13 | 53820 | 53820 | 46823.4 | 54083.6329 | 0.87 | 0.86576 | TRUE | TRUE | TRUE | 107 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147167 | HCMEF5Z5490 | F5 Z5 :Mechanical Final Fix | 26525 | 2013-11-13 08:00 | 2013-12-10 17:00 | 27 | 760 | 100 | 87 | -13 | 29025 | 29025 | 25251.75 | 33778.1998 | 0.87 | 0.74758 | TRUE | TRUE | TRUE | 95 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147168 | HCMEF5Z5495 | F5 Z5 :Horizontal F.F Piping Work | 26527 | 2013-09-11 16:00 | 2013-10-09 16:00 | 28 | 568 | 100 | 100 | 0 | 23072 | 23072 | 23072 | 24160.0412 | 1 | 0.95497 | FALSE | FALSE | FALSE | 71 | FALSE | 0 | Green | Continue normal monitoring.
147169 | HCMEF5Z5500 | F5 Z5 :Fire Hose Cabinets | 26527 | 2013-10-09 16:00 | 2013-10-23 16:00 | 14 | 568 | 100 | 88 | -12 | 26810 | 26810 | 23592.8 | 24728.1984 | 0.88 | 0.95408 | FALSE | TRUE | TRUE | 71 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147170 | HCMEF5Z5505 | F5 Z5 :Sprinklers Final Fix | 26527 | 2014-02-03 08:00 | 2014-02-14 17:00 | 11 | 551 | 100 | 81 | -19 | 15719 | 15719 | 12732.39 | 17981.0384 | 0.81 | 0.7081 | TRUE | TRUE | TRUE | 68.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147171 | HCMEF5Z5510 | F5 Z5 :Duct Installation& Dusct Accecories Installation, Fan coil Unit | 26528 | 2013-10-17 16:00 | 2013-11-06 16:00 | 20 | 296 | 100 | 94 | -6 | 39260 | 39260 | 36904.4 | 37330.6687 | 0.94 | 0.98858 | FALSE | FALSE | FALSE | 37 | FALSE | 0 | Green | Continue normal monitoring.
147172 | HCMEF5Z5515 | F5 Z5 :Duct Insulation Work | 26528 | 2013-11-06 16:00 | 2013-11-27 16:00 | 21 | 328 | 100 | 97 | -3 | 36267 | 36267 | 35178.99 | 37947.0369 | 0.97 | 0.92705 | FALSE | FALSE | FALSE | 41 | FALSE | 0 | Green | Continue normal monitoring.
147173 | HCMEF5Z5520 | F5 Z5 :Exhaust Fans | 26528 | 2013-11-27 16:00 | 2013-12-18 16:00 | 21 | 328 | 100 | 82 | -18 | 27972 | 27972 | 22937.04 | 24621.3266 | 0.82 | 0.93159 | FALSE | TRUE | TRUE | 41 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147174 | HCMEF5Z5525 | F5 Z5 :Grills & Diffusers | 26528 | 2014-02-26 16:00 | 2014-03-12 16:00 | 14 | 328 | 100 | 96 | -4 | 21756 | 21756 | 20885.76 | 23869.5228 | 0.96 | 0.875 | TRUE | FALSE | FALSE | 41 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147175 | HCMEF5Z5530 | F5 Z5 :Mechanical final Fix | 26528 | 2014-03-12 16:00 | 2014-03-26 16:00 | 14 | 328 | 100 | 83 | -17 | 26754 | 26754 | 22205.82 | 29866.6435 | 0.83 | 0.7435 | TRUE | TRUE | TRUE | 41 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147176 | HCMEF5Z5535 | F5 Z5 :All Vertical Piping Works | 26529 | 2013-04-29 08:00 | 2013-05-10 17:00 | 11 | 1111 | 100 | 100 | 0 | 21527 | 21527 | 21527 | 21558.6379 | 1 | 0.99853 | FALSE | FALSE | FALSE | 138.875 | FALSE | 0 | Green | Continue normal monitoring.
147177 | HCMEF5Z5540 | F5 Z5 :All Horizantal Piping Works | 26529 | 2013-05-13 08:00 | 2013-06-21 17:00 | 39 | 1111 | 100 | 83 | -17 | 52104 | 52104 | 43246.32 | 64180.0978 | 0.83 | 0.67383 | TRUE | TRUE | TRUE | 138.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147178 | HCMEF5Z5545 | F5 Z5 :Mechanical Final Fix | 26529 | 2013-10-28 08:00 | 2013-11-22 17:00 | 25 | 1111 | 100 | 93 | -7 | 35625 | 35625 | 33131.25 | 42738.1571 | 0.93 | 0.77521 | TRUE | FALSE | FALSE | 138.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147179 | HCMEF6Z1545 | F6 Z1 :Blocks Start Date for All Parts | 26533 | 2013-05-11 16:00 | 2013-05-11 16:00 | 1 | 1401 | 100 | 88 | -12 | 1899 | 1899 | 1671.12 | 2151.9019 | 0.88 | 0.77658 | TRUE | TRUE | TRUE | 175.125 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147180 | HCMEF6Z1550 | F6 Z1 :Tiling Finish Date for All Parts | 26533 | 2013-12-15 16:00 | 2013-12-15 16:00 | 1 | 584 | 100 | 88 | -12 | 1867 | 1867 | 1642.96 | 2119.9054 | 0.88 | 0.77502 | TRUE | TRUE | TRUE | 73 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147181 | HCMEF6Z1555 | F6 Z1 :Plastering Finish Date for All Parts | 26533 | 2013-08-26 12:00 | 2013-08-26 12:00 | 1 | 1155 | 100 | 100 | 0 | 942 | 942 | 942 | 895.805 | 1 | 1.0516 | FALSE | FALSE | FALSE | 144.375 | FALSE | 0 | Green | Continue normal monitoring.
147182 | HCMEF6Z1560 | F6 Z1 :Gypsum Boards Finish Date for All Parts | 26533 | 2014-04-09 16:00 | 2014-04-09 16:00 | 1 | 296 | 100 | 100 | 0 | 574 | 574 | 574 | 638.7048 | 1 | 0.89869 | TRUE | FALSE | FALSE | 37 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147183 | HCMEF6Z1575 | F6 Z1 :Electrical Coduits & Boards F.F for All Systems | 26533 | 2013-05-13 08:00 | 2013-05-28 17:00 | 15 | 1167 | 100 | 100 | 0 | 15840 | 15840 | 15840 | 14719.8349 | 1 | 1.0761 | FALSE | FALSE | FALSE | 145.875 | FALSE | 0 | Green | Continue normal monitoring.
147184 | HCMEF6Z1580 | F6 Z1 :Electrical Boards Seconed Fix | 26533 | 2013-09-12 16:00 | 2013-09-30 16:00 | 18 | 952 | 100 | 100 | 0 | 30204 | 30204 | 30204 | 27413.1894 | 1 | 1.1018 | FALSE | FALSE | FALSE | 119 | FALSE | 0 | Green | Continue normal monitoring.
147185 | HCMEF6Z1585 | F6 Z1 :Cable Tray Installation | 26533 | 2014-02-12 16:00 | 2014-02-26 16:00 | 14 | 0 | 100 | 100 | 0 | 27342 | 27342 | 27342 | 34171.6805 | 1 | 0.80014 | TRUE | FALSE | FALSE | 0 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147186 | HCMEF6Z1590 | F6 Z1 :Electrcial Wiring | 26533 | 2014-03-10 08:00 | 2014-04-04 17:00 | 25 | 15 | 100 | 97 | -3 | 21550 | 21550 | 20903.5 | 23682.3805 | 0.97 | 0.88266 | TRUE | FALSE | FALSE | 1.875 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147187 | HCMEF6Z1595 | F6 Z1 :Cable Laying | 26533 | 2014-03-04 16:00 | 2014-03-18 16:00 | 14 | 0 | 100 | 89 | -11 | 13258 | 13258 | 11799.62 | 13554.9149 | 0.89 | 0.8705 | TRUE | TRUE | TRUE | 0 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
147188 | HCMEF6Z1600 | F6 Z1 :Electrical Final Fix for All Systems & Boards (Vertical Elements) | 26533 | 2014-05-07 08:00 | 2014-05-20 17:00 | 13 | 15 | 100 | 100 | 0 | 22841 | 22841 | 22841 | 22047.6363 | 1 | 1.036 | FALSE | FALSE | FALSE | 1.875 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147189 | HCMEF6Z1605 | F6 Z1 :Electrical Final Fix for All Systems (Horizantel Elements) | 26533 | 2014-05-21 08:00 | 2014-06-03 17:00 | 13 | 15 | 100 | 83 | -17 | 9893 | 9893 | 8211.19 | 10798.884 | 0.83 | 0.76037 | TRUE | TRUE | TRUE | 1.875 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
147190 | HCMEF6Z1615 | F6 Z1 :All Vertical Piping Works | 26532 | 2013-05-13 08:00 | 2013-05-24 17:00 | 11 | 871 | 100 | 91 | -9 | 6864 | 6864 | 6246.24 | 5970.5639 | 0.91 | 1.0462 | FALSE | FALSE | FALSE | 108.875 | FALSE | 0 | Green | Continue normal monitoring.
147191 | HCMEF6Z1620 | F6 Z1 :All Horizantal Piping Works | 26532 | 2013-05-27 08:00 | 2013-07-05 17:00 | 39 | 871 | 100 | 100 | 0 | 54990 | 54990 | 54990 | 48824.1031 | 1 | 1.1263 | FALSE | FALSE | FALSE | 108.875 | FALSE | 0 | Green | Continue normal monitoring.
147192 | HCMEF6Z1625 | F6 Z1 :Mechanical Final Fix | 26532 | 2014-03-03 08:00 | 2014-03-28 17:00 | 25 | 231 | 100 | 87 | -13 | 18600 | 18600 | 16182 | 16054.4538 | 0.87 | 1.0079 | FALSE | TRUE | TRUE | 28.875 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147193 | HCMEF6Z1630 | F6 Z1 :Horizontal F.F Piping Work | 26534 | 2013-05-13 08:00 | 2013-06-07 17:00 | 25 | 1271 | 100 | 81 | -19 | 26025 | 26025 | 21080.25 | 27317.608 | 0.81 | 0.77167 | TRUE | TRUE | TRUE | 158.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147194 | HCMEF6Z1635 | F6 Z1 :Fire Hose Cabinets | 26534 | 2013-06-10 08:00 | 2013-06-21 17:00 | 11 | 1271 | 100 | 100 | 0 | 10824 | 10824 | 10824 | 11800.7865 | 1 | 0.91723 | FALSE | FALSE | FALSE | 158.875 | FALSE | 0 | Green | Continue normal monitoring.
147195 | HCMEF6Z1640 | F6 Z1 :Sprinklers Final Fix | 26534 | 2014-03-24 16:00 | 2014-04-07 16:00 | 14 | 264 | 100 | 92 | -8 | 8694 | 8694 | 7998.48 | 7607.1796 | 0.92 | 1.0514 | FALSE | FALSE | FALSE | 33 | FALSE | 0 | Green | Continue normal monitoring.
147196 | HCMEF6Z1645 | F6 Z1 :Duct Installation& Dusct Accecories Installation, Fan coil Unit | 26535 | 2013-11-18 16:00 | 2013-12-02 16:00 | 14 | 184 | 100 | 100 | 0 | 8736 | 8736 | 8736 | 9945.8468 | 1 | 0.87836 | TRUE | FALSE | FALSE | 23 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147197 | HCMEF6Z1650 | F6 Z1 :Duct Insulation Work | 26535 | 2013-12-02 16:00 | 2013-12-23 16:00 | 21 | 184 | 100 | 100 | 0 | 14049 | 14049 | 14049 | 13236.3781 | 1 | 1.0614 | FALSE | FALSE | FALSE | 23 | FALSE | 0 | Green | Continue normal monitoring.
147198 | HCMEF6Z1655 | F6 Z1 :Exhaust Fans | 26535 | 2013-12-23 16:00 | 2014-01-13 16:00 | 21 | 184 | 100 | 95 | -5 | 13083 | 13083 | 12428.85 | 14706.3462 | 0.95 | 0.84514 | TRUE | FALSE | FALSE | 23 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147199 | HCMEF6Z1660 | F6 Z1 :Grills & Diffusers | 26535 | 2014-04-22 16:00 | 2014-05-06 16:00 | 14 | 16 | 100 | 100 | 0 | 21812 | 21812 | 21812 | 27107.0562 | 1 | 0.80466 | TRUE | FALSE | FALSE | 2 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147200 | HCMEF6Z1665 | F6 Z1 :Mechanical final Fix | 26535 | 2014-05-08 16:00 | 2014-05-22 16:00 | 14 | 0 | 100 | 81 | -19 | 22540 | 22540 | 18257.4 | 25390.0105 | 0.81 | 0.71908 | TRUE | TRUE | TRUE | 0 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
147201 | HCMEF6Z1670 | F6 Z1 :All Vertical Piping Works | 26536 | 2013-05-13 08:00 | 2013-05-24 17:00 | 11 | 871 | 100 | 90 | -10 | 12595 | 12595 | 11335.5 | 15155.2766 | 0.9 | 0.74796 | TRUE | FALSE | FALSE | 108.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147202 | HCMEF6Z1675 | F6 Z1 :All Horizantal Piping Works | 26536 | 2013-05-27 08:00 | 2013-07-05 17:00 | 39 | 871 | 100 | 89 | -11 | 50115 | 50115 | 44602.35 | 61605.3373 | 0.89 | 0.724 | TRUE | TRUE | TRUE | 108.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147203 | HCMEF6Z1680 | F6 Z1 :Mechanical Final Fix | 26536 | 2014-03-03 08:00 | 2014-03-28 17:00 | 25 | 231 | 100 | 94 | -6 | 17500 | 17500 | 16450 | 18282.2573 | 0.94 | 0.89978 | TRUE | FALSE | FALSE | 28.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147204 | HCMEF6Z2550 | F6 Z2 :Blocks Start Date for All Parts | 26539 | 2013-07-07 16:00 | 2013-07-07 16:00 | 1 | 1081 | 100 | 96 | -4 | 868 | 868 | 833.28 | 981.6472 | 0.96 | 0.84886 | TRUE | FALSE | FALSE | 135.125 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147205 | HCMEF6Z2555 | F6 Z2 :Tiling Finish Date for All Parts | 26539 | 2013-12-15 16:00 | 2013-12-15 16:00 | 1 | 584 | 100 | 87 | -13 | 1296 | 1296 | 1127.52 | 1543.2609 | 0.87 | 0.73061 | TRUE | TRUE | TRUE | 73 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147206 | HCMEF6Z2560 | F6 Z2 :Plastering Finish Date for All Parts | 26539 | 2013-11-02 16:00 | 2013-11-02 16:00 | 1 | 792 | 100 | 97 | -3 | 576 | 576 | 558.72 | 571.7627 | 0.97 | 0.97719 | FALSE | FALSE | FALSE | 99 | FALSE | 0 | Green | Continue normal monitoring.
147207 | HCMEF6Z2565 | F6 Z2 :Gypsum Boards Finish Date for All Parts | 26539 | 2014-04-08 16:00 | 2014-04-08 16:00 | 1 | 304 | 100 | 100 | 0 | 558 | 558 | 558 | 532.6439 | 1 | 1.0476 | FALSE | FALSE | FALSE | 38 | FALSE | 0 | Green | Continue normal monitoring.
147208 | HCMEF6Z2580 | F6 Z2 :Electrical Coduits & Boards F.F for All Systems | 26539 | 2013-07-08 08:00 | 2013-07-23 17:00 | 15 | 919 | 100 | 88 | -12 | 13950 | 13950 | 12276 | 17139.52 | 0.88 | 0.71624 | TRUE | TRUE | TRUE | 114.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147209 | HCMEF6Z2585 | F6 Z2 :Electrical Boards Seconed Fix | 26539 | 2013-11-04 08:00 | 2013-11-19 17:00 | 15 | 735 | 100 | 100 | 0 | 17055 | 17055 | 17055 | 19451.5925 | 1 | 0.87679 | TRUE | FALSE | FALSE | 91.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147210 | HCMEF6Z2590 | F6 Z2 :Cable Tray Installation | 26539 | 2014-02-12 16:00 | 2014-02-26 16:00 | 14 | 88 | 100 | 87 | -13 | 8512 | 8512 | 7405.44 | 7983.1737 | 0.87 | 0.92763 | FALSE | TRUE | TRUE | 11 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147211 | HCMEF6Z2595 | F6 Z2 :Electrcial Wiring | 26539 | 2014-02-03 08:00 | 2014-02-28 17:00 | 25 | 215 | 100 | 100 | 0 | 37675 | 37675 | 37675 | 38791.4367 | 1 | 0.97122 | FALSE | FALSE | FALSE | 26.875 | FALSE | 0 | Green | Continue normal monitoring.
147212 | HCMEF6Z2600 | F6 Z2 :Cable Laying | 26539 | 2014-02-26 16:00 | 2014-03-12 16:00 | 14 | 88 | 100 | 93 | -7 | 25214 | 25214 | 23449.02 | 29464.594 | 0.93 | 0.79584 | TRUE | FALSE | FALSE | 11 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147213 | HCMEF6Z2605 | F6 Z2 :Electrical Final Fix for All Systems & Boards (Vertical Elements) | 26539 | 2014-04-23 16:00 | 2014-05-07 16:00 | 14 | 88 | 100 | 100 | 0 | 7938 | 7938 | 7938 | 8484.3344 | 1 | 0.93561 | FALSE | FALSE | FALSE | 11 | FALSE | 0 | Green | Continue normal monitoring.
147214 | HCMEF6Z2610 | F6 Z2 :Electrical Final Fix for All Systems (Horizantel Elements) | 26539 | 2014-05-07 16:00 | 2014-05-21 16:00 | 14 | 88 | 100 | 100 | 0 | 22288 | 22288 | 22288 | 24739.2529 | 1 | 0.90092 | FALSE | FALSE | FALSE | 11 | FALSE | 0 | Green | Continue normal monitoring.
147215 | HCMEF6Z2620 | F6 Z2 :All Vertical Piping Works | 26538 | 2013-05-13 08:00 | 2013-05-24 17:00 | 11 | 936 | 100 | 100 | 0 | 18568 | 18568 | 18568 | 21381.1872 | 1 | 0.86843 | TRUE | FALSE | FALSE | 117 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147216 | HCMEF6Z2625 | F6 Z2 :All Horizantal Piping Works | 26538 | 2013-05-27 08:00 | 2013-07-05 17:00 | 39 | 1031 | 100 | 97 | -3 | 31356 | 31356 | 30415.32 | 34454.088 | 0.97 | 0.88278 | TRUE | FALSE | FALSE | 128.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147217 | HCMEF6Z2630 | F6 Z2 :Mechanical Final Fix | 26538 | 2014-03-03 08:00 | 2014-03-28 17:00 | 25 | 391 | 100 | 100 | 0 | 29325 | 29325 | 29325 | 31261.3804 | 1 | 0.93806 | FALSE | FALSE | FALSE | 48.875 | FALSE | 0 | Green | Continue normal monitoring.
147218 | HCMEF6Z2635 | F6 Z2 :Horizontal F.F Piping Work | 26540 | 2013-07-08 08:00 | 2013-08-02 17:00 | 25 | 1031 | 100 | 99 | -1 | 21600 | 21600 | 21384 | 24836.6674 | 0.99 | 0.86099 | TRUE | FALSE | FALSE | 128.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147219 | HCMEF6Z2640 | F6 Z2 :Fire Hose Cabinets | 26540 | 2013-08-05 08:00 | 2013-08-16 17:00 | 11 | 1031 | 100 | 100 | 0 | 14520 | 14520 | 14520 | 16567.6861 | 1 | 0.8764 | TRUE | FALSE | FALSE | 128.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147220 | HCMEF6Z2645 | F6 Z2 :Sprinklers Final Fix | 26540 | 2014-03-24 16:00 | 2014-04-07 16:00 | 14 | 344 | 100 | 99 | -1 | 26628 | 26628 | 26361.72 | 29342.6969 | 0.99 | 0.89841 | TRUE | FALSE | FALSE | 43 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147221 | HCMEF6Z2650 | F6 Z2 :Duct Installation& Dusct Accecories Installation, Fan coil Unit | 26541 | 2013-10-31 16:00 | 2013-11-12 16:00 | 12 | 281 | 100 | 100 | 0 | 10104 | 10104 | 10104 | 10042.5249 | 1 | 1.0061 | FALSE | FALSE | FALSE | 35.125 | FALSE | 0 | Green | Continue normal monitoring.
147222 | HCMEF6Z2655 | F6 Z2 :Duct Insulation Work | 26541 | 2013-11-12 16:00 | 2013-12-03 16:00 | 21 | 281 | 100 | 91 | -9 | 30366 | 30366 | 27633.06 | 30740.256 | 0.91 | 0.89892 | TRUE | FALSE | FALSE | 35.125 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147223 | HCMEF6Z2660 | F6 Z2 :Exhaust Fans | 26541 | 2013-12-03 16:00 | 2013-12-24 16:00 | 21 | 281 | 100 | 98 | -2 | 29358 | 29358 | 28770.84 | 36350.354 | 0.98 | 0.79149 | TRUE | FALSE | FALSE | 35.125 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147224 | HCMEF6Z2665 | F6 Z2 :Grills & Diffusers | 26541 | 2014-04-17 16:00 | 2014-05-01 16:00 | 14 | 25 | 100 | 93 | -7 | 26278 | 26278 | 24438.54 | 23517.611 | 0.93 | 1.0392 | FALSE | FALSE | FALSE | 3.125 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147225 | HCMEF6Z2670 | F6 Z2 :Mechanical final Fix | 26541 | 2014-05-01 16:00 | 2014-05-15 16:00 | 14 | 25 | 100 | 96 | -4 | 27146 | 27146 | 26060.16 | 25989.6338 | 0.96 | 1.0027 | FALSE | FALSE | FALSE | 3.125 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147226 | HCMEF6Z2675 | F6 Z2 :All Vertical Piping Works | 26542 | 2013-05-13 08:00 | 2013-05-24 17:00 | 11 | 1031 | 100 | 100 | 0 | 17952 | 17952 | 17952 | 18795.0386 | 1 | 0.95515 | FALSE | FALSE | FALSE | 128.875 | FALSE | 0 | Green | Continue normal monitoring.
147227 | HCMEF6Z2680 | F6 Z2 :All Horizantal Piping Works | 26542 | 2013-05-27 08:00 | 2013-07-05 17:00 | 39 | 1031 | 100 | 100 | 0 | 49179 | 49179 | 49179 | 58261.9617 | 1 | 0.8441 | TRUE | FALSE | FALSE | 128.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147228 | HCMEF6Z2685 | F6 Z2 :Mechanical Final Fix | 26542 | 2014-03-03 08:00 | 2014-03-28 17:00 | 25 | 391 | 100 | 82 | -18 | 21000 | 21000 | 17220 | 19224.8756 | 0.82 | 0.89571 | TRUE | TRUE | TRUE | 48.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147229 | HCMEF6Z3555 | F6 Z3 :Blocks Start Date for All Parts | 26544 | 2013-09-09 16:00 | 2013-09-09 16:00 | 1 | 768 | 100 | 100 | 0 | 1441 | 1441 | 1441 | 1384.4866 | 1 | 1.0408 | FALSE | FALSE | FALSE | 96 | FALSE | 0 | Green | Continue normal monitoring.
147230 | HCMEF6Z3560 | F6 Z3 :Tiling Finish Date for All Parts | 26544 | 2014-04-02 16:00 | 2014-04-02 16:00 | 1 | 96 | 100 | 100 | 0 | 882 | 882 | 882 | 772.9136 | 1 | 1.1411 | FALSE | FALSE | FALSE | 12 | FALSE | 0 | Green | Continue normal monitoring.
147231 | HCMEF6Z3565 | F6 Z3 :Plastering Finish Date for All Parts | 26544 | 2014-01-22 16:00 | 2014-01-22 16:00 | 1 | 368 | 100 | 100 | 0 | 1503 | 1503 | 1503 | 1701.9883 | 1 | 0.88308 | TRUE | FALSE | FALSE | 46 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147232 | HCMEF6Z3570 | F6 Z3 :Gypsum Boards Finish Date for All Parts | 26544 | 2014-05-19 16:00 | 2014-05-19 16:00 | 1 | 73 | 100 | 86 | -14 | 799 | 799 | 687.14 | 755.2817 | 0.86 | 0.90978 | FALSE | TRUE | TRUE | 9.125 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147233 | HCMEF6Z3585 | F6 Z3 :Electrical Coduits & Boards F.F for All Systems | 26544 | 2013-09-09 16:00 | 2013-09-25 16:00 | 16 | 648 | 100 | 96 | -4 | 10208 | 10208 | 9799.68 | 10263.8367 | 0.96 | 0.95478 | FALSE | FALSE | FALSE | 81 | FALSE | 0 | Green | Continue normal monitoring.
147234 | HCMEF6Z3590 | F6 Z3 :Electrical Boards Seconed Fix | 26544 | 2014-01-22 16:00 | 2014-02-07 16:00 | 16 | 368 | 100 | 91 | -9 | 13728 | 13728 | 12492.48 | 14105.2534 | 0.91 | 0.88566 | TRUE | FALSE | FALSE | 46 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147235 | HCMEF6Z3595 | F6 Z3 :Cable Tray Installation | 26544 | 2014-02-12 16:00 | 2014-02-26 16:00 | 14 | 184 | 100 | 88 | -12 | 18690 | 18690 | 16447.2 | 22549.963 | 0.88 | 0.72937 | TRUE | TRUE | TRUE | 23 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147236 | HCMEF6Z3600 | F6 Z3 :Electrcial Wiring | 26544 | 2014-04-02 16:00 | 2014-04-10 16:00 | 8 | 80 | 100 | 94 | -6 | 15264 | 15264 | 14348.16 | 15485.8182 | 0.94 | 0.92654 | FALSE | FALSE | FALSE | 10 | FALSE | 0 | Green | Continue normal monitoring.
147237 | HCMEF6Z3605 | F6 Z3 :Cable Laying | 26544 | 2014-02-26 16:00 | 2014-03-12 16:00 | 14 | 184 | 100 | 97 | -3 | 25242 | 25242 | 24484.74 | 22922.008 | 0.97 | 1.0682 | FALSE | FALSE | FALSE | 23 | FALSE | 0 | Green | Continue normal monitoring.
147238 | HCMEF6Z3610 | F6 Z3 :Electrical Final Fix for All Systems & Boards (Vertical Elements) | 26544 | 2014-05-12 16:00 | 2014-05-16 16:00 | 4 | 80 | 100 | 100 | 0 | 3928 | 3928 | 3928 | 4162.6036 | 1 | 0.94364 | FALSE | FALSE | FALSE | 10 | FALSE | 0 | Green | Continue normal monitoring.
147239 | HCMEF6Z3615 | F6 Z3 :Electrical Final Fix for All Systems (Horizantel Elements) | 26544 | 2014-05-19 16:00 | 2014-05-23 16:00 | 4 | 72 | 100 | 92 | -8 | 5632 | 5632 | 5181.44 | 6956.5518 | 0.92 | 0.74483 | TRUE | FALSE | FALSE | 9 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147240 | HCMEF6Z3625 | F6 Z3 :All Vertical Piping Works | 26543 | 2013-05-13 08:00 | 2013-05-24 17:00 | 11 | 936 | 100 | 100 | 0 | 17974 | 17974 | 17974 | 19646.9167 | 1 | 0.91485 | FALSE | FALSE | FALSE | 117 | FALSE | 0 | Green | Continue normal monitoring.
147241 | HCMEF6Z3630 | F6 Z3 :All Horizantal Piping Works | 26543 | 2013-05-27 08:00 | 2013-07-05 17:00 | 39 | 1031 | 100 | 100 | 0 | 53235 | 53235 | 53235 | 66189.9975 | 1 | 0.80428 | TRUE | FALSE | FALSE | 128.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147242 | HCMEF6Z3635 | F6 Z3 :Mechanical Final Fix | 26543 | 2014-03-03 08:00 | 2014-03-28 17:00 | 25 | 391 | 100 | 100 | 0 | 15950 | 15950 | 15950 | 18923.7646 | 1 | 0.84286 | TRUE | FALSE | FALSE | 48.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147243 | HCMEF6Z3640 | F6 Z3 :Horizontal F.F Piping Work | 26545 | 2013-09-09 16:00 | 2013-10-07 16:00 | 28 | 664 | 100 | 87 | -13 | 41860 | 41860 | 36418.2 | 36183.2106 | 0.87 | 1.0065 | FALSE | TRUE | TRUE | 83 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147244 | HCMEF6Z3645 | F6 Z3 :Fire Hose Cabinets | 26545 | 2013-10-07 16:00 | 2013-10-21 16:00 | 14 | 664 | 100 | 93 | -7 | 13076 | 13076 | 12160.68 | 14558.2932 | 0.93 | 0.83531 | TRUE | FALSE | FALSE | 83 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147245 | HCMEF6Z3650 | F6 Z3 :Sprinklers Final Fix | 26545 | 2014-03-24 16:00 | 2014-04-07 16:00 | 14 | 344 | 100 | 87 | -13 | 14112 | 14112 | 12277.44 | 13613.9417 | 0.87 | 0.90183 | FALSE | TRUE | TRUE | 43 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147246 | HCMEF6Z3655 | F6 Z3 :Duct Installation& Dusct Accecories Installation, Fan coil Unit | 26546 | 2013-11-12 16:00 | 2013-11-22 16:00 | 10 | 312 | 100 | 93 | -7 | 7720 | 7720 | 7179.6 | 8290.0969 | 0.93 | 0.86605 | TRUE | FALSE | FALSE | 39 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147247 | HCMEF6Z3660 | F6 Z3 :Duct Insulation Work | 26546 | 2013-11-22 16:00 | 2013-12-13 16:00 | 21 | 312 | 100 | 86 | -14 | 34062 | 34062 | 29293.32 | 32758.7224 | 0.86 | 0.89421 | TRUE | TRUE | TRUE | 39 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147248 | HCMEF6Z3665 | F6 Z3 :Exhaust Fans | 26546 | 2013-12-13 16:00 | 2014-01-03 16:00 | 21 | 312 | 100 | 100 | 0 | 12663 | 12663 | 12663 | 12530.6484 | 1 | 1.0106 | FALSE | FALSE | FALSE | 39 | FALSE | 0 | Green | Continue normal monitoring.
147249 | HCMEF6Z3670 | F6 Z3 :Grills & Diffusers | 26546 | 2014-04-17 16:00 | 2014-05-01 16:00 | 14 | 120 | 100 | 91 | -9 | 24318 | 24318 | 22129.38 | 29650.1467 | 0.91 | 0.74635 | TRUE | FALSE | FALSE | 15 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147250 | HCMEF6Z3675 | F6 Z3 :Mechanical final Fix | 26546 | 2014-05-01 16:00 | 2014-05-15 16:00 | 14 | 120 | 100 | 90 | -10 | 17654 | 17654 | 15888.6 | 16465.1315 | 0.9 | 0.96498 | FALSE | FALSE | FALSE | 15 | FALSE | 0 | Green | Continue normal monitoring.
147251 | HCMEF6Z3680 | F6 Z3 :All Vertical Piping Works | 26547 | 2013-05-13 08:00 | 2013-05-24 17:00 | 11 | 1031 | 100 | 100 | 0 | 14146 | 14146 | 14146 | 16970.159 | 1 | 0.83358 | TRUE | FALSE | FALSE | 128.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147252 | HCMEF6Z3685 | F6 Z3 :All Horizantal Piping Works | 26547 | 2013-05-27 08:00 | 2013-07-05 17:00 | 39 | 1031 | 100 | 100 | 0 | 25896 | 25896 | 25896 | 22327.0942 | 1 | 1.1598 | FALSE | FALSE | FALSE | 128.875 | FALSE | 0 | Green | Continue normal monitoring.
147253 | HCMEF6Z3690 | F6 Z3 :Mechanical Final Fix | 26547 | 2014-03-03 08:00 | 2014-03-28 17:00 | 25 | 391 | 100 | 90 | -10 | 37450 | 37450 | 33705 | 33193.8305 | 0.9 | 1.0154 | FALSE | FALSE | FALSE | 48.875 | FALSE | 0 | Green | Continue normal monitoring.
147254 | HCMEF6Z4560 | F6 Z4 :Blocks Start Date for All Parts | 26549 | 2013-09-23 16:00 | 2013-09-23 16:00 | 1 | 545 | 100 | 100 | 0 | 1019 | 1019 | 1019 | 1214.5155 | 1 | 0.83902 | TRUE | FALSE | FALSE | 68.125 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147255 | HCMEF6Z4565 | F6 Z4 :Tiling Finish Date for All Parts | 26549 | 2013-12-29 16:00 | 2013-12-29 16:00 | 1 | 488 | 100 | 100 | 0 | 1807 | 1807 | 1807 | 1991.7159 | 1 | 0.90726 | FALSE | FALSE | FALSE | 61 | FALSE | 0 | Green | Continue normal monitoring.
147256 | HCMEF6Z4570 | F6 Z4 :Plastering Finish Date for All Parts | 26549 | 2014-01-13 16:00 | 2014-01-13 16:00 | 1 | 312 | 100 | 100 | 0 | 1016 | 1016 | 1016 | 1167.2768 | 1 | 0.8704 | TRUE | FALSE | FALSE | 39 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147257 | HCMEF6Z4575 | F6 Z4 :Gypsum Boards Finish Date for All Parts | 26549 | 2014-02-25 16:00 | 2014-02-25 16:00 | 1 | 592 | 100 | 100 | 0 | 1156 | 1156 | 1156 | 1079.4347 | 1 | 1.0709 | FALSE | FALSE | FALSE | 74 | FALSE | 0 | Green | Continue normal monitoring.
147258 | HCMEF6Z4590 | F6 Z4 :Electrical Coduits & Boards F.F for All Systems | 26549 | 2013-09-23 16:00 | 2013-10-09 16:00 | 16 | 472 | 100 | 92 | -8 | 17792 | 17792 | 16368.64 | 18945.5155 | 0.92 | 0.86398 | TRUE | FALSE | FALSE | 59 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147259 | HCMEF6Z4595 | F6 Z4 :Electrical Boards Seconed Fix | 26549 | 2014-01-13 16:00 | 2014-01-29 16:00 | 16 | 328 | 100 | 97 | -3 | 10608 | 10608 | 10289.76 | 12144.9686 | 0.97 | 0.84724 | TRUE | FALSE | FALSE | 41 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147260 | HCMEF6Z4600 | F6 Z4 :Cable Tray Installation | 26549 | 2014-01-13 16:00 | 2014-01-27 16:00 | 14 | 264 | 100 | 81 | -19 | 7882 | 7882 | 6384.42 | 8677.496 | 0.81 | 0.73574 | TRUE | TRUE | TRUE | 33 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147261 | HCMEF6Z4605 | F6 Z4 :Electrcial Wiring | 26549 | 2014-01-23 16:00 | 2014-02-20 16:00 | 28 | 264 | 100 | 100 | 0 | 45192 | 45192 | 45192 | 46940.0043 | 1 | 0.96276 | FALSE | FALSE | FALSE | 33 | FALSE | 0 | Green | Continue normal monitoring.
147262 | HCMEF6Z4610 | F6 Z4 :Cable Laying | 26549 | 2014-01-27 16:00 | 2014-02-10 16:00 | 14 | 264 | 100 | 100 | 0 | 22960 | 22960 | 22960 | 28330.6543 | 1 | 0.81043 | TRUE | FALSE | FALSE | 33 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147263 | HCMEF6Z4615 | F6 Z4 :Electrical Final Fix for All Systems & Boards (Vertical Elements) | 26549 | 2014-03-24 16:00 | 2014-04-07 16:00 | 14 | 264 | 100 | 94 | -6 | 10724 | 10724 | 10080.56 | 12015.8445 | 0.94 | 0.83894 | TRUE | FALSE | FALSE | 33 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147264 | HCMEF6Z4620 | F6 Z4 :Electrical Final Fix for All Systems (Horizantel Elements) | 26549 | 2014-04-07 16:00 | 2014-04-21 16:00 | 14 | 264 | 100 | 99 | -1 | 23282 | 23282 | 23049.18 | 28243.4017 | 0.99 | 0.81609 | TRUE | FALSE | FALSE | 33 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147265 | HCMEF6Z4630 | F6 Z4 :All Vertical Piping Works | 26548 | 2013-05-13 08:00 | 2013-05-24 17:00 | 11 | 936 | 100 | 100 | 0 | 8195 | 8195 | 8195 | 9357.9377 | 1 | 0.87573 | TRUE | FALSE | FALSE | 117 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147266 | HCMEF6Z4635 | F6 Z4 :All Horizantal Piping Works | 26548 | 2013-05-27 08:00 | 2013-07-05 17:00 | 39 | 1031 | 100 | 97 | -3 | 34866 | 34866 | 33820.02 | 39893.1686 | 0.97 | 0.84776 | TRUE | FALSE | FALSE | 128.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147267 | HCMEF6Z4640 | F6 Z4 :Mechanical Final Fix | 26548 | 2013-12-11 08:00 | 2014-01-07 17:00 | 27 | 855 | 100 | 100 | 0 | 26325 | 26325 | 26325 | 23218.8424 | 1 | 1.1338 | FALSE | FALSE | FALSE | 106.875 | FALSE | 0 | Green | Continue normal monitoring.
147268 | HCMEF6Z4645 | F6 Z4 :Horizontal F.F Piping Work | 26550 | 2013-09-23 16:00 | 2013-10-21 16:00 | 28 | 584 | 100 | 94 | -6 | 41328 | 41328 | 38848.32 | 41071.1816 | 0.94 | 0.94588 | FALSE | FALSE | FALSE | 73 | FALSE | 0 | Green | Continue normal monitoring.
147269 | HCMEF6Z4650 | F6 Z4 :Fire Hose Cabinets | 26550 | 2013-10-21 16:00 | 2013-11-04 16:00 | 14 | 584 | 100 | 98 | -2 | 23898 | 23898 | 23420.04 | 28518.6248 | 0.98 | 0.82122 | TRUE | FALSE | FALSE | 73 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147270 | HCMEF6Z4655 | F6 Z4 :Sprinklers Final Fix | 26550 | 2014-02-12 16:00 | 2014-02-26 16:00 | 14 | 568 | 100 | 100 | 0 | 21602 | 21602 | 21602 | 20371.5835 | 1 | 1.0604 | FALSE | FALSE | FALSE | 71 | FALSE | 0 | Green | Continue normal monitoring.
147271 | HCMEF6Z4660 | F6 Z4 :Duct Installation& Dusct Accecories Installation, Fan coil Unit | 26551 | 2013-11-06 16:00 | 2013-11-26 16:00 | 20 | 296 | 100 | 100 | 0 | 21140 | 21140 | 21140 | 18945.7176 | 1 | 1.1158 | FALSE | FALSE | FALSE | 37 | FALSE | 0 | Green | Continue normal monitoring.
147272 | HCMEF6Z4665 | F6 Z4 :Duct Insulation Work | 26551 | 2013-11-26 16:00 | 2013-12-17 16:00 | 21 | 296 | 100 | 91 | -9 | 31857 | 31857 | 28989.87 | 31233.9543 | 0.91 | 0.92815 | FALSE | FALSE | FALSE | 37 | FALSE | 0 | Green | Continue normal monitoring.
147273 | HCMEF6Z4670 | F6 Z4 :Exhaust Fans | 26551 | 2013-12-17 16:00 | 2014-01-07 16:00 | 21 | 296 | 100 | 92 | -8 | 29022 | 29022 | 26700.24 | 27227.7193 | 0.92 | 0.98063 | FALSE | FALSE | FALSE | 37 | FALSE | 0 | Green | Continue normal monitoring.
147274 | HCMEF6Z4675 | F6 Z4 :Grills & Diffusers | 26551 | 2014-03-18 16:00 | 2014-04-01 16:00 | 14 | 296 | 100 | 100 | 0 | 9044 | 9044 | 9044 | 11034.7226 | 1 | 0.81959 | TRUE | FALSE | FALSE | 37 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147275 | HCMEF6Z4680 | F6 Z4 :Mechanical final Fix | 26551 | 2014-04-01 16:00 | 2014-04-15 16:00 | 14 | 296 | 100 | 90 | -10 | 16310 | 16310 | 14679 | 19526.1144 | 0.9 | 0.75176 | TRUE | FALSE | FALSE | 37 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147276 | HCMEF6Z4685 | F6 Z4 :All Vertical Piping Works | 26552 | 2013-05-13 08:00 | 2013-05-24 17:00 | 11 | 1031 | 100 | 84 | -16 | 20097 | 20097 | 16881.48 | 21099.3036 | 0.84 | 0.8001 | TRUE | TRUE | TRUE | 128.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147277 | HCMEF6Z4690 | F6 Z4 :All Horizantal Piping Works | 26552 | 2013-05-27 08:00 | 2013-07-05 17:00 | 39 | 1031 | 100 | 100 | 0 | 43641 | 43641 | 43641 | 38165.6932 | 1 | 1.1435 | FALSE | FALSE | FALSE | 128.875 | FALSE | 0 | Green | Continue normal monitoring.
147278 | HCMEF6Z4695 | F6 Z4 :Mechanical Final Fix | 26552 | 2013-12-11 08:00 | 2014-01-07 17:00 | 27 | 855 | 100 | 80 | -20 | 35613 | 35613 | 28490.4 | 40450.1335 | 0.8 | 0.70433 | TRUE | TRUE | TRUE | 106.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147279 | HCMEF6Z5565 | F6 Z5 :Blocks Start Date for All Parts | 26554 | 2013-09-23 16:00 | 2013-09-23 16:00 | 1 | 641 | 100 | 100 | 0 | 1363 | 1363 | 1363 | 1498.4341 | 1 | 0.90962 | FALSE | FALSE | FALSE | 80.125 | FALSE | 0 | Green | Continue normal monitoring.
147280 | HCMEF6Z5570 | F6 Z5 :Tiling Finish Date for All Parts | 26554 | 2014-04-17 16:00 | 2014-04-17 16:00 | 1 | 1 | 100 | 82 | -18 | 1081 | 1081 | 886.42 | 1338.5178 | 0.82 | 0.66224 | TRUE | TRUE | TRUE | 0.125 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
147281 | HCMEF6Z5575 | F6 Z5 :Plastering Finish Date for All Parts | 26554 | 2013-12-04 12:00 | 2013-12-04 12:00 | 1 | 699 | 100 | 100 | 0 | 1522 | 1522 | 1522 | 1633.9907 | 1 | 0.93146 | FALSE | FALSE | FALSE | 87.375 | FALSE | 0 | Green | Continue normal monitoring.
147282 | HCMEF6Z5580 | F6 Z5 :Gypsum Boards Finish Date for All Parts | 26554 | 2014-04-08 12:00 | 2014-04-08 12:00 | 1 | 356 | 100 | 100 | 0 | 1194 | 1194 | 1194 | 1175.5616 | 1 | 1.0157 | FALSE | FALSE | FALSE | 44.5 | FALSE | 0 | Green | Continue normal monitoring.
147283 | HCMEF6Z5595 | F6 Z5 :Electrical Coduits & Boards F.F for All Systems | 26554 | 2013-09-23 16:00 | 2013-10-09 16:00 | 16 | 568 | 100 | 98 | -2 | 28016 | 28016 | 27455.68 | 29629.9647 | 0.98 | 0.92662 | FALSE | FALSE | FALSE | 71 | FALSE | 0 | Green | Continue normal monitoring.
147284 | HCMEF6Z5600 | F6 Z5 :Electrical Boards Seconed Fix | 26554 | 2013-12-31 08:00 | 2014-01-15 17:00 | 15 | 503 | 100 | 100 | 0 | 24375 | 24375 | 24375 | 30266.5671 | 1 | 0.80534 | TRUE | FALSE | FALSE | 62.875 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147285 | HCMEF6Z5605 | F6 Z5 :Cable Tray Installation | 26554 | 2013-12-18 16:00 | 2014-01-01 16:00 | 14 | 504 | 100 | 100 | 0 | 27160 | 27160 | 27160 | 30651.2815 | 1 | 0.8861 | TRUE | FALSE | FALSE | 63 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147286 | HCMEF6Z5610 | F6 Z5 :Electrcial Wiring | 26554 | 2014-04-17 16:00 | 2014-04-23 16:00 | 6 | 8 | 100 | 100 | 0 | 10434 | 10434 | 10434 | 11673.4596 | 1 | 0.89382 | TRUE | FALSE | FALSE | 1 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147287 | HCMEF6Z5615 | F6 Z5 :Cable Laying | 26554 | 2014-01-01 16:00 | 2014-01-15 16:00 | 14 | 504 | 100 | 86 | -14 | 12684 | 12684 | 10908.24 | 12002.5221 | 0.86 | 0.90883 | FALSE | TRUE | TRUE | 63 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147288 | HCMEF6Z5620 | F6 Z5 :Electrical Final Fix for All Systems & Boards (Vertical Elements) | 26554 | 2014-05-23 16:00 | 2014-05-29 16:00 | 6 | 8 | 100 | 91 | -9 | 5388 | 5388 | 4903.08 | 6182.4121 | 0.91 | 0.79307 | TRUE | FALSE | FALSE | 1 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147289 | HCMEF6Z5625 | F6 Z5 :Electrical Final Fix for All Systems (Horizantel Elements) | 26554 | 2014-05-29 16:00 | 2014-06-04 16:00 | 6 | 8 | 100 | 94 | -6 | 7284 | 7284 | 6846.96 | 8377.392 | 0.94 | 0.81731 | TRUE | FALSE | FALSE | 1 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147290 | HCMEF6Z5635 | F6 Z5 :All Vertical Piping Works | 26553 | 2013-05-13 08:00 | 2013-05-24 17:00 | 11 | 936 | 100 | 100 | 0 | 13233 | 13233 | 13233 | 12927.524 | 1 | 1.0236 | FALSE | FALSE | FALSE | 117 | FALSE | 0 | Green | Continue normal monitoring.
147291 | HCMEF6Z5640 | F6 Z5 :All Horizantal Piping Works | 26553 | 2013-05-27 08:00 | 2013-07-05 17:00 | 39 | 936 | 100 | 84 | -16 | 49140 | 49140 | 41277.6 | 51276.8791 | 0.84 | 0.80499 | TRUE | TRUE | TRUE | 117 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147292 | HCMEF6Z5645 | F6 Z5 :Mechanical Final Fix | 26553 | 2013-12-11 08:00 | 2014-01-07 17:00 | 27 | 760 | 100 | 94 | -6 | 26946 | 26946 | 25329.24 | 26079.4526 | 0.94 | 0.97123 | FALSE | FALSE | FALSE | 95 | FALSE | 0 | Green | Continue normal monitoring.
147293 | HCMEF6Z5650 | F6 Z5 :Horizontal F.F Piping Work | 26555 | 2013-09-23 16:00 | 2013-10-21 16:00 | 28 | 584 | 100 | 87 | -13 | 55664 | 55664 | 48427.68 | 53074.6236 | 0.87 | 0.91245 | FALSE | TRUE | TRUE | 73 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147294 | HCMEF6Z5655 | F6 Z5 :Fire Hose Cabinets | 26555 | 2013-10-21 16:00 | 2013-11-04 16:00 | 14 | 584 | 100 | 89 | -11 | 20622 | 20622 | 18353.58 | 17742.3115 | 0.89 | 1.0345 | FALSE | TRUE | TRUE | 73 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147295 | HCMEF6Z5660 | F6 Z5 :Sprinklers Final Fix | 26555 | 2014-02-17 08:00 | 2014-02-28 17:00 | 11 | 551 | 100 | 100 | 0 | 6391 | 6391 | 6391 | 6161.4653 | 1 | 1.0373 | FALSE | FALSE | FALSE | 68.875 | FALSE | 0 | Green | Continue normal monitoring.
147296 | HCMEF6Z5665 | F6 Z5 :Duct Installation& Dusct Accecories Installation, Fan coil Unit | 26556 | 2013-11-06 16:00 | 2013-11-26 16:00 | 20 | 296 | 100 | 95 | -5 | 22060 | 22060 | 20957 | 23639.2308 | 0.95 | 0.88653 | TRUE | FALSE | FALSE | 37 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147297 | HCMEF6Z5670 | F6 Z5 :Duct Insulation Work | 26556 | 2013-11-26 16:00 | 2013-12-17 16:00 | 21 | 296 | 100 | 87 | -13 | 26691 | 26691 | 23221.17 | 22704.4449 | 0.87 | 1.0228 | FALSE | TRUE | TRUE | 37 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147298 | HCMEF6Z5675 | F6 Z5 :Exhaust Fans | 26556 | 2013-12-17 16:00 | 2014-01-07 16:00 | 21 | 296 | 100 | 80 | -20 | 29442 | 29442 | 23553.6 | 28361.1145 | 0.8 | 0.83049 | TRUE | TRUE | TRUE | 37 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147299 | HCMEF6Z5680 | F6 Z5 :Grills & Diffusers | 26556 | 2014-03-18 16:00 | 2014-04-01 16:00 | 14 | 296 | 100 | 91 | -9 | 12096 | 12096 | 11007.36 | 14546.2158 | 0.91 | 0.75672 | TRUE | FALSE | FALSE | 37 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147300 | HCMEF6Z5685 | F6 Z5 :Mechanical final Fix | 26556 | 2014-04-01 16:00 | 2014-04-15 16:00 | 14 | 296 | 100 | 84 | -16 | 9268 | 9268 | 7785.12 | 10078.574 | 0.84 | 0.77244 | TRUE | TRUE | TRUE | 37 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147301 | HCMEF6Z5690 | F6 Z5 :All Vertical Piping Works | 26557 | 2013-05-13 08:00 | 2013-05-24 17:00 | 11 | 1031 | 100 | 82 | -18 | 17281 | 17281 | 14170.42 | 18890.641 | 0.82 | 0.75013 | TRUE | TRUE | TRUE | 128.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147302 | HCMEF6Z5695 | F6 Z5 :All Horizantal Piping Works | 26557 | 2013-05-27 08:00 | 2013-07-05 17:00 | 39 | 1031 | 100 | 80 | -20 | 39390 | 39390 | 31512 | 39836.908 | 0.8 | 0.79103 | TRUE | TRUE | TRUE | 128.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147303 | HCMEF6Z5700 | F6 Z5 :Mechanical Final Fix | 26557 | 2013-11-11 08:00 | 2013-12-06 17:00 | 25 | 1031 | 100 | 83 | -17 | 46300 | 46300 | 38429 | 51883.2641 | 0.83 | 0.74068 | TRUE | TRUE | TRUE | 128.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147304 | HCMERF00090 | RF :All Vertical Piping Works | 26257 | 2013-10-28 08:00 | 2013-11-08 17:00 | 11 | 80 | 100 | 87 | -13 | 6765 | 6765 | 5885.55 | 6264.2081 | 0.87 | 0.93955 | FALSE | TRUE | TRUE | 10 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147305 | HCMERF00100 | RF :All Horizantal Piping Works | 26257 | 2013-11-11 08:00 | 2013-12-20 17:00 | 39 | 80 | 100 | 82 | -18 | 56160 | 56160 | 46051.2 | 66128.3283 | 0.82 | 0.69639 | TRUE | TRUE | TRUE | 10 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147306 | HCMERF00110 | RF :Mechanical Final Fix | 26257 | 2014-04-28 08:00 | 2014-05-23 17:00 | 25 | 80 | 100 | 89 | -11 | 20900 | 20900 | 18601 | 18740.521 | 0.89 | 0.99256 | FALSE | TRUE | TRUE | 10 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147307 | HCMEF7Z1700 | F7 :Blocks Start Date for All Parts | 26561 | 2013-10-10 16:00 | 2013-10-10 16:00 | 1 | 464 | 100 | 81 | -19 | 1380 | 1380 | 1117.8 | 1535.1127 | 0.81 | 0.72815 | TRUE | TRUE | TRUE | 58 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147308 | HCMEF7Z1710 | F7 :Plastering Finish Date for All Parts | 26561 | 2013-12-10 16:00 | 2013-12-10 16:00 | 1 | 528 | 100 | 90 | -10 | 1236 | 1236 | 1112.4 | 1219.2642 | 0.9 | 0.91235 | FALSE | FALSE | FALSE | 66 | FALSE | 0 | Green | Continue normal monitoring.
147309 | HCMEF7Z1730 | F7 :Electrical Coduits & Boards F.F for All Systems | 26561 | 2013-10-10 16:00 | 2013-10-28 16:00 | 18 | 392 | 100 | 100 | 0 | 24102 | 24102 | 24102 | 27693.323 | 1 | 0.87032 | TRUE | FALSE | FALSE | 49 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147310 | HCMEF7Z1735 | F7 :Electrical Boards Seconed Fix | 26561 | 2014-01-06 16:00 | 2014-01-22 16:00 | 16 | 392 | 100 | 89 | -11 | 10336 | 10336 | 9199.04 | 11058.5466 | 0.89 | 0.83185 | TRUE | TRUE | TRUE | 49 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147311 | HCMEF7Z1740 | F7 :Cable Tray Installation | 26561 | 2014-02-26 16:00 | 2014-03-18 16:00 | 20 | 0 | 100 | 100 | 0 | 36920 | 36920 | 36920 | 38062.3497 | 1 | 0.96999 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147312 | HCMEF7Z1750 | F7 :Cable Laying | 26561 | 2014-03-18 16:00 | 2014-04-01 16:00 | 14 | 0 | 100 | 93 | -7 | 13188 | 13188 | 12264.84 | 12103.5371 | 0.93 | 1.0133 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147313 | HCMEF7Z1755 | F7 :Electrical Final Fix for All Systems & Boards (Vertical Elements) | 26561 | 2014-05-13 16:00 | 2014-05-26 16:00 | 13 | 0 | 100 | 86 | -14 | 17368 | 17368 | 14936.48 | 19186.9261 | 0.86 | 0.77847 | TRUE | TRUE | TRUE | 0 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
147314 | HCMEF7Z1760 | F7 :Electrical Final Fix for All Systems (Horizantel Elements) | 26561 | 2014-05-26 16:00 | 2014-06-05 16:00 | 10 | 0 | 100 | 100 | 0 | 15360 | 15360 | 15360 | 19044.9859 | 1 | 0.80651 | TRUE | FALSE | FALSE | 0 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147315 | HCMEF7Z1770 | F7 :All Vertical Piping Works | 26560 | 2013-10-14 08:00 | 2013-10-25 17:00 | 11 | 80 | 100 | 100 | 0 | 15862 | 15862 | 15862 | 18720.9886 | 1 | 0.84728 | TRUE | FALSE | FALSE | 10 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147316 | HCMEF7Z1775 | F7 :All Horizantal Piping Works | 26560 | 2013-10-28 08:00 | 2013-12-06 17:00 | 39 | 151 | 100 | 81 | -19 | 30654 | 30654 | 24829.74 | 26791.6965 | 0.81 | 0.92677 | FALSE | TRUE | TRUE | 18.875 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147317 | HCMEF7Z1780 | F7 :Mechanical Final Fix | 26560 | 2014-04-14 08:00 | 2014-05-09 17:00 | 25 | 151 | 100 | 88 | -12 | 30475 | 30475 | 26818 | 30489.9861 | 0.88 | 0.87957 | TRUE | TRUE | TRUE | 18.875 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147318 | HCMEF7Z1785 | F7 :Horizontal F.F Piping Work | 26562 | 2013-10-10 16:00 | 2013-11-07 16:00 | 28 | 480 | 100 | 95 | -5 | 45836 | 45836 | 43544.2 | 55930.6091 | 0.95 | 0.77854 | TRUE | FALSE | FALSE | 60 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147319 | HCMEF7Z1790 | F7 :Fire Hose Cabinets | 26562 | 2013-11-07 16:00 | 2013-11-21 16:00 | 14 | 480 | 100 | 92 | -8 | 13706 | 13706 | 12609.52 | 14407.987 | 0.92 | 0.87518 | TRUE | FALSE | FALSE | 60 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147320 | HCMEF7Z1795 | F7 :Sprinklers Final Fix | 26562 | 2014-04-07 16:00 | 2014-04-21 16:00 | 14 | 264 | 100 | 88 | -12 | 7294 | 7294 | 6418.72 | 8131.6775 | 0.88 | 0.78935 | TRUE | TRUE | TRUE | 33 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147321 | HCMEF7Z1800 | F7 :Duct Installation& Dusct Accecories Installation, Fan coil Unit | 26563 | 2013-12-02 16:00 | 2013-12-16 16:00 | 14 | 184 | 100 | 99 | -1 | 26208 | 26208 | 25945.92 | 31843.7615 | 0.99 | 0.81479 | TRUE | FALSE | FALSE | 23 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147322 | HCMEF7Z1805 | F7 :Duct Insulation Work | 26563 | 2013-12-16 16:00 | 2014-01-06 16:00 | 21 | 184 | 100 | 83 | -17 | 24822 | 24822 | 20602.26 | 29774.4327 | 0.83 | 0.69194 | TRUE | TRUE | TRUE | 23 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147323 | HCMEF7Z1810 | F7 :Exhaust Fans | 26563 | 2014-01-06 16:00 | 2014-01-27 16:00 | 21 | 184 | 100 | 100 | 0 | 29505 | 29505 | 29505 | 31001.7341 | 1 | 0.95172 | FALSE | FALSE | FALSE | 23 | FALSE | 0 | Green | Continue normal monitoring.
147324 | HCMEF7Z1815 | F7 :Grills & Diffusers | 26563 | 2014-05-06 16:00 | 2014-05-20 16:00 | 14 | 16 | 100 | 89 | -11 | 11466 | 11466 | 10204.74 | 11753.321 | 0.89 | 0.86824 | TRUE | TRUE | TRUE | 2 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
147325 | HCMEF7Z1820 | F7 :Mechanical final Fix | 26563 | 2014-05-22 16:00 | 2014-06-05 16:00 | 14 | 0 | 100 | 100 | 0 | 8750 | 8750 | 8750 | 8626.4242 | 1 | 1.0143 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147326 | HCMEF7Z1825 | F7 :All Vertical Piping Works | 26564 | 2013-10-14 08:00 | 2013-10-25 17:00 | 11 | 80 | 100 | 100 | 0 | 8536 | 8536 | 8536 | 9710.62 | 1 | 0.87904 | TRUE | FALSE | FALSE | 10 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147327 | HCMEF7Z1830 | F7 :All Horizantal Piping Works | 26564 | 2013-10-28 08:00 | 2013-12-06 17:00 | 39 | 151 | 100 | 100 | 0 | 67353 | 67353 | 67353 | 64981.8188 | 1 | 1.0365 | FALSE | FALSE | FALSE | 18.875 | FALSE | 0 | Green | Continue normal monitoring.
147328 | HCMEF7Z1835 | F7 :Mechanical Final Fix | 26564 | 2014-04-14 08:00 | 2014-05-09 17:00 | 25 | 151 | 100 | 91 | -9 | 17325 | 17325 | 15765.75 | 16457.9711 | 0.91 | 0.95794 | FALSE | FALSE | FALSE | 18.875 | FALSE | 0 | Green | Continue normal monitoring.
147329 | HCMERF00000 | RF :Start Roof Floor EM Works | 26035 | 2013-09-18 08:00 | 2013-09-18 08:00 | 1 | 296 | 100 | 96 | -4 | 1195 | 1195 | 1147.2 | 1186.0374 | 0.96 | 0.96725 | FALSE | FALSE | FALSE | 37 | FALSE | 0 | Green | Continue normal monitoring.
147330 | HCMERF000000 | RF :End Roof Floor EM Works | 26035 | 2014-04-16 08:00 | 2014-04-16 08:00 | 1 | 328 | 100 | 93 | -7 | 1809 | 1809 | 1682.37 | 1665.8828 | 0.93 | 1.0099 | FALSE | FALSE | FALSE | 41 | FALSE | 0 | Green | Continue normal monitoring.
147331 | HCMEF7000 | F7 :Start Seventh Floor EM Works | 26032 | 2013-10-12 08:00 | 2013-10-12 08:00 | 1 | 80 | 100 | 93 | -7 | 556 | 556 | 517.08 | 627.1946 | 0.93 | 0.82443 | TRUE | FALSE | FALSE | 10 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147332 | HCMEF70000 | F7 :End Seventh Floor EM Works | 26032 | 2014-06-05 16:00 | 2014-06-05 16:00 | 1 | 0 | 100 | 100 | 0 | 1826 | 1826 | 1826 | 2002.2022 | 1 | 0.912 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147333 | HCMEF6000 | Start Sixth Floor EM Works | 26031 | 2013-05-12 08:00 | 2013-05-12 08:00 | 1 | 1016 | 100 | 81 | -19 | 1686 | 1686 | 1365.66 | 1758.7533 | 0.81 | 0.77649 | TRUE | TRUE | TRUE | 127 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147334 | HCMEF60000 | End Sixth Floor EM Works | 26031 | 2014-05-22 16:00 | 2014-05-22 16:00 | 1 | 80 | 100 | 100 | 0 | 518 | 518 | 518 | 521.1755 | 1 | 0.99391 | FALSE | FALSE | FALSE | 10 | FALSE | 0 | Green | Continue normal monitoring.
147335 | HCMEF5000 | Start Fifth Floor EM Works | 26041 | 2013-04-29 08:00 | 2013-04-29 08:00 | 1 | 904 | 100 | 100 | 0 | 1893 | 1893 | 1893 | 2297.3922 | 1 | 0.82398 | TRUE | FALSE | FALSE | 113 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147336 | HCMEF50000 | End Fifth Floor EM Works | 26041 | 2014-05-08 16:00 | 2014-05-08 16:00 | 1 | 176 | 100 | 99 | -1 | 763 | 763 | 755.37 | 657.4386 | 0.99 | 1.149 | FALSE | FALSE | FALSE | 22 | FALSE | 0 | Green | Continue normal monitoring.
147337 | HCMEF4000 | Start Fourth Floor EM Works | 26039 | 2013-04-17 08:00 | 2013-04-17 08:00 | 1 | 792 | 100 | 90 | -10 | 1293 | 1293 | 1163.7 | 1496.8325 | 0.9 | 0.77744 | TRUE | FALSE | FALSE | 99 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147338 | HCMEF40000 | End Fourth Floor EM Works | 26039 | 2014-04-24 16:00 | 2014-04-24 16:00 | 1 | 264 | 100 | 95 | -5 | 612 | 612 | 581.4 | 740.9875 | 0.95 | 0.78463 | TRUE | FALSE | FALSE | 33 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147339 | HCMEF3000 | Start Third Floor EM Works | 26043 | 2013-04-06 08:00 | 2013-04-06 08:00 | 1 | 704 | 100 | 98 | -2 | 1850 | 1850 | 1813 | 1902.8024 | 0.98 | 0.95281 | FALSE | FALSE | FALSE | 88 | FALSE | 0 | Green | Continue normal monitoring.
147340 | HCMEF30000 | End Third Floor EM Works | 26043 | 2014-04-10 16:00 | 2014-04-10 16:00 | 1 | 360 | 100 | 100 | 0 | 1041 | 1041 | 1041 | 1114.1575 | 1 | 0.93434 | FALSE | FALSE | FALSE | 45 | FALSE | 0 | Green | Continue normal monitoring.
147341 | HCMEF2000 | Start Second Floor EM Works | 26048 | 2013-03-25 08:00 | 2013-03-25 08:00 | 1 | 592 | 100 | 100 | 0 | 1146 | 1146 | 1146 | 1407.0422 | 1 | 0.81447 | TRUE | FALSE | FALSE | 74 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147342 | HCMEF20000 | End Second Floor EM Works | 26048 | 2014-05-15 16:00 | 2014-05-15 16:00 | 1 | 128 | 100 | 85 | -15 | 1078 | 1078 | 916.3 | 1007.8341 | 0.85 | 0.90918 | FALSE | TRUE | TRUE | 16 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147343 | HCMEF1000 | Start First Floor EM Works | 26033 | 2013-03-13 08:00 | 2013-03-13 08:00 | 1 | 488 | 100 | 100 | 0 | 1588 | 1588 | 1588 | 1680.1897 | 1 | 0.94513 | FALSE | FALSE | FALSE | 61 | FALSE | 0 | Green | Continue normal monitoring.
147344 | HCMEF10000 | End First Floor EM Works | 26033 | 2014-03-13 16:00 | 2014-03-13 16:00 | 1 | 552 | 100 | 98 | -2 | 1815 | 1815 | 1778.7 | 1887.3975 | 0.98 | 0.94241 | FALSE | FALSE | FALSE | 69 | FALSE | 0 | Green | Continue normal monitoring.
147345 | HCMEGF000 | Start Ground Floor EM Works | 26034 | 2013-02-27 08:00 | 2013-02-27 08:00 | 1 | 400 | 100 | 84 | -16 | 524 | 524 | 440.16 | 499.5591 | 0.84 | 0.8811 | TRUE | TRUE | TRUE | 50 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147346 | HCMEGF0000 | End Ground Floor EM Works | 26034 | 2014-02-27 16:00 | 2014-02-27 16:00 | 1 | 648 | 100 | 100 | 0 | 500 | 500 | 500 | 588.7186 | 1 | 0.8493 | TRUE | FALSE | FALSE | 81 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147347 | HCMEB4000 | Start Basement 4 Floor EM Works | 26038 | 2012-10-13 08:00 | 2012-10-13 08:00 | 1 | 528 | 100 | 83 | -17 | 1410 | 1410 | 1170.3 | 1705.8747 | 0.83 | 0.68604 | TRUE | TRUE | TRUE | 66 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147348 | HCMEB40000 | End Basement 4 Floor EM Works | 26038 | 2014-01-02 16:00 | 2014-01-02 16:00 | 1 | 1024 | 100 | 94 | -6 | 640 | 640 | 601.6 | 744.1747 | 0.94 | 0.80841 | TRUE | FALSE | FALSE | 128 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147349 | HCMEB3000 | Start Basement 3 Floor EM Works | 26036 | 2012-12-03 08:00 | 2012-12-03 08:00 | 1 | 400 | 100 | 100 | 0 | 1147 | 1147 | 1147 | 1064.5807 | 1 | 1.0774 | FALSE | FALSE | FALSE | 50 | FALSE | 0 | Green | Continue normal monitoring.
147350 | HCMEB30000 | End Basement 3 Floor EM Works | 26036 | 2014-01-16 16:00 | 2014-01-16 16:00 | 1 | 936 | 100 | 83 | -17 | 687 | 687 | 570.21 | 607.7885 | 0.83 | 0.93817 | FALSE | TRUE | TRUE | 117 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147351 | HCMEB2000 | Start Basement 2 Floor EM Works | 26037 | 2012-12-31 08:00 | 2012-12-31 08:00 | 1 | 400 | 100 | 99 | -1 | 1651 | 1651 | 1634.49 | 1803.1855 | 0.99 | 0.90645 | FALSE | FALSE | FALSE | 50 | FALSE | 0 | Green | Continue normal monitoring.
147352 | HCMEB20000 | End Basement 2 Floor EM Works | 26037 | 2014-01-30 16:00 | 2014-01-30 16:00 | 1 | 840 | 100 | 89 | -11 | 700 | 700 | 623 | 610.9865 | 0.89 | 1.0197 | FALSE | TRUE | TRUE | 105 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147353 | HCMEB1000 | Start Basement 1 Floor EM Works | 26040 | 2013-02-16 08:00 | 2013-02-16 08:00 | 1 | 288 | 100 | 100 | 0 | 1650 | 1650 | 1650 | 1846.5651 | 1 | 0.89355 | TRUE | FALSE | FALSE | 36 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147354 | HCMEB10000 | End Basement 1 Floor EM Works | 26040 | 2014-02-15 08:00 | 2014-02-15 08:00 | 1 | 744 | 100 | 100 | 0 | 756 | 756 | 756 | 803.0003 | 1 | 0.94147 | FALSE | FALSE | FALSE | 93 | FALSE | 0 | Green | Continue normal monitoring.
147355 | HCSWAFAZ000 | Construct of left over areas (crane # 3) | 25722 | 2013-08-27 08:00 | 2013-10-27 16:00 | 61 | 0 | 100 | 82 | -18 | 63806 | 63806 | 52320.92 | 71150.9826 | 0.82 | 0.73535 | TRUE | TRUE | TRUE | 0 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
147356 | HCSWAFAZ010 | Construct of left over areas (crane # 2) | 25722 | 2014-02-19 08:00 | 2014-03-31 16:00 | 40 | 104 | 100 | 100 | 0 | 27720 | 27720 | 27720 | 30105.8135 | 1 | 0.92075 | FALSE | FALSE | FALSE | 13 | FALSE | 0 | Green | Continue normal monitoring.
147357 | HCFWAFAZ000 | Finish Left over areas (Crane #3) | 25722 | 2013-10-28 08:00 | 2014-04-15 16:00 | 169 | 0 | 100 | 84 | -16 | 203138 | 203138 | 170635.92 | 207014.0818 | 0.84 | 0.82427 | TRUE | TRUE | TRUE | 0 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
147358 | HCFWAFAZ010 | Finish Left over areas (Crane #2) | 25722 | 2014-04-16 08:00 | 2014-07-22 16:00 | 97 | 0 | 100 | 85 | -15 | 157819 | 157819 | 134146.15 | 146827.0443 | 0.85 | 0.91363 | FALSE | TRUE | TRUE | 0 | TRUE | 4 | Orange | Develop recovery plan and review schedule and cost exposure.
147359 | HCEXWERW010 | EXT :External Earth Works | 25752 | 2013-09-18 08:00 | 2013-10-27 16:00 | 39 | 128 | 100 | 100 | 0 | 69732 | 69732 | 69732 | 67799.0885 | 1 | 1.0285 | FALSE | FALSE | FALSE | 16 | FALSE | 0 | Green | Continue normal monitoring.
147360 | HHAWAFAZ0010 | Snag and de-snag | 25705 | 2014-06-07 08:00 | 2014-07-10 16:00 | 33 | 0 | 100 | 100 | 0 | 42933 | 42933 | 42933 | 45500.4033 | 1 | 0.94357 | FALSE | FALSE | FALSE | 0 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147361 | HHAWAFAZ0020 | Test and commision for All systems | 25705 | 2014-06-18 08:00 | 2014-07-22 16:00 | 34 | 0 | 100 | 87 | -13 | 48994 | 48994 | 42624.78 | 54419.9502 | 0.87 | 0.78326 | TRUE | TRUE | TRUE | 0 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
147362 | HEMSSFI0270 | MS submission: Toilet & corian vanity tops | 25761 | 2012-11-03 08:00 | 2012-11-19 16:00 | 16 | 1768 | 100 | 86 | -14 | 30512 | 30512 | 26240.32 | 35448.6343 | 0.86 | 0.74024 | TRUE | TRUE | TRUE | 221 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147363 | HEMSSFI0320 | MS submission: Metal Works | 25761 | 2013-01-14 08:00 | 2013-01-30 16:00 | 16 | 520 | 100 | 100 | 0 | 28528 | 28528 | 28528 | 33003.1385 | 1 | 0.8644 | TRUE | FALSE | FALSE | 65 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147364 | HCFWF1Z1120 | F1 Z1 :Plaster First Layer | 26209 | 2013-03-28 12:00 | 2013-04-08 10:00 | 10 | 568 | 100 | 89 | -11 | 9130 | 9130 | 8125.7 | 11312.7593 | 0.89 | 0.71828 | TRUE | TRUE | TRUE | 71 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147365 | HCFWF1Z1130 | F1 Z1 :Plaster Final Layer | 26209 | 2013-04-17 10:00 | 2013-04-27 16:00 | 10 | 568 | 100 | 85 | -15 | 18810 | 18810 | 15988.5 | 18139.1711 | 0.85 | 0.88143 | TRUE | TRUE | TRUE | 71 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147366 | HCFWF1Z1010 | F1 Z1 :Rubber Skirting | 26208 | 2014-01-08 08:00 | 2014-01-09 16:00 | 1 | 784 | 100 | 93 | -7 | 1598 | 1598 | 1486.14 | 1403.754 | 0.93 | 1.0587 | FALSE | FALSE | FALSE | 98 | FALSE | 0 | Green | Continue normal monitoring.
147367 | HCFWF1Z1110 | F1 Z1 :Plaster Second Layer | 26209 | 2013-04-08 10:00 | 2013-04-17 10:00 | 9 | 568 | 100 | 83 | -17 | 16902 | 16902 | 14028.66 | 16703.6174 | 0.83 | 0.83986 | TRUE | TRUE | TRUE | 71 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147368 | HCFWF1Z20030 | F1 Z2 :Rubber Skirting | 26362 | 2014-01-11 08:00 | 2014-01-12 16:00 | 1 | 784 | 100 | 100 | 0 | 1409 | 1409 | 1409 | 1616.5708 | 1 | 0.8716 | TRUE | FALSE | FALSE | 98 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147369 | HCFWF1Z30029 | F1 Z3 :Rubber Skirting | 26150 | 2014-01-13 08:00 | 2014-01-15 16:00 | 2 | 784 | 100 | 100 | 0 | 1374 | 1374 | 1374 | 1408.6862 | 1 | 0.97538 | FALSE | FALSE | FALSE | 98 | FALSE | 0 | Green | Continue normal monitoring.
147370 | HCFWF1Z30046 | F1 Z3 :Block Works | 26151 | 2013-06-29 08:00 | 2013-07-09 16:00 | 10 | 600 | 100 | 92 | -8 | 18130 | 18130 | 16679.6 | 21341.1017 | 0.92 | 0.78157 | TRUE | FALSE | FALSE | 75 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147371 | HCFWF1Z1160 | F1 Z1 :Stone Cladding | 26209 | 2013-04-28 08:00 | 2013-05-09 16:00 | 11 | 2568 | 100 | 99 | -1 | 5984 | 5984 | 5924.16 | 6401.2676 | 0.99 | 0.92547 | FALSE | FALSE | FALSE | 321 | FALSE | 0 | Green | Continue normal monitoring.
147372 | HCFWF2Z11063 | F2 Z1Block Works | 26225 | 2013-03-09 08:00 | 2013-03-19 16:00 | 10 | 624 | 100 | 96 | -4 | 5820 | 5820 | 5587.2 | 7111.5551 | 0.96 | 0.78565 | TRUE | FALSE | FALSE | 78 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147373 | HCFWF2Z1010 | F2 Z1Rubber Skirting | 26224 | 2014-01-16 08:00 | 2014-01-18 16:00 | 2 | 784 | 100 | 100 | 0 | 3292 | 3292 | 3292 | 4046.3466 | 1 | 0.81357 | TRUE | FALSE | FALSE | 98 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147374 | HCFWF2Z21055 | F2 Z2 :Rubber Skirting | 26229 | 2014-01-19 08:00 | 2014-01-20 16:00 | 1 | 784 | 100 | 86 | -14 | 857 | 857 | 737.02 | 752.2076 | 0.86 | 0.97981 | FALSE | TRUE | TRUE | 98 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147375 | HCFWF2Z21057 | F2 Z2 :Block Works | 26230 | 2013-05-05 08:00 | 2013-05-15 16:00 | 10 | 968 | 100 | 83 | -17 | 15890 | 15890 | 13188.7 | 16407.4638 | 0.83 | 0.80382 | TRUE | TRUE | TRUE | 121 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147376 | HCFWGFZ3064 | F2 Z3 :GF Z3 :Rubber Skirting | 26383 | 2014-01-21 08:00 | 2014-01-22 16:00 | 1 | 784 | 100 | 100 | 0 | 1435 | 1435 | 1435 | 1569.7115 | 1 | 0.91418 | FALSE | FALSE | FALSE | 98 | FALSE | 0 | Green | Continue normal monitoring.
147377 | HCFWGFZ3086 | F2 Z3 :GF Z3 :Block Works | 26384 | 2013-07-10 08:00 | 2013-07-21 16:00 | 11 | 600 | 100 | 93 | -7 | 9614 | 9614 | 8941.02 | 9155.8834 | 0.93 | 0.97653 | FALSE | FALSE | FALSE | 75 | FALSE | 0 | Green | Continue normal monitoring.
147378 | HCFWF3Z11093 | F3 Z1 :Block Works | 26241 | 2013-03-20 08:00 | 2013-03-31 16:00 | 11 | 736 | 100 | 82 | -18 | 7271 | 7271 | 5962.22 | 7364.2921 | 0.82 | 0.80961 | TRUE | TRUE | TRUE | 92 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147379 | HCFWF3Z11119 | F3 Z1 :Rubber Skirting | 26240 | 2014-01-23 08:00 | 2014-01-25 16:00 | 2 | 784 | 100 | 100 | 0 | 3806 | 3806 | 3806 | 4266.8024 | 1 | 0.892 | TRUE | FALSE | FALSE | 98 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147380 | HCFWF3Z21080 | F3 Z2 :Rubber Skirting | 26245 | 2014-01-26 08:00 | 2014-01-27 16:00 | 1 | 784 | 100 | 84 | -16 | 1881 | 1881 | 1580.04 | 1769.4448 | 0.84 | 0.89296 | TRUE | TRUE | TRUE | 98 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147381 | HCFWF3Z21082 | F3 Z2 :Block Works | 26137 | 2013-05-16 08:00 | 2013-05-28 16:00 | 12 | 968 | 100 | 95 | -5 | 20532 | 20532 | 19505.4 | 22396.1525 | 0.95 | 0.87093 | TRUE | FALSE | FALSE | 121 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147382 | HCFWF3Z31094 | F3 Z3 :Rubber Skirting | 26141 | 2014-01-28 08:00 | 2014-01-29 16:00 | 1 | 784 | 100 | 100 | 0 | 821 | 821 | 821 | 926.8919 | 1 | 0.88576 | TRUE | FALSE | FALSE | 98 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147383 | HCFWF3Z31126 | F3 Z3 :Block Works | 26142 | 2013-07-22 08:00 | 2013-08-01 16:00 | 10 | 632 | 100 | 100 | 0 | 9490 | 9490 | 9490 | 8410.024 | 1 | 1.1284 | FALSE | FALSE | FALSE | 79 | FALSE | 0 | Green | Continue normal monitoring.
147384 | HCFWF4Z11123 | F4 Z1 :Block Works | 26148 | 2013-04-01 08:00 | 2013-04-11 16:00 | 10 | 824 | 100 | 99 | -1 | 19970 | 19970 | 19770.3 | 20948.7642 | 0.99 | 0.94375 | FALSE | FALSE | FALSE | 103 | FALSE | 0 | Green | Continue normal monitoring.
147385 | HCFWF4Z11155 | F4 Z1 :Rubber Skirting | 26147 | 2014-01-30 08:00 | 2014-02-01 16:00 | 2 | 784 | 100 | 83 | -17 | 3072 | 3072 | 2549.76 | 2934.4727 | 0.83 | 0.8689 | TRUE | TRUE | TRUE | 98 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147386 | HCFWF4Z21105 | F4 Z2 :Rubber Skirting | 26311 | 2014-02-02 08:00 | 2014-02-03 16:00 | 1 | 784 | 100 | 100 | 0 | 683 | 683 | 683 | 778.4524 | 1 | 0.87738 | TRUE | FALSE | FALSE | 98 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147387 | HCFWF4Z21107 | F4 Z2 :Block Works | 26153 | 2013-05-29 08:00 | 2013-06-09 16:00 | 11 | 1000 | 100 | 100 | 0 | 6710 | 6710 | 6710 | 6212.267 | 1 | 1.0801 | FALSE | FALSE | FALSE | 125 | FALSE | 0 | Green | Continue normal monitoring.
147388 | HCFWF4Z31124 | F4 Z3 :Rubber Skirting | 26156 | 2014-02-04 08:00 | 2014-02-05 16:00 | 1 | 784 | 100 | 100 | 0 | 1007 | 1007 | 1007 | 1215.3434 | 1 | 0.82857 | TRUE | FALSE | FALSE | 98 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147389 | HCFWF4Z31166 | F4 Z3 :Block Works | 26157 | 2013-08-03 08:00 | 2013-08-17 16:00 | 14 | 664 | 100 | 81 | -19 | 25382 | 25382 | 20559.42 | 25949.9612 | 0.81 | 0.79227 | TRUE | TRUE | TRUE | 83 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147390 | HCFWF4Z51163 | F4 Z5 :Block Works | 26161 | 2013-08-20 08:00 | 2013-08-31 16:00 | 11 | 512 | 100 | 100 | 0 | 8734 | 8734 | 8734 | 8115.6434 | 1 | 1.0762 | FALSE | FALSE | FALSE | 64 | FALSE | 0 | Green | Continue normal monitoring.
147391 | HCFWF4Z41130 | F4 Z4 :Rubber Skirting | 26164 | 2014-02-06 08:00 | 2014-02-08 16:00 | 2 | 784 | 100 | 97 | -3 | 3948 | 3948 | 3829.56 | 4047.524 | 0.97 | 0.94615 | FALSE | FALSE | FALSE | 98 | FALSE | 0 | Green | Continue normal monitoring.
147392 | HCFWF4Z41132 | F4 Z4 :Block Works | 26165 | 2013-05-19 08:00 | 2013-05-30 16:00 | 11 | 1064 | 100 | 98 | -2 | 15433 | 15433 | 15124.34 | 15641.307 | 0.98 | 0.96695 | FALSE | FALSE | FALSE | 133 | FALSE | 0 | Green | Continue normal monitoring.
147393 | HCFWF5Z11153 | F5 Z1 :Block Works | 26337 | 2013-04-13 08:00 | 2013-04-23 16:00 | 10 | 936 | 100 | 100 | 0 | 17380 | 17380 | 17380 | 17754.8446 | 1 | 0.97889 | FALSE | FALSE | FALSE | 117 | FALSE | 0 | Green | Continue normal monitoring.
147394 | HCFWF5Z21157 | F5 Z2 :Block Works | 26323 | 2013-06-10 08:00 | 2013-06-20 16:00 | 10 | 1032 | 100 | 100 | 0 | 14730 | 14730 | 14730 | 15970.6271 | 1 | 0.92232 | FALSE | FALSE | FALSE | 129 | FALSE | 0 | Green | Continue normal monitoring.
147395 | HCFWF5Z31206 | F5 Z3 :Block Works | 26330 | 2013-08-18 08:00 | 2013-08-28 16:00 | 10 | 688 | 100 | 100 | 0 | 11310 | 11310 | 11310 | 11971.2899 | 1 | 0.94476 | FALSE | FALSE | FALSE | 86 | FALSE | 0 | Green | Continue normal monitoring.
147396 | HCFWF5Z51203 | F5 Z5 :Block Works | 26316 | 2013-09-01 08:00 | 2013-09-11 16:00 | 10 | 568 | 100 | 98 | -2 | 15500 | 15500 | 15190 | 14103.6182 | 0.98 | 1.077 | FALSE | FALSE | FALSE | 71 | FALSE | 0 | Green | Continue normal monitoring.
147397 | HCFWGFZ4082 | F5 Z4 :GF Z4 :Block Works | 26331 | 2013-09-01 08:00 | 2013-09-11 16:00 | 10 | 488 | 100 | 96 | -4 | 12320 | 12320 | 11827.2 | 10795.1737 | 0.96 | 1.0956 | FALSE | FALSE | FALSE | 61 | FALSE | 0 | Green | Continue normal monitoring.
147398 | HCFWF6Z11183 | F6 Z1 :Block Works | 26195 | 2013-04-24 08:00 | 2013-05-06 16:00 | 12 | 1048 | 100 | 100 | 0 | 21048 | 21048 | 21048 | 24031.8945 | 1 | 0.87584 | TRUE | FALSE | FALSE | 131 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147399 | HCFWF6Z21207 | F6 Z2 :Block Works | 26343 | 2013-06-22 08:00 | 2013-07-02 16:00 | 10 | 1056 | 100 | 93 | -7 | 8200 | 8200 | 7626 | 8805.8732 | 0.93 | 0.86601 | TRUE | FALSE | FALSE | 132 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147400 | HCFWF6Z31246 | F6 Z3 :Block Works | 26355 | 2013-08-29 08:00 | 2013-09-09 16:00 | 11 | 728 | 100 | 98 | -2 | 15532 | 15532 | 15221.36 | 15432.6 | 0.98 | 0.98631 | FALSE | FALSE | FALSE | 91 | FALSE | 0 | Green | Continue normal monitoring.
147401 | HCFWF6Z51243 | F6 Z5 :Block Works | 26359 | 2013-09-12 08:00 | 2013-09-23 16:00 | 11 | 600 | 100 | 100 | 0 | 19316 | 19316 | 19316 | 22664.2959 | 1 | 0.85227 | TRUE | FALSE | FALSE | 75 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147402 | HCFWF6Z41232 | F6 Z4 :Block Works | 26356 | 2013-09-12 08:00 | 2013-09-23 16:00 | 11 | 512 | 100 | 100 | 0 | 10296 | 10296 | 10296 | 10349.78 | 1 | 0.9948 | FALSE | FALSE | FALSE | 64 | FALSE | 0 | Green | Continue normal monitoring.
147403 | HCFWF7AZ010 | F7 :Block Works | 26007 | 2013-09-25 08:00 | 2013-10-10 16:00 | 15 | 80 | 100 | 92 | -8 | 19200 | 19200 | 17664 | 22433.0119 | 0.92 | 0.78741 | TRUE | FALSE | FALSE | 10 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147404 | HCFWF7AZ020 | F7 :Plaster First Layer | 26007 | 2013-10-12 08:00 | 2013-11-03 12:00 | 22 | 512 | 100 | 91 | -9 | 42372 | 42372 | 38558.52 | 41198.3995 | 0.91 | 0.93592 | FALSE | FALSE | FALSE | 64 | FALSE | 0 | Green | Continue normal monitoring.
147405 | HCFWF7AZ030 | F7 :Plaster Second Layer | 26007 | 2013-11-03 12:00 | 2013-11-23 12:00 | 20 | 512 | 100 | 100 | 0 | 31520 | 31520 | 31520 | 27710.4335 | 1 | 1.1375 | FALSE | FALSE | FALSE | 64 | FALSE | 0 | Green | Continue normal monitoring.
147406 | HCFWF7AZ040 | F7 :Plaster Final Layer | 26007 | 2013-11-23 12:00 | 2013-12-10 16:00 | 17 | 512 | 100 | 100 | 0 | 31212 | 31212 | 31212 | 38174.02 | 1 | 0.81762 | TRUE | FALSE | FALSE | 64 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147407 | HCFWF7AZ070 | F7 :Paint prime coat | 26007 | 2013-12-11 08:00 | 2013-12-22 16:00 | 11 | 808 | 100 | 85 | -15 | 19844 | 19844 | 16867.4 | 19999.189 | 0.85 | 0.8434 | TRUE | TRUE | TRUE | 101 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147408 | HCFWF7AZ080 | F7 :Paint putty coat | 26007 | 2013-12-23 08:00 | 2014-01-05 16:00 | 13 | 808 | 100 | 100 | 0 | 15925 | 15925 | 15925 | 18585.7017 | 1 | 0.85684 | TRUE | FALSE | FALSE | 101 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147409 | HCFWF7AZ090 | F7 :Acoustic Wall Panels | 26007 | 2013-12-23 08:00 | 2014-01-05 16:00 | 13 | 888 | 100 | 100 | 0 | 6890 | 6890 | 6890 | 6625.8212 | 1 | 1.0399 | FALSE | FALSE | FALSE | 111 | FALSE | 0 | Green | Continue normal monitoring.
147410 | HCESCN030 | s/c nomination: Convying system Subcontractor | 25737 | 2012-06-23 08:00 | 2012-07-15 16:00 | 22 | 688 | 100 | 83 | -17 | 18392 | 18392 | 15265.36 | 20388.3789 | 0.83 | 0.74873 | TRUE | TRUE | TRUE | 86 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147411 | HCESCA030 | s/c approval: Conveying system Subcontractor | 25733 | 2012-07-16 08:00 | 2012-07-31 16:00 | 15 | 688 | 100 | 98 | -2 | 10230 | 10230 | 10025.4 | 12269.0881 | 0.98 | 0.81713 | TRUE | FALSE | FALSE | 86 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147412 | HEPSCVS0020 | Elecrical Cables & System | 25720 | 2013-08-01 08:00 | 2013-08-21 16:00 | 20 | 688 | 100 | 95 | -5 | 30920 | 30920 | 29374 | 26797.0533 | 0.95 | 1.0962 | FALSE | FALSE | FALSE | 86 | FALSE | 0 | Green | Continue normal monitoring.
147413 | HEPSCVS0040 | Accessories & Finishings | 25720 | 2013-08-01 08:00 | 2013-08-21 16:00 | 20 | 1576 | 100 | 92 | -8 | 20860 | 20860 | 19191.2 | 24661.8248 | 0.92 | 0.77817 | TRUE | FALSE | FALSE | 197 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147414 | HEPSCVS0010 | Manufacturing & Importing Materials | 25720 | 2012-08-01 08:00 | 2013-07-31 16:00 | 364 | 688 | 100 | 83 | -17 | 716716 | 716716 | 594874.28 | 773002.0024 | 0.83 | 0.76956 | TRUE | TRUE | TRUE | 86 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147415 | HCFWB1Z3042 | B1 Z3 :Wood Flooring | 26212 | 2013-12-05 08:00 | 2013-12-16 16:00 | 11 | 808 | 100 | 100 | 0 | 17567 | 17567 | 17567 | 19200.5325 | 1 | 0.91492 | FALSE | FALSE | FALSE | 101 | FALSE | 0 | Green | Continue normal monitoring.
147416 | HCMEPSSE010 | SPS :Installation for Parking Control Equipment | 26066 | 2014-02-11 08:00 | 2014-03-17 16:00 | 34 | 608 | 100 | 100 | 0 | 52122 | 52122 | 52122 | 55210.9165 | 1 | 0.94405 | FALSE | FALSE | FALSE | 76 | FALSE | 0 | Green | Continue normal monitoring.
147417 | HCSDSMEP010 | SD submission: MEP Plans & Details | 25847 | 2012-08-09 08:00 | 2013-09-16 16:00 | 403 | 328 | 100 | 96 | -4 | 797537 | 797537 | 765635.52 | 956876.9502 | 0.96 | 0.80014 | TRUE | FALSE | FALSE | 41 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147418 | HCSDSMEP020 | SD submission: Spicial Systems Plans & Details with coordination | 25847 | 2012-08-09 08:00 | 2013-09-16 16:00 | 403 | 328 | 100 | 100 | 0 | 467077 | 467077 | 467077 | 405130.1389 | 1 | 1.1529 | FALSE | FALSE | FALSE | 41 | FALSE | 0 | Green | Continue normal monitoring.
147419 | HCSDAMEP010 | SD approval: MEP Plans & Details | 25849 | 2012-08-30 08:00 | 2013-10-02 16:00 | 398 | 328 | 100 | 80 | -20 | 262282 | 262282 | 209825.6 | 250324.9194 | 0.8 | 0.83821 | TRUE | TRUE | TRUE | 41 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147420 | HCSDAMEP020 | SD approval: Spicial Systems Plans & Details with coordination | 25849 | 2012-08-30 08:00 | 2013-10-02 16:00 | 398 | 328 | 100 | 97 | -3 | 611726 | 611726 | 593374.22 | 734257.7859 | 0.97 | 0.80813 | TRUE | FALSE | FALSE | 41 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147421 | HCSDSFW010 | SD submission: Floor Finishing Plans & Details | 25846 | 2012-11-07 08:00 | 2013-05-05 16:00 | 179 | 480 | 100 | 100 | 0 | 304479 | 304479 | 304479 | 350436.5369 | 1 | 0.86886 | TRUE | FALSE | FALSE | 60 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147422 | HCSDSFW020 | SD submission: Wall Finishing Plans & Details | 25846 | 2012-11-07 08:00 | 2013-05-05 16:00 | 179 | 56 | 100 | 99 | -1 | 163069 | 163069 | 161438.31 | 139759.6015 | 0.99 | 1.1551 | FALSE | FALSE | FALSE | 7 | FALSE | 0 | Green | Continue normal monitoring.
147423 | HCSDSFW030 | SD submission: Ceiling Finishing Plans & Details | 25846 | 2012-11-07 08:00 | 2013-05-05 16:00 | 179 | 208 | 100 | 96 | -4 | 270469 | 270469 | 259650.24 | 285832.319 | 0.96 | 0.9084 | FALSE | FALSE | FALSE | 26 | FALSE | 0 | Green | Continue normal monitoring.
147424 | HCSDSFW040 | SD submission: Special Interiors | 25846 | 2012-11-07 08:00 | 2013-05-05 16:00 | 179 | 568 | 100 | 100 | 0 | 98808 | 98808 | 98808 | 104917.207 | 1 | 0.94177 | FALSE | FALSE | FALSE | 71 | FALSE | 0 | Green | Continue normal monitoring.
147425 | HCSDAFW010 | SD approval: Floor Finishing Plans & Details | 25848 | 2012-11-25 08:00 | 2013-05-21 16:00 | 177 | 480 | 100 | 100 | 0 | 160539 | 160539 | 160539 | 162201.0368 | 1 | 0.98975 | FALSE | FALSE | FALSE | 60 | FALSE | 0 | Green | Continue normal monitoring.
147426 | HCSDAFW020 | SD approval: Wall Finishing Plans & Details | 25848 | 2012-11-25 08:00 | 2013-05-21 16:00 | 177 | 392 | 100 | 100 | 0 | 238242 | 238242 | 238242 | 230846.3329 | 1 | 1.032 | FALSE | FALSE | FALSE | 49 | FALSE | 0 | Green | Continue normal monitoring.
147427 | HCSDAFW030 | SD approval: Ceiling Finishing Plans & Details | 25848 | 2012-11-25 08:00 | 2013-05-21 16:00 | 177 | 208 | 100 | 94 | -6 | 273465 | 273465 | 257057.1 | 307016.4045 | 0.94 | 0.83727 | TRUE | FALSE | FALSE | 26 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147428 | HCSDAFW040 | SD approval: Special Interiors | 25848 | 2012-11-25 08:00 | 2013-05-21 16:00 | 177 | 568 | 100 | 90 | -10 | 274881 | 274881 | 247392.9 | 256495.9103 | 0.9 | 0.96451 | FALSE | FALSE | FALSE | 71 | FALSE | 0 | Green | Continue normal monitoring.
147429 | HEMSSME1450 | MS submission: Spicial MEP Systems & Equipments | 25832 | 2012-10-22 08:00 | 2013-02-11 16:00 | 112 | 328 | 100 | 100 | 0 | 134624 | 134624 | 134624 | 157453.4605 | 1 | 0.85501 | TRUE | FALSE | FALSE | 41 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147430 | HEMSSME1460 | MS approval: Spicial MEP Systems & Equipments | 25812 | 2013-02-05 08:00 | 2013-02-27 16:00 | 22 | 328 | 100 | 100 | 0 | 16698 | 16698 | 16698 | 19556.9458 | 1 | 0.85381 | TRUE | FALSE | FALSE | 41 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147431 | HEPSSME1470 | Spicial MEP Systems & Equipments | 25719 | 2013-02-05 08:00 | 2013-10-13 16:00 | 250 | 328 | 100 | 100 | 0 | 432000 | 432000 | 432000 | 438957.1764 | 1 | 0.98415 | FALSE | FALSE | FALSE | 41 | FALSE | 0 | Green | Continue normal monitoring.
147432 | HCMEPSSWW010 | SPS :Installation for Window Washing system | 26065 | 2013-12-17 08:00 | 2014-01-23 16:00 | 37 | 968 | 100 | 92 | -8 | 58534 | 58534 | 53851.28 | 56392.7797 | 0.92 | 0.95493 | FALSE | FALSE | FALSE | 121 | FALSE | 0 | Green | Continue normal monitoring.
147433 | HCMEPSSFA010 | SPS :Fire Alarm Control Panel and valves | 26064 | 2013-10-14 08:00 | 2013-10-20 16:00 | 6 | 1360 | 100 | 80 | -20 | 11964 | 11964 | 9571.2 | 11527.9274 | 0.8 | 0.83026 | TRUE | TRUE | TRUE | 170 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147434 | HCMEPSSFA020 | SPS :Vertical & Horizantal Conduts | 26064 | 2013-10-21 08:00 | 2013-11-07 16:00 | 17 | 1360 | 100 | 96 | -4 | 21675 | 21675 | 20808 | 22605.2158 | 0.96 | 0.9205 | FALSE | FALSE | FALSE | 170 | FALSE | 0 | Green | Continue normal monitoring.
147435 | HCMEPSSFA030 | SPS :Fire Alarm Cables & Connect to Panel | 26064 | 2013-11-09 08:00 | 2013-11-16 16:00 | 7 | 1360 | 100 | 85 | -15 | 13923 | 13923 | 11834.55 | 15842.0306 | 0.85 | 0.74703 | TRUE | TRUE | TRUE | 170 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147436 | HCMEPSSFA040 | SPS :Final Fixtures (Detectors, Sound & Flash Alarms) | 26064 | 2013-11-17 08:00 | 2013-11-24 16:00 | 7 | 1360 | 100 | 83 | -17 | 10745 | 10745 | 8918.35 | 10675.6676 | 0.83 | 0.83539 | TRUE | TRUE | TRUE | 170 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147437 | HCMEPSSCV030 | SPS :Main Control system in Security Room with server & software | 26063 | 2013-11-23 08:00 | 2013-12-03 16:00 | 10 | 1216 | 100 | 99 | -1 | 18130 | 18130 | 17948.7 | 19834.5343 | 0.99 | 0.90492 | FALSE | FALSE | FALSE | 152 | FALSE | 0 | Green | Continue normal monitoring.
147438 | HCMEPSSCV010 | SPS :Vertical & Horizantal Conduits | 26063 | 2013-10-14 08:00 | 2013-11-04 16:00 | 21 | 1216 | 100 | 95 | -5 | 28329 | 28329 | 26912.55 | 28413.8109 | 0.95 | 0.94716 | FALSE | FALSE | FALSE | 152 | FALSE | 0 | Green | Continue normal monitoring.
147439 | HCMEPSSCV020 | SPS :Data & power Cables | 26063 | 2013-11-06 08:00 | 2013-11-21 16:00 | 15 | 1216 | 100 | 94 | -6 | 12795 | 12795 | 12027.3 | 12434.2997 | 0.94 | 0.96727 | FALSE | FALSE | FALSE | 152 | FALSE | 0 | Green | Continue normal monitoring.
147440 | HCMEPSSCV040 | SPS :Final Fixtures ( Cameras, Monitors, Remot controls) | 26063 | 2013-12-04 08:00 | 2013-12-15 16:00 | 11 | 1216 | 100 | 100 | 0 | 17578 | 17578 | 17578 | 15116.0922 | 1 | 1.1629 | FALSE | FALSE | FALSE | 152 | FALSE | 0 | Green | Continue normal monitoring.
147441 | HCMEPSSAC040 | SPS :ACS management Software | 26062 | 2013-11-23 08:00 | 2013-11-23 16:00 | 1 | 1368 | 100 | 94 | -6 | 1372 | 1372 | 1289.68 | 1168.3481 | 0.94 | 1.1038 | FALSE | FALSE | FALSE | 171 | FALSE | 0 | Green | Continue normal monitoring.
147442 | HCMEPSSAC030 | SPS :Final Fixtures (Intercom Units, Locks, Controllers, Cardreader) | 26062 | 2013-11-14 08:00 | 2013-11-21 16:00 | 7 | 1368 | 100 | 85 | -15 | 13748 | 13748 | 11685.8 | 12935.2605 | 0.85 | 0.90341 | FALSE | TRUE | TRUE | 171 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147443 | HCMEPSSAC010 | SPS :Main ACS Work Station @ Control room | 26062 | 2013-10-14 08:00 | 2013-10-26 16:00 | 12 | 1368 | 100 | 94 | -6 | 17880 | 17880 | 16807.2 | 18104.6178 | 0.94 | 0.92834 | FALSE | FALSE | FALSE | 171 | FALSE | 0 | Green | Continue normal monitoring.
147444 | HCMEPSSAC020 | SPS :Vertical & Horizantal Pipes & Cables | 26062 | 2013-10-27 08:00 | 2013-11-13 16:00 | 17 | 1368 | 100 | 93 | -7 | 29988 | 29988 | 27888.84 | 35700.848 | 0.93 | 0.78118 | TRUE | FALSE | FALSE | 171 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147445 | HCMEPSSAV010 | SPS :Full Executive Boardrooms hardware & Wiring System | 26061 | 2014-05-20 08:00 | 2014-05-29 16:00 | 9 | 112 | 100 | 100 | 0 | 13653 | 13653 | 13653 | 15965.7321 | 1 | 0.85514 | TRUE | FALSE | FALSE | 14 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147446 | HCMEPSSER010 | SPS :Earthing System | 26059 | 2013-10-14 08:00 | 2013-12-29 16:00 | 76 | 1072 | 100 | 90 | -10 | 127452 | 127452 | 114706.8 | 121954.4988 | 0.9 | 0.94057 | FALSE | FALSE | FALSE | 134 | FALSE | 0 | Green | Continue normal monitoring.
147447 | HCMEPSSER020 | SPS :Connect to Main Rod | 26059 | 2013-12-30 08:00 | 2014-01-07 16:00 | 8 | 1072 | 100 | 86 | -14 | 12952 | 12952 | 11138.72 | 12276.1151 | 0.86 | 0.90735 | FALSE | TRUE | TRUE | 134 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147448 | HCMEPSSIT020 | SPS :Floor Boxes | 26060 | 2013-11-24 08:00 | 2013-12-29 16:00 | 35 | 648 | 100 | 88 | -12 | 27755 | 27755 | 24424.4 | 26115.4796 | 0.88 | 0.93525 | FALSE | TRUE | TRUE | 81 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147449 | HCMEPSSIT040 | SPS :Telecommunication Outlets Installation | 26060 | 2014-02-05 08:00 | 2014-03-11 16:00 | 34 | 648 | 100 | 100 | 0 | 24072 | 24072 | 24072 | 23727.6485 | 1 | 1.0145 | FALSE | FALSE | FALSE | 81 | FALSE | 0 | Green | Continue normal monitoring.
147450 | HCMEPSSIT030 | SPS :IT Cabinits & Pach Panels | 26060 | 2013-12-30 08:00 | 2014-02-04 16:00 | 36 | 648 | 100 | 95 | -5 | 67176 | 67176 | 63817.2 | 70486.3989 | 0.95 | 0.90538 | FALSE | FALSE | FALSE | 81 | FALSE | 0 | Green | Continue normal monitoring.
147451 | HCMEPSSIT010 | SPS :All Vertical & Horizantal Conduts & Wiring Installations | 26060 | 2013-10-14 08:00 | 2013-11-23 16:00 | 40 | 648 | 100 | 84 | -16 | 64440 | 64440 | 54129.6 | 66081.1005 | 0.84 | 0.81914 | TRUE | TRUE | TRUE | 81 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147452 | HCMEPSSAV020 | SPS :Full Auditorium hardware & Wiring System | 26061 | 2014-05-20 08:00 | 2014-05-29 16:00 | 9 | 112 | 100 | 100 | 0 | 11853 | 11853 | 11853 | 11109.9269 | 1 | 1.0669 | FALSE | FALSE | FALSE | 14 | FALSE | 0 | Green | Continue normal monitoring.
147453 | HCMEPSSAV030 | SPS :Full Modular Conference Room hardware & Wiring System | 26061 | 2014-05-20 08:00 | 2014-05-29 16:00 | 9 | 112 | 100 | 99 | -1 | 8001 | 8001 | 7920.99 | 7218.3467 | 0.99 | 1.0973 | FALSE | FALSE | FALSE | 14 | FALSE | 0 | Green | Continue normal monitoring.
147454 | HCMEPSSAV040 | SPS :Full Large Conference Room hardware & Wiring System | 26061 | 2014-05-20 08:00 | 2014-05-29 16:00 | 9 | 112 | 100 | 100 | 0 | 7416 | 7416 | 7416 | 6340.9108 | 1 | 1.1695 | FALSE | FALSE | FALSE | 14 | FALSE | 0 | Green | Continue normal monitoring.
147455 | HCMEPSSAV050 | SPS :Full Meduim Conference Room hardware & Wiring System | 26061 | 2014-05-20 08:00 | 2014-05-29 16:00 | 9 | 112 | 100 | 89 | -11 | 12951 | 12951 | 11526.39 | 11805.9412 | 0.89 | 0.97632 | FALSE | TRUE | TRUE | 14 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147456 | HCMEPSSAV060 | SPS :Connect to Mains | 26061 | 2014-05-31 08:00 | 2014-06-01 16:00 | 1 | 112 | 100 | 97 | -3 | 1388 | 1388 | 1346.36 | 1571.4139 | 0.97 | 0.85678 | TRUE | FALSE | FALSE | 14 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147457 | HCMEPSGN020 | SPS :Install Generator With All Fixtures | 26052 | 2014-03-24 12:00 | 2014-04-09 12:00 | 16 | 452 | 100 | 82 | -18 | 26880 | 26880 | 22041.6 | 25467.6019 | 0.82 | 0.86548 | TRUE | TRUE | TRUE | 56.5 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147458 | HCMEPSHV010 | SPS :Chillers Installation | 26053 | 2014-03-24 12:00 | 2014-05-22 12:00 | 59 | 164 | 100 | 92 | -8 | 68853 | 68853 | 63344.76 | 71430.9062 | 0.92 | 0.8868 | TRUE | FALSE | FALSE | 20.5 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147459 | HCMEPSHV020 | SPS :Boiler Installation On Boiler Room | 26053 | 2014-03-24 12:00 | 2014-04-09 12:00 | 16 | 212 | 100 | 90 | -10 | 18112 | 18112 | 16300.8 | 19679.0586 | 0.9 | 0.82833 | TRUE | FALSE | FALSE | 26.5 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147460 | HCMEPSHV030 | SPS :BMS & Automation Control System | 26053 | 2013-10-12 08:00 | 2013-10-14 16:00 | 2 | 1600 | 100 | 96 | -4 | 2152 | 2152 | 2065.92 | 2592.5926 | 0.96 | 0.79685 | TRUE | FALSE | FALSE | 200 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147461 | HCEXWCPW010 | EXT :Blinding & Protection to Water proofing | 25753 | 2013-10-28 08:00 | 2013-11-09 16:00 | 12 | 128 | 100 | 100 | 0 | 7632 | 7632 | 7632 | 9200.6968 | 1 | 0.8295 | TRUE | FALSE | FALSE | 16 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147462 | HCEXWERW020 | EXT :Compacted Base Coarse | 25752 | 2013-10-28 08:00 | 2013-11-13 16:00 | 16 | 160 | 100 | 100 | 0 | 14832 | 14832 | 14832 | 17031.4891 | 1 | 0.87086 | TRUE | FALSE | FALSE | 20 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147463 | HCEXWERW030 | EXT :SubGrade | 25752 | 2013-11-14 08:00 | 2013-11-30 16:00 | 16 | 160 | 100 | 100 | 0 | 31600 | 31600 | 31600 | 27304.3844 | 1 | 1.1573 | FALSE | FALSE | FALSE | 20 | FALSE | 0 | Green | Continue normal monitoring.
147464 | HCEXWERW040 | EXT :Asphalt Paving | 25752 | 2013-12-01 08:00 | 2013-12-17 16:00 | 16 | 160 | 100 | 92 | -8 | 17776 | 17776 | 16353.92 | 19198.5807 | 0.92 | 0.85183 | TRUE | FALSE | FALSE | 20 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147465 | HCEXWCPW020 | EXT :Foundation Works | 25753 | 2013-11-10 08:00 | 2013-11-26 16:00 | 16 | 128 | 100 | 85 | -15 | 22560 | 22560 | 19176 | 26274.1292 | 0.85 | 0.72984 | TRUE | TRUE | TRUE | 16 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147466 | HCEXWCPW030 | EXT :Walls & Stairs | 25753 | 2013-11-27 08:00 | 2013-12-14 16:00 | 17 | 128 | 100 | 96 | -4 | 22406 | 22406 | 21509.76 | 19200.0424 | 0.96 | 1.1203 | FALSE | FALSE | FALSE | 16 | FALSE | 0 | Green | Continue normal monitoring.
147467 | HCEXWCPW040 | EXT :Slab On Grade | 25753 | 2013-12-15 08:00 | 2013-12-22 16:00 | 7 | 128 | 100 | 100 | 0 | 4480 | 4480 | 4480 | 4793.0348 | 1 | 0.93469 | FALSE | FALSE | FALSE | 16 | FALSE | 0 | Green | Continue normal monitoring.
147468 | HCEXWSTN010 | EXT :Gabion walls cell | 25754 | 2013-12-23 08:00 | 2014-01-09 16:00 | 17 | 712 | 100 | 92 | -8 | 27302 | 27302 | 25117.84 | 32574.1707 | 0.92 | 0.7711 | TRUE | FALSE | FALSE | 89 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147469 | HCEXWSTN020 | EXT :Stone Cladding With Various finishes | 25754 | 2014-01-11 08:00 | 2014-01-27 16:00 | 16 | 712 | 100 | 98 | -2 | 10816 | 10816 | 10599.68 | 11244.7552 | 0.98 | 0.94263 | FALSE | FALSE | FALSE | 89 | FALSE | 0 | Green | Continue normal monitoring.
147470 | HCEXWSTN030 | EXT :Stone Copping With Various Finishes | 25754 | 2014-01-18 08:00 | 2014-02-02 16:00 | 15 | 712 | 100 | 100 | 0 | 10455 | 10455 | 10455 | 8903.9221 | 1 | 1.1742 | FALSE | FALSE | FALSE | 89 | FALSE | 0 | Green | Continue normal monitoring.
147471 | HCEXWSTN040 | EXT :Stone Screen & Seat Walls | 25754 | 2014-02-03 08:00 | 2014-02-18 16:00 | 15 | 712 | 100 | 98 | -2 | 16845 | 16845 | 16508.1 | 14392.458 | 0.98 | 1.147 | FALSE | FALSE | FALSE | 89 | FALSE | 0 | Green | Continue normal monitoring.
147472 | HCEXWSTN050 | EXT :Stone Flooring | 25754 | 2013-12-23 08:00 | 2014-01-09 16:00 | 17 | 128 | 100 | 89 | -11 | 20230 | 20230 | 18004.7 | 20566.9188 | 0.89 | 0.87542 | TRUE | TRUE | TRUE | 16 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147473 | HCEXWLDP010 | EXT :Curbstone | 25750 | 2013-12-23 08:00 | 2014-01-09 16:00 | 17 | 128 | 100 | 82 | -18 | 33048 | 33048 | 27099.36 | 30139.8906 | 0.82 | 0.89912 | TRUE | TRUE | TRUE | 16 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147474 | HCEXWLDP020 | EXT :Landscape | 25750 | 2014-01-11 08:00 | 2014-02-09 16:00 | 29 | 664 | 100 | 93 | -7 | 26100 | 26100 | 24273 | 29121.8649 | 0.93 | 0.8335 | TRUE | FALSE | FALSE | 83 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147475 | HCEXWLDP030 | EXT :Planters | 25750 | 2014-02-10 08:00 | 2014-02-25 16:00 | 15 | 664 | 100 | 100 | 0 | 14550 | 14550 | 14550 | 16492.7117 | 1 | 0.88221 | TRUE | FALSE | FALSE | 83 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147476 | HCEXWGRD010 | EXT :Guard House Construction Works | 25751 | 2013-11-27 08:00 | 2014-02-08 16:00 | 73 | 344 | 100 | 98 | -2 | 52341 | 52341 | 51294.18 | 48214.0125 | 0.98 | 1.0639 | FALSE | FALSE | FALSE | 43 | FALSE | 0 | Green | Continue normal monitoring.
147477 | HCEXWGRD020 | EXT :Guard House Finishing Works | 25751 | 2014-02-09 08:00 | 2014-04-01 16:00 | 51 | 344 | 100 | 84 | -16 | 72828 | 72828 | 61175.52 | 87787.8409 | 0.84 | 0.69686 | TRUE | TRUE | TRUE | 43 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147478 | HCEXWGRD030 | EXT :Guard House Interior MEP Works | 25751 | 2014-02-20 08:00 | 2014-04-13 16:00 | 52 | 344 | 100 | 100 | 0 | 58812 | 58812 | 58812 | 60385.9937 | 1 | 0.97393 | FALSE | FALSE | FALSE | 43 | FALSE | 0 | Green | Continue normal monitoring.
147479 | HCEXWWFP010 | EXT :Water Feature All Works | 25755 | 2013-12-23 08:00 | 2014-05-15 16:00 | 143 | 128 | 100 | 84 | -16 | 207350 | 207350 | 174174 | 188095.1396 | 0.84 | 0.92599 | FALSE | TRUE | TRUE | 16 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147480 | HCEXWMFN010 | EXT :Wood Decking | 25756 | 2013-12-23 08:00 | 2014-02-04 16:00 | 43 | 408 | 100 | 99 | -1 | 60415 | 60415 | 59810.85 | 69821.6541 | 0.99 | 0.85662 | TRUE | FALSE | FALSE | 51 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147481 | HCEXWMFN020 | EXT :Doors & Windows, Steel Security Gates | 25756 | 2014-02-05 08:00 | 2014-03-05 16:00 | 28 | 408 | 100 | 96 | -4 | 18872 | 18872 | 18117.12 | 22004.5595 | 0.96 | 0.82333 | TRUE | FALSE | FALSE | 51 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147482 | HCEXWMFN030 | EXT :Stainless Steel Bollards | 25756 | 2014-03-06 08:00 | 2014-04-03 16:00 | 28 | 408 | 100 | 100 | 0 | 14616 | 14616 | 14616 | 16161.1771 | 1 | 0.90439 | FALSE | FALSE | FALSE | 51 | FALSE | 0 | Green | Continue normal monitoring.
147483 | HCEXWMEP010 | EXT :Plumping, Piping All Sizes | 25757 | 2013-12-23 08:00 | 2013-12-29 16:00 | 6 | 968 | 100 | 89 | -11 | 4404 | 4404 | 3919.56 | 5246.8649 | 0.89 | 0.74703 | TRUE | TRUE | TRUE | 121 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147484 | HCEXWMEP020 | EXT :Fire Suppression piping & Hydrants | 25757 | 2013-12-23 08:00 | 2013-12-29 16:00 | 6 | 1048 | 100 | 84 | -16 | 9216 | 9216 | 7741.44 | 10551.8517 | 0.84 | 0.73366 | TRUE | TRUE | TRUE | 131 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147485 | HCEXWMEP030 | EXT :Manholes & Water Cabinet | 25757 | 2013-12-23 08:00 | 2014-01-11 16:00 | 19 | 1048 | 100 | 83 | -17 | 30856 | 30856 | 25610.48 | 37116.1361 | 0.83 | 0.69001 | TRUE | TRUE | TRUE | 131 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147486 | HCEXWMEP040 | EXT :Fuel Oil Piping & Valves | 25757 | 2013-12-23 08:00 | 2013-12-29 16:00 | 6 | 1048 | 100 | 85 | -15 | 8568 | 8568 | 7282.8 | 8769.8211 | 0.85 | 0.83044 | TRUE | TRUE | TRUE | 131 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147487 | HCEXWMEP050 | EXT :Irrigation System All Works | 25757 | 2013-12-23 08:00 | 2014-01-11 16:00 | 19 | 1048 | 100 | 100 | 0 | 19418 | 19418 | 19418 | 22312.0364 | 1 | 0.87029 | TRUE | FALSE | FALSE | 131 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147488 | HCFWB1Z4035 | B1 Z4 :Ceramic Wall Tiles | 26217 | 2013-12-08 08:00 | 2013-12-18 16:00 | 10 | 584 | 100 | 83 | -17 | 19750 | 19750 | 16392.5 | 24685.5374 | 0.83 | 0.66405 | TRUE | TRUE | TRUE | 73 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147489 | HCFWB1Z5034 | B1 Z5 :Ceramic Wall Tiles | 26186 | 2013-10-01 10:00 | 2013-10-13 10:00 | 12 | 1006 | 100 | 100 | 0 | 11160 | 11160 | 11160 | 12722.0929 | 1 | 0.87721 | TRUE | FALSE | FALSE | 125.75 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147490 | HCFWRFAZ010 | RF :Parapet Walls | 25843 | 2013-10-12 08:00 | 2013-10-27 16:00 | 15 | 992 | 100 | 86 | -14 | 19380 | 19380 | 16666.8 | 17358.1527 | 0.86 | 0.96017 | FALSE | TRUE | TRUE | 124 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147491 | HCFWRFAZ020 | RF :Plaster First layers for parapets | 25843 | 2013-10-28 08:00 | 2013-10-30 16:00 | 2 | 992 | 100 | 86 | -14 | 2064 | 2064 | 1775.04 | 2182.3239 | 0.86 | 0.81337 | TRUE | TRUE | TRUE | 124 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147492 | HCFWRFAZ030 | RF :Plaster Second Layer For parapets | 25843 | 2013-10-31 08:00 | 2013-11-03 16:00 | 3 | 992 | 100 | 97 | -3 | 4434 | 4434 | 4300.98 | 4810.62 | 0.97 | 0.89406 | TRUE | FALSE | FALSE | 124 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147493 | HCFWRFAZ040 | RF :Plaster Final Layer For parapets | 25843 | 2013-11-04 08:00 | 2013-11-07 16:00 | 3 | 992 | 100 | 82 | -18 | 5448 | 5448 | 4467.36 | 5010.4399 | 0.82 | 0.89161 | TRUE | TRUE | TRUE | 124 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147494 | HCFWRFAZ050 | RF :Stone Sills for parapets | 25843 | 2013-11-09 08:00 | 2013-11-11 16:00 | 2 | 992 | 100 | 80 | -20 | 2618 | 2618 | 2094.4 | 3233.6401 | 0.8 | 0.64769 | TRUE | TRUE | TRUE | 124 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147495 | HCFWRFAZ060 | RF :Foundation Base for Equipments on Roof | 25843 | 2013-11-12 08:00 | 2013-12-05 16:00 | 23 | 992 | 100 | 100 | 0 | 32476 | 32476 | 32476 | 29885.4515 | 1 | 1.0867 | FALSE | FALSE | FALSE | 124 | FALSE | 0 | Green | Continue normal monitoring.
147496 | HCFWRFAZ070 | RF :Water Proofing | 25843 | 2013-12-07 08:00 | 2013-12-09 16:00 | 2 | 992 | 100 | 100 | 0 | 3248 | 3248 | 3248 | 2991.4832 | 1 | 1.0857 | FALSE | FALSE | FALSE | 124 | FALSE | 0 | Green | Continue normal monitoring.
147497 | HCFWRFAZ080 | RF :Thermal Insulation | 25843 | 2013-12-10 08:00 | 2013-12-12 16:00 | 2 | 992 | 100 | 83 | -17 | 3654 | 3654 | 3032.82 | 4443.5083 | 0.83 | 0.68253 | TRUE | TRUE | TRUE | 124 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147498 | HCFWRFAZ090 | RF :Roof Flooring | 25843 | 2013-12-14 08:00 | 2013-12-18 16:00 | 4 | 992 | 100 | 85 | -15 | 5480 | 5480 | 4658 | 5677.7303 | 0.85 | 0.8204 | TRUE | TRUE | TRUE | 124 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147499 | HCMEPSSWW020 | SPS :Installation of Automated motorized sun screen shades | 26065 | 2013-12-19 08:00 | 2013-12-31 16:00 | 12 | 1112 | 100 | 88 | -12 | 12468 | 12468 | 10971.84 | 10912.9326 | 0.88 | 1.0054 | FALSE | TRUE | TRUE | 139 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147500 | HCMEPSHV040 | SPS :Automatic retractable and fixed bollards | 26053 | 2013-10-12 08:00 | 2013-10-14 16:00 | 2 | 1600 | 100 | 100 | 0 | 3046 | 3046 | 3046 | 3317.9316 | 1 | 0.91804 | FALSE | FALSE | FALSE | 200 | FALSE | 0 | Green | Continue normal monitoring.
147501 | HCFWGFZ4287 | GF Z4 :Trawelled smooth Concrete screed | 26318 | 2013-08-29 08:00 | 2013-09-07 16:00 | 9 | 1264 | 100 | 93 | -7 | 16902 | 16902 | 15718.86 | 18435.5276 | 0.93 | 0.85264 | TRUE | FALSE | FALSE | 158 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147502 | HCFWGFZ4297 | GF Z4 :Foam Concrete Under Floorings | 26318 | 2013-08-07 08:00 | 2013-08-28 16:00 | 21 | 1264 | 100 | 100 | 0 | 38346 | 38346 | 38346 | 33583.4384 | 1 | 1.1418 | FALSE | FALSE | FALSE | 158 | FALSE | 0 | Green | Continue normal monitoring.
147503 | HCFWGFZ4307 | GF Z4 :Rubber Flooring | 26318 | 2013-10-06 08:00 | 2013-10-21 16:00 | 15 | 1408 | 100 | 91 | -9 | 10890 | 10890 | 9909.9 | 13492.808 | 0.91 | 0.73446 | TRUE | FALSE | FALSE | 176 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147504 | HCFWGFZ4317 | GF Z4 :Rubber Skirting | 26318 | 2013-10-22 08:00 | 2013-10-23 16:00 | 1 | 1424 | 100 | 100 | 0 | 1759 | 1759 | 1759 | 1877.9295 | 1 | 0.93667 | FALSE | FALSE | FALSE | 178 | FALSE | 0 | Green | Continue normal monitoring.
147505 | HCFWGFZ4327 | GF Z4 :Block Works | 26319 | 2013-06-29 08:00 | 2013-07-09 16:00 | 10 | 1264 | 100 | 100 | 0 | 13720 | 13720 | 13720 | 14734.1589 | 1 | 0.93117 | FALSE | FALSE | FALSE | 158 | FALSE | 0 | Green | Continue normal monitoring.
147506 | HCFWGFZ4337 | GF Z4 :Plaster First Layer | 26319 | 2013-07-10 08:00 | 2013-07-18 16:00 | 8 | 1264 | 100 | 100 | 0 | 11128 | 11128 | 11128 | 11773.9377 | 1 | 0.94514 | FALSE | FALSE | FALSE | 158 | FALSE | 0 | Green | Continue normal monitoring.
147507 | HCFWGFZ4347 | GF Z4 :Plaster Final Layer | 26319 | 2013-07-29 08:00 | 2013-08-06 16:00 | 8 | 1264 | 100 | 99 | -1 | 15824 | 15824 | 15665.76 | 17316.0879 | 0.99 | 0.90469 | FALSE | FALSE | FALSE | 158 | FALSE | 0 | Green | Continue normal monitoring.
147508 | HCFWGFZ4357 | GF Z4 :Paint prime coat | 26319 | 2013-08-07 08:00 | 2013-08-24 16:00 | 17 | 1456 | 100 | 100 | 0 | 26112 | 26112 | 26112 | 24955.7581 | 1 | 1.0463 | FALSE | FALSE | FALSE | 182 | FALSE | 0 | Green | Continue normal monitoring.
147509 | HCFWGFZ4367 | GF Z4 :Paint putty coat | 26319 | 2013-08-25 08:00 | 2013-09-07 16:00 | 13 | 1456 | 100 | 100 | 0 | 9217 | 9217 | 9217 | 8893.4514 | 1 | 1.0364 | FALSE | FALSE | FALSE | 182 | FALSE | 0 | Green | Continue normal monitoring.
147510 | HCFWGFZ4377 | GF Z4 :Plaster Second Layer | 26319 | 2013-07-20 08:00 | 2013-07-28 16:00 | 8 | 1264 | 100 | 83 | -17 | 9920 | 9920 | 8233.6 | 10460.9935 | 0.83 | 0.78708 | TRUE | TRUE | TRUE | 158 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147511 | HCFWGFZ4387 | GF Z4 :Plaster First Layer | 26320 | 2013-09-08 08:00 | 2013-09-16 16:00 | 8 | 1264 | 100 | 100 | 0 | 7168 | 7168 | 7168 | 8405.7297 | 1 | 0.85275 | TRUE | FALSE | FALSE | 158 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147512 | HCFWGFZ4397 | GF Z4 :Plaster Final Layer | 26320 | 2013-09-26 08:00 | 2013-10-05 16:00 | 9 | 1264 | 100 | 100 | 0 | 14607 | 14607 | 14607 | 12707.2987 | 1 | 1.1495 | FALSE | FALSE | FALSE | 158 | FALSE | 0 | Green | Continue normal monitoring.
147513 | HCFWGFZ4407 | GF Z4 :Paint prime coat | 26320 | 2013-10-06 08:00 | 2013-10-21 16:00 | 15 | 1264 | 100 | 100 | 0 | 7950 | 7950 | 7950 | 8676.3254 | 1 | 0.91629 | FALSE | FALSE | FALSE | 158 | FALSE | 0 | Green | Continue normal monitoring.
147514 | HCFWGFZ4417 | GF Z4 :Paint putty coat | 26320 | 2013-11-09 08:00 | 2013-11-19 16:00 | 10 | 1312 | 100 | 91 | -9 | 13970 | 13970 | 12712.7 | 16382.7763 | 0.91 | 0.77598 | TRUE | FALSE | FALSE | 164 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147515 | HCFWGFZ4427 | GF Z4 :Gybsum Board Ceiling | 26320 | 2013-10-22 08:00 | 2013-11-07 16:00 | 16 | 1312 | 100 | 89 | -11 | 18368 | 18368 | 16347.52 | 16765.7026 | 0.89 | 0.97506 | FALSE | TRUE | TRUE | 164 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147516 | HCFWGFZ4437 | GF Z4 :Plaster Second Layer | 26320 | 2013-09-17 08:00 | 2013-09-25 16:00 | 8 | 1264 | 100 | 100 | 0 | 6624 | 6624 | 6624 | 5670.2037 | 1 | 1.1682 | FALSE | FALSE | FALSE | 158 | FALSE | 0 | Green | Continue normal monitoring.
147517 | HCFWGFZ4447 | GF Z4 :Steel Fire Rated Doors | 26321 | 2013-10-22 08:00 | 2013-11-02 16:00 | 11 | 1344 | 100 | 100 | 0 | 18579 | 18579 | 18579 | 18116.1101 | 1 | 1.0256 | FALSE | FALSE | FALSE | 168 | FALSE | 0 | Green | Continue normal monitoring.
147518 | HCFWGFZ4457 | GF Z4 :Steel Doors | 26321 | 2013-11-03 08:00 | 2013-11-14 16:00 | 11 | 1264 | 100 | 100 | 0 | 21802 | 21802 | 21802 | 23660.7836 | 1 | 0.92144 | FALSE | FALSE | FALSE | 158 | FALSE | 0 | Green | Continue normal monitoring.
147519 | HCFWGFZ4467 | GF Z4 :Wooden Doors | 26321 | 2013-11-03 08:00 | 2013-11-14 16:00 | 11 | 1264 | 100 | 86 | -14 | 15961 | 15961 | 13726.46 | 14449.7051 | 0.86 | 0.94995 | FALSE | TRUE | TRUE | 158 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147520 | HCFWGFZ4477 | GF Z4 :Metal Works | 26321 | 2013-10-22 08:00 | 2013-11-02 16:00 | 11 | 1264 | 100 | 82 | -18 | 17853 | 17853 | 14639.46 | 18218.0751 | 0.82 | 0.80357 | TRUE | TRUE | TRUE | 158 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147521 | HCFWGFZ4487 | GF Z4 :Handrails & Railling | 26321 | 2013-10-22 08:00 | 2013-11-09 16:00 | 18 | 1424 | 100 | 100 | 0 | 20160 | 20160 | 20160 | 21589.9206 | 1 | 0.93377 | FALSE | FALSE | FALSE | 178 | FALSE | 0 | Green | Continue normal monitoring.
147522 | HCFWGFZ4497 | GF Z4 :Epoxy Screed Finish | 26318 | 2013-09-08 08:00 | 2013-09-18 16:00 | 10 | 1696 | 100 | 100 | 0 | 16960 | 16960 | 16960 | 18478.8229 | 1 | 0.91781 | FALSE | FALSE | FALSE | 212 | FALSE | 0 | Green | Continue normal monitoring.
147523 | HCFWGFZ4507 | GF Z4 :Stone Flooring All types | 26318 | 2013-10-06 08:00 | 2013-10-23 16:00 | 17 | 1408 | 100 | 93 | -7 | 11237 | 11237 | 10450.41 | 10784.8758 | 0.93 | 0.96899 | FALSE | FALSE | FALSE | 176 | FALSE | 0 | Green | Continue normal monitoring.
147524 | HCFWGFZ4517 | GF Z4 :Aluminum & Stainless Steel Skirting | 26318 | 2013-10-22 08:00 | 2013-11-02 16:00 | 11 | 1424 | 100 | 100 | 0 | 14025 | 14025 | 14025 | 14165.4163 | 1 | 0.99009 | FALSE | FALSE | FALSE | 178 | FALSE | 0 | Green | Continue normal monitoring.
147525 | HCFWGFZ4527 | GF Z4 :Stainless steel Wire Cloth Finish For Elev Lobby | 26319 | 2013-08-25 08:00 | 2013-09-04 16:00 | 10 | 1792 | 100 | 89 | -11 | 17860 | 17860 | 15895.4 | 20741.4555 | 0.89 | 0.76636 | TRUE | TRUE | TRUE | 224 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147526 | HCFWGFZ4537 | GF Z4 :Stone Decoration For Benches | 26321 | 2013-10-22 08:00 | 2013-11-02 16:00 | 11 | 1424 | 100 | 95 | -5 | 8503 | 8503 | 8077.85 | 10428.8094 | 0.95 | 0.77457 | TRUE | FALSE | FALSE | 178 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147527 | HCFWGFZ4547 | GF Z4 :Mirror | 26321 | 2013-11-16 08:00 | 2013-11-26 16:00 | 10 | 1264 | 100 | 95 | -5 | 15260 | 15260 | 14497 | 18231.9175 | 0.95 | 0.79514 | TRUE | FALSE | FALSE | 158 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147528 | HCFWGFZ4557 | GF Z4 :Toilet & corian vanity tops | 26321 | 2013-11-16 08:00 | 2013-11-26 16:00 | 10 | 1264 | 100 | 100 | 0 | 15510 | 15510 | 15510 | 16684.3148 | 1 | 0.92962 | FALSE | FALSE | FALSE | 158 | FALSE | 0 | Green | Continue normal monitoring.
147529 | HCFWGFZ4567 | GF Z4 :Carpet Tile Flooring | 26318 | 2013-10-06 08:00 | 2013-10-21 16:00 | 15 | 1504 | 100 | 100 | 0 | 12375 | 12375 | 12375 | 12549.6994 | 1 | 0.98608 | FALSE | FALSE | FALSE | 188 | FALSE | 0 | Green | Continue normal monitoring.
147530 | HCFWGFZ4577 | GF Z4 :Acoustical Ceiling | 26320 | 2013-10-22 08:00 | 2013-11-02 16:00 | 11 | 1312 | 100 | 89 | -11 | 15829 | 15829 | 14087.81 | 15562.7981 | 0.89 | 0.90522 | FALSE | TRUE | TRUE | 164 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147531 | HCFWGFZ4587 | GF Z4 :Stone Base Skirting | 26318 | 2013-10-24 08:00 | 2013-11-04 16:00 | 11 | 1408 | 100 | 100 | 0 | 18392 | 18392 | 18392 | 16552.4805 | 1 | 1.1111 | FALSE | FALSE | FALSE | 176 | FALSE | 0 | Green | Continue normal monitoring.
147532 | HCFWGFZ4597 | GF Z4 :Glass Wall Cladding | 26319 | 2013-08-07 08:00 | 2013-08-28 16:00 | 21 | 1888 | 100 | 92 | -8 | 21819 | 21819 | 20073.48 | 19476.0867 | 0.92 | 1.0307 | FALSE | FALSE | FALSE | 236 | FALSE | 0 | Green | Continue normal monitoring.
147533 | HCFWGFZ4607 | GF Z4 :Gybsum Board Partitions | 26319 | 2013-06-29 08:00 | 2013-07-09 16:00 | 10 | 1264 | 100 | 85 | -15 | 9870 | 9870 | 8389.5 | 11107.1359 | 0.85 | 0.75533 | TRUE | TRUE | TRUE | 158 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147534 | HCFWGFZ4617 | GF Z4 :Stone Cladding | 26319 | 2013-08-07 08:00 | 2013-08-21 16:00 | 14 | 1888 | 100 | 91 | -9 | 18494 | 18494 | 16829.54 | 17641.7552 | 0.91 | 0.95396 | FALSE | FALSE | FALSE | 236 | FALSE | 0 | Green | Continue normal monitoring.
147535 | HCFWGFZ4627 | GF Z4 :Glass Doors | 26321 | 2013-10-22 08:00 | 2013-11-02 16:00 | 11 | 1424 | 100 | 88 | -12 | 21571 | 21571 | 18982.48 | 20532.6729 | 0.88 | 0.9245 | FALSE | TRUE | TRUE | 178 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147536 | HCFWGFZ1039 | GF Z1 :Reception Counter & Decoration | 26197 | 2014-01-22 08:00 | 2014-02-02 16:00 | 11 | 824 | 100 | 92 | -8 | 17468 | 17468 | 16070.56 | 21822.3885 | 0.92 | 0.73643 | TRUE | FALSE | FALSE | 103 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147537 | HCFWGFZ4637 | GF Z4 :Wooden Stage & Interior Decoration for Auditoruim | 26321 | 2013-11-16 08:00 | 2013-11-26 16:00 | 10 | 1264 | 100 | 83 | -17 | 8550 | 8550 | 7096.5 | 7910.2068 | 0.83 | 0.89713 | TRUE | TRUE | TRUE | 158 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147538 | HCFWGFZ4647 | GF Z4 :Wood Decking | 26321 | 2013-11-16 08:00 | 2013-11-26 16:00 | 10 | 1264 | 100 | 100 | 0 | 17750 | 17750 | 17750 | 16138.7243 | 1 | 1.0998 | FALSE | FALSE | FALSE | 158 | FALSE | 0 | Green | Continue normal monitoring.
147539 | HCFWGFZ4657 | GF Z4 :Block Boards | 26321 | 2013-11-16 08:00 | 2013-11-26 16:00 | 10 | 1264 | 100 | 90 | -10 | 7340 | 7340 | 6606 | 6528.7398 | 0.9 | 1.0118 | FALSE | FALSE | FALSE | 158 | FALSE | 0 | Green | Continue normal monitoring.
147540 | HCMEPSSCO010 | SPS :Electrical Cables & Motors | 26087 | 2013-08-22 08:00 | 2013-12-10 16:00 | 110 | 688 | 100 | 99 | -1 | 79860 | 79860 | 79061.4 | 86402.3019 | 0.99 | 0.91504 | FALSE | FALSE | FALSE | 86 | FALSE | 0 | Green | Continue normal monitoring.
147541 | HCMEPSSCO020 | SPS :Lifts Rooms Installation | 26087 | 2013-12-11 08:00 | 2014-01-06 16:00 | 26 | 688 | 100 | 97 | -3 | 47736 | 47736 | 46303.92 | 52564.283 | 0.97 | 0.8809 | TRUE | FALSE | FALSE | 86 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147542 | HCMEPSSCO030 | SPS :Final Fix & Fixtures | 26087 | 2014-01-07 08:00 | 2014-02-01 16:00 | 25 | 688 | 100 | 100 | 0 | 13700 | 13700 | 13700 | 13646.449 | 1 | 1.0039 | FALSE | FALSE | FALSE | 86 | FALSE | 0 | Green | Continue normal monitoring.
147543 | HCMEPSSCO040 | SPS :Calibration and commissioning | 26087 | 2014-02-02 08:00 | 2014-03-05 16:00 | 31 | 688 | 100 | 90 | -10 | 19127 | 19127 | 17214.3 | 20354.2903 | 0.9 | 0.84573 | TRUE | FALSE | TRUE | 86 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147544 | HEMSSME1180 | MS submission: Windows Washing Machine | 25832 | 2012-12-19 08:00 | 2013-02-11 16:00 | 54 | 608 | 100 | 100 | 0 | 29862 | 29862 | 29862 | 34799.9747 | 1 | 0.8581 | TRUE | FALSE | FALSE | 76 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147545 | HEMSAME1180 | MS approval: Windows Washing Machine | 25812 | 2013-02-12 08:00 | 2013-02-27 16:00 | 15 | 968 | 100 | 100 | 0 | 15960 | 15960 | 15960 | 18788.777 | 1 | 0.84944 | TRUE | FALSE | FALSE | 121 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147546 | HEPSAME1180 | Windows Washing Machine | 25719 | 2013-02-28 08:00 | 2013-12-16 16:00 | 291 | 968 | 100 | 83 | -17 | 455997 | 455997 | 378477.51 | 562319.4631 | 0.83 | 0.67306 | TRUE | TRUE | TRUE | 121 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147547 | HEMSSME1190 | MS submission: Parking Control Equipment | 25832 | 2013-02-12 08:00 | 2013-04-04 16:00 | 51 | 608 | 100 | 97 | -3 | 28152 | 28152 | 27307.44 | 33211.1169 | 0.97 | 0.82224 | TRUE | FALSE | FALSE | 76 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147548 | HEMSAME1190 | MS approval: Parking Control Equipment | 25812 | 2013-04-06 08:00 | 2013-04-21 16:00 | 15 | 608 | 100 | 80 | -20 | 15855 | 15855 | 12684 | 17058.9744 | 0.8 | 0.74354 | TRUE | TRUE | TRUE | 76 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147549 | HEPSAME1190 | Parking Control Equipment | 25719 | 2013-04-22 08:00 | 2014-02-10 16:00 | 294 | 608 | 100 | 100 | 0 | 477750 | 477750 | 477750 | 440419.9462 | 1 | 1.0848 | FALSE | FALSE | FALSE | 76 | FALSE | 0 | Green | Continue normal monitoring.
147550 | HEMSSME1200 | MS submission: Stand by Generator | 25832 | 2012-10-04 08:00 | 2012-11-12 16:00 | 39 | 1216 | 100 | 86 | -14 | 53313 | 53313 | 45849.18 | 47443.5278 | 0.86 | 0.96639 | FALSE | TRUE | TRUE | 152 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147551 | HEMSAME1200 | MS approval: Stand by Generator | 25812 | 2012-11-13 08:00 | 2012-11-29 16:00 | 16 | 1216 | 100 | 85 | -15 | 14352 | 14352 | 12199.2 | 12512.1419 | 0.85 | 0.97499 | FALSE | TRUE | TRUE | 152 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147552 | HEPSAME1200 | Stand by Generator | 25719 | 2012-12-01 08:00 | 2013-11-28 16:00 | 362 | 1216 | 100 | 100 | 0 | 601282 | 601282 | 601282 | 671397.6941 | 1 | 0.89557 | TRUE | FALSE | FALSE | 152 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147553 | HEMSSME1210 | MS submission: Chillers | 25832 | 2012-10-16 08:00 | 2012-12-30 16:00 | 75 | 608 | 100 | 94 | -6 | 88050 | 88050 | 82767 | 103283.9269 | 0.94 | 0.80135 | TRUE | FALSE | FALSE | 76 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147554 | HEMSAME1210 | MS approval: Chillers | 25812 | 2012-12-31 08:00 | 2013-01-16 16:00 | 16 | 608 | 100 | 97 | -3 | 14176 | 14176 | 13750.72 | 14934.0415 | 0.97 | 0.92076 | FALSE | FALSE | FALSE | 76 | FALSE | 0 | Green | Continue normal monitoring.
147555 | HEPSAME1210 | Chillers | 25719 | 2013-01-17 08:00 | 2014-01-18 16:00 | 366 | 608 | 100 | 100 | 0 | 223260 | 223260 | 223260 | 194657.1947 | 1 | 1.1469 | FALSE | FALSE | FALSE | 76 | FALSE | 0 | Green | Continue normal monitoring.
147556 | HEMSSME1220 | MS submission: Boiler | 25832 | 2012-12-31 08:00 | 2013-02-05 16:00 | 36 | 1056 | 100 | 90 | -10 | 40068 | 40068 | 36061.2 | 42639.894 | 0.9 | 0.84572 | TRUE | FALSE | FALSE | 132 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147557 | HEMSAME1220 | MS approval: Boilers | 25812 | 2013-02-06 08:00 | 2013-02-21 16:00 | 15 | 1056 | 100 | 99 | -1 | 7740 | 7740 | 7662.6 | 9476.0797 | 0.99 | 0.80863 | TRUE | FALSE | FALSE | 132 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147558 | HEPSAME1220 | Boiler | 25719 | 2013-02-23 08:00 | 2013-11-17 16:00 | 267 | 1056 | 100 | 100 | 0 | 455235 | 455235 | 455235 | 495771.5264 | 1 | 0.91824 | FALSE | FALSE | FALSE | 132 | FALSE | 0 | Green | Continue normal monitoring.
147559 | HCFWRFAZ100 | RF :Wood Decking | 25843 | 2013-12-19 08:00 | 2014-01-07 16:00 | 19 | 992 | 100 | 94 | -6 | 26277 | 26277 | 24700.38 | 30843.1804 | 0.94 | 0.80084 | TRUE | FALSE | FALSE | 124 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147560 | HCERDA000 | Receiving IFC drawings from consultant | 25721 | 2012-06-05 08:00 | 2012-06-30 16:00 | 25 | 192 | 100 | 95 | -5 | 26000 | 26000 | 24700 | 30421.5875 | 0.95 | 0.81192 | TRUE | FALSE | FALSE | 24 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147561 | HCERDA10 | Receiving load criteria + structural element forces from consultant | 25721 | 2012-06-05 08:00 | 2012-06-30 16:00 | 25 | 88 | 100 | 86 | -14 | 16750 | 16750 | 14405 | 20482.765 | 0.86 | 0.70327 | TRUE | TRUE | TRUE | 11 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147562 | HESDSCI0010 | SD submission: Reinforced Concrete Shopdrawings | 25806 | 2012-06-07 08:00 | 2012-11-10 16:00 | 156 | 616 | 100 | 100 | 0 | 141648 | 141648 | 141648 | 164041.3457 | 1 | 0.86349 | TRUE | FALSE | FALSE | 77 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147563 | HESDACI0010 | SD approval: Reinforced Concrete Shopdrawings | 25836 | 2012-06-25 08:00 | 2012-11-27 16:00 | 155 | 616 | 100 | 89 | -11 | 192045 | 192045 | 170920.05 | 220675.1081 | 0.89 | 0.77453 | TRUE | TRUE | TRUE | 77 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147564 | HEMSSCI0010 | MS submission: Steel Rebar | 25808 | 2012-06-05 08:00 | 2012-06-09 16:00 | 4 | 56 | 100 | 100 | 0 | 7604 | 7604 | 7604 | 7175.4467 | 1 | 1.0597 | FALSE | FALSE | FALSE | 7 | FALSE | 0 | Green | Continue normal monitoring.
147565 | HEMSSCI0020 | MS submission: water proofing Material | 25808 | 2012-06-05 08:00 | 2012-06-09 16:00 | 4 | 24 | 100 | 91 | -9 | 6844 | 6844 | 6228.04 | 5981.4511 | 0.91 | 1.0412 | FALSE | FALSE | FALSE | 3 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147566 | HEMSMCI0010 | MS approval: Steel Rebar | 25762 | 2012-06-10 08:00 | 2012-06-18 16:00 | 8 | 56 | 100 | 100 | 0 | 10856 | 10856 | 10856 | 11475.2239 | 1 | 0.94604 | FALSE | FALSE | FALSE | 7 | FALSE | 0 | Green | Continue normal monitoring.
147567 | HEMSMCI0020 | MS approval: Water proofing Materials | 25762 | 2012-06-10 08:00 | 2012-06-13 16:00 | 3 | 24 | 100 | 93 | -7 | 2187 | 2187 | 2033.91 | 1967.805 | 0.93 | 1.0336 | FALSE | FALSE | FALSE | 3 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147568 | HEMSSME1230 | MS submission: Mech 1st fix items | 25832 | 2012-06-20 08:00 | 2012-08-23 16:00 | 64 | 312 | 100 | 100 | 0 | 39552 | 39552 | 39552 | 48841.9085 | 1 | 0.8098 | TRUE | FALSE | FALSE | 39 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147569 | HEMSSME1240 | MS submission: Elec 1st fix items | 25832 | 2012-06-20 08:00 | 2012-08-23 16:00 | 64 | 312 | 100 | 84 | -16 | 107456 | 107456 | 90263.04 | 103799.2621 | 0.84 | 0.86959 | TRUE | TRUE | TRUE | 39 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147570 | HEMSAME1230 | MS approval: Mech 1st fix items | 25812 | 2012-07-07 08:00 | 2012-09-09 16:00 | 64 | 312 | 100 | 100 | 0 | 82112 | 82112 | 82112 | 97809.9818 | 1 | 0.83951 | TRUE | FALSE | FALSE | 39 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147571 | HEMSAME1240 | MS approval: Elec 1st fix items | 25812 | 2012-07-07 08:00 | 2012-09-09 16:00 | 64 | 312 | 100 | 100 | 0 | 61696 | 61696 | 61696 | 62007.5556 | 1 | 0.99498 | FALSE | FALSE | FALSE | 39 | FALSE | 0 | Green | Continue normal monitoring.
147572 | HCSWSSZ1005 | SS Z1 :Excavation Works - P2 | 25860 | 2012-07-30 08:00 | 2012-08-02 16:00 | 3 | 16 | 100 | 97 | -3 | 1809 | 1809 | 1754.73 | 1771.5134 | 0.97 | 0.99053 | FALSE | FALSE | FALSE | 2 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147573 | HCSWSSZ2005 | SS Z2 :Excavation Works - P2 | 25787 | 2012-07-22 08:00 | 2012-07-25 16:00 | 3 | 72 | 100 | 84 | -16 | 3591 | 3591 | 3016.44 | 4395.6118 | 0.84 | 0.68624 | TRUE | TRUE | TRUE | 9 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147574 | HCSWSSZ3005 | SS Z3 :Excavation Works - P2 | 25783 | 2012-08-04 08:00 | 2012-08-09 16:00 | 5 | 16 | 100 | 82 | -18 | 3370 | 3370 | 2763.4 | 3354.2588 | 0.82 | 0.82385 | TRUE | TRUE | TRUE | 2 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
147575 | HCSWSSZ4005 | SS Z4 :Excavation Works - P2 | 25766 | 2012-08-11 08:00 | 2012-08-16 16:00 | 5 | 142 | 100 | 100 | 0 | 6220 | 6220 | 6220 | 6258.0363 | 1 | 0.99392 | FALSE | FALSE | FALSE | 17.75 | FALSE | 0 | Green | Continue normal monitoring.
147576 | HCSWSSZ3015 | SS Z3 :Pour blinding under membrane - P2 | 25926 | 2012-08-07 08:00 | 2012-08-13 16:00 | 6 | 16 | 100 | 100 | 0 | 11664 | 11664 | 11664 | 10409.3818 | 1 | 1.1205 | FALSE | FALSE | FALSE | 2 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147577 | HCSWSSZ4040 | SS Z4 :Formwork and rebar for foundations | 25929 | 2012-08-22 08:00 | 2012-09-04 16:00 | 13 | 102 | 100 | 84 | -16 | 21541 | 21541 | 18094.44 | 24086.6866 | 0.84 | 0.75122 | TRUE | TRUE | TRUE | 12.75 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147578 | HCSWSSZ1380 | SS Z1 :Pour blinding under membrane | 26089 | 2012-08-04 08:00 | 2012-08-07 16:00 | 3 | 24 | 100 | 100 | 0 | 5742 | 5742 | 5742 | 5544.1064 | 1 | 1.0357 | FALSE | FALSE | FALSE | 3 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147579 | HCSWSSZ1390 | SS Z1 :Construct block works (formwork) | 26089 | 2012-08-08 08:00 | 2012-08-12 16:00 | 4 | 24 | 100 | 96 | -4 | 4656 | 4656 | 4469.76 | 5048.2292 | 0.96 | 0.88541 | TRUE | FALSE | FALSE | 3 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147580 | HCSWSSZ1400 | SS Z1 :Apply water Proofing and protection (inside) | 26089 | 2012-08-13 08:00 | 2012-08-15 16:00 | 2 | 24 | 100 | 98 | -2 | 1064 | 1064 | 1042.72 | 1156.0793 | 0.98 | 0.90195 | FALSE | FALSE | FALSE | 3 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147581 | HCSWSSZ1410 | SS Z1 :Formwork and rebar for foundations | 26089 | 2012-08-16 08:00 | 2012-08-23 16:00 | 7 | 24 | 100 | 98 | -2 | 3878 | 3878 | 3800.44 | 4411.9226 | 0.98 | 0.8614 | TRUE | FALSE | FALSE | 3 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147582 | HCSWSSZ1420 | SS Z1 :Cast concrete for foundations | 26089 | 2012-08-25 08:00 | 2012-08-25 16:00 | 1 | 24 | 100 | 100 | 0 | 1018 | 1018 | 1018 | 1168.7623 | 1 | 0.87101 | TRUE | FALSE | FALSE | 3 | TRUE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147583 | HCSWSSZ1430 | SS Z1 :De-shutter formwork | 26089 | 2012-08-26 08:00 | 2012-08-26 16:00 | 1 | 24 | 100 | 100 | 0 | 1255 | 1255 | 1255 | 1325.0051 | 1 | 0.94717 | FALSE | FALSE | FALSE | 3 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147584 | HCSWSSZ2440 | SS Z2 :Pour blinding under membrane | 26090 | 2012-07-26 08:00 | 2012-07-26 16:00 | 1 | 173 | 100 | 91 | -9 | 511 | 511 | 465.01 | 502.0048 | 0.91 | 0.92631 | FALSE | FALSE | FALSE | 21.625 | FALSE | 0 | Green | Continue normal monitoring.
147585 | HCSWSSZ2450 | SS Z2 :Construct block works (formwork) | 26090 | 2012-07-28 08:00 | 2012-08-04 16:00 | 7 | 173 | 100 | 100 | 0 | 8533 | 8533 | 8533 | 10111.4374 | 1 | 0.8439 | TRUE | FALSE | FALSE | 21.625 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147586 | HCSWSSZ2460 | SS Z2 :Apply water Proofing and protection (inside) | 26090 | 2012-08-05 08:00 | 2012-08-08 16:00 | 3 | 173 | 100 | 100 | 0 | 3162 | 3162 | 3162 | 3079.6181 | 1 | 1.0268 | FALSE | FALSE | FALSE | 21.625 | FALSE | 0 | Green | Continue normal monitoring.
147587 | HCSWSSZ2470 | SS Z2 :Formwork and rebar for foundations | 26090 | 2012-08-09 08:00 | 2012-08-14 16:00 | 5 | 173 | 100 | 88 | -12 | 4360 | 4360 | 3836.8 | 4591.0959 | 0.88 | 0.8357 | TRUE | TRUE | TRUE | 21.625 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147588 | HCSWSSZ2480 | SS Z2 :Cast concrete for foundations | 26090 | 2012-08-15 08:00 | 2012-08-15 16:00 | 1 | 173 | 100 | 80 | -20 | 983 | 983 | 786.4 | 993.3225 | 0.8 | 0.79169 | TRUE | TRUE | TRUE | 21.625 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147589 | HCSWSSZ2490 | SS Z2 :De-shutter formwork | 26090 | 2012-08-16 08:00 | 2012-08-16 16:00 | 1 | 173 | 100 | 97 | -3 | 1472 | 1472 | 1427.84 | 1754.6702 | 0.97 | 0.81374 | TRUE | FALSE | FALSE | 21.625 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147590 | HCSWSSZ4500 | SS Z4 :Pour blinding under membrane | 26086 | 2012-08-14 08:00 | 2012-08-22 16:00 | 8 | 142 | 100 | 100 | 0 | 14008 | 14008 | 14008 | 14326.9259 | 1 | 0.97774 | FALSE | FALSE | FALSE | 17.75 | FALSE | 0 | Green | Continue normal monitoring.
147591 | HCSWSSZ4510 | SS Z4 :Construct block works (formwork) | 26086 | 2012-08-23 08:00 | 2012-08-29 16:00 | 6 | 142 | 100 | 83 | -17 | 6732 | 6732 | 5587.56 | 6761.8879 | 0.83 | 0.82633 | TRUE | TRUE | TRUE | 17.75 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147592 | HCSWSSZ4520 | SS Z4 :Apply water Proofing and protection (inside) | 26086 | 2012-08-26 08:00 | 2012-09-02 16:00 | 7 | 142 | 100 | 100 | 0 | 5642 | 5642 | 5642 | 6352.4941 | 1 | 0.88816 | TRUE | FALSE | FALSE | 17.75 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147593 | HCSWSSZ4530 | SS Z4 :Cast concrete for foundations | 26086 | 2012-08-28 08:00 | 2012-09-04 16:00 | 7 | 142 | 100 | 89 | -11 | 6692 | 6692 | 5955.88 | 7300.8144 | 0.89 | 0.81578 | TRUE | TRUE | TRUE | 17.75 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147594 | HCSWSSZ4540 | SS Z4 :De-shutter formwork | 26086 | 2012-08-29 08:00 | 2012-09-05 16:00 | 7 | 142 | 100 | 100 | 0 | 4613 | 4613 | 4613 | 4118.9419 | 1 | 1.1199 | FALSE | FALSE | FALSE | 17.75 | FALSE | 0 | Green | Continue normal monitoring.
147595 | HCSWSSZ4550 | SS Z4 :Formwork and rebar for foundations | 26086 | 2012-08-27 08:00 | 2012-09-03 16:00 | 7 | 142 | 100 | 86 | -14 | 5810 | 5810 | 4996.6 | 6119.4843 | 0.86 | 0.81651 | TRUE | TRUE | TRUE | 17.75 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147596 | HEMSSCI0030 | MS submission: Wire Mesh | 25808 | 2012-06-10 08:00 | 2012-06-24 16:00 | 14 | 168 | 100 | 100 | 0 | 17850 | 17850 | 17850 | 20423.8157 | 1 | 0.87398 | TRUE | FALSE | FALSE | 21 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147597 | HEMSMCI0030 | MS approval: Wire Mesh | 25762 | 2012-06-25 08:00 | 2012-06-28 16:00 | 3 | 416 | 100 | 100 | 0 | 2172 | 2172 | 2172 | 2708.1146 | 1 | 0.80203 | TRUE | FALSE | FALSE | 52 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147598 | HEMSSCI0040 | MS submission: Formwork System | 25808 | 2012-06-25 08:00 | 2012-07-17 16:00 | 22 | 168 | 100 | 80 | -20 | 32604 | 32604 | 26083.2 | 35918.4813 | 0.8 | 0.72618 | TRUE | TRUE | TRUE | 21 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147599 | HEMSMCI0040 | MS approval: Formwork system | 25762 | 2012-07-02 08:00 | 2012-07-24 16:00 | 22 | 168 | 100 | 96 | -4 | 27016 | 27016 | 25935.36 | 26965.135 | 0.96 | 0.96181 | FALSE | FALSE | FALSE | 21 | FALSE | 0 | Green | Continue normal monitoring.
147600 | HCSWB4Z1340 | B4 Z1 :Fix Steel Rebar for columns | 26077 | 2012-08-26 08:00 | 2012-08-26 16:00 | 1 | 72 | 100 | 100 | 0 | 1979 | 1979 | 1979 | 1861.1716 | 1 | 1.0633 | FALSE | FALSE | FALSE | 9 | FALSE | 0 | Green | Continue normal monitoring.
147601 | HCSWB4Z1350 | B4 Z1 :Erect columns formwork | 26077 | 2012-08-27 08:00 | 2012-08-27 16:00 | 1 | 72 | 100 | 100 | 0 | 1568 | 1568 | 1568 | 1880.2391 | 1 | 0.83394 | TRUE | FALSE | FALSE | 9 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147602 | HCSWB4Z1360 | B4 Z1 :Cast concrete for columns | 26077 | 2012-08-28 08:00 | 2012-08-28 16:00 | 1 | 72 | 100 | 100 | 0 | 1737 | 1737 | 1737 | 2042.4099 | 1 | 0.85047 | TRUE | FALSE | FALSE | 9 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147603 | HCSWB4Z1370 | B4 Z1 :De-shutter columns formwork | 26077 | 2012-08-29 08:00 | 2012-08-29 16:00 | 1 | 72 | 100 | 81 | -19 | 1582 | 1582 | 1281.42 | 1492.7264 | 0.81 | 0.85844 | TRUE | TRUE | TRUE | 9 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147604 | HCSWB4Z2380 | B4 Z2 :Fix Steel Rebar for columns | 26078 | 2012-08-16 08:00 | 2012-08-16 16:00 | 1 | 229 | 100 | 100 | 0 | 1143 | 1143 | 1143 | 1063.279 | 1 | 1.075 | FALSE | FALSE | FALSE | 28.625 | FALSE | 0 | Green | Continue normal monitoring.
147605 | HCSWB4Z2390 | B4 Z2 :Erect columns formwork | 26078 | 2012-08-22 08:00 | 2012-08-22 16:00 | 1 | 229 | 100 | 100 | 0 | 1115 | 1115 | 1115 | 1266.701 | 1 | 0.88024 | TRUE | FALSE | FALSE | 28.625 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147606 | HCSWB4Z2400 | B4 Z2 :Cast concrete for columns | 26078 | 2012-08-23 08:00 | 2012-08-23 16:00 | 1 | 229 | 100 | 90 | -10 | 694 | 694 | 624.6 | 677.3307 | 0.9 | 0.92215 | FALSE | FALSE | FALSE | 28.625 | FALSE | 0 | Green | Continue normal monitoring.
147607 | HCSWB4Z2410 | B4 Z2 :De-shutter columns formwork | 26078 | 2012-08-25 08:00 | 2012-08-25 16:00 | 1 | 229 | 100 | 88 | -12 | 988 | 988 | 869.44 | 960.8888 | 0.88 | 0.90483 | FALSE | TRUE | TRUE | 28.625 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147608 | HCSWB4Z4420 | B4 Z4 :Fix Steel Rebar for columns | 26079 | 2012-09-05 08:00 | 2012-09-05 16:00 | 1 | 222 | 100 | 86 | -14 | 656 | 656 | 564.16 | 597.561 | 0.86 | 0.9441 | FALSE | TRUE | TRUE | 27.75 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147609 | HCSWB4Z4430 | B4 Z4 :Erect columns formwork | 26079 | 2012-09-06 08:00 | 2012-09-06 16:00 | 1 | 222 | 100 | 100 | 0 | 1109 | 1109 | 1109 | 1059.7495 | 1 | 1.0465 | FALSE | FALSE | FALSE | 27.75 | FALSE | 0 | Green | Continue normal monitoring.
147610 | HCSWB4Z4440 | B4 Z4 :Cast concrete for columns | 26079 | 2012-09-08 08:00 | 2012-09-08 16:00 | 1 | 222 | 100 | 96 | -4 | 1749 | 1749 | 1679.04 | 1785.7343 | 0.96 | 0.94025 | FALSE | FALSE | FALSE | 27.75 | FALSE | 0 | Green | Continue normal monitoring.
147611 | HCSWB4Z4450 | B4 Z4 :De-shutter columns formwork | 26079 | 2012-09-09 08:00 | 2012-09-09 16:00 | 1 | 222 | 100 | 96 | -4 | 911 | 911 | 874.56 | 1041.3963 | 0.96 | 0.8398 | TRUE | FALSE | FALSE | 27.75 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147612 | HEMSSSS0020 | Design Submittal | 25767 | 2012-07-04 08:00 | 2012-07-28 16:00 | 24 | 64 | 100 | 81 | -19 | 41472 | 41472 | 33592.32 | 40830.1477 | 0.81 | 0.82273 | TRUE | TRUE | TRUE | 8 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147613 | HEMSASS0020 | Approval: Design | 25779 | 2012-07-29 08:00 | 2012-08-13 16:00 | 15 | 64 | 100 | 85 | -15 | 24030 | 24030 | 20425.5 | 23584.0449 | 0.85 | 0.86607 | TRUE | TRUE | TRUE | 8 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147614 | HEMSSAL0080 | MS submission: Design | 25764 | 2012-07-04 08:00 | 2012-08-29 16:00 | 56 | 408 | 100 | 93 | -7 | 92232 | 92232 | 85775.76 | 88908.4476 | 0.93 | 0.96477 | FALSE | FALSE | FALSE | 51 | FALSE | 0 | Green | Continue normal monitoring.
147615 | HEMSAAL0080 | MS approval: Design | 25817 | 2012-08-30 08:00 | 2012-09-15 16:00 | 16 | 408 | 100 | 85 | -15 | 15520 | 15520 | 13192 | 16161.185 | 0.85 | 0.81628 | TRUE | TRUE | TRUE | 51 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147616 | HCSWSSZ6255 | SS Z6 :Cut and Fill (Cyclopean) | 25776 | 2012-09-03 08:00 | 2012-09-18 16:00 | 15 | 200 | 100 | 81 | -19 | 26115 | 26115 | 21153.15 | 24084.6809 | 0.81 | 0.87828 | TRUE | TRUE | TRUE | 25 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147617 | HCSWSSZ1225 | SS Z1 :Fill imported base course around Foundations P2 & under SOG | 25879 | 2012-08-22 08:00 | 2012-08-26 16:00 | 4 | 24 | 100 | 80 | -20 | 4060 | 4060 | 3248 | 4239.6643 | 0.8 | 0.7661 | TRUE | TRUE | TRUE | 3 | TRUE | 5 | Red | Executive escalation required. Immediate recovery actions and management review needed.
147618 | HCSWSSZ2225 | SS Z2 :Fill imported base course around Foundations P2 & under SOG | 25908 | 2012-08-14 08:00 | 2012-08-22 16:00 | 8 | 173 | 100 | 89 | -11 | 13016 | 13016 | 11584.24 | 14729.8196 | 0.89 | 0.78645 | TRUE | TRUE | TRUE | 21.625 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147619 | HCSWSSZ3225 | SS Z3 :Fill imported base course under SOG | 25927 | 2012-09-03 08:00 | 2012-09-05 16:00 | 2 | 16 | 100 | 100 | 0 | 1784 | 1784 | 1784 | 1537.6585 | 1 | 1.1602 | FALSE | FALSE | FALSE | 2 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147620 | HCSWSSZ4225 | SS Z4 :Fill imported base course around Foundations P2 & under SOG | 25930 | 2012-09-10 08:00 | 2012-09-13 16:00 | 3 | 102 | 100 | 84 | -16 | 3390 | 3390 | 2847.6 | 2894.7608 | 0.84 | 0.98371 | FALSE | TRUE | TRUE | 12.75 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147621 | HCSWSSZ5225 | SS Z5 :Fill imported base course under SOG | 26042 | 2012-09-17 08:00 | 2012-09-19 16:00 | 2 | 8 | 100 | 81 | -19 | 2214 | 2214 | 1793.34 | 1948.4288 | 0.81 | 0.9204 | FALSE | TRUE | TRUE | 1 | TRUE | 4 | Orange | Develop recovery plan and review schedule and cost exposure.
147622 | HCSWSSZ6325 | SS Z6 :Fill imported base course under SOG | 25994 | 2012-10-09 08:00 | 2012-10-13 16:00 | 4 | 16 | 100 | 100 | 0 | 5916 | 5916 | 5916 | 6296.186 | 1 | 0.93962 | FALSE | FALSE | FALSE | 2 | TRUE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147623 | HCSWB4Z6340 | B4 Z6 :Formwork Ramp walls shutters - 1st side | 26080 | 2012-10-11 08:00 | 2012-10-14 16:00 | 3 | 56 | 100 | 95 | -5 | 2799 | 2799 | 2659.05 | 3335.7979 | 0.95 | 0.79713 | TRUE | FALSE | FALSE | 7 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147624 | HCSWB4Z6350 | B4 Z6 :Fix steel rebar for Ramp walls | 26080 | 2012-10-11 08:00 | 2012-10-14 16:00 | 3 | 56 | 100 | 100 | 0 | 5562 | 5562 | 5562 | 4738.567 | 1 | 1.1738 | FALSE | FALSE | FALSE | 7 | FALSE | 0 | Green | Continue normal monitoring.
147625 | HCSWB4Z6370 | B4 Z6 :Close shutter for Ramp walls | 26080 | 2012-10-14 08:00 | 2012-10-16 16:00 | 2 | 56 | 100 | 81 | -19 | 3332 | 3332 | 2698.92 | 4080.5822 | 0.81 | 0.66141 | TRUE | TRUE | TRUE | 7 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147626 | HCSWB4Z6380 | B4 Z6 :Cast concrete for Ramp walls | 26080 | 2012-10-15 08:00 | 2012-10-17 16:00 | 2 | 56 | 100 | 89 | -11 | 2078 | 2078 | 1849.42 | 1854.6387 | 0.89 | 0.99719 | FALSE | TRUE | TRUE | 7 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147627 | HCSWB4Z6390 | B4 Z6 :De-shutter Ramp walls | 26080 | 2012-10-16 08:00 | 2012-10-18 16:00 | 2 | 56 | 100 | 81 | -19 | 1554 | 1554 | 1258.74 | 1844.277 | 0.81 | 0.68251 | TRUE | TRUE | TRUE | 7 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147628 | HCSWB1RA000 | Erect ramb's slab formwork and proping | 25759 | 2012-12-22 08:00 | 2013-01-05 16:00 | 14 | 288 | 100 | 95 | -5 | 10248 | 10248 | 9735.6 | 10690.1183 | 0.95 | 0.91071 | FALSE | FALSE | FALSE | 36 | FALSE | 0 | Green | Continue normal monitoring.
147629 | HCSWB1RA010 | Fix steel rebar for ramp | 25759 | 2012-12-27 08:00 | 2013-01-10 16:00 | 14 | 288 | 100 | 95 | -5 | 22582 | 22582 | 21452.9 | 25150.5434 | 0.95 | 0.85298 | TRUE | FALSE | FALSE | 36 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147630 | HCSWB1RA020 | Fix MEP first Fix for Ramp | 25759 | 2013-01-12 08:00 | 2013-01-13 16:00 | 1 | 288 | 100 | 98 | -2 | 1722 | 1722 | 1687.56 | 1815.4584 | 0.98 | 0.92955 | FALSE | FALSE | FALSE | 36 | FALSE | 0 | Green | Continue normal monitoring.
147631 | HCSWB1RA030 | Fix side shutters and casting guides for Ramp | 25759 | 2013-01-14 08:00 | 2013-01-15 16:00 | 1 | 288 | 100 | 100 | 0 | 861 | 861 | 861 | 896.1454 | 1 | 0.96078 | FALSE | FALSE | FALSE | 36 | FALSE | 0 | Green | Continue normal monitoring.
147632 | HCSWB1RA040 | Cast concrete for Ramp | 25759 | 2013-01-16 08:00 | 2013-01-16 16:00 | 1 | 288 | 100 | 86 | -14 | 1964 | 1964 | 1689.04 | 2325.297 | 0.86 | 0.72638 | TRUE | TRUE | TRUE | 36 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147633 | HCSWB1RA050 | Cure and De-shutter Ramp formwork | 25759 | 2013-01-17 08:00 | 2013-02-03 16:00 | 17 | 288 | 100 | 100 | 0 | 8925 | 8925 | 8925 | 10284.7644 | 1 | 0.86779 | TRUE | FALSE | FALSE | 36 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147634 | HCSWSSZ6380 | SS Z6E :Pour blinding under membrane | 26083 | 2013-01-22 08:00 | 2013-02-07 16:00 | 16 | 128 | 100 | 91 | -9 | 24768 | 24768 | 22538.88 | 25841.9626 | 0.91 | 0.87218 | TRUE | FALSE | FALSE | 16 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147635 | HCSWSSZ6390 | SS Z6E :Construct block works (formwork) | 26083 | 2013-01-23 08:00 | 2013-02-09 16:00 | 17 | 128 | 100 | 100 | 0 | 32589 | 32589 | 32589 | 29155.8913 | 1 | 1.1178 | FALSE | FALSE | FALSE | 16 | FALSE | 0 | Green | Continue normal monitoring.
147636 | HCSWSSZ6400 | SS Z6E :Apply water Proofing and protection (inside) | 26083 | 2013-01-26 08:00 | 2013-02-10 16:00 | 15 | 128 | 100 | 94 | -6 | 15090 | 15090 | 14184.6 | 13523.0723 | 0.94 | 1.0489 | FALSE | FALSE | FALSE | 16 | FALSE | 0 | Green | Continue normal monitoring.
147637 | HCSWSSZ6410 | SS Z6E :Formwork and rebar for foundations | 26083 | 2013-01-28 08:00 | 2013-02-12 16:00 | 15 | 128 | 100 | 87 | -13 | 27360 | 27360 | 23803.2 | 32028.0479 | 0.87 | 0.7432 | TRUE | TRUE | TRUE | 16 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147638 | HCSWSSZ6420 | SS Z6E :Cast concrete for foundations | 26083 | 2013-02-03 08:00 | 2013-02-18 16:00 | 15 | 128 | 100 | 85 | -15 | 27930 | 27930 | 23740.5 | 29654.852 | 0.85 | 0.80056 | TRUE | TRUE | TRUE | 16 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147639 | HCSWSSZ6430 | SS Z6E :De-shutter formwork | 26083 | 2013-02-04 08:00 | 2013-02-19 16:00 | 15 | 128 | 100 | 100 | 0 | 11490 | 11490 | 11490 | 11979.8837 | 1 | 0.95911 | FALSE | FALSE | FALSE | 16 | FALSE | 0 | Green | Continue normal monitoring.
147640 | HCSWB2Z6400 | B2 Z6 :B2 Z6E :Formwork retaining walls shutters - 1st side | 26084 | 2013-02-19 08:00 | 2013-02-27 16:00 | 8 | 136 | 100 | 100 | 0 | 7680 | 7680 | 7680 | 8618.7013 | 1 | 0.89109 | TRUE | FALSE | FALSE | 17 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147641 | HCSWB2Z6410 | B2 Z6 :B2 Z6E :Fix steel rebar for reatining walls | 26084 | 2013-02-19 08:00 | 2013-02-27 16:00 | 8 | 136 | 100 | 89 | -11 | 7640 | 7640 | 6799.6 | 9118.6199 | 0.89 | 0.74568 | TRUE | TRUE | TRUE | 17 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147642 | HCSWB2Z6420 | B2 Z6 :B2 Z6E :Fix MEP first fix in walls | 26084 | 2013-02-20 08:00 | 2013-02-28 16:00 | 8 | 136 | 100 | 82 | -18 | 15064 | 15064 | 12352.48 | 16593.738 | 0.82 | 0.74441 | TRUE | TRUE | TRUE | 17 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147643 | HCSWB2Z6430 | B2 Z6 :B2 Z6E :Close shutter for retaining walls | 26084 | 2013-02-21 08:00 | 2013-03-02 16:00 | 9 | 136 | 100 | 98 | -2 | 14319 | 14319 | 14032.62 | 16540.4376 | 0.98 | 0.84838 | TRUE | FALSE | FALSE | 17 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147644 | HCSWB2Z6440 | B2 Z6 :B2 Z6E :Cast concrete for retaining walls | 26084 | 2013-02-23 08:00 | 2013-03-03 16:00 | 8 | 136 | 100 | 100 | 0 | 12048 | 12048 | 12048 | 13928.7917 | 1 | 0.86497 | TRUE | FALSE | FALSE | 17 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147645 | HCSWB2Z6450 | B2 Z6 :B2 Z6E :De-shutter retaining walls | 26084 | 2013-02-24 08:00 | 2013-03-04 16:00 | 8 | 136 | 100 | 96 | -4 | 10896 | 10896 | 10460.16 | 10814.3299 | 0.96 | 0.96725 | FALSE | FALSE | FALSE | 17 | FALSE | 0 | Green | Continue normal monitoring.
147646 | HCSWB2Z6460 | B2 Z6 :B2 Z6E :Apply water proofing membrane behind Basement Walls | 26084 | 2013-03-02 08:00 | 2013-03-10 16:00 | 8 | 136 | 100 | 86 | -14 | 15480 | 15480 | 13312.8 | 14855.1231 | 0.86 | 0.89618 | TRUE | TRUE | TRUE | 17 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147647 | HCSWB2Z6470 | B2 Z6 :B2 Z6E :Apply Protection for Basement Walls | 26084 | 2013-03-04 08:00 | 2013-03-12 16:00 | 8 | 136 | 100 | 100 | 0 | 7920 | 7920 | 7920 | 9270.0878 | 1 | 0.85436 | TRUE | FALSE | FALSE | 17 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147648 | HCSWSSZ6440 | SS Z6E :Fill imported base course around Foundations & under SOG | 26085 | 2013-02-21 08:00 | 2013-02-25 16:00 | 4 | 128 | 100 | 99 | -1 | 6288 | 6288 | 6225.12 | 6293.4801 | 0.99 | 0.98914 | FALSE | FALSE | FALSE | 16 | FALSE | 0 | Green | Continue normal monitoring.
147649 | HCSWSSZ6450 | SS Z6E :Lay polythene sheets under SOG | 26085 | 2013-02-26 08:00 | 2013-02-26 16:00 | 1 | 128 | 100 | 100 | 0 | 1063 | 1063 | 1063 | 1287.6485 | 1 | 0.82554 | TRUE | FALSE | FALSE | 16 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147650 | HCSWSSZ6460 | SS Z6E :Formwork and Erect steel for SOG | 26085 | 2013-02-27 08:00 | 2013-03-03 16:00 | 4 | 128 | 100 | 100 | 0 | 6500 | 6500 | 6500 | 5706.1958 | 1 | 1.1391 | FALSE | FALSE | FALSE | 16 | FALSE | 0 | Green | Continue normal monitoring.
147651 | HCSWSSZ6470 | SS Z6E :Cast Concrete for SOG | 26085 | 2013-03-04 08:00 | 2013-03-04 16:00 | 1 | 128 | 100 | 83 | -17 | 715 | 715 | 593.45 | 624.4002 | 0.83 | 0.95043 | FALSE | TRUE | TRUE | 16 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147652 | HCSWSSZ6480 | SS Z6 :Cut and Fill (Cyclopean) | 25857 | 2013-01-06 08:00 | 2013-01-21 16:00 | 15 | 128 | 100 | 93 | -7 | 29415 | 29415 | 27355.95 | 35909.8809 | 0.93 | 0.76179 | TRUE | FALSE | FALSE | 16 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147653 | HEMSSAL0090 | MS submission: Aluminum Doors | 25764 | 2012-07-04 08:00 | 2012-07-21 16:00 | 17 | 3776 | 100 | 99 | -1 | 17986 | 17986 | 17806.14 | 19953.344 | 0.99 | 0.89239 | TRUE | FALSE | FALSE | 472 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147654 | HEMSAAL0090 | MS Approvals: Aluminum Doors | 25817 | 2012-07-22 08:00 | 2012-08-06 16:00 | 15 | 3776 | 100 | 100 | 0 | 9870 | 9870 | 9870 | 9888.1583 | 1 | 0.99816 | FALSE | FALSE | FALSE | 472 | FALSE | 0 | Green | Continue normal monitoring.
147655 | HEPSAAL0080 | Aluminum Doors | 25718 | 2012-08-07 08:00 | 2012-10-20 16:00 | 74 | 3776 | 100 | 94 | -6 | 73112 | 73112 | 68725.28 | 84226.7908 | 0.94 | 0.81596 | TRUE | FALSE | FALSE | 472 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147656 | HCFWGFZ1049 | GF Z1: Aluminum Doors | 26197 | 2012-10-21 08:00 | 2012-11-10 16:00 | 20 | 3776 | 100 | 100 | 0 | 23700 | 23700 | 23700 | 26518.6582 | 1 | 0.89371 | TRUE | FALSE | FALSE | 472 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147657 | HCFWGFZ1037 | GF Z1: Ceramic Floor Tiles | 26380 | 2013-12-17 08:00 | 2013-12-29 16:00 | 12 | 1048 | 100 | 87 | -13 | 21180 | 21180 | 18426.6 | 22503.3353 | 0.87 | 0.81884 | TRUE | TRUE | TRUE | 131 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147658 | HCFWGFZ3688 | GF Z3: Ceramic Floor Tiles | 26203 | 2013-12-17 08:00 | 2013-12-29 16:00 | 12 | 1048 | 100 | 100 | 0 | 15516 | 15516 | 15516 | 13802.2475 | 1 | 1.1242 | FALSE | FALSE | FALSE | 131 | FALSE | 0 | Green | Continue normal monitoring.
147659 | HCFWGFZ4698 | GF Z4: Ceramic Floor Tiles | 26318 | 2013-12-17 08:00 | 2013-12-29 16:00 | 12 | 1048 | 100 | 94 | -6 | 6048 | 6048 | 5685.12 | 7105.6249 | 0.94 | 0.80009 | TRUE | FALSE | FALSE | 131 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147660 | HCFWF1Z4708 | F1 Z1: Ceramic Floor Tiles | 26208 | 2013-12-17 08:00 | 2013-12-29 16:00 | 12 | 1048 | 100 | 100 | 0 | 10320 | 10320 | 10320 | 12346.9437 | 1 | 0.83583 | TRUE | FALSE | FALSE | 131 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147661 | HCFWGFZ4718 | F1 Z3: Ceramic Floor Tiles | 26150 | 2013-12-17 08:00 | 2013-12-29 16:00 | 12 | 1048 | 100 | 99 | -1 | 11496 | 11496 | 11381.04 | 10563.3005 | 0.99 | 1.0774 | FALSE | FALSE | FALSE | 131 | FALSE | 0 | Green | Continue normal monitoring.
147662 | HCFWF2Z1728 | F2 Z1Ceramic Floor Tiles | 26224 | 2013-12-17 08:00 | 2013-12-29 16:00 | 12 | 1048 | 100 | 100 | 0 | 8964 | 8964 | 8964 | 10668.9946 | 1 | 0.84019 | TRUE | FALSE | FALSE | 131 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147663 | HCFWF2Z1738 | F2 Z3 :Ceramic Floor Tiles | 26383 | 2013-12-17 08:00 | 2013-12-29 16:00 | 12 | 1048 | 100 | 93 | -7 | 17340 | 17340 | 16126.2 | 20827.7489 | 0.93 | 0.77427 | TRUE | FALSE | FALSE | 131 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147664 | HCFWF3Z1748 | F3 Z1 :Ceramic Floor Tiles | 26240 | 2013-12-17 08:00 | 2013-12-29 16:00 | 12 | 1048 | 100 | 100 | 0 | 11052 | 11052 | 11052 | 11823.114 | 1 | 0.93478 | FALSE | FALSE | FALSE | 131 | FALSE | 0 | Green | Continue normal monitoring.
147665 | HCFWF3Z3758 | F3 Z3 :Ceramic Floor Tiles | 26141 | 2014-01-06 08:00 | 2014-01-18 16:00 | 12 | 928 | 100 | 100 | 0 | 6168 | 6168 | 6168 | 6861.7249 | 1 | 0.8989 | TRUE | FALSE | FALSE | 116 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147666 | HCFWF4Z1768 | F4 Z1 :Ceramic Floor Tiles | 26147 | 2013-12-17 08:00 | 2013-12-29 16:00 | 12 | 1048 | 100 | 88 | -12 | 14820 | 14820 | 13041.6 | 14862.9028 | 0.88 | 0.87746 | TRUE | TRUE | TRUE | 131 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147667 | HCFWF4Z3778 | F4 Z3 :Ceramic Floor Tiles | 26156 | 2014-01-23 08:00 | 2014-02-03 16:00 | 11 | 816 | 100 | 87 | -13 | 18095 | 18095 | 15742.65 | 17420.3579 | 0.87 | 0.90369 | FALSE | TRUE | TRUE | 102 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147668 | HCFWF4Z5788 | F4 Z5 :Ceramic Floor Tiles | 26160 | 2013-12-17 08:00 | 2013-12-29 16:00 | 12 | 1048 | 100 | 100 | 0 | 9312 | 9312 | 9312 | 10604.4428 | 1 | 0.87812 | TRUE | FALSE | FALSE | 131 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147669 | HCFWF5Z51173 | F5 Z1 :Ceramic Floor Tiles | 26336 | 2013-12-17 08:00 | 2013-12-29 16:00 | 12 | 1048 | 100 | 100 | 0 | 11424 | 11424 | 11424 | 13648.8247 | 1 | 0.837 | TRUE | FALSE | FALSE | 131 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147670 | HCFWF5Z3117 | F5 Z3 :Ceramic Floor Tiles | 26328 | 2014-02-20 08:00 | 2014-03-03 16:00 | 11 | 624 | 100 | 100 | 0 | 21043 | 21043 | 21043 | 23392.0516 | 1 | 0.89958 | TRUE | FALSE | FALSE | 78 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147671 | HCFWF5Z5248 | F5 Z5 :Ceramic Floor Tiles | 26315 | 2014-01-21 08:00 | 2014-02-01 16:00 | 11 | 832 | 100 | 96 | -4 | 19987 | 19987 | 19187.52 | 21079.0146 | 0.96 | 0.91027 | FALSE | FALSE | FALSE | 104 | FALSE | 0 | Green | Continue normal monitoring.
147672 | HCFWF6Z1240 | F6 Z1 :Ceramic Floor Tiles | 26194 | 2013-12-17 08:00 | 2013-12-29 16:00 | 12 | 1048 | 100 | 100 | 0 | 13164 | 13164 | 13164 | 12026.2343 | 1 | 1.0946 | FALSE | FALSE | FALSE | 131 | FALSE | 0 | Green | Continue normal monitoring.
147673 | HCFWF6Z3125 | F6 Z3 :Ceramic Floor Tiles | 26348 | 2014-03-20 08:00 | 2014-03-31 16:00 | 11 | 432 | 100 | 81 | -19 | 10395 | 10395 | 8419.95 | 9058.0313 | 0.81 | 0.92956 | FALSE | TRUE | TRUE | 54 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147674 | HCFWF6Z5280 | F6 Z5 :Ceramic Floor Tiles | 26363 | 2014-02-27 10:00 | 2014-03-11 10:00 | 12 | 574 | 100 | 100 | 0 | 8508 | 8508 | 8508 | 8748.5783 | 1 | 0.9725 | FALSE | FALSE | FALSE | 71.75 | FALSE | 0 | Green | Continue normal monitoring.
147675 | HCFWGFZ1032 | GF Z1: Spicial Metal Ceiling | 26227 | 2013-12-14 08:00 | 2013-12-30 16:00 | 16 | 480 | 100 | 100 | 0 | 19408 | 19408 | 19408 | 16879.9105 | 1 | 1.1498 | FALSE | FALSE | FALSE | 60 | FALSE | 0 | Green | Continue normal monitoring.
147676 | HCFWF1Z1728 | F1 Z1: Spicial Metal Ceiling | 26210 | 2013-12-31 08:00 | 2014-01-18 16:00 | 18 | 480 | 100 | 100 | 0 | 14418 | 14418 | 14418 | 15538.7667 | 1 | 0.92787 | FALSE | FALSE | FALSE | 60 | FALSE | 0 | Green | Continue normal monitoring.
147677 | HCFWF2Z1090 | F2 Z1Spicial Metal Ceiling | 26226 | 2014-01-30 08:00 | 2014-02-15 16:00 | 16 | 288 | 100 | 82 | -18 | 27936 | 27936 | 22907.52 | 28022.3691 | 0.82 | 0.81747 | TRUE | TRUE | TRUE | 36 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147678 | HCFWF3Z1120 | F3 Z1 :Spicial Metal Ceiling | 26242 | 2014-02-16 08:00 | 2014-03-03 16:00 | 15 | 288 | 100 | 87 | -13 | 7530 | 7530 | 6551.1 | 8681.1536 | 0.87 | 0.75463 | TRUE | TRUE | TRUE | 36 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147679 | HCFWF4Z1150 | F4 Z1 :Spicial Metal Ceiling | 26149 | 2014-03-04 08:00 | 2014-03-19 16:00 | 15 | 288 | 100 | 91 | -9 | 22335 | 22335 | 20324.85 | 21715.4137 | 0.91 | 0.93596 | FALSE | FALSE | FALSE | 36 | FALSE | 0 | Green | Continue normal monitoring.
147680 | HCFWF5Z1180 | F5 Z1 :Spicial Metal Ceiling | 26338 | 2014-03-20 08:00 | 2014-04-05 16:00 | 16 | 288 | 100 | 80 | -20 | 25856 | 25856 | 20684.8 | 28110.4643 | 0.8 | 0.73584 | TRUE | TRUE | TRUE | 36 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147681 | HCFWF6Z1280 | F6 Z1 :Spicial Metal Ceiling | 26344 | 2014-04-06 08:00 | 2014-04-21 16:00 | 15 | 288 | 100 | 89 | -11 | 15285 | 15285 | 13603.65 | 16279.6471 | 0.89 | 0.83562 | TRUE | TRUE | TRUE | 36 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147682 | HEMSSFI0220 | MS submission: Spicial Metal Ceiling | 25761 | 2013-01-08 08:00 | 2013-01-31 16:00 | 23 | 600 | 100 | 99 | -1 | 44873 | 44873 | 44424.27 | 38226.6343 | 0.99 | 1.1621 | FALSE | FALSE | FALSE | 75 | FALSE | 0 | Green | Continue normal monitoring.
147683 | HEMSAFI0220 | MS approval: Spicial Metal ceiling | 25781 | 2013-02-02 08:00 | 2013-02-17 16:00 | 15 | 600 | 100 | 82 | -18 | 14880 | 14880 | 12201.6 | 13078.8617 | 0.82 | 0.93293 | FALSE | TRUE | TRUE | 75 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147684 | HCMEPSAF030 | SPS :Access Flooring Accessories | 26099 | 2014-03-12 08:00 | 2014-03-23 16:00 | 11 | 488 | 100 | 85 | -15 | 19338 | 19338 | 16437.3 | 18683.3562 | 0.85 | 0.87978 | TRUE | TRUE | TRUE | 61 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147685 | HCMEPSAF020 | SPS :Access Panels | 26099 | 2013-12-30 08:00 | 2014-03-11 16:00 | 71 | 488 | 100 | 86 | -14 | 79449 | 79449 | 68326.14 | 95568.728 | 0.86 | 0.71494 | TRUE | TRUE | TRUE | 61 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147686 | HCMEPSAF010 | SPS :Steel Base Structures | 26099 | 2013-10-14 08:00 | 2013-12-29 16:00 | 76 | 488 | 100 | 99 | -1 | 127984 | 127984 | 126704.16 | 116312.6248 | 0.99 | 1.0893 | FALSE | FALSE | FALSE | 61 | FALSE | 0 | Green | Continue normal monitoring.
147687 | HEMSSFI0560 | MS submission: Access flooring system | 25761 | 2012-06-05 08:00 | 2012-06-21 16:00 | 16 | 3288 | 100 | 100 | 0 | 13280 | 13280 | 13280 | 15064.2707 | 1 | 0.88156 | TRUE | FALSE | FALSE | 411 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147688 | HEMSSFI560 | MS Approval: Access flooring system | 25781 | 2012-06-23 08:00 | 2012-07-08 16:00 | 15 | 3288 | 100 | 100 | 0 | 12480 | 12480 | 12480 | 15467.0459 | 1 | 0.80688 | TRUE | FALSE | FALSE | 411 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147689 | HEPSAFI0560 | Access Flooring system | 25712 | 2012-07-09 08:00 | 2012-08-12 16:00 | 34 | 3288 | 100 | 100 | 0 | 18666 | 18666 | 18666 | 21768.7936 | 1 | 0.85747 | TRUE | FALSE | FALSE | 411 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147690 | HCEXWWFP020 | EXT :Reflecting Pool All Works | 25755 | 2013-12-23 08:00 | 2014-05-15 16:00 | 143 | 128 | 100 | 97 | -3 | 194766 | 194766 | 188923.02 | 184478.0985 | 0.97 | 1.0241 | FALSE | FALSE | FALSE | 16 | FALSE | 0 | Green | Continue normal monitoring.
147691 | HCMEPSRS010 | SPS :Motor & Electrical Intallations | 26095 | 2013-10-14 08:00 | 2013-11-23 16:00 | 40 | 1128 | 100 | 90 | -10 | 30840 | 30840 | 27756 | 37419.5939 | 0.9 | 0.74175 | TRUE | FALSE | FALSE | 141 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147692 | HCMEPSRS020 | SPS :Hardware | 26095 | 2013-11-24 08:00 | 2013-12-29 16:00 | 35 | 1128 | 100 | 98 | -2 | 37765 | 37765 | 37009.7 | 33506.7267 | 0.98 | 1.1045 | FALSE | FALSE | FALSE | 141 | FALSE | 0 | Green | Continue normal monitoring.
147693 | HCMEPSRS030 | SPS :PVC Roller Doors final fix | 26095 | 2013-12-30 08:00 | 2014-02-04 16:00 | 36 | 1128 | 100 | 84 | -16 | 63900 | 63900 | 53676 | 66280.708 | 0.84 | 0.80983 | TRUE | TRUE | TRUE | 141 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147694 | HCFWB1Z3052 | B1 Z3: Wall paper cover | 26219 | 2014-01-06 08:00 | 2014-01-18 16:00 | 12 | 608 | 100 | 98 | -2 | 12708 | 12708 | 12453.84 | 15313.353 | 0.98 | 0.81327 | TRUE | FALSE | FALSE | 76 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147695 | HCFWB1Z1031 | B1 Z1: Gybsum board partitions | 26249 | 2013-02-16 08:00 | 2013-02-26 16:00 | 10 | 394 | 100 | 90 | -10 | 11950 | 11950 | 10755 | 13222.7501 | 0.9 | 0.81337 | TRUE | FALSE | FALSE | 49.25 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147696 | HCFWB1Z2037 | B1 Z2: Gybsum board partitions | 26234 | 2013-02-27 08:00 | 2013-03-10 16:00 | 11 | 394 | 100 | 100 | 0 | 17743 | 17743 | 17743 | 18017.2682 | 1 | 0.98478 | FALSE | FALSE | FALSE | 49.25 | FALSE | 0 | Green | Continue normal monitoring.
147697 | HCFWB1Z3055 | B1 Z3: Gybsum board partitions | 26219 | 2013-12-12 08:00 | 2013-12-23 16:00 | 11 | 520 | 100 | 91 | -9 | 10395 | 10395 | 9459.45 | 10053.2659 | 0.91 | 0.94093 | FALSE | FALSE | FALSE | 65 | FALSE | 0 | Green | Continue normal monitoring.
147698 | HCFWB1Z4037 | B1 Z4: Gybsum board partitions | 26217 | 2013-12-24 08:00 | 2014-01-06 16:00 | 13 | 520 | 100 | 89 | -11 | 19708 | 19708 | 17540.12 | 19708.7836 | 0.89 | 0.88996 | TRUE | TRUE | TRUE | 65 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147699 | HCFWB1Z5037 | B1 Z5: Gybsum board partitions | 26186 | 2014-01-07 08:00 | 2014-01-19 16:00 | 12 | 520 | 100 | 87 | -13 | 22260 | 22260 | 19366.2 | 23452.6176 | 0.87 | 0.82576 | TRUE | TRUE | TRUE | 65 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147700 | HCFWB1Z6037 | B1 B6: Gybsum board partitions | 26190 | 2014-01-20 08:00 | 2014-01-30 16:00 | 10 | 520 | 100 | 100 | 0 | 16620 | 16620 | 16620 | 16248.004 | 1 | 1.0229 | FALSE | FALSE | FALSE | 65 | FALSE | 0 | Green | Continue normal monitoring.
147701 | HCFWB4Z1026 | B4 Z1: Curb Stone & Wheel Stopper for Parkings | 26248 | 2013-12-17 08:00 | 2013-12-26 16:00 | 9 | 80 | 100 | 100 | 0 | 7704 | 7704 | 7704 | 9534.3714 | 1 | 0.80802 | TRUE | FALSE | FALSE | 10 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147702 | HCFWB4Z2010 | B4 Z2: Curb Stone & Wheel Stopper for Parkings | 26218 | 2013-12-28 08:00 | 2014-01-06 16:00 | 9 | 80 | 100 | 100 | 0 | 6957 | 6957 | 6957 | 8510.0185 | 1 | 0.81751 | TRUE | FALSE | FALSE | 10 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147703 | HCFWB4Z3100 | B4 Z3: Curb Stone & Wheel Stopper for Parkings | 26326 | 2014-01-07 08:00 | 2014-01-16 16:00 | 9 | 80 | 100 | 88 | -12 | 13878 | 13878 | 12212.64 | 16629.5715 | 0.88 | 0.73439 | TRUE | TRUE | TRUE | 10 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147704 | HCFWB4Z4100 | B4 Z4: Curb Stone & Wheel Stopper for Parkings | 26371 | 2014-01-18 08:00 | 2014-01-26 16:00 | 8 | 80 | 100 | 83 | -17 | 6480 | 6480 | 5378.4 | 6601.3829 | 0.83 | 0.81474 | TRUE | TRUE | TRUE | 10 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147705 | HCFWB4Z5100 | B4 Z5: Curb Stone & Wheel Stopper for Parkings | 26365 | 2014-01-27 08:00 | 2014-02-04 16:00 | 8 | 80 | 100 | 84 | -16 | 10952 | 10952 | 9199.68 | 12337.6548 | 0.84 | 0.74566 | TRUE | TRUE | TRUE | 10 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147706 | HCFWB4Z6100 | B4 Z6: Curb Stone & Wheel Stopper for Parkings | 26213 | 2014-02-05 08:00 | 2014-02-12 16:00 | 7 | 80 | 100 | 100 | 0 | 9695 | 9695 | 9695 | 11741.9221 | 1 | 0.82567 | TRUE | FALSE | FALSE | 10 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147707 | HCFWB3Z20010 | B3 Z1: Curb Stone & Wheel Stopper for Parkings | 26172 | 2014-02-13 08:00 | 2014-02-20 16:00 | 7 | 80 | 100 | 87 | -13 | 4571 | 4571 | 3976.77 | 5440.2753 | 0.87 | 0.73099 | TRUE | TRUE | TRUE | 10 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147708 | HCFWB3Z2100 | B3 Z2: Curb Stone & Wheel Stopper for Parkings | 26340 | 2014-02-22 08:00 | 2014-03-01 16:00 | 7 | 80 | 100 | 100 | 0 | 13391 | 13391 | 13391 | 13601.6512 | 1 | 0.98451 | FALSE | FALSE | FALSE | 10 | FALSE | 0 | Green | Continue normal monitoring.
147709 | HCFWB3Z3030 | B3 Z3: Curb Stone & Wheel Stopper for Parkings | 26177 | 2014-03-02 08:00 | 2014-03-09 16:00 | 7 | 80 | 100 | 88 | -12 | 12481 | 12481 | 10983.28 | 11169.9261 | 0.88 | 0.98329 | FALSE | TRUE | TRUE | 10 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147710 | HCFWB3Z4100 | B3 Z4: Curb Stone & Wheel Stopper for Parkings | 26182 | 2014-03-10 08:00 | 2014-03-17 16:00 | 7 | 80 | 100 | 94 | -6 | 7833 | 7833 | 7363.02 | 6895.0151 | 0.94 | 1.0679 | FALSE | FALSE | FALSE | 10 | FALSE | 0 | Green | Continue normal monitoring.
147711 | HCFWB3Z5100 | B4 Z5: Curb Stone & Wheel Stopper for Parkings | 26374 | 2014-03-18 08:00 | 2014-03-25 16:00 | 7 | 80 | 100 | 94 | -6 | 9674 | 9674 | 9093.56 | 10455.907 | 0.94 | 0.86971 | TRUE | FALSE | FALSE | 10 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147712 | HCFWB3Z6100 | B4 Z6: Curb Stone & Wheel Stopper for Parkings | 26136 | 2014-03-26 08:00 | 2014-04-02 16:00 | 7 | 80 | 100 | 95 | -5 | 9072 | 9072 | 8618.4 | 10043.1683 | 0.95 | 0.85814 | TRUE | FALSE | FALSE | 10 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147713 | HCFWB2Z1100 | B2 Z1: Curb Stone & Wheel Stopper for Parkings | 26367 | 2014-04-03 08:00 | 2014-04-10 16:00 | 7 | 80 | 100 | 93 | -7 | 4368 | 4368 | 4062.24 | 5197.645 | 0.93 | 0.78155 | TRUE | FALSE | FALSE | 10 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147714 | HCFWB2Z2100 | B2 Z2: Curb Stone & Wheel Stopper for Parkings | 26134 | 2014-04-12 08:00 | 2014-04-19 16:00 | 7 | 80 | 100 | 87 | -13 | 13139 | 13139 | 11430.93 | 12705.4919 | 0.87 | 0.89968 | TRUE | TRUE | TRUE | 10 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147715 | HCFWB2Z3100 | B2 Z3: Curb Stone & Wheel Stopper for Parkings | 26173 | 2014-04-20 08:00 | 2014-04-27 16:00 | 7 | 80 | 100 | 97 | -3 | 12572 | 12572 | 12194.84 | 11528.3756 | 0.97 | 1.0578 | FALSE | FALSE | FALSE | 10 | FALSE | 0 | Green | Continue normal monitoring.
147716 | HCFWB2Z4100 | B2 Z4: Curb Stone & Wheel Stopper for Parkings | 26231 | 2014-04-28 08:00 | 2014-05-06 16:00 | 8 | 80 | 100 | 89 | -11 | 8944 | 8944 | 7960.16 | 8958.3313 | 0.89 | 0.88858 | TRUE | TRUE | TRUE | 10 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147717 | HCFWB2Z5100 | B2 Z5: Curb Stone & Wheel Stopper for Parkings | 26179 | 2014-05-07 08:00 | 2014-05-14 16:00 | 7 | 80 | 100 | 100 | 0 | 5208 | 5208 | 5208 | 5163.3677 | 1 | 1.0086 | FALSE | FALSE | FALSE | 10 | FALSE | 0 | Green | Continue normal monitoring.
147718 | HCFWB2Z6100 | B2 Z6: Curb Stone & Wheel Stopper for Parkings | 26389 | 2014-05-15 08:00 | 2014-05-22 16:00 | 7 | 80 | 100 | 99 | -1 | 9429 | 9429 | 9334.71 | 8514.2699 | 0.99 | 1.0964 | FALSE | FALSE | FALSE | 10 | FALSE | 0 | Green | Continue normal monitoring.
147719 | HCEXWMEP060 | EXT :External Pumps All works & Connect to mains | 25757 | 2013-12-30 08:00 | 2014-01-23 16:00 | 24 | 968 | 100 | 85 | -15 | 22776 | 22776 | 19359.6 | 25484.3639 | 0.85 | 0.75967 | TRUE | TRUE | TRUE | 121 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147720 | HCMEPSPL030 | SPS :Building EM Pumps All Works & Connect to mains | 26096 | 2013-10-14 08:00 | 2013-11-11 16:00 | 28 | 1288 | 100 | 91 | -9 | 40012 | 40012 | 36410.92 | 42151.7128 | 0.91 | 0.86381 | TRUE | FALSE | FALSE | 161 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147721 | HCMEPSPL040 | SPS :Copper silver ionization water treatment unit | 26096 | 2013-10-14 08:00 | 2013-11-11 16:00 | 28 | 1288 | 100 | 81 | -19 | 49560 | 49560 | 40143.6 | 56421.5375 | 0.81 | 0.71149 | TRUE | TRUE | TRUE | 161 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147722 | HCMEPSPL050 | SPS :GRP Tank | 26096 | 2013-10-14 08:00 | 2013-11-11 16:00 | 28 | 1288 | 100 | 86 | -14 | 28532 | 28532 | 24537.52 | 28277.3932 | 0.86 | 0.86774 | TRUE | TRUE | TRUE | 161 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147723 | HCMEPSPL060 | SPS :Expansion tank | 26096 | 2013-10-14 08:00 | 2013-11-11 16:00 | 28 | 1288 | 100 | 95 | -5 | 46592 | 46592 | 44262.4 | 45673.247 | 0.95 | 0.96911 | FALSE | FALSE | FALSE | 161 | FALSE | 0 | Green | Continue normal monitoring.
147724 | HCMEPSPL070 | SPS :Sand Oil intercepter | 26096 | 2013-11-12 08:00 | 2013-12-04 16:00 | 22 | 1288 | 100 | 82 | -18 | 18942 | 18942 | 15532.44 | 19681.3127 | 0.82 | 0.7892 | TRUE | TRUE | TRUE | 161 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147725 | HCMEPSHV050 | SPS :Air Handiling Units All works & connect to mains | 26053 | 2014-03-24 12:00 | 2014-04-28 12:00 | 35 | 324 | 100 | 92 | -8 | 17745 | 17745 | 16325.4 | 21311.0873 | 0.92 | 0.76605 | TRUE | FALSE | FALSE | 40.5 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147726 | HCMEPSHV060 | SPS :Chimney steel ductwork, Accesss, connect to boiler | 26053 | 2014-04-09 12:00 | 2014-05-15 12:00 | 36 | 212 | 100 | 82 | -18 | 35172 | 35172 | 28841.04 | 30462.9096 | 0.82 | 0.94676 | FALSE | TRUE | TRUE | 26.5 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147727 | HCMEPSGR070 | SPS :Grounding system for building structure - elec | 26097 | 2013-10-14 08:00 | 2013-11-03 16:00 | 20 | 824 | 100 | 100 | 0 | 37500 | 37500 | 37500 | 43947.4923 | 1 | 0.85329 | TRUE | FALSE | FALSE | 103 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147728 | HCMEPSGR080 | SPS :Grounding system to main/submain electrical panels - elec | 26097 | 2013-11-04 08:00 | 2013-11-20 16:00 | 16 | 824 | 100 | 97 | -3 | 15904 | 15904 | 15426.88 | 15865.7516 | 0.97 | 0.97234 | FALSE | FALSE | FALSE | 103 | FALSE | 0 | Green | Continue normal monitoring.
147729 | HCMEPSGR090 | SPS :Grounding system to MCC panels - elec | 26097 | 2013-11-21 08:00 | 2013-12-07 16:00 | 16 | 824 | 100 | 90 | -10 | 21312 | 21312 | 19180.8 | 25400.6563 | 0.9 | 0.75513 | TRUE | FALSE | TRUE | 103 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147730 | HCMEPSGR100 | SPS :Grounding system to Mechanical equipments - elec | 26097 | 2013-12-08 08:00 | 2013-12-23 16:00 | 15 | 824 | 100 | 87 | -13 | 29250 | 29250 | 25447.5 | 34248.2752 | 0.87 | 0.74303 | TRUE | TRUE | TRUE | 103 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147731 | HCMEPSGR110 | SPS :Clean grounding system for equipment rooms- comm | 26097 | 2013-12-24 08:00 | 2014-01-11 16:00 | 18 | 824 | 100 | 85 | -15 | 28116 | 28116 | 23898.6 | 27820.9085 | 0.85 | 0.85902 | TRUE | TRUE | TRUE | 103 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147732 | HCMEPSGR120 | SPS :Clean grounding system for all floors Telecom rooms - comm | 26097 | 2014-01-12 08:00 | 2014-01-28 16:00 | 16 | 824 | 100 | 80 | -20 | 17472 | 17472 | 13977.6 | 19700.5643 | 0.8 | 0.7095 | TRUE | TRUE | TRUE | 103 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147733 | HCMEPSGR130 | SPS :Clean grounding system for low current systems equipment rooms - saf | 26097 | 2014-01-29 08:00 | 2014-02-13 16:00 | 15 | 824 | 100 | 100 | 0 | 10290 | 10290 | 10290 | 9403.5484 | 1 | 1.0943 | FALSE | FALSE | FALSE | 103 | FALSE | 0 | Green | Continue normal monitoring.
147734 | HCMEPSBW130 | SPS :Enclosed Bus Assemblies (BBT/Busways) | 26098 | 2013-10-14 08:00 | 2013-11-23 16:00 | 40 | 888 | 100 | 80 | -20 | 50120 | 50120 | 40096 | 60570.6526 | 0.8 | 0.66197 | TRUE | TRUE | TRUE | 111 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147735 | HCMEPSBW140 | SPS :Tap-off plug in unit type, including MCCB circuit breaker for busway system | 26098 | 2013-11-24 08:00 | 2013-12-29 16:00 | 35 | 888 | 100 | 100 | 0 | 20720 | 20720 | 20720 | 20964.4219 | 1 | 0.98834 | FALSE | FALSE | FALSE | 111 | FALSE | 0 | Green | Continue normal monitoring.
147736 | HCMEPSBW150 | SPS :Transition Box for connection electrical cables to busway distribution system | 26098 | 2013-12-30 08:00 | 2014-02-04 16:00 | 36 | 888 | 100 | 87 | -13 | 21060 | 21060 | 18322.2 | 21739.1902 | 0.87 | 0.84282 | TRUE | TRUE | TRUE | 111 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147737 | HCMEPSLS150 | SPS :lighting points | 26100 | 2013-04-04 08:00 | 2013-06-15 16:00 | 72 | 328 | 100 | 84 | -16 | 112824 | 112824 | 94772.16 | 127751.0237 | 0.84 | 0.74185 | TRUE | TRUE | TRUE | 41 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147738 | HCMEPSLS160 | SPS :Lighting Fixtures | 26100 | 2013-06-16 08:00 | 2013-08-27 16:00 | 72 | 328 | 100 | 100 | 0 | 45792 | 45792 | 45792 | 53958.3664 | 1 | 0.84865 | TRUE | FALSE | FALSE | 41 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147739 | HCMEPSLS170 | SPS :Exterior Lighting | 26100 | 2013-08-28 08:00 | 2013-11-11 16:00 | 75 | 328 | 100 | 95 | -5 | 69000 | 69000 | 65550 | 65173.0597 | 0.95 | 1.0058 | FALSE | FALSE | FALSE | 41 | FALSE | 0 | Green | Continue normal monitoring.
147740 | HCMEPSLS180 | SPS :Emergency & Exit Lighting | 26100 | 2013-11-12 08:00 | 2014-01-23 16:00 | 72 | 328 | 100 | 90 | -10 | 41256 | 41256 | 37130.4 | 45981.4645 | 0.9 | 0.80751 | TRUE | FALSE | FALSE | 41 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147741 | HCMEPSLS190 | SPS :Lighting Switches/control | 26100 | 2014-01-25 08:00 | 2014-04-03 16:00 | 68 | 328 | 100 | 84 | -16 | 114172 | 114172 | 95904.48 | 114948.2803 | 0.84 | 0.83433 | TRUE | TRUE | TRUE | 41 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147742 | HCMEPSLS200 | SPS :Facility Lightning Protection | 26100 | 2014-04-05 08:00 | 2014-04-27 16:00 | 22 | 328 | 100 | 83 | -17 | 39116 | 39116 | 32466.28 | 39017.4734 | 0.83 | 0.8321 | TRUE | TRUE | TRUE | 41 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147743 | HEMSSFI0080 | MS submission:Ceramic Tiles | 25761 | 2012-11-22 08:00 | 2012-12-08 16:00 | 16 | 592 | 100 | 100 | 0 | 10720 | 10720 | 10720 | 12070.8307 | 1 | 0.88809 | TRUE | FALSE | FALSE | 74 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147744 | HEMSAFI0080 | MS approval: Ceramic Tiles | 25781 | 2012-12-09 08:00 | 2012-12-24 16:00 | 15 | 592 | 100 | 85 | -15 | 10035 | 10035 | 8529.75 | 10083.9037 | 0.85 | 0.84588 | TRUE | TRUE | TRUE | 74 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147745 | HCSWB4Z1260 | B4 Z1 :De-tensioning | 26110 | 2012-10-10 08:00 | 2012-10-13 16:00 | 3 | 464 | 100 | 93 | -7 | 4113 | 4113 | 3825.09 | 4065.4677 | 0.93 | 0.94087 | FALSE | FALSE | FALSE | 58 | FALSE | 0 | Green | Continue normal monitoring.
147746 | HCSWB4Z2100 | B4 Z2 :De-tensioning | 26111 | 2012-10-06 08:00 | 2012-10-08 16:00 | 2 | 496 | 100 | 100 | 0 | 1642 | 1642 | 1642 | 1944.7115 | 1 | 0.84434 | TRUE | FALSE | FALSE | 62 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147747 | HCSWB4Z3260 | B4 Z3 :De-tensioning | 26112 | 2012-10-11 08:00 | 2012-10-13 16:00 | 2 | 928 | 100 | 98 | -2 | 1910 | 1910 | 1871.8 | 1700.875 | 0.98 | 1.1005 | FALSE | FALSE | FALSE | 116 | FALSE | 0 | Green | Continue normal monitoring.
147748 | HCSWB4Z4100 | B4 Z4 :De-tensioning | 26113 | 2012-10-23 08:00 | 2012-10-24 16:00 | 1 | 832 | 100 | 88 | -12 | 1443 | 1443 | 1269.84 | 1616.6752 | 0.88 | 0.78546 | TRUE | TRUE | TRUE | 104 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147749 | HCSWB4Z5260 | B4 Z5 :De-tensioning | 26114 | 2012-11-04 08:00 | 2012-11-05 16:00 | 1 | 680 | 100 | 91 | -9 | 1289 | 1289 | 1172.99 | 1223.8928 | 0.91 | 0.95841 | FALSE | FALSE | FALSE | 85 | FALSE | 0 | Green | Continue normal monitoring.
147750 | HCSWB4Z1270 | B4 Z1 :Backfill behind basement walls up slab level | 26110 | 2012-10-14 08:00 | 2012-10-24 16:00 | 10 | 464 | 100 | 90 | -10 | 11120 | 11120 | 10008 | 9520.9362 | 0.9 | 1.0512 | FALSE | FALSE | FALSE | 58 | FALSE | 0 | Green | Continue normal monitoring.
147751 | HCSWB4Z2110 | B4 Z2 :Backfill behind basement walls up slab level | 26111 | 2012-10-09 08:00 | 2012-10-20 16:00 | 11 | 496 | 100 | 93 | -7 | 18458 | 18458 | 17165.94 | 16920.5539 | 0.93 | 1.0145 | FALSE | FALSE | FALSE | 62 | FALSE | 0 | Green | Continue normal monitoring.
147752 | HCSWB4Z3270 | B4 Z3 :Backfill behind basement walls up slab level | 26112 | 2012-10-14 08:00 | 2012-10-17 16:00 | 3 | 928 | 100 | 100 | 0 | 4164 | 4164 | 4164 | 4549.8554 | 1 | 0.91519 | FALSE | FALSE | FALSE | 116 | FALSE | 0 | Green | Continue normal monitoring.
147753 | HCSWB4Z4110 | B4 Z4 :Backfill behind basement walls up slab level | 26113 | 2012-10-30 08:00 | 2012-11-03 16:00 | 4 | 832 | 100 | 95 | -5 | 3392 | 3392 | 3222.4 | 3845.3438 | 0.95 | 0.838 | TRUE | FALSE | FALSE | 104 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147754 | HCSWB4Z5270 | B4 Z5 :Backfill behind basement walls up slab level | 26114 | 2012-11-06 08:00 | 2012-11-12 16:00 | 6 | 680 | 100 | 80 | -20 | 11844 | 11844 | 9475.2 | 10167.1634 | 0.8 | 0.93194 | FALSE | TRUE | TRUE | 85 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147755 | HCSWB4Z6110 | B4 Z6 :Backfill behind basement walls up slab level | 26115 | 2012-12-04 08:00 | 2012-12-10 16:00 | 6 | 576 | 100 | 100 | 0 | 10176 | 10176 | 10176 | 8797.8661 | 1 | 1.1566 | FALSE | FALSE | FALSE | 72 | FALSE | 0 | Green | Continue normal monitoring.
147756 | HCSWB3Z1250 | B3 Z1 :Backfill behind basement walls up to anchor level | 26117 | 2012-10-30 08:00 | 2012-11-22 16:00 | 23 | 464 | 100 | 92 | -8 | 11707 | 11707 | 10770.44 | 14177.3742 | 0.92 | 0.75969 | TRUE | FALSE | FALSE | 58 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147757 | HCSWB3Z2090 | B3 Z2 :Backfill behind basement walls up to anchor level | 26118 | 2012-11-07 08:00 | 2012-12-01 16:00 | 24 | 408 | 100 | 100 | 0 | 29736 | 29736 | 29736 | 26147.5287 | 1 | 1.1372 | FALSE | FALSE | FALSE | 51 | FALSE | 0 | Green | Continue normal monitoring.
147758 | HCSWB3Z3250 | B3 Z3 :Backfill behind basement walls up to anchor level | 26119 | 2012-11-10 08:00 | 2012-11-24 16:00 | 14 | 808 | 100 | 100 | 0 | 25032 | 25032 | 25032 | 30230.4671 | 1 | 0.82804 | TRUE | FALSE | FALSE | 101 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147759 | HCSWB3Z4090 | B3 Z4 :Backfill behind basement walls up to anchor level | 26101 | 2012-12-12 08:00 | 2012-12-25 16:00 | 13 | 576 | 100 | 100 | 0 | 25493 | 25493 | 25493 | 23995.7035 | 1 | 1.0624 | FALSE | FALSE | FALSE | 72 | FALSE | 0 | Green | Continue normal monitoring.
147760 | HCSWB3Z5250 | B3 Z5 :Backfill behind basement walls up to anchor level | 26102 | 2012-11-25 08:00 | 2012-12-10 16:00 | 15 | 608 | 100 | 100 | 0 | 26550 | 26550 | 26550 | 30426.489 | 1 | 0.87259 | TRUE | FALSE | FALSE | 76 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147761 | HCSWB3Z6090 | B3 Z6 :Backfill behind basement walls up to anchor level | 26103 | 2012-12-15 08:00 | 2012-12-30 16:00 | 15 | 552 | 100 | 92 | -8 | 17490 | 17490 | 16090.8 | 17033.3938 | 0.92 | 0.94466 | FALSE | FALSE | FALSE | 69 | FALSE | 0 | Green | Continue normal monitoring.
147762 | HCSWB3Z6100 | B3 Z6 :De-tensioning | 26103 | 2012-12-31 08:00 | 2013-01-02 16:00 | 2 | 552 | 100 | 81 | -19 | 2090 | 2090 | 1692.9 | 2494.4167 | 0.81 | 0.67868 | TRUE | TRUE | TRUE | 69 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147763 | HCSWB3Z1260 | B3 Z1 :De-tensioning | 26117 | 2012-11-24 08:00 | 2012-11-26 16:00 | 2 | 464 | 100 | 83 | -17 | 1256 | 1256 | 1042.48 | 1419.5085 | 0.83 | 0.7344 | TRUE | TRUE | TRUE | 58 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147764 | HCSWB3Z2100 | B3 Z2 :De-tensioning | 26118 | 2012-12-02 08:00 | 2012-12-04 16:00 | 2 | 408 | 100 | 100 | 0 | 2200 | 2200 | 2200 | 2223.5958 | 1 | 0.98939 | FALSE | FALSE | FALSE | 51 | FALSE | 0 | Green | Continue normal monitoring.
147765 | HCSWB3Z3260 | B3 Z3 :De-tensioning | 26119 | 2012-11-25 08:00 | 2012-11-26 16:00 | 1 | 808 | 100 | 85 | -15 | 1104 | 1104 | 938.4 | 972.0952 | 0.85 | 0.96534 | FALSE | TRUE | TRUE | 101 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147766 | HCSWB3Z4100 | B3 Z4 :De-tensioning | 26101 | 2012-12-26 08:00 | 2012-12-27 16:00 | 1 | 576 | 100 | 100 | 0 | 826 | 826 | 826 | 944.1841 | 1 | 0.87483 | TRUE | FALSE | FALSE | 72 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147767 | HCSWB3Z5260 | B3 Z5 :De-tensioning | 26102 | 2012-12-11 08:00 | 2012-12-12 16:00 | 1 | 608 | 100 | 100 | 0 | 1479 | 1479 | 1479 | 1622.099 | 1 | 0.91178 | FALSE | FALSE | FALSE | 76 | FALSE | 0 | Green | Continue normal monitoring.
147768 | HCSWB3Z1270 | B3 Z1 :Backfill behind basement walls up slab level | 26117 | 2012-11-27 08:00 | 2012-12-08 16:00 | 11 | 464 | 100 | 100 | 0 | 9933 | 9933 | 9933 | 8454.6188 | 1 | 1.1749 | FALSE | FALSE | FALSE | 58 | FALSE | 0 | Green | Continue normal monitoring.
147769 | HCSWB3Z2110 | B3 Z2 :Backfill behind basement walls up slab level | 26118 | 2012-12-05 08:00 | 2012-12-16 16:00 | 11 | 408 | 100 | 100 | 0 | 12408 | 12408 | 12408 | 10593.5526 | 1 | 1.1713 | FALSE | FALSE | FALSE | 51 | FALSE | 0 | Green | Continue normal monitoring.
147770 | HCSWB3Z3270 | B3 Z3 :Backfill behind basement walls up slab level | 26119 | 2012-11-27 08:00 | 2012-12-01 16:00 | 4 | 808 | 100 | 100 | 0 | 7528 | 7528 | 7528 | 8834.2374 | 1 | 0.85214 | TRUE | FALSE | FALSE | 101 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147771 | HCSWB3Z4110 | B3 Z4 :Backfill behind basement walls up slab level | 26101 | 2012-12-29 08:00 | 2013-01-02 16:00 | 4 | 576 | 100 | 84 | -16 | 4868 | 4868 | 4089.12 | 4642.9032 | 0.84 | 0.88072 | TRUE | TRUE | TRUE | 72 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147772 | HCSWB3Z5270 | B3 Z5 :Backfill behind basement walls up slab level | 26102 | 2012-12-13 08:00 | 2012-12-31 16:00 | 18 | 608 | 100 | 100 | 0 | 27720 | 27720 | 27720 | 30615.4501 | 1 | 0.90543 | FALSE | FALSE | FALSE | 76 | FALSE | 0 | Green | Continue normal monitoring.
147773 | HCSWB3Z6110 | B3 Z6 :Backfill behind basement walls up slab level | 26103 | 2013-01-03 08:00 | 2013-01-09 16:00 | 6 | 552 | 100 | 82 | -18 | 4638 | 4638 | 3803.16 | 4784.9586 | 0.82 | 0.79482 | TRUE | TRUE | TRUE | 69 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147774 | HCSWB2Z1250 | B2 Z1 :Backfill behind basement walls up to anchor level | 26105 | 2012-12-09 08:00 | 2012-12-25 16:00 | 16 | 464 | 100 | 80 | -20 | 18944 | 18944 | 15155.2 | 22645.1273 | 0.8 | 0.66925 | TRUE | TRUE | TRUE | 58 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147775 | HCSWB2Z2090 | B2 Z2 :Backfill behind basement walls up to anchor level | 26106 | 2013-01-08 08:00 | 2013-01-26 16:00 | 18 | 264 | 100 | 83 | -17 | 11070 | 11070 | 9188.1 | 13469.8038 | 0.83 | 0.68213 | TRUE | TRUE | TRUE | 33 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147776 | HCSWB2Z3250 | B2 Z3 :Backfill behind basement walls up to anchor level | 26107 | 2012-12-02 08:00 | 2012-12-10 16:00 | 8 | 808 | 100 | 100 | 0 | 10880 | 10880 | 10880 | 13586.1072 | 1 | 0.80082 | TRUE | FALSE | FALSE | 101 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147777 | HCSWB2Z4090 | B2 Z4 :Backfill behind basement walls up to anchor level | 26108 | 2013-01-10 08:00 | 2013-01-19 16:00 | 9 | 528 | 100 | 99 | -1 | 10728 | 10728 | 10620.72 | 9778.2894 | 0.99 | 1.0862 | FALSE | FALSE | FALSE | 66 | FALSE | 0 | Green | Continue normal monitoring.
147778 | HCSWB2Z5250 | B2 Z5 :Backfill behind basement walls up to anchor level | 26109 | 2013-01-02 08:00 | 2013-01-17 16:00 | 15 | 608 | 100 | 81 | -19 | 24210 | 24210 | 19610.1 | 28935.4438 | 0.81 | 0.67772 | TRUE | TRUE | TRUE | 76 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147779 | HCSWB2Z6090 | B2 Z6 :Backfill behind basement walls up to anchor level | 26124 | 2013-03-13 08:00 | 2013-03-28 16:00 | 15 | 136 | 100 | 100 | 0 | 24075 | 24075 | 24075 | 23025.5359 | 1 | 1.0456 | FALSE | FALSE | FALSE | 17 | FALSE | 0 | Green | Continue normal monitoring.
147780 | HCSWB2Z6100 | B2 Z6 :De-tensioning | 26124 | 2013-03-30 08:00 | 2013-03-31 16:00 | 1 | 136 | 100 | 100 | 0 | 823 | 823 | 823 | 894.0466 | 1 | 0.92053 | FALSE | FALSE | FALSE | 17 | FALSE | 0 | Green | Continue normal monitoring.
147781 | HCSWB2Z1260 | B2 Z1 :De-tensioning | 26105 | 2012-12-26 08:00 | 2012-12-29 16:00 | 3 | 464 | 100 | 100 | 0 | 4380 | 4380 | 4380 | 4609.114 | 1 | 0.95029 | FALSE | FALSE | FALSE | 58 | FALSE | 0 | Green | Continue normal monitoring.
147782 | HCSWB2Z2100 | B2 Z2 :De-tensioning | 26106 | 2013-01-27 08:00 | 2013-01-29 16:00 | 2 | 264 | 100 | 84 | -16 | 1226 | 1226 | 1029.84 | 1050.9214 | 0.84 | 0.97994 | FALSE | TRUE | TRUE | 33 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147783 | HCSWB2Z3260 | B2 Z3 :De-tensioning | 26107 | 2012-12-22 08:00 | 2012-12-23 16:00 | 1 | 736 | 100 | 82 | -18 | 1581 | 1581 | 1296.42 | 1933.7346 | 0.82 | 0.67042 | TRUE | TRUE | TRUE | 92 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147784 | HCSWB2Z4100 | B2 Z4 :De-tensioning | 26108 | 2013-01-20 08:00 | 2013-01-21 16:00 | 1 | 528 | 100 | 100 | 0 | 653 | 653 | 653 | 575.509 | 1 | 1.1346 | FALSE | FALSE | FALSE | 66 | FALSE | 0 | Green | Continue normal monitoring.
147785 | HCSWB2Z5260 | B2 Z5 :De-tensioning | 26109 | 2013-01-19 08:00 | 2013-01-20 16:00 | 1 | 608 | 100 | 100 | 0 | 1927 | 1927 | 1927 | 2168.4291 | 1 | 0.88866 | TRUE | FALSE | FALSE | 76 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147786 | HCSWB2Z1270 | B2 Z1 :Backfill behind basement walls up next anchor level | 26105 | 2012-12-30 08:00 | 2013-01-08 16:00 | 9 | 464 | 100 | 100 | 0 | 16101 | 16101 | 16101 | 18741.608 | 1 | 0.8591 | TRUE | FALSE | FALSE | 58 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147787 | HCSWB2Z2110 | B2 Z2 :Backfill behind basement walls up to next anchor level | 26106 | 2013-01-30 08:00 | 2013-02-07 16:00 | 8 | 264 | 100 | 88 | -12 | 6512 | 6512 | 5730.56 | 7606.7658 | 0.88 | 0.75335 | TRUE | TRUE | TRUE | 33 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147788 | HCSWB2Z3270 | B2 Z3 :Backfill behind basement walls up to next anchor level | 26107 | 2012-12-24 08:00 | 2012-12-27 16:00 | 3 | 736 | 100 | 99 | -1 | 4692 | 4692 | 4645.08 | 4242.4961 | 0.99 | 1.0949 | FALSE | FALSE | FALSE | 92 | FALSE | 0 | Green | Continue normal monitoring.
147789 | HCSWB2Z4110 | B2 Z4 :Backfill behind basement walls up to next anchor level | 26108 | 2013-01-22 08:00 | 2013-01-27 16:00 | 5 | 528 | 100 | 85 | -15 | 3020 | 3020 | 2567 | 3107.6645 | 0.85 | 0.82602 | TRUE | TRUE | TRUE | 66 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147790 | HCSWB2Z5270 | B2 Z5 :Backfill behind basement walls up slab level | 26109 | 2013-01-21 08:00 | 2013-01-28 16:00 | 7 | 608 | 100 | 97 | -3 | 12012 | 12012 | 11651.64 | 14195.4398 | 0.97 | 0.8208 | TRUE | FALSE | FALSE | 76 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147791 | HCSWB2Z6110 | B2 Z6 :Backfill behind basement walls up slab level | 26124 | 2013-04-01 08:00 | 2013-04-07 16:00 | 6 | 136 | 100 | 85 | -15 | 11544 | 11544 | 9812.4 | 11210.0515 | 0.85 | 0.87532 | TRUE | TRUE | TRUE | 17 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147792 | HCSWB1Z1250 | B1 Z1 :Backfill behind basement walls up to anchor level | 26121 | 2013-01-21 08:00 | 2013-01-30 16:00 | 9 | 464 | 100 | 98 | -2 | 16209 | 16209 | 15884.82 | 16810.3453 | 0.98 | 0.94494 | FALSE | FALSE | FALSE | 58 | FALSE | 0 | Green | Continue normal monitoring.
147793 | HCSWB1Z2090 | B1 Z2 :Backfill behind basement walls up to anchor level | 26122 | 2013-02-20 08:00 | 2013-02-28 16:00 | 8 | 264 | 100 | 100 | 0 | 6824 | 6824 | 6824 | 6545.0182 | 1 | 1.0426 | FALSE | FALSE | FALSE | 33 | FALSE | 0 | Green | Continue normal monitoring.
147794 | HCSWB1Z3250 | B1 Z3 :Backfill behind basement walls up to anchor level | 26123 | 2013-01-28 08:00 | 2013-02-05 16:00 | 8 | 584 | 100 | 91 | -9 | 12120 | 12120 | 11029.2 | 12549.2973 | 0.91 | 0.87887 | TRUE | FALSE | FALSE | 73 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147795 | HCSWB1Z4090 | B1 Z4 :Backfill behind basement walls up to anchor level | 26127 | 2013-03-02 08:00 | 2013-03-10 16:00 | 8 | 352 | 100 | 100 | 0 | 9856 | 9856 | 9856 | 11877.8122 | 1 | 0.82978 | TRUE | FALSE | FALSE | 44 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147796 | HCSWB1Z5250 | B1 Z5 :Backfill behind basement walls up to anchor level | 26125 | 2013-02-11 08:00 | 2013-02-19 16:00 | 8 | 520 | 100 | 90 | -10 | 9664 | 9664 | 8697.6 | 9973.7282 | 0.9 | 0.87205 | TRUE | FALSE | FALSE | 65 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147797 | HCSWB1Z6090 | B1 Z6 :Backfill behind basement walls up to anchor level | 26126 | 2013-04-08 08:00 | 2013-04-16 16:00 | 8 | 136 | 100 | 81 | -19 | 14232 | 14232 | 11527.92 | 15261.8959 | 0.81 | 0.75534 | TRUE | TRUE | TRUE | 17 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147798 | HCSWB1Z6100 | B1 Z6 :De-tensioning | 26126 | 2013-04-17 08:00 | 2013-04-18 16:00 | 1 | 136 | 100 | 94 | -6 | 1150 | 1150 | 1081 | 1163.3291 | 0.94 | 0.92923 | FALSE | FALSE | FALSE | 17 | FALSE | 0 | Green | Continue normal monitoring.
147799 | HCSWB1Z1260 | B1 Z1 :De-tensioning | 26121 | 2013-01-31 08:00 | 2013-02-03 16:00 | 3 | 464 | 100 | 91 | -9 | 3969 | 3969 | 3611.79 | 4104.132 | 0.91 | 0.88004 | TRUE | FALSE | FALSE | 58 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147800 | HCSWB1Z2100 | B1 Z2 :De-tensioning | 26122 | 2013-03-02 08:00 | 2013-03-04 16:00 | 2 | 264 | 100 | 91 | -9 | 2892 | 2892 | 2631.72 | 2475.7535 | 0.91 | 1.063 | FALSE | FALSE | FALSE | 33 | FALSE | 0 | Green | Continue normal monitoring.
147801 | HCSWB1Z3260 | B1 Z3 :De-tensioning | 26123 | 2013-02-06 08:00 | 2013-02-07 16:00 | 1 | 584 | 100 | 88 | -12 | 1160 | 1160 | 1020.8 | 1117.6579 | 0.88 | 0.91334 | FALSE | TRUE | TRUE | 73 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147802 | HCSWB1Z4100 | B1 Z4 :De-tensioning | 26127 | 2013-03-11 08:00 | 2013-03-12 16:00 | 1 | 352 | 100 | 100 | 0 | 598 | 598 | 598 | 612.7303 | 1 | 0.97596 | FALSE | FALSE | FALSE | 44 | FALSE | 0 | Green | Continue normal monitoring.
147803 | HCSWB1Z5260 | B1 Z5 :De-tensioning | 26125 | 2013-02-20 08:00 | 2013-02-21 16:00 | 1 | 520 | 100 | 100 | 0 | 1087 | 1087 | 1087 | 1199.5249 | 1 | 0.90619 | FALSE | FALSE | FALSE | 65 | FALSE | 0 | Green | Continue normal monitoring.
147804 | HCSWB1Z1270 | B1 Z1 :Backfill behind basement walls up next anchor level | 26121 | 2013-02-04 08:00 | 2013-02-11 16:00 | 7 | 464 | 100 | 81 | -19 | 5467 | 5467 | 4428.27 | 5631.1236 | 0.81 | 0.78639 | TRUE | TRUE | TRUE | 58 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147805 | HCSWB1Z2110 | B1 Z2 :Backfill behind basement walls up to next anchor level | 26122 | 2013-03-05 08:00 | 2013-03-12 16:00 | 7 | 264 | 100 | 100 | 0 | 6314 | 6314 | 6314 | 6220.0907 | 1 | 1.0151 | FALSE | FALSE | FALSE | 33 | FALSE | 0 | Green | Continue normal monitoring.
147806 | HCSWB1Z3270 | B1 Z3 :Backfill behind basement walls up to next anchor level | 26123 | 2013-02-09 08:00 | 2013-02-12 16:00 | 3 | 584 | 100 | 82 | -18 | 4896 | 4896 | 4014.72 | 4921.6526 | 0.82 | 0.81573 | TRUE | TRUE | TRUE | 73 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147807 | HCSWB1Z4110 | B1 Z4 :Backfill behind basement walls up to next anchor level | 26127 | 2013-03-13 08:00 | 2013-03-17 16:00 | 4 | 352 | 100 | 91 | -9 | 4796 | 4796 | 4364.36 | 4541.4155 | 0.91 | 0.96101 | FALSE | FALSE | FALSE | 44 | FALSE | 0 | Green | Continue normal monitoring.
147808 | HCSWB1Z5270 | B1 Z5 :Backfill behind basement walls up to next anchor level | 26125 | 2013-02-23 08:00 | 2013-02-28 16:00 | 5 | 520 | 100 | 100 | 0 | 3490 | 3490 | 3490 | 4257.094 | 1 | 0.81981 | TRUE | FALSE | FALSE | 65 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147809 | HCSWB1Z6110 | B1 Z6 :Backfill behind basement walls up to next anchor level | 26126 | 2013-04-20 08:00 | 2013-04-25 16:00 | 5 | 136 | 100 | 100 | 0 | 9130 | 9130 | 9130 | 9665.9063 | 1 | 0.94456 | FALSE | FALSE | FALSE | 17 | FALSE | 0 | Green | Continue normal monitoring.
147810 | HCSWB2Z1280 | B2 Z1 :De-tensioning | 26105 | 2013-01-09 08:00 | 2013-01-12 16:00 | 3 | 464 | 100 | 100 | 0 | 2478 | 2478 | 2478 | 2119.5915 | 1 | 1.1691 | FALSE | FALSE | FALSE | 58 | FALSE | 0 | Green | Continue normal monitoring.
147811 | HCSWB2Z1290 | B2 Z1 :Backfill behind basement walls up slab level | 26105 | 2013-01-13 08:00 | 2013-01-20 16:00 | 7 | 464 | 100 | 95 | -5 | 4571 | 4571 | 4342.45 | 3920.9055 | 0.95 | 1.1075 | FALSE | FALSE | FALSE | 58 | FALSE | 0 | Green | Continue normal monitoring.
147812 | HCSWB1Z1280 | B1 Z1 :De-tensioning | 26121 | 2013-02-12 08:00 | 2013-02-14 16:00 | 2 | 464 | 100 | 100 | 0 | 2102 | 2102 | 2102 | 2604.7661 | 1 | 0.80698 | TRUE | FALSE | FALSE | 58 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147813 | HCSWB1Z1290 | B1 Z1 :Backfill behind basement walls up next anchor level | 26121 | 2013-02-16 08:00 | 2013-02-24 16:00 | 8 | 464 | 100 | 100 | 0 | 7232 | 7232 | 7232 | 6787.8131 | 1 | 1.0654 | FALSE | FALSE | FALSE | 58 | FALSE | 0 | Green | Continue normal monitoring.
147814 | HCSWB1Z1300 | B1 Z1 :De-tensioning | 26121 | 2013-02-25 08:00 | 2013-02-27 16:00 | 2 | 464 | 100 | 100 | 0 | 1922 | 1922 | 1922 | 2253.0517 | 1 | 0.85307 | TRUE | FALSE | FALSE | 58 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147815 | HCSWB1Z1310 | B1 Z1 :Backfill behind basement walls up slab level | 26121 | 2013-02-28 08:00 | 2013-03-07 16:00 | 7 | 464 | 100 | 100 | 0 | 4417 | 4417 | 4417 | 3857.4108 | 1 | 1.1451 | FALSE | FALSE | FALSE | 58 | FALSE | 0 | Green | Continue normal monitoring.
147816 | HCSWB2Z2120 | B2 Z2 :De-tensioning | 26106 | 2013-02-09 08:00 | 2013-02-11 16:00 | 2 | 264 | 100 | 100 | 0 | 2580 | 2580 | 2580 | 3143.6399 | 1 | 0.8207 | TRUE | FALSE | FALSE | 33 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147817 | HCSWB2Z2130 | B2 Z2 :Backfill behind basement walls up slab level | 26106 | 2013-02-12 08:00 | 2013-02-19 16:00 | 7 | 264 | 100 | 80 | -20 | 9611 | 9611 | 7688.8 | 11530.9587 | 0.8 | 0.6668 | TRUE | TRUE | TRUE | 33 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147818 | HCSWB1Z2120 | B1 Z2 :De-tensioning | 26122 | 2013-03-13 08:00 | 2013-03-16 16:00 | 3 | 264 | 100 | 100 | 0 | 1749 | 1749 | 1749 | 1886.1868 | 1 | 0.92727 | FALSE | FALSE | FALSE | 33 | FALSE | 0 | Green | Continue normal monitoring.
147819 | HCSWB1Z2130 | B1 Z2 :Backfill behind basement walls up to next anchor level | 26122 | 2013-03-17 08:00 | 2013-03-25 16:00 | 8 | 264 | 100 | 82 | -18 | 15376 | 15376 | 12608.32 | 13124.9453 | 0.82 | 0.96064 | FALSE | TRUE | TRUE | 33 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147820 | HCSWB1Z2140 | B1 Z2 :De-tensioning | 26122 | 2013-03-26 08:00 | 2013-03-28 16:00 | 2 | 264 | 100 | 99 | -1 | 2506 | 2506 | 2480.94 | 2388.5296 | 0.99 | 1.0387 | FALSE | FALSE | FALSE | 33 | FALSE | 0 | Green | Continue normal monitoring.
147821 | HCSWB1Z2250 | B1 Z2 :Backfill behind basement walls up slab level | 26122 | 2013-03-30 08:00 | 2013-04-06 16:00 | 7 | 264 | 100 | 81 | -19 | 7889 | 7889 | 6390.09 | 7989.4195 | 0.81 | 0.79982 | TRUE | TRUE | TRUE | 33 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147822 | HCSWB2Z3280 | B2 Z3 :De-tensioning | 26107 | 2012-12-29 08:00 | 2012-12-29 16:00 | 1 | 736 | 100 | 88 | -12 | 1632 | 1632 | 1436.16 | 1687.5299 | 0.88 | 0.85104 | TRUE | TRUE | TRUE | 92 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147823 | HCSWB2Z3290 | B2 Z3 :Backfill behind basement walls up slab level | 26107 | 2012-12-30 08:00 | 2013-01-03 16:00 | 4 | 736 | 100 | 98 | -2 | 2880 | 2880 | 2822.4 | 2790.9259 | 0.98 | 1.0113 | FALSE | FALSE | FALSE | 92 | FALSE | 0 | Green | Continue normal monitoring.
147824 | HCSWB1Z3280 | B1 Z3 :De-tensioning | 26123 | 2013-02-13 08:00 | 2013-02-13 16:00 | 1 | 584 | 100 | 94 | -6 | 1052 | 1052 | 988.88 | 908.0645 | 0.94 | 1.089 | FALSE | FALSE | FALSE | 73 | FALSE | 0 | Green | Continue normal monitoring.
147825 | HCSWB1Z3290 | B1 Z3 :Backfill behind basement walls up slab level | 26123 | 2013-02-14 08:00 | 2013-02-18 16:00 | 4 | 584 | 100 | 97 | -3 | 7564 | 7564 | 7337.08 | 8214.8895 | 0.97 | 0.89314 | TRUE | FALSE | FALSE | 73 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147826 | HCSWB2Z4120 | B2 Z4 :De-tensioning | 26108 | 2013-01-28 08:00 | 2013-01-29 16:00 | 1 | 528 | 100 | 100 | 0 | 1670 | 1670 | 1670 | 1769.6353 | 1 | 0.9437 | FALSE | FALSE | FALSE | 66 | FALSE | 0 | Green | Continue normal monitoring.
147827 | HCSWB2Z4130 | B2 Z4 :Backfill behind basement walls up slab level | 26108 | 2013-01-30 08:00 | 2013-02-03 16:00 | 4 | 528 | 100 | 90 | -10 | 2444 | 2444 | 2199.6 | 2354.0614 | 0.9 | 0.93439 | FALSE | FALSE | TRUE | 66 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147828 | HCSWB1Z4120 | B1 Z4 :De-tensioning | 26127 | 2013-03-18 08:00 | 2013-03-19 16:00 | 1 | 352 | 100 | 100 | 0 | 1114 | 1114 | 1114 | 963.8221 | 1 | 1.1558 | FALSE | FALSE | FALSE | 44 | FALSE | 0 | Green | Continue normal monitoring.
147829 | HCSWB1Z4130 | B1 Z4 :Backfill behind basement walls up slab level | 26127 | 2013-03-20 08:00 | 2013-03-24 16:00 | 4 | 352 | 100 | 100 | 0 | 5692 | 5692 | 5692 | 7102.692 | 1 | 0.80139 | TRUE | FALSE | FALSE | 44 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147830 | HCSWB1Z5280 | B1 Z5 :De-tensioning | 26125 | 2013-03-02 08:00 | 2013-03-03 16:00 | 1 | 520 | 100 | 95 | -5 | 974 | 974 | 925.3 | 1015.6818 | 0.95 | 0.91101 | FALSE | FALSE | FALSE | 65 | FALSE | 0 | Green | Continue normal monitoring.
147831 | HCSWB1Z5290 | B1 Z5 :Backfill behind basement walls up slab level | 26125 | 2013-03-04 08:00 | 2013-03-10 16:00 | 6 | 520 | 100 | 100 | 0 | 8010 | 8010 | 8010 | 9230.7376 | 1 | 0.86775 | TRUE | FALSE | FALSE | 65 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147832 | HCSWB1Z6120 | B1 Z6 :De-tensioning | 26126 | 2013-04-27 08:00 | 2013-04-28 16:00 | 1 | 136 | 100 | 96 | -4 | 770 | 770 | 739.2 | 793.8127 | 0.96 | 0.9312 | FALSE | FALSE | FALSE | 17 | FALSE | 0 | Green | Continue normal monitoring.
147833 | HCSWB1Z6130 | B1 Z6 :Backfill behind basement walls up slab level | 26126 | 2013-04-29 08:00 | 2013-05-06 16:00 | 7 | 136 | 100 | 84 | -16 | 6440 | 6440 | 5409.6 | 5585.2067 | 0.84 | 0.96856 | FALSE | TRUE | TRUE | 17 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147834 | HCSWGFZ1100 | GF Z1 :Fire Proofing | 25954 | 2013-02-13 08:00 | 2013-02-19 16:00 | 6 | 1232 | 100 | 91 | -9 | 7236 | 7236 | 6584.76 | 7046.7084 | 0.91 | 0.93444 | FALSE | FALSE | FALSE | 154 | FALSE | 0 | Green | Continue normal monitoring.
147835 | HCSWGFZ2100 | GF Z2 :Fire Proofing | 25957 | 2013-04-20 08:00 | 2013-04-25 16:00 | 5 | 744 | 100 | 90 | -10 | 9450 | 9450 | 8505 | 9242.5163 | 0.9 | 0.9202 | FALSE | FALSE | FALSE | 93 | FALSE | 0 | Green | Continue normal monitoring.
147836 | HCSSGFZ3100 | GF Z3 :Fire Proofing | 25960 | 2013-06-17 08:00 | 2013-06-23 16:00 | 6 | 360 | 100 | 100 | 0 | 10818 | 10818 | 10818 | 12823.0207 | 1 | 0.84364 | TRUE | FALSE | FALSE | 45 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147837 | HCSWFFZ1100 | FF Z1 :Fire Proofing | 25885 | 2013-03-02 08:00 | 2013-03-07 16:00 | 5 | 1168 | 100 | 94 | -6 | 9030 | 9030 | 8488.2 | 10038.5787 | 0.94 | 0.84556 | TRUE | FALSE | FALSE | 146 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147838 | HCSWFFZ2100 | Fire Proofing | 25895 | 2013-04-27 08:00 | 2013-05-04 16:00 | 7 | 744 | 100 | 100 | 0 | 3773 | 3773 | 3773 | 3622.7288 | 1 | 1.0415 | FALSE | FALSE | FALSE | 93 | FALSE | 0 | Green | Continue normal monitoring.
147839 | HCSWFFZ3100 | Fire Proofing | 25898 | 2013-06-24 08:00 | 2013-06-30 16:00 | 6 | 360 | 100 | 82 | -18 | 4128 | 4128 | 3384.96 | 5106.7322 | 0.82 | 0.66284 | TRUE | TRUE | TRUE | 45 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147840 | HCSW2FZ1100 | Fire Proofing | 25884 | 2013-03-09 08:00 | 2013-03-09 16:00 | 1 | 1168 | 100 | 80 | -20 | 1687 | 1687 | 1349.6 | 1650.9264 | 0.8 | 0.81748 | TRUE | TRUE | TRUE | 146 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147841 | HCSW2FZ2100 | Fire Proofing | 25882 | 2013-05-05 08:00 | 2013-05-11 16:00 | 6 | 744 | 100 | 99 | -1 | 8958 | 8958 | 8868.42 | 11191.1722 | 0.99 | 0.79245 | TRUE | FALSE | FALSE | 93 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147842 | HCSW2FZ3100 | Fire Proofing | 25968 | 2013-07-01 08:00 | 2013-07-07 16:00 | 6 | 360 | 100 | 100 | 0 | 6210 | 6210 | 6210 | 7752.9706 | 1 | 0.80098 | TRUE | FALSE | FALSE | 45 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147843 | HCSW3FZ1100 | Fire Proofing | 25869 | 2013-03-16 08:00 | 2013-03-21 16:00 | 5 | 1128 | 100 | 95 | -5 | 7635 | 7635 | 7253.25 | 7073.7069 | 0.95 | 1.0254 | FALSE | FALSE | FALSE | 141 | FALSE | 0 | Green | Continue normal monitoring.
147844 | HCSW3FZ2100 | Fire Proofing | 25913 | 2013-05-12 08:00 | 2013-05-18 16:00 | 6 | 744 | 100 | 81 | -19 | 4734 | 4734 | 3834.54 | 4616.1066 | 0.81 | 0.83069 | TRUE | TRUE | TRUE | 93 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147845 | HCSW3FZ3100 | Fire Proofing | 25977 | 2013-07-08 08:00 | 2013-07-14 16:00 | 6 | 360 | 100 | 81 | -19 | 5592 | 5592 | 4529.52 | 5840.3837 | 0.81 | 0.77555 | TRUE | TRUE | TRUE | 45 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147846 | HCSW4FZ1100 | Fire Proofing | 25980 | 2013-03-23 08:00 | 2013-03-28 16:00 | 5 | 1128 | 100 | 82 | -18 | 4850 | 4850 | 3977 | 5410.8553 | 0.82 | 0.735 | TRUE | TRUE | TRUE | 141 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147847 | HCSW4FZ2100 | Fire Proofing | 25881 | 2013-05-19 08:00 | 2013-05-26 16:00 | 7 | 744 | 100 | 87 | -13 | 11928 | 11928 | 10377.36 | 12658.22 | 0.87 | 0.81981 | TRUE | TRUE | TRUE | 93 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147848 | HCSW4FZ3100 | Fire Proofing | 25993 | 2013-07-15 08:00 | 2013-07-21 16:00 | 6 | 360 | 100 | 100 | 0 | 10626 | 10626 | 10626 | 13152.614 | 1 | 0.8079 | TRUE | FALSE | FALSE | 45 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147849 | HCSW4FZ4100 | Fire Proofing | 25925 | 2013-08-21 08:00 | 2013-08-27 16:00 | 6 | 128 | 100 | 100 | 0 | 6762 | 6762 | 6762 | 7705.9459 | 1 | 0.8775 | TRUE | FALSE | FALSE | 16 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147850 | HCSW4FZ5100 | Fire Proofing | 25888 | 2013-08-20 08:00 | 2013-08-26 16:00 | 6 | 136 | 100 | 94 | -6 | 4668 | 4668 | 4387.92 | 4363.7301 | 0.94 | 1.0055 | FALSE | FALSE | FALSE | 17 | FALSE | 0 | Green | Continue normal monitoring.
147851 | HCSW5FZ1100 | Fire Proofing | 25928 | 2013-03-30 08:00 | 2013-04-04 16:00 | 5 | 1128 | 100 | 86 | -14 | 6880 | 6880 | 5916.8 | 6137.2285 | 0.86 | 0.96408 | FALSE | TRUE | TRUE | 141 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147852 | HCSW5FZ2100 | Fire Proofing | 25894 | 2013-05-27 08:00 | 2013-06-02 16:00 | 6 | 744 | 100 | 85 | -15 | 6480 | 6480 | 5508 | 7292.3361 | 0.85 | 0.75531 | TRUE | TRUE | TRUE | 93 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147853 | HCSW5FZ3100 | Fire Proofing | 25897 | 2013-07-23 08:00 | 2013-07-29 16:00 | 6 | 352 | 100 | 88 | -12 | 8172 | 8172 | 7191.36 | 7464.1493 | 0.88 | 0.96345 | FALSE | TRUE | TRUE | 44 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147854 | HCSW5FZ4100 | Fire Proofing | 25899 | 2013-09-01 08:00 | 2013-09-07 16:00 | 6 | 104 | 100 | 99 | -1 | 4518 | 4518 | 4472.82 | 5263.7896 | 0.99 | 0.84973 | TRUE | FALSE | FALSE | 13 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147855 | HCSW5FZ5100 | Fire Proofing | 25901 | 2013-08-27 08:00 | 2013-09-02 16:00 | 6 | 136 | 100 | 100 | 0 | 4080 | 4080 | 4080 | 3975.6118 | 1 | 1.0263 | FALSE | FALSE | FALSE | 17 | FALSE | 0 | Green | Continue normal monitoring.
147856 | HCSW6FZ1100 | Fire Proofing | 25904 | 2013-04-06 08:00 | 2013-04-11 16:00 | 5 | 1128 | 100 | 80 | -20 | 5900 | 5900 | 4720 | 5786.4681 | 0.8 | 0.8157 | TRUE | TRUE | TRUE | 141 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147857 | HCSW6FZ2100 | Fire Proofing | 26029 | 2013-06-03 08:00 | 2013-06-09 16:00 | 6 | 744 | 100 | 87 | -13 | 7944 | 7944 | 6911.28 | 6786.713 | 0.87 | 1.0184 | FALSE | TRUE | TRUE | 93 | FALSE | 2 | Yellow | Increase monitoring frequency and investigate performance trends.
147858 | HCSW6FZ3100 | Fire Proofing | 26016 | 2013-08-01 08:00 | 2013-08-07 16:00 | 6 | 336 | 100 | 100 | 0 | 7194 | 7194 | 7194 | 8132.13 | 1 | 0.88464 | TRUE | FALSE | FALSE | 42 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147859 | HCSW6FZ4100 | Fire Proofing | 25943 | 2013-09-11 08:00 | 2013-09-17 16:00 | 6 | 80 | 100 | 100 | 0 | 6390 | 6390 | 6390 | 5721.0175 | 1 | 1.1169 | FALSE | FALSE | FALSE | 10 | FALSE | 0 | Green | Continue normal monitoring.
147860 | HCSW6FZ5100 | Fire Proofing | 25911 | 2013-09-03 08:00 | 2013-09-09 16:00 | 6 | 136 | 100 | 100 | 0 | 11094 | 11094 | 11094 | 12859.6349 | 1 | 0.8627 | TRUE | FALSE | FALSE | 17 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.
147861 | HCSW7FZ1100 | Fire Proofing | 26023 | 2013-04-13 08:00 | 2013-04-18 16:00 | 5 | 1128 | 100 | 82 | -18 | 9400 | 9400 | 7708 | 9839.423 | 0.82 | 0.78338 | TRUE | TRUE | TRUE | 141 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147862 | HCSW7FZ2100 | Fire Proofing | 25951 | 2013-06-10 08:00 | 2013-06-16 16:00 | 6 | 744 | 100 | 83 | -17 | 7074 | 7074 | 5871.42 | 8232.0982 | 0.83 | 0.71323 | TRUE | TRUE | TRUE | 93 | FALSE | 3 | Orange | Develop recovery plan and review schedule and cost exposure.
147863 | HCSW7FZ3100 | Fire Proofing | 25920 | 2013-08-12 08:00 | 2013-08-18 16:00 | 6 | 336 | 100 | 100 | 0 | 5340 | 5340 | 5340 | 5786.2671 | 1 | 0.92287 | FALSE | FALSE | FALSE | 42 | FALSE | 0 | Green | Continue normal monitoring.
147864 | HCSW7FZ4100 | Fire Proofing | 26030 | 2013-09-18 08:00 | 2013-09-24 16:00 | 6 | 80 | 100 | 100 | 0 | 9648 | 9648 | 9648 | 8518.9265 | 1 | 1.1325 | FALSE | FALSE | FALSE | 10 | FALSE | 0 | Green | Continue normal monitoring.
147865 | HCSW7FZ5100 | Fire Proofing | 25923 | 2013-09-10 08:00 | 2013-09-16 16:00 | 6 | 136 | 100 | 94 | -6 | 11040 | 11040 | 10377.6 | 12765.1207 | 0.94 | 0.81297 | TRUE | FALSE | FALSE | 17 | FALSE | 1 | Yellow | Increase monitoring frequency and investigate performance trends.