## Executive_KPIs
KPI | Value
Total Delay Events | 30
Total Delay Days | 373
Potential EOT Cases | 8
Potential Exceptional Event Cases | 6

## Claims_Intelligence
delay_id | task_code | task_name | delay_event | delay_days | delay_type | potential_eot | notice_issued | evidence_available
D001 | HCMEF2Z3340 | F2 Z3 :Duct Insulation Work | Severe rainfall | 19 | Third Party | Requires Review | No | Yes
D002 | HCSWB1Z3240 | B1 Z3 :Cure and De-shutter slab formwork | Subcontractor delay | 8 | Third Party | Requires Review | Yes | No
D003 | HCFWF6Z2238 | F6 Z4 :Steel Fire Rated Doors | Subcontractor delay | 8 | Exceptional Event | Potential | No | Yes
D004 | HCMEF1Z2230 | F1 Z2 :Cable Tray Installation | Late drawing approval | 11 | Employer | Yes | No | No
D005 | HCSWSSZ6325 | SS Z6 :Fill imported base course under SOG | Equipment breakdown | 16 | Contractor | No | Yes | No
D006 | HCMEF5Z1320 | F5 Z1 :Plastering Finish Date for All Parts | Site access restriction | 14 | Contractor | No | Yes | Yes
D007 | HCFWF4Z2110 | F4 Z2 :Plaster Second Layer | Site access restriction | 4 | Employer | Yes | Yes | No
D008 | HCSWB3Z3140 | B3 Z3 :De-shutter core wall formwork | Utility relocation delay | 8 | Third Party | Requires Review | No | No
D009 | HEMSSME1200 | MS submission: Stand by Generator | Delayed material delivery | 16 | Contractor | No | No | Yes
D010 | HCSWB2Z3150 | B2 Z3 :Fix Steel Rebar for columns | Late drawing approval | 17 | Exceptional Event | Potential | Yes | No
D011 | HCSWB4Z1030 | B4 Z1 :Fix MEP first fix in walls | Utility relocation delay | 4 | Unknown | Requires Review | Yes | Yes
D012 | HCMEPSSWW010 | SPS :Installation for Window Washing system | Subcontractor delay | 13 | Employer | Yes | No | Yes
D013 | HCFWF5Z1151 | F5 Z1 :Foam Concrete Under Floorings | Subcontractor delay | 16 | Employer | Yes | No | No
D014 | HCMEB3Z2300 | B3 Z2 :Duct Installation& Dusct Accecories Installation, Fan coil Unit | Subcontractor delay | 16 | Contractor | No | No | No
D015 | HCFWF1Z2028 | F1 Z2 :Paint putty coat | Late drawing approval | 19 | Employer | Yes | No | No
D016 | HCFWGFZ3032 | GF Z3 :Mirror | Subcontractor delay | 15 | Exceptional Event | Potential | Yes | Yes
D017 | HCFWF7AZ080 | F7 :Paint putty coat | Late drawing approval | 19 | Exceptional Event | Potential | Yes | Yes
D018 | HCMEB4Z2345 | B4 Z2 :All Vertical Piping Works | Utility relocation delay | 10 | Contractor | No | Yes | No
D019 | HCFWB3Z1014 | B3 Z1 :Plaster Second Layer | Severe rainfall | 16 | Exceptional Event | Potential | No | Yes
D020 | HCSWB1Z4010 | B1 Z4 :Formwork retaining walls shutters - 1st side | Severe rainfall | 12 | Employer | Yes | Yes | No
D021 | HCFWB1Z6017 | B1 Z6 :B1 Z6 :Plaster First Layer | Severe rainfall | 19 | Employer | Yes | No | Yes
D022 | HCFWB4Z2012 | B4 Z2 :Paint Final Layer | Subcontractor delay | 5 | Employer | Yes | Yes | Yes
D023 | HCSWSSZ2225 | SS Z2 :Fill imported base course around Foundations P2 & under SOG | Subcontractor delay | 10 | Third Party | Requires Review | No | No
D024 | HCFWB1Z4009 | B1 Z4 :Plaster First Layer | Utility relocation delay | 4 | Exceptional Event | Potential | Yes | Yes
D025 | HCFWF4Z2115 | F4 Z2 :Plaster First Layer | Delayed material delivery | 5 | Unknown | Requires Review | Yes | No
D026 | HCMEF3Z3245 | F3 Z3 :Cable Tray Installation | Site access restriction | 3 | Contractor | No | Yes | Yes
D027 | HCFWF7AZ020 | F7 :Plaster First Layer | Delayed material delivery | 15 | Contractor | No | Yes | No
D028 | HCMEF3Z2090 | F3 Z2 :Mechanical Final Fix | Design change instruction | 15 | Contractor | No | No | Yes
D029 | HCSWB2Z4240 | B2 Z4 :Cure and De-shutter slab formwork | Utility relocation delay | 16 | Contractor | No | Yes | Yes
D030 | HCFWF6Z1175 | F6 Z1 :Stone Cladding | Equipment breakdown | 20 | Third Party | Requires Review | No | Yes