## PROJECT_SUMMARY
Update_ID | Project_ID | Project_Name | Data_Date | Planned_Start | Forecast_Finish | Total_Activities | Completed | In_Progress | Not_Started | Critical_Activities | Relationships | BAC | PV | EV | AC | CPI | SPI | CV | SV | QA_Status | QA_Errors | QA_Warnings | EAC_Budget_Rate | EAC_CPI_Based | EAC_CPI_SPI | Primary_EAC | Primary_ETC | Primary_VAC | Primary_VAC_Percent | Negative_Float_Activities | Low_Float_Activities | Stage2_QA_Status
Update 02 | DC-HYP-FINAL-6 | Hyperscale Data Center Development | 2026-02-28 | 2026-01-05 | 2027-07-19 16:00 | 808 | 62 | 58 | 688 | 89 | 1406 | 120000000 | 13314904.3115 | 13018484.6697 | 13366568.9244 | 0.97396 | 0.97774 | -348084.2547 | -296419.6418 | WARNING | 0 | 2 | 120348084.2547 | 123208523.2362 | 126013874.8001 | 123208523.2362 | 109841954.3118 | -3208523.2362 | -0.026738 | 0 | 140 | PASS

## WBS_PERFORMANCE
Update_ID | Data_Date | Level1_WBS | Activities | Completed | In_Progress | Not_Started | Critical_Activities | BAC | PV | EV | AC | CV | SV | CPI | SPI
Update 02 | 2026-02-28 | Building Envelope | 47 | 0 | 0 | 47 | 0 | 4800000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | Civil & Structural Works | 67 | 0 | 0 | 67 | 0 | 12000000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | Client Acceptance & Handover | 42 | 1 | 0 | 41 | 14 | 1200000 | 29000 | 29000 | 30141.2916 | -1141.2916 | 0 | 0.96214 | 1
Update 02 | 2026-02-28 | Controls, BMS & DCIM | 56 | 0 | 0 | 56 | 0 | 3600000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | Design & Engineering | 78 | 19 | 36 | 23 | 7 | 7200000 | 5455002.2199 | 5303854.4495 | 5466210.6939 | -162356.2444 | -151147.7704 | 0.9703 | 0.97229
Update 02 | 2026-02-28 | Electrical Systems | 86 | 0 | 0 | 86 | 15 | 16800000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | Enabling & Site Works | 55 | 9 | 8 | 38 | 0 | 4800000 | 1284961.039 | 1276007.4573 | 1302631.0354 | -26623.5781 | -8953.5817 | 0.97956 | 0.99303
Update 02 | 2026-02-28 | Fire & Life Safety | 61 | 0 | 0 | 61 | 0 | 3600000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | Mechanical & Cooling Systems | 85 | 0 | 0 | 85 | 0 | 13200000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | Procurement | 80 | 6 | 10 | 64 | 6 | 42000000 | 1480941.0526 | 1407592.8468 | 1457556.4566 | -49963.6098 | -73348.2058 | 0.96572 | 0.95047
Update 02 | 2026-02-28 | Project Management & Controls | 23 | 21 | 2 | 0 | 0 | 4800000 | 4800000 | 4752015.1218 | 4851352.4575 | -99337.3357 | -47984.8782 | 0.97952 | 0.99
Update 02 | 2026-02-28 | Testing & Commissioning | 77 | 6 | 2 | 69 | 24 | 2400000 | 265000 | 250014.7943 | 258676.9894 | -8662.1951 | -14985.2057 | 0.96651 | 0.94345
Update 02 | 2026-02-28 | Utility Connection & Energization | 51 | 0 | 0 | 51 | 23 | 3600000 | 0 | 0 | 0 | 0 | 0

## ACTIVITY_STATUS
Update_ID | Data_Date | Activity_ID | Activity_Name | Level1_WBS | Activity_WBS | Status | Planned_Start | Planned_Finish | Actual_Start | Actual_Finish | Original_Duration_Days | Remaining_Duration_Days | Total_Float_Days | Is_Critical | Float_Path | Float_Path_Order | BAC | PV | EV | AC | CV | SV | CPI | SPI
Update 02 | 2026-02-28 | PM-001 | Notice to Proceed | Project Management & Controls | Project Management | Completed | 2026-02-02 08:00 | 2026-02-02 08:00 | 2026-01-05 | 2026-01-05 | 0 | 0 |  | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | PM-010 | Project Kick-Off Meeting | Project Management & Controls | Project Management | Completed | 2026-01-05 08:00 | 2026-01-05 16:00 | 2026-01-05 08:00 | 2026-01-05 16:00 | 1 | 0 |  | No |  |  | 80000 | 80000 | 80000 | 80729.9406 | -729.9406 | 0 | 0.99096 | 1
Update 02 | 2026-02-28 | PM-020 | Establish Project Organization | Project Management & Controls | Project Management | Completed | 2026-01-06 08:00 | 2026-01-12 16:00 | 2026-01-06 08:00 | 2026-01-12 16:00 | 5 | 0 |  | No |  |  | 293000 | 293000 | 293000 | 299727.3389 | -6727.3389 | 0 | 0.97756 | 1
Update 02 | 2026-02-28 | PM-030 | Establish Project Management Procedures | Project Management & Controls | Project Management | Completed | 2026-01-06 08:00 | 2026-01-19 16:00 | 2026-01-06 08:00 | 2026-01-19 16:00 | 10 | 0 |  | No |  |  | 361000 | 361000 | 361000 | 363053.4606 | -2053.4606 | 0 | 0.99434 | 1
Update 02 | 2026-02-28 | PC-010 | Develop Project Controls Procedures | Project Management & Controls | Project Controls | Completed | 2026-01-05 08:00 | 2026-01-09 16:00 | 2026-01-05 08:00 | 2026-01-09 16:00 | 5 | 0 |  | No |  |  | 293000 | 293000 | 293000 | 296590.3084 | -3590.3084 | 0 | 0.98789 | 1
Update 02 | 2026-02-28 | PC-020 | Develop Detailed Baseline Programme | Project Management & Controls | Project Controls | Completed | 2026-01-12 08:00 | 2026-01-30 16:00 | 2026-01-12 08:00 | 2026-01-30 16:00 | 15 | 0 |  | No |  |  | 408000 | 408000 | 408000 | 423338.7948 | -15338.7948 | 0 | 0.96377 | 1
Update 02 | 2026-02-28 | PC-030 | Baseline Schedule Review | Project Management & Controls | Project Controls | Completed | 2026-02-02 08:00 | 2026-02-06 16:00 | 2026-02-02 08:00 | 2026-02-06 16:00 | 5 | 0 | 26 | No |  |  | 130000 | 130000 | 130000 | 131122.0676 | -1122.0676 | 0 | 0.99144 | 1
Update 02 | 2026-02-28 | PC-040 | Baseline Schedule Approval | Project Management & Controls | Project Controls | In Progress | 2026-02-09 08:00 | 2026-02-13 16:00 | 2026-02-09 08:00 |  | 5 | 5.9496 | 26 | No |  |  | 195000 | 195000 | 157965.0516 | 165303.5542 | -7338.5026 | -37034.9484 | 0.95561 | 0.81008
Update 02 | 2026-02-28 | PC-050 | Baseline Programme Approved | Project Management & Controls | Project Controls | Completed | 2026-02-13 16:00 | 2026-02-13 16:00 | 2026-02-13 16:00 | 2026-02-13 16:00 | 0 | 0 | 26 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | HSE-010 | Develop Project HSE Plan | Project Management & Controls | HSE Management | Completed | 2026-01-05 08:00 | 2026-01-16 16:00 | 2026-01-05 08:00 | 2026-01-16 16:00 | 10 | 0 |  | No |  |  | 361000 | 361000 | 361000 | 369220.1068 | -8220.1068 | 0 | 0.97774 | 1
Update 02 | 2026-02-28 | HSE-020 | HSE Plan Review | Project Management & Controls | HSE Management | Completed | 2026-01-19 08:00 | 2026-01-23 16:00 | 2026-01-19 08:00 | 2026-01-23 16:00 | 5 | 0 |  | No |  |  | 130000 | 130000 | 130000 | 134146.5298 | -4146.5298 | 0 | 0.96909 | 1
Update 02 | 2026-02-28 | HSE-030 | HSE Plan Approval | Project Management & Controls | HSE Management | Completed | 2026-01-26 08:00 | 2026-01-28 16:00 | 2026-01-26 08:00 | 2026-01-28 16:00 | 3 | 0 |  | No |  |  | 168000 | 168000 | 168000 | 171047.4861 | -3047.4861 | 0 | 0.98218 | 1
Update 02 | 2026-02-28 | QA-010 | Develop Project Quality Plan | Project Management & Controls | Quality Management | Completed | 2026-01-05 08:00 | 2026-01-16 16:00 | 2026-01-05 08:00 | 2026-01-16 16:00 | 10 | 0 |  | No |  |  | 361000 | 361000 | 361000 | 375044.404 | -14044.404 | 0 | 0.96255 | 1
Update 02 | 2026-02-28 | QA-020 | Quality Plan Review | Project Management & Controls | Quality Management | Completed | 2026-01-19 08:00 | 2026-01-23 16:00 | 2026-01-19 08:00 | 2026-01-23 16:00 | 5 | 0 |  | No |  |  | 130000 | 130000 | 130000 | 130902.5407 | -902.5407 | 0 | 0.99311 | 1
Update 02 | 2026-02-28 | QA-030 | Quality Plan Approval | Project Management & Controls | Quality Management | Completed | 2026-01-26 08:00 | 2026-01-28 16:00 | 2026-01-26 08:00 | 2026-01-28 16:00 | 3 | 0 |  | No |  |  | 168000 | 168000 | 168000 | 170512.229 | -2512.229 | 0 | 0.98527 | 1
Update 02 | 2026-02-28 | COM-010 | Establish Contract Administration Procedures | Project Management & Controls | Contract & Commercial Management | Completed | 2026-01-06 08:00 | 2026-01-12 16:00 | 2026-01-06 08:00 | 2026-01-12 16:00 | 5 | 0 |  | No |  |  | 293000 | 293000 | 293000 | 295862.9147 | -2862.9147 | 0 | 0.99032 | 1
Update 02 | 2026-02-28 | COM-020 | Establish Change and Variation Control Procedure | Project Management & Controls | Contract & Commercial Management | Completed | 2026-01-13 08:00 | 2026-01-19 16:00 | 2026-01-13 08:00 | 2026-01-19 16:00 | 5 | 0 |  | No |  |  | 293000 | 293000 | 293000 | 300765.4515 | -7765.4515 | 0 | 0.97418 | 1
Update 02 | 2026-02-28 | COM-030 | Establish Payment and Cost Control Procedure | Project Management & Controls | Contract & Commercial Management | Completed | 2026-01-13 08:00 | 2026-01-19 16:00 | 2026-01-13 08:00 | 2026-01-19 16:00 | 5 | 0 |  | No |  |  | 293000 | 293000 | 293000 | 293343.8221 | -343.8221 | 0 | 0.99883 | 1
Update 02 | 2026-02-28 | COM-040 | Establish Commercial Reporting Procedure | Project Management & Controls | Contract & Commercial Management | Completed | 2026-01-13 08:00 | 2026-01-19 16:00 | 2026-01-13 08:00 | 2026-01-19 16:00 | 5 | 0 |  | No |  |  | 130000 | 130000 | 130000 | 130558.1564 | -558.1564 | 0 | 0.99572 | 1
Update 02 | 2026-02-28 | INT-010 | Develop Stakeholder Register | Project Management & Controls | Stakeholder & Interface Management | Completed | 2026-01-06 08:00 | 2026-01-12 16:00 | 2026-01-06 08:00 | 2026-01-12 16:00 | 5 | 0 |  | No |  |  | 130000 | 130000 | 130000 | 131162.7129 | -1162.7129 | 0 | 0.99114 | 1
Update 02 | 2026-02-28 | INT-020 | Develop Interface Register | Project Management & Controls | Stakeholder & Interface Management | Completed | 2026-01-13 08:00 | 2026-01-26 16:00 | 2026-01-13 08:00 | 2026-01-26 16:00 | 10 | 0 |  | No |  |  | 160000 | 160000 | 160000 | 165325.8827 | -5325.8827 | 0 | 0.96779 | 1
Update 02 | 2026-02-28 | INT-030 | Establish Interface Management Procedure | Project Management & Controls | Stakeholder & Interface Management | In Progress | 2026-01-27 08:00 | 2026-02-02 16:00 | 2026-01-27 08:00 |  | 5 | 0.18686 | 35 | No |  |  | 293000 | 293000 | 282050.0702 | 291925.4469 | -9875.3767 | -10949.9298 | 0.96617 | 0.96263
Update 02 | 2026-02-28 | INT-040 | Establish Communication and Reporting Matrix | Project Management & Controls | Stakeholder & Interface Management | Completed | 2026-01-13 08:00 | 2026-01-19 16:00 | 2026-01-13 08:00 | 2026-01-19 16:00 | 5 | 0 |  | No |  |  | 130000 | 130000 | 130000 | 131669.309 | -1669.309 | 0 | 0.98732 | 1
Update 02 | 2026-02-28 | DM-010 | Establish Design Management Plan | Design & Engineering | Design Management & Coordination | Completed | 2026-01-06 08:00 | 2026-01-12 16:00 | 2026-01-06 08:00 | 2026-01-12 16:00 | 5 | 0 |  | No |  |  | 111000 | 111000 | 111000 | 112144.9454 | -1144.9454 | 0 | 0.98979 | 1
Update 02 | 2026-02-28 | DM-020 | Establish Design Deliverables Register | Design & Engineering | Design Management & Coordination | Completed | 2026-01-08 08:00 | 2026-01-12 16:00 | 2026-01-08 08:00 | 2026-01-12 16:00 | 3 | 0 |  | No |  |  | 16000 | 16000 | 16000 | 16020.8208 | -20.8208 | 0 | 0.9987 | 1
Update 02 | 2026-02-28 | DM-030 | Establish Design Responsibility Matrix | Design & Engineering | Design Management & Coordination | Completed | 2026-01-08 08:00 | 2026-01-12 16:00 | 2026-01-08 08:00 | 2026-01-12 16:00 | 3 | 0 |  | No |  |  | 95000 | 95000 | 95000 | 97632.864 | -2632.864 | 0 | 0.97303 | 1
Update 02 | 2026-02-28 | DM-040 | Develop Design Coordination Schedule | Design & Engineering | Design Management & Coordination | Completed | 2026-01-13 08:00 | 2026-01-19 16:00 | 2026-01-13 08:00 | 2026-01-19 16:00 | 5 | 0 |  | No |  |  | 18000 | 18000 | 18000 | 18464.9779 | -464.9779 | 0 | 0.97482 | 1
Update 02 | 2026-02-28 | DM-050 | Conduct Multidiscipline Design Coordination | Design & Engineering | Design Management & Coordination | In Progress | 2026-01-20 08:00 | 2026-03-16 16:00 | 2026-01-20 08:00 |  | 40 | 12.8485 | 175 | No |  |  | 34000 | 23759.0361 | 23078.7741 | 23910.9503 | -832.1761 | -680.262 | 0.9652 | 0.97137
Update 02 | 2026-02-28 | DM-060 | Design Coordination Complete | Design & Engineering | Design Management & Coordination | Not Started | 2026-04-16 16:00 | 2026-04-16 16:00 |  |  | 0 | 0 | 152 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CIV-010 | Develop Civil and Structural Design Criteria | Design & Engineering | Civil & Structural Design | Completed | 2026-01-13 08:00 | 2026-01-19 16:00 | 2026-01-13 08:00 | 2026-01-20 16:00 | 5 | 0 |  | No |  |  | 111000 | 111000 | 111000 | 113377.7355 | -2377.7355 | 0 | 0.97903 | 1
Update 02 | 2026-02-28 | CIV-020 | Develop Site Grading and Drainage Design | Design & Engineering | Civil & Structural Design | Completed | 2026-01-20 08:00 | 2026-02-02 16:00 | 2026-01-21 08:00 | 2026-02-02 16:00 | 10 | 0 | 89 | No |  |  | 136000 | 136000 | 136000 | 139132.4165 | -3132.4165 | 0 | 0.97749 | 1
Update 02 | 2026-02-28 | CIV-030 | Develop Foundation Design | Design & Engineering | Civil & Structural Design | Completed | 2026-01-20 08:00 | 2026-02-09 16:00 | 2026-01-20 08:00 | 2026-02-09 16:00 | 15 | 0 | 85 | No |  |  | 154000 | 154000 | 154000 | 158355.6244 | -4355.6244 | 0 | 0.97249 | 1
Update 02 | 2026-02-28 | CIV-040 | Develop Main Structural Frame Design | Design & Engineering | Civil & Structural Design | Completed | 2026-01-20 08:00 | 2026-02-16 16:00 | 2026-01-20 08:00 | 2026-02-16 16:00 | 20 | 0 | 12 | No |  |  | 170000 | 170000 | 170000 | 174269.7598 | -4269.7598 | 0 | 0.9755 | 1
Update 02 | 2026-02-28 | CIV-050 | Develop Equipment Foundation and Plinth Design | Design & Engineering | Civil & Structural Design | In Progress | 2026-02-25 08:00 | 2026-03-10 16:00 | 2026-02-25 08:00 |  | 10 | 7.9981 | 64 | No |  |  | 136000 | 27200 | 27225.8327 | 28196.0562 | -970.2235 | 25.8327 | 0.96559 | 1.0009
Update 02 | 2026-02-28 | CIV-060 | Civil and Structural Design Review | Design & Engineering | Civil & Structural Design | Not Started | 2026-03-11 08:00 | 2026-03-17 16:00 |  |  | 5 | 5 | 64 | No |  |  | 18000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CIV-070 | Civil and Structural Design Approved | Design & Engineering | Civil & Structural Design | Not Started | 2026-03-17 16:00 | 2026-03-17 16:00 |  |  | 0 | 0 | 64 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | ARC-010 | Develop Architectural Design Criteria | Design & Engineering | Architectural Design | Completed | 2026-01-13 08:00 | 2026-01-19 16:00 | 2026-01-13 08:00 | 2026-01-21 16:00 | 5 | 0 |  | No |  |  | 111000 | 111000 | 111000 | 114669.8565 | -3669.8565 | 0 | 0.968 | 1
Update 02 | 2026-02-28 | ARC-020 | Develop Data Hall Layout | Design & Engineering | Architectural Design | In Progress | 2026-01-20 08:00 | 2026-02-02 16:00 | 2026-01-20 08:00 |  | 10 | 5 | 17 | No |  |  | 136000 | 136000 | 122400 | 130227.8597 | -7827.8597 | -13600 | 0.93989 | 0.9
Update 02 | 2026-02-28 | ARC-030 | Develop Technical Room Layouts | Design & Engineering | Architectural Design | Completed | 2026-01-20 08:00 | 2026-02-02 16:00 | 2026-01-21 08:00 | 2026-02-02 16:00 | 10 | 0 | 0 | Yes | 1 | 1 | 136000 | 136000 | 136000 | 139008.6147 | -3008.6147 | 0 | 0.97836 | 1
Update 02 | 2026-02-28 | ARC-040 | Develop Building Envelope Design | Design & Engineering | Architectural Design | In Progress | 2026-01-20 08:00 | 2026-02-09 16:00 | 2026-01-20 08:00 |  | 15 | 0.47418 | 101 | No |  |  | 154000 | 154000 | 149131.7243 | 154607.7446 | -5476.0203 | -4868.2757 | 0.96458 | 0.96839
Update 02 | 2026-02-28 | ARC-050 | Develop Internal Partition and Door Layouts | Design & Engineering | Architectural Design | In Progress | 2026-02-05 08:00 | 2026-02-18 16:00 | 2026-02-05 08:00 |  | 10 | 0.11734 | 94 | No |  |  | 136000 | 136000 | 134404.145 | 136782.8753 | -2378.7302 | -1595.855 | 0.98261 | 0.98827
Update 02 | 2026-02-28 | ARC-060 | Architectural Design Review | Design & Engineering | Architectural Design | In Progress | 2026-02-19 08:00 | 2026-02-25 16:00 | 2026-02-19 08:00 |  | 5 | 0.0095845 | 94 | No |  |  | 18000 | 18000 | 17965.4958 | 18292.1352 | -326.6394 | -34.5042 | 0.98214 | 0.99808
Update 02 | 2026-02-28 | ARC-070 | Architectural Design Approved | Design & Engineering | Architectural Design | In Progress | 2026-02-25 16:00 | 2026-02-25 16:00 | 2026-02-25 16:00 |  | 0 | 0 | 94 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | ELE-D-010 | Develop Electrical Design Criteria | Design & Engineering | Electrical Design | Completed | 2026-01-13 08:00 | 2026-01-19 16:00 | 2026-01-13 08:00 | 2026-01-22 16:00 | 5 | 0 |  | No |  |  | 111000 | 111000 | 111000 | 115476.7191 | -4476.7191 | 0 | 0.96123 | 1
Update 02 | 2026-02-28 | ELE-D-020 | Develop Electrical Load Schedule | Design & Engineering | Electrical Design | In Progress | 2026-01-20 08:00 | 2026-02-02 16:00 | 2026-01-21 08:00 |  | 10 | 0.27125 | 0 | Yes |  |  | 79000 | 79000 | 76857.1313 | 78719.5456 | -1862.4143 | -2142.8687 | 0.97634 | 0.97288
Update 02 | 2026-02-28 | ELE-D-030 | Develop MV Distribution Design | Design & Engineering | Electrical Design | In Progress | 2026-02-12 08:00 | 2026-03-04 16:00 | 2026-02-12 08:00 |  | 15 | 3.7427 | 10 | No |  |  | 154000 | 118655.7377 | 115575.0039 | 120098.8752 | -4523.8713 | -3080.7338 | 0.96233 | 0.97404
Update 02 | 2026-02-28 | ELE-D-040 | Develop Transformer Design and Sizing | Design & Engineering | Electrical Design | In Progress | 2026-02-05 08:00 | 2026-02-18 16:00 | 2026-02-05 08:00 |  | 10 | 0.22384 | 20 | No |  |  | 136000 | 136000 | 132955.7251 | 134778.3788 | -1822.6538 | -3044.2749 | 0.98648 | 0.97762
Update 02 | 2026-02-28 | ELE-D-050 | Develop Generator System Design | Design & Engineering | Electrical Design | Completed | 2026-02-05 08:00 | 2026-02-18 16:00 | 2026-02-05 08:00 | 2026-02-18 16:00 | 10 | 0 | 20 | No |  |  | 136000 | 136000 | 136000 | 137850.9884 | -1850.9884 | 0 | 0.98657 | 1
Update 02 | 2026-02-28 | ELE-D-060 | Develop LV Distribution Design | Design & Engineering | Electrical Design | Completed | 2026-02-05 08:00 | 2026-02-25 16:00 | 2026-02-05 08:00 | 2026-02-25 16:00 | 15 | 0 | 0 | Yes | 1 | 2 | 154000 | 154000 | 154000 | 159308.326 | -5308.326 | 0 | 0.96668 | 1
Update 02 | 2026-02-28 | ELE-D-070 | Develop UPS and Battery System Design | Design & Engineering | Electrical Design | In Progress | 2026-02-05 08:00 | 2026-02-25 16:00 | 2026-02-05 08:00 |  | 15 | 9.9299 | 0 | Yes |  |  | 154000 | 154000 | 113653.4741 | 122509.3525 | -8855.8784 | -40346.5259 | 0.92771 | 0.73801
Update 02 | 2026-02-28 | ELE-D-080 | Develop Busway and Data Hall Power Distribution Design | Design & Engineering | Electrical Design | In Progress | 2026-02-26 08:00 | 2026-03-18 16:00 | 2026-02-26 08:00 |  | 15 | 19.9915 | 0 | Yes | 1 | 3 | 154000 | 12622.9508 | 10353.4573 | 11388.204 | -1034.7467 | -2269.4935 | 0.90914 | 0.82021
Update 02 | 2026-02-28 | ELE-D-090 | Develop Earthing and Lightning Protection Design | Design & Engineering | Electrical Design | In Progress | 2026-02-17 08:00 | 2026-03-02 16:00 | 2026-02-17 08:00 |  | 10 | 2.1058 | 12 | No |  |  | 136000 | 108800 | 107360.5082 | 110086.1477 | -2725.6395 | -1439.4918 | 0.97524 | 0.98677
Update 02 | 2026-02-28 | ELE-D-100 | Electrical Design Review | Design & Engineering | Electrical Design | Not Started | 2026-03-19 08:00 | 2026-03-27 16:00 |  |  | 7 | 7 | 0 | Yes | 1 | 4 | 20000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | ELE-D-110 | Electrical Design Approved | Design & Engineering | Electrical Design | Not Started | 2026-03-27 16:00 | 2026-03-27 16:00 |  |  | 0 | 0 | 0 | Yes | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | MEC-D-010 | Develop Mechanical Design Criteria | Design & Engineering | Mechanical & Cooling Design | Completed | 2026-01-13 08:00 | 2026-01-19 16:00 | 2026-01-13 08:00 | 2026-01-21 16:00 | 5 | 0 |  | No |  |  | 111000 | 111000 | 111000 | 114190.4253 | -3190.4253 | 0 | 0.97206 | 1
Update 02 | 2026-02-28 | MEC-D-020 | Develop Cooling Load Calculations | Design & Engineering | Mechanical & Cooling Design | In Progress | 2026-01-20 08:00 | 2026-02-02 16:00 | 2026-01-21 08:00 |  | 10 | 0.18291 | 39 | No |  |  | 136000 | 136000 | 133512.3909 | 138569.3409 | -5056.95 | -2487.6091 | 0.96351 | 0.98171
Update 02 | 2026-02-28 | MEC-D-030 | Develop Cooling Plant Design | Design & Engineering | Mechanical & Cooling Design | In Progress | 2026-02-04 08:00 | 2026-02-24 16:00 | 2026-02-04 08:00 |  | 15 | 5.3143 | 39 | No |  |  | 154000 | 154000 | 140506.4481 | 149160.3706 | -8653.9225 | -13493.5519 | 0.94198 | 0.91238
Update 02 | 2026-02-28 | MEC-D-040 | Develop Chilled Water Distribution Design | Design & Engineering | Mechanical & Cooling Design | In Progress | 2026-02-11 08:00 | 2026-03-03 16:00 | 2026-02-11 08:00 |  | 15 | 2.4818 | 39 | No |  |  | 154000 | 126229.5082 | 128520.6473 | 129668.2063 | -1147.5589 | 2291.1391 | 0.99115 | 1.0182
Update 02 | 2026-02-28 | MEC-D-050 | Develop CRAH CRAC System Design | Design & Engineering | Mechanical & Cooling Design | In Progress | 2026-02-04 08:00 | 2026-02-17 16:00 | 2026-02-04 08:00 |  | 10 | 0.13038 | 44 | No |  |  | 136000 | 136000 | 134226.7899 | 138251.3328 | -4024.543 | -1773.2101 | 0.97089 | 0.98696
Update 02 | 2026-02-28 | MEC-D-060 | Develop Ventilation and Exhaust Design | Design & Engineering | Mechanical & Cooling Design | In Progress | 2026-02-05 08:00 | 2026-02-18 16:00 | 2026-02-05 08:00 |  | 10 | 7.9948 | 43 | No |  |  | 136000 | 136000 | 122470.7852 | 132065.8189 | -9595.0338 | -13529.2148 | 0.92735 | 0.90052
Update 02 | 2026-02-28 | MEC-D-070 | Develop Mechanical Controls Requirements | Design & Engineering | Mechanical & Cooling Design | In Progress | 2026-02-18 08:00 | 2026-03-03 16:00 | 2026-02-18 08:00 |  | 10 | 2.9069 | 39 | No |  |  | 79000 | 57275 | 56035.4199 | 56994.7103 | -959.2904 | -1239.5801 | 0.98317 | 0.97836
Update 02 | 2026-02-28 | MEC-D-080 | Mechanical Design Review | Design & Engineering | Mechanical & Cooling Design | Not Started | 2026-03-04 08:00 | 2026-03-12 16:00 |  |  | 7 | 7 | 39 | No |  |  | 20000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | MEC-D-090 | Mechanical Design Approved | Design & Engineering | Mechanical & Cooling Design | Not Started | 2026-03-12 16:00 | 2026-03-12 16:00 |  |  | 0 | 0 | 39 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | FLS-D-010 | Develop Fire and Life Safety Design Criteria | Design & Engineering | Fire & Life Safety Design | Completed | 2026-01-13 08:00 | 2026-01-19 16:00 | 2026-01-13 08:00 | 2026-01-19 16:00 | 5 | 0 |  | No |  |  | 111000 | 111000 | 111000 | 114779.5872 | -3779.5872 | 0 | 0.96707 | 1
Update 02 | 2026-02-28 | FLS-D-020 | Develop Fire Detection and Alarm Design | Design & Engineering | Fire & Life Safety Design | Completed | 2026-01-20 08:00 | 2026-02-02 16:00 | 2026-01-20 08:00 | 2026-02-02 16:00 | 10 | 0 | 113 | No |  |  | 136000 | 136000 | 136000 | 137543.4412 | -1543.4412 | 0 | 0.98878 | 1
Update 02 | 2026-02-28 | FLS-D-030 | Develop Fire Suppression System Design | Design & Engineering | Fire & Life Safety Design | In Progress | 2026-01-20 08:00 | 2026-02-02 16:00 | 2026-01-20 08:00 |  | 10 | 0.023615 | 113 | No |  |  | 136000 | 136000 | 135678.8401 | 137974.19 | -2295.3498 | -321.1599 | 0.98336 | 0.99764
Update 02 | 2026-02-28 | FLS-D-040 | Develop VESDA and Early Warning Detection Design | Design & Engineering | Fire & Life Safety Design | In Progress | 2026-01-20 08:00 | 2026-01-29 16:00 | 2026-01-21 08:00 |  | 8 | 0.27947 | 112 | No |  |  | 127000 | 127000 | 122563.4657 | 125496.0196 | -2932.5538 | -4436.5343 | 0.97663 | 0.96507
Update 02 | 2026-02-28 | FLS-D-050 | Develop Fire System Interface Matrix | Design & Engineering | Fire & Life Safety Design | In Progress | 2026-01-27 08:00 | 2026-02-02 16:00 | 2026-01-27 08:00 |  | 5 | 3.906 | 112 | No |  |  | 65000 | 65000 | 53221.8806 | 58571.0936 | -5349.213 | -11778.1194 | 0.90867 | 0.8188
Update 02 | 2026-02-28 | FLS-D-060 | Fire and Life Safety Design Review | Design & Engineering | Fire & Life Safety Design | In Progress | 2026-02-04 08:00 | 2026-02-10 16:00 | 2026-02-04 08:00 |  | 5 | 3.8124 | 145 | No |  |  | 18000 | 18000 | 15075.5205 | 16562.2184 | -1486.698 | -2924.4795 | 0.91024 | 0.83753
Update 02 | 2026-02-28 | FLS-D-070 | Fire and Life Safety Design Approved | Design & Engineering | Fire & Life Safety Design | In Progress | 2026-02-10 16:00 | 2026-02-10 16:00 | 2026-02-10 16:00 |  | 0 | 0 | 145 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | BMS-D-010 | Develop BMS Design Architecture | Design & Engineering | BMS, DCIM & Controls Design | In Progress | 2026-01-20 08:00 | 2026-02-02 16:00 | 2026-01-20 08:00 |  | 10 | 0.045451 | 103 | No |  |  | 136000 | 136000 | 135381.8704 | 140888.9145 | -5507.0441 | -618.1296 | 0.96091 | 0.99545
Update 02 | 2026-02-28 | BMS-D-020 | Develop Mechanical Controls Architecture | Design & Engineering | BMS, DCIM & Controls Design | Not Started | 2026-03-04 08:00 | 2026-03-17 16:00 |  |  | 10 | 10 | 82 | No |  |  | 79000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | BMS-D-030 | Develop Electrical Monitoring Architecture | Design & Engineering | BMS, DCIM & Controls Design | In Progress | 2026-02-26 08:00 | 2026-03-11 16:00 | 2026-02-26 08:00 |  | 10 | 8.7638 | 86 | No |  |  | 23000 | 2875 | 2843.1973 | 2868.123 | -24.9257 | -31.8027 | 0.99131 | 0.98894
Update 02 | 2026-02-28 | BMS-D-040 | Develop DCIM Architecture | Design & Engineering | BMS, DCIM & Controls Design | In Progress | 2026-02-03 08:00 | 2026-02-16 16:00 | 2026-02-03 08:00 |  | 10 | 7.8267 | 103 | No |  |  | 79000 | 79000 | 64569.2016 | 67521.965 | -2952.7634 | -14430.7984 | 0.95627 | 0.81733
Update 02 | 2026-02-28 | BMS-D-050 | Develop Controls Integration Matrix | Design & Engineering | BMS, DCIM & Controls Design | Not Started | 2026-03-18 08:00 | 2026-03-31 16:00 |  |  | 10 | 10 | 82 | No |  |  | 79000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | BMS-D-060 | BMS DCIM and Controls Design Review | Design & Engineering | BMS, DCIM & Controls Design | Not Started | 2026-04-01 08:00 | 2026-04-07 16:00 |  |  | 5 | 5 | 82 | No |  |  | 18000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | BMS-D-070 | BMS DCIM and Controls Design Approved | Design & Engineering | BMS, DCIM & Controls Design | Not Started | 2026-04-07 16:00 | 2026-04-07 16:00 |  |  | 0 | 0 | 82 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | ICT-D-010 | Develop ICT Infrastructure Design | Design & Engineering | ICT & Security Systems Design | Completed | 2026-01-13 08:00 | 2026-01-26 16:00 | 2026-01-13 08:00 | 2026-01-26 16:00 | 10 | 0 |  | No |  |  | 136000 | 136000 | 136000 | 138370.4065 | -2370.4065 | 0 | 0.98287 | 1
Update 02 | 2026-02-28 | ICT-D-020 | Develop Structured Cabling Design | Design & Engineering | ICT & Security Systems Design | In Progress | 2026-01-27 08:00 | 2026-02-09 16:00 | 2026-01-27 08:00 |  | 10 | 0.23981 | 98 | No |  |  | 136000 | 136000 | 132738.5214 | 136385.0821 | -3646.5607 | -3261.4786 | 0.97326 | 0.97602
Update 02 | 2026-02-28 | ICT-D-030 | Develop CCTV System Design | Design & Engineering | ICT & Security Systems Design | In Progress | 2026-01-27 08:00 | 2026-02-05 16:00 | 2026-01-27 08:00 |  | 8 | 0.10932 | 100 | No |  |  | 127000 | 127000 | 125264.5053 | 130366.4643 | -5101.959 | -1735.4947 | 0.96086 | 0.98633
Update 02 | 2026-02-28 | ICT-D-040 | Develop Access Control System Design | Design & Engineering | ICT & Security Systems Design | Completed | 2026-01-27 08:00 | 2026-02-05 16:00 | 2026-01-27 08:00 | 2026-02-05 16:00 | 8 | 0 | 100 | No |  |  | 127000 | 127000 | 127000 | 131523.0836 | -4523.0836 | 0 | 0.96561 | 1
Update 02 | 2026-02-28 | ICT-D-050 | Develop Security System Integration Design | Design & Engineering | ICT & Security Systems Design | In Progress | 2026-02-10 08:00 | 2026-02-23 16:00 | 2026-02-10 08:00 |  | 10 | 0.33485 | 98 | No |  |  | 136000 | 136000 | 131445.978 | 133192.1803 | -1746.2023 | -4554.022 | 0.98689 | 0.96651
Update 02 | 2026-02-28 | ICT-D-060 | ICT and Security Design Review | Design & Engineering | ICT & Security Systems Design | In Progress | 2026-02-24 08:00 | 2026-03-02 16:00 | 2026-02-24 08:00 |  | 5 | 2.1065 | 185 | No |  |  | 18000 | 10421.0526 | 10416.5232 | 10531.5298 | -115.0066 | -4.5294 | 0.98908 | 0.99957
Update 02 | 2026-02-28 | ICT-D-070 | ICT and Security Design Approved | Design & Engineering | ICT & Security Systems Design | Not Started | 2026-03-02 16:00 | 2026-03-02 16:00 |  |  | 0 | 0 | 185 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | UTL-D-010 | Confirm Utility Power Requirements | Design & Engineering | Utility & Grid Connection Design | In Progress | 2026-02-05 08:00 | 2026-02-11 16:00 | 2026-02-05 08:00 |  | 5 | 0.16768 | 10 | No |  |  | 65000 | 65000 | 62820.1897 | 63031.9472 | -211.7575 | -2179.8103 | 0.99664 | 0.96646
Update 02 | 2026-02-28 | UTL-D-020 | Develop Utility Connection Design | Design & Engineering | Utility & Grid Connection Design | In Progress | 2026-02-12 08:00 | 2026-03-04 16:00 | 2026-02-12 08:00 |  | 15 | 3.879 | 148 | No |  |  | 154000 | 118655.7377 | 114175.8611 | 116245.7209 | -2069.8598 | -4479.8766 | 0.98219 | 0.96224
Update 02 | 2026-02-28 | UTL-D-030 | Develop Incoming MV Connection Design | Design & Engineering | Utility & Grid Connection Design | In Progress | 2026-02-12 08:00 | 2026-03-04 16:00 | 2026-02-12 08:00 |  | 15 | 3.3295 | 138 | No |  |  | 154000 | 118655.7377 | 119817.067 | 120743.16 | -926.0929 | 1161.3293 | 0.99233 | 1.0098
Update 02 | 2026-02-28 | UTL-D-040 | Coordinate Utility Protection Requirements | Design & Engineering | Utility & Grid Connection Design | Not Started | 2026-03-05 08:00 | 2026-03-18 16:00 |  |  | 10 | 10 | 138 | No |  |  | 23000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | UTL-D-050 | Submit Utility Connection Design | Design & Engineering | Utility & Grid Connection Design | Not Started | 2026-03-19 08:00 | 2026-03-19 16:00 |  |  | 1 | 1 | 138 | No |  |  | 17000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | UTL-D-060 | Utility Design Review | Design & Engineering | Utility & Grid Connection Design | Not Started | 2026-03-20 08:00 | 2026-04-16 16:00 |  |  | 20 | 20 | 138 | No |  |  | 28000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | UTL-D-070 | Utility Connection Design Approved | Design & Engineering | Utility & Grid Connection Design | Not Started | 2026-04-16 16:00 | 2026-04-16 16:00 |  |  | 0 | 0 | 138 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | SD-010 | Establish Shop Drawing Schedule | Design & Engineering | Shop Drawings & Technical Approvals | Completed | 2026-01-20 08:00 | 2026-01-26 16:00 | 2026-01-20 08:00 | 2026-01-26 16:00 | 5 | 0 |  | No |  |  | 111000 | 111000 | 111000 | 114117.0436 | -3117.0436 | 0 | 0.97269 | 1
Update 02 | 2026-02-28 | SD-020 | Prepare Civil and Structural Shop Drawings | Design & Engineering | Shop Drawings & Technical Approvals | Not Started | 2026-03-18 08:00 | 2026-04-07 16:00 |  |  | 15 | 15 | 149 | No |  |  | 154000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | SD-030 | Prepare Architectural Shop Drawings | Design & Engineering | Shop Drawings & Technical Approvals | In Progress | 2026-02-26 08:00 | 2026-03-18 16:00 | 2026-02-26 08:00 |  | 15 | 13.7982 | 163 | No |  |  | 154000 | 12622.9508 | 12338.3673 | 12582.4378 | -244.0705 | -284.5835 | 0.9806 | 0.97746
Update 02 | 2026-02-28 | SD-040 | Prepare Electrical Shop Drawings | Design & Engineering | Shop Drawings & Technical Approvals | Not Started | 2026-03-30 08:00 | 2026-04-24 16:00 |  |  | 20 | 20 | 136 | No |  |  | 168000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | SD-050 | Prepare Mechanical Shop Drawings | Design & Engineering | Shop Drawings & Technical Approvals | Not Started | 2026-03-13 08:00 | 2026-04-09 16:00 |  |  | 20 | 20 | 147 | No |  |  | 168000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | SD-060 | Prepare Fire and Life Safety Shop Drawings | Design & Engineering | Shop Drawings & Technical Approvals | In Progress | 2026-02-11 08:00 | 2026-03-03 16:00 | 2026-02-11 08:00 |  | 15 | 2.5062 | 174 | No |  |  | 154000 | 126229.5082 | 128269.707 | 132704.1059 | -4434.3989 | 2040.1988 | 0.96658 | 1.0162
Update 02 | 2026-02-28 | SD-070 | Prepare BMS DCIM and Controls Shop Drawings | Design & Engineering | Shop Drawings & Technical Approvals | Not Started | 2026-04-08 08:00 | 2026-04-28 16:00 |  |  | 15 | 15 | 134 | No |  |  | 154000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | SD-080 | Consultant Review of Shop Drawings | Design & Engineering | Shop Drawings & Technical Approvals | Not Started | 2026-04-15 08:00 | 2026-04-28 16:00 |  |  | 10 | 10 | 134 | No |  |  | 23000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | SD-090 | Resolve Shop Drawing Comments | Design & Engineering | Shop Drawings & Technical Approvals | Not Started | 2026-04-29 08:00 | 2026-05-12 16:00 |  |  | 10 | 10 | 134 | No |  |  | 136000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | SD-100 | Technical Shop Drawings Approved | Design & Engineering | Shop Drawings & Technical Approvals | Not Started | 2026-05-12 16:00 | 2026-05-12 16:00 |  |  | 0 | 0 | 134 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | PRM-010 | Develop Project Procurement Plan | Procurement | Procurement Management | Completed | 2026-01-06 08:00 | 2026-01-12 16:00 | 2026-01-06 08:00 | 2026-01-12 16:00 | 5 | 0 |  | No |  |  | 89000 | 89000 | 89000 | 92535.1745 | -3535.1745 | 0 | 0.9618 | 1
Update 02 | 2026-02-28 | PRM-020 | Develop Procurement Schedule | Procurement | Procurement Management | Completed | 2026-01-13 08:00 | 2026-01-19 16:00 | 2026-01-13 08:00 | 2026-01-19 16:00 | 5 | 0 |  | No |  |  | 89000 | 89000 | 89000 | 91057.547 | -2057.547 | 0 | 0.9774 | 1
Update 02 | 2026-02-28 | PRM-030 | Establish Approved Vendor List | Procurement | Procurement Management | Completed | 2026-01-20 08:00 | 2026-01-28 16:00 | 2026-01-21 08:00 | 2026-01-28 16:00 | 7 | 0 | 127 | No |  |  | 49000 | 49000 | 49000 | 49497.7333 | -497.7333 | 0 | 0.98994 | 1
Update 02 | 2026-02-28 | PRM-040 | Establish Procurement Tracking Register | Procurement | Procurement Management | Completed | 2026-02-05 08:00 | 2026-02-18 16:00 | 2026-02-05 08:00 | 2026-02-18 16:00 | 10 | 0 | 127 | No |  |  | 55000 | 55000 | 55000 | 56079.2831 | -1079.2831 | 0 | 0.98075 | 1
Update 02 | 2026-02-28 | PRM-050 | Procurement Strategy Approved | Procurement | Procurement Management | Completed | 2026-02-19 08:00 | 2026-02-27 16:00 | 2026-02-19 08:00 | 2026-02-27 16:00 | 7 | 0 | 127 | No |  |  | 74000 | 74000 | 74000 | 75015.2222 | -1015.2222 | 0 | 0.98647 | 1
Update 02 | 2026-02-28 | SWG-010 | Prepare MV/LV Switchgear Technical Submittal | Procurement | MV/LV Switchgear | Not Started | 2026-03-05 08:00 | 2026-03-13 16:00 |  |  | 7 | 7 | 31 | No |  |  | 186000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | SWG-020 | MV/LV Switchgear Technical Submittal Approval | Procurement | MV/LV Switchgear | Not Started | 2026-03-30 08:00 | 2026-04-07 16:00 |  |  | 7 | 7 | 21 | No |  |  | 186000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | SWG-030 | Issue Purchase Order - MV/LV Switchgear | Procurement | MV/LV Switchgear | Not Started | 2026-04-08 08:00 | 2026-04-10 16:00 |  |  | 3 | 3 | 21 | No |  |  | 240000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | SWG-040 | Manufacture MV/LV Switchgear | Procurement | MV/LV Switchgear | Not Started | 2026-04-13 08:00 | 2026-09-25 16:00 |  |  | 120 | 120 | 21 | No |  |  | 4353000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | SWG-050 | Factory Acceptance Test - MV/LV Switchgear | Procurement | MV/LV Switchgear | Not Started | 2026-09-28 08:00 | 2026-09-30 16:00 |  |  | 3 | 3 | 21 | No |  |  | 312000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | SWG-060 | Ship MV/LV Switchgear | Procurement | MV/LV Switchgear | Not Started | 2026-10-01 08:00 | 2026-10-21 16:00 |  |  | 15 | 15 | 21 | No |  |  | 311000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | SWG-070 | Deliver MV/LV Switchgear to Site | Procurement | MV/LV Switchgear | Not Started | 2026-10-22 08:00 | 2026-10-23 16:00 |  |  | 2 | 2 | 21 | No |  |  | 170000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | TRF-010 | Prepare Transformer Technical Submittal | Procurement | Transformers | In Progress | 2026-02-19 08:00 | 2026-02-27 16:00 | 2026-02-19 08:00 |  | 7 | 0.24032 | 20 | No |  |  | 223000 | 223000 | 215343.964 | 217547.3742 | -2203.4102 | -7656.036 | 0.98987 | 0.96567
Update 02 | 2026-02-28 | TRF-020 | Transformer Technical Submittal Approval | Procurement | Transformers | Not Started | 2026-03-30 08:00 | 2026-04-07 16:00 |  |  | 7 | 7 | 0 | Yes | 1 | 6 | 223000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | TRF-030 | Issue Purchase Order - Transformers | Procurement | Transformers | Not Started | 2026-04-08 08:00 | 2026-04-10 16:00 |  |  | 3 | 3 | 0 | Yes | 1 | 7 | 288000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | TRF-040 | Manufacture Transformers | Procurement | Transformers | Not Started | 2026-04-13 08:00 | 2026-11-06 16:00 |  |  | 150 | 150 | 0 | Yes | 1 | 8 | 5588000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | TRF-050 | Factory Acceptance Test - Transformers | Procurement | Transformers | Not Started | 2026-11-09 08:00 | 2026-11-11 16:00 |  |  | 3 | 3 | 0 | Yes | 1 | 9 | 374000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | TRF-060 | Ship Transformers | Procurement | Transformers | Not Started | 2026-11-12 08:00 | 2026-12-09 16:00 |  |  | 20 | 20 | 0 | Yes | 1 | 10 | 407000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | TRF-070 | Deliver Transformers to Site | Procurement | Transformers | Not Started | 2026-12-10 08:00 | 2026-12-11 16:00 |  |  | 2 | 2 | 0 | Yes | 1 | 11 | 204000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | UPS-010 | Prepare UPS and Battery Technical Submittal | Procurement | UPS Systems & Batteries | In Progress | 2026-02-26 08:00 | 2026-03-06 16:00 | 2026-02-26 08:00 |  | 7 | 5.5773 | 52 | No |  |  | 186000 | 37200 | 37802.967 | 38986.6475 | -1183.6805 | 602.967 | 0.96964 | 1.0162
Update 02 | 2026-02-28 | UPS-020 | UPS and Battery Technical Submittal Approval | Procurement | UPS Systems & Batteries | Not Started | 2026-03-30 08:00 | 2026-04-07 16:00 |  |  | 7 | 7 | 37 | No |  |  | 186000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | UPS-030 | Issue Purchase Order - UPS and Batteries | Procurement | UPS Systems & Batteries | Not Started | 2026-04-08 08:00 | 2026-04-10 16:00 |  |  | 3 | 3 | 37 | No |  |  | 240000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | UPS-040 | Manufacture UPS Systems and Batteries | Procurement | UPS Systems & Batteries | Not Started | 2026-04-13 08:00 | 2026-09-25 16:00 |  |  | 120 | 120 | 37 | No |  |  | 4353000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | UPS-050 | Factory Acceptance Test - UPS Systems | Procurement | UPS Systems & Batteries | Not Started | 2026-09-28 08:00 | 2026-09-30 16:00 |  |  | 3 | 3 | 37 | No |  |  | 312000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | UPS-060 | Ship UPS Systems and Batteries | Procurement | UPS Systems & Batteries | Not Started | 2026-10-01 08:00 | 2026-10-21 16:00 |  |  | 15 | 15 | 37 | No |  |  | 311000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | UPS-070 | Deliver UPS Systems and Batteries to Site | Procurement | UPS Systems & Batteries | Not Started | 2026-10-22 08:00 | 2026-10-23 16:00 |  |  | 2 | 2 | 37 | No |  |  | 170000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | GEN-010 | Prepare Standby Generator Technical Submittal | Procurement | Standby Generators | In Progress | 2026-02-19 08:00 | 2026-02-27 16:00 | 2026-02-19 08:00 |  | 7 | 4.7964 | 38 | No |  |  | 208000 | 208000 | 184334.2872 | 202744.0425 | -18409.7553 | -23665.7128 | 0.9092 | 0.88622
Update 02 | 2026-02-28 | GEN-020 | Standby Generator Technical Submittal Approval | Procurement | Standby Generators | Not Started | 2026-03-30 08:00 | 2026-04-07 16:00 |  |  | 7 | 7 | 18 | No |  |  | 208000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | GEN-030 | Issue Purchase Order - Standby Generators | Procurement | Standby Generators | Not Started | 2026-04-08 08:00 | 2026-04-10 16:00 |  |  | 3 | 3 | 18 | No |  |  | 269000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | GEN-040 | Manufacture Standby Generators | Procurement | Standby Generators | Not Started | 2026-04-13 08:00 | 2026-11-06 16:00 |  |  | 150 | 150 | 18 | No |  |  | 5213000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | GEN-050 | Factory Acceptance Test - Standby Generators | Procurement | Standby Generators | Not Started | 2026-11-09 08:00 | 2026-11-11 16:00 |  |  | 3 | 3 | 18 | No |  |  | 349000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | GEN-060 | Ship Standby Generators | Procurement | Standby Generators | Not Started | 2026-11-12 08:00 | 2026-12-09 16:00 |  |  | 20 | 20 | 18 | No |  |  | 380000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | GEN-070 | Deliver Standby Generators to Site | Procurement | Standby Generators | Not Started | 2026-12-10 08:00 | 2026-12-11 16:00 |  |  | 2 | 2 | 18 | No |  |  | 190000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CLP-010 | Prepare Cooling Plant Equipment Technical Submittal | Procurement | Cooling Plant Equipment | In Progress | 2026-02-25 08:00 | 2026-03-05 16:00 | 2026-02-25 08:00 |  | 7 | 11.1187 | 44 | No |  |  | 178000 | 56960 | 47839.3688 | 52467.7551 | -4628.3864 | -9120.6312 | 0.91179 | 0.83988
Update 02 | 2026-02-28 | CLP-020 | Cooling Plant Equipment Technical Submittal Approval | Procurement | Cooling Plant Equipment | Not Started | 2026-03-13 08:00 | 2026-03-23 16:00 |  |  | 7 | 7 | 39 | No |  |  | 178000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CLP-030 | Issue Purchase Order - Cooling Plant Equipment | Procurement | Cooling Plant Equipment | Not Started | 2026-03-24 08:00 | 2026-03-26 16:00 |  |  | 3 | 3 | 39 | No |  |  | 230000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CLP-040 | Manufacture Cooling Plant Equipment | Procurement | Cooling Plant Equipment | Not Started | 2026-03-27 08:00 | 2026-07-30 16:00 |  |  | 90 | 90 | 39 | No |  |  | 3833000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CLP-050 | Factory Acceptance Test - Cooling Plant Equipment | Procurement | Cooling Plant Equipment | Not Started | 2026-07-31 08:00 | 2026-08-04 16:00 |  |  | 3 | 3 | 39 | No |  |  | 299000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CLP-060 | Ship Cooling Plant Equipment | Procurement | Cooling Plant Equipment | Not Started | 2026-08-05 08:00 | 2026-08-25 16:00 |  |  | 15 | 15 | 39 | No |  |  | 299000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CLP-070 | Deliver Cooling Plant Equipment to Site | Procurement | Cooling Plant Equipment | Not Started | 2026-08-26 08:00 | 2026-08-27 16:00 |  |  | 2 | 2 | 39 | No |  |  | 163000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CRAH-010 | Prepare CRAH/CRAC Technical Submittal | Procurement | CRAH/CRAC Units | Completed | 2026-02-18 08:00 | 2026-02-26 16:00 | 2026-02-18 08:00 | 2026-02-26 16:00 | 7 | 0 | 63 | No |  |  | 148000 | 148000 | 148000 | 148166.9757 | -166.9757 | 0 | 0.99887 | 1
Update 02 | 2026-02-28 | CRAH-020 | CRAH/CRAC Technical Submittal Approval | Procurement | CRAH/CRAC Units | Not Started | 2026-03-13 08:00 | 2026-03-23 16:00 |  |  | 7 | 7 | 53 | No |  |  | 148000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CRAH-030 | Issue Purchase Order - CRAH/CRAC Units | Procurement | CRAH/CRAC Units | Not Started | 2026-03-24 08:00 | 2026-03-26 16:00 |  |  | 3 | 3 | 53 | No |  |  | 192000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CRAH-040 | Manufacture CRAH/CRAC Units | Procurement | CRAH/CRAC Units | Not Started | 2026-03-27 08:00 | 2026-07-30 16:00 |  |  | 90 | 90 | 53 | No |  |  | 3194000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CRAH-050 | Factory Acceptance Test - CRAH/CRAC Units | Procurement | CRAH/CRAC Units | Not Started | 2026-07-31 08:00 | 2026-08-04 16:00 |  |  | 3 | 3 | 53 | No |  |  | 249000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CRAH-060 | Ship CRAH/CRAC Units | Procurement | CRAH/CRAC Units | Not Started | 2026-08-05 08:00 | 2026-08-25 16:00 |  |  | 15 | 15 | 53 | No |  |  | 249000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CRAH-070 | Deliver CRAH/CRAC Units to Site | Procurement | CRAH/CRAC Units | Not Started | 2026-08-26 08:00 | 2026-08-27 16:00 |  |  | 2 | 2 | 53 | No |  |  | 136000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | FLS-P-010 | Prepare Fire and Life Safety Equipment Submittal | Procurement | Fire & Life Safety Equipment | In Progress | 2026-02-04 08:00 | 2026-02-10 16:00 | 2026-02-04 08:00 |  | 5 | 0.15683 | 145 | No |  |  | 94000 | 94000 | 91051.5819 | 94790.3551 | -3738.7732 | -2948.4181 | 0.96056 | 0.96863
Update 02 | 2026-02-28 | FLS-P-020 | Fire and Life Safety Equipment Submittal Approval | Procurement | Fire & Life Safety Equipment | In Progress | 2026-02-11 08:00 | 2026-02-19 16:00 | 2026-02-11 08:00 |  | 7 | 0.22463 | 145 | No |  |  | 104000 | 104000 | 100662.5706 | 101977.4323 | -1314.8616 | -3337.4294 | 0.98711 | 0.96791
Update 02 | 2026-02-28 | FLS-P-030 | Issue Purchase Order - Fire and Life Safety Equipment | Procurement | Fire & Life Safety Equipment | In Progress | 2026-02-20 08:00 | 2026-02-24 16:00 | 2026-02-20 08:00 |  | 3 | 7.5362 | 145 | No |  |  | 134000 | 134000 | 110049.6422 | 116868.232 | -6818.5898 | -23950.3578 | 0.94166 | 0.82127
Update 02 | 2026-02-28 | FLS-P-040 | Manufacture Fire and Life Safety Equipment | Procurement | Fire & Life Safety Equipment | In Progress | 2026-02-25 08:00 | 2026-05-19 16:00 | 2026-02-25 08:00 |  | 60 | 58.1338 | 145 | No |  |  | 1980000 | 63360 | 61585.0671 | 62071.3977 | -486.3306 | -1774.9329 | 0.99216 | 0.97199
Update 02 | 2026-02-28 | FLS-P-050 | Factory Testing - Fire and Life Safety Equipment | Procurement | Fire & Life Safety Equipment | Not Started | 2026-05-20 08:00 | 2026-05-22 16:00 |  |  | 3 | 3 | 145 | No |  |  | 107000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | FLS-P-060 | Ship Fire and Life Safety Equipment | Procurement | Fire & Life Safety Equipment | Not Started | 2026-05-25 08:00 | 2026-06-05 16:00 |  |  | 10 | 10 | 145 | No |  |  | 154000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | FLS-P-070 | Deliver Fire and Life Safety Equipment to Site | Procurement | Fire & Life Safety Equipment | Not Started | 2026-06-08 08:00 | 2026-06-09 16:00 |  |  | 2 | 2 | 145 | No |  |  | 95000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | BMS-P-010 | Prepare BMS DCIM and Controls Equipment Submittal | Procurement | BMS, DCIM & Controls Equipment | Not Started | 2026-04-01 08:00 | 2026-04-07 16:00 |  |  | 5 | 5 | 82 | No |  |  | 101000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | BMS-P-020 | BMS DCIM and Controls Equipment Submittal Approval | Procurement | BMS, DCIM & Controls Equipment | Not Started | 2026-04-08 08:00 | 2026-04-16 16:00 |  |  | 7 | 7 | 82 | No |  |  | 111000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | BMS-P-030 | Issue Purchase Order - BMS DCIM and Controls Equipment | Procurement | BMS, DCIM & Controls Equipment | Not Started | 2026-04-17 08:00 | 2026-04-21 16:00 |  |  | 3 | 3 | 82 | No |  |  | 144000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | BMS-P-040 | Configure and Manufacture Controls Equipment | Procurement | BMS, DCIM & Controls Equipment | Not Started | 2026-04-22 08:00 | 2026-07-14 16:00 |  |  | 60 | 60 | 82 | No |  |  | 1414000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | BMS-P-050 | Factory Testing - BMS DCIM and Controls | Procurement | BMS, DCIM & Controls Equipment | Not Started | 2026-07-15 08:00 | 2026-07-21 16:00 |  |  | 5 | 5 | 82 | No |  |  | 134000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | BMS-P-060 | Ship BMS DCIM and Controls Equipment | Procurement | BMS, DCIM & Controls Equipment | Not Started | 2026-07-22 08:00 | 2026-08-04 16:00 |  |  | 10 | 10 | 82 | No |  |  | 165000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | BMS-P-070 | Deliver BMS DCIM and Controls Equipment to Site | Procurement | BMS, DCIM & Controls Equipment | Not Started | 2026-08-05 08:00 | 2026-08-06 16:00 |  |  | 2 | 2 | 82 | No |  |  | 102000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | ICT-P-010 | Prepare ICT and Security Equipment Submittal | Procurement | ICT & Security Equipment | In Progress | 2026-02-24 08:00 | 2026-03-02 16:00 | 2026-02-24 08:00 |  | 5 | 2.0927 | 242 | No |  |  | 67000 | 38789.4737 | 38957.7828 | 40360.6249 | -1402.8421 | 168.3091 | 0.96524 | 1.0043
Update 02 | 2026-02-28 | ICT-P-020 | ICT and Security Equipment Submittal Approval | Procurement | ICT & Security Equipment | Not Started | 2026-03-03 08:00 | 2026-03-09 16:00 |  |  | 5 | 5 | 242 | No |  |  | 67000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | ICT-P-030 | Issue Purchase Order - ICT and Security Equipment | Procurement | ICT & Security Equipment | Not Started | 2026-03-10 08:00 | 2026-03-12 16:00 |  |  | 3 | 3 | 242 | No |  |  | 96000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | ICT-P-040 | Procure ICT and Security Equipment | Procurement | ICT & Security Equipment | Not Started | 2026-03-13 08:00 | 2026-04-23 16:00 |  |  | 30 | 30 | 242 | No |  |  | 153000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | ICT-P-050 | Factory Configuration and Testing - ICT and Security | Procurement | ICT & Security Equipment | Not Started | 2026-04-24 08:00 | 2026-04-30 16:00 |  |  | 5 | 5 | 242 | No |  |  | 89000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | ICT-P-060 | Ship ICT and Security Equipment | Procurement | ICT & Security Equipment | Not Started | 2026-05-01 08:00 | 2026-05-14 16:00 |  |  | 10 | 10 | 242 | No |  |  | 110000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | ICT-P-070 | Deliver ICT and Security Equipment to Site | Procurement | ICT & Security Equipment | Not Started | 2026-05-15 08:00 | 2026-05-18 16:00 |  |  | 2 | 2 | 242 | No |  |  | 68000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | ABM-010 | Prepare Architectural Materials Submittals | Procurement | Architectural & Building Materials | In Progress | 2026-02-26 08:00 | 2026-03-04 16:00 | 2026-02-26 08:00 |  | 5 | 5.8085 | 94 | No |  |  | 67000 | 17631.5789 | 15965.6153 | 17390.6595 | -1425.0442 | -1665.9636 | 0.91806 | 0.90551
Update 02 | 2026-02-28 | ABM-020 | Architectural Materials Submittals Approval | Procurement | Architectural & Building Materials | Not Started | 2026-03-05 08:00 | 2026-03-11 16:00 |  |  | 5 | 5 | 94 | No |  |  | 67000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | ABM-030 | Procure Roofing and Waterproofing Materials | Procurement | Architectural & Building Materials | Not Started | 2026-03-12 08:00 | 2026-04-01 16:00 |  |  | 15 | 15 | 94 | No |  |  | 124000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | ABM-040 | Procure External Cladding Materials | Procurement | Architectural & Building Materials | Not Started | 2026-04-02 08:00 | 2026-04-29 16:00 |  |  | 20 | 20 | 94 | No |  |  | 136000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | ABM-050 | Procure Doors Louvers and Fire-Rated Assemblies | Procurement | Architectural & Building Materials | Not Started | 2026-04-30 08:00 | 2026-05-20 16:00 |  |  | 15 | 15 | 94 | No |  |  | 174000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | ABM-060 | Deliver Architectural Materials to Site | Procurement | Architectural & Building Materials | Not Started | 2026-05-21 08:00 | 2026-05-25 16:00 |  |  | 3 | 3 | 94 | No |  |  | 77000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | LLE-010 | Identify Long-Lead Equipment | Procurement | Long-Lead Equipment Management | Not Started | 2026-03-02 08:00 | 2026-03-06 16:00 |  |  | 5 | 5 | 127 | No |  |  | 89000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | LLE-020 | Establish Long-Lead Equipment Register | Procurement | Long-Lead Equipment Management | Not Started | 2026-03-09 08:00 | 2026-03-13 16:00 |  |  | 5 | 5 | 127 | No |  |  | 45000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | LLE-030 | Confirm Required-on-Site Dates | Procurement | Long-Lead Equipment Management | Not Started | 2026-03-16 08:00 | 2026-03-20 16:00 |  |  | 5 | 5 | 127 | No |  |  | 89000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | LLE-040 | Monitor Vendor Engineering and Manufacturing | Procurement | Long-Lead Equipment Management | Not Started | 2026-04-08 08:00 | 2026-08-11 16:00 |  |  | 90 | 90 | 115 | No |  |  | 106000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | LLE-050 | Monitor FAT and Shipping Readiness | Procurement | Long-Lead Equipment Management | Not Started | 2026-08-12 08:00 | 2026-08-18 16:00 |  |  | 5 | 5 | 115 | No |  |  | 45000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | LLE-060 | Long-Lead Equipment Delivery Readiness Confirmed | Procurement | Long-Lead Equipment Management | Not Started | 2026-11-11 16:00 | 2026-11-11 16:00 |  |  | 0 | 0 | 54 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | MOB-010 | Mobilize Project Team to Site | Enabling & Site Works | Mobilization & Temporary Facilities | Completed | 2026-01-06 08:00 | 2026-01-10 16:00 | 2026-01-06 08:00 | 2026-01-10 16:00 | 5 | 0 |  | No |  |  | 87000 | 87000 | 87000 | 88816.8951 | -1816.8951 | 0 | 0.97954 | 1
Update 02 | 2026-02-28 | MOB-020 | Establish Site Offices and Welfare Facilities | Enabling & Site Works | Mobilization & Temporary Facilities | Completed | 2026-01-12 08:00 | 2026-01-16 16:00 | 2026-01-12 08:00 | 2026-01-16 16:00 | 5 | 0 |  | No |  |  | 87000 | 87000 | 87000 | 88189.2704 | -1189.2704 | 0 | 0.98651 | 1
Update 02 | 2026-02-28 | MOB-030 | Install Temporary Site Fencing and Hoarding | Enabling & Site Works | Mobilization & Temporary Facilities | Completed | 2026-01-12 08:00 | 2026-01-16 16:00 | 2026-01-12 08:00 | 2026-01-16 16:00 | 5 | 0 |  | No |  |  | 116000 | 116000 | 116000 | 116206.2742 | -206.2742 | 0 | 0.99822 | 1
Update 02 | 2026-02-28 | MOB-040 | Establish Temporary Storage and Laydown Areas | Enabling & Site Works | Mobilization & Temporary Facilities | Completed | 2026-01-12 08:00 | 2026-01-16 16:00 | 2026-01-12 08:00 | 2026-01-16 16:00 | 5 | 0 |  | No |  |  | 87000 | 87000 | 87000 | 89556.1244 | -2556.1244 | 0 | 0.97146 | 1
Update 02 | 2026-02-28 | MOB-050 | Establish Site Security and Access Control | Enabling & Site Works | Mobilization & Temporary Facilities | Completed | 2026-01-12 08:00 | 2026-01-16 16:00 | 2026-01-12 08:00 | 2026-01-16 16:00 | 5 | 0 |  | No |  |  | 87000 | 87000 | 87000 | 87262.456 | -262.456 | 0 | 0.99699 | 1
Update 02 | 2026-02-28 | MOB-060 | Site Mobilization Complete | Enabling & Site Works | Mobilization & Temporary Facilities | In Progress | 2026-02-14 08:00 | 2026-02-14 08:00 | 2026-02-14 08:00 |  | 0 | 4 | 32 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | SUR-010 | Establish Survey Control Points | Enabling & Site Works | Surveying & Setting Out | In Progress | 2026-02-14 08:00 | 2026-02-17 16:00 | 2026-02-14 08:00 |  | 3 | 0.10094 | 32 | No |  |  | 75000 | 75000 | 72476.5383 | 75057.4966 | -2580.9583 | -2523.4617 | 0.96561 | 0.96635
Update 02 | 2026-02-28 | SUR-020 | Conduct Existing Site Topographic Survey | Enabling & Site Works | Surveying & Setting Out | Completed | 2026-02-18 08:00 | 2026-02-23 16:00 | 2026-02-18 08:00 | 2026-02-23 16:00 | 5 | 0 | 32 | No |  |  | 87000 | 87000 | 87000 | 88428.8599 | -1428.8599 | 0 | 0.98384 | 1
Update 02 | 2026-02-28 | SUR-030 | Verify Existing Site Levels and Boundaries | Enabling & Site Works | Surveying & Setting Out | Completed | 2026-02-24 08:00 | 2026-02-25 16:00 | 2026-02-24 08:00 | 2026-02-25 16:00 | 2 | 0 | 32 | No |  |  | 66000 | 66000 | 66000 | 67436.7215 | -1436.7215 | 0 | 0.9787 | 1
Update 02 | 2026-02-28 | SUR-040 | Set Out Main Building Footprint | Enabling & Site Works | Surveying & Setting Out | In Progress | 2026-02-26 08:00 | 2026-02-28 16:00 | 2026-02-26 08:00 |  | 3 | 0.94056 | 91 | No |  |  | 75000 | 53571.4286 | 51485.9039 | 53388.3575 | -1902.4536 | -2085.5246 | 0.96437 | 0.96107
Update 02 | 2026-02-28 | SUR-050 | Set Out External Infrastructure and Utility Routes | Enabling & Site Works | Surveying & Setting Out | In Progress | 2026-02-26 08:00 | 2026-02-28 16:00 | 2026-02-26 08:00 |  | 3 | 0.84041 | 91 | No |  |  | 75000 | 53571.4286 | 53989.7692 | 55699.4281 | -1709.6589 | 418.3406 | 0.96931 | 1.0078
Update 02 | 2026-02-28 | SUR-060 | Survey and Setting Out Complete | Enabling & Site Works | Surveying & Setting Out | Not Started | 2026-03-02 08:00 | 2026-03-02 08:00 |  |  | 0 | 0 | 91 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | SCP-010 | Clear Existing Vegetation and Obstructions | Enabling & Site Works | Site Clearance & Preparation | In Progress | 2026-02-26 08:00 | 2026-03-05 16:00 | 2026-02-26 08:00 |  | 7 | 5.4149 | 32 | No |  |  | 96000 | 21818.1818 | 21738.7843 | 21854.4038 | -115.6195 | -79.3975 | 0.99471 | 0.99636
Update 02 | 2026-02-28 | SCP-020 | Remove Existing Surface Materials | Enabling & Site Works | Site Clearance & Preparation | Not Started | 2026-03-06 08:00 | 2026-03-11 16:00 |  |  | 5 | 5 | 32 | No |  |  | 87000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | SCP-030 | Remove or Divert Existing Minor Services | Enabling & Site Works | Site Clearance & Preparation | Not Started | 2026-03-12 08:00 | 2026-03-19 16:00 |  |  | 7 | 7 | 32 | No |  |  | 96000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | SCP-040 | Strip and Stockpile Topsoil | Enabling & Site Works | Site Clearance & Preparation | Not Started | 2026-03-20 08:00 | 2026-03-25 16:00 |  |  | 5 | 5 | 32 | No |  |  | 87000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | SCP-050 | Prepare Site for Earthworks | Enabling & Site Works | Site Clearance & Preparation | Not Started | 2026-03-26 08:00 | 2026-03-28 16:00 |  |  | 3 | 3 | 32 | No |  |  | 75000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | SCP-060 | Site Clearance Complete | Enabling & Site Works | Site Clearance & Preparation | Not Started | 2026-03-30 08:00 | 2026-03-30 08:00 |  |  | 0 | 0 | 32 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | EW-010 | Bulk Excavation | Enabling & Site Works | Earthworks & Excavation | Not Started | 2026-03-30 08:00 | 2026-04-09 16:00 |  |  | 10 | 10 | 32 | No |  |  | 107000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | EW-020 | Excavate Building Formation | Enabling & Site Works | Earthworks & Excavation | Not Started | 2026-04-10 08:00 | 2026-04-21 16:00 |  |  | 10 | 10 | 32 | No |  |  | 107000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | EW-030 | Excavate Utility and Drainage Routes | Enabling & Site Works | Earthworks & Excavation | Not Started | 2026-04-01 08:00 | 2026-04-11 16:00 |  |  | 10 | 10 | 139 | No |  |  | 107000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | EW-040 | Place Engineered Fill | Enabling & Site Works | Earthworks & Excavation | Not Started | 2026-04-22 08:00 | 2026-04-29 16:00 |  |  | 7 | 7 | 32 | No |  |  | 96000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | EW-050 | Compact and Test Formation | Enabling & Site Works | Earthworks & Excavation | Not Started | 2026-04-30 08:00 | 2026-05-02 16:00 |  |  | 3 | 3 | 32 | No |  |  | 75000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | EW-060 | Prepare Formation for Foundations | Enabling & Site Works | Earthworks & Excavation | Not Started | 2026-05-04 08:00 | 2026-05-08 16:00 |  |  | 5 | 5 | 32 | No |  |  | 116000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | EW-070 | Earthworks Complete | Enabling & Site Works | Earthworks & Excavation | Not Started | 2026-05-09 08:00 | 2026-05-09 08:00 |  |  | 0 | 0 | 300 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | TU-010 | Install Temporary Electrical Supply | Enabling & Site Works | Temporary Utilities | In Progress | 2026-02-14 08:00 | 2026-02-19 16:00 | 2026-02-14 08:00 |  | 5 | 0.076229 | 37 | No |  |  | 116000 | 116000 | 114231.4981 | 117164.433 | -2932.9349 | -1768.5019 | 0.97497 | 0.98475
Update 02 | 2026-02-28 | TU-020 | Install Temporary Water Supply | Enabling & Site Works | Temporary Utilities | Completed | 2026-02-14 08:00 | 2026-02-19 16:00 | 2026-02-14 08:00 | 2026-02-19 16:00 | 5 | 0 | 37 | No |  |  | 116000 | 116000 | 116000 | 116618.1197 | -618.1197 | 0 | 0.9947 | 1
Update 02 | 2026-02-28 | TU-030 | Install Temporary Drainage Facilities | Enabling & Site Works | Temporary Utilities | In Progress | 2026-02-14 08:00 | 2026-02-19 16:00 | 2026-02-14 08:00 |  | 5 | 0.12565 | 37 | No |  |  | 116000 | 116000 | 113084.9634 | 116646.5927 | -3561.6294 | -2915.0366 | 0.96947 | 0.97487
Update 02 | 2026-02-28 | TU-040 | Install Temporary Site Lighting | Enabling & Site Works | Temporary Utilities | Completed | 2026-02-14 08:00 | 2026-02-19 16:00 | 2026-02-14 08:00 | 2026-02-19 16:00 | 5 | 0 | 37 | No |  |  | 116000 | 116000 | 116000 | 120305.6024 | -4305.6024 | 0 | 0.96421 | 1
Update 02 | 2026-02-28 | TU-050 | Temporary Site Utilities Operational | Enabling & Site Works | Temporary Utilities | In Progress | 2026-02-20 08:00 | 2026-02-20 08:00 | 2026-02-20 08:00 |  | 0 | 4 | 37 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | UGU-010 | Set Out Underground Utility Routes | Enabling & Site Works | Underground Site Utilities | Not Started | 2026-04-13 08:00 | 2026-04-15 16:00 |  |  | 3 | 3 | 139 | No |  |  | 75000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | UGU-020 | Excavate Underground Utility Trenches | Enabling & Site Works | Underground Site Utilities | Not Started | 2026-04-16 08:00 | 2026-04-27 16:00 |  |  | 10 | 10 | 139 | No |  |  | 107000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | UGU-030 | Install Underground Electrical Duct Banks | Enabling & Site Works | Underground Site Utilities | Not Started | 2026-04-28 08:00 | 2026-05-08 16:00 |  |  | 10 | 10 | 139 | No |  |  | 136000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | UGU-040 | Install Underground ICT Duct Banks | Enabling & Site Works | Underground Site Utilities | Not Started | 2026-04-28 08:00 | 2026-05-06 16:00 |  |  | 8 | 8 | 141 | No |  |  | 133000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | UGU-050 | Install Underground Water Services | Enabling & Site Works | Underground Site Utilities | Not Started | 2026-04-28 08:00 | 2026-05-06 16:00 |  |  | 8 | 8 | 141 | No |  |  | 133000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | UGU-060 | Install Underground Fire Water Services | Enabling & Site Works | Underground Site Utilities | Not Started | 2026-04-28 08:00 | 2026-05-06 16:00 |  |  | 8 | 8 | 141 | No |  |  | 133000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | UGU-070 | Install Utility Chambers and Manholes | Enabling & Site Works | Underground Site Utilities | Not Started | 2026-04-28 08:00 | 2026-05-06 16:00 |  |  | 8 | 8 | 141 | No |  |  | 133000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | UGU-080 | Inspect and Test Underground Utilities | Enabling & Site Works | Underground Site Utilities | Not Started | 2026-05-09 08:00 | 2026-05-12 16:00 |  |  | 3 | 3 | 139 | No |  |  | 75000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | UGU-090 | Backfill and Compact Utility Trenches | Enabling & Site Works | Underground Site Utilities | Not Started | 2026-05-13 08:00 | 2026-05-18 16:00 |  |  | 5 | 5 | 139 | No |  |  | 87000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | UGU-100 | Underground Site Utilities Complete | Enabling & Site Works | Underground Site Utilities | Not Started | 2026-05-19 08:00 | 2026-05-19 08:00 |  |  | 0 | 0 | 139 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | RDA-010 | Prepare Site Road Subgrade | Enabling & Site Works | Site Roads & Access | Not Started | 2026-05-04 08:00 | 2026-05-08 16:00 |  |  | 5 | 5 | 271 | No |  |  | 87000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | RDA-020 | Install Road Subbase and Base Course | Enabling & Site Works | Site Roads & Access | Not Started | 2026-05-09 08:00 | 2026-05-16 16:00 |  |  | 7 | 7 | 271 | No |  |  | 128000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | RDA-030 | Construct Heavy Equipment Access Routes | Enabling & Site Works | Site Roads & Access | Not Started | 2026-05-18 08:00 | 2026-05-22 16:00 |  |  | 5 | 5 | 271 | No |  |  | 116000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | RDA-040 | Construct Permanent Internal Roads | Enabling & Site Works | Site Roads & Access | Not Started | 2026-05-23 08:00 | 2026-06-03 16:00 |  |  | 10 | 10 | 271 | No |  |  | 143000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | RDA-050 | Construct Kerbs and Hardstanding Areas | Enabling & Site Works | Site Roads & Access | Not Started | 2026-06-04 08:00 | 2026-06-11 16:00 |  |  | 7 | 7 | 271 | No |  |  | 128000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | RDA-060 | Complete Final Road Surfacing | Enabling & Site Works | Site Roads & Access | Not Started | 2026-06-12 08:00 | 2026-06-15 16:00 |  |  | 3 | 3 | 271 | No |  |  | 75000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | RDA-070 | Site Roads and Access Complete | Enabling & Site Works | Site Roads & Access | Not Started | 2026-06-16 08:00 | 2026-06-16 08:00 |  |  | 0 | 0 | 271 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | DRN-010 | Set Out External Drainage Network | Enabling & Site Works | External Drainage | Not Started | 2026-04-13 08:00 | 2026-04-15 16:00 |  |  | 3 | 3 | 277 | No |  |  | 75000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | DRN-020 | Excavate Drainage Trenches | Enabling & Site Works | External Drainage | Not Started | 2026-04-16 08:00 | 2026-04-24 16:00 |  |  | 8 | 8 | 277 | No |  |  | 100000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | DRN-030 | Install Stormwater Drainage Pipework | Enabling & Site Works | External Drainage | Not Started | 2026-04-25 08:00 | 2026-05-06 16:00 |  |  | 10 | 10 | 277 | No |  |  | 143000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | DRN-040 | Install Drainage Manholes and Catch Basins | Enabling & Site Works | External Drainage | Not Started | 2026-04-18 08:00 | 2026-04-27 16:00 |  |  | 8 | 8 | 285 | No |  |  | 133000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | DRN-050 | Construct Stormwater Management Facilities | Enabling & Site Works | External Drainage | Not Started | 2026-04-18 08:00 | 2026-04-29 16:00 |  |  | 10 | 10 | 283 | No |  |  | 143000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | DRN-060 | Test and Inspect External Drainage | Enabling & Site Works | External Drainage | Not Started | 2026-05-07 08:00 | 2026-05-09 16:00 |  |  | 3 | 3 | 277 | No |  |  | 75000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | DRN-070 | Backfill Drainage Trenches | Enabling & Site Works | External Drainage | Not Started | 2026-05-11 08:00 | 2026-05-15 16:00 |  |  | 5 | 5 | 277 | No |  |  | 87000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | DRN-080 | External Drainage Complete | Enabling & Site Works | External Drainage | Not Started | 2026-05-16 08:00 | 2026-05-16 08:00 |  |  | 0 | 0 | 277 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | FND-010 | Set Out Building Foundations | Civil & Structural Works | Foundations | Not Started | 2026-05-09 08:00 | 2026-05-12 16:00 |  |  | 3 | 3 | 32 | No |  |  | 175000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | FND-020 | Excavate Building Foundations | Civil & Structural Works | Foundations | Not Started | 2026-05-13 08:00 | 2026-05-23 16:00 |  |  | 10 | 10 | 32 | No |  |  | 250000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | FND-030 | Prepare Foundation Formation | Civil & Structural Works | Foundations | Not Started | 2026-05-25 08:00 | 2026-05-29 16:00 |  |  | 5 | 5 | 32 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | FND-040 | Place Blinding Concrete | Civil & Structural Works | Foundations | Not Started | 2026-05-30 08:00 | 2026-06-02 16:00 |  |  | 3 | 3 | 32 | No |  |  | 175000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | FND-050 | Install Foundation Reinforcement | Civil & Structural Works | Foundations | Not Started | 2026-06-03 08:00 | 2026-06-13 16:00 |  |  | 10 | 10 | 32 | No |  |  | 250000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | FND-060 | Install Foundation Formwork | Civil & Structural Works | Foundations | Not Started | 2026-06-06 08:00 | 2026-06-15 16:00 |  |  | 8 | 8 | 32 | No |  |  | 234000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | FND-070 | Install Foundation Embedded Items | Civil & Structural Works | Foundations | Not Started | 2026-06-06 08:00 | 2026-06-11 16:00 |  |  | 5 | 5 | 35 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | FND-080 | Cast Foundation Concrete | Civil & Structural Works | Foundations | Not Started | 2026-06-16 08:00 | 2026-06-20 16:00 |  |  | 5 | 5 | 32 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | FND-090 | Cure Foundation Concrete | Civil & Structural Works | Foundations | Not Started | 2026-06-22 08:00 | 2026-06-29 16:00 |  |  | 7 | 7 | 32 | No |  |  | 225000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | FND-100 | Strip Foundation Formwork | Civil & Structural Works | Foundations | Not Started | 2026-06-30 08:00 | 2026-07-02 16:00 |  |  | 3 | 3 | 32 | No |  |  | 175000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | FND-110 | Backfill Around Foundations | Civil & Structural Works | Foundations | Not Started | 2026-07-20 08:00 | 2026-07-24 16:00 |  |  | 5 | 5 | 32 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | FND-120 | Building Foundations Complete | Civil & Structural Works | Foundations | Not Started | 2026-07-25 08:00 | 2026-07-25 08:00 |  |  | 0 | 0 | 32 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | SLB-010 | Prepare Ground Floor Subgrade | Civil & Structural Works | Ground Floor & Slabs | Not Started | 2026-07-25 08:00 | 2026-07-30 16:00 |  |  | 5 | 5 | 42 | No |  |  | 127000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | SLB-020 | Install Subbase and Compact | Civil & Structural Works | Ground Floor & Slabs | Not Started | 2026-07-31 08:00 | 2026-08-05 16:00 |  |  | 5 | 5 | 42 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | SLB-030 | Install Under-Slab Services | Civil & Structural Works | Ground Floor & Slabs | Not Started | 2026-08-06 08:00 | 2026-08-17 16:00 |  |  | 10 | 10 | 42 | No |  |  | 250000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | SLB-040 | Install Damp-Proof Membrane | Civil & Structural Works | Ground Floor & Slabs | Not Started | 2026-08-18 08:00 | 2026-08-20 16:00 |  |  | 3 | 3 | 42 | No |  |  | 175000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | SLB-050 | Install Ground Floor Reinforcement | Civil & Structural Works | Ground Floor & Slabs | Not Started | 2026-08-21 08:00 | 2026-08-29 16:00 |  |  | 8 | 8 | 42 | No |  |  | 234000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | SLB-060 | Install Slab Embedded Items and Openings | Civil & Structural Works | Ground Floor & Slabs | Not Started | 2026-08-25 08:00 | 2026-08-29 16:00 |  |  | 5 | 5 | 42 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | SLB-070 | Cast Ground Floor Slab | Civil & Structural Works | Ground Floor & Slabs | Not Started | 2026-08-31 08:00 | 2026-09-04 16:00 |  |  | 5 | 5 | 42 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | SLB-080 | Cure Ground Floor Slab | Civil & Structural Works | Ground Floor & Slabs | Not Started | 2026-09-05 08:00 | 2026-09-12 16:00 |  |  | 7 | 7 | 42 | No |  |  | 225000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | SLB-090 | Ground Floor Slab Complete | Civil & Structural Works | Ground Floor & Slabs | Not Started | 2026-09-14 08:00 | 2026-09-14 08:00 |  |  | 0 | 0 | 42 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | STR-010 | Mobilize Structural Steel Erection | Civil & Structural Works | Structural Frame | Not Started | 2026-07-25 08:00 | 2026-07-28 16:00 |  |  | 3 | 3 | 32 | No |  |  | 175000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | STR-020 | Erect Primary Structural Columns | Civil & Structural Works | Structural Frame | Not Started | 2026-07-29 08:00 | 2026-08-08 16:00 |  |  | 10 | 10 | 32 | No |  |  | 250000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | STR-030 | Erect Primary Structural Beams | Civil & Structural Works | Structural Frame | Not Started | 2026-08-03 08:00 | 2026-08-13 16:00 |  |  | 10 | 10 | 32 | No |  |  | 250000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | STR-040 | Install Secondary Structural Steel | Civil & Structural Works | Structural Frame | Not Started | 2026-08-07 08:00 | 2026-08-15 16:00 |  |  | 8 | 8 | 32 | No |  |  | 234000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | STR-050 | Install Structural Bracing | Civil & Structural Works | Structural Frame | Not Started | 2026-08-07 08:00 | 2026-08-12 16:00 |  |  | 5 | 5 | 35 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | STR-060 | Complete Bolting and Connections | Civil & Structural Works | Structural Frame | Not Started | 2026-08-17 08:00 | 2026-08-20 16:00 |  |  | 4 | 4 | 32 | No |  |  | 119000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | STR-070 | Structural Alignment and Inspection | Civil & Structural Works | Structural Frame | Not Started | 2026-08-21 08:00 | 2026-08-24 16:00 |  |  | 3 | 3 | 32 | No |  |  | 131000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | STR-080 | Structural Frame Complete | Civil & Structural Works | Structural Frame | Not Started | 2026-08-25 08:00 | 2026-08-25 08:00 |  |  | 0 | 0 | 32 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | DHS-010 | Construct Data Hall Structural Frame | Civil & Structural Works | Data Hall Structure | Not Started | 2026-08-08 08:00 | 2026-08-25 16:00 |  |  | 15 | 15 | 59 | No |  |  | 295000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | DHS-020 | Install Data Hall Floor Structure | Civil & Structural Works | Data Hall Structure | Not Started | 2026-08-14 08:00 | 2026-08-22 16:00 |  |  | 8 | 8 | 61 | No |  |  | 234000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | DHS-030 | Install Data Hall Roof Support Structure | Civil & Structural Works | Data Hall Structure | Not Started | 2026-08-17 08:00 | 2026-08-25 16:00 |  |  | 8 | 8 | 59 | No |  |  | 234000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | DHS-040 | Install Data Hall Equipment Support Steel | Civil & Structural Works | Data Hall Structure | Not Started | 2026-08-17 08:00 | 2026-08-21 16:00 |  |  | 5 | 5 | 62 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | DHS-050 | Complete Data Hall Structural Connections | Civil & Structural Works | Data Hall Structure | Not Started | 2026-08-26 08:00 | 2026-08-29 16:00 |  |  | 4 | 4 | 59 | No |  |  | 119000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | DHS-060 | Inspect Data Hall Structure | Civil & Structural Works | Data Hall Structure | Not Started | 2026-08-31 08:00 | 2026-09-02 16:00 |  |  | 3 | 3 | 59 | No |  |  | 131000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | DHS-070 | Data Hall Structure Complete | Civil & Structural Works | Data Hall Structure | Not Started | 2026-09-03 08:00 | 2026-09-03 08:00 |  |  | 0 | 0 | 59 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | EUS-010 | Construct Electrical Room Structure | Civil & Structural Works | Electrical & UPS Rooms Structure | Not Started | 2026-09-14 08:00 | 2026-09-24 16:00 |  |  | 10 | 10 | 42 | No |  |  | 250000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | EUS-020 | Construct UPS and Battery Room Structure | Civil & Structural Works | Electrical & UPS Rooms Structure | Not Started | 2026-09-14 08:00 | 2026-09-24 16:00 |  |  | 10 | 10 | 42 | No |  |  | 250000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | EUS-030 | Construct MV and LV Switchgear Room Structure | Civil & Structural Works | Electrical & UPS Rooms Structure | Not Started | 2026-09-14 08:00 | 2026-09-24 16:00 |  |  | 10 | 10 | 42 | No |  |  | 250000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | EUS-040 | Construct Transformer Room Structure | Civil & Structural Works | Electrical & UPS Rooms Structure | Not Started | 2026-09-14 08:00 | 2026-09-24 16:00 |  |  | 10 | 10 | 42 | No |  |  | 250000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | EUS-050 | Install Equipment Support Steel | Civil & Structural Works | Electrical & UPS Rooms Structure | Not Started | 2026-09-25 08:00 | 2026-09-30 16:00 |  |  | 5 | 5 | 42 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | EUS-060 | Complete Equipment Access Openings | Civil & Structural Works | Electrical & UPS Rooms Structure | Not Started | 2026-10-01 08:00 | 2026-10-03 16:00 |  |  | 3 | 3 | 42 | No |  |  | 109000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | EUS-070 | Electrical and UPS Rooms Structure Complete | Civil & Structural Works | Electrical & UPS Rooms Structure | Not Started | 2026-10-05 08:00 | 2026-10-05 08:00 |  |  | 0 | 0 | 42 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | GUS-010 | Construct Generator Foundations | Civil & Structural Works | Generator & Utility Structures | Not Started | 2026-07-25 08:00 | 2026-08-05 16:00 |  |  | 10 | 10 | 118 | No |  |  | 250000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | GUS-020 | Construct Generator Support Structures | Civil & Structural Works | Generator & Utility Structures | Not Started | 2026-08-06 08:00 | 2026-08-14 16:00 |  |  | 8 | 8 | 118 | No |  |  | 234000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | GUS-030 | Construct Utility and MV Structures | Civil & Structural Works | Generator & Utility Structures | Not Started | 2026-08-06 08:00 | 2026-08-14 16:00 |  |  | 8 | 8 | 123 | No |  |  | 234000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | GUS-040 | Construct Fuel System Structural Supports | Civil & Structural Works | Generator & Utility Structures | Not Started | 2026-08-06 08:00 | 2026-08-11 16:00 |  |  | 5 | 5 | 121 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | GUS-050 | Install Generator Equipment Plinths | Civil & Structural Works | Generator & Utility Structures | Not Started | 2026-08-15 08:00 | 2026-08-20 16:00 |  |  | 5 | 5 | 118 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | GUS-060 | Generator and Utility Structures Complete | Civil & Structural Works | Generator & Utility Structures | Not Started | 2026-08-21 08:00 | 2026-08-21 08:00 |  |  | 0 | 0 | 118 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CPS-010 | Construct Cooling Plant Foundations | Civil & Structural Works | Cooling Plant Structures | Not Started | 2026-07-25 08:00 | 2026-08-05 16:00 |  |  | 10 | 10 | 44 | No |  |  | 250000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CPS-020 | Construct Chiller Equipment Bases | Civil & Structural Works | Cooling Plant Structures | Not Started | 2026-08-06 08:00 | 2026-08-11 16:00 |  |  | 5 | 5 | 55 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CPS-030 | Construct Pump Equipment Bases | Civil & Structural Works | Cooling Plant Structures | Not Started | 2026-08-06 08:00 | 2026-08-11 16:00 |  |  | 5 | 5 | 55 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CPS-040 | Construct Cooling Plant Structural Supports | Civil & Structural Works | Cooling Plant Structures | Not Started | 2026-08-06 08:00 | 2026-08-14 16:00 |  |  | 8 | 8 | 44 | No |  |  | 234000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CPS-050 | Install Pipework Support Structures | Civil & Structural Works | Cooling Plant Structures | Not Started | 2026-08-15 08:00 | 2026-08-24 16:00 |  |  | 8 | 8 | 44 | No |  |  | 234000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CPS-060 | Cooling Plant Structures Complete | Civil & Structural Works | Cooling Plant Structures | Not Started | 2026-08-25 08:00 | 2026-08-25 08:00 |  |  | 0 | 0 | 44 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | RFS-010 | Confirm Operational Readiness | Client Acceptance & Handover | Final Acceptance & Project Closeout | Not Started | 2027-07-13 08:00 | 2027-07-19 16:00 |  |  | 5 | 5 | 0 | Yes | 1 | 55 | 29000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | RFS-020 | Confirm Systems Acceptance | Client Acceptance & Handover | Final Acceptance & Project Closeout | Not Started | 2027-06-16 08:00 | 2027-06-22 16:00 |  |  | 5 | 5 | 19 | No |  |  | 29000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | RFS-030 | Confirm Documentation and Training Complete | Client Acceptance & Handover | Final Acceptance & Project Closeout | Not Started | 2027-05-11 16:00 | 2027-05-11 16:00 |  |  | 0 | 0 | 49 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | RFS-040 | Ready for Service | Client Acceptance & Handover | Final Acceptance & Project Closeout | Not Started | 2027-07-19 16:00 | 2027-07-19 16:00 |  |  | 0 | 0 | 0 | Yes | 1 | 56 | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | RFS-050 | Complete Roof Structural Connections | Civil & Structural Works | Roof Structure | Not Started | 2026-08-25 08:00 | 2026-08-29 16:00 |  |  | 5 | 5 | 32 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | RFS-060 | Inspect Roof Structure | Civil & Structural Works | Roof Structure | Not Started | 2026-08-31 08:00 | 2026-09-02 16:00 |  |  | 3 | 3 | 32 | No |  |  | 175000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | RFS-070 | Roof Structure Complete | Civil & Structural Works | Roof Structure | Not Started | 2026-09-03 08:00 | 2026-09-03 08:00 |  |  | 0 | 0 | 32 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | EPF-010 | Confirm Equipment Foundation Requirements | Civil & Structural Works | Equipment Plinths & Foundations | Not Started | 2026-09-14 08:00 | 2026-09-18 16:00 |  |  | 5 | 5 | 55 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | EPF-020 | Set Out Equipment Foundations and Plinths | Civil & Structural Works | Equipment Plinths & Foundations | Not Started | 2026-09-19 08:00 | 2026-09-22 16:00 |  |  | 3 | 3 | 55 | No |  |  | 175000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | EPF-030 | Construct Transformer Plinths | Civil & Structural Works | Equipment Plinths & Foundations | Not Started | 2026-09-23 08:00 | 2026-09-28 16:00 |  |  | 5 | 5 | 55 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | EPF-040 | Construct Switchgear and UPS Equipment Plinths | Civil & Structural Works | Equipment Plinths & Foundations | Not Started | 2026-09-23 08:00 | 2026-09-28 16:00 |  |  | 5 | 5 | 55 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | EPF-050 | Construct Generator Equipment Plinths | Civil & Structural Works | Equipment Plinths & Foundations | Not Started | 2026-09-23 08:00 | 2026-09-28 16:00 |  |  | 5 | 5 | 55 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | EPF-060 | Construct Cooling Equipment Plinths | Civil & Structural Works | Equipment Plinths & Foundations | Not Started | 2026-09-23 08:00 | 2026-09-28 16:00 |  |  | 5 | 5 | 55 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | EPF-070 | Install Equipment Anchor Bolts and Embedded Plates | Civil & Structural Works | Equipment Plinths & Foundations | Not Started | 2026-09-29 08:00 | 2026-10-03 16:00 |  |  | 5 | 5 | 55 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | EPF-080 | Inspect Equipment Foundations and Plinths | Civil & Structural Works | Equipment Plinths & Foundations | Not Started | 2026-10-05 08:00 | 2026-10-07 16:00 |  |  | 3 | 3 | 55 | No |  |  | 175000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | EPF-090 | Equipment Foundations Ready for Installation | Civil & Structural Works | Equipment Plinths & Foundations | Not Started | 2026-10-08 08:00 | 2026-10-08 08:00 |  |  | 0 | 0 | 55 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CLD-010 | Set Out External Wall and Cladding System | Building Envelope | External Walls & Cladding | Not Started | 2026-08-08 08:00 | 2026-08-11 16:00 |  |  | 3 | 3 | 48 | No |  |  | 113000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CLD-020 | Install External Wall Framing and Supports | Building Envelope | External Walls & Cladding | Not Started | 2026-08-12 08:00 | 2026-08-22 16:00 |  |  | 10 | 10 | 48 | No |  |  | 163000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CLD-030 | Install External Wall Insulation | Building Envelope | External Walls & Cladding | Not Started | 2026-08-15 08:00 | 2026-08-24 16:00 |  |  | 8 | 8 | 48 | No |  |  | 152000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CLD-040 | Install External Cladding Panels | Building Envelope | External Walls & Cladding | Not Started | 2026-08-19 08:00 | 2026-09-01 16:00 |  |  | 12 | 12 | 48 | No |  |  | 177000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CLD-050 | Install Flashings and Interface Seals | Building Envelope | External Walls & Cladding | Not Started | 2026-08-27 08:00 | 2026-09-01 16:00 |  |  | 5 | 5 | 48 | No |  |  | 132000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CLD-060 | Complete Cladding Joint Sealing | Building Envelope | External Walls & Cladding | Not Started | 2026-09-02 08:00 | 2026-09-04 16:00 |  |  | 3 | 3 | 48 | No |  |  | 113000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CLD-070 | Inspect External Walls and Cladding | Building Envelope | External Walls & Cladding | Not Started | 2026-09-05 08:00 | 2026-09-07 16:00 |  |  | 2 | 2 | 48 | No |  |  | 100000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CLD-080 | External Walls and Cladding Complete | Building Envelope | External Walls & Cladding | Not Started | 2026-09-08 08:00 | 2026-09-08 08:00 |  |  | 0 | 0 | 48 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | ROF-010 | Prepare Roof Deck for Roofing Works | Building Envelope | Roofing System | Not Started | 2026-09-03 08:00 | 2026-09-05 16:00 |  |  | 3 | 3 | 32 | No |  |  | 113000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | ROF-020 | Install Roof Vapour Control Layer | Building Envelope | Roofing System | Not Started | 2026-09-07 08:00 | 2026-09-11 16:00 |  |  | 5 | 5 | 32 | No |  |  | 132000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | ROF-030 | Install Roof Insulation | Building Envelope | Roofing System | Not Started | 2026-09-09 08:00 | 2026-09-14 16:00 |  |  | 5 | 5 | 32 | No |  |  | 132000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | ROF-040 | Install Roofing Membrane | Building Envelope | Roofing System | Not Started | 2026-09-11 08:00 | 2026-09-19 16:00 |  |  | 8 | 8 | 32 | No |  |  | 152000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | ROF-050 | Install Roof Flashings and Upstands | Building Envelope | Roofing System | Not Started | 2026-09-15 08:00 | 2026-09-19 16:00 |  |  | 5 | 5 | 32 | No |  |  | 132000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | ROF-060 | Seal Roof Equipment Penetrations | Building Envelope | Roofing System | Not Started | 2026-09-21 08:00 | 2026-09-23 16:00 |  |  | 3 | 3 | 32 | No |  |  | 113000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | ROF-070 | Inspect and Test Roofing System | Building Envelope | Roofing System | Not Started | 2026-09-24 08:00 | 2026-09-25 16:00 |  |  | 2 | 2 | 32 | No |  |  | 100000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | ROF-080 | Roofing System Complete | Building Envelope | Roofing System | Not Started | 2026-09-26 08:00 | 2026-09-26 08:00 |  |  | 0 | 0 | 32 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | WPF-010 | Prepare Surfaces for Waterproofing | Building Envelope | Waterproofing | Not Started | 2026-07-03 08:00 | 2026-07-04 16:00 |  |  | 2 | 2 | 32 | No |  |  | 100000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | WPF-020 | Apply Foundation Waterproofing | Building Envelope | Waterproofing | Not Started | 2026-07-06 08:00 | 2026-07-10 16:00 |  |  | 5 | 5 | 32 | No |  |  | 132000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | WPF-030 | Apply Below-Grade Wall Waterproofing | Building Envelope | Waterproofing | Not Started | 2026-07-08 08:00 | 2026-07-13 16:00 |  |  | 5 | 5 | 32 | No |  |  | 132000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | WPF-040 | Waterproof Service Penetrations | Building Envelope | Waterproofing | Not Started | 2026-07-10 08:00 | 2026-07-13 16:00 |  |  | 3 | 3 | 32 | No |  |  | 113000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | WPF-050 | Install Waterproofing Protection Layer | Building Envelope | Waterproofing | Not Started | 2026-07-14 08:00 | 2026-07-16 16:00 |  |  | 3 | 3 | 32 | No |  |  | 113000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | WPF-060 | Inspect and Test Waterproofing Works | Building Envelope | Waterproofing | Not Started | 2026-07-17 08:00 | 2026-07-18 16:00 |  |  | 2 | 2 | 32 | No |  |  | 100000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | WPF-070 | Waterproofing Complete | Building Envelope | Waterproofing | Not Started | 2026-07-20 08:00 | 2026-07-20 08:00 |  |  | 0 | 0 | 32 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | EDL-010 | Prepare External Door and Louver Openings | Building Envelope | External Doors & Louvers | Not Started | 2026-08-15 08:00 | 2026-08-18 16:00 |  |  | 3 | 3 | 49 | No |  |  | 71000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | EDL-020 | Install External Door Frames | Building Envelope | External Doors & Louvers | Not Started | 2026-08-19 08:00 | 2026-08-24 16:00 |  |  | 5 | 5 | 49 | No |  |  | 132000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | EDL-030 | Install External Doors | Building Envelope | External Doors & Louvers | Not Started | 2026-08-21 08:00 | 2026-08-26 16:00 |  |  | 5 | 5 | 49 | No |  |  | 132000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | EDL-040 | Install External Louvers | Building Envelope | External Doors & Louvers | Not Started | 2026-08-21 08:00 | 2026-08-26 16:00 |  |  | 5 | 5 | 53 | No |  |  | 132000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | EDL-050 | Install Door Hardware and Security Interfaces | Building Envelope | External Doors & Louvers | Not Started | 2026-08-27 08:00 | 2026-08-31 16:00 |  |  | 4 | 4 | 49 | No |  |  | 124000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | EDL-060 | Seal Door and Louver Interfaces | Building Envelope | External Doors & Louvers | Not Started | 2026-09-01 08:00 | 2026-09-03 16:00 |  |  | 3 | 3 | 49 | No |  |  | 71000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | EDL-070 | Inspect External Doors and Louvers | Building Envelope | External Doors & Louvers | Not Started | 2026-09-04 08:00 | 2026-09-05 16:00 |  |  | 2 | 2 | 49 | No |  |  | 75000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | EDL-080 | External Doors and Louvers Complete | Building Envelope | External Doors & Louvers | Not Started | 2026-09-07 08:00 | 2026-09-07 08:00 |  |  | 0 | 0 | 49 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | PAR-010 | Set Out Internal Partitions | Building Envelope | Internal Partitions & Fire-Rated Enclosures | Not Started | 2026-09-14 08:00 | 2026-09-17 16:00 |  |  | 4 | 4 | 67 | No |  |  | 77000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | PAR-020 | Install Internal Partition Framing | Building Envelope | Internal Partitions & Fire-Rated Enclosures | Not Started | 2026-09-18 08:00 | 2026-09-26 16:00 |  |  | 8 | 8 | 67 | No |  |  | 152000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | PAR-030 | Install Fire-Rated Wall Systems | Building Envelope | Internal Partitions & Fire-Rated Enclosures | Not Started | 2026-09-22 08:00 | 2026-09-28 16:00 |  |  | 6 | 6 | 67 | No |  |  | 140000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | PAR-040 | Construct Electrical Room Fire-Rated Enclosures | Building Envelope | Internal Partitions & Fire-Rated Enclosures | Not Started | 2026-09-24 08:00 | 2026-10-02 16:00 |  |  | 8 | 8 | 69 | No |  |  | 152000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | PAR-050 | Construct UPS and Battery Room Fire-Rated Enclosures | Building Envelope | Internal Partitions & Fire-Rated Enclosures | Not Started | 2026-09-24 08:00 | 2026-10-02 16:00 |  |  | 8 | 8 | 69 | No |  |  | 152000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | PAR-060 | Construct Data Hall Fire-Rated Enclosures | Building Envelope | Internal Partitions & Fire-Rated Enclosures | Not Started | 2026-09-24 08:00 | 2026-10-05 16:00 |  |  | 10 | 10 | 67 | No |  |  | 163000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | PAR-070 | Install Fire-Stopping at Service Penetrations | Building Envelope | Internal Partitions & Fire-Rated Enclosures | Not Started | 2026-09-30 08:00 | 2026-10-05 16:00 |  |  | 5 | 5 | 67 | No |  |  | 132000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | PAR-080 | Inspect Fire-Rated Partitions and Enclosures | Building Envelope | Internal Partitions & Fire-Rated Enclosures | Not Started | 2026-10-06 08:00 | 2026-10-07 16:00 |  |  | 2 | 2 | 67 | No |  |  | 75000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | PAR-090 | Internal Partitions and Fire-Rated Enclosures Complete | Building Envelope | Internal Partitions & Fire-Rated Enclosures | Not Started | 2026-10-08 08:00 | 2026-10-08 08:00 |  |  | 0 | 0 | 67 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | ENV-010 | Inspect Building Envelope Interfaces | Building Envelope | Weather-Tightness & Envelope Completion | Not Started | 2026-09-26 08:00 | 2026-09-28 16:00 |  |  | 2 | 2 | 32 | No |  |  | 75000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | ENV-020 | Perform Roof Water-Tightness Testing | Building Envelope | Weather-Tightness & Envelope Completion | Not Started | 2026-09-29 08:00 | 2026-10-01 16:00 |  |  | 3 | 3 | 32 | No |  |  | 113000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | ENV-030 | Perform External Wall Water-Tightness Testing | Building Envelope | Weather-Tightness & Envelope Completion | Not Started | 2026-09-29 08:00 | 2026-10-01 16:00 |  |  | 3 | 3 | 32 | No |  |  | 85000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | ENV-040 | Inspect Doors Louvers and Penetration Seals | Building Envelope | Weather-Tightness & Envelope Completion | Not Started | 2026-09-29 08:00 | 2026-09-30 16:00 |  |  | 2 | 2 | 33 | No |  |  | 75000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | ENV-050 | Rectify Building Envelope Defects | Building Envelope | Weather-Tightness & Envelope Completion | Not Started | 2026-10-02 08:00 | 2026-10-07 16:00 |  |  | 5 | 5 | 32 | No |  |  | 83000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | ENV-060 | Complete Final Building Envelope Inspection | Building Envelope | Weather-Tightness & Envelope Completion | Not Started | 2026-10-08 08:00 | 2026-10-09 16:00 |  |  | 2 | 2 | 32 | No |  |  | 75000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | ENV-070 | Building Weather-Tight | Building Envelope | Weather-Tightness & Envelope Completion | Not Started | 2026-10-10 08:00 | 2026-10-10 08:00 |  |  | 0 | 0 | 32 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | MV-010 | Set Out MV Power Infrastructure | Electrical Systems | Utility / MV Power Infrastructure | Not Started | 2026-05-19 08:00 | 2026-05-20 16:00 |  |  | 2 | 2 | 139 | No |  |  | 118000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | MV-020 | Install MV Cable Duct Banks | Electrical Systems | Utility / MV Power Infrastructure | Not Started | 2026-05-21 08:00 | 2026-06-06 16:00 |  |  | 15 | 15 | 139 | No |  |  | 352000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | MV-030 | Install MV Cable Chambers and Pull Pits | Electrical Systems | Utility / MV Power Infrastructure | Not Started | 2026-05-27 08:00 | 2026-06-06 16:00 |  |  | 10 | 10 | 139 | No |  |  | 307000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | MV-040 | Install Incoming MV Cables | Electrical Systems | Utility / MV Power Infrastructure | Not Started | 2026-06-08 08:00 | 2026-06-18 16:00 |  |  | 10 | 10 | 139 | No |  |  | 307000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | MV-050 | Terminate Incoming MV Cables | Electrical Systems | Utility / MV Power Infrastructure | Not Started | 2026-06-19 08:00 | 2026-06-24 16:00 |  |  | 5 | 5 | 139 | No |  |  | 249000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | MV-060 | Test Incoming MV Cable System | Electrical Systems | Utility / MV Power Infrastructure | Not Started | 2026-06-25 08:00 | 2026-06-27 16:00 |  |  | 3 | 3 | 139 | No |  |  | 214000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | MV-070 | MV Power Infrastructure Ready | Electrical Systems | Utility / MV Power Infrastructure | Not Started | 2026-06-27 16:00 | 2026-06-27 16:00 |  |  | 0 | 0 | 139 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | MVSG-010 | Prepare MV Switchgear Room for Installation | Electrical Systems | MV Switchgear | Not Started | 2026-10-10 08:00 | 2026-10-13 16:00 |  |  | 3 | 3 | 37 | No |  |  | 214000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | MVSG-020 | Receive and Inspect MV Switchgear | Electrical Systems | MV Switchgear | Not Started | 2026-10-24 08:00 | 2026-10-26 16:00 |  |  | 2 | 2 | 26 | No |  |  | 142000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | MVSG-030 | Position and Install MV Switchgear | Electrical Systems | MV Switchgear | Not Started | 2026-10-27 08:00 | 2026-10-31 16:00 |  |  | 5 | 5 | 26 | No |  |  | 249000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | MVSG-040 | Assemble MV Switchgear Sections | Electrical Systems | MV Switchgear | Not Started | 2026-11-02 08:00 | 2026-11-06 16:00 |  |  | 5 | 5 | 26 | No |  |  | 156000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | MVSG-050 | Install MV Switchgear Control Wiring | Electrical Systems | MV Switchgear | Not Started | 2026-11-04 08:00 | 2026-11-09 16:00 |  |  | 5 | 5 | 29 | No |  |  | 249000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | MVSG-060 | Terminate MV Power Cables | Electrical Systems | MV Switchgear | Not Started | 2026-11-07 08:00 | 2026-11-12 16:00 |  |  | 5 | 5 | 26 | No |  |  | 249000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | MVSG-070 | Complete MV Switchgear Installation Inspection | Electrical Systems | MV Switchgear | Not Started | 2026-11-13 08:00 | 2026-11-14 16:00 |  |  | 2 | 2 | 26 | No |  |  | 189000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | MVSG-080 | MV Switchgear Ready for Pre-Commissioning | Electrical Systems | MV Switchgear | Not Started | 2026-11-14 16:00 | 2026-11-14 16:00 |  |  | 0 | 0 | 26 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | TRI-010 | Prepare Transformer Areas for Installation | Electrical Systems | Transformers | Not Started | 2026-10-08 08:00 | 2026-10-10 16:00 |  |  | 3 | 3 | 55 | No |  |  | 214000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | TRI-020 | Receive and Inspect Transformers | Electrical Systems | Transformers | Not Started | 2026-12-12 08:00 | 2026-12-14 16:00 |  |  | 2 | 2 | 0 | Yes | 1 | 12 | 142000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | TRI-030 | Position Transformers on Plinths | Electrical Systems | Transformers | Not Started | 2026-12-15 08:00 | 2026-12-17 16:00 |  |  | 3 | 3 | 0 | Yes | 1 | 13 | 134000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | TRI-040 | Install Transformer Ancillary Equipment | Electrical Systems | Transformers | Not Started | 2026-12-18 08:00 | 2026-12-23 16:00 |  |  | 5 | 5 | 0 | Yes | 10 | 1 | 249000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | TRI-050 | Complete MV Transformer Connections | Electrical Systems | Transformers | Not Started | 2026-12-18 08:00 | 2026-12-21 16:00 |  |  | 3 | 3 | 2 | No |  |  | 134000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | TRI-060 | Complete LV Transformer Connections | Electrical Systems | Transformers | Not Started | 2026-12-18 08:00 | 2026-12-21 16:00 |  |  | 3 | 3 | 0 | Yes | 1 | 14 | 134000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | TRI-070 | Complete Transformer Installation Inspection | Electrical Systems | Transformers | Not Started | 2026-12-24 08:00 | 2026-12-25 16:00 |  |  | 2 | 2 | 0 | Yes | 10 | 2 | 189000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | TRI-080 | Transformers Ready for Pre-Commissioning | Electrical Systems | Transformers | Not Started | 2026-12-25 16:00 | 2026-12-25 16:00 |  |  | 0 | 0 | 0 | Yes | 10 | 3 | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | SGI-010 | Prepare Generator Areas for Installation | Electrical Systems | Standby Generator System | Not Started | 2026-08-21 08:00 | 2026-08-24 16:00 |  |  | 3 | 3 | 118 | No |  |  | 214000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | SGI-020 | Receive and Inspect Standby Generators | Electrical Systems | Standby Generator System | Not Started | 2026-12-12 08:00 | 2026-12-14 16:00 |  |  | 2 | 2 | 22 | No |  |  | 142000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | SGI-030 | Position Standby Generators on Plinths | Electrical Systems | Standby Generator System | Not Started | 2026-12-15 08:00 | 2026-12-19 16:00 |  |  | 5 | 5 | 22 | No |  |  | 156000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | SGI-040 | Install Generator Exhaust Systems | Electrical Systems | Standby Generator System | Not Started | 2026-12-21 08:00 | 2026-12-28 16:00 |  |  | 7 | 7 | 23 | No |  |  | 276000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | SGI-050 | Install Generator Fuel System Connections | Electrical Systems | Standby Generator System | Not Started | 2026-12-21 08:00 | 2026-12-28 16:00 |  |  | 7 | 7 | 23 | No |  |  | 276000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | SGI-060 | Install Generator Power Connections | Electrical Systems | Standby Generator System | Not Started | 2026-12-21 08:00 | 2026-12-25 16:00 |  |  | 5 | 5 | 25 | No |  |  | 249000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | SGI-070 | Install Generator Control Connections | Electrical Systems | Standby Generator System | Not Started | 2026-12-21 08:00 | 2026-12-25 16:00 |  |  | 5 | 5 | 25 | No |  |  | 249000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | SGI-080 | Complete Generator Installation Inspection | Electrical Systems | Standby Generator System | Not Started | 2026-12-29 08:00 | 2026-12-30 16:00 |  |  | 2 | 2 | 23 | No |  |  | 189000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | SGI-090 | Standby Generators Ready for Pre-Commissioning | Electrical Systems | Standby Generator System | Not Started | 2026-12-30 16:00 | 2026-12-30 16:00 |  |  | 0 | 0 | 23 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | LV-010 | Prepare LV Electrical Rooms for Installation | Electrical Systems | LV Main Distribution | Not Started | 2026-10-10 08:00 | 2026-10-13 16:00 |  |  | 3 | 3 | 42 | No |  |  | 214000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | LV-020 | Receive and Inspect LV Switchgear | Electrical Systems | LV Main Distribution | Not Started | 2026-10-24 08:00 | 2026-10-26 16:00 |  |  | 2 | 2 | 38 | No |  |  | 142000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | LV-030 | Position and Install LV Switchgear | Electrical Systems | LV Main Distribution | Not Started | 2026-10-27 08:00 | 2026-10-31 16:00 |  |  | 5 | 5 | 38 | No |  |  | 249000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | LV-040 | Install Main LV Cable Containment | Electrical Systems | LV Main Distribution | Not Started | 2026-10-14 08:00 | 2026-10-22 16:00 |  |  | 8 | 8 | 42 | No |  |  | 287000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | LV-050 | Install Main LV Power Cables | Electrical Systems | LV Main Distribution | Not Started | 2026-10-16 08:00 | 2026-10-27 16:00 |  |  | 10 | 10 | 42 | No |  |  | 307000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | LV-060 | Terminate Main LV Power Cables | Electrical Systems | LV Main Distribution | Not Started | 2026-11-02 08:00 | 2026-11-06 16:00 |  |  | 5 | 5 | 38 | No |  |  | 249000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | LV-070 | Install LV Control and Interlock Wiring | Electrical Systems | LV Main Distribution | Not Started | 2026-11-02 08:00 | 2026-11-06 16:00 |  |  | 5 | 5 | 38 | No |  |  | 249000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | LV-080 | Complete LV Distribution Installation Inspection | Electrical Systems | LV Main Distribution | Not Started | 2026-12-22 08:00 | 2026-12-23 16:00 |  |  | 2 | 2 | 0 | Yes | 1 | 15 | 189000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | LV-090 | LV Main Distribution Ready for Pre-Commissioning | Electrical Systems | LV Main Distribution | Not Started | 2026-12-23 16:00 | 2026-12-23 16:00 |  |  | 0 | 0 | 0 | Yes | 1 | 16 | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | UPSI-010 | Prepare UPS and Battery Rooms for Installation | Electrical Systems | UPS Systems & Batteries | Not Started | 2026-10-10 08:00 | 2026-10-13 16:00 |  |  | 3 | 3 | 54 | No |  |  | 214000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | UPSI-020 | Receive and Inspect UPS Equipment | Electrical Systems | UPS Systems & Batteries | Not Started | 2026-10-24 08:00 | 2026-10-26 16:00 |  |  | 2 | 2 | 45 | No |  |  | 142000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | UPSI-030 | Install UPS Units | Electrical Systems | UPS Systems & Batteries | Not Started | 2026-10-27 08:00 | 2026-10-31 16:00 |  |  | 5 | 5 | 45 | No |  |  | 249000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | UPSI-040 | Install Battery Racks and Cabinets | Electrical Systems | UPS Systems & Batteries | Not Started | 2026-10-14 08:00 | 2026-10-19 16:00 |  |  | 5 | 5 | 54 | No |  |  | 249000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | UPSI-050 | Install Battery Systems | Electrical Systems | UPS Systems & Batteries | Not Started | 2026-10-20 08:00 | 2026-10-27 16:00 |  |  | 7 | 7 | 54 | No |  |  | 276000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | UPSI-060 | Install UPS Input and Output Power Connections | Electrical Systems | UPS Systems & Batteries | Not Started | 2026-12-24 08:00 | 2026-12-29 16:00 |  |  | 5 | 5 | 0 | Yes | 1 | 17 | 249000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | UPSI-070 | Install UPS Control and Monitoring Connections | Electrical Systems | UPS Systems & Batteries | Not Started | 2026-11-02 08:00 | 2026-11-06 16:00 |  |  | 5 | 5 | 45 | No |  |  | 31000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | UPSI-080 | Complete UPS and Battery Installation Inspection | Electrical Systems | UPS Systems & Batteries | Not Started | 2026-12-30 08:00 | 2026-12-31 16:00 |  |  | 2 | 2 | 0 | Yes | 1 | 18 | 189000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | UPSI-090 | UPS and Battery Systems Ready for Pre-Commissioning | Electrical Systems | UPS Systems & Batteries | Not Started | 2026-12-31 16:00 | 2026-12-31 16:00 |  |  | 0 | 0 | 0 | Yes | 1 | 19 | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | BUS-010 | Set Out PDU and Busway Routes | Electrical Systems | PDUs & Busway Distribution | Not Started | 2026-09-03 08:00 | 2026-09-05 16:00 |  |  | 3 | 3 | 72 | No |  |  | 214000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | BUS-020 | Install Busway Support Systems | Electrical Systems | PDUs & Busway Distribution | Not Started | 2026-09-07 08:00 | 2026-09-17 16:00 |  |  | 10 | 10 | 72 | No |  |  | 307000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | BUS-030 | Install Main Busway Distribution | Electrical Systems | PDUs & Busway Distribution | Not Started | 2026-09-10 08:00 | 2026-09-26 16:00 |  |  | 15 | 15 | 72 | No |  |  | 347000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | BUS-040 | Install Power Distribution Units | Electrical Systems | PDUs & Busway Distribution | Not Started | 2026-09-19 08:00 | 2026-09-26 16:00 |  |  | 7 | 7 | 72 | No |  |  | 276000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | BUS-050 | Install Busway Tap-Off Units | Electrical Systems | PDUs & Busway Distribution | Not Started | 2026-09-28 08:00 | 2026-10-08 16:00 |  |  | 10 | 10 | 72 | No |  |  | 307000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | BUS-060 | Complete Busway and PDU Connections | Electrical Systems | PDUs & Busway Distribution | Not Started | 2027-01-01 08:00 | 2027-01-06 16:00 |  |  | 5 | 5 | 0 | Yes | 1 | 20 | 249000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | BUS-070 | Inspect PDU and Busway Installation | Electrical Systems | PDUs & Busway Distribution | Not Started | 2027-01-07 08:00 | 2027-01-08 16:00 |  |  | 2 | 2 | 13 | No |  |  | 189000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | BUS-080 | PDU and Busway Distribution Ready for Pre-Commissioning | Electrical Systems | PDUs & Busway Distribution | Not Started | 2027-01-08 16:00 | 2027-01-08 16:00 |  |  | 0 | 0 | 13 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | DHP-010 | Install Data Hall Cable Containment | Electrical Systems | Data Hall Power Distribution | Not Started | 2026-09-03 08:00 | 2026-09-14 16:00 |  |  | 10 | 10 | 90 | No |  |  | 307000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | DHP-020 | Install Data Hall Power Distribution Cables | Electrical Systems | Data Hall Power Distribution | Not Started | 2026-09-07 08:00 | 2026-09-23 16:00 |  |  | 15 | 15 | 90 | No |  |  | 347000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | DHP-030 | Install Rack Power Distribution Connections | Electrical Systems | Data Hall Power Distribution | Not Started | 2026-09-28 08:00 | 2026-10-08 16:00 |  |  | 10 | 10 | 77 | No |  |  | 307000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | DHP-040 | Install Data Hall Power Monitoring Devices | Electrical Systems | Data Hall Power Distribution | Not Started | 2026-09-15 08:00 | 2026-09-22 16:00 |  |  | 7 | 7 | 101 | No |  |  | 34000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | DHP-050 | Terminate Data Hall Power Circuits | Electrical Systems | Data Hall Power Distribution | Not Started | 2027-01-07 08:00 | 2027-01-18 16:00 |  |  | 10 | 10 | 0 | Yes | 1 | 21 | 307000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | DHP-060 | Test Data Hall Distribution Circuits | Electrical Systems | Data Hall Power Distribution | Not Started | 2027-01-19 08:00 | 2027-01-23 16:00 |  |  | 5 | 5 | 0 | Yes | 1 | 22 | 187000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | DHP-070 | Data Hall Power Distribution Ready for Pre-Commissioning | Electrical Systems | Data Hall Power Distribution | Not Started | 2027-01-23 16:00 | 2027-01-23 16:00 |  |  | 0 | 0 | 0 | Yes | 1 | 23 | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | LPS-010 | Install Roof Lightning Protection Network | Electrical Systems | Lightning Protection | Not Started | 2026-09-21 08:00 | 2026-09-28 16:00 |  |  | 7 | 7 | 98 | No |  |  | 276000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | LPS-020 | Install Lightning Protection Down Conductors | Electrical Systems | Lightning Protection | Not Started | 2026-09-23 08:00 | 2026-09-28 16:00 |  |  | 5 | 5 | 98 | No |  |  | 249000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | LPS-030 | Connect Lightning Protection to Earth Network | Electrical Systems | Lightning Protection | Not Started | 2026-09-29 08:00 | 2026-10-01 16:00 |  |  | 3 | 3 | 98 | No |  |  | 134000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | LPS-040 | Test Lightning Protection System | Electrical Systems | Lightning Protection | Not Started | 2026-10-02 08:00 | 2026-10-03 16:00 |  |  | 2 | 2 | 98 | No |  |  | 142000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | LPS-050 | Lightning Protection System Complete | Electrical Systems | Lightning Protection | Not Started | 2026-10-03 16:00 | 2026-10-03 16:00 |  |  | 0 | 0 | 98 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | ERT-010 | Install Main Site Earthing Grid | Electrical Systems | Earthing & Bonding | Not Started | 2026-04-13 08:00 | 2026-04-23 16:00 |  |  | 10 | 10 | 215 | No |  |  | 307000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | ERT-020 | Install Building Earthing Network | Electrical Systems | Earthing & Bonding | Not Started | 2026-06-12 08:00 | 2026-06-23 16:00 |  |  | 10 | 10 | 166 | No |  |  | 307000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | ERT-030 | Install Electrical Room Earth Bars | Electrical Systems | Earthing & Bonding | Not Started | 2026-10-05 08:00 | 2026-10-09 16:00 |  |  | 5 | 5 | 78 | No |  |  | 249000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | ERT-040 | Bond Transformers and Switchgear | Electrical Systems | Earthing & Bonding | Not Started | 2026-12-18 08:00 | 2026-12-23 16:00 |  |  | 5 | 5 | 24 | No |  |  | 156000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | ERT-050 | Bond UPS and Generator Equipment | Electrical Systems | Earthing & Bonding | Not Started | 2026-12-21 08:00 | 2026-12-25 16:00 |  |  | 5 | 5 | 22 | No |  |  | 156000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | ERT-060 | Bond Mechanical and Data Hall Equipment | Electrical Systems | Earthing & Bonding | Not Started | 2026-10-22 08:00 | 2026-11-02 16:00 |  |  | 10 | 10 | 68 | No |  |  | 192000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | ERT-070 | Perform Earthing Resistance Tests | Electrical Systems | Earthing & Bonding | Not Started | 2026-12-26 08:00 | 2026-12-29 16:00 |  |  | 3 | 3 | 22 | No |  |  | 160000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | ERT-080 | Earthing and Bonding System Complete | Electrical Systems | Earthing & Bonding | Not Started | 2026-12-29 16:00 | 2026-12-29 16:00 |  |  | 0 | 0 | 22 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | ERA-010 | Install Electrical Room Cable Trays and Containment | Electrical Systems | Electrical Rooms & Ancillary Systems | Not Started | 2026-10-05 08:00 | 2026-10-15 16:00 |  |  | 10 | 10 | 86 | No |  |  | 307000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | ERA-020 | Install Electrical Room Lighting | Electrical Systems | Electrical Rooms & Ancillary Systems | Not Started | 2026-10-08 08:00 | 2026-10-15 16:00 |  |  | 7 | 7 | 86 | No |  |  | 276000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | ERA-030 | Install Electrical Room Small Power | Electrical Systems | Electrical Rooms & Ancillary Systems | Not Started | 2026-10-08 08:00 | 2026-10-15 16:00 |  |  | 7 | 7 | 86 | No |  |  | 276000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | ERA-040 | Install Emergency Lighting | Electrical Systems | Electrical Rooms & Ancillary Systems | Not Started | 2026-10-10 08:00 | 2026-10-15 16:00 |  |  | 5 | 5 | 86 | No |  |  | 249000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | ERA-050 | Install Electrical Room Identification and Labels | Electrical Systems | Electrical Rooms & Ancillary Systems | Not Started | 2027-01-01 08:00 | 2027-01-04 16:00 |  |  | 3 | 3 | 17 | No |  |  | 214000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | ERA-060 | Complete Electrical Room Fire-Stopping | Electrical Systems | Electrical Rooms & Ancillary Systems | Not Started | 2026-12-30 08:00 | 2027-01-04 16:00 |  |  | 5 | 5 | 17 | No |  |  | 156000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | ERA-070 | Complete Electrical Room Installation Inspection | Electrical Systems | Electrical Rooms & Ancillary Systems | Not Started | 2027-01-05 08:00 | 2027-01-06 16:00 |  |  | 2 | 2 | 17 | No |  |  | 189000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | ERA-080 | Electrical Rooms Ready for Commissioning | Electrical Systems | Electrical Rooms & Ancillary Systems | Not Started | 2027-01-06 16:00 | 2027-01-06 16:00 |  |  | 0 | 0 | 17 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CLG-010 | Prepare Cooling Plant Area for Installation | Mechanical & Cooling Systems | Cooling Plant | Not Started | 2026-08-25 08:00 | 2026-08-27 16:00 |  |  | 3 | 3 | 108 | No |  |  | 158000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CLG-020 | Install Cooling Plant Equipment Supports | Mechanical & Cooling Systems | Cooling Plant | Not Started | 2026-08-28 08:00 | 2026-09-02 16:00 |  |  | 5 | 5 | 108 | No |  |  | 185000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CLG-030 | Install Cooling Plant Main Headers | Mechanical & Cooling Systems | Cooling Plant | Not Started | 2026-09-03 08:00 | 2026-09-14 16:00 |  |  | 10 | 10 | 108 | No |  |  | 227000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CLG-040 | Install Cooling Plant Valves and Accessories | Mechanical & Cooling Systems | Cooling Plant | Not Started | 2026-09-15 08:00 | 2026-09-19 16:00 |  |  | 5 | 5 | 108 | No |  |  | 185000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CLG-050 | Install Cooling Plant Electrical Interfaces | Mechanical & Cooling Systems | Cooling Plant | Not Started | 2026-09-09 08:00 | 2026-09-14 16:00 |  |  | 5 | 5 | 113 | No |  |  | 185000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CLG-060 | Install Cooling Plant Controls Interfaces | Mechanical & Cooling Systems | Cooling Plant | Not Started | 2026-09-09 08:00 | 2026-09-14 16:00 |  |  | 5 | 5 | 113 | No |  |  | 185000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CLG-070 | Inspect Cooling Plant Installation | Mechanical & Cooling Systems | Cooling Plant | Not Started | 2026-09-21 08:00 | 2026-09-22 16:00 |  |  | 2 | 2 | 108 | No |  |  | 140000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CLG-080 | Cooling Plant Ready for Pre-Commissioning | Mechanical & Cooling Systems | Cooling Plant | Not Started | 2026-09-22 16:00 | 2026-09-22 16:00 |  |  | 0 | 0 | 108 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CHR-010 | Prepare Chiller and Heat Rejection Equipment Areas | Mechanical & Cooling Systems | Chillers / Heat Rejection Equipment | Not Started | 2026-08-28 08:00 | 2026-08-31 16:00 |  |  | 3 | 3 | 47 | No |  |  | 99000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CHR-020 | Receive and Inspect Chillers and Heat Rejection Equipment | Mechanical & Cooling Systems | Chillers / Heat Rejection Equipment | Not Started | 2026-09-01 08:00 | 2026-09-02 16:00 |  |  | 2 | 2 | 47 | No |  |  | 105000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CHR-030 | Position Chillers on Equipment Bases | Mechanical & Cooling Systems | Chillers / Heat Rejection Equipment | Not Started | 2026-09-03 08:00 | 2026-09-08 16:00 |  |  | 5 | 5 | 47 | No |  |  | 115000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CHR-040 | Position Heat Rejection Equipment | Mechanical & Cooling Systems | Chillers / Heat Rejection Equipment | Not Started | 2026-09-03 08:00 | 2026-09-08 16:00 |  |  | 5 | 5 | 99 | No |  |  | 115000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CHR-050 | Install Chiller Mechanical Connections | Mechanical & Cooling Systems | Chillers / Heat Rejection Equipment | Not Started | 2026-09-09 08:00 | 2026-09-19 16:00 |  |  | 10 | 10 | 47 | No |  |  | 227000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CHR-060 | Install Heat Rejection Equipment Connections | Mechanical & Cooling Systems | Chillers / Heat Rejection Equipment | Not Started | 2026-09-09 08:00 | 2026-09-16 16:00 |  |  | 7 | 7 | 99 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CHR-070 | Install Electrical and Controls Connections | Mechanical & Cooling Systems | Chillers / Heat Rejection Equipment | Not Started | 2026-09-05 08:00 | 2026-09-12 16:00 |  |  | 7 | 7 | 102 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CHR-080 | Complete Chiller Installation Inspection | Mechanical & Cooling Systems | Chillers / Heat Rejection Equipment | Not Started | 2026-09-21 08:00 | 2026-09-22 16:00 |  |  | 2 | 2 | 96 | No |  |  | 140000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CHR-090 | Chillers and Heat Rejection Equipment Ready for Pre-Commissioning | Mechanical & Cooling Systems | Chillers / Heat Rejection Equipment | Not Started | 2026-09-22 16:00 | 2026-09-22 16:00 |  |  | 0 | 0 | 96 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | PMP-010 | Prepare Pump Bases for Installation | Mechanical & Cooling Systems | Pumps & Pumping Systems | Not Started | 2026-08-25 08:00 | 2026-08-27 16:00 |  |  | 3 | 3 | 53 | No |  |  | 158000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | PMP-020 | Receive and Inspect Pumps | Mechanical & Cooling Systems | Pumps & Pumping Systems | Not Started | 2026-08-28 08:00 | 2026-08-29 16:00 |  |  | 2 | 2 | 53 | No |  |  | 105000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | PMP-030 | Install Primary Cooling Pumps | Mechanical & Cooling Systems | Pumps & Pumping Systems | Not Started | 2026-08-31 08:00 | 2026-09-04 16:00 |  |  | 5 | 5 | 53 | No |  |  | 185000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | PMP-040 | Install Secondary Cooling Pumps | Mechanical & Cooling Systems | Pumps & Pumping Systems | Not Started | 2026-08-31 08:00 | 2026-09-04 16:00 |  |  | 5 | 5 | 53 | No |  |  | 185000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | PMP-050 | Install Pump Suction and Discharge Connections | Mechanical & Cooling Systems | Pumps & Pumping Systems | Not Started | 2026-09-05 08:00 | 2026-09-12 16:00 |  |  | 7 | 7 | 53 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | PMP-060 | Install Pump Electrical Connections | Mechanical & Cooling Systems | Pumps & Pumping Systems | Not Started | 2026-09-02 08:00 | 2026-09-07 16:00 |  |  | 5 | 5 | 107 | No |  |  | 185000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | PMP-070 | Install Pump Controls and Instrumentation | Mechanical & Cooling Systems | Pumps & Pumping Systems | Not Started | 2026-09-02 08:00 | 2026-09-07 16:00 |  |  | 5 | 5 | 107 | No |  |  | 185000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | PMP-080 | Inspect Pumping System Installation | Mechanical & Cooling Systems | Pumps & Pumping Systems | Not Started | 2026-09-14 08:00 | 2026-09-15 16:00 |  |  | 2 | 2 | 102 | No |  |  | 140000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | PMP-090 | Pumping Systems Ready for Pre-Commissioning | Mechanical & Cooling Systems | Pumps & Pumping Systems | Not Started | 2026-09-15 16:00 | 2026-09-15 16:00 |  |  | 0 | 0 | 102 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CHW-010 | Set Out Chilled Water Pipework Routes | Mechanical & Cooling Systems | Chilled Water Distribution | Not Started | 2026-08-25 08:00 | 2026-08-27 16:00 |  |  | 3 | 3 | 44 | No |  |  | 158000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CHW-020 | Install Chilled Water Pipe Supports | Mechanical & Cooling Systems | Chilled Water Distribution | Not Started | 2026-08-28 08:00 | 2026-09-08 16:00 |  |  | 10 | 10 | 44 | No |  |  | 227000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CHW-030 | Install Main Chilled Water Pipework | Mechanical & Cooling Systems | Chilled Water Distribution | Not Started | 2026-09-01 08:00 | 2026-09-17 16:00 |  |  | 15 | 15 | 44 | No |  |  | 262000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CHW-040 | Install Chilled Water Branch Pipework | Mechanical & Cooling Systems | Chilled Water Distribution | Not Started | 2026-09-07 08:00 | 2026-09-23 16:00 |  |  | 15 | 15 | 44 | No |  |  | 257000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CHW-050 | Install Chilled Water Valves and Accessories | Mechanical & Cooling Systems | Chilled Water Distribution | Not Started | 2026-09-16 08:00 | 2026-09-23 16:00 |  |  | 7 | 7 | 44 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CHW-060 | Pressure Test Chilled Water Pipework | Mechanical & Cooling Systems | Chilled Water Distribution | Not Started | 2026-09-24 08:00 | 2026-10-01 16:00 |  |  | 7 | 7 | 44 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CHW-070 | Flush and Clean Chilled Water System | Mechanical & Cooling Systems | Chilled Water Distribution | Not Started | 2026-10-02 08:00 | 2026-10-07 16:00 |  |  | 5 | 5 | 44 | No |  |  | 115000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CHW-080 | Install Chilled Water Pipe Insulation | Mechanical & Cooling Systems | Chilled Water Distribution | Not Started | 2026-09-26 08:00 | 2026-10-07 16:00 |  |  | 10 | 10 | 95 | No |  |  | 227000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CHW-090 | Chilled Water Distribution Ready for Pre-Commissioning | Mechanical & Cooling Systems | Chilled Water Distribution | Not Started | 2026-10-07 16:00 | 2026-10-07 16:00 |  |  | 0 | 0 | 95 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CRAC-010 | Prepare CRAH/CRAC Installation Areas | Mechanical & Cooling Systems | CRAH / CRAC Systems | Not Started | 2026-09-03 08:00 | 2026-09-05 16:00 |  |  | 3 | 3 | 59 | No |  |  | 158000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CRAC-020 | Receive and Inspect CRAH/CRAC Units | Mechanical & Cooling Systems | CRAH / CRAC Systems | Not Started | 2026-09-07 08:00 | 2026-09-08 16:00 |  |  | 2 | 2 | 59 | No |  |  | 105000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CRAC-030 | Position and Install CRAH/CRAC Units | Mechanical & Cooling Systems | CRAH / CRAC Systems | Not Started | 2026-10-10 08:00 | 2026-10-21 16:00 |  |  | 10 | 10 | 32 | No |  |  | 227000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CRAC-040 | Install CRAH/CRAC Chilled Water Connections | Mechanical & Cooling Systems | CRAH / CRAC Systems | Not Started | 2026-10-22 08:00 | 2026-11-02 16:00 |  |  | 10 | 10 | 32 | No |  |  | 227000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CRAC-050 | Install CRAH/CRAC Condensate Connections | Mechanical & Cooling Systems | CRAH / CRAC Systems | Not Started | 2026-10-22 08:00 | 2026-10-29 16:00 |  |  | 7 | 7 | 62 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CRAC-060 | Install CRAH/CRAC Electrical Connections | Mechanical & Cooling Systems | CRAH / CRAC Systems | Not Started | 2026-10-22 08:00 | 2026-10-29 16:00 |  |  | 7 | 7 | 62 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CRAC-070 | Install CRAH/CRAC Controls Connections | Mechanical & Cooling Systems | CRAH / CRAC Systems | Not Started | 2026-10-22 08:00 | 2026-10-29 16:00 |  |  | 7 | 7 | 62 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CRAC-080 | Complete CRAH/CRAC Installation Inspection | Mechanical & Cooling Systems | CRAH / CRAC Systems | Not Started | 2026-11-03 08:00 | 2026-11-04 16:00 |  |  | 2 | 2 | 59 | No |  |  | 140000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CRAC-090 | CRAH/CRAC Systems Ready for Pre-Commissioning | Mechanical & Cooling Systems | CRAH / CRAC Systems | Not Started | 2026-11-04 16:00 | 2026-11-04 16:00 |  |  | 0 | 0 | 59 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | DHC-010 | Set Out Data Hall Cooling Distribution | Mechanical & Cooling Systems | Data Hall Cooling Distribution | Not Started | 2026-09-03 08:00 | 2026-09-05 16:00 |  |  | 3 | 3 | 70 | No |  |  | 99000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | DHC-020 | Install Data Hall Cooling Pipe Supports | Mechanical & Cooling Systems | Data Hall Cooling Distribution | Not Started | 2026-09-07 08:00 | 2026-09-14 16:00 |  |  | 7 | 7 | 70 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | DHC-030 | Install Data Hall Cooling Distribution Pipework | Mechanical & Cooling Systems | Data Hall Cooling Distribution | Not Started | 2026-09-10 08:00 | 2026-09-26 16:00 |  |  | 15 | 15 | 70 | No |  |  | 257000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | DHC-040 | Install Data Hall Cooling Valves and Accessories | Mechanical & Cooling Systems | Data Hall Cooling Distribution | Not Started | 2026-09-19 08:00 | 2026-09-26 16:00 |  |  | 7 | 7 | 70 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | DHC-050 | Connect Cooling Distribution to CRAH/CRAC Systems | Mechanical & Cooling Systems | Data Hall Cooling Distribution | Not Started | 2026-10-22 08:00 | 2026-11-02 16:00 |  |  | 10 | 10 | 49 | No |  |  | 142000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | DHC-060 | Pressure Test Data Hall Cooling Distribution | Mechanical & Cooling Systems | Data Hall Cooling Distribution | Not Started | 2026-11-03 08:00 | 2026-11-07 16:00 |  |  | 5 | 5 | 49 | No |  |  | 138000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | DHC-070 | Flush Data Hall Cooling Distribution | Mechanical & Cooling Systems | Data Hall Cooling Distribution | Not Started | 2026-11-09 08:00 | 2026-11-13 16:00 |  |  | 5 | 5 | 51 | No |  |  | 115000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | DHC-080 | Insulate Data Hall Cooling Pipework | Mechanical & Cooling Systems | Data Hall Cooling Distribution | Not Started | 2026-11-05 08:00 | 2026-11-16 16:00 |  |  | 10 | 10 | 49 | No |  |  | 227000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | DHC-090 | Data Hall Cooling Distribution Ready for Pre-Commissioning | Mechanical & Cooling Systems | Data Hall Cooling Distribution | Not Started | 2026-11-16 16:00 | 2026-11-16 16:00 |  |  | 0 | 0 | 49 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | VEN-010 | Install Ventilation Ductwork Supports | Mechanical & Cooling Systems | Ventilation & Exhaust Systems | Not Started | 2026-10-05 08:00 | 2026-10-12 16:00 |  |  | 7 | 7 | 77 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | VEN-020 | Install Ventilation and Exhaust Ductwork | Mechanical & Cooling Systems | Ventilation & Exhaust Systems | Not Started | 2026-10-07 08:00 | 2026-10-23 16:00 |  |  | 15 | 15 | 77 | No |  |  | 257000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | VEN-030 | Install Ventilation Fans | Mechanical & Cooling Systems | Ventilation & Exhaust Systems | Not Started | 2026-10-07 08:00 | 2026-10-14 16:00 |  |  | 7 | 7 | 80 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | VEN-040 | Install Dampers and Air Control Devices | Mechanical & Cooling Systems | Ventilation & Exhaust Systems | Not Started | 2026-10-10 08:00 | 2026-10-17 16:00 |  |  | 7 | 7 | 77 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | VEN-050 | Install Louvers Grilles and Terminals | Mechanical & Cooling Systems | Ventilation & Exhaust Systems | Not Started | 2026-10-10 08:00 | 2026-10-17 16:00 |  |  | 7 | 7 | 77 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | VEN-060 | Install Ventilation Controls Connections | Mechanical & Cooling Systems | Ventilation & Exhaust Systems | Not Started | 2026-10-19 08:00 | 2026-10-26 16:00 |  |  | 7 | 7 | 77 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | VEN-070 | Inspect Ventilation and Exhaust Installation | Mechanical & Cooling Systems | Ventilation & Exhaust Systems | Not Started | 2026-10-27 08:00 | 2026-10-28 16:00 |  |  | 2 | 2 | 77 | No |  |  | 140000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | VEN-080 | Ventilation and Exhaust Systems Ready for Pre-Commissioning | Mechanical & Cooling Systems | Ventilation & Exhaust Systems | Not Started | 2026-10-28 16:00 | 2026-10-28 16:00 |  |  | 0 | 0 | 77 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | MCI-010 | Install Mechanical Control Panels | Mechanical & Cooling Systems | Mechanical Controls & Instrumentation | Not Started | 2026-10-22 08:00 | 2026-10-27 16:00 |  |  | 5 | 5 | 40 | No |  |  | 185000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | MCI-020 | Install Temperature Sensors | Mechanical & Cooling Systems | Mechanical Controls & Instrumentation | Not Started | 2026-10-24 08:00 | 2026-10-31 16:00 |  |  | 7 | 7 | 43 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | MCI-030 | Install Pressure Sensors | Mechanical & Cooling Systems | Mechanical Controls & Instrumentation | Not Started | 2026-10-24 08:00 | 2026-10-31 16:00 |  |  | 7 | 7 | 43 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | MCI-040 | Install Flow Measurement Devices | Mechanical & Cooling Systems | Mechanical Controls & Instrumentation | Not Started | 2026-10-24 08:00 | 2026-10-31 16:00 |  |  | 7 | 7 | 43 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | MCI-050 | Install Control Valves and Actuators | Mechanical & Cooling Systems | Mechanical Controls & Instrumentation | Not Started | 2026-11-03 08:00 | 2026-11-13 16:00 |  |  | 10 | 10 | 32 | No |  |  | 227000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | MCI-060 | Complete Mechanical Controls Field Wiring | Mechanical & Cooling Systems | Mechanical Controls & Instrumentation | Not Started | 2026-11-14 08:00 | 2026-11-25 16:00 |  |  | 10 | 10 | 32 | No |  |  | 142000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | MCI-070 | Complete BMS Interface Connections | Mechanical & Cooling Systems | Mechanical Controls & Instrumentation | Not Started | 2026-11-26 08:00 | 2026-12-03 16:00 |  |  | 7 | 7 | 32 | No |  |  | 128000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | MCI-080 | Inspect Mechanical Controls and Instrumentation | Mechanical & Cooling Systems | Mechanical Controls & Instrumentation | Not Started | 2026-12-04 08:00 | 2026-12-07 16:00 |  |  | 3 | 3 | 32 | No |  |  | 119000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | MCI-090 | Mechanical Controls Ready for Pre-Commissioning | Mechanical & Cooling Systems | Mechanical Controls & Instrumentation | Not Started | 2026-12-07 16:00 | 2026-12-07 16:00 |  |  | 0 | 0 | 32 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | WTM-010 | Prepare Water Treatment Equipment Area | Mechanical & Cooling Systems | Water Treatment & Make-Up Systems | Not Started | 2026-08-25 08:00 | 2026-08-27 16:00 |  |  | 3 | 3 | 113 | No |  |  | 99000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | WTM-020 | Install Water Treatment Equipment | Mechanical & Cooling Systems | Water Treatment & Make-Up Systems | Not Started | 2026-08-28 08:00 | 2026-09-02 16:00 |  |  | 5 | 5 | 113 | No |  |  | 185000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | WTM-030 | Install Chemical Dosing System | Mechanical & Cooling Systems | Water Treatment & Make-Up Systems | Not Started | 2026-09-03 08:00 | 2026-09-08 16:00 |  |  | 5 | 5 | 113 | No |  |  | 185000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | WTM-040 | Install Cooling System Make-Up Water Connections | Mechanical & Cooling Systems | Water Treatment & Make-Up Systems | Not Started | 2026-09-03 08:00 | 2026-09-08 16:00 |  |  | 5 | 5 | 113 | No |  |  | 185000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | WTM-050 | Install Water Treatment Instrumentation | Mechanical & Cooling Systems | Water Treatment & Make-Up Systems | Not Started | 2026-08-31 08:00 | 2026-09-04 16:00 |  |  | 5 | 5 | 116 | No |  |  | 185000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | WTM-060 | Complete Electrical and Controls Connections | Mechanical & Cooling Systems | Water Treatment & Make-Up Systems | Not Started | 2026-09-09 08:00 | 2026-09-14 16:00 |  |  | 5 | 5 | 113 | No |  |  | 115000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | WTM-070 | Inspect Water Treatment and Make-Up Systems | Mechanical & Cooling Systems | Water Treatment & Make-Up Systems | Not Started | 2026-09-15 08:00 | 2026-09-16 16:00 |  |  | 2 | 2 | 113 | No |  |  | 105000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | WTM-080 | Water Treatment and Make-Up Systems Ready for Pre-Commissioning | Mechanical & Cooling Systems | Water Treatment & Make-Up Systems | Not Started | 2026-09-16 16:00 | 2026-09-16 16:00 |  |  | 0 | 0 | 113 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | MCA-010 | Install Mechanical Equipment Drainage Connections | Mechanical & Cooling Systems | Mechanical Ancillary Systems | Not Started | 2026-10-22 08:00 | 2026-10-29 16:00 |  |  | 7 | 7 | 73 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | MCA-020 | Install Condensate Drainage Systems | Mechanical & Cooling Systems | Mechanical Ancillary Systems | Not Started | 2026-10-22 08:00 | 2026-10-29 16:00 |  |  | 7 | 7 | 73 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | MCA-030 | Install Mechanical Equipment Identification and Labels | Mechanical & Cooling Systems | Mechanical Ancillary Systems | Not Started | 2026-09-07 08:00 | 2026-09-11 16:00 |  |  | 5 | 5 | 114 | No |  |  | 185000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | MCA-040 | Complete Mechanical Equipment Fire-Stopping | Mechanical & Cooling Systems | Mechanical Ancillary Systems | Not Started | 2026-10-14 08:00 | 2026-10-19 16:00 |  |  | 5 | 5 | 82 | No |  |  | 115000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | MCA-050 | Complete Mechanical Plant Access and Maintenance Provisions | Mechanical & Cooling Systems | Mechanical Ancillary Systems | Not Started | 2026-09-07 08:00 | 2026-09-11 16:00 |  |  | 5 | 5 | 114 | No |  |  | 115000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | MCA-060 | Complete Mechanical Installation Inspection | Mechanical & Cooling Systems | Mechanical Ancillary Systems | Not Started | 2026-10-30 08:00 | 2026-11-02 16:00 |  |  | 3 | 3 | 73 | No |  |  | 158000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | MCA-070 | Mechanical Systems Installation Complete | Mechanical & Cooling Systems | Mechanical Ancillary Systems | Not Started | 2026-11-02 16:00 | 2026-11-02 16:00 |  |  | 0 | 0 | 73 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | FAD-010 | Install Fire Alarm Control Panels | Fire & Life Safety | Fire Detection & Alarm | Not Started | 2026-06-10 08:00 | 2026-06-15 16:00 |  |  | 5 | 5 | 175 | No |  |  | 82000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | FAD-020 | Install Fire Alarm Cabling | Fire & Life Safety | Fire Detection & Alarm | Not Started | 2026-10-08 08:00 | 2026-10-19 16:00 |  |  | 10 | 10 | 67 | No |  |  | 106000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | FAD-030 | Install Smoke and Heat Detectors | Fire & Life Safety | Fire Detection & Alarm | Not Started | 2026-10-10 08:00 | 2026-10-19 16:00 |  |  | 8 | 8 | 67 | No |  |  | 95000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | FAD-040 | Install Manual Call Points | Fire & Life Safety | Fire Detection & Alarm | Not Started | 2026-10-10 08:00 | 2026-10-14 16:00 |  |  | 4 | 4 | 71 | No |  |  | 77000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | FAD-050 | Install Notification Devices | Fire & Life Safety | Fire Detection & Alarm | Not Started | 2026-10-10 08:00 | 2026-10-16 16:00 |  |  | 6 | 6 | 69 | No |  |  | 87000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | FAD-060 | Complete Fire Alarm Device Addressing | Fire & Life Safety | Fire Detection & Alarm | Not Started | 2026-10-20 08:00 | 2026-10-21 16:00 |  |  | 2 | 2 | 67 | No |  |  | 39000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | FAD-070 | Inspect Fire Detection and Alarm Installation | Fire & Life Safety | Fire Detection & Alarm | Not Started | 2026-10-22 08:00 | 2026-10-23 16:00 |  |  | 2 | 2 | 67 | No |  |  | 63000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | FAD-080 | Fire Detection and Alarm Ready for Pre-Commissioning | Fire & Life Safety | Fire Detection & Alarm | Not Started | 2026-10-23 16:00 | 2026-10-23 16:00 |  |  | 0 | 0 | 67 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | SPR-010 | Install Sprinkler Main Pipework | Fire & Life Safety | Sprinkler System | Not Started | 2026-10-08 08:00 | 2026-10-19 16:00 |  |  | 10 | 10 | 71 | No |  |  | 101000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | SPR-020 | Install Sprinkler Branch Pipework | Fire & Life Safety | Sprinkler System | Not Started | 2026-10-12 08:00 | 2026-10-22 16:00 |  |  | 10 | 10 | 71 | No |  |  | 101000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | SPR-030 | Install Sprinkler Heads | Fire & Life Safety | Sprinkler System | Not Started | 2026-10-15 08:00 | 2026-10-23 16:00 |  |  | 8 | 8 | 71 | No |  |  | 95000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | SPR-040 | Install Zone Control Assemblies | Fire & Life Safety | Sprinkler System | Not Started | 2026-10-10 08:00 | 2026-10-15 16:00 |  |  | 5 | 5 | 78 | No |  |  | 82000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | SPR-050 | Pressure Test Sprinkler System | Fire & Life Safety | Sprinkler System | Not Started | 2026-10-24 08:00 | 2026-10-27 16:00 |  |  | 3 | 3 | 71 | No |  |  | 53000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | SPR-060 | Flush Sprinkler System | Fire & Life Safety | Sprinkler System | Not Started | 2026-10-28 08:00 | 2026-11-02 16:00 |  |  | 5 | 5 | 71 | No |  |  | 51000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | SPR-070 | Inspect Sprinkler Installation | Fire & Life Safety | Sprinkler System | Not Started | 2026-11-03 08:00 | 2026-11-04 16:00 |  |  | 2 | 2 | 71 | No |  |  | 63000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | SPR-080 | Sprinkler System Ready for Pre-Commissioning | Fire & Life Safety | Sprinkler System | Not Started | 2026-11-04 16:00 | 2026-11-04 16:00 |  |  | 0 | 0 | 71 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CAF-010 | Prepare Clean Agent Protected Areas | Fire & Life Safety | Clean Agent Fire Suppression | Not Started | 2026-10-08 08:00 | 2026-10-13 16:00 |  |  | 5 | 5 | 73 | No |  |  | 51000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CAF-020 | Install Clean Agent Cylinders | Fire & Life Safety | Clean Agent Fire Suppression | Not Started | 2026-10-14 08:00 | 2026-10-19 16:00 |  |  | 5 | 5 | 76 | No |  |  | 82000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CAF-030 | Install Clean Agent Distribution Pipework | Fire & Life Safety | Clean Agent Fire Suppression | Not Started | 2026-10-14 08:00 | 2026-10-22 16:00 |  |  | 8 | 8 | 73 | No |  |  | 95000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CAF-040 | Install Clean Agent Discharge Nozzles | Fire & Life Safety | Clean Agent Fire Suppression | Not Started | 2026-10-23 08:00 | 2026-10-28 16:00 |  |  | 5 | 5 | 73 | No |  |  | 82000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CAF-050 | Install Release and Control Interfaces | Fire & Life Safety | Clean Agent Fire Suppression | Not Started | 2026-10-22 08:00 | 2026-10-27 16:00 |  |  | 5 | 5 | 74 | No |  |  | 82000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CAF-060 | Complete Room Integrity Preparations | Fire & Life Safety | Clean Agent Fire Suppression | Not Started | 2026-10-29 08:00 | 2026-10-30 16:00 |  |  | 2 | 2 | 73 | No |  |  | 39000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CAF-070 | Inspect Clean Agent Suppression Installation | Fire & Life Safety | Clean Agent Fire Suppression | Not Started | 2026-10-31 08:00 | 2026-11-02 16:00 |  |  | 2 | 2 | 73 | No |  |  | 63000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CAF-080 | Clean Agent Suppression Ready for Pre-Commissioning | Fire & Life Safety | Clean Agent Fire Suppression | Not Started | 2026-11-02 16:00 | 2026-11-02 16:00 |  |  | 0 | 0 | 73 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | FPW-010 | Prepare Fire Pump Room | Fire & Life Safety | Fire Pump & Water Supply | Not Started | 2026-06-10 08:00 | 2026-06-15 16:00 |  |  | 5 | 5 | 178 | No |  |  | 51000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | FPW-020 | Install Fire Water Tank Connections | Fire & Life Safety | Fire Pump & Water Supply | Not Started | 2026-06-16 08:00 | 2026-06-20 16:00 |  |  | 5 | 5 | 178 | No |  |  | 82000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | FPW-030 | Install Main Fire Pumps | Fire & Life Safety | Fire Pump & Water Supply | Not Started | 2026-06-16 08:00 | 2026-06-20 16:00 |  |  | 5 | 5 | 178 | No |  |  | 82000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | FPW-040 | Install Jockey Pump | Fire & Life Safety | Fire Pump & Water Supply | Not Started | 2026-06-16 08:00 | 2026-06-20 16:00 |  |  | 5 | 5 | 178 | No |  |  | 82000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | FPW-050 | Install Fire Pump Pipework and Valves | Fire & Life Safety | Fire Pump & Water Supply | Not Started | 2026-06-22 08:00 | 2026-06-30 16:00 |  |  | 8 | 8 | 178 | No |  |  | 95000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | FPW-060 | Install Fire Pump Electrical Connections | Fire & Life Safety | Fire Pump & Water Supply | Not Started | 2026-06-22 08:00 | 2026-06-26 16:00 |  |  | 5 | 5 | 181 | No |  |  | 82000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | FPW-070 | Install Fire Pump Controls | Fire & Life Safety | Fire Pump & Water Supply | Not Started | 2026-10-22 08:00 | 2026-10-27 16:00 |  |  | 5 | 5 | 76 | No |  |  | 82000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | FPW-080 | Inspect Fire Pump and Water Supply Installation | Fire & Life Safety | Fire Pump & Water Supply | Not Started | 2026-10-28 08:00 | 2026-10-29 16:00 |  |  | 2 | 2 | 76 | No |  |  | 63000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | FPW-090 | Fire Pump and Water Supply Ready for Pre-Commissioning | Fire & Life Safety | Fire Pump & Water Supply | Not Started | 2026-10-29 16:00 | 2026-10-29 16:00 |  |  | 0 | 0 | 76 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | VES-010 | Install VESDA Control Units | Fire & Life Safety | Smoke Detection / VESDA | Not Started | 2026-06-10 08:00 | 2026-06-15 16:00 |  |  | 5 | 5 | 187 | No |  |  | 82000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | VES-020 | Install VESDA Sampling Pipe Network | Fire & Life Safety | Smoke Detection / VESDA | Not Started | 2026-10-08 08:00 | 2026-10-16 16:00 |  |  | 8 | 8 | 81 | No |  |  | 95000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | VES-030 | Install VESDA Sampling Points | Fire & Life Safety | Smoke Detection / VESDA | Not Started | 2026-10-12 08:00 | 2026-10-16 16:00 |  |  | 5 | 5 | 81 | No |  |  | 82000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | VES-040 | Complete VESDA Electrical Connections | Fire & Life Safety | Smoke Detection / VESDA | Not Started | 2026-10-17 08:00 | 2026-10-19 16:00 |  |  | 2 | 2 | 81 | No |  |  | 39000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | VES-050 | Complete VESDA Fire Alarm Interfaces | Fire & Life Safety | Smoke Detection / VESDA | Not Started | 2026-10-22 08:00 | 2026-10-23 16:00 |  |  | 2 | 2 | 79 | No |  |  | 39000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | VES-060 | Inspect VESDA Installation | Fire & Life Safety | Smoke Detection / VESDA | Not Started | 2026-10-24 08:00 | 2026-10-26 16:00 |  |  | 2 | 2 | 79 | No |  |  | 63000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | VES-070 | VESDA System Ready for Pre-Commissioning | Fire & Life Safety | Smoke Detection / VESDA | Not Started | 2026-10-26 16:00 | 2026-10-26 16:00 |  |  | 0 | 0 | 79 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | EML-010 | Install Emergency Lighting Fixtures | Fire & Life Safety | Emergency Lighting & Exit Systems | Not Started | 2026-12-25 08:00 | 2026-12-30 16:00 |  |  | 5 | 5 | 21 | No |  |  | 82000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | EML-020 | Install Exit Signage | Fire & Life Safety | Emergency Lighting & Exit Systems | Not Started | 2026-12-25 08:00 | 2026-12-30 16:00 |  |  | 5 | 5 | 21 | No |  |  | 82000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | EML-030 | Install Emergency Lighting Circuits | Fire & Life Safety | Emergency Lighting & Exit Systems | Not Started | 2026-12-24 08:00 | 2026-12-29 16:00 |  |  | 5 | 5 | 17 | No |  |  | 82000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | EML-040 | Install Emergency Lighting Controls | Fire & Life Safety | Emergency Lighting & Exit Systems | Not Started | 2026-12-30 08:00 | 2027-01-04 16:00 |  |  | 5 | 5 | 17 | No |  |  | 82000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | EML-050 | Inspect Emergency Lighting and Exit Systems | Fire & Life Safety | Emergency Lighting & Exit Systems | Not Started | 2027-01-05 08:00 | 2027-01-06 16:00 |  |  | 2 | 2 | 17 | No |  |  | 47000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | EML-060 | Emergency Lighting and Exit Systems Ready for Testing | Fire & Life Safety | Emergency Lighting & Exit Systems | Not Started | 2027-01-06 16:00 | 2027-01-06 16:00 |  |  | 0 | 0 | 17 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | FSI-010 | Install Fire Alarm Interface Modules | Fire & Life Safety | Fire System Interfaces | Not Started | 2026-10-24 08:00 | 2026-10-29 16:00 |  |  | 5 | 5 | 67 | No |  |  | 82000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | FSI-020 | Connect Fire Alarm to Mechanical Systems | Fire & Life Safety | Fire System Interfaces | Not Started | 2026-12-08 08:00 | 2026-12-12 16:00 |  |  | 5 | 5 | 34 | No |  |  | 51000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | FSI-030 | Connect Fire Alarm to Electrical Systems | Fire & Life Safety | Fire System Interfaces | Not Started | 2026-12-24 08:00 | 2026-12-29 16:00 |  |  | 5 | 5 | 20 | No |  |  | 51000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | FSI-040 | Connect Fire Alarm to Access Control System | Fire & Life Safety | Fire System Interfaces | Not Started | 2026-10-30 08:00 | 2026-11-04 16:00 |  |  | 5 | 5 | 67 | No |  |  | 51000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | FSI-050 | Connect Fire Alarm to BMS | Fire & Life Safety | Fire System Interfaces | Not Started | 2026-12-29 08:00 | 2027-01-02 16:00 |  |  | 5 | 5 | 16 | No |  |  | 51000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | FSI-060 | Complete Fire Cause and Effect Configuration | Fire & Life Safety | Fire System Interfaces | Not Started | 2027-01-04 08:00 | 2027-01-05 16:00 |  |  | 2 | 2 | 16 | No |  |  | 39000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | FSI-070 | Inspect Fire System Interfaces | Fire & Life Safety | Fire System Interfaces | Not Started | 2027-01-06 08:00 | 2027-01-07 16:00 |  |  | 2 | 2 | 16 | No |  |  | 47000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | FSI-080 | Fire System Interfaces Ready for Integrated Testing | Fire & Life Safety | Fire System Interfaces | Not Started | 2027-01-07 16:00 | 2027-01-07 16:00 |  |  | 0 | 0 | 16 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | LSC-010 | Conduct Internal Fire and Life Safety Inspection | Fire & Life Safety | Life Safety Compliance & Inspections | Not Started | 2027-02-08 08:00 | 2027-02-09 16:00 |  |  | 2 | 2 | 63 | No |  |  | 47000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | LSC-020 | Conduct Fire-Stopping Inspection | Fire & Life Safety | Life Safety Compliance & Inspections | Not Started | 2026-10-08 08:00 | 2026-10-09 16:00 |  |  | 2 | 2 | 168 | No |  |  | 47000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | LSC-030 | Conduct Emergency Egress Inspection | Fire & Life Safety | Life Safety Compliance & Inspections | Not Started | 2026-10-08 08:00 | 2026-10-09 16:00 |  |  | 2 | 2 | 168 | No |  |  | 47000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | LSC-040 | Conduct Fire System Compliance Review | Fire & Life Safety | Life Safety Compliance & Inspections | Not Started | 2027-02-10 08:00 | 2027-02-15 16:00 |  |  | 5 | 5 | 63 | No |  |  | 10000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | LSC-050 | Rectify Fire and Life Safety Inspection Comments | Fire & Life Safety | Life Safety Compliance & Inspections | Not Started | 2027-02-16 08:00 | 2027-02-17 16:00 |  |  | 2 | 2 | 63 | No |  |  | 47000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | LSC-060 | Prepare Authority Inspection Documentation | Fire & Life Safety | Life Safety Compliance & Inspections | Not Started | 2027-02-18 08:00 | 2027-02-19 16:00 |  |  | 2 | 2 | 63 | No |  |  | 47000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | LSC-070 | Fire and Life Safety Systems Ready for Authority Inspection | Fire & Life Safety | Life Safety Compliance & Inspections | Not Started | 2027-02-19 16:00 | 2027-02-19 16:00 |  |  | 0 | 0 | 63 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | BMSI-010 | Prepare BMS Installation Areas | Controls, BMS & DCIM | BMS Infrastructure | Not Started | 2026-10-10 08:00 | 2026-10-15 16:00 |  |  | 5 | 5 | 44 | No |  |  | 126000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | BMSI-020 | Install BMS Control Panels | Controls, BMS & DCIM | BMS Infrastructure | Not Started | 2026-10-16 08:00 | 2026-10-21 16:00 |  |  | 5 | 5 | 65 | No |  |  | 126000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | BMSI-030 | Install BMS Network Infrastructure | Controls, BMS & DCIM | BMS Infrastructure | Not Started | 2026-10-16 08:00 | 2026-10-24 16:00 |  |  | 8 | 8 | 44 | No |  |  | 145000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | BMSI-040 | Install BMS Field Cabling | Controls, BMS & DCIM | BMS Infrastructure | Not Started | 2026-10-19 08:00 | 2026-10-29 16:00 |  |  | 10 | 10 | 65 | No |  |  | 150000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | BMSI-050 | Complete BMS Panel Power Connections | Controls, BMS & DCIM | BMS Infrastructure | Not Started | 2026-12-24 08:00 | 2026-12-25 16:00 |  |  | 2 | 2 | 16 | No |  |  | 60000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | BMSI-060 | Inspect BMS Infrastructure Installation | Controls, BMS & DCIM | BMS Infrastructure | Not Started | 2026-12-26 08:00 | 2026-12-28 16:00 |  |  | 2 | 2 | 16 | No |  |  | 96000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | BMSI-070 | BMS Infrastructure Ready for Pre-Commissioning | Controls, BMS & DCIM | BMS Infrastructure | Not Started | 2026-12-28 16:00 | 2026-12-28 16:00 |  |  | 0 | 0 | 16 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | EMC-010 | Install Electrical Monitoring Devices | Controls, BMS & DCIM | Electrical Monitoring & Controls | Not Started | 2026-11-16 08:00 | 2026-11-20 16:00 |  |  | 5 | 5 | 50 | No |  |  | 16000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | EMC-020 | Install Power Metering Devices | Controls, BMS & DCIM | Electrical Monitoring & Controls | Not Started | 2026-12-24 08:00 | 2026-12-29 16:00 |  |  | 5 | 5 | 17 | No |  |  | 126000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | EMC-030 | Install Switchgear Monitoring Interfaces | Controls, BMS & DCIM | Electrical Monitoring & Controls | Not Started | 2026-11-16 08:00 | 2026-11-21 16:00 |  |  | 6 | 6 | 49 | No |  |  | 17000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | EMC-040 | Install UPS Monitoring Interfaces | Controls, BMS & DCIM | Electrical Monitoring & Controls | Not Started | 2027-01-01 08:00 | 2027-01-06 16:00 |  |  | 5 | 5 | 10 | No |  |  | 16000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | EMC-050 | Install Generator Monitoring Interfaces | Controls, BMS & DCIM | Electrical Monitoring & Controls | Not Started | 2026-12-12 08:00 | 2026-12-18 16:00 |  |  | 6 | 6 | 26 | No |  |  | 17000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | EMC-060 | Complete Monitoring Communication Connections | Controls, BMS & DCIM | Electrical Monitoring & Controls | Not Started | 2027-01-07 08:00 | 2027-01-08 16:00 |  |  | 2 | 2 | 10 | No |  |  | 12000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | EMC-070 | Electrical Monitoring Ready for Pre-Commissioning | Controls, BMS & DCIM | Electrical Monitoring & Controls | Not Started | 2027-01-08 16:00 | 2027-01-08 16:00 |  |  | 0 | 0 | 10 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | MMC-010 | Install Mechanical Monitoring Interfaces | Controls, BMS & DCIM | Mechanical Monitoring & Controls | Not Started | 2026-12-08 08:00 | 2026-12-11 16:00 |  |  | 4 | 4 | 32 | No |  |  | 15000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | MMC-020 | Connect Chiller Monitoring Points | Controls, BMS & DCIM | Mechanical Monitoring & Controls | Not Started | 2026-09-23 08:00 | 2026-09-28 16:00 |  |  | 5 | 5 | 96 | No |  |  | 16000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | MMC-030 | Connect Pump Monitoring Points | Controls, BMS & DCIM | Mechanical Monitoring & Controls | Not Started | 2026-09-16 08:00 | 2026-09-21 16:00 |  |  | 5 | 5 | 102 | No |  |  | 16000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | MMC-040 | Connect CRAH CRAC Monitoring Points | Controls, BMS & DCIM | Mechanical Monitoring & Controls | Not Started | 2026-11-05 08:00 | 2026-11-10 16:00 |  |  | 5 | 5 | 59 | No |  |  | 16000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | MMC-050 | Connect Cooling Sensors to BMS | Controls, BMS & DCIM | Mechanical Monitoring & Controls | Not Started | 2026-11-17 08:00 | 2026-11-21 16:00 |  |  | 5 | 5 | 49 | No |  |  | 79000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | MMC-060 | Verify Mechanical Control Wiring | Controls, BMS & DCIM | Mechanical Monitoring & Controls | Not Started | 2026-12-12 08:00 | 2026-12-14 16:00 |  |  | 2 | 2 | 32 | No |  |  | 60000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | MMC-070 | Mechanical Monitoring Ready for Pre-Commissioning | Controls, BMS & DCIM | Mechanical Monitoring & Controls | Not Started | 2026-12-14 16:00 | 2026-12-14 16:00 |  |  | 0 | 0 | 32 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | DCIM-010 | Install DCIM Server Infrastructure | Controls, BMS & DCIM | DCIM Platform | Not Started | 2026-11-12 08:00 | 2026-11-17 16:00 |  |  | 5 | 5 | 44 | No |  |  | 126000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | DCIM-020 | Configure DCIM Platform | Controls, BMS & DCIM | DCIM Platform | Not Started | 2026-11-18 08:00 | 2026-11-26 16:00 |  |  | 8 | 8 | 44 | No |  |  | 91000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | DCIM-030 | Configure Data Hall Asset Database | Controls, BMS & DCIM | DCIM Platform | Not Started | 2026-11-27 08:00 | 2026-12-05 16:00 |  |  | 8 | 8 | 44 | No |  |  | 91000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | DCIM-040 | Configure Power Monitoring Integration | Controls, BMS & DCIM | DCIM Platform | Not Started | 2027-01-09 08:00 | 2027-01-14 16:00 |  |  | 5 | 5 | 10 | No |  |  | 16000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | DCIM-050 | Configure Cooling Monitoring Integration | Controls, BMS & DCIM | DCIM Platform | Not Started | 2026-12-15 08:00 | 2026-12-19 16:00 |  |  | 5 | 5 | 32 | No |  |  | 16000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | DCIM-060 | Configure Alarm and Event Management | Controls, BMS & DCIM | DCIM Platform | Not Started | 2026-11-27 08:00 | 2026-12-02 16:00 |  |  | 5 | 5 | 47 | No |  |  | 79000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | DCIM-070 | DCIM Platform Ready for Functional Testing | Controls, BMS & DCIM | DCIM Platform | Not Started | 2027-01-14 16:00 | 2027-01-14 16:00 |  |  | 0 | 0 | 10 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | SFD-010 | Install Environmental Sensors | Controls, BMS & DCIM | Sensors & Field Devices | Not Started | 2026-10-10 08:00 | 2026-10-15 16:00 |  |  | 5 | 5 | 79 | No |  |  | 126000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | SFD-020 | Install Temperature and Humidity Sensors | Controls, BMS & DCIM | Sensors & Field Devices | Not Started | 2026-10-12 08:00 | 2026-10-16 16:00 |  |  | 5 | 5 | 79 | No |  |  | 126000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | SFD-030 | Install Differential Pressure Sensors | Controls, BMS & DCIM | Sensors & Field Devices | Not Started | 2026-10-12 08:00 | 2026-10-16 16:00 |  |  | 5 | 5 | 79 | No |  |  | 126000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | SFD-040 | Install Leak Detection Sensors | Controls, BMS & DCIM | Sensors & Field Devices | Not Started | 2026-10-12 08:00 | 2026-10-16 16:00 |  |  | 5 | 5 | 79 | No |  |  | 126000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | SFD-050 | Install Energy Metering Devices | Controls, BMS & DCIM | Sensors & Field Devices | Not Started | 2026-10-12 08:00 | 2026-10-16 16:00 |  |  | 5 | 5 | 79 | No |  |  | 126000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | SFD-060 | Terminate Sensor and Field Device Cabling | Controls, BMS & DCIM | Sensors & Field Devices | Not Started | 2026-11-12 08:00 | 2026-11-20 16:00 |  |  | 8 | 8 | 57 | No |  |  | 145000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | SFD-070 | Sensors and Field Devices Ready for Testing | Controls, BMS & DCIM | Sensors & Field Devices | Not Started | 2026-11-20 16:00 | 2026-11-20 16:00 |  |  | 0 | 0 | 57 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CNW-010 | Install Controls Network Switches | Controls, BMS & DCIM | Controls Network | Not Started | 2026-10-26 08:00 | 2026-10-30 16:00 |  |  | 5 | 5 | 44 | No |  |  | 126000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CNW-020 | Install Controls Network Cabling | Controls, BMS & DCIM | Controls Network | Not Started | 2026-10-19 08:00 | 2026-10-27 16:00 |  |  | 8 | 8 | 47 | No |  |  | 145000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CNW-030 | Configure Controls Network | Controls, BMS & DCIM | Controls Network | Not Started | 2026-10-31 08:00 | 2026-11-04 16:00 |  |  | 4 | 4 | 44 | No |  |  | 74000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CNW-040 | Configure Network Segmentation | Controls, BMS & DCIM | Controls Network | Not Started | 2026-11-05 08:00 | 2026-11-07 16:00 |  |  | 3 | 3 | 44 | No |  |  | 68000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CNW-050 | Perform Controls Network Connectivity Testing | Controls, BMS & DCIM | Controls Network | Not Started | 2026-11-09 08:00 | 2026-11-11 16:00 |  |  | 3 | 3 | 44 | No |  |  | 81000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CNW-060 | Controls Network Ready | Controls, BMS & DCIM | Controls Network | Not Started | 2026-11-11 16:00 | 2026-11-11 16:00 |  |  | 0 | 0 | 44 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CSI-010 | Integrate BMS with Electrical Systems | Controls, BMS & DCIM | System Integration | Not Started | 2027-01-09 08:00 | 2027-01-13 16:00 |  |  | 4 | 4 | 33 | No |  |  | 74000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CSI-020 | Integrate BMS with Mechanical Systems | Controls, BMS & DCIM | System Integration | Not Started | 2026-12-29 08:00 | 2027-01-01 16:00 |  |  | 4 | 4 | 43 | No |  |  | 74000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CSI-030 | Integrate BMS with Fire Alarm System | Controls, BMS & DCIM | System Integration | Not Started | 2027-01-08 08:00 | 2027-01-11 16:00 |  |  | 3 | 3 | 35 | No |  |  | 68000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CSI-040 | Integrate BMS with UPS and Generator Systems | Controls, BMS & DCIM | System Integration | Not Started | 2027-01-09 08:00 | 2027-01-13 16:00 |  |  | 4 | 4 | 33 | No |  |  | 74000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CSI-050 | Integrate DCIM with Power Monitoring | Controls, BMS & DCIM | System Integration | Not Started | 2027-01-15 08:00 | 2027-01-19 16:00 |  |  | 4 | 4 | 28 | No |  |  | 15000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CSI-060 | Integrate DCIM with Cooling Monitoring | Controls, BMS & DCIM | System Integration | Not Started | 2027-01-15 08:00 | 2027-01-19 16:00 |  |  | 4 | 4 | 28 | No |  |  | 15000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CSI-070 | Verify System Integration Interfaces | Controls, BMS & DCIM | System Integration | Not Started | 2027-01-20 08:00 | 2027-01-21 16:00 |  |  | 2 | 2 | 28 | No |  |  | 60000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CSI-080 | Controls Integration Ready for IST | Controls, BMS & DCIM | System Integration | Not Started | 2027-01-21 16:00 | 2027-01-21 16:00 |  |  | 0 | 0 | 28 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | GCP-010 | Develop BMS Control Logic | Controls, BMS & DCIM | Graphics, Configuration & Programming | Not Started | 2026-08-07 08:00 | 2026-08-15 16:00 |  |  | 8 | 8 | 130 | No |  |  | 91000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | GCP-020 | Configure BMS Alarm Logic | Controls, BMS & DCIM | Graphics, Configuration & Programming | Not Started | 2026-08-10 08:00 | 2026-08-14 16:00 |  |  | 5 | 5 | 133 | No |  |  | 79000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | GCP-030 | Develop BMS Graphics | Controls, BMS & DCIM | Graphics, Configuration & Programming | Not Started | 2026-08-10 08:00 | 2026-08-18 16:00 |  |  | 8 | 8 | 130 | No |  |  | 91000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | GCP-040 | Configure DCIM Dashboards | Controls, BMS & DCIM | Graphics, Configuration & Programming | Not Started | 2026-08-10 08:00 | 2026-08-14 16:00 |  |  | 5 | 5 | 133 | No |  |  | 79000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | GCP-050 | Configure Trend Logging and Reporting | Controls, BMS & DCIM | Graphics, Configuration & Programming | Not Started | 2026-08-10 08:00 | 2026-08-13 16:00 |  |  | 4 | 4 | 134 | No |  |  | 15000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | GCP-060 | Complete Controls Software Configuration | Controls, BMS & DCIM | Graphics, Configuration & Programming | Not Started | 2026-08-19 08:00 | 2026-08-21 16:00 |  |  | 3 | 3 | 130 | No |  |  | 68000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | GCP-070 | BMS and DCIM Configuration Complete | Controls, BMS & DCIM | Graphics, Configuration & Programming | Not Started | 2026-08-21 16:00 | 2026-08-21 16:00 |  |  | 0 | 0 | 130 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | UTL-010 | Submit Utility Connection Application | Utility Connection & Energization | Utility Coordination & Approvals | Not Started | 2026-03-20 08:00 | 2026-03-25 16:00 |  |  | 5 | 5 | 177 | No |  |  | 30000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | UTL-020 | Coordinate Utility Technical Requirements | Utility Connection & Energization | Utility Coordination & Approvals | Not Started | 2026-03-26 08:00 | 2026-04-06 16:00 |  |  | 10 | 10 | 177 | No |  |  | 25000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | UTL-030 | Submit Utility Protection Study | Utility Connection & Energization | Utility Coordination & Approvals | Not Started | 2026-03-26 08:00 | 2026-04-06 16:00 |  |  | 10 | 10 | 177 | No |  |  | 37000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | UTL-040 | Resolve Utility Review Comments | Utility Connection & Energization | Utility Coordination & Approvals | Not Started | 2026-04-07 08:00 | 2026-04-17 16:00 |  |  | 10 | 10 | 177 | No |  |  | 25000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | UTL-050 | Obtain Utility Connection Approval | Utility Connection & Energization | Utility Coordination & Approvals | Not Started | 2026-04-17 16:00 | 2026-04-17 16:00 |  |  | 0 | 0 | 177 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | UCMV-010 | Complete Incoming Utility MV Infrastructure | Utility Connection & Energization | Incoming Utility / MV Connection | Not Started | 2026-04-18 08:00 | 2026-05-05 16:00 |  |  | 15 | 15 | 177 | No |  |  | 141000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | UCMV-020 | Install Utility Metering Equipment | Utility Connection & Energization | Incoming Utility / MV Connection | Not Started | 2026-04-22 08:00 | 2026-04-27 16:00 |  |  | 5 | 5 | 189 | No |  |  | 166000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | UCMV-030 | Complete Utility MV Cable Connections | Utility Connection & Energization | Incoming Utility / MV Connection | Not Started | 2026-05-06 08:00 | 2026-05-11 16:00 |  |  | 5 | 5 | 177 | No |  |  | 162000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | UCMV-040 | Complete Utility Protection Interfaces | Utility Connection & Energization | Incoming Utility / MV Connection | Not Started | 2026-04-24 08:00 | 2026-04-29 16:00 |  |  | 5 | 5 | 187 | No |  |  | 101000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | UCMV-050 | Incoming Utility Connection Ready | Utility Connection & Energization | Incoming Utility / MV Connection | Not Started | 2026-05-11 16:00 | 2026-05-11 16:00 |  |  | 0 | 0 | 177 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | SUB-010 | Inspect Utility Substation Installation | Utility Connection & Energization | Utility Substation Readiness | Not Started | 2026-05-12 08:00 | 2026-05-13 16:00 |  |  | 2 | 2 | 177 | No |  |  | 123000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | SUB-020 | Complete Substation Protection Testing | Utility Connection & Energization | Utility Substation Readiness | Not Started | 2026-05-14 08:00 | 2026-05-16 16:00 |  |  | 3 | 3 | 177 | No |  |  | 104000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | SUB-030 | Complete Substation Metering Testing | Utility Connection & Energization | Utility Substation Readiness | Not Started | 2026-05-14 08:00 | 2026-05-16 16:00 |  |  | 3 | 3 | 177 | No |  |  | 104000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | SUB-040 | Close Utility Substation Punch List | Utility Connection & Energization | Utility Substation Readiness | Not Started | 2026-05-18 08:00 | 2026-05-22 16:00 |  |  | 5 | 5 | 177 | No |  |  | 101000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | SUB-050 | Utility Substation Ready for Energization | Utility Connection & Energization | Utility Substation Readiness | Not Started | 2026-05-22 16:00 | 2026-05-22 16:00 |  |  | 0 | 0 | 177 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | MVE-010 | Complete MV Pre-Energization Checks | Utility Connection & Energization | MV System Energization | Not Started | 2026-11-16 08:00 | 2026-11-17 16:00 |  |  | 2 | 2 | 26 | No |  |  | 92000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | MVE-020 | Verify MV Protection Settings | Utility Connection & Energization | MV System Energization | Not Started | 2026-11-18 08:00 | 2026-11-19 16:00 |  |  | 2 | 2 | 26 | No |  |  | 77000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | MVE-030 | Obtain MV Energization Permit | Utility Connection & Energization | MV System Energization | Not Started | 2026-11-20 08:00 | 2026-11-21 16:00 |  |  | 2 | 2 | 26 | No |  |  | 92000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | MVE-040 | Energize Incoming MV System | Utility Connection & Energization | MV System Energization | Not Started | 2026-11-23 08:00 | 2026-11-23 16:00 |  |  | 1 | 1 | 26 | No |  |  | 75000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | MVE-050 | Verify MV System Operation | Utility Connection & Energization | MV System Energization | Not Started | 2026-11-24 08:00 | 2026-11-25 16:00 |  |  | 2 | 2 | 26 | No |  |  | 77000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | MVE-060 | MV System Energized | Utility Connection & Energization | MV System Energization | Not Started | 2026-11-25 16:00 | 2026-11-25 16:00 |  |  | 0 | 0 | 26 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | TRE-010 | Complete Transformer Pre-Energization Checks | Utility Connection & Energization | LV System Energization | Not Started | 2026-12-26 08:00 | 2026-12-26 16:00 |  |  | 1 | 1 | 0 | Yes | 10 | 4 | 75000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | TRE-020 | Verify Transformer Protection and Controls | Utility Connection & Energization | LV System Energization | Not Started | 2026-12-28 08:00 | 2026-12-29 16:00 |  |  | 2 | 2 | 0 | Yes | 10 | 5 | 77000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | TRE-030 | Energize Transformers | Utility Connection & Energization | LV System Energization | Not Started | 2026-12-30 08:00 | 2026-12-30 16:00 |  |  | 1 | 1 | 0 | Yes | 10 | 6 | 75000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | TRE-040 | Perform Transformer Operational Checks | Utility Connection & Energization | LV System Energization | Not Started | 2026-12-31 08:00 | 2027-01-01 16:00 |  |  | 2 | 2 | 0 | Yes | 10 | 7 | 77000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | TRE-050 | Transformers Energized | Utility Connection & Energization | LV System Energization | Not Started | 2027-01-01 16:00 | 2027-01-01 16:00 |  |  | 0 | 0 | 0 | Yes | 10 | 8 | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | LVE-010 | Complete LV Pre-Energization Checks | Utility Connection & Energization | UPS & Critical Power Energization | Not Started | 2027-01-02 08:00 | 2027-01-02 16:00 |  |  | 1 | 1 | 0 | Yes | 10 | 9 | 75000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | LVE-020 | Verify LV Protection Settings | Utility Connection & Energization | UPS & Critical Power Energization | Not Started | 2027-01-04 08:00 | 2027-01-05 16:00 |  |  | 2 | 2 | 0 | Yes | 10 | 10 | 77000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | LVE-030 | Energize Main LV Switchgear | Utility Connection & Energization | UPS & Critical Power Energization | Not Started | 2027-01-06 08:00 | 2027-01-06 16:00 |  |  | 1 | 1 | 0 | Yes | 10 | 11 | 75000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | LVE-040 | Energize LV Distribution Boards | Utility Connection & Energization | UPS & Critical Power Energization | Not Started | 2027-01-07 08:00 | 2027-01-09 16:00 |  |  | 3 | 3 | 0 | Yes | 10 | 12 | 104000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | LVE-050 | Verify LV System Operation | Utility Connection & Energization | UPS & Critical Power Energization | Not Started | 2027-01-11 08:00 | 2027-01-12 16:00 |  |  | 2 | 2 | 0 | Yes | 10 | 13 | 77000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | LVE-060 | LV System Energized | Utility Connection & Energization | UPS & Critical Power Energization | Not Started | 2027-01-12 16:00 | 2027-01-12 16:00 |  |  | 0 | 0 | 0 | Yes | 10 | 14 | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | UPE-010 | Complete UPS Pre-Energization Checks | Utility Connection & Energization | Generator & Backup Power Readiness | Not Started | 2027-01-13 08:00 | 2027-01-13 16:00 |  |  | 1 | 1 | 0 | Yes | 10 | 15 | 75000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | UPE-020 | Energize UPS Input Supply | Utility Connection & Energization | Generator & Backup Power Readiness | Not Started | 2027-01-14 08:00 | 2027-01-14 16:00 |  |  | 1 | 1 | 0 | Yes | 10 | 16 | 75000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | UPE-030 | Start and Configure UPS Systems | Utility Connection & Energization | Generator & Backup Power Readiness | Not Started | 2027-01-15 08:00 | 2027-01-18 16:00 |  |  | 3 | 3 | 0 | Yes | 10 | 17 | 87000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | UPE-040 | Energize UPS Output Distribution | Utility Connection & Energization | Generator & Backup Power Readiness | Not Started | 2027-01-19 08:00 | 2027-01-21 16:00 |  |  | 3 | 3 | 0 | Yes | 10 | 18 | 104000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | UPE-050 | Verify Battery System Operation | Utility Connection & Energization | Generator & Backup Power Readiness | Not Started | 2027-01-22 08:00 | 2027-01-23 16:00 |  |  | 2 | 2 | 0 | Yes | 10 | 19 | 77000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | UPE-060 | Critical Power System Energized | Utility Connection & Energization | Generator & Backup Power Readiness | Not Started | 2027-01-23 16:00 | 2027-01-23 16:00 |  |  | 0 | 0 | 0 | Yes | 10 | 20 | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | GBP-010 | Complete Generator Pre-Start Checks | Utility Connection & Energization | Data Hall Power-On | Not Started | 2026-12-31 08:00 | 2026-12-31 16:00 |  |  | 1 | 1 | 23 | No |  |  | 63000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | GBP-020 | Complete Generator Fuel System Readiness Checks | Utility Connection & Energization | Data Hall Power-On | Not Started | 2026-12-31 08:00 | 2026-12-31 16:00 |  |  | 1 | 1 | 23 | No |  |  | 63000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | GBP-030 | Start Standby Generators | Utility Connection & Energization | Data Hall Power-On | Not Started | 2027-01-01 08:00 | 2027-01-02 16:00 |  |  | 2 | 2 | 23 | No |  |  | 77000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | GBP-040 | Verify Generator Controls and Protection | Utility Connection & Energization | Data Hall Power-On | Not Started | 2027-01-04 08:00 | 2027-01-05 16:00 |  |  | 2 | 2 | 23 | No |  |  | 77000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | GBP-050 | Verify Generator Automatic Transfer Sequence | Utility Connection & Energization | Data Hall Power-On | Not Started | 2027-01-13 08:00 | 2027-01-14 16:00 |  |  | 2 | 2 | 17 | No |  |  | 77000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | GBP-060 | Backup Power System Ready | Utility Connection & Energization | Data Hall Power-On | Not Started | 2027-01-14 16:00 | 2027-01-14 16:00 |  |  | 0 | 0 | 17 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | DPO-010 | Verify Data Hall Electrical Installation Readiness | Utility Connection & Energization | Data Hall Power-On | Not Started | 2027-01-25 08:00 | 2027-01-26 16:00 |  |  | 2 | 2 | 0 | Yes | 1 | 24 | 123000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | DPO-020 | Verify UPS and PDU Availability | Utility Connection & Energization | Data Hall Power-On | Not Started | 2027-01-25 08:00 | 2027-01-26 16:00 |  |  | 2 | 2 | 0 | Yes | 10 | 21 | 77000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | DPO-030 | Verify Data Hall Earthing and Bonding | Utility Connection & Energization | Data Hall Power-On | Not Started | 2026-12-30 08:00 | 2026-12-31 16:00 |  |  | 2 | 2 | 22 | No |  |  | 77000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | DPO-040 | Energize Data Hall Busway Distribution | Utility Connection & Energization | Data Hall Power-On | Not Started | 2027-01-27 08:00 | 2027-01-28 16:00 |  |  | 2 | 2 | 0 | Yes | 1 | 25 | 123000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | DPO-050 | Energize Data Hall Power Distribution | Utility Connection & Energization | Data Hall Power-On | Not Started | 2027-01-29 08:00 | 2027-02-01 16:00 |  |  | 3 | 3 | 0 | Yes | 1 | 26 | 104000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | DPO-060 | Verify Data Hall Power Availability | Utility Connection & Energization | Data Hall Power-On | Not Started | 2027-02-02 08:00 | 2027-02-03 16:00 |  |  | 2 | 2 | 0 | Yes | 1 | 27 | 77000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | DPO-070 | Data Hall Power-On Complete | Utility Connection & Energization | Data Hall Power-On | Not Started | 2027-02-03 16:00 | 2027-02-03 16:00 |  |  | 0 | 0 | 0 | Yes | 1 | 28 | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CXP-010 | Develop Commissioning Management Plan | Testing & Commissioning | Commissioning Management & Planning | Completed | 2026-01-06 08:00 | 2026-01-10 16:00 | 2026-01-06 08:00 | 2026-01-10 16:00 | 5 | 0 |  | No |  |  | 41000 | 41000 | 41000 | 41289.5817 | -289.5817 | 0 | 0.99299 | 1
Update 02 | 2026-02-28 | CXP-020 | Develop Commissioning Schedule | Testing & Commissioning | Commissioning Management & Planning | Completed | 2026-01-12 08:00 | 2026-01-16 16:00 | 2026-01-12 08:00 | 2026-01-16 16:00 | 5 | 0 |  | No |  |  | 41000 | 41000 | 41000 | 42163.1382 | -1163.1382 | 0 | 0.97241 | 1
Update 02 | 2026-02-28 | CXP-030 | Develop Commissioning Procedures | Testing & Commissioning | Commissioning Management & Planning | Completed | 2026-01-12 08:00 | 2026-01-16 16:00 | 2026-01-12 08:00 | 2026-01-16 16:00 | 5 | 0 |  | No |  |  | 41000 | 41000 | 41000 | 42453.8369 | -1453.8369 | 0 | 0.96575 | 1
Update 02 | 2026-02-28 | CXP-040 | Develop Systems Completion Matrix | Testing & Commissioning | Commissioning Management & Planning | Completed | 2026-01-12 08:00 | 2026-01-16 16:00 | 2026-01-12 08:00 | 2026-01-16 16:00 | 5 | 0 |  | No |  |  | 34000 | 34000 | 34000 | 34107.821 | -107.821 | 0 | 0.99684 | 1
Update 02 | 2026-02-28 | CXP-050 | Establish Commissioning Documentation Register | Testing & Commissioning | Commissioning Management & Planning | Completed | 2026-01-12 08:00 | 2026-01-22 16:00 | 2026-01-12 08:00 | 2026-01-22 16:00 | 10 | 0 |  | No |  |  | 8000 | 8000 | 8000 | 8276.2507 | -276.2507 | 0 | 0.96662 | 1
Update 02 | 2026-02-28 | CXP-060 | Commissioning Plan Approved | Testing & Commissioning | Commissioning Management & Planning | Completed | 2026-01-22 16:00 | 2026-01-22 16:00 | 2026-01-22 16:00 | 2026-01-22 16:00 | 0 | 0 |  | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | PRE-010 | Complete Electrical Pre-Commissioning Inspections | Testing & Commissioning | Pre-Commissioning & Inspections | Not Started | 2027-01-25 08:00 | 2027-01-26 16:00 |  |  | 2 | 2 | 2 | No |  |  | 31000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | PRE-020 | Complete Mechanical Pre-Commissioning Inspections | Testing & Commissioning | Pre-Commissioning & Inspections | Not Started | 2026-12-08 08:00 | 2026-12-09 16:00 |  |  | 2 | 2 | 43 | No |  |  | 31000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | PRE-030 | Complete Fire System Pre-Commissioning Inspections | Testing & Commissioning | Pre-Commissioning & Inspections | Not Started | 2027-01-08 08:00 | 2027-01-09 16:00 |  |  | 2 | 2 | 16 | No |  |  | 31000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | PRE-040 | Complete BMS and Controls Pre-Commissioning Inspections | Testing & Commissioning | Pre-Commissioning & Inspections | Not Started | 2027-01-15 08:00 | 2027-01-16 16:00 |  |  | 2 | 2 | 10 | No |  |  | 31000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | PRE-050 | Complete Pre-Commissioning Punch List | Testing & Commissioning | Pre-Commissioning & Inspections | Not Started | 2027-01-27 08:00 | 2027-01-29 16:00 |  |  | 3 | 3 | 2 | No |  |  | 35000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | PRE-060 | Systems Ready for Functional Commissioning | Testing & Commissioning | Pre-Commissioning & Inspections | Not Started | 2027-01-29 16:00 | 2027-01-29 16:00 |  |  | 0 | 0 | 2 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | ELC-CX-010 | Commission MV Switchgear | Testing & Commissioning | Electrical Systems Commissioning | Not Started | 2027-02-04 08:00 | 2027-02-09 16:00 |  |  | 5 | 5 | 5 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | ELC-CX-020 | Commission Transformers | Testing & Commissioning | Electrical Systems Commissioning | Not Started | 2027-01-30 08:00 | 2027-02-04 16:00 |  |  | 5 | 5 | 9 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | ELC-CX-030 | Commission LV Switchgear | Testing & Commissioning | Electrical Systems Commissioning | Not Started | 2027-01-30 08:00 | 2027-02-04 16:00 |  |  | 5 | 5 | 9 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | ELC-CX-040 | Commission UPS Systems | Testing & Commissioning | Electrical Systems Commissioning | Not Started | 2027-01-30 08:00 | 2027-02-04 16:00 |  |  | 5 | 5 | 9 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | ELC-CX-050 | Commission Battery Systems | Testing & Commissioning | Electrical Systems Commissioning | Not Started | 2027-01-30 08:00 | 2027-02-04 16:00 |  |  | 5 | 5 | 9 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | ELC-CX-060 | Commission Standby Generators | Testing & Commissioning | Electrical Systems Commissioning | Not Started | 2027-01-30 08:00 | 2027-02-04 16:00 |  |  | 5 | 5 | 9 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | ELC-CX-070 | Commission PDU and Busway Distribution | Testing & Commissioning | Electrical Systems Commissioning | Not Started | 2027-02-04 08:00 | 2027-02-15 16:00 |  |  | 10 | 10 | 0 | Yes | 8 | 1 | 62000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | ELC-CX-080 | Electrical Systems Functional Testing Complete | Testing & Commissioning | Electrical Systems Commissioning | Not Started | 2027-02-15 16:00 | 2027-02-15 16:00 |  |  | 0 | 0 | 0 | Yes | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | MEC-CX-010 | Commission Chillers and Heat Rejection Equipment | Testing & Commissioning | Mechanical & Cooling Commissioning | Not Started | 2027-01-30 08:00 | 2027-02-04 16:00 |  |  | 5 | 5 | 2 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | MEC-CX-020 | Commission Cooling Pumps | Testing & Commissioning | Mechanical & Cooling Commissioning | Not Started | 2027-01-30 08:00 | 2027-02-04 16:00 |  |  | 5 | 5 | 2 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | MEC-CX-030 | Commission Chilled Water System | Testing & Commissioning | Mechanical & Cooling Commissioning | Not Started | 2027-01-30 08:00 | 2027-02-04 16:00 |  |  | 5 | 5 | 2 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | MEC-CX-040 | Commission CRAH CRAC Systems | Testing & Commissioning | Mechanical & Cooling Commissioning | Not Started | 2027-01-30 08:00 | 2027-02-04 16:00 |  |  | 5 | 5 | 2 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | MEC-CX-050 | Perform Air and Water Balancing | Testing & Commissioning | Mechanical & Cooling Commissioning | Not Started | 2027-02-05 08:00 | 2027-02-10 16:00 |  |  | 5 | 5 | 2 | No |  |  | 34000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | MEC-CX-060 | Verify Cooling System Controls | Testing & Commissioning | Mechanical & Cooling Commissioning | Not Started | 2027-02-11 08:00 | 2027-02-12 16:00 |  |  | 2 | 2 | 2 | No |  |  | 26000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | MEC-CX-070 | Mechanical Systems Functional Testing Complete | Testing & Commissioning | Mechanical & Cooling Commissioning | Not Started | 2027-02-12 16:00 | 2027-02-12 16:00 |  |  | 0 | 0 | 2 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | FLS-CX-010 | Commission Fire Detection and Alarm System | Testing & Commissioning | Fire & Life Safety Commissioning | Not Started | 2027-01-30 08:00 | 2027-02-04 16:00 |  |  | 5 | 5 | 10 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | FLS-CX-020 | Commission Sprinkler System | Testing & Commissioning | Fire & Life Safety Commissioning | Not Started | 2027-01-30 08:00 | 2027-02-04 16:00 |  |  | 5 | 5 | 10 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | FLS-CX-030 | Commission Clean Agent Fire Suppression | Testing & Commissioning | Fire & Life Safety Commissioning | Not Started | 2027-01-30 08:00 | 2027-02-04 16:00 |  |  | 5 | 5 | 10 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | FLS-CX-040 | Commission Fire Pumps | Testing & Commissioning | Fire & Life Safety Commissioning | Not Started | 2027-01-30 08:00 | 2027-02-04 16:00 |  |  | 5 | 5 | 10 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | FLS-CX-050 | Commission VESDA System | Testing & Commissioning | Fire & Life Safety Commissioning | Not Started | 2027-01-30 08:00 | 2027-02-04 16:00 |  |  | 5 | 5 | 10 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | FLS-CX-060 | Verify Fire Cause and Effect Matrix | Testing & Commissioning | Fire & Life Safety Commissioning | Not Started | 2027-02-05 08:00 | 2027-02-06 16:00 |  |  | 2 | 2 | 10 | No |  |  | 26000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | FLS-CX-070 | Fire and Life Safety Commissioning Complete | Testing & Commissioning | Fire & Life Safety Commissioning | Not Started | 2027-02-06 16:00 | 2027-02-06 16:00 |  |  | 0 | 0 | 10 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | BMS-CX-010 | Commission BMS Infrastructure | Testing & Commissioning | BMS & DCIM Commissioning | Not Started | 2027-01-30 08:00 | 2027-02-04 16:00 |  |  | 5 | 5 | 5 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | BMS-CX-020 | Verify BMS Field Points | Testing & Commissioning | BMS & DCIM Commissioning | Not Started | 2027-02-05 08:00 | 2027-02-06 16:00 |  |  | 2 | 2 | 5 | No |  |  | 26000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | BMS-CX-030 | Commission BMS Graphics and Alarms | Testing & Commissioning | BMS & DCIM Commissioning | Not Started | 2027-02-08 08:00 | 2027-02-12 16:00 |  |  | 5 | 5 | 5 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | BMS-CX-040 | Commission DCIM Platform | Testing & Commissioning | BMS & DCIM Commissioning | Not Started | 2027-01-30 08:00 | 2027-02-04 16:00 |  |  | 5 | 5 | 10 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | BMS-CX-050 | Verify DCIM Power Monitoring | Testing & Commissioning | BMS & DCIM Commissioning | Not Started | 2027-02-16 08:00 | 2027-02-17 16:00 |  |  | 2 | 2 | 1 | No |  |  | 5000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | BMS-CX-060 | Verify DCIM Cooling Monitoring | Testing & Commissioning | BMS & DCIM Commissioning | Not Started | 2027-02-13 08:00 | 2027-02-15 16:00 |  |  | 2 | 2 | 3 | No |  |  | 5000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | BMS-CX-070 | BMS and DCIM Commissioning Complete | Testing & Commissioning | BMS & DCIM Commissioning | Not Started | 2027-02-17 16:00 | 2027-02-17 16:00 |  |  | 0 | 0 | 1 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | INT-CX-010 | Verify Electrical to BMS Integration | Testing & Commissioning | Controls & Systems Integration | Not Started | 2027-02-18 08:00 | 2027-02-19 16:00 |  |  | 2 | 2 | 1 | No |  |  | 26000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | INT-CX-020 | Verify Mechanical to BMS Integration | Testing & Commissioning | Controls & Systems Integration | Not Started | 2027-02-18 08:00 | 2027-02-19 16:00 |  |  | 2 | 2 | 1 | No |  |  | 26000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | INT-CX-030 | Verify Fire System Integration | Testing & Commissioning | Controls & Systems Integration | Not Started | 2027-02-18 08:00 | 2027-02-19 16:00 |  |  | 2 | 2 | 1 | No |  |  | 26000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | INT-CX-040 | Verify UPS and Generator Controls Integration | Testing & Commissioning | Controls & Systems Integration | Not Started | 2027-02-18 08:00 | 2027-02-19 16:00 |  |  | 2 | 2 | 1 | No |  |  | 26000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | INT-CX-050 | Complete Integrated Controls Testing | Testing & Commissioning | Controls & Systems Integration | Not Started | 2027-02-20 08:00 | 2027-02-22 16:00 |  |  | 2 | 2 | 1 | No |  |  | 31000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | INT-CX-060 | Systems Integration Complete | Testing & Commissioning | Controls & Systems Integration | Not Started | 2027-02-22 16:00 | 2027-02-22 16:00 |  |  | 0 | 0 | 1 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | IST-010 | Prepare Integrated Systems Test Scripts | Testing & Commissioning | Integrated Systems Testing (IST) | In Progress | 2026-01-23 08:00 | 2026-02-03 16:00 | 2026-01-23 08:00 |  | 10 | 0.30783 | 328 | No |  |  | 50000 | 50000 | 48460.8402 | 50238.2909 | -1777.4507 | -1539.1598 | 0.96462 | 0.96922
Update 02 | 2026-02-28 | IST-020 | Conduct Utility Power Failure Scenario | Testing & Commissioning | Integrated Systems Testing (IST) | Not Started | 2027-02-24 08:00 | 2027-03-01 16:00 |  |  | 5 | 5 | 0 | Yes | 1 | 34 | 34000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | IST-030 | Conduct Generator Transfer Scenario | Testing & Commissioning | Integrated Systems Testing (IST) | Not Started | 2027-02-24 08:00 | 2027-03-01 16:00 |  |  | 5 | 5 | 0 | Yes | 4 | 1 | 34000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | IST-040 | Conduct UPS Battery Ride-Through Scenario | Testing & Commissioning | Integrated Systems Testing (IST) | Not Started | 2027-02-24 08:00 | 2027-03-01 16:00 |  |  | 5 | 5 | 0 | Yes | 5 | 1 | 34000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | IST-050 | Conduct Cooling Failure Scenario | Testing & Commissioning | Integrated Systems Testing (IST) | Not Started | 2027-02-24 08:00 | 2027-03-01 16:00 |  |  | 5 | 5 | 0 | Yes | 6 | 1 | 34000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | IST-060 | Conduct Fire Alarm Integration Scenario | Testing & Commissioning | Integrated Systems Testing (IST) | Not Started | 2027-02-24 08:00 | 2027-03-01 16:00 |  |  | 5 | 5 | 0 | Yes | 7 | 1 | 34000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | IST-070 | Conduct BMS DCIM Alarm Response Testing | Testing & Commissioning | Integrated Systems Testing (IST) | Not Started | 2027-02-24 08:00 | 2027-02-26 16:00 |  |  | 3 | 3 | 2 | No |  |  | 35000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | IST-080 | Resolve IST Deficiencies | Testing & Commissioning | Integrated Systems Testing (IST) | Not Started | 2027-03-02 08:00 | 2027-03-12 16:00 |  |  | 10 | 10 | 0 | Yes | 1 | 35 | 42000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | IST-090 | Integrated Systems Testing Complete | Testing & Commissioning | Integrated Systems Testing (IST) | Not Started | 2027-03-12 16:00 | 2027-03-12 16:00 |  |  | 0 | 0 | 0 | Yes | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | LBT-010 | Mobilize Load Bank Equipment | Testing & Commissioning | Load Bank & Performance Testing | Not Started | 2027-02-04 08:00 | 2027-02-09 16:00 |  |  | 5 | 5 | 0 | Yes | 1 | 29 | 41000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | LBT-020 | Connect Load Bank Equipment | Testing & Commissioning | Load Bank & Performance Testing | Not Started | 2027-02-10 08:00 | 2027-02-15 16:00 |  |  | 5 | 5 | 0 | Yes | 1 | 30 | 41000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | LBT-030 | Perform UPS Load Bank Testing | Testing & Commissioning | Load Bank & Performance Testing | Not Started | 2027-02-16 08:00 | 2027-02-20 16:00 |  |  | 5 | 5 | 0 | Yes | 1 | 31 | 41000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | LBT-040 | Perform Generator Load Bank Testing | Testing & Commissioning | Load Bank & Performance Testing | Not Started | 2027-02-16 08:00 | 2027-02-20 16:00 |  |  | 5 | 5 | 0 | Yes | 8 | 3 | 41000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | LBT-050 | Perform Cooling Performance Testing | Testing & Commissioning | Load Bank & Performance Testing | Not Started | 2027-02-16 08:00 | 2027-02-20 16:00 |  |  | 5 | 5 | 0 | Yes | 9 | 1 | 41000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | LBT-060 | Verify Data Hall Environmental Performance | Testing & Commissioning | Load Bank & Performance Testing | Not Started | 2027-02-22 08:00 | 2027-02-23 16:00 |  |  | 2 | 2 | 0 | Yes | 1 | 32 | 26000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | LBT-070 | Load Bank and Performance Testing Complete | Testing & Commissioning | Load Bank & Performance Testing | Not Started | 2027-02-23 16:00 | 2027-02-23 16:00 |  |  | 0 | 0 | 0 | Yes | 1 | 33 | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | RRT-010 | Develop Reliability Test Plan | Testing & Commissioning | Reliability / Resilience Testing | In Progress | 2026-01-23 08:00 | 2026-02-03 16:00 | 2026-01-23 08:00 |  | 10 | 4.6892 | 343 | No |  |  | 50000 | 50000 | 36553.9541 | 40148.07 | -3594.1159 | -13446.0459 | 0.91048 | 0.73108
Update 02 | 2026-02-28 | RRT-020 | Perform Utility Loss Resilience Test | Testing & Commissioning | Reliability / Resilience Testing | Not Started | 2027-03-13 08:00 | 2027-03-24 16:00 |  |  | 10 | 10 | 0 | Yes | 1 | 37 | 50000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | RRT-030 | Perform Generator Failure Simulation | Testing & Commissioning | Reliability / Resilience Testing | Not Started | 2027-03-13 08:00 | 2027-03-18 16:00 |  |  | 5 | 5 | 5 | No |  |  | 34000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | RRT-040 | Perform UPS Failure Simulation | Testing & Commissioning | Reliability / Resilience Testing | Not Started | 2027-03-13 08:00 | 2027-03-18 16:00 |  |  | 5 | 5 | 5 | No |  |  | 34000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | RRT-050 | Perform Cooling Failure Simulation | Testing & Commissioning | Reliability / Resilience Testing | Not Started | 2027-03-13 08:00 | 2027-03-18 16:00 |  |  | 5 | 5 | 5 | No |  |  | 34000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | RRT-060 | Complete Reliability Demonstration | Testing & Commissioning | Reliability / Resilience Testing | Not Started | 2027-03-25 08:00 | 2027-03-26 16:00 |  |  | 2 | 2 | 0 | Yes | 1 | 38 | 31000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | RRT-070 | Reliability Testing Complete | Testing & Commissioning | Reliability / Resilience Testing | Not Started | 2027-03-26 16:00 | 2027-03-26 16:00 |  |  | 0 | 0 | 0 | Yes | 1 | 39 | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CXC-010 | Compile Commissioning Defects List | Testing & Commissioning | Commissioning Defects & Closeout | Not Started | 2027-03-27 08:00 | 2027-04-07 16:00 |  |  | 10 | 10 | 0 | Yes | 1 | 40 | 50000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CXC-020 | Rectify Electrical Commissioning Defects | Testing & Commissioning | Commissioning Defects & Closeout | Not Started | 2027-04-08 08:00 | 2027-04-13 16:00 |  |  | 5 | 5 | 2 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CXC-030 | Rectify Mechanical Commissioning Defects | Testing & Commissioning | Commissioning Defects & Closeout | Not Started | 2027-04-08 08:00 | 2027-04-13 16:00 |  |  | 5 | 5 | 2 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CXC-040 | Rectify Controls and BMS Defects | Testing & Commissioning | Commissioning Defects & Closeout | Not Started | 2027-04-08 08:00 | 2027-04-15 16:00 |  |  | 7 | 7 | 0 | Yes | 1 | 41 | 38000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CXC-050 | Rectify Fire System Defects | Testing & Commissioning | Commissioning Defects & Closeout | Not Started | 2027-04-08 08:00 | 2027-04-15 16:00 |  |  | 7 | 7 | 0 | Yes | 3 | 1 | 38000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CXC-060 | Close Commissioning Punch List | Testing & Commissioning | Commissioning Defects & Closeout | Not Started | 2027-04-16 08:00 | 2027-04-27 16:00 |  |  | 10 | 10 | 0 | Yes | 1 | 42 | 50000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CXC-070 | Commissioning Complete | Testing & Commissioning | Commissioning Defects & Closeout | Not Started | 2027-04-27 16:00 | 2027-04-27 16:00 |  |  | 0 | 0 | 0 | Yes | 1 | 43 | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | HND-010 | Conduct Client Pre-Handover Inspection | Client Acceptance & Handover | Punch List / Snagging | Not Started | 2027-04-28 08:00 | 2027-04-29 16:00 |  |  | 2 | 2 | 0 | Yes | 1 | 44 | 44000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | HND-020 | Prepare Final Punch List | Client Acceptance & Handover | Punch List / Snagging | Not Started | 2027-04-30 08:00 | 2027-05-13 16:00 |  |  | 10 | 10 | 0 | Yes | 1 | 45 | 35000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | HND-030 | Rectify Final Punch List Items | Client Acceptance & Handover | Punch List / Snagging | Not Started | 2027-05-14 08:00 | 2027-05-27 16:00 |  |  | 10 | 10 | 0 | Yes | 1 | 46 | 35000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | HND-040 | Verify Punch List Closure | Client Acceptance & Handover | Punch List / Snagging | Not Started | 2027-05-28 08:00 | 2027-05-31 16:00 |  |  | 2 | 2 | 0 | Yes | 1 | 47 | 22000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | ASB-010 | Compile Civil and Architectural As-Built Drawings | Client Acceptance & Handover | As-Built Documentation | Not Started | 2026-08-25 08:00 | 2026-09-07 16:00 |  |  | 10 | 10 | 172 | No |  |  | 35000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | ASB-020 | Compile Electrical As-Built Drawings | Client Acceptance & Handover | As-Built Documentation | Not Started | 2027-01-11 08:00 | 2027-01-22 16:00 |  |  | 10 | 10 | 73 | No |  |  | 35000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | ASB-030 | Compile Mechanical As-Built Drawings | Client Acceptance & Handover | As-Built Documentation | Not Started | 2026-12-15 08:00 | 2026-12-28 16:00 |  |  | 10 | 10 | 92 | No |  |  | 35000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | ASB-040 | Compile Controls and Fire As-Built Drawings | Client Acceptance & Handover | As-Built Documentation | Not Started | 2027-01-08 08:00 | 2027-01-21 16:00 |  |  | 10 | 10 | 74 | No |  |  | 35000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | ASB-050 | Submit Final As-Built Documentation | Client Acceptance & Handover | As-Built Documentation | Not Started | 2027-01-25 08:00 | 2027-02-05 16:00 |  |  | 10 | 10 | 73 | No |  |  | 18000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | OMM-010 | Compile Electrical O&M Manuals | Client Acceptance & Handover | O&M Manuals | Not Started | 2026-12-14 08:00 | 2026-12-25 16:00 |  |  | 10 | 10 | 93 | No |  |  | 35000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | OMM-020 | Compile Mechanical O&M Manuals | Client Acceptance & Handover | O&M Manuals | Not Started | 2026-08-28 08:00 | 2026-09-10 16:00 |  |  | 10 | 10 | 169 | No |  |  | 35000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | OMM-030 | Compile Fire and Life Safety O&M Manuals | Client Acceptance & Handover | O&M Manuals | Not Started | 2026-06-10 08:00 | 2026-06-23 16:00 |  |  | 10 | 10 | 226 | No |  |  | 35000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | OMM-040 | Compile BMS and DCIM O&M Manuals | Client Acceptance & Handover | O&M Manuals | Not Started | 2026-08-07 08:00 | 2026-08-20 16:00 |  |  | 10 | 10 | 184 | No |  |  | 35000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | OMM-050 | Submit Final O&M Manuals | Client Acceptance & Handover | O&M Manuals | Not Started | 2026-12-28 08:00 | 2027-01-08 16:00 |  |  | 10 | 10 | 93 | No |  |  | 18000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | TRN-010 | Develop Operations Training Plan | Client Acceptance & Handover | Training & Knowledge Transfer | Completed | 2026-01-23 08:00 | 2026-01-29 16:00 | 2026-01-23 08:00 | 2026-01-29 16:00 | 5 | 0 |  | No |  |  | 29000 | 29000 | 29000 | 30141.2916 | -1141.2916 | 0 | 0.96214 | 1
Update 02 | 2026-02-28 | TRN-020 | Conduct Electrical Systems Training | Client Acceptance & Handover | Training & Knowledge Transfer | Not Started | 2027-02-16 08:00 | 2027-02-22 16:00 |  |  | 5 | 5 | 72 | No |  |  | 29000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | TRN-030 | Conduct Mechanical Systems Training | Client Acceptance & Handover | Training & Knowledge Transfer | Not Started | 2027-02-15 08:00 | 2027-02-19 16:00 |  |  | 5 | 5 | 73 | No |  |  | 29000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | TRN-040 | Conduct Fire and Life Safety Training | Client Acceptance & Handover | Training & Knowledge Transfer | Not Started | 2027-02-08 08:00 | 2027-02-12 16:00 |  |  | 5 | 5 | 78 | No |  |  | 29000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | TRN-050 | Conduct BMS and DCIM Training | Client Acceptance & Handover | Training & Knowledge Transfer | Not Started | 2027-02-18 08:00 | 2027-02-24 16:00 |  |  | 5 | 5 | 70 | No |  |  | 29000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | TRN-060 | Operations Training Complete | Client Acceptance & Handover | Training & Knowledge Transfer | Not Started | 2027-02-24 16:00 | 2027-02-24 16:00 |  |  | 0 | 0 | 70 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | AUT-010 | Submit Final Authority Inspection Request | Client Acceptance & Handover | Authority / Regulatory Approvals | Not Started | 2027-02-22 08:00 | 2027-02-23 16:00 |  |  | 2 | 2 | 52 | No |  |  | 11000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | AUT-020 | Conduct Fire Authority Inspection | Client Acceptance & Handover | Authority / Regulatory Approvals | Not Started | 2027-02-24 08:00 | 2027-02-25 16:00 |  |  | 2 | 2 | 52 | No |  |  | 44000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | AUT-030 | Conduct Electrical Authority Inspection | Client Acceptance & Handover | Authority / Regulatory Approvals | Not Started | 2027-02-24 08:00 | 2027-02-25 16:00 |  |  | 2 | 2 | 52 | No |  |  | 44000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | AUT-040 | Resolve Authority Inspection Comments | Client Acceptance & Handover | Authority / Regulatory Approvals | Not Started | 2027-02-26 08:00 | 2027-03-01 16:00 |  |  | 2 | 2 | 52 | No |  |  | 44000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | AUT-050 | Obtain Final Authority Approvals | Client Acceptance & Handover | Authority / Regulatory Approvals | Not Started | 2027-03-02 08:00 | 2027-03-10 16:00 |  |  | 7 | 7 | 52 | No |  |  | 16000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CFI-010 | Conduct Client Final Technical Inspection | Client Acceptance & Handover | Client Final Inspections | Not Started | 2027-06-01 08:00 | 2027-06-02 16:00 |  |  | 2 | 2 | 0 | Yes | 1 | 48 | 44000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CFI-020 | Conduct Client Operations Readiness Review | Client Acceptance & Handover | Client Final Inspections | Not Started | 2027-06-03 08:00 | 2027-06-09 16:00 |  |  | 5 | 5 | 0 | Yes | 1 | 49 | 10000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CFI-030 | Resolve Client Final Inspection Comments | Client Acceptance & Handover | Client Final Inspections | Not Started | 2027-06-10 08:00 | 2027-06-11 16:00 |  |  | 2 | 2 | 0 | Yes | 1 | 50 | 44000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | CFI-040 | Client Final Inspection Accepted | Client Acceptance & Handover | Client Final Inspections | Not Started | 2027-06-14 08:00 | 2027-06-15 16:00 |  |  | 2 | 2 | 0 | Yes | 1 | 51 | 44000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | DFC-010 | Compile Outstanding Defects Register | Client Acceptance & Handover | Final Documentation & Turnover | Not Started | 2027-06-16 08:00 | 2027-06-29 16:00 |  |  | 10 | 10 | 0 | Yes | 1 | 52 | 12000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | DFC-020 | Rectify Outstanding Construction Defects | Client Acceptance & Handover | Final Documentation & Turnover | Not Started | 2027-06-30 08:00 | 2027-07-08 16:00 |  |  | 7 | 7 | 0 | Yes | 1 | 53 | 80000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | DFC-030 | Rectify Outstanding Systems Defects | Client Acceptance & Handover | Final Documentation & Turnover | Not Started | 2027-06-30 08:00 | 2027-07-08 16:00 |  |  | 7 | 7 | 0 | Yes | 2 | 1 | 32000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | DFC-040 | Verify Outstanding Defects Closure | Client Acceptance & Handover | Final Documentation & Turnover | Not Started | 2027-07-09 08:00 | 2027-07-12 16:00 |  |  | 2 | 2 | 0 | Yes | 1 | 54 | 22000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | FDT-010 | Compile Final Handover Dossier | Client Acceptance & Handover | Ready for Service | Not Started | 2027-02-08 08:00 | 2027-02-12 16:00 |  |  | 5 | 5 | 73 | No |  |  | 29000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | FDT-020 | Submit Commissioning Records | Client Acceptance & Handover | Ready for Service | Not Started | 2027-04-28 08:00 | 2027-05-04 16:00 |  |  | 5 | 5 | 16 | No |  |  | 14000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | FDT-030 | Submit Testing Certificates | Client Acceptance & Handover | Ready for Service | Not Started | 2027-03-29 08:00 | 2027-03-31 16:00 |  |  | 3 | 3 | 40 | No |  |  | 12000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | FDT-040 | Submit Equipment Warranties | Client Acceptance & Handover | Ready for Service | Not Started | 2026-11-12 08:00 | 2026-11-18 16:00 |  |  | 5 | 5 | 135 | No |  |  | 14000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | FDT-050 | Final Handover Documentation Accepted | Client Acceptance & Handover | Ready for Service | Not Started | 2027-05-05 08:00 | 2027-05-11 16:00 |  |  | 5 | 5 | 16 | No |  |  | 29000 | 0 | 0 | 0 | 0 | 0

## UPDATE_HISTORY
Update_ID | Project_ID | Data_Date | BAC | PV | EV | AC | CPI | SPI | CV | SV | Completed | In_Progress | Not_Started | Critical_Activities | Forecast_Finish
Update 01 | DC-HYP-FINAL-6 | 2026-01-31 17:00 | 120000000 | 7850498.753 | 7837700 | 7985259.46 | 0.98152 | 0.99837 | -147559.46 | -12798.7531 | 44 | 21 | 743 | 1900-03-29 | 2027-07-19 16:00
Update 02 | DC-HYP-FINAL-6 | 2026-02-28 | 120000000 | 13314904.3115 | 13018484.6697 | 13366568.9244 | 0.97396 | 0.97774 | -348084.2547 | -296419.6418 | 62 | 58 | 688 | 1900-03-29 | 2027-07-19 16:00

## PROJECT_SUMMARY_HISTORY
Update_ID | Project_ID | Project_Name | Data_Date | Planned_Start | Forecast_Finish | Total_Activities | Completed | In_Progress | Not_Started | Critical_Activities | Relationships | BAC | PV | EV | AC | CPI | SPI | CV | SV | QA_Status | QA_Errors | QA_Warnings | EAC_Budget_Rate | EAC_CPI_Based | EAC_CPI_SPI | Primary_EAC | Primary_ETC | Primary_VAC | Primary_VAC_Percent | Negative_Float_Activities | Low_Float_Activities | Stage2_QA_Status
Update 01 | DC-HYP-FINAL-6 | Hyperscale Data Center Development | 2026-01-31 17:00 | 2026-01-05 | 2027-07-19 16:00 | 808 | 44 | 21 | 743 | 89 | 1406 | 120000000 | 7850498.753 | 7837700 | 7985259.46 | 0.98152 | 0.99837 | -147559.46 | -12798.7531 | WARNING | 0 | 2 | 120147559.5 | 122259225.9 | 122458872 | 122259225.9 | 114273966.5 | -2259225.946 | -0.018827 | 0 | 140 | PASS
Update 02 | DC-HYP-FINAL-6 | Hyperscale Data Center Development | 2026-02-28 | 2026-01-05 | 2027-07-19 16:00 | 808 | 62 | 58 | 688 | 89 | 1406 | 120000000 | 13314904.3115 | 13018484.6697 | 13366568.9244 | 0.97396 | 0.97774 | -348084.2547 | -296419.6418 | WARNING | 0 | 2 | 120348084.2547 | 123208523.2362 | 126013874.8001 | 123208523.2362 | 109841954.3118 | -3208523.2362 | -0.026738 | 0 | 140 | PASS

## WBS_PERFORMANCE_HISTORY
Update_ID | Data_Date | Level1_WBS | Activities | Completed | In_Progress | Not_Started | Critical_Activities | BAC | PV | EV | AC | CV | SV | CPI | SPI
Update 01 | 2026-01-31 17:00 | Building Envelope | 47 | 0 | 0 | 47 | 0 | 4800000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | Civil & Structural Works | 67 | 0 | 0 | 67 | 0 | 12000000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | Client Acceptance & Handover | 42 | 1 | 0 | 41 | 14 | 1200000 | 29000 | 29000 | 29102.15 | -102.15 | 0 | 0.99649 | 1
Update 01 | 2026-01-31 17:00 | Controls, BMS & DCIM | 56 | 0 | 0 | 56 | 0 | 3600000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | Design & Engineering | 78 | 11 | 17 | 50 | 7 | 7200000 | 2507200.379 | 2497300 | 2608238.62 | -110938.62 | -9900.3785 | 0.95747 | 0.99605
Update 01 | 2026-01-31 17:00 | Electrical Systems | 86 | 0 | 0 | 86 | 15 | 16800000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | Enabling & Site Works | 55 | 5 | 0 | 50 | 0 | 4800000 | 464000 | 464000 | 459616.92 | 4383.08 | 0 | 1.0095 | 1
Update 01 | 2026-01-31 17:00 | Fire & Life Safety | 61 | 0 | 0 | 61 | 0 | 3600000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | Mechanical & Cooling Systems | 85 | 0 | 0 | 85 | 0 | 13200000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | Procurement | 80 | 2 | 1 | 77 | 6 | 42000000 | 227000 | 206000 | 215649.86 | -9649.86 | -21000 | 0.95525 | 0.90749
Update 01 | 2026-01-31 17:00 | Project Management & Controls | 23 | 19 | 1 | 3 | 0 | 4800000 | 4384401.316 | 4416400 | 4447161.25 | -30761.25 | 31998.6842 | 0.99308 | 1.0073
Update 01 | 2026-01-31 17:00 | Testing & Commissioning | 77 | 6 | 2 | 69 | 24 | 2400000 | 238897.0588 | 225000 | 225490.66 | -490.66 | -13897.0588 | 0.99782 | 0.94183
Update 01 | 2026-01-31 17:00 | Utility Connection & Energization | 51 | 0 | 0 | 51 | 23 | 3600000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | Building Envelope | 47 | 0 | 0 | 47 | 0 | 4800000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | Civil & Structural Works | 67 | 0 | 0 | 67 | 0 | 12000000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | Client Acceptance & Handover | 42 | 1 | 0 | 41 | 14 | 1200000 | 29000 | 29000 | 30141.2916 | -1141.2916 | 0 | 0.96214 | 1
Update 02 | 2026-02-28 | Controls, BMS & DCIM | 56 | 0 | 0 | 56 | 0 | 3600000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | Design & Engineering | 78 | 19 | 36 | 23 | 7 | 7200000 | 5455002.2199 | 5303854.4495 | 5466210.6939 | -162356.2444 | -151147.7704 | 0.9703 | 0.97229
Update 02 | 2026-02-28 | Electrical Systems | 86 | 0 | 0 | 86 | 15 | 16800000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | Enabling & Site Works | 55 | 9 | 8 | 38 | 0 | 4800000 | 1284961.039 | 1276007.4573 | 1302631.0354 | -26623.5781 | -8953.5817 | 0.97956 | 0.99303
Update 02 | 2026-02-28 | Fire & Life Safety | 61 | 0 | 0 | 61 | 0 | 3600000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | Mechanical & Cooling Systems | 85 | 0 | 0 | 85 | 0 | 13200000 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | Procurement | 80 | 6 | 10 | 64 | 6 | 42000000 | 1480941.0526 | 1407592.8468 | 1457556.4566 | -49963.6098 | -73348.2058 | 0.96572 | 0.95047
Update 02 | 2026-02-28 | Project Management & Controls | 23 | 21 | 2 | 0 | 0 | 4800000 | 4800000 | 4752015.1218 | 4851352.4575 | -99337.3357 | -47984.8782 | 0.97952 | 0.99
Update 02 | 2026-02-28 | Testing & Commissioning | 77 | 6 | 2 | 69 | 24 | 2400000 | 265000 | 250014.7943 | 258676.9894 | -8662.1951 | -14985.2057 | 0.96651 | 0.94345
Update 02 | 2026-02-28 | Utility Connection & Energization | 51 | 0 | 0 | 51 | 23 | 3600000 | 0 | 0 | 0 | 0 | 0

## ACTIVITY_STATUS_HISTORY
Update_ID | Data_Date | Activity_ID | Activity_Name | Level1_WBS | Activity_WBS | Status | Planned_Start | Planned_Finish | Actual_Start | Actual_Finish | Original_Duration_Days | Remaining_Duration_Days | Total_Float_Days | Is_Critical | Float_Path | Float_Path_Order | BAC | PV | EV | AC | CV | SV | CPI | SPI | BAC_Source_Status | PV_Source_Status | EV_Source_Status | AC_Source_Status
Update 01 | 2026-01-31 17:00 | ABM-010 | Prepare Architectural Materials Submittals | Procurement | Architectural & Building Materials | Not Started | 2026-02-26 08:00 | 2026-03-04 16:00 |  |  | 5 | 5 | 94 | No |  |  | 67000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ABM-020 | Architectural Materials Submittals Approval | Procurement | Architectural & Building Materials | Not Started | 2026-03-05 08:00 | 2026-03-11 16:00 |  |  | 5 | 5 | 94 | No |  |  | 67000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ABM-030 | Procure Roofing and Waterproofing Materials | Procurement | Architectural & Building Materials | Not Started | 2026-03-12 08:00 | 2026-04-01 16:00 |  |  | 15 | 15 | 94 | No |  |  | 124000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ABM-040 | Procure External Cladding Materials | Procurement | Architectural & Building Materials | Not Started | 2026-04-02 08:00 | 2026-04-29 16:00 |  |  | 20 | 20 | 94 | No |  |  | 136000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ABM-050 | Procure Doors Louvers and Fire-Rated Assemblies | Procurement | Architectural & Building Materials | Not Started | 2026-04-30 08:00 | 2026-05-20 16:00 |  |  | 15 | 15 | 94 | No |  |  | 174000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ABM-060 | Deliver Architectural Materials to Site | Procurement | Architectural & Building Materials | Not Started | 2026-05-21 08:00 | 2026-05-25 16:00 |  |  | 3 | 3 | 94 | No |  |  | 77000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ARC-010 | Develop Architectural Design Criteria | Design & Engineering | Architectural Design | Completed | 2026-01-13 08:00 | 2026-01-19 16:00 | 2026-01-13 08:00 | 2026-01-21 16:00 | 5 | 0 |  | No |  |  | 111000 | 111000 | 111000 | 115715.26 | -4715.26 | 0 | 0.95925 | 1
Update 01 | 2026-01-31 17:00 | ARC-020 | Develop Data Hall Layout | Design & Engineering | Architectural Design | In Progress | 2026-01-20 08:00 | 2026-02-02 16:00 | 2026-01-20 08:00 |  | 10 | 1 | 17 | No |  |  | 136000 | 116025 | 122400 | 126978.12 | -4578.12 | 6375 | 0.96395 | 1.0549
Update 01 | 2026-01-31 17:00 | ARC-030 | Develop Technical Room Layouts | Design & Engineering | Architectural Design | In Progress | 2026-01-20 08:00 | 2026-02-02 16:00 | 2026-01-21 08:00 |  | 10 | 3 | 0 | Yes | 1 | 1 | 136000 | 116025 | 95200 | 100124.86 | -4924.86 | -20825 | 0.95081 | 0.82051
Update 01 | 2026-01-31 17:00 | ARC-040 | Develop Building Envelope Design | Design & Engineering | Architectural Design | In Progress | 2026-01-20 08:00 | 2026-02-09 16:00 | 2026-01-20 08:00 |  | 15 | 6 | 101 | No |  |  | 154000 | 86151.6393 | 92400 | 97703.83 | -5303.83 | 6248.3607 | 0.94572 | 1.0725
Update 01 | 2026-01-31 17:00 | ARC-050 | Develop Internal Partition and Door Layouts | Design & Engineering | Architectural Design | Not Started | 2026-02-05 08:00 | 2026-02-18 16:00 |  |  | 10 | 10 | 94 | No |  |  | 136000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ARC-060 | Architectural Design Review | Design & Engineering | Architectural Design | Not Started | 2026-02-19 08:00 | 2026-02-25 16:00 |  |  | 5 | 5 | 94 | No |  |  | 18000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ARC-070 | Architectural Design Approved | Design & Engineering | Architectural Design | Not Started | 2026-02-25 16:00 | 2026-02-25 16:00 |  |  | 0 | 0 | 94 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ASB-010 | Compile Civil and Architectural As-Built Drawings | Client Acceptance & Handover | As-Built Documentation | Not Started | 2026-08-25 08:00 | 2026-09-07 16:00 |  |  | 10 | 10 | 172 | No |  |  | 35000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ASB-020 | Compile Electrical As-Built Drawings | Client Acceptance & Handover | As-Built Documentation | Not Started | 2027-01-11 08:00 | 2027-01-22 16:00 |  |  | 10 | 10 | 73 | No |  |  | 35000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ASB-030 | Compile Mechanical As-Built Drawings | Client Acceptance & Handover | As-Built Documentation | Not Started | 2026-12-15 08:00 | 2026-12-28 16:00 |  |  | 10 | 10 | 92 | No |  |  | 35000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ASB-040 | Compile Controls and Fire As-Built Drawings | Client Acceptance & Handover | As-Built Documentation | Not Started | 2027-01-08 08:00 | 2027-01-21 16:00 |  |  | 10 | 10 | 74 | No |  |  | 35000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ASB-050 | Submit Final As-Built Documentation | Client Acceptance & Handover | As-Built Documentation | Not Started | 2027-01-25 08:00 | 2027-02-05 16:00 |  |  | 10 | 10 | 73 | No |  |  | 18000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | AUT-010 | Submit Final Authority Inspection Request | Client Acceptance & Handover | Authority / Regulatory Approvals | Not Started | 2027-02-22 08:00 | 2027-02-23 16:00 |  |  | 2 | 2 | 52 | No |  |  | 11000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | AUT-020 | Conduct Fire Authority Inspection | Client Acceptance & Handover | Authority / Regulatory Approvals | Not Started | 2027-02-24 08:00 | 2027-02-25 16:00 |  |  | 2 | 2 | 52 | No |  |  | 44000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | AUT-030 | Conduct Electrical Authority Inspection | Client Acceptance & Handover | Authority / Regulatory Approvals | Not Started | 2027-02-24 08:00 | 2027-02-25 16:00 |  |  | 2 | 2 | 52 | No |  |  | 44000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | AUT-040 | Resolve Authority Inspection Comments | Client Acceptance & Handover | Authority / Regulatory Approvals | Not Started | 2027-02-26 08:00 | 2027-03-01 16:00 |  |  | 2 | 2 | 52 | No |  |  | 44000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | AUT-050 | Obtain Final Authority Approvals | Client Acceptance & Handover | Authority / Regulatory Approvals | Not Started | 2027-03-02 08:00 | 2027-03-10 16:00 |  |  | 7 | 7 | 52 | No |  |  | 16000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | BMS-CX-010 | Commission BMS Infrastructure | Testing & Commissioning | BMS & DCIM Commissioning | Not Started | 2027-01-30 08:00 | 2027-02-04 16:00 |  |  | 5 | 5 | 5 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | BMS-CX-020 | Verify BMS Field Points | Testing & Commissioning | BMS & DCIM Commissioning | Not Started | 2027-02-05 08:00 | 2027-02-06 16:00 |  |  | 2 | 2 | 5 | No |  |  | 26000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | BMS-CX-030 | Commission BMS Graphics and Alarms | Testing & Commissioning | BMS & DCIM Commissioning | Not Started | 2027-02-08 08:00 | 2027-02-12 16:00 |  |  | 5 | 5 | 5 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | BMS-CX-040 | Commission DCIM Platform | Testing & Commissioning | BMS & DCIM Commissioning | Not Started | 2027-01-30 08:00 | 2027-02-04 16:00 |  |  | 5 | 5 | 10 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | BMS-CX-050 | Verify DCIM Power Monitoring | Testing & Commissioning | BMS & DCIM Commissioning | Not Started | 2027-02-16 08:00 | 2027-02-17 16:00 |  |  | 2 | 2 | 1 | No |  |  | 5000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | BMS-CX-060 | Verify DCIM Cooling Monitoring | Testing & Commissioning | BMS & DCIM Commissioning | Not Started | 2027-02-13 08:00 | 2027-02-15 16:00 |  |  | 2 | 2 | 3 | No |  |  | 5000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | BMS-CX-070 | BMS and DCIM Commissioning Complete | Testing & Commissioning | BMS & DCIM Commissioning | Not Started | 2027-02-17 16:00 | 2027-02-17 16:00 |  |  | 0 | 0 | 1 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | BMS-D-010 | Develop BMS Design Architecture | Design & Engineering | BMS, DCIM & Controls Design | In Progress | 2026-01-20 08:00 | 2026-02-02 16:00 | 2026-01-20 08:00 |  | 10 | 1 | 103 | No |  |  | 136000 | 116025 | 122400 | 128374.23 | -5974.23 | 6375 | 0.95346 | 1.0549
Update 01 | 2026-01-31 17:00 | BMS-D-020 | Develop Mechanical Controls Architecture | Design & Engineering | BMS, DCIM & Controls Design | Not Started | 2026-03-04 08:00 | 2026-03-17 16:00 |  |  | 10 | 10 | 82 | No |  |  | 79000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | BMS-D-030 | Develop Electrical Monitoring Architecture | Design & Engineering | BMS, DCIM & Controls Design | Not Started | 2026-02-26 08:00 | 2026-03-11 16:00 |  |  | 10 | 10 | 86 | No |  |  | 23000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | BMS-D-040 | Develop DCIM Architecture | Design & Engineering | BMS, DCIM & Controls Design | Not Started | 2026-02-03 08:00 | 2026-02-16 16:00 |  |  | 10 | 10 | 103 | No |  |  | 79000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | BMS-D-050 | Develop Controls Integration Matrix | Design & Engineering | BMS, DCIM & Controls Design | Not Started | 2026-03-18 08:00 | 2026-03-31 16:00 |  |  | 10 | 10 | 82 | No |  |  | 79000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | BMS-D-060 | BMS DCIM and Controls Design Review | Design & Engineering | BMS, DCIM & Controls Design | Not Started | 2026-04-01 08:00 | 2026-04-07 16:00 |  |  | 5 | 5 | 82 | No |  |  | 18000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | BMS-D-070 | BMS DCIM and Controls Design Approved | Design & Engineering | BMS, DCIM & Controls Design | Not Started | 2026-04-07 16:00 | 2026-04-07 16:00 |  |  | 0 | 0 | 82 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | BMS-P-010 | Prepare BMS DCIM and Controls Equipment Submittal | Procurement | BMS, DCIM & Controls Equipment | Not Started | 2026-04-01 08:00 | 2026-04-07 16:00 |  |  | 5 | 5 | 82 | No |  |  | 101000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | BMS-P-020 | BMS DCIM and Controls Equipment Submittal Approval | Procurement | BMS, DCIM & Controls Equipment | Not Started | 2026-04-08 08:00 | 2026-04-16 16:00 |  |  | 7 | 7 | 82 | No |  |  | 111000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | BMS-P-030 | Issue Purchase Order - BMS DCIM and Controls Equipment | Procurement | BMS, DCIM & Controls Equipment | Not Started | 2026-04-17 08:00 | 2026-04-21 16:00 |  |  | 3 | 3 | 82 | No |  |  | 144000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | BMS-P-040 | Configure and Manufacture Controls Equipment | Procurement | BMS, DCIM & Controls Equipment | Not Started | 2026-04-22 08:00 | 2026-07-14 16:00 |  |  | 60 | 60 | 82 | No |  |  | 1414000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | BMS-P-050 | Factory Testing - BMS DCIM and Controls | Procurement | BMS, DCIM & Controls Equipment | Not Started | 2026-07-15 08:00 | 2026-07-21 16:00 |  |  | 5 | 5 | 82 | No |  |  | 134000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | BMS-P-060 | Ship BMS DCIM and Controls Equipment | Procurement | BMS, DCIM & Controls Equipment | Not Started | 2026-07-22 08:00 | 2026-08-04 16:00 |  |  | 10 | 10 | 82 | No |  |  | 165000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | BMS-P-070 | Deliver BMS DCIM and Controls Equipment to Site | Procurement | BMS, DCIM & Controls Equipment | Not Started | 2026-08-05 08:00 | 2026-08-06 16:00 |  |  | 2 | 2 | 82 | No |  |  | 102000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | BMSI-010 | Prepare BMS Installation Areas | Controls, BMS & DCIM | BMS Infrastructure | Not Started | 2026-10-10 08:00 | 2026-10-15 16:00 |  |  | 5 | 5 | 44 | No |  |  | 126000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | BMSI-020 | Install BMS Control Panels | Controls, BMS & DCIM | BMS Infrastructure | Not Started | 2026-10-16 08:00 | 2026-10-21 16:00 |  |  | 5 | 5 | 65 | No |  |  | 126000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | BMSI-030 | Install BMS Network Infrastructure | Controls, BMS & DCIM | BMS Infrastructure | Not Started | 2026-10-16 08:00 | 2026-10-24 16:00 |  |  | 8 | 8 | 44 | No |  |  | 145000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | BMSI-040 | Install BMS Field Cabling | Controls, BMS & DCIM | BMS Infrastructure | Not Started | 2026-10-19 08:00 | 2026-10-29 16:00 |  |  | 10 | 10 | 65 | No |  |  | 150000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | BMSI-050 | Complete BMS Panel Power Connections | Controls, BMS & DCIM | BMS Infrastructure | Not Started | 2026-12-24 08:00 | 2026-12-25 16:00 |  |  | 2 | 2 | 16 | No |  |  | 60000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | BMSI-060 | Inspect BMS Infrastructure Installation | Controls, BMS & DCIM | BMS Infrastructure | Not Started | 2026-12-26 08:00 | 2026-12-28 16:00 |  |  | 2 | 2 | 16 | No |  |  | 96000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | BMSI-070 | BMS Infrastructure Ready for Pre-Commissioning | Controls, BMS & DCIM | BMS Infrastructure | Not Started | 2026-12-28 16:00 | 2026-12-28 16:00 |  |  | 0 | 0 | 16 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | BUS-010 | Set Out PDU and Busway Routes | Electrical Systems | PDUs & Busway Distribution | Not Started | 2026-09-03 08:00 | 2026-09-05 16:00 |  |  | 3 | 3 | 72 | No |  |  | 214000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | BUS-020 | Install Busway Support Systems | Electrical Systems | PDUs & Busway Distribution | Not Started | 2026-09-07 08:00 | 2026-09-17 16:00 |  |  | 10 | 10 | 72 | No |  |  | 307000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | BUS-030 | Install Main Busway Distribution | Electrical Systems | PDUs & Busway Distribution | Not Started | 2026-09-10 08:00 | 2026-09-26 16:00 |  |  | 15 | 15 | 72 | No |  |  | 347000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | BUS-040 | Install Power Distribution Units | Electrical Systems | PDUs & Busway Distribution | Not Started | 2026-09-19 08:00 | 2026-09-26 16:00 |  |  | 7 | 7 | 72 | No |  |  | 276000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | BUS-050 | Install Busway Tap-Off Units | Electrical Systems | PDUs & Busway Distribution | Not Started | 2026-09-28 08:00 | 2026-10-08 16:00 |  |  | 10 | 10 | 72 | No |  |  | 307000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | BUS-060 | Complete Busway and PDU Connections | Electrical Systems | PDUs & Busway Distribution | Not Started | 2027-01-01 08:00 | 2027-01-06 16:00 |  |  | 5 | 5 | 0 | Yes | 1 | 20 | 249000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | BUS-070 | Inspect PDU and Busway Installation | Electrical Systems | PDUs & Busway Distribution | Not Started | 2027-01-07 08:00 | 2027-01-08 16:00 |  |  | 2 | 2 | 13 | No |  |  | 189000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | BUS-080 | PDU and Busway Distribution Ready for Pre-Commissioning | Electrical Systems | PDUs & Busway Distribution | Not Started | 2027-01-08 16:00 | 2027-01-08 16:00 |  |  | 0 | 0 | 13 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CAF-010 | Prepare Clean Agent Protected Areas | Fire & Life Safety | Clean Agent Fire Suppression | Not Started | 2026-10-08 08:00 | 2026-10-13 16:00 |  |  | 5 | 5 | 73 | No |  |  | 51000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CAF-020 | Install Clean Agent Cylinders | Fire & Life Safety | Clean Agent Fire Suppression | Not Started | 2026-10-14 08:00 | 2026-10-19 16:00 |  |  | 5 | 5 | 76 | No |  |  | 82000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CAF-030 | Install Clean Agent Distribution Pipework | Fire & Life Safety | Clean Agent Fire Suppression | Not Started | 2026-10-14 08:00 | 2026-10-22 16:00 |  |  | 8 | 8 | 73 | No |  |  | 95000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CAF-040 | Install Clean Agent Discharge Nozzles | Fire & Life Safety | Clean Agent Fire Suppression | Not Started | 2026-10-23 08:00 | 2026-10-28 16:00 |  |  | 5 | 5 | 73 | No |  |  | 82000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CAF-050 | Install Release and Control Interfaces | Fire & Life Safety | Clean Agent Fire Suppression | Not Started | 2026-10-22 08:00 | 2026-10-27 16:00 |  |  | 5 | 5 | 74 | No |  |  | 82000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CAF-060 | Complete Room Integrity Preparations | Fire & Life Safety | Clean Agent Fire Suppression | Not Started | 2026-10-29 08:00 | 2026-10-30 16:00 |  |  | 2 | 2 | 73 | No |  |  | 39000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CAF-070 | Inspect Clean Agent Suppression Installation | Fire & Life Safety | Clean Agent Fire Suppression | Not Started | 2026-10-31 08:00 | 2026-11-02 16:00 |  |  | 2 | 2 | 73 | No |  |  | 63000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CAF-080 | Clean Agent Suppression Ready for Pre-Commissioning | Fire & Life Safety | Clean Agent Fire Suppression | Not Started | 2026-11-02 16:00 | 2026-11-02 16:00 |  |  | 0 | 0 | 73 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CFI-010 | Conduct Client Final Technical Inspection | Client Acceptance & Handover | Client Final Inspections | Not Started | 2027-06-01 08:00 | 2027-06-02 16:00 |  |  | 2 | 2 | 0 | Yes | 1 | 48 | 44000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CFI-020 | Conduct Client Operations Readiness Review | Client Acceptance & Handover | Client Final Inspections | Not Started | 2027-06-03 08:00 | 2027-06-09 16:00 |  |  | 5 | 5 | 0 | Yes | 1 | 49 | 10000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CFI-030 | Resolve Client Final Inspection Comments | Client Acceptance & Handover | Client Final Inspections | Not Started | 2027-06-10 08:00 | 2027-06-11 16:00 |  |  | 2 | 2 | 0 | Yes | 1 | 50 | 44000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CFI-040 | Client Final Inspection Accepted | Client Acceptance & Handover | Client Final Inspections | Not Started | 2027-06-14 08:00 | 2027-06-15 16:00 |  |  | 2 | 2 | 0 | Yes | 1 | 51 | 44000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CHR-010 | Prepare Chiller and Heat Rejection Equipment Areas | Mechanical & Cooling Systems | Chillers / Heat Rejection Equipment | Not Started | 2026-08-28 08:00 | 2026-08-31 16:00 |  |  | 3 | 3 | 47 | No |  |  | 99000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CHR-020 | Receive and Inspect Chillers and Heat Rejection Equipment | Mechanical & Cooling Systems | Chillers / Heat Rejection Equipment | Not Started | 2026-09-01 08:00 | 2026-09-02 16:00 |  |  | 2 | 2 | 47 | No |  |  | 105000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CHR-030 | Position Chillers on Equipment Bases | Mechanical & Cooling Systems | Chillers / Heat Rejection Equipment | Not Started | 2026-09-03 08:00 | 2026-09-08 16:00 |  |  | 5 | 5 | 47 | No |  |  | 115000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CHR-040 | Position Heat Rejection Equipment | Mechanical & Cooling Systems | Chillers / Heat Rejection Equipment | Not Started | 2026-09-03 08:00 | 2026-09-08 16:00 |  |  | 5 | 5 | 99 | No |  |  | 115000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CHR-050 | Install Chiller Mechanical Connections | Mechanical & Cooling Systems | Chillers / Heat Rejection Equipment | Not Started | 2026-09-09 08:00 | 2026-09-19 16:00 |  |  | 10 | 10 | 47 | No |  |  | 227000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CHR-060 | Install Heat Rejection Equipment Connections | Mechanical & Cooling Systems | Chillers / Heat Rejection Equipment | Not Started | 2026-09-09 08:00 | 2026-09-16 16:00 |  |  | 7 | 7 | 99 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CHR-070 | Install Electrical and Controls Connections | Mechanical & Cooling Systems | Chillers / Heat Rejection Equipment | Not Started | 2026-09-05 08:00 | 2026-09-12 16:00 |  |  | 7 | 7 | 102 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CHR-080 | Complete Chiller Installation Inspection | Mechanical & Cooling Systems | Chillers / Heat Rejection Equipment | Not Started | 2026-09-21 08:00 | 2026-09-22 16:00 |  |  | 2 | 2 | 96 | No |  |  | 140000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CHR-090 | Chillers and Heat Rejection Equipment Ready for Pre-Commissioning | Mechanical & Cooling Systems | Chillers / Heat Rejection Equipment | Not Started | 2026-09-22 16:00 | 2026-09-22 16:00 |  |  | 0 | 0 | 96 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CHW-010 | Set Out Chilled Water Pipework Routes | Mechanical & Cooling Systems | Chilled Water Distribution | Not Started | 2026-08-25 08:00 | 2026-08-27 16:00 |  |  | 3 | 3 | 44 | No |  |  | 158000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CHW-020 | Install Chilled Water Pipe Supports | Mechanical & Cooling Systems | Chilled Water Distribution | Not Started | 2026-08-28 08:00 | 2026-09-08 16:00 |  |  | 10 | 10 | 44 | No |  |  | 227000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CHW-030 | Install Main Chilled Water Pipework | Mechanical & Cooling Systems | Chilled Water Distribution | Not Started | 2026-09-01 08:00 | 2026-09-17 16:00 |  |  | 15 | 15 | 44 | No |  |  | 262000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CHW-040 | Install Chilled Water Branch Pipework | Mechanical & Cooling Systems | Chilled Water Distribution | Not Started | 2026-09-07 08:00 | 2026-09-23 16:00 |  |  | 15 | 15 | 44 | No |  |  | 257000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CHW-050 | Install Chilled Water Valves and Accessories | Mechanical & Cooling Systems | Chilled Water Distribution | Not Started | 2026-09-16 08:00 | 2026-09-23 16:00 |  |  | 7 | 7 | 44 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CHW-060 | Pressure Test Chilled Water Pipework | Mechanical & Cooling Systems | Chilled Water Distribution | Not Started | 2026-09-24 08:00 | 2026-10-01 16:00 |  |  | 7 | 7 | 44 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CHW-070 | Flush and Clean Chilled Water System | Mechanical & Cooling Systems | Chilled Water Distribution | Not Started | 2026-10-02 08:00 | 2026-10-07 16:00 |  |  | 5 | 5 | 44 | No |  |  | 115000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CHW-080 | Install Chilled Water Pipe Insulation | Mechanical & Cooling Systems | Chilled Water Distribution | Not Started | 2026-09-26 08:00 | 2026-10-07 16:00 |  |  | 10 | 10 | 95 | No |  |  | 227000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CHW-090 | Chilled Water Distribution Ready for Pre-Commissioning | Mechanical & Cooling Systems | Chilled Water Distribution | Not Started | 2026-10-07 16:00 | 2026-10-07 16:00 |  |  | 0 | 0 | 95 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CIV-010 | Develop Civil and Structural Design Criteria | Design & Engineering | Civil & Structural Design | Completed | 2026-01-13 08:00 | 2026-01-19 16:00 | 2026-01-13 08:00 | 2026-01-20 16:00 | 5 | 0 |  | No |  |  | 111000 | 111000 | 111000 | 116032.27 | -5032.27 | 0 | 0.95663 | 1
Update 01 | 2026-01-31 17:00 | CIV-020 | Develop Site Grading and Drainage Design | Design & Engineering | Civil & Structural Design | In Progress | 2026-01-20 08:00 | 2026-02-02 16:00 | 2026-01-21 08:00 |  | 10 | 2 | 89 | No |  |  | 136000 | 116025 | 108800 | 112379.23 | -3579.23 | -7225 | 0.96815 | 0.93773
Update 01 | 2026-01-31 17:00 | CIV-030 | Develop Foundation Design | Design & Engineering | Civil & Structural Design | In Progress | 2026-01-20 08:00 | 2026-02-09 16:00 | 2026-01-20 08:00 |  | 15 | 6 | 85 | No |  |  | 154000 | 86151.6393 | 92400 | 96784.25 | -4384.25 | 6248.3607 | 0.9547 | 1.0725
Update 01 | 2026-01-31 17:00 | CIV-040 | Develop Main Structural Frame Design | Design & Engineering | Civil & Structural Design | In Progress | 2026-01-20 08:00 | 2026-02-16 16:00 | 2026-01-20 08:00 |  | 20 | 11 | 12 | No |  |  | 170000 | 70746.9512 | 76500 | 78712.26 | -2212.26 | 5753.0488 | 0.97189 | 1.0813
Update 01 | 2026-01-31 17:00 | CIV-050 | Develop Equipment Foundation and Plinth Design | Design & Engineering | Civil & Structural Design | Not Started | 2026-02-25 08:00 | 2026-03-10 16:00 |  |  | 10 | 10 | 64 | No |  |  | 136000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CIV-060 | Civil and Structural Design Review | Design & Engineering | Civil & Structural Design | Not Started | 2026-03-11 08:00 | 2026-03-17 16:00 |  |  | 5 | 5 | 64 | No |  |  | 18000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CIV-070 | Civil and Structural Design Approved | Design & Engineering | Civil & Structural Design | Not Started | 2026-03-17 16:00 | 2026-03-17 16:00 |  |  | 0 | 0 | 64 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CLD-010 | Set Out External Wall and Cladding System | Building Envelope | External Walls & Cladding | Not Started | 2026-08-08 08:00 | 2026-08-11 16:00 |  |  | 3 | 3 | 48 | No |  |  | 113000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CLD-020 | Install External Wall Framing and Supports | Building Envelope | External Walls & Cladding | Not Started | 2026-08-12 08:00 | 2026-08-22 16:00 |  |  | 10 | 10 | 48 | No |  |  | 163000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CLD-030 | Install External Wall Insulation | Building Envelope | External Walls & Cladding | Not Started | 2026-08-15 08:00 | 2026-08-24 16:00 |  |  | 8 | 8 | 48 | No |  |  | 152000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CLD-040 | Install External Cladding Panels | Building Envelope | External Walls & Cladding | Not Started | 2026-08-19 08:00 | 2026-09-01 16:00 |  |  | 12 | 12 | 48 | No |  |  | 177000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CLD-050 | Install Flashings and Interface Seals | Building Envelope | External Walls & Cladding | Not Started | 2026-08-27 08:00 | 2026-09-01 16:00 |  |  | 5 | 5 | 48 | No |  |  | 132000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CLD-060 | Complete Cladding Joint Sealing | Building Envelope | External Walls & Cladding | Not Started | 2026-09-02 08:00 | 2026-09-04 16:00 |  |  | 3 | 3 | 48 | No |  |  | 113000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CLD-070 | Inspect External Walls and Cladding | Building Envelope | External Walls & Cladding | Not Started | 2026-09-05 08:00 | 2026-09-07 16:00 |  |  | 2 | 2 | 48 | No |  |  | 100000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CLD-080 | External Walls and Cladding Complete | Building Envelope | External Walls & Cladding | Not Started | 2026-09-08 08:00 | 2026-09-08 08:00 |  |  | 0 | 0 | 48 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CLG-010 | Prepare Cooling Plant Area for Installation | Mechanical & Cooling Systems | Cooling Plant | Not Started | 2026-08-25 08:00 | 2026-08-27 16:00 |  |  | 3 | 3 | 108 | No |  |  | 158000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CLG-020 | Install Cooling Plant Equipment Supports | Mechanical & Cooling Systems | Cooling Plant | Not Started | 2026-08-28 08:00 | 2026-09-02 16:00 |  |  | 5 | 5 | 108 | No |  |  | 185000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CLG-030 | Install Cooling Plant Main Headers | Mechanical & Cooling Systems | Cooling Plant | Not Started | 2026-09-03 08:00 | 2026-09-14 16:00 |  |  | 10 | 10 | 108 | No |  |  | 227000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CLG-040 | Install Cooling Plant Valves and Accessories | Mechanical & Cooling Systems | Cooling Plant | Not Started | 2026-09-15 08:00 | 2026-09-19 16:00 |  |  | 5 | 5 | 108 | No |  |  | 185000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CLG-050 | Install Cooling Plant Electrical Interfaces | Mechanical & Cooling Systems | Cooling Plant | Not Started | 2026-09-09 08:00 | 2026-09-14 16:00 |  |  | 5 | 5 | 113 | No |  |  | 185000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CLG-060 | Install Cooling Plant Controls Interfaces | Mechanical & Cooling Systems | Cooling Plant | Not Started | 2026-09-09 08:00 | 2026-09-14 16:00 |  |  | 5 | 5 | 113 | No |  |  | 185000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CLG-070 | Inspect Cooling Plant Installation | Mechanical & Cooling Systems | Cooling Plant | Not Started | 2026-09-21 08:00 | 2026-09-22 16:00 |  |  | 2 | 2 | 108 | No |  |  | 140000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CLG-080 | Cooling Plant Ready for Pre-Commissioning | Mechanical & Cooling Systems | Cooling Plant | Not Started | 2026-09-22 16:00 | 2026-09-22 16:00 |  |  | 0 | 0 | 108 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CLP-010 | Prepare Cooling Plant Equipment Technical Submittal | Procurement | Cooling Plant Equipment | Not Started | 2026-02-25 08:00 | 2026-03-05 16:00 |  |  | 7 | 7 | 44 | No |  |  | 178000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CLP-020 | Cooling Plant Equipment Technical Submittal Approval | Procurement | Cooling Plant Equipment | Not Started | 2026-03-13 08:00 | 2026-03-23 16:00 |  |  | 7 | 7 | 39 | No |  |  | 178000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CLP-030 | Issue Purchase Order - Cooling Plant Equipment | Procurement | Cooling Plant Equipment | Not Started | 2026-03-24 08:00 | 2026-03-26 16:00 |  |  | 3 | 3 | 39 | No |  |  | 230000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CLP-040 | Manufacture Cooling Plant Equipment | Procurement | Cooling Plant Equipment | Not Started | 2026-03-27 08:00 | 2026-07-30 16:00 |  |  | 90 | 90 | 39 | No |  |  | 3833000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CLP-050 | Factory Acceptance Test - Cooling Plant Equipment | Procurement | Cooling Plant Equipment | Not Started | 2026-07-31 08:00 | 2026-08-04 16:00 |  |  | 3 | 3 | 39 | No |  |  | 299000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CLP-060 | Ship Cooling Plant Equipment | Procurement | Cooling Plant Equipment | Not Started | 2026-08-05 08:00 | 2026-08-25 16:00 |  |  | 15 | 15 | 39 | No |  |  | 299000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CLP-070 | Deliver Cooling Plant Equipment to Site | Procurement | Cooling Plant Equipment | Not Started | 2026-08-26 08:00 | 2026-08-27 16:00 |  |  | 2 | 2 | 39 | No |  |  | 163000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CNW-010 | Install Controls Network Switches | Controls, BMS & DCIM | Controls Network | Not Started | 2026-10-26 08:00 | 2026-10-30 16:00 |  |  | 5 | 5 | 44 | No |  |  | 126000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CNW-020 | Install Controls Network Cabling | Controls, BMS & DCIM | Controls Network | Not Started | 2026-10-19 08:00 | 2026-10-27 16:00 |  |  | 8 | 8 | 47 | No |  |  | 145000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CNW-030 | Configure Controls Network | Controls, BMS & DCIM | Controls Network | Not Started | 2026-10-31 08:00 | 2026-11-04 16:00 |  |  | 4 | 4 | 44 | No |  |  | 74000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CNW-040 | Configure Network Segmentation | Controls, BMS & DCIM | Controls Network | Not Started | 2026-11-05 08:00 | 2026-11-07 16:00 |  |  | 3 | 3 | 44 | No |  |  | 68000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CNW-050 | Perform Controls Network Connectivity Testing | Controls, BMS & DCIM | Controls Network | Not Started | 2026-11-09 08:00 | 2026-11-11 16:00 |  |  | 3 | 3 | 44 | No |  |  | 81000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CNW-060 | Controls Network Ready | Controls, BMS & DCIM | Controls Network | Not Started | 2026-11-11 16:00 | 2026-11-11 16:00 |  |  | 0 | 0 | 44 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | COM-010 | Establish Contract Administration Procedures | Project Management & Controls | Contract & Commercial Management | Completed | 2026-01-06 08:00 | 2026-01-12 16:00 | 2026-01-06 08:00 | 2026-01-12 16:00 | 5 | 0 |  | No |  |  | 293000 | 293000 | 293000 | 298828.35 | -5828.35 | 0 | 0.9805 | 1
Update 01 | 2026-01-31 17:00 | COM-020 | Establish Change and Variation Control Procedure | Project Management & Controls | Contract & Commercial Management | Completed | 2026-01-13 08:00 | 2026-01-19 16:00 | 2026-01-13 08:00 | 2026-01-19 16:00 | 5 | 0 |  | No |  |  | 293000 | 293000 | 293000 | 298584.15 | -5584.15 | 0 | 0.9813 | 1
Update 01 | 2026-01-31 17:00 | COM-030 | Establish Payment and Cost Control Procedure | Project Management & Controls | Contract & Commercial Management | Completed | 2026-01-13 08:00 | 2026-01-19 16:00 | 2026-01-13 08:00 | 2026-01-19 16:00 | 5 | 0 |  | No |  |  | 293000 | 293000 | 293000 | 291956.87 | 1043.13 | 0 | 1.0036 | 1
Update 01 | 2026-01-31 17:00 | COM-040 | Establish Commercial Reporting Procedure | Project Management & Controls | Contract & Commercial Management | Completed | 2026-01-13 08:00 | 2026-01-19 16:00 | 2026-01-13 08:00 | 2026-01-19 16:00 | 5 | 0 |  | No |  |  | 130000 | 130000 | 130000 | 132738.75 | -2738.75 | 0 | 0.97937 | 1
Update 01 | 2026-01-31 17:00 | CPS-010 | Construct Cooling Plant Foundations | Civil & Structural Works | Cooling Plant Structures | Not Started | 2026-07-25 08:00 | 2026-08-05 16:00 |  |  | 10 | 10 | 44 | No |  |  | 250000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CPS-020 | Construct Chiller Equipment Bases | Civil & Structural Works | Cooling Plant Structures | Not Started | 2026-08-06 08:00 | 2026-08-11 16:00 |  |  | 5 | 5 | 55 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CPS-030 | Construct Pump Equipment Bases | Civil & Structural Works | Cooling Plant Structures | Not Started | 2026-08-06 08:00 | 2026-08-11 16:00 |  |  | 5 | 5 | 55 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CPS-040 | Construct Cooling Plant Structural Supports | Civil & Structural Works | Cooling Plant Structures | Not Started | 2026-08-06 08:00 | 2026-08-14 16:00 |  |  | 8 | 8 | 44 | No |  |  | 234000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CPS-050 | Install Pipework Support Structures | Civil & Structural Works | Cooling Plant Structures | Not Started | 2026-08-15 08:00 | 2026-08-24 16:00 |  |  | 8 | 8 | 44 | No |  |  | 234000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CPS-060 | Cooling Plant Structures Complete | Civil & Structural Works | Cooling Plant Structures | Not Started | 2026-08-25 08:00 | 2026-08-25 08:00 |  |  | 0 | 0 | 44 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CRAC-010 | Prepare CRAH/CRAC Installation Areas | Mechanical & Cooling Systems | CRAH / CRAC Systems | Not Started | 2026-09-03 08:00 | 2026-09-05 16:00 |  |  | 3 | 3 | 59 | No |  |  | 158000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CRAC-020 | Receive and Inspect CRAH/CRAC Units | Mechanical & Cooling Systems | CRAH / CRAC Systems | Not Started | 2026-09-07 08:00 | 2026-09-08 16:00 |  |  | 2 | 2 | 59 | No |  |  | 105000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CRAC-030 | Position and Install CRAH/CRAC Units | Mechanical & Cooling Systems | CRAH / CRAC Systems | Not Started | 2026-10-10 08:00 | 2026-10-21 16:00 |  |  | 10 | 10 | 32 | No |  |  | 227000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CRAC-040 | Install CRAH/CRAC Chilled Water Connections | Mechanical & Cooling Systems | CRAH / CRAC Systems | Not Started | 2026-10-22 08:00 | 2026-11-02 16:00 |  |  | 10 | 10 | 32 | No |  |  | 227000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CRAC-050 | Install CRAH/CRAC Condensate Connections | Mechanical & Cooling Systems | CRAH / CRAC Systems | Not Started | 2026-10-22 08:00 | 2026-10-29 16:00 |  |  | 7 | 7 | 62 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CRAC-060 | Install CRAH/CRAC Electrical Connections | Mechanical & Cooling Systems | CRAH / CRAC Systems | Not Started | 2026-10-22 08:00 | 2026-10-29 16:00 |  |  | 7 | 7 | 62 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CRAC-070 | Install CRAH/CRAC Controls Connections | Mechanical & Cooling Systems | CRAH / CRAC Systems | Not Started | 2026-10-22 08:00 | 2026-10-29 16:00 |  |  | 7 | 7 | 62 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CRAC-080 | Complete CRAH/CRAC Installation Inspection | Mechanical & Cooling Systems | CRAH / CRAC Systems | Not Started | 2026-11-03 08:00 | 2026-11-04 16:00 |  |  | 2 | 2 | 59 | No |  |  | 140000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CRAC-090 | CRAH/CRAC Systems Ready for Pre-Commissioning | Mechanical & Cooling Systems | CRAH / CRAC Systems | Not Started | 2026-11-04 16:00 | 2026-11-04 16:00 |  |  | 0 | 0 | 59 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CRAH-010 | Prepare CRAH/CRAC Technical Submittal | Procurement | CRAH/CRAC Units | Not Started | 2026-02-18 08:00 | 2026-02-26 16:00 |  |  | 7 | 7 | 63 | No |  |  | 148000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CRAH-020 | CRAH/CRAC Technical Submittal Approval | Procurement | CRAH/CRAC Units | Not Started | 2026-03-13 08:00 | 2026-03-23 16:00 |  |  | 7 | 7 | 53 | No |  |  | 148000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CRAH-030 | Issue Purchase Order - CRAH/CRAC Units | Procurement | CRAH/CRAC Units | Not Started | 2026-03-24 08:00 | 2026-03-26 16:00 |  |  | 3 | 3 | 53 | No |  |  | 192000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CRAH-040 | Manufacture CRAH/CRAC Units | Procurement | CRAH/CRAC Units | Not Started | 2026-03-27 08:00 | 2026-07-30 16:00 |  |  | 90 | 90 | 53 | No |  |  | 3194000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CRAH-050 | Factory Acceptance Test - CRAH/CRAC Units | Procurement | CRAH/CRAC Units | Not Started | 2026-07-31 08:00 | 2026-08-04 16:00 |  |  | 3 | 3 | 53 | No |  |  | 249000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CRAH-060 | Ship CRAH/CRAC Units | Procurement | CRAH/CRAC Units | Not Started | 2026-08-05 08:00 | 2026-08-25 16:00 |  |  | 15 | 15 | 53 | No |  |  | 249000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CRAH-070 | Deliver CRAH/CRAC Units to Site | Procurement | CRAH/CRAC Units | Not Started | 2026-08-26 08:00 | 2026-08-27 16:00 |  |  | 2 | 2 | 53 | No |  |  | 136000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CSI-010 | Integrate BMS with Electrical Systems | Controls, BMS & DCIM | System Integration | Not Started | 2027-01-09 08:00 | 2027-01-13 16:00 |  |  | 4 | 4 | 33 | No |  |  | 74000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CSI-020 | Integrate BMS with Mechanical Systems | Controls, BMS & DCIM | System Integration | Not Started | 2026-12-29 08:00 | 2027-01-01 16:00 |  |  | 4 | 4 | 43 | No |  |  | 74000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CSI-030 | Integrate BMS with Fire Alarm System | Controls, BMS & DCIM | System Integration | Not Started | 2027-01-08 08:00 | 2027-01-11 16:00 |  |  | 3 | 3 | 35 | No |  |  | 68000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CSI-040 | Integrate BMS with UPS and Generator Systems | Controls, BMS & DCIM | System Integration | Not Started | 2027-01-09 08:00 | 2027-01-13 16:00 |  |  | 4 | 4 | 33 | No |  |  | 74000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CSI-050 | Integrate DCIM with Power Monitoring | Controls, BMS & DCIM | System Integration | Not Started | 2027-01-15 08:00 | 2027-01-19 16:00 |  |  | 4 | 4 | 28 | No |  |  | 15000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CSI-060 | Integrate DCIM with Cooling Monitoring | Controls, BMS & DCIM | System Integration | Not Started | 2027-01-15 08:00 | 2027-01-19 16:00 |  |  | 4 | 4 | 28 | No |  |  | 15000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CSI-070 | Verify System Integration Interfaces | Controls, BMS & DCIM | System Integration | Not Started | 2027-01-20 08:00 | 2027-01-21 16:00 |  |  | 2 | 2 | 28 | No |  |  | 60000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CSI-080 | Controls Integration Ready for IST | Controls, BMS & DCIM | System Integration | Not Started | 2027-01-21 16:00 | 2027-01-21 16:00 |  |  | 0 | 0 | 28 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CXC-010 | Compile Commissioning Defects List | Testing & Commissioning | Commissioning Defects & Closeout | Not Started | 2027-03-27 08:00 | 2027-04-07 16:00 |  |  | 10 | 10 | 0 | Yes | 1 | 40 | 50000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CXC-020 | Rectify Electrical Commissioning Defects | Testing & Commissioning | Commissioning Defects & Closeout | Not Started | 2027-04-08 08:00 | 2027-04-13 16:00 |  |  | 5 | 5 | 2 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CXC-030 | Rectify Mechanical Commissioning Defects | Testing & Commissioning | Commissioning Defects & Closeout | Not Started | 2027-04-08 08:00 | 2027-04-13 16:00 |  |  | 5 | 5 | 2 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CXC-040 | Rectify Controls and BMS Defects | Testing & Commissioning | Commissioning Defects & Closeout | Not Started | 2027-04-08 08:00 | 2027-04-15 16:00 |  |  | 7 | 7 | 0 | Yes | 1 | 41 | 38000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CXC-050 | Rectify Fire System Defects | Testing & Commissioning | Commissioning Defects & Closeout | Not Started | 2027-04-08 08:00 | 2027-04-15 16:00 |  |  | 7 | 7 | 0 | Yes | 3 | 1 | 38000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CXC-060 | Close Commissioning Punch List | Testing & Commissioning | Commissioning Defects & Closeout | Not Started | 2027-04-16 08:00 | 2027-04-27 16:00 |  |  | 10 | 10 | 0 | Yes | 1 | 42 | 50000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CXC-070 | Commissioning Complete | Testing & Commissioning | Commissioning Defects & Closeout | Not Started | 2027-04-27 16:00 | 2027-04-27 16:00 |  |  | 0 | 0 | 0 | Yes | 1 | 43 | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | CXP-010 | Develop Commissioning Management Plan | Testing & Commissioning | Commissioning Management & Planning | Completed | 2026-01-06 08:00 | 2026-01-10 16:00 | 2026-01-06 08:00 | 2026-01-10 16:00 | 5 | 0 |  | No |  |  | 41000 | 41000 | 41000 | 40874.92 | 125.08 | 0 | 1.0031 | 1
Update 01 | 2026-01-31 17:00 | CXP-020 | Develop Commissioning Schedule | Testing & Commissioning | Commissioning Management & Planning | Completed | 2026-01-12 08:00 | 2026-01-16 16:00 | 2026-01-12 08:00 | 2026-01-16 16:00 | 5 | 0 |  | No |  |  | 41000 | 41000 | 41000 | 41486.64 | -486.64 | 0 | 0.98827 | 1
Update 01 | 2026-01-31 17:00 | CXP-030 | Develop Commissioning Procedures | Testing & Commissioning | Commissioning Management & Planning | Completed | 2026-01-12 08:00 | 2026-01-16 16:00 | 2026-01-12 08:00 | 2026-01-16 16:00 | 5 | 0 |  | No |  |  | 41000 | 41000 | 41000 | 40969.27 | 30.73 | 0 | 1.0008 | 1
Update 01 | 2026-01-31 17:00 | CXP-040 | Develop Systems Completion Matrix | Testing & Commissioning | Commissioning Management & Planning | Completed | 2026-01-12 08:00 | 2026-01-16 16:00 | 2026-01-12 08:00 | 2026-01-16 16:00 | 5 | 0 |  | No |  |  | 34000 | 34000 | 34000 | 34489.4 | -489.4 | 0 | 0.98581 | 1
Update 01 | 2026-01-31 17:00 | CXP-050 | Establish Commissioning Documentation Register | Testing & Commissioning | Commissioning Management & Planning | Completed | 2026-01-12 08:00 | 2026-01-22 16:00 | 2026-01-12 08:00 | 2026-01-22 16:00 | 10 | 0 |  | No |  |  | 8000 | 8000 | 8000 | 8113.43 | -113.43 | 0 | 0.98602 | 1
Update 01 | 2026-01-31 17:00 | CXP-060 | Commissioning Plan Approved | Testing & Commissioning | Commissioning Management & Planning | Completed | 2026-01-22 16:00 | 2026-01-22 16:00 | 2026-01-22 16:00 | 2026-01-22 16:00 | 0 | 0 |  | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | DCIM-010 | Install DCIM Server Infrastructure | Controls, BMS & DCIM | DCIM Platform | Not Started | 2026-11-12 08:00 | 2026-11-17 16:00 |  |  | 5 | 5 | 44 | No |  |  | 126000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | DCIM-020 | Configure DCIM Platform | Controls, BMS & DCIM | DCIM Platform | Not Started | 2026-11-18 08:00 | 2026-11-26 16:00 |  |  | 8 | 8 | 44 | No |  |  | 91000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | DCIM-030 | Configure Data Hall Asset Database | Controls, BMS & DCIM | DCIM Platform | Not Started | 2026-11-27 08:00 | 2026-12-05 16:00 |  |  | 8 | 8 | 44 | No |  |  | 91000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | DCIM-040 | Configure Power Monitoring Integration | Controls, BMS & DCIM | DCIM Platform | Not Started | 2027-01-09 08:00 | 2027-01-14 16:00 |  |  | 5 | 5 | 10 | No |  |  | 16000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | DCIM-050 | Configure Cooling Monitoring Integration | Controls, BMS & DCIM | DCIM Platform | Not Started | 2026-12-15 08:00 | 2026-12-19 16:00 |  |  | 5 | 5 | 32 | No |  |  | 16000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | DCIM-060 | Configure Alarm and Event Management | Controls, BMS & DCIM | DCIM Platform | Not Started | 2026-11-27 08:00 | 2026-12-02 16:00 |  |  | 5 | 5 | 47 | No |  |  | 79000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | DCIM-070 | DCIM Platform Ready for Functional Testing | Controls, BMS & DCIM | DCIM Platform | Not Started | 2027-01-14 16:00 | 2027-01-14 16:00 |  |  | 0 | 0 | 10 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | DFC-010 | Compile Outstanding Defects Register | Client Acceptance & Handover | Final Documentation & Turnover | Not Started | 2027-06-16 08:00 | 2027-06-29 16:00 |  |  | 10 | 10 | 0 | Yes | 1 | 52 | 12000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | DFC-020 | Rectify Outstanding Construction Defects | Client Acceptance & Handover | Final Documentation & Turnover | Not Started | 2027-06-30 08:00 | 2027-07-08 16:00 |  |  | 7 | 7 | 0 | Yes | 1 | 53 | 80000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | DFC-030 | Rectify Outstanding Systems Defects | Client Acceptance & Handover | Final Documentation & Turnover | Not Started | 2027-06-30 08:00 | 2027-07-08 16:00 |  |  | 7 | 7 | 0 | Yes | 2 | 1 | 32000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | DFC-040 | Verify Outstanding Defects Closure | Client Acceptance & Handover | Final Documentation & Turnover | Not Started | 2027-07-09 08:00 | 2027-07-12 16:00 |  |  | 2 | 2 | 0 | Yes | 1 | 54 | 22000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | DHC-010 | Set Out Data Hall Cooling Distribution | Mechanical & Cooling Systems | Data Hall Cooling Distribution | Not Started | 2026-09-03 08:00 | 2026-09-05 16:00 |  |  | 3 | 3 | 70 | No |  |  | 99000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | DHC-020 | Install Data Hall Cooling Pipe Supports | Mechanical & Cooling Systems | Data Hall Cooling Distribution | Not Started | 2026-09-07 08:00 | 2026-09-14 16:00 |  |  | 7 | 7 | 70 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | DHC-030 | Install Data Hall Cooling Distribution Pipework | Mechanical & Cooling Systems | Data Hall Cooling Distribution | Not Started | 2026-09-10 08:00 | 2026-09-26 16:00 |  |  | 15 | 15 | 70 | No |  |  | 257000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | DHC-040 | Install Data Hall Cooling Valves and Accessories | Mechanical & Cooling Systems | Data Hall Cooling Distribution | Not Started | 2026-09-19 08:00 | 2026-09-26 16:00 |  |  | 7 | 7 | 70 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | DHC-050 | Connect Cooling Distribution to CRAH/CRAC Systems | Mechanical & Cooling Systems | Data Hall Cooling Distribution | Not Started | 2026-10-22 08:00 | 2026-11-02 16:00 |  |  | 10 | 10 | 49 | No |  |  | 142000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | DHC-060 | Pressure Test Data Hall Cooling Distribution | Mechanical & Cooling Systems | Data Hall Cooling Distribution | Not Started | 2026-11-03 08:00 | 2026-11-07 16:00 |  |  | 5 | 5 | 49 | No |  |  | 138000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | DHC-070 | Flush Data Hall Cooling Distribution | Mechanical & Cooling Systems | Data Hall Cooling Distribution | Not Started | 2026-11-09 08:00 | 2026-11-13 16:00 |  |  | 5 | 5 | 51 | No |  |  | 115000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | DHC-080 | Insulate Data Hall Cooling Pipework | Mechanical & Cooling Systems | Data Hall Cooling Distribution | Not Started | 2026-11-05 08:00 | 2026-11-16 16:00 |  |  | 10 | 10 | 49 | No |  |  | 227000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | DHC-090 | Data Hall Cooling Distribution Ready for Pre-Commissioning | Mechanical & Cooling Systems | Data Hall Cooling Distribution | Not Started | 2026-11-16 16:00 | 2026-11-16 16:00 |  |  | 0 | 0 | 49 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | DHP-010 | Install Data Hall Cable Containment | Electrical Systems | Data Hall Power Distribution | Not Started | 2026-09-03 08:00 | 2026-09-14 16:00 |  |  | 10 | 10 | 90 | No |  |  | 307000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | DHP-020 | Install Data Hall Power Distribution Cables | Electrical Systems | Data Hall Power Distribution | Not Started | 2026-09-07 08:00 | 2026-09-23 16:00 |  |  | 15 | 15 | 90 | No |  |  | 347000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | DHP-030 | Install Rack Power Distribution Connections | Electrical Systems | Data Hall Power Distribution | Not Started | 2026-09-28 08:00 | 2026-10-08 16:00 |  |  | 10 | 10 | 77 | No |  |  | 307000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | DHP-040 | Install Data Hall Power Monitoring Devices | Electrical Systems | Data Hall Power Distribution | Not Started | 2026-09-15 08:00 | 2026-09-22 16:00 |  |  | 7 | 7 | 101 | No |  |  | 34000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | DHP-050 | Terminate Data Hall Power Circuits | Electrical Systems | Data Hall Power Distribution | Not Started | 2027-01-07 08:00 | 2027-01-18 16:00 |  |  | 10 | 10 | 0 | Yes | 1 | 21 | 307000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | DHP-060 | Test Data Hall Distribution Circuits | Electrical Systems | Data Hall Power Distribution | Not Started | 2027-01-19 08:00 | 2027-01-23 16:00 |  |  | 5 | 5 | 0 | Yes | 1 | 22 | 187000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | DHP-070 | Data Hall Power Distribution Ready for Pre-Commissioning | Electrical Systems | Data Hall Power Distribution | Not Started | 2027-01-23 16:00 | 2027-01-23 16:00 |  |  | 0 | 0 | 0 | Yes | 1 | 23 | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | DHS-010 | Construct Data Hall Structural Frame | Civil & Structural Works | Data Hall Structure | Not Started | 2026-08-08 08:00 | 2026-08-25 16:00 |  |  | 15 | 15 | 59 | No |  |  | 295000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | DHS-020 | Install Data Hall Floor Structure | Civil & Structural Works | Data Hall Structure | Not Started | 2026-08-14 08:00 | 2026-08-22 16:00 |  |  | 8 | 8 | 61 | No |  |  | 234000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | DHS-030 | Install Data Hall Roof Support Structure | Civil & Structural Works | Data Hall Structure | Not Started | 2026-08-17 08:00 | 2026-08-25 16:00 |  |  | 8 | 8 | 59 | No |  |  | 234000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | DHS-040 | Install Data Hall Equipment Support Steel | Civil & Structural Works | Data Hall Structure | Not Started | 2026-08-17 08:00 | 2026-08-21 16:00 |  |  | 5 | 5 | 62 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | DHS-050 | Complete Data Hall Structural Connections | Civil & Structural Works | Data Hall Structure | Not Started | 2026-08-26 08:00 | 2026-08-29 16:00 |  |  | 4 | 4 | 59 | No |  |  | 119000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | DHS-060 | Inspect Data Hall Structure | Civil & Structural Works | Data Hall Structure | Not Started | 2026-08-31 08:00 | 2026-09-02 16:00 |  |  | 3 | 3 | 59 | No |  |  | 131000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | DHS-070 | Data Hall Structure Complete | Civil & Structural Works | Data Hall Structure | Not Started | 2026-09-03 08:00 | 2026-09-03 08:00 |  |  | 0 | 0 | 59 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | DM-010 | Establish Design Management Plan | Design & Engineering | Design Management & Coordination | Completed | 2026-01-06 08:00 | 2026-01-12 16:00 | 2026-01-06 08:00 | 2026-01-12 16:00 | 5 | 0 |  | No |  |  | 111000 | 111000 | 111000 | 116820.07 | -5820.07 | 0 | 0.95018 | 1
Update 01 | 2026-01-31 17:00 | DM-020 | Establish Design Deliverables Register | Design & Engineering | Design Management & Coordination | Completed | 2026-01-08 08:00 | 2026-01-12 16:00 | 2026-01-08 08:00 | 2026-01-12 16:00 | 3 | 0 |  | No |  |  | 16000 | 16000 | 16000 | 16867.05 | -867.05 | 0 | 0.9486 | 1
Update 01 | 2026-01-31 17:00 | DM-030 | Establish Design Responsibility Matrix | Design & Engineering | Design Management & Coordination | Completed | 2026-01-08 08:00 | 2026-01-12 16:00 | 2026-01-08 08:00 | 2026-01-12 16:00 | 3 | 0 |  | No |  |  | 95000 | 95000 | 95000 | 98600.41 | -3600.41 | 0 | 0.96348 | 1
Update 01 | 2026-01-31 17:00 | DM-040 | Develop Design Coordination Schedule | Design & Engineering | Design Management & Coordination | Completed | 2026-01-13 08:00 | 2026-01-19 16:00 | 2026-01-13 08:00 | 2026-01-19 16:00 | 5 | 0 |  | No |  |  | 18000 | 18000 | 18000 | 18498.6 | -498.6 | 0 | 0.97305 | 1
Update 01 | 2026-01-31 17:00 | DM-050 | Conduct Multidiscipline Design Coordination | Design & Engineering | Design Management & Coordination | In Progress | 2026-01-20 08:00 | 2026-03-16 16:00 | 2026-01-20 08:00 |  | 40 | 31 | 175 | No |  |  | 34000 | 6989.4578 | 7650 | 7864.93 | -214.93 | 660.5422 | 0.97267 | 1.0945
Update 01 | 2026-01-31 17:00 | DM-060 | Design Coordination Complete | Design & Engineering | Design Management & Coordination | Not Started | 2026-04-16 16:00 | 2026-04-16 16:00 |  |  | 0 | 0 | 152 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | DPO-010 | Verify Data Hall Electrical Installation Readiness | Utility Connection & Energization | Data Hall Power-On | Not Started | 2027-01-25 08:00 | 2027-01-26 16:00 |  |  | 2 | 2 | 0 | Yes | 1 | 24 | 123000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | DPO-020 | Verify UPS and PDU Availability | Utility Connection & Energization | Data Hall Power-On | Not Started | 2027-01-25 08:00 | 2027-01-26 16:00 |  |  | 2 | 2 | 0 | Yes | 10 | 21 | 77000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | DPO-030 | Verify Data Hall Earthing and Bonding | Utility Connection & Energization | Data Hall Power-On | Not Started | 2026-12-30 08:00 | 2026-12-31 16:00 |  |  | 2 | 2 | 22 | No |  |  | 77000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | DPO-040 | Energize Data Hall Busway Distribution | Utility Connection & Energization | Data Hall Power-On | Not Started | 2027-01-27 08:00 | 2027-01-28 16:00 |  |  | 2 | 2 | 0 | Yes | 1 | 25 | 123000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | DPO-050 | Energize Data Hall Power Distribution | Utility Connection & Energization | Data Hall Power-On | Not Started | 2027-01-29 08:00 | 2027-02-01 16:00 |  |  | 3 | 3 | 0 | Yes | 1 | 26 | 104000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | DPO-060 | Verify Data Hall Power Availability | Utility Connection & Energization | Data Hall Power-On | Not Started | 2027-02-02 08:00 | 2027-02-03 16:00 |  |  | 2 | 2 | 0 | Yes | 1 | 27 | 77000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | DPO-070 | Data Hall Power-On Complete | Utility Connection & Energization | Data Hall Power-On | Not Started | 2027-02-03 16:00 | 2027-02-03 16:00 |  |  | 0 | 0 | 0 | Yes | 1 | 28 | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | DRN-010 | Set Out External Drainage Network | Enabling & Site Works | External Drainage | Not Started | 2026-04-13 08:00 | 2026-04-15 16:00 |  |  | 3 | 3 | 277 | No |  |  | 75000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | DRN-020 | Excavate Drainage Trenches | Enabling & Site Works | External Drainage | Not Started | 2026-04-16 08:00 | 2026-04-24 16:00 |  |  | 8 | 8 | 277 | No |  |  | 100000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | DRN-030 | Install Stormwater Drainage Pipework | Enabling & Site Works | External Drainage | Not Started | 2026-04-25 08:00 | 2026-05-06 16:00 |  |  | 10 | 10 | 277 | No |  |  | 143000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | DRN-040 | Install Drainage Manholes and Catch Basins | Enabling & Site Works | External Drainage | Not Started | 2026-04-18 08:00 | 2026-04-27 16:00 |  |  | 8 | 8 | 285 | No |  |  | 133000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | DRN-050 | Construct Stormwater Management Facilities | Enabling & Site Works | External Drainage | Not Started | 2026-04-18 08:00 | 2026-04-29 16:00 |  |  | 10 | 10 | 283 | No |  |  | 143000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | DRN-060 | Test and Inspect External Drainage | Enabling & Site Works | External Drainage | Not Started | 2026-05-07 08:00 | 2026-05-09 16:00 |  |  | 3 | 3 | 277 | No |  |  | 75000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | DRN-070 | Backfill Drainage Trenches | Enabling & Site Works | External Drainage | Not Started | 2026-05-11 08:00 | 2026-05-15 16:00 |  |  | 5 | 5 | 277 | No |  |  | 87000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | DRN-080 | External Drainage Complete | Enabling & Site Works | External Drainage | Not Started | 2026-05-16 08:00 | 2026-05-16 08:00 |  |  | 0 | 0 | 277 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | EDL-010 | Prepare External Door and Louver Openings | Building Envelope | External Doors & Louvers | Not Started | 2026-08-15 08:00 | 2026-08-18 16:00 |  |  | 3 | 3 | 49 | No |  |  | 71000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | EDL-020 | Install External Door Frames | Building Envelope | External Doors & Louvers | Not Started | 2026-08-19 08:00 | 2026-08-24 16:00 |  |  | 5 | 5 | 49 | No |  |  | 132000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | EDL-030 | Install External Doors | Building Envelope | External Doors & Louvers | Not Started | 2026-08-21 08:00 | 2026-08-26 16:00 |  |  | 5 | 5 | 49 | No |  |  | 132000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | EDL-040 | Install External Louvers | Building Envelope | External Doors & Louvers | Not Started | 2026-08-21 08:00 | 2026-08-26 16:00 |  |  | 5 | 5 | 53 | No |  |  | 132000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | EDL-050 | Install Door Hardware and Security Interfaces | Building Envelope | External Doors & Louvers | Not Started | 2026-08-27 08:00 | 2026-08-31 16:00 |  |  | 4 | 4 | 49 | No |  |  | 124000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | EDL-060 | Seal Door and Louver Interfaces | Building Envelope | External Doors & Louvers | Not Started | 2026-09-01 08:00 | 2026-09-03 16:00 |  |  | 3 | 3 | 49 | No |  |  | 71000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | EDL-070 | Inspect External Doors and Louvers | Building Envelope | External Doors & Louvers | Not Started | 2026-09-04 08:00 | 2026-09-05 16:00 |  |  | 2 | 2 | 49 | No |  |  | 75000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | EDL-080 | External Doors and Louvers Complete | Building Envelope | External Doors & Louvers | Not Started | 2026-09-07 08:00 | 2026-09-07 08:00 |  |  | 0 | 0 | 49 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ELC-CX-010 | Commission MV Switchgear | Testing & Commissioning | Electrical Systems Commissioning | Not Started | 2027-02-04 08:00 | 2027-02-09 16:00 |  |  | 5 | 5 | 5 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ELC-CX-020 | Commission Transformers | Testing & Commissioning | Electrical Systems Commissioning | Not Started | 2027-01-30 08:00 | 2027-02-04 16:00 |  |  | 5 | 5 | 9 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ELC-CX-030 | Commission LV Switchgear | Testing & Commissioning | Electrical Systems Commissioning | Not Started | 2027-01-30 08:00 | 2027-02-04 16:00 |  |  | 5 | 5 | 9 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ELC-CX-040 | Commission UPS Systems | Testing & Commissioning | Electrical Systems Commissioning | Not Started | 2027-01-30 08:00 | 2027-02-04 16:00 |  |  | 5 | 5 | 9 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ELC-CX-050 | Commission Battery Systems | Testing & Commissioning | Electrical Systems Commissioning | Not Started | 2027-01-30 08:00 | 2027-02-04 16:00 |  |  | 5 | 5 | 9 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ELC-CX-060 | Commission Standby Generators | Testing & Commissioning | Electrical Systems Commissioning | Not Started | 2027-01-30 08:00 | 2027-02-04 16:00 |  |  | 5 | 5 | 9 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ELC-CX-070 | Commission PDU and Busway Distribution | Testing & Commissioning | Electrical Systems Commissioning | Not Started | 2027-02-04 08:00 | 2027-02-15 16:00 |  |  | 10 | 10 | 0 | Yes | 8 | 1 | 62000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ELC-CX-080 | Electrical Systems Functional Testing Complete | Testing & Commissioning | Electrical Systems Commissioning | Not Started | 2027-02-15 16:00 | 2027-02-15 16:00 |  |  | 0 | 0 | 0 | Yes | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ELE-D-010 | Develop Electrical Design Criteria | Design & Engineering | Electrical Design | Completed | 2026-01-13 08:00 | 2026-01-19 16:00 | 2026-01-13 08:00 | 2026-01-22 16:00 | 5 | 0 |  | No |  |  | 111000 | 111000 | 111000 | 117168.1 | -6168.1 | 0 | 0.94736 | 1
Update 01 | 2026-01-31 17:00 | ELE-D-020 | Develop Electrical Load Schedule | Design & Engineering | Electrical Design | In Progress | 2026-01-20 08:00 | 2026-02-02 16:00 | 2026-01-21 08:00 |  | 10 | 3 | 0 | Yes |  |  | 79000 | 67396.875 | 55300 | 57768.81 | -2468.81 | -12096.875 | 0.95726 | 0.82051
Update 01 | 2026-01-31 17:00 | ELE-D-030 | Develop MV Distribution Design | Design & Engineering | Electrical Design | Not Started | 2026-02-12 08:00 | 2026-03-04 16:00 |  |  | 15 | 15 | 10 | No |  |  | 154000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ELE-D-040 | Develop Transformer Design and Sizing | Design & Engineering | Electrical Design | Not Started | 2026-02-05 08:00 | 2026-02-18 16:00 |  |  | 10 | 10 | 20 | No |  |  | 136000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ELE-D-050 | Develop Generator System Design | Design & Engineering | Electrical Design | Not Started | 2026-02-05 08:00 | 2026-02-18 16:00 |  |  | 10 | 10 | 20 | No |  |  | 136000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ELE-D-060 | Develop LV Distribution Design | Design & Engineering | Electrical Design | Not Started | 2026-02-05 08:00 | 2026-02-25 16:00 |  |  | 15 | 15 | 0 | Yes | 1 | 2 | 154000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ELE-D-070 | Develop UPS and Battery System Design | Design & Engineering | Electrical Design | Not Started | 2026-02-05 08:00 | 2026-02-25 16:00 |  |  | 15 | 15 | 0 | Yes |  |  | 154000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ELE-D-080 | Develop Busway and Data Hall Power Distribution Design | Design & Engineering | Electrical Design | Not Started | 2026-02-26 08:00 | 2026-03-18 16:00 |  |  | 15 | 15 | 0 | Yes | 1 | 3 | 154000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ELE-D-090 | Develop Earthing and Lightning Protection Design | Design & Engineering | Electrical Design | Not Started | 2026-02-17 08:00 | 2026-03-02 16:00 |  |  | 10 | 10 | 12 | No |  |  | 136000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ELE-D-100 | Electrical Design Review | Design & Engineering | Electrical Design | Not Started | 2026-03-19 08:00 | 2026-03-27 16:00 |  |  | 7 | 7 | 0 | Yes | 1 | 4 | 20000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ELE-D-110 | Electrical Design Approved | Design & Engineering | Electrical Design | Not Started | 2026-03-27 16:00 | 2026-03-27 16:00 |  |  | 0 | 0 | 0 | Yes | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | EMC-010 | Install Electrical Monitoring Devices | Controls, BMS & DCIM | Electrical Monitoring & Controls | Not Started | 2026-11-16 08:00 | 2026-11-20 16:00 |  |  | 5 | 5 | 50 | No |  |  | 16000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | EMC-020 | Install Power Metering Devices | Controls, BMS & DCIM | Electrical Monitoring & Controls | Not Started | 2026-12-24 08:00 | 2026-12-29 16:00 |  |  | 5 | 5 | 17 | No |  |  | 126000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | EMC-030 | Install Switchgear Monitoring Interfaces | Controls, BMS & DCIM | Electrical Monitoring & Controls | Not Started | 2026-11-16 08:00 | 2026-11-21 16:00 |  |  | 6 | 6 | 49 | No |  |  | 17000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | EMC-040 | Install UPS Monitoring Interfaces | Controls, BMS & DCIM | Electrical Monitoring & Controls | Not Started | 2027-01-01 08:00 | 2027-01-06 16:00 |  |  | 5 | 5 | 10 | No |  |  | 16000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | EMC-050 | Install Generator Monitoring Interfaces | Controls, BMS & DCIM | Electrical Monitoring & Controls | Not Started | 2026-12-12 08:00 | 2026-12-18 16:00 |  |  | 6 | 6 | 26 | No |  |  | 17000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | EMC-060 | Complete Monitoring Communication Connections | Controls, BMS & DCIM | Electrical Monitoring & Controls | Not Started | 2027-01-07 08:00 | 2027-01-08 16:00 |  |  | 2 | 2 | 10 | No |  |  | 12000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | EMC-070 | Electrical Monitoring Ready for Pre-Commissioning | Controls, BMS & DCIM | Electrical Monitoring & Controls | Not Started | 2027-01-08 16:00 | 2027-01-08 16:00 |  |  | 0 | 0 | 10 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | EML-010 | Install Emergency Lighting Fixtures | Fire & Life Safety | Emergency Lighting & Exit Systems | Not Started | 2026-12-25 08:00 | 2026-12-30 16:00 |  |  | 5 | 5 | 21 | No |  |  | 82000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | EML-020 | Install Exit Signage | Fire & Life Safety | Emergency Lighting & Exit Systems | Not Started | 2026-12-25 08:00 | 2026-12-30 16:00 |  |  | 5 | 5 | 21 | No |  |  | 82000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | EML-030 | Install Emergency Lighting Circuits | Fire & Life Safety | Emergency Lighting & Exit Systems | Not Started | 2026-12-24 08:00 | 2026-12-29 16:00 |  |  | 5 | 5 | 17 | No |  |  | 82000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | EML-040 | Install Emergency Lighting Controls | Fire & Life Safety | Emergency Lighting & Exit Systems | Not Started | 2026-12-30 08:00 | 2027-01-04 16:00 |  |  | 5 | 5 | 17 | No |  |  | 82000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | EML-050 | Inspect Emergency Lighting and Exit Systems | Fire & Life Safety | Emergency Lighting & Exit Systems | Not Started | 2027-01-05 08:00 | 2027-01-06 16:00 |  |  | 2 | 2 | 17 | No |  |  | 47000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | EML-060 | Emergency Lighting and Exit Systems Ready for Testing | Fire & Life Safety | Emergency Lighting & Exit Systems | Not Started | 2027-01-06 16:00 | 2027-01-06 16:00 |  |  | 0 | 0 | 17 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ENV-010 | Inspect Building Envelope Interfaces | Building Envelope | Weather-Tightness & Envelope Completion | Not Started | 2026-09-26 08:00 | 2026-09-28 16:00 |  |  | 2 | 2 | 32 | No |  |  | 75000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ENV-020 | Perform Roof Water-Tightness Testing | Building Envelope | Weather-Tightness & Envelope Completion | Not Started | 2026-09-29 08:00 | 2026-10-01 16:00 |  |  | 3 | 3 | 32 | No |  |  | 113000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ENV-030 | Perform External Wall Water-Tightness Testing | Building Envelope | Weather-Tightness & Envelope Completion | Not Started | 2026-09-29 08:00 | 2026-10-01 16:00 |  |  | 3 | 3 | 32 | No |  |  | 85000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ENV-040 | Inspect Doors Louvers and Penetration Seals | Building Envelope | Weather-Tightness & Envelope Completion | Not Started | 2026-09-29 08:00 | 2026-09-30 16:00 |  |  | 2 | 2 | 33 | No |  |  | 75000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ENV-050 | Rectify Building Envelope Defects | Building Envelope | Weather-Tightness & Envelope Completion | Not Started | 2026-10-02 08:00 | 2026-10-07 16:00 |  |  | 5 | 5 | 32 | No |  |  | 83000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ENV-060 | Complete Final Building Envelope Inspection | Building Envelope | Weather-Tightness & Envelope Completion | Not Started | 2026-10-08 08:00 | 2026-10-09 16:00 |  |  | 2 | 2 | 32 | No |  |  | 75000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ENV-070 | Building Weather-Tight | Building Envelope | Weather-Tightness & Envelope Completion | Not Started | 2026-10-10 08:00 | 2026-10-10 08:00 |  |  | 0 | 0 | 32 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | EPF-010 | Confirm Equipment Foundation Requirements | Civil & Structural Works | Equipment Plinths & Foundations | Not Started | 2026-09-14 08:00 | 2026-09-18 16:00 |  |  | 5 | 5 | 55 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | EPF-020 | Set Out Equipment Foundations and Plinths | Civil & Structural Works | Equipment Plinths & Foundations | Not Started | 2026-09-19 08:00 | 2026-09-22 16:00 |  |  | 3 | 3 | 55 | No |  |  | 175000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | EPF-030 | Construct Transformer Plinths | Civil & Structural Works | Equipment Plinths & Foundations | Not Started | 2026-09-23 08:00 | 2026-09-28 16:00 |  |  | 5 | 5 | 55 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | EPF-040 | Construct Switchgear and UPS Equipment Plinths | Civil & Structural Works | Equipment Plinths & Foundations | Not Started | 2026-09-23 08:00 | 2026-09-28 16:00 |  |  | 5 | 5 | 55 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | EPF-050 | Construct Generator Equipment Plinths | Civil & Structural Works | Equipment Plinths & Foundations | Not Started | 2026-09-23 08:00 | 2026-09-28 16:00 |  |  | 5 | 5 | 55 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | EPF-060 | Construct Cooling Equipment Plinths | Civil & Structural Works | Equipment Plinths & Foundations | Not Started | 2026-09-23 08:00 | 2026-09-28 16:00 |  |  | 5 | 5 | 55 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | EPF-070 | Install Equipment Anchor Bolts and Embedded Plates | Civil & Structural Works | Equipment Plinths & Foundations | Not Started | 2026-09-29 08:00 | 2026-10-03 16:00 |  |  | 5 | 5 | 55 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | EPF-080 | Inspect Equipment Foundations and Plinths | Civil & Structural Works | Equipment Plinths & Foundations | Not Started | 2026-10-05 08:00 | 2026-10-07 16:00 |  |  | 3 | 3 | 55 | No |  |  | 175000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | EPF-090 | Equipment Foundations Ready for Installation | Civil & Structural Works | Equipment Plinths & Foundations | Not Started | 2026-10-08 08:00 | 2026-10-08 08:00 |  |  | 0 | 0 | 55 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ERA-010 | Install Electrical Room Cable Trays and Containment | Electrical Systems | Electrical Rooms & Ancillary Systems | Not Started | 2026-10-05 08:00 | 2026-10-15 16:00 |  |  | 10 | 10 | 86 | No |  |  | 307000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ERA-020 | Install Electrical Room Lighting | Electrical Systems | Electrical Rooms & Ancillary Systems | Not Started | 2026-10-08 08:00 | 2026-10-15 16:00 |  |  | 7 | 7 | 86 | No |  |  | 276000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ERA-030 | Install Electrical Room Small Power | Electrical Systems | Electrical Rooms & Ancillary Systems | Not Started | 2026-10-08 08:00 | 2026-10-15 16:00 |  |  | 7 | 7 | 86 | No |  |  | 276000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ERA-040 | Install Emergency Lighting | Electrical Systems | Electrical Rooms & Ancillary Systems | Not Started | 2026-10-10 08:00 | 2026-10-15 16:00 |  |  | 5 | 5 | 86 | No |  |  | 249000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ERA-050 | Install Electrical Room Identification and Labels | Electrical Systems | Electrical Rooms & Ancillary Systems | Not Started | 2027-01-01 08:00 | 2027-01-04 16:00 |  |  | 3 | 3 | 17 | No |  |  | 214000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ERA-060 | Complete Electrical Room Fire-Stopping | Electrical Systems | Electrical Rooms & Ancillary Systems | Not Started | 2026-12-30 08:00 | 2027-01-04 16:00 |  |  | 5 | 5 | 17 | No |  |  | 156000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ERA-070 | Complete Electrical Room Installation Inspection | Electrical Systems | Electrical Rooms & Ancillary Systems | Not Started | 2027-01-05 08:00 | 2027-01-06 16:00 |  |  | 2 | 2 | 17 | No |  |  | 189000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ERA-080 | Electrical Rooms Ready for Commissioning | Electrical Systems | Electrical Rooms & Ancillary Systems | Not Started | 2027-01-06 16:00 | 2027-01-06 16:00 |  |  | 0 | 0 | 17 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ERT-010 | Install Main Site Earthing Grid | Electrical Systems | Earthing & Bonding | Not Started | 2026-04-13 08:00 | 2026-04-23 16:00 |  |  | 10 | 10 | 215 | No |  |  | 307000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ERT-020 | Install Building Earthing Network | Electrical Systems | Earthing & Bonding | Not Started | 2026-06-12 08:00 | 2026-06-23 16:00 |  |  | 10 | 10 | 166 | No |  |  | 307000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ERT-030 | Install Electrical Room Earth Bars | Electrical Systems | Earthing & Bonding | Not Started | 2026-10-05 08:00 | 2026-10-09 16:00 |  |  | 5 | 5 | 78 | No |  |  | 249000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ERT-040 | Bond Transformers and Switchgear | Electrical Systems | Earthing & Bonding | Not Started | 2026-12-18 08:00 | 2026-12-23 16:00 |  |  | 5 | 5 | 24 | No |  |  | 156000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ERT-050 | Bond UPS and Generator Equipment | Electrical Systems | Earthing & Bonding | Not Started | 2026-12-21 08:00 | 2026-12-25 16:00 |  |  | 5 | 5 | 22 | No |  |  | 156000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ERT-060 | Bond Mechanical and Data Hall Equipment | Electrical Systems | Earthing & Bonding | Not Started | 2026-10-22 08:00 | 2026-11-02 16:00 |  |  | 10 | 10 | 68 | No |  |  | 192000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ERT-070 | Perform Earthing Resistance Tests | Electrical Systems | Earthing & Bonding | Not Started | 2026-12-26 08:00 | 2026-12-29 16:00 |  |  | 3 | 3 | 22 | No |  |  | 160000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ERT-080 | Earthing and Bonding System Complete | Electrical Systems | Earthing & Bonding | Not Started | 2026-12-29 16:00 | 2026-12-29 16:00 |  |  | 0 | 0 | 22 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | EUS-010 | Construct Electrical Room Structure | Civil & Structural Works | Electrical & UPS Rooms Structure | Not Started | 2026-09-14 08:00 | 2026-09-24 16:00 |  |  | 10 | 10 | 42 | No |  |  | 250000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | EUS-020 | Construct UPS and Battery Room Structure | Civil & Structural Works | Electrical & UPS Rooms Structure | Not Started | 2026-09-14 08:00 | 2026-09-24 16:00 |  |  | 10 | 10 | 42 | No |  |  | 250000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | EUS-030 | Construct MV and LV Switchgear Room Structure | Civil & Structural Works | Electrical & UPS Rooms Structure | Not Started | 2026-09-14 08:00 | 2026-09-24 16:00 |  |  | 10 | 10 | 42 | No |  |  | 250000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | EUS-040 | Construct Transformer Room Structure | Civil & Structural Works | Electrical & UPS Rooms Structure | Not Started | 2026-09-14 08:00 | 2026-09-24 16:00 |  |  | 10 | 10 | 42 | No |  |  | 250000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | EUS-050 | Install Equipment Support Steel | Civil & Structural Works | Electrical & UPS Rooms Structure | Not Started | 2026-09-25 08:00 | 2026-09-30 16:00 |  |  | 5 | 5 | 42 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | EUS-060 | Complete Equipment Access Openings | Civil & Structural Works | Electrical & UPS Rooms Structure | Not Started | 2026-10-01 08:00 | 2026-10-03 16:00 |  |  | 3 | 3 | 42 | No |  |  | 109000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | EUS-070 | Electrical and UPS Rooms Structure Complete | Civil & Structural Works | Electrical & UPS Rooms Structure | Not Started | 2026-10-05 08:00 | 2026-10-05 08:00 |  |  | 0 | 0 | 42 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | EW-010 | Bulk Excavation | Enabling & Site Works | Earthworks & Excavation | Not Started | 2026-03-30 08:00 | 2026-04-09 16:00 |  |  | 10 | 10 | 32 | No |  |  | 107000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | EW-020 | Excavate Building Formation | Enabling & Site Works | Earthworks & Excavation | Not Started | 2026-04-10 08:00 | 2026-04-21 16:00 |  |  | 10 | 10 | 32 | No |  |  | 107000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | EW-030 | Excavate Utility and Drainage Routes | Enabling & Site Works | Earthworks & Excavation | Not Started | 2026-04-01 08:00 | 2026-04-11 16:00 |  |  | 10 | 10 | 139 | No |  |  | 107000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | EW-040 | Place Engineered Fill | Enabling & Site Works | Earthworks & Excavation | Not Started | 2026-04-22 08:00 | 2026-04-29 16:00 |  |  | 7 | 7 | 32 | No |  |  | 96000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | EW-050 | Compact and Test Formation | Enabling & Site Works | Earthworks & Excavation | Not Started | 2026-04-30 08:00 | 2026-05-02 16:00 |  |  | 3 | 3 | 32 | No |  |  | 75000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | EW-060 | Prepare Formation for Foundations | Enabling & Site Works | Earthworks & Excavation | Not Started | 2026-05-04 08:00 | 2026-05-08 16:00 |  |  | 5 | 5 | 32 | No |  |  | 116000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | EW-070 | Earthworks Complete | Enabling & Site Works | Earthworks & Excavation | Not Started | 2026-05-09 08:00 | 2026-05-09 08:00 |  |  | 0 | 0 | 300 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | FAD-010 | Install Fire Alarm Control Panels | Fire & Life Safety | Fire Detection & Alarm | Not Started | 2026-06-10 08:00 | 2026-06-15 16:00 |  |  | 5 | 5 | 175 | No |  |  | 82000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | FAD-020 | Install Fire Alarm Cabling | Fire & Life Safety | Fire Detection & Alarm | Not Started | 2026-10-08 08:00 | 2026-10-19 16:00 |  |  | 10 | 10 | 67 | No |  |  | 106000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | FAD-030 | Install Smoke and Heat Detectors | Fire & Life Safety | Fire Detection & Alarm | Not Started | 2026-10-10 08:00 | 2026-10-19 16:00 |  |  | 8 | 8 | 67 | No |  |  | 95000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | FAD-040 | Install Manual Call Points | Fire & Life Safety | Fire Detection & Alarm | Not Started | 2026-10-10 08:00 | 2026-10-14 16:00 |  |  | 4 | 4 | 71 | No |  |  | 77000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | FAD-050 | Install Notification Devices | Fire & Life Safety | Fire Detection & Alarm | Not Started | 2026-10-10 08:00 | 2026-10-16 16:00 |  |  | 6 | 6 | 69 | No |  |  | 87000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | FAD-060 | Complete Fire Alarm Device Addressing | Fire & Life Safety | Fire Detection & Alarm | Not Started | 2026-10-20 08:00 | 2026-10-21 16:00 |  |  | 2 | 2 | 67 | No |  |  | 39000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | FAD-070 | Inspect Fire Detection and Alarm Installation | Fire & Life Safety | Fire Detection & Alarm | Not Started | 2026-10-22 08:00 | 2026-10-23 16:00 |  |  | 2 | 2 | 67 | No |  |  | 63000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | FAD-080 | Fire Detection and Alarm Ready for Pre-Commissioning | Fire & Life Safety | Fire Detection & Alarm | Not Started | 2026-10-23 16:00 | 2026-10-23 16:00 |  |  | 0 | 0 | 67 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | FDT-010 | Compile Final Handover Dossier | Client Acceptance & Handover | Ready for Service | Not Started | 2027-02-08 08:00 | 2027-02-12 16:00 |  |  | 5 | 5 | 73 | No |  |  | 29000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | FDT-020 | Submit Commissioning Records | Client Acceptance & Handover | Ready for Service | Not Started | 2027-04-28 08:00 | 2027-05-04 16:00 |  |  | 5 | 5 | 16 | No |  |  | 14000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | FDT-030 | Submit Testing Certificates | Client Acceptance & Handover | Ready for Service | Not Started | 2027-03-29 08:00 | 2027-03-31 16:00 |  |  | 3 | 3 | 40 | No |  |  | 12000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | FDT-040 | Submit Equipment Warranties | Client Acceptance & Handover | Ready for Service | Not Started | 2026-11-12 08:00 | 2026-11-18 16:00 |  |  | 5 | 5 | 135 | No |  |  | 14000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | FDT-050 | Final Handover Documentation Accepted | Client Acceptance & Handover | Ready for Service | Not Started | 2027-05-05 08:00 | 2027-05-11 16:00 |  |  | 5 | 5 | 16 | No |  |  | 29000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | FLS-CX-010 | Commission Fire Detection and Alarm System | Testing & Commissioning | Fire & Life Safety Commissioning | Not Started | 2027-01-30 08:00 | 2027-02-04 16:00 |  |  | 5 | 5 | 10 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | FLS-CX-020 | Commission Sprinkler System | Testing & Commissioning | Fire & Life Safety Commissioning | Not Started | 2027-01-30 08:00 | 2027-02-04 16:00 |  |  | 5 | 5 | 10 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | FLS-CX-030 | Commission Clean Agent Fire Suppression | Testing & Commissioning | Fire & Life Safety Commissioning | Not Started | 2027-01-30 08:00 | 2027-02-04 16:00 |  |  | 5 | 5 | 10 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | FLS-CX-040 | Commission Fire Pumps | Testing & Commissioning | Fire & Life Safety Commissioning | Not Started | 2027-01-30 08:00 | 2027-02-04 16:00 |  |  | 5 | 5 | 10 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | FLS-CX-050 | Commission VESDA System | Testing & Commissioning | Fire & Life Safety Commissioning | Not Started | 2027-01-30 08:00 | 2027-02-04 16:00 |  |  | 5 | 5 | 10 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | FLS-CX-060 | Verify Fire Cause and Effect Matrix | Testing & Commissioning | Fire & Life Safety Commissioning | Not Started | 2027-02-05 08:00 | 2027-02-06 16:00 |  |  | 2 | 2 | 10 | No |  |  | 26000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | FLS-CX-070 | Fire and Life Safety Commissioning Complete | Testing & Commissioning | Fire & Life Safety Commissioning | Not Started | 2027-02-06 16:00 | 2027-02-06 16:00 |  |  | 0 | 0 | 10 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | FLS-D-010 | Develop Fire and Life Safety Design Criteria | Design & Engineering | Fire & Life Safety Design | Completed | 2026-01-13 08:00 | 2026-01-19 16:00 | 2026-01-13 08:00 | 2026-01-19 16:00 | 5 | 0 |  | No |  |  | 111000 | 111000 | 111000 | 114866.88 | -3866.88 | 0 | 0.96634 | 1
Update 01 | 2026-01-31 17:00 | FLS-D-020 | Develop Fire Detection and Alarm Design | Design & Engineering | Fire & Life Safety Design | In Progress | 2026-01-20 08:00 | 2026-02-02 16:00 | 2026-01-20 08:00 |  | 10 | 1 | 113 | No |  |  | 136000 | 116025 | 122400 | 128254.13 | -5854.13 | 6375 | 0.95436 | 1.0549
Update 01 | 2026-01-31 17:00 | FLS-D-030 | Develop Fire Suppression System Design | Design & Engineering | Fire & Life Safety Design | In Progress | 2026-01-20 08:00 | 2026-02-02 16:00 | 2026-01-20 08:00 |  | 10 | 1 | 113 | No |  |  | 136000 | 116025 | 122400 | 126029.24 | -3629.24 | 6375 | 0.9712 | 1.0549
Update 01 | 2026-01-31 17:00 | FLS-D-040 | Develop VESDA and Early Warning Detection Design | Design & Engineering | Fire & Life Safety Design | In Progress | 2026-01-20 08:00 | 2026-01-29 16:00 | 2026-01-21 08:00 |  | 8 | 2 | 112 | No |  |  | 127000 | 127000 | 95250 | 100350.71 | -5100.71 | -31750 | 0.94917 | 0.75
Update 01 | 2026-01-31 17:00 | FLS-D-050 | Develop Fire System Interface Matrix | Design & Engineering | Fire & Life Safety Design | In Progress | 2026-01-27 08:00 | 2026-02-02 16:00 | 2026-01-27 08:00 |  | 5 | 1 | 112 | No |  |  | 65000 | 44901.3158 | 52000 | 54876.22 | -2876.22 | 7098.6842 | 0.94759 | 1.1581
Update 01 | 2026-01-31 17:00 | FLS-D-060 | Fire and Life Safety Design Review | Design & Engineering | Fire & Life Safety Design | Not Started | 2026-02-04 08:00 | 2026-02-10 16:00 |  |  | 5 | 5 | 145 | No |  |  | 18000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | FLS-D-070 | Fire and Life Safety Design Approved | Design & Engineering | Fire & Life Safety Design | Not Started | 2026-02-10 16:00 | 2026-02-10 16:00 |  |  | 0 | 0 | 145 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | FLS-P-010 | Prepare Fire and Life Safety Equipment Submittal | Procurement | Fire & Life Safety Equipment | Not Started | 2026-02-04 08:00 | 2026-02-10 16:00 |  |  | 5 | 5 | 145 | No |  |  | 94000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | FLS-P-020 | Fire and Life Safety Equipment Submittal Approval | Procurement | Fire & Life Safety Equipment | Not Started | 2026-02-11 08:00 | 2026-02-19 16:00 |  |  | 7 | 7 | 145 | No |  |  | 104000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | FLS-P-030 | Issue Purchase Order - Fire and Life Safety Equipment | Procurement | Fire & Life Safety Equipment | Not Started | 2026-02-20 08:00 | 2026-02-24 16:00 |  |  | 3 | 3 | 145 | No |  |  | 134000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | FLS-P-040 | Manufacture Fire and Life Safety Equipment | Procurement | Fire & Life Safety Equipment | Not Started | 2026-02-25 08:00 | 2026-05-19 16:00 |  |  | 60 | 60 | 145 | No |  |  | 1980000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | FLS-P-050 | Factory Testing - Fire and Life Safety Equipment | Procurement | Fire & Life Safety Equipment | Not Started | 2026-05-20 08:00 | 2026-05-22 16:00 |  |  | 3 | 3 | 145 | No |  |  | 107000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | FLS-P-060 | Ship Fire and Life Safety Equipment | Procurement | Fire & Life Safety Equipment | Not Started | 2026-05-25 08:00 | 2026-06-05 16:00 |  |  | 10 | 10 | 145 | No |  |  | 154000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | FLS-P-070 | Deliver Fire and Life Safety Equipment to Site | Procurement | Fire & Life Safety Equipment | Not Started | 2026-06-08 08:00 | 2026-06-09 16:00 |  |  | 2 | 2 | 145 | No |  |  | 95000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | FND-010 | Set Out Building Foundations | Civil & Structural Works | Foundations | Not Started | 2026-05-09 08:00 | 2026-05-12 16:00 |  |  | 3 | 3 | 32 | No |  |  | 175000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | FND-020 | Excavate Building Foundations | Civil & Structural Works | Foundations | Not Started | 2026-05-13 08:00 | 2026-05-23 16:00 |  |  | 10 | 10 | 32 | No |  |  | 250000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | FND-030 | Prepare Foundation Formation | Civil & Structural Works | Foundations | Not Started | 2026-05-25 08:00 | 2026-05-29 16:00 |  |  | 5 | 5 | 32 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | FND-040 | Place Blinding Concrete | Civil & Structural Works | Foundations | Not Started | 2026-05-30 08:00 | 2026-06-02 16:00 |  |  | 3 | 3 | 32 | No |  |  | 175000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | FND-050 | Install Foundation Reinforcement | Civil & Structural Works | Foundations | Not Started | 2026-06-03 08:00 | 2026-06-13 16:00 |  |  | 10 | 10 | 32 | No |  |  | 250000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | FND-060 | Install Foundation Formwork | Civil & Structural Works | Foundations | Not Started | 2026-06-06 08:00 | 2026-06-15 16:00 |  |  | 8 | 8 | 32 | No |  |  | 234000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | FND-070 | Install Foundation Embedded Items | Civil & Structural Works | Foundations | Not Started | 2026-06-06 08:00 | 2026-06-11 16:00 |  |  | 5 | 5 | 35 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | FND-080 | Cast Foundation Concrete | Civil & Structural Works | Foundations | Not Started | 2026-06-16 08:00 | 2026-06-20 16:00 |  |  | 5 | 5 | 32 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | FND-090 | Cure Foundation Concrete | Civil & Structural Works | Foundations | Not Started | 2026-06-22 08:00 | 2026-06-29 16:00 |  |  | 7 | 7 | 32 | No |  |  | 225000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | FND-100 | Strip Foundation Formwork | Civil & Structural Works | Foundations | Not Started | 2026-06-30 08:00 | 2026-07-02 16:00 |  |  | 3 | 3 | 32 | No |  |  | 175000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | FND-110 | Backfill Around Foundations | Civil & Structural Works | Foundations | Not Started | 2026-07-20 08:00 | 2026-07-24 16:00 |  |  | 5 | 5 | 32 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | FND-120 | Building Foundations Complete | Civil & Structural Works | Foundations | Not Started | 2026-07-25 08:00 | 2026-07-25 08:00 |  |  | 0 | 0 | 32 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | FPW-010 | Prepare Fire Pump Room | Fire & Life Safety | Fire Pump & Water Supply | Not Started | 2026-06-10 08:00 | 2026-06-15 16:00 |  |  | 5 | 5 | 178 | No |  |  | 51000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | FPW-020 | Install Fire Water Tank Connections | Fire & Life Safety | Fire Pump & Water Supply | Not Started | 2026-06-16 08:00 | 2026-06-20 16:00 |  |  | 5 | 5 | 178 | No |  |  | 82000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | FPW-030 | Install Main Fire Pumps | Fire & Life Safety | Fire Pump & Water Supply | Not Started | 2026-06-16 08:00 | 2026-06-20 16:00 |  |  | 5 | 5 | 178 | No |  |  | 82000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | FPW-040 | Install Jockey Pump | Fire & Life Safety | Fire Pump & Water Supply | Not Started | 2026-06-16 08:00 | 2026-06-20 16:00 |  |  | 5 | 5 | 178 | No |  |  | 82000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | FPW-050 | Install Fire Pump Pipework and Valves | Fire & Life Safety | Fire Pump & Water Supply | Not Started | 2026-06-22 08:00 | 2026-06-30 16:00 |  |  | 8 | 8 | 178 | No |  |  | 95000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | FPW-060 | Install Fire Pump Electrical Connections | Fire & Life Safety | Fire Pump & Water Supply | Not Started | 2026-06-22 08:00 | 2026-06-26 16:00 |  |  | 5 | 5 | 181 | No |  |  | 82000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | FPW-070 | Install Fire Pump Controls | Fire & Life Safety | Fire Pump & Water Supply | Not Started | 2026-10-22 08:00 | 2026-10-27 16:00 |  |  | 5 | 5 | 76 | No |  |  | 82000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | FPW-080 | Inspect Fire Pump and Water Supply Installation | Fire & Life Safety | Fire Pump & Water Supply | Not Started | 2026-10-28 08:00 | 2026-10-29 16:00 |  |  | 2 | 2 | 76 | No |  |  | 63000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | FPW-090 | Fire Pump and Water Supply Ready for Pre-Commissioning | Fire & Life Safety | Fire Pump & Water Supply | Not Started | 2026-10-29 16:00 | 2026-10-29 16:00 |  |  | 0 | 0 | 76 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | FSI-010 | Install Fire Alarm Interface Modules | Fire & Life Safety | Fire System Interfaces | Not Started | 2026-10-24 08:00 | 2026-10-29 16:00 |  |  | 5 | 5 | 67 | No |  |  | 82000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | FSI-020 | Connect Fire Alarm to Mechanical Systems | Fire & Life Safety | Fire System Interfaces | Not Started | 2026-12-08 08:00 | 2026-12-12 16:00 |  |  | 5 | 5 | 34 | No |  |  | 51000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | FSI-030 | Connect Fire Alarm to Electrical Systems | Fire & Life Safety | Fire System Interfaces | Not Started | 2026-12-24 08:00 | 2026-12-29 16:00 |  |  | 5 | 5 | 20 | No |  |  | 51000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | FSI-040 | Connect Fire Alarm to Access Control System | Fire & Life Safety | Fire System Interfaces | Not Started | 2026-10-30 08:00 | 2026-11-04 16:00 |  |  | 5 | 5 | 67 | No |  |  | 51000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | FSI-050 | Connect Fire Alarm to BMS | Fire & Life Safety | Fire System Interfaces | Not Started | 2026-12-29 08:00 | 2027-01-02 16:00 |  |  | 5 | 5 | 16 | No |  |  | 51000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | FSI-060 | Complete Fire Cause and Effect Configuration | Fire & Life Safety | Fire System Interfaces | Not Started | 2027-01-04 08:00 | 2027-01-05 16:00 |  |  | 2 | 2 | 16 | No |  |  | 39000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | FSI-070 | Inspect Fire System Interfaces | Fire & Life Safety | Fire System Interfaces | Not Started | 2027-01-06 08:00 | 2027-01-07 16:00 |  |  | 2 | 2 | 16 | No |  |  | 47000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | FSI-080 | Fire System Interfaces Ready for Integrated Testing | Fire & Life Safety | Fire System Interfaces | Not Started | 2027-01-07 16:00 | 2027-01-07 16:00 |  |  | 0 | 0 | 16 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | GBP-010 | Complete Generator Pre-Start Checks | Utility Connection & Energization | Data Hall Power-On | Not Started | 2026-12-31 08:00 | 2026-12-31 16:00 |  |  | 1 | 1 | 23 | No |  |  | 63000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | GBP-020 | Complete Generator Fuel System Readiness Checks | Utility Connection & Energization | Data Hall Power-On | Not Started | 2026-12-31 08:00 | 2026-12-31 16:00 |  |  | 1 | 1 | 23 | No |  |  | 63000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | GBP-030 | Start Standby Generators | Utility Connection & Energization | Data Hall Power-On | Not Started | 2027-01-01 08:00 | 2027-01-02 16:00 |  |  | 2 | 2 | 23 | No |  |  | 77000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | GBP-040 | Verify Generator Controls and Protection | Utility Connection & Energization | Data Hall Power-On | Not Started | 2027-01-04 08:00 | 2027-01-05 16:00 |  |  | 2 | 2 | 23 | No |  |  | 77000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | GBP-050 | Verify Generator Automatic Transfer Sequence | Utility Connection & Energization | Data Hall Power-On | Not Started | 2027-01-13 08:00 | 2027-01-14 16:00 |  |  | 2 | 2 | 17 | No |  |  | 77000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | GBP-060 | Backup Power System Ready | Utility Connection & Energization | Data Hall Power-On | Not Started | 2027-01-14 16:00 | 2027-01-14 16:00 |  |  | 0 | 0 | 17 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | GCP-010 | Develop BMS Control Logic | Controls, BMS & DCIM | Graphics, Configuration & Programming | Not Started | 2026-08-07 08:00 | 2026-08-15 16:00 |  |  | 8 | 8 | 130 | No |  |  | 91000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | GCP-020 | Configure BMS Alarm Logic | Controls, BMS & DCIM | Graphics, Configuration & Programming | Not Started | 2026-08-10 08:00 | 2026-08-14 16:00 |  |  | 5 | 5 | 133 | No |  |  | 79000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | GCP-030 | Develop BMS Graphics | Controls, BMS & DCIM | Graphics, Configuration & Programming | Not Started | 2026-08-10 08:00 | 2026-08-18 16:00 |  |  | 8 | 8 | 130 | No |  |  | 91000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | GCP-040 | Configure DCIM Dashboards | Controls, BMS & DCIM | Graphics, Configuration & Programming | Not Started | 2026-08-10 08:00 | 2026-08-14 16:00 |  |  | 5 | 5 | 133 | No |  |  | 79000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | GCP-050 | Configure Trend Logging and Reporting | Controls, BMS & DCIM | Graphics, Configuration & Programming | Not Started | 2026-08-10 08:00 | 2026-08-13 16:00 |  |  | 4 | 4 | 134 | No |  |  | 15000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | GCP-060 | Complete Controls Software Configuration | Controls, BMS & DCIM | Graphics, Configuration & Programming | Not Started | 2026-08-19 08:00 | 2026-08-21 16:00 |  |  | 3 | 3 | 130 | No |  |  | 68000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | GCP-070 | BMS and DCIM Configuration Complete | Controls, BMS & DCIM | Graphics, Configuration & Programming | Not Started | 2026-08-21 16:00 | 2026-08-21 16:00 |  |  | 0 | 0 | 130 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | GEN-010 | Prepare Standby Generator Technical Submittal | Procurement | Standby Generators | Not Started | 2026-02-19 08:00 | 2026-02-27 16:00 |  |  | 7 | 7 | 38 | No |  |  | 208000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | GEN-020 | Standby Generator Technical Submittal Approval | Procurement | Standby Generators | Not Started | 2026-03-30 08:00 | 2026-04-07 16:00 |  |  | 7 | 7 | 18 | No |  |  | 208000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | GEN-030 | Issue Purchase Order - Standby Generators | Procurement | Standby Generators | Not Started | 2026-04-08 08:00 | 2026-04-10 16:00 |  |  | 3 | 3 | 18 | No |  |  | 269000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | GEN-040 | Manufacture Standby Generators | Procurement | Standby Generators | Not Started | 2026-04-13 08:00 | 2026-11-06 16:00 |  |  | 150 | 150 | 18 | No |  |  | 5213000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | GEN-050 | Factory Acceptance Test - Standby Generators | Procurement | Standby Generators | Not Started | 2026-11-09 08:00 | 2026-11-11 16:00 |  |  | 3 | 3 | 18 | No |  |  | 349000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | GEN-060 | Ship Standby Generators | Procurement | Standby Generators | Not Started | 2026-11-12 08:00 | 2026-12-09 16:00 |  |  | 20 | 20 | 18 | No |  |  | 380000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | GEN-070 | Deliver Standby Generators to Site | Procurement | Standby Generators | Not Started | 2026-12-10 08:00 | 2026-12-11 16:00 |  |  | 2 | 2 | 18 | No |  |  | 190000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | GUS-010 | Construct Generator Foundations | Civil & Structural Works | Generator & Utility Structures | Not Started | 2026-07-25 08:00 | 2026-08-05 16:00 |  |  | 10 | 10 | 118 | No |  |  | 250000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | GUS-020 | Construct Generator Support Structures | Civil & Structural Works | Generator & Utility Structures | Not Started | 2026-08-06 08:00 | 2026-08-14 16:00 |  |  | 8 | 8 | 118 | No |  |  | 234000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | GUS-030 | Construct Utility and MV Structures | Civil & Structural Works | Generator & Utility Structures | Not Started | 2026-08-06 08:00 | 2026-08-14 16:00 |  |  | 8 | 8 | 123 | No |  |  | 234000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | GUS-040 | Construct Fuel System Structural Supports | Civil & Structural Works | Generator & Utility Structures | Not Started | 2026-08-06 08:00 | 2026-08-11 16:00 |  |  | 5 | 5 | 121 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | GUS-050 | Install Generator Equipment Plinths | Civil & Structural Works | Generator & Utility Structures | Not Started | 2026-08-15 08:00 | 2026-08-20 16:00 |  |  | 5 | 5 | 118 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | GUS-060 | Generator and Utility Structures Complete | Civil & Structural Works | Generator & Utility Structures | Not Started | 2026-08-21 08:00 | 2026-08-21 08:00 |  |  | 0 | 0 | 118 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | HND-010 | Conduct Client Pre-Handover Inspection | Client Acceptance & Handover | Punch List / Snagging | Not Started | 2027-04-28 08:00 | 2027-04-29 16:00 |  |  | 2 | 2 | 0 | Yes | 1 | 44 | 44000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | HND-020 | Prepare Final Punch List | Client Acceptance & Handover | Punch List / Snagging | Not Started | 2027-04-30 08:00 | 2027-05-13 16:00 |  |  | 10 | 10 | 0 | Yes | 1 | 45 | 35000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | HND-030 | Rectify Final Punch List Items | Client Acceptance & Handover | Punch List / Snagging | Not Started | 2027-05-14 08:00 | 2027-05-27 16:00 |  |  | 10 | 10 | 0 | Yes | 1 | 46 | 35000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | HND-040 | Verify Punch List Closure | Client Acceptance & Handover | Punch List / Snagging | Not Started | 2027-05-28 08:00 | 2027-05-31 16:00 |  |  | 2 | 2 | 0 | Yes | 1 | 47 | 22000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | HSE-010 | Develop Project HSE Plan | Project Management & Controls | HSE Management | Completed | 2026-01-05 08:00 | 2026-01-16 16:00 | 2026-01-05 08:00 | 2026-01-16 16:00 | 10 | 0 |  | No |  |  | 361000 | 361000 | 361000 | 366372.08 | -5372.08 | 0 | 0.98534 | 1
Update 01 | 2026-01-31 17:00 | HSE-020 | HSE Plan Review | Project Management & Controls | HSE Management | Completed | 2026-01-19 08:00 | 2026-01-23 16:00 | 2026-01-19 08:00 | 2026-01-23 16:00 | 5 | 0 |  | No |  |  | 130000 | 130000 | 130000 | 130312.33 | -312.33 | 0 | 0.9976 | 1
Update 01 | 2026-01-31 17:00 | HSE-030 | HSE Plan Approval | Project Management & Controls | HSE Management | Completed | 2026-01-26 08:00 | 2026-01-28 16:00 | 2026-01-26 08:00 | 2026-01-28 16:00 | 3 | 0 |  | No |  |  | 168000 | 168000 | 168000 | 172118.68 | -4118.68 | 0 | 0.97607 | 1
Update 01 | 2026-01-31 17:00 | ICT-D-010 | Develop ICT Infrastructure Design | Design & Engineering | ICT & Security Systems Design | Completed | 2026-01-13 08:00 | 2026-01-26 16:00 | 2026-01-13 08:00 | 2026-01-26 16:00 | 10 | 0 |  | No |  |  | 136000 | 136000 | 136000 | 142582.04 | -6582.04 | 0 | 0.95384 | 1
Update 01 | 2026-01-31 17:00 | ICT-D-020 | Develop Structured Cabling Design | Design & Engineering | ICT & Security Systems Design | In Progress | 2026-01-27 08:00 | 2026-02-09 16:00 | 2026-01-27 08:00 |  | 10 | 6 | 98 | No |  |  | 136000 | 44625 | 54400 | 57501.59 | -3101.59 | 9775 | 0.94606 | 1.219
Update 01 | 2026-01-31 17:00 | ICT-D-030 | Develop CCTV System Design | Design & Engineering | ICT & Security Systems Design | In Progress | 2026-01-27 08:00 | 2026-02-05 16:00 | 2026-01-27 08:00 |  | 8 | 4 | 100 | No |  |  | 127000 | 59531.25 | 63500 | 65311.16 | -1811.16 | 3968.75 | 0.97227 | 1.0667
Update 01 | 2026-01-31 17:00 | ICT-D-040 | Develop Access Control System Design | Design & Engineering | ICT & Security Systems Design | In Progress | 2026-01-27 08:00 | 2026-02-05 16:00 | 2026-01-27 08:00 |  | 8 | 4 | 100 | No |  |  | 127000 | 59531.25 | 63500 | 65765.05 | -2265.05 | 3968.75 | 0.96556 | 1.0667
Update 01 | 2026-01-31 17:00 | ICT-D-050 | Develop Security System Integration Design | Design & Engineering | ICT & Security Systems Design | Not Started | 2026-02-10 08:00 | 2026-02-23 16:00 |  |  | 10 | 10 | 98 | No |  |  | 136000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ICT-D-060 | ICT and Security Design Review | Design & Engineering | ICT & Security Systems Design | Not Started | 2026-02-24 08:00 | 2026-03-02 16:00 |  |  | 5 | 5 | 185 | No |  |  | 18000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ICT-D-070 | ICT and Security Design Approved | Design & Engineering | ICT & Security Systems Design | Not Started | 2026-03-02 16:00 | 2026-03-02 16:00 |  |  | 0 | 0 | 185 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ICT-P-010 | Prepare ICT and Security Equipment Submittal | Procurement | ICT & Security Equipment | Not Started | 2026-02-24 08:00 | 2026-03-02 16:00 |  |  | 5 | 5 | 242 | No |  |  | 67000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ICT-P-020 | ICT and Security Equipment Submittal Approval | Procurement | ICT & Security Equipment | Not Started | 2026-03-03 08:00 | 2026-03-09 16:00 |  |  | 5 | 5 | 242 | No |  |  | 67000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ICT-P-030 | Issue Purchase Order - ICT and Security Equipment | Procurement | ICT & Security Equipment | Not Started | 2026-03-10 08:00 | 2026-03-12 16:00 |  |  | 3 | 3 | 242 | No |  |  | 96000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ICT-P-040 | Procure ICT and Security Equipment | Procurement | ICT & Security Equipment | Not Started | 2026-03-13 08:00 | 2026-04-23 16:00 |  |  | 30 | 30 | 242 | No |  |  | 153000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ICT-P-050 | Factory Configuration and Testing - ICT and Security | Procurement | ICT & Security Equipment | Not Started | 2026-04-24 08:00 | 2026-04-30 16:00 |  |  | 5 | 5 | 242 | No |  |  | 89000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ICT-P-060 | Ship ICT and Security Equipment | Procurement | ICT & Security Equipment | Not Started | 2026-05-01 08:00 | 2026-05-14 16:00 |  |  | 10 | 10 | 242 | No |  |  | 110000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ICT-P-070 | Deliver ICT and Security Equipment to Site | Procurement | ICT & Security Equipment | Not Started | 2026-05-15 08:00 | 2026-05-18 16:00 |  |  | 2 | 2 | 242 | No |  |  | 68000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | INT-010 | Develop Stakeholder Register | Project Management & Controls | Stakeholder & Interface Management | Completed | 2026-01-06 08:00 | 2026-01-12 16:00 | 2026-01-06 08:00 | 2026-01-12 16:00 | 5 | 0 |  | No |  |  | 130000 | 130000 | 130000 | 131648.84 | -1648.84 | 0 | 0.98748 | 1
Update 01 | 2026-01-31 17:00 | INT-020 | Develop Interface Register | Project Management & Controls | Stakeholder & Interface Management | Completed | 2026-01-13 08:00 | 2026-01-26 16:00 | 2026-01-13 08:00 | 2026-01-26 16:00 | 10 | 0 |  | No |  |  | 160000 | 160000 | 160000 | 159482.29 | 517.71 | 0 | 1.0032 | 1
Update 01 | 2026-01-31 17:00 | INT-030 | Establish Interface Management Procedure | Project Management & Controls | Stakeholder & Interface Management | In Progress | 2026-01-27 08:00 | 2026-02-02 16:00 | 2026-01-27 08:00 |  | 5 | 1 | 35 | No |  |  | 293000 | 202401.3158 | 234400 | 233372.11 | 1027.89 | 31998.6842 | 1.0044 | 1.1581
Update 01 | 2026-01-31 17:00 | INT-040 | Establish Communication and Reporting Matrix | Project Management & Controls | Stakeholder & Interface Management | Completed | 2026-01-13 08:00 | 2026-01-19 16:00 | 2026-01-13 08:00 | 2026-01-19 16:00 | 5 | 0 |  | No |  |  | 130000 | 130000 | 130000 | 132449.55 | -2449.55 | 0 | 0.98151 | 1
Update 01 | 2026-01-31 17:00 | INT-CX-010 | Verify Electrical to BMS Integration | Testing & Commissioning | Controls & Systems Integration | Not Started | 2027-02-18 08:00 | 2027-02-19 16:00 |  |  | 2 | 2 | 1 | No |  |  | 26000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | INT-CX-020 | Verify Mechanical to BMS Integration | Testing & Commissioning | Controls & Systems Integration | Not Started | 2027-02-18 08:00 | 2027-02-19 16:00 |  |  | 2 | 2 | 1 | No |  |  | 26000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | INT-CX-030 | Verify Fire System Integration | Testing & Commissioning | Controls & Systems Integration | Not Started | 2027-02-18 08:00 | 2027-02-19 16:00 |  |  | 2 | 2 | 1 | No |  |  | 26000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | INT-CX-040 | Verify UPS and Generator Controls Integration | Testing & Commissioning | Controls & Systems Integration | Not Started | 2027-02-18 08:00 | 2027-02-19 16:00 |  |  | 2 | 2 | 1 | No |  |  | 26000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | INT-CX-050 | Complete Integrated Controls Testing | Testing & Commissioning | Controls & Systems Integration | Not Started | 2027-02-20 08:00 | 2027-02-22 16:00 |  |  | 2 | 2 | 1 | No |  |  | 31000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | INT-CX-060 | Systems Integration Complete | Testing & Commissioning | Controls & Systems Integration | Not Started | 2027-02-22 16:00 | 2027-02-22 16:00 |  |  | 0 | 0 | 1 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | IST-010 | Prepare Integrated Systems Test Scripts | Testing & Commissioning | Integrated Systems Testing (IST) | In Progress | 2026-01-23 08:00 | 2026-02-03 16:00 | 2026-01-23 08:00 |  | 10 | 4 | 328 | No |  |  | 50000 | 36948.5294 | 30000 | 29899.54 | 100.46 | -6948.5294 | 1.0034 | 0.81194
Update 01 | 2026-01-31 17:00 | IST-020 | Conduct Utility Power Failure Scenario | Testing & Commissioning | Integrated Systems Testing (IST) | Not Started | 2027-02-24 08:00 | 2027-03-01 16:00 |  |  | 5 | 5 | 0 | Yes | 1 | 34 | 34000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | IST-030 | Conduct Generator Transfer Scenario | Testing & Commissioning | Integrated Systems Testing (IST) | Not Started | 2027-02-24 08:00 | 2027-03-01 16:00 |  |  | 5 | 5 | 0 | Yes | 4 | 1 | 34000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | IST-040 | Conduct UPS Battery Ride-Through Scenario | Testing & Commissioning | Integrated Systems Testing (IST) | Not Started | 2027-02-24 08:00 | 2027-03-01 16:00 |  |  | 5 | 5 | 0 | Yes | 5 | 1 | 34000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | IST-050 | Conduct Cooling Failure Scenario | Testing & Commissioning | Integrated Systems Testing (IST) | Not Started | 2027-02-24 08:00 | 2027-03-01 16:00 |  |  | 5 | 5 | 0 | Yes | 6 | 1 | 34000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | IST-060 | Conduct Fire Alarm Integration Scenario | Testing & Commissioning | Integrated Systems Testing (IST) | Not Started | 2027-02-24 08:00 | 2027-03-01 16:00 |  |  | 5 | 5 | 0 | Yes | 7 | 1 | 34000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | IST-070 | Conduct BMS DCIM Alarm Response Testing | Testing & Commissioning | Integrated Systems Testing (IST) | Not Started | 2027-02-24 08:00 | 2027-02-26 16:00 |  |  | 3 | 3 | 2 | No |  |  | 35000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | IST-080 | Resolve IST Deficiencies | Testing & Commissioning | Integrated Systems Testing (IST) | Not Started | 2027-03-02 08:00 | 2027-03-12 16:00 |  |  | 10 | 10 | 0 | Yes | 1 | 35 | 42000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | IST-090 | Integrated Systems Testing Complete | Testing & Commissioning | Integrated Systems Testing (IST) | Not Started | 2027-03-12 16:00 | 2027-03-12 16:00 |  |  | 0 | 0 | 0 | Yes | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | LBT-010 | Mobilize Load Bank Equipment | Testing & Commissioning | Load Bank & Performance Testing | Not Started | 2027-02-04 08:00 | 2027-02-09 16:00 |  |  | 5 | 5 | 0 | Yes | 1 | 29 | 41000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | LBT-020 | Connect Load Bank Equipment | Testing & Commissioning | Load Bank & Performance Testing | Not Started | 2027-02-10 08:00 | 2027-02-15 16:00 |  |  | 5 | 5 | 0 | Yes | 1 | 30 | 41000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | LBT-030 | Perform UPS Load Bank Testing | Testing & Commissioning | Load Bank & Performance Testing | Not Started | 2027-02-16 08:00 | 2027-02-20 16:00 |  |  | 5 | 5 | 0 | Yes | 1 | 31 | 41000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | LBT-040 | Perform Generator Load Bank Testing | Testing & Commissioning | Load Bank & Performance Testing | Not Started | 2027-02-16 08:00 | 2027-02-20 16:00 |  |  | 5 | 5 | 0 | Yes | 8 | 3 | 41000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | LBT-050 | Perform Cooling Performance Testing | Testing & Commissioning | Load Bank & Performance Testing | Not Started | 2027-02-16 08:00 | 2027-02-20 16:00 |  |  | 5 | 5 | 0 | Yes | 9 | 1 | 41000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | LBT-060 | Verify Data Hall Environmental Performance | Testing & Commissioning | Load Bank & Performance Testing | Not Started | 2027-02-22 08:00 | 2027-02-23 16:00 |  |  | 2 | 2 | 0 | Yes | 1 | 32 | 26000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | LBT-070 | Load Bank and Performance Testing Complete | Testing & Commissioning | Load Bank & Performance Testing | Not Started | 2027-02-23 16:00 | 2027-02-23 16:00 |  |  | 0 | 0 | 0 | Yes | 1 | 33 | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | LLE-010 | Identify Long-Lead Equipment | Procurement | Long-Lead Equipment Management | Not Started | 2026-03-02 08:00 | 2026-03-06 16:00 |  |  | 5 | 5 | 127 | No |  |  | 89000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | LLE-020 | Establish Long-Lead Equipment Register | Procurement | Long-Lead Equipment Management | Not Started | 2026-03-09 08:00 | 2026-03-13 16:00 |  |  | 5 | 5 | 127 | No |  |  | 45000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | LLE-030 | Confirm Required-on-Site Dates | Procurement | Long-Lead Equipment Management | Not Started | 2026-03-16 08:00 | 2026-03-20 16:00 |  |  | 5 | 5 | 127 | No |  |  | 89000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | LLE-040 | Monitor Vendor Engineering and Manufacturing | Procurement | Long-Lead Equipment Management | Not Started | 2026-04-08 08:00 | 2026-08-11 16:00 |  |  | 90 | 90 | 115 | No |  |  | 106000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | LLE-050 | Monitor FAT and Shipping Readiness | Procurement | Long-Lead Equipment Management | Not Started | 2026-08-12 08:00 | 2026-08-18 16:00 |  |  | 5 | 5 | 115 | No |  |  | 45000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | LLE-060 | Long-Lead Equipment Delivery Readiness Confirmed | Procurement | Long-Lead Equipment Management | Not Started | 2026-11-11 16:00 | 2026-11-11 16:00 |  |  | 0 | 0 | 54 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | LPS-010 | Install Roof Lightning Protection Network | Electrical Systems | Lightning Protection | Not Started | 2026-09-21 08:00 | 2026-09-28 16:00 |  |  | 7 | 7 | 98 | No |  |  | 276000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | LPS-020 | Install Lightning Protection Down Conductors | Electrical Systems | Lightning Protection | Not Started | 2026-09-23 08:00 | 2026-09-28 16:00 |  |  | 5 | 5 | 98 | No |  |  | 249000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | LPS-030 | Connect Lightning Protection to Earth Network | Electrical Systems | Lightning Protection | Not Started | 2026-09-29 08:00 | 2026-10-01 16:00 |  |  | 3 | 3 | 98 | No |  |  | 134000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | LPS-040 | Test Lightning Protection System | Electrical Systems | Lightning Protection | Not Started | 2026-10-02 08:00 | 2026-10-03 16:00 |  |  | 2 | 2 | 98 | No |  |  | 142000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | LPS-050 | Lightning Protection System Complete | Electrical Systems | Lightning Protection | Not Started | 2026-10-03 16:00 | 2026-10-03 16:00 |  |  | 0 | 0 | 98 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | LSC-010 | Conduct Internal Fire and Life Safety Inspection | Fire & Life Safety | Life Safety Compliance & Inspections | Not Started | 2027-02-08 08:00 | 2027-02-09 16:00 |  |  | 2 | 2 | 63 | No |  |  | 47000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | LSC-020 | Conduct Fire-Stopping Inspection | Fire & Life Safety | Life Safety Compliance & Inspections | Not Started | 2026-10-08 08:00 | 2026-10-09 16:00 |  |  | 2 | 2 | 168 | No |  |  | 47000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | LSC-030 | Conduct Emergency Egress Inspection | Fire & Life Safety | Life Safety Compliance & Inspections | Not Started | 2026-10-08 08:00 | 2026-10-09 16:00 |  |  | 2 | 2 | 168 | No |  |  | 47000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | LSC-040 | Conduct Fire System Compliance Review | Fire & Life Safety | Life Safety Compliance & Inspections | Not Started | 2027-02-10 08:00 | 2027-02-15 16:00 |  |  | 5 | 5 | 63 | No |  |  | 10000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | LSC-050 | Rectify Fire and Life Safety Inspection Comments | Fire & Life Safety | Life Safety Compliance & Inspections | Not Started | 2027-02-16 08:00 | 2027-02-17 16:00 |  |  | 2 | 2 | 63 | No |  |  | 47000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | LSC-060 | Prepare Authority Inspection Documentation | Fire & Life Safety | Life Safety Compliance & Inspections | Not Started | 2027-02-18 08:00 | 2027-02-19 16:00 |  |  | 2 | 2 | 63 | No |  |  | 47000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | LSC-070 | Fire and Life Safety Systems Ready for Authority Inspection | Fire & Life Safety | Life Safety Compliance & Inspections | Not Started | 2027-02-19 16:00 | 2027-02-19 16:00 |  |  | 0 | 0 | 63 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | LV-010 | Prepare LV Electrical Rooms for Installation | Electrical Systems | LV Main Distribution | Not Started | 2026-10-10 08:00 | 2026-10-13 16:00 |  |  | 3 | 3 | 42 | No |  |  | 214000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | LV-020 | Receive and Inspect LV Switchgear | Electrical Systems | LV Main Distribution | Not Started | 2026-10-24 08:00 | 2026-10-26 16:00 |  |  | 2 | 2 | 38 | No |  |  | 142000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | LV-030 | Position and Install LV Switchgear | Electrical Systems | LV Main Distribution | Not Started | 2026-10-27 08:00 | 2026-10-31 16:00 |  |  | 5 | 5 | 38 | No |  |  | 249000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | LV-040 | Install Main LV Cable Containment | Electrical Systems | LV Main Distribution | Not Started | 2026-10-14 08:00 | 2026-10-22 16:00 |  |  | 8 | 8 | 42 | No |  |  | 287000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | LV-050 | Install Main LV Power Cables | Electrical Systems | LV Main Distribution | Not Started | 2026-10-16 08:00 | 2026-10-27 16:00 |  |  | 10 | 10 | 42 | No |  |  | 307000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | LV-060 | Terminate Main LV Power Cables | Electrical Systems | LV Main Distribution | Not Started | 2026-11-02 08:00 | 2026-11-06 16:00 |  |  | 5 | 5 | 38 | No |  |  | 249000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | LV-070 | Install LV Control and Interlock Wiring | Electrical Systems | LV Main Distribution | Not Started | 2026-11-02 08:00 | 2026-11-06 16:00 |  |  | 5 | 5 | 38 | No |  |  | 249000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | LV-080 | Complete LV Distribution Installation Inspection | Electrical Systems | LV Main Distribution | Not Started | 2026-12-22 08:00 | 2026-12-23 16:00 |  |  | 2 | 2 | 0 | Yes | 1 | 15 | 189000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | LV-090 | LV Main Distribution Ready for Pre-Commissioning | Electrical Systems | LV Main Distribution | Not Started | 2026-12-23 16:00 | 2026-12-23 16:00 |  |  | 0 | 0 | 0 | Yes | 1 | 16 | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | LVE-010 | Complete LV Pre-Energization Checks | Utility Connection & Energization | UPS & Critical Power Energization | Not Started | 2027-01-02 08:00 | 2027-01-02 16:00 |  |  | 1 | 1 | 0 | Yes | 10 | 9 | 75000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | LVE-020 | Verify LV Protection Settings | Utility Connection & Energization | UPS & Critical Power Energization | Not Started | 2027-01-04 08:00 | 2027-01-05 16:00 |  |  | 2 | 2 | 0 | Yes | 10 | 10 | 77000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | LVE-030 | Energize Main LV Switchgear | Utility Connection & Energization | UPS & Critical Power Energization | Not Started | 2027-01-06 08:00 | 2027-01-06 16:00 |  |  | 1 | 1 | 0 | Yes | 10 | 11 | 75000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | LVE-040 | Energize LV Distribution Boards | Utility Connection & Energization | UPS & Critical Power Energization | Not Started | 2027-01-07 08:00 | 2027-01-09 16:00 |  |  | 3 | 3 | 0 | Yes | 10 | 12 | 104000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | LVE-050 | Verify LV System Operation | Utility Connection & Energization | UPS & Critical Power Energization | Not Started | 2027-01-11 08:00 | 2027-01-12 16:00 |  |  | 2 | 2 | 0 | Yes | 10 | 13 | 77000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | LVE-060 | LV System Energized | Utility Connection & Energization | UPS & Critical Power Energization | Not Started | 2027-01-12 16:00 | 2027-01-12 16:00 |  |  | 0 | 0 | 0 | Yes | 10 | 14 | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | MCA-010 | Install Mechanical Equipment Drainage Connections | Mechanical & Cooling Systems | Mechanical Ancillary Systems | Not Started | 2026-10-22 08:00 | 2026-10-29 16:00 |  |  | 7 | 7 | 73 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | MCA-020 | Install Condensate Drainage Systems | Mechanical & Cooling Systems | Mechanical Ancillary Systems | Not Started | 2026-10-22 08:00 | 2026-10-29 16:00 |  |  | 7 | 7 | 73 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | MCA-030 | Install Mechanical Equipment Identification and Labels | Mechanical & Cooling Systems | Mechanical Ancillary Systems | Not Started | 2026-09-07 08:00 | 2026-09-11 16:00 |  |  | 5 | 5 | 114 | No |  |  | 185000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | MCA-040 | Complete Mechanical Equipment Fire-Stopping | Mechanical & Cooling Systems | Mechanical Ancillary Systems | Not Started | 2026-10-14 08:00 | 2026-10-19 16:00 |  |  | 5 | 5 | 82 | No |  |  | 115000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | MCA-050 | Complete Mechanical Plant Access and Maintenance Provisions | Mechanical & Cooling Systems | Mechanical Ancillary Systems | Not Started | 2026-09-07 08:00 | 2026-09-11 16:00 |  |  | 5 | 5 | 114 | No |  |  | 115000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | MCA-060 | Complete Mechanical Installation Inspection | Mechanical & Cooling Systems | Mechanical Ancillary Systems | Not Started | 2026-10-30 08:00 | 2026-11-02 16:00 |  |  | 3 | 3 | 73 | No |  |  | 158000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | MCA-070 | Mechanical Systems Installation Complete | Mechanical & Cooling Systems | Mechanical Ancillary Systems | Not Started | 2026-11-02 16:00 | 2026-11-02 16:00 |  |  | 0 | 0 | 73 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | MCI-010 | Install Mechanical Control Panels | Mechanical & Cooling Systems | Mechanical Controls & Instrumentation | Not Started | 2026-10-22 08:00 | 2026-10-27 16:00 |  |  | 5 | 5 | 40 | No |  |  | 185000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | MCI-020 | Install Temperature Sensors | Mechanical & Cooling Systems | Mechanical Controls & Instrumentation | Not Started | 2026-10-24 08:00 | 2026-10-31 16:00 |  |  | 7 | 7 | 43 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | MCI-030 | Install Pressure Sensors | Mechanical & Cooling Systems | Mechanical Controls & Instrumentation | Not Started | 2026-10-24 08:00 | 2026-10-31 16:00 |  |  | 7 | 7 | 43 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | MCI-040 | Install Flow Measurement Devices | Mechanical & Cooling Systems | Mechanical Controls & Instrumentation | Not Started | 2026-10-24 08:00 | 2026-10-31 16:00 |  |  | 7 | 7 | 43 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | MCI-050 | Install Control Valves and Actuators | Mechanical & Cooling Systems | Mechanical Controls & Instrumentation | Not Started | 2026-11-03 08:00 | 2026-11-13 16:00 |  |  | 10 | 10 | 32 | No |  |  | 227000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | MCI-060 | Complete Mechanical Controls Field Wiring | Mechanical & Cooling Systems | Mechanical Controls & Instrumentation | Not Started | 2026-11-14 08:00 | 2026-11-25 16:00 |  |  | 10 | 10 | 32 | No |  |  | 142000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | MCI-070 | Complete BMS Interface Connections | Mechanical & Cooling Systems | Mechanical Controls & Instrumentation | Not Started | 2026-11-26 08:00 | 2026-12-03 16:00 |  |  | 7 | 7 | 32 | No |  |  | 128000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | MCI-080 | Inspect Mechanical Controls and Instrumentation | Mechanical & Cooling Systems | Mechanical Controls & Instrumentation | Not Started | 2026-12-04 08:00 | 2026-12-07 16:00 |  |  | 3 | 3 | 32 | No |  |  | 119000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | MCI-090 | Mechanical Controls Ready for Pre-Commissioning | Mechanical & Cooling Systems | Mechanical Controls & Instrumentation | Not Started | 2026-12-07 16:00 | 2026-12-07 16:00 |  |  | 0 | 0 | 32 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | MEC-CX-010 | Commission Chillers and Heat Rejection Equipment | Testing & Commissioning | Mechanical & Cooling Commissioning | Not Started | 2027-01-30 08:00 | 2027-02-04 16:00 |  |  | 5 | 5 | 2 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | MEC-CX-020 | Commission Cooling Pumps | Testing & Commissioning | Mechanical & Cooling Commissioning | Not Started | 2027-01-30 08:00 | 2027-02-04 16:00 |  |  | 5 | 5 | 2 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | MEC-CX-030 | Commission Chilled Water System | Testing & Commissioning | Mechanical & Cooling Commissioning | Not Started | 2027-01-30 08:00 | 2027-02-04 16:00 |  |  | 5 | 5 | 2 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | MEC-CX-040 | Commission CRAH CRAC Systems | Testing & Commissioning | Mechanical & Cooling Commissioning | Not Started | 2027-01-30 08:00 | 2027-02-04 16:00 |  |  | 5 | 5 | 2 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | MEC-CX-050 | Perform Air and Water Balancing | Testing & Commissioning | Mechanical & Cooling Commissioning | Not Started | 2027-02-05 08:00 | 2027-02-10 16:00 |  |  | 5 | 5 | 2 | No |  |  | 34000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | MEC-CX-060 | Verify Cooling System Controls | Testing & Commissioning | Mechanical & Cooling Commissioning | Not Started | 2027-02-11 08:00 | 2027-02-12 16:00 |  |  | 2 | 2 | 2 | No |  |  | 26000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | MEC-CX-070 | Mechanical Systems Functional Testing Complete | Testing & Commissioning | Mechanical & Cooling Commissioning | Not Started | 2027-02-12 16:00 | 2027-02-12 16:00 |  |  | 0 | 0 | 2 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | MEC-D-010 | Develop Mechanical Design Criteria | Design & Engineering | Mechanical & Cooling Design | Completed | 2026-01-13 08:00 | 2026-01-19 16:00 | 2026-01-13 08:00 | 2026-01-21 16:00 | 5 | 0 |  | No |  |  | 111000 | 111000 | 111000 | 114880.57 | -3880.57 | 0 | 0.96622 | 1
Update 01 | 2026-01-31 17:00 | MEC-D-020 | Develop Cooling Load Calculations | Design & Engineering | Mechanical & Cooling Design | In Progress | 2026-01-20 08:00 | 2026-02-02 16:00 | 2026-01-21 08:00 |  | 10 | 2 | 39 | No |  |  | 136000 | 116025 | 108800 | 114317.61 | -5517.61 | -7225 | 0.95173 | 0.93773
Update 01 | 2026-01-31 17:00 | MEC-D-030 | Develop Cooling Plant Design | Design & Engineering | Mechanical & Cooling Design | Not Started | 2026-02-04 08:00 | 2026-02-24 16:00 |  |  | 15 | 15 | 39 | No |  |  | 154000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | MEC-D-040 | Develop Chilled Water Distribution Design | Design & Engineering | Mechanical & Cooling Design | Not Started | 2026-02-11 08:00 | 2026-03-03 16:00 |  |  | 15 | 15 | 39 | No |  |  | 154000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | MEC-D-050 | Develop CRAH CRAC System Design | Design & Engineering | Mechanical & Cooling Design | Not Started | 2026-02-04 08:00 | 2026-02-17 16:00 |  |  | 10 | 10 | 44 | No |  |  | 136000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | MEC-D-060 | Develop Ventilation and Exhaust Design | Design & Engineering | Mechanical & Cooling Design | Not Started | 2026-02-05 08:00 | 2026-02-18 16:00 |  |  | 10 | 10 | 43 | No |  |  | 136000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | MEC-D-070 | Develop Mechanical Controls Requirements | Design & Engineering | Mechanical & Cooling Design | Not Started | 2026-02-18 08:00 | 2026-03-03 16:00 |  |  | 10 | 10 | 39 | No |  |  | 79000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | MEC-D-080 | Mechanical Design Review | Design & Engineering | Mechanical & Cooling Design | Not Started | 2026-03-04 08:00 | 2026-03-12 16:00 |  |  | 7 | 7 | 39 | No |  |  | 20000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | MEC-D-090 | Mechanical Design Approved | Design & Engineering | Mechanical & Cooling Design | Not Started | 2026-03-12 16:00 | 2026-03-12 16:00 |  |  | 0 | 0 | 39 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | MMC-010 | Install Mechanical Monitoring Interfaces | Controls, BMS & DCIM | Mechanical Monitoring & Controls | Not Started | 2026-12-08 08:00 | 2026-12-11 16:00 |  |  | 4 | 4 | 32 | No |  |  | 15000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | MMC-020 | Connect Chiller Monitoring Points | Controls, BMS & DCIM | Mechanical Monitoring & Controls | Not Started | 2026-09-23 08:00 | 2026-09-28 16:00 |  |  | 5 | 5 | 96 | No |  |  | 16000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | MMC-030 | Connect Pump Monitoring Points | Controls, BMS & DCIM | Mechanical Monitoring & Controls | Not Started | 2026-09-16 08:00 | 2026-09-21 16:00 |  |  | 5 | 5 | 102 | No |  |  | 16000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | MMC-040 | Connect CRAH CRAC Monitoring Points | Controls, BMS & DCIM | Mechanical Monitoring & Controls | Not Started | 2026-11-05 08:00 | 2026-11-10 16:00 |  |  | 5 | 5 | 59 | No |  |  | 16000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | MMC-050 | Connect Cooling Sensors to BMS | Controls, BMS & DCIM | Mechanical Monitoring & Controls | Not Started | 2026-11-17 08:00 | 2026-11-21 16:00 |  |  | 5 | 5 | 49 | No |  |  | 79000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | MMC-060 | Verify Mechanical Control Wiring | Controls, BMS & DCIM | Mechanical Monitoring & Controls | Not Started | 2026-12-12 08:00 | 2026-12-14 16:00 |  |  | 2 | 2 | 32 | No |  |  | 60000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | MMC-070 | Mechanical Monitoring Ready for Pre-Commissioning | Controls, BMS & DCIM | Mechanical Monitoring & Controls | Not Started | 2026-12-14 16:00 | 2026-12-14 16:00 |  |  | 0 | 0 | 32 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | MOB-010 | Mobilize Project Team to Site | Enabling & Site Works | Mobilization & Temporary Facilities | Completed | 2026-01-06 08:00 | 2026-01-10 16:00 | 2026-01-06 08:00 | 2026-01-10 16:00 | 5 | 0 |  | No |  |  | 87000 | 87000 | 87000 | 85304.34 | 1695.66 | 0 | 1.0199 | 1
Update 01 | 2026-01-31 17:00 | MOB-020 | Establish Site Offices and Welfare Facilities | Enabling & Site Works | Mobilization & Temporary Facilities | Completed | 2026-01-12 08:00 | 2026-01-16 16:00 | 2026-01-12 08:00 | 2026-01-16 16:00 | 5 | 0 |  | No |  |  | 87000 | 87000 | 87000 | 86275.79 | 724.21 | 0 | 1.0084 | 1
Update 01 | 2026-01-31 17:00 | MOB-030 | Install Temporary Site Fencing and Hoarding | Enabling & Site Works | Mobilization & Temporary Facilities | Completed | 2026-01-12 08:00 | 2026-01-16 16:00 | 2026-01-12 08:00 | 2026-01-16 16:00 | 5 | 0 |  | No |  |  | 116000 | 116000 | 116000 | 115391.52 | 608.48 | 0 | 1.0053 | 1
Update 01 | 2026-01-31 17:00 | MOB-040 | Establish Temporary Storage and Laydown Areas | Enabling & Site Works | Mobilization & Temporary Facilities | Completed | 2026-01-12 08:00 | 2026-01-16 16:00 | 2026-01-12 08:00 | 2026-01-16 16:00 | 5 | 0 |  | No |  |  | 87000 | 87000 | 87000 | 87333.33 | -333.33 | 0 | 0.99618 | 1
Update 01 | 2026-01-31 17:00 | MOB-050 | Establish Site Security and Access Control | Enabling & Site Works | Mobilization & Temporary Facilities | Completed | 2026-01-12 08:00 | 2026-01-16 16:00 | 2026-01-12 08:00 | 2026-01-16 16:00 | 5 | 0 |  | No |  |  | 87000 | 87000 | 87000 | 85311.94 | 1688.06 | 0 | 1.0198 | 1
Update 01 | 2026-01-31 17:00 | MOB-060 | Site Mobilization Complete | Enabling & Site Works | Mobilization & Temporary Facilities | Not Started | 2026-02-14 08:00 | 2026-02-14 08:00 |  |  | 0 | 0 | 32 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | MV-010 | Set Out MV Power Infrastructure | Electrical Systems | Utility / MV Power Infrastructure | Not Started | 2026-05-19 08:00 | 2026-05-20 16:00 |  |  | 2 | 2 | 139 | No |  |  | 118000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | MV-020 | Install MV Cable Duct Banks | Electrical Systems | Utility / MV Power Infrastructure | Not Started | 2026-05-21 08:00 | 2026-06-06 16:00 |  |  | 15 | 15 | 139 | No |  |  | 352000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | MV-030 | Install MV Cable Chambers and Pull Pits | Electrical Systems | Utility / MV Power Infrastructure | Not Started | 2026-05-27 08:00 | 2026-06-06 16:00 |  |  | 10 | 10 | 139 | No |  |  | 307000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | MV-040 | Install Incoming MV Cables | Electrical Systems | Utility / MV Power Infrastructure | Not Started | 2026-06-08 08:00 | 2026-06-18 16:00 |  |  | 10 | 10 | 139 | No |  |  | 307000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | MV-050 | Terminate Incoming MV Cables | Electrical Systems | Utility / MV Power Infrastructure | Not Started | 2026-06-19 08:00 | 2026-06-24 16:00 |  |  | 5 | 5 | 139 | No |  |  | 249000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | MV-060 | Test Incoming MV Cable System | Electrical Systems | Utility / MV Power Infrastructure | Not Started | 2026-06-25 08:00 | 2026-06-27 16:00 |  |  | 3 | 3 | 139 | No |  |  | 214000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | MV-070 | MV Power Infrastructure Ready | Electrical Systems | Utility / MV Power Infrastructure | Not Started | 2026-06-27 16:00 | 2026-06-27 16:00 |  |  | 0 | 0 | 139 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | MVE-010 | Complete MV Pre-Energization Checks | Utility Connection & Energization | MV System Energization | Not Started | 2026-11-16 08:00 | 2026-11-17 16:00 |  |  | 2 | 2 | 26 | No |  |  | 92000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | MVE-020 | Verify MV Protection Settings | Utility Connection & Energization | MV System Energization | Not Started | 2026-11-18 08:00 | 2026-11-19 16:00 |  |  | 2 | 2 | 26 | No |  |  | 77000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | MVE-030 | Obtain MV Energization Permit | Utility Connection & Energization | MV System Energization | Not Started | 2026-11-20 08:00 | 2026-11-21 16:00 |  |  | 2 | 2 | 26 | No |  |  | 92000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | MVE-040 | Energize Incoming MV System | Utility Connection & Energization | MV System Energization | Not Started | 2026-11-23 08:00 | 2026-11-23 16:00 |  |  | 1 | 1 | 26 | No |  |  | 75000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | MVE-050 | Verify MV System Operation | Utility Connection & Energization | MV System Energization | Not Started | 2026-11-24 08:00 | 2026-11-25 16:00 |  |  | 2 | 2 | 26 | No |  |  | 77000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | MVE-060 | MV System Energized | Utility Connection & Energization | MV System Energization | Not Started | 2026-11-25 16:00 | 2026-11-25 16:00 |  |  | 0 | 0 | 26 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | MVSG-010 | Prepare MV Switchgear Room for Installation | Electrical Systems | MV Switchgear | Not Started | 2026-10-10 08:00 | 2026-10-13 16:00 |  |  | 3 | 3 | 37 | No |  |  | 214000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | MVSG-020 | Receive and Inspect MV Switchgear | Electrical Systems | MV Switchgear | Not Started | 2026-10-24 08:00 | 2026-10-26 16:00 |  |  | 2 | 2 | 26 | No |  |  | 142000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | MVSG-030 | Position and Install MV Switchgear | Electrical Systems | MV Switchgear | Not Started | 2026-10-27 08:00 | 2026-10-31 16:00 |  |  | 5 | 5 | 26 | No |  |  | 249000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | MVSG-040 | Assemble MV Switchgear Sections | Electrical Systems | MV Switchgear | Not Started | 2026-11-02 08:00 | 2026-11-06 16:00 |  |  | 5 | 5 | 26 | No |  |  | 156000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | MVSG-050 | Install MV Switchgear Control Wiring | Electrical Systems | MV Switchgear | Not Started | 2026-11-04 08:00 | 2026-11-09 16:00 |  |  | 5 | 5 | 29 | No |  |  | 249000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | MVSG-060 | Terminate MV Power Cables | Electrical Systems | MV Switchgear | Not Started | 2026-11-07 08:00 | 2026-11-12 16:00 |  |  | 5 | 5 | 26 | No |  |  | 249000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | MVSG-070 | Complete MV Switchgear Installation Inspection | Electrical Systems | MV Switchgear | Not Started | 2026-11-13 08:00 | 2026-11-14 16:00 |  |  | 2 | 2 | 26 | No |  |  | 189000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | MVSG-080 | MV Switchgear Ready for Pre-Commissioning | Electrical Systems | MV Switchgear | Not Started | 2026-11-14 16:00 | 2026-11-14 16:00 |  |  | 0 | 0 | 26 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | OMM-010 | Compile Electrical O&M Manuals | Client Acceptance & Handover | O&M Manuals | Not Started | 2026-12-14 08:00 | 2026-12-25 16:00 |  |  | 10 | 10 | 93 | No |  |  | 35000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | OMM-020 | Compile Mechanical O&M Manuals | Client Acceptance & Handover | O&M Manuals | Not Started | 2026-08-28 08:00 | 2026-09-10 16:00 |  |  | 10 | 10 | 169 | No |  |  | 35000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | OMM-030 | Compile Fire and Life Safety O&M Manuals | Client Acceptance & Handover | O&M Manuals | Not Started | 2026-06-10 08:00 | 2026-06-23 16:00 |  |  | 10 | 10 | 226 | No |  |  | 35000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | OMM-040 | Compile BMS and DCIM O&M Manuals | Client Acceptance & Handover | O&M Manuals | Not Started | 2026-08-07 08:00 | 2026-08-20 16:00 |  |  | 10 | 10 | 184 | No |  |  | 35000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | OMM-050 | Submit Final O&M Manuals | Client Acceptance & Handover | O&M Manuals | Not Started | 2026-12-28 08:00 | 2027-01-08 16:00 |  |  | 10 | 10 | 93 | No |  |  | 18000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | PAR-010 | Set Out Internal Partitions | Building Envelope | Internal Partitions & Fire-Rated Enclosures | Not Started | 2026-09-14 08:00 | 2026-09-17 16:00 |  |  | 4 | 4 | 67 | No |  |  | 77000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | PAR-020 | Install Internal Partition Framing | Building Envelope | Internal Partitions & Fire-Rated Enclosures | Not Started | 2026-09-18 08:00 | 2026-09-26 16:00 |  |  | 8 | 8 | 67 | No |  |  | 152000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | PAR-030 | Install Fire-Rated Wall Systems | Building Envelope | Internal Partitions & Fire-Rated Enclosures | Not Started | 2026-09-22 08:00 | 2026-09-28 16:00 |  |  | 6 | 6 | 67 | No |  |  | 140000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | PAR-040 | Construct Electrical Room Fire-Rated Enclosures | Building Envelope | Internal Partitions & Fire-Rated Enclosures | Not Started | 2026-09-24 08:00 | 2026-10-02 16:00 |  |  | 8 | 8 | 69 | No |  |  | 152000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | PAR-050 | Construct UPS and Battery Room Fire-Rated Enclosures | Building Envelope | Internal Partitions & Fire-Rated Enclosures | Not Started | 2026-09-24 08:00 | 2026-10-02 16:00 |  |  | 8 | 8 | 69 | No |  |  | 152000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | PAR-060 | Construct Data Hall Fire-Rated Enclosures | Building Envelope | Internal Partitions & Fire-Rated Enclosures | Not Started | 2026-09-24 08:00 | 2026-10-05 16:00 |  |  | 10 | 10 | 67 | No |  |  | 163000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | PAR-070 | Install Fire-Stopping at Service Penetrations | Building Envelope | Internal Partitions & Fire-Rated Enclosures | Not Started | 2026-09-30 08:00 | 2026-10-05 16:00 |  |  | 5 | 5 | 67 | No |  |  | 132000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | PAR-080 | Inspect Fire-Rated Partitions and Enclosures | Building Envelope | Internal Partitions & Fire-Rated Enclosures | Not Started | 2026-10-06 08:00 | 2026-10-07 16:00 |  |  | 2 | 2 | 67 | No |  |  | 75000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | PAR-090 | Internal Partitions and Fire-Rated Enclosures Complete | Building Envelope | Internal Partitions & Fire-Rated Enclosures | Not Started | 2026-10-08 08:00 | 2026-10-08 08:00 |  |  | 0 | 0 | 67 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | PC-010 | Develop Project Controls Procedures | Project Management & Controls | Project Controls | Completed | 2026-01-05 08:00 | 2026-01-09 16:00 | 2026-01-05 08:00 | 2026-01-09 16:00 | 5 | 0 |  | No |  |  | 293000 | 293000 | 293000 | 295604.87 | -2604.87 | 0 | 0.99119 | 1
Update 01 | 2026-01-31 17:00 | PC-020 | Develop Detailed Baseline Programme | Project Management & Controls | Project Controls | Completed | 2026-01-12 08:00 | 2026-01-30 16:00 | 2026-01-12 08:00 | 2026-01-30 16:00 | 15 | 0 |  | No |  |  | 408000 | 408000 | 408000 | 408250.99 | -250.99 | 0 | 0.99939 | 1
Update 01 | 2026-01-31 17:00 | PC-030 | Baseline Schedule Review | Project Management & Controls | Project Controls | Not Started | 2026-02-02 08:00 | 2026-02-06 16:00 |  |  | 5 | 5 | 26 | No |  |  | 130000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | PC-040 | Baseline Schedule Approval | Project Management & Controls | Project Controls | Not Started | 2026-02-09 08:00 | 2026-02-13 16:00 |  |  | 5 | 5 | 26 | No |  |  | 195000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | PC-050 | Baseline Programme Approved | Project Management & Controls | Project Controls | Not Started | 2026-02-13 16:00 | 2026-02-13 16:00 |  |  | 0 | 0 | 26 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | PM-001 | Notice to Proceed | Project Management & Controls | Project Management | Completed | 2026-02-02 08:00 | 2026-02-02 08:00 | 2026-01-05 | 2026-01-05 | 0 | 0 |  | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | PM-010 | Project Kick-Off Meeting | Project Management & Controls | Project Management | Completed | 2026-01-05 08:00 | 2026-01-05 16:00 | 2026-01-05 08:00 | 2026-01-05 16:00 | 1 | 0 |  | No |  |  | 80000 | 80000 | 80000 | 80609.78 | -609.78 | 0 | 0.99244 | 1
Update 01 | 2026-01-31 17:00 | PM-020 | Establish Project Organization | Project Management & Controls | Project Management | Completed | 2026-01-06 08:00 | 2026-01-12 16:00 | 2026-01-06 08:00 | 2026-01-12 16:00 | 5 | 0 |  | No |  |  | 293000 | 293000 | 293000 | 295755.52 | -2755.52 | 0 | 0.99068 | 1
Update 01 | 2026-01-31 17:00 | PM-030 | Establish Project Management Procedures | Project Management & Controls | Project Management | Completed | 2026-01-06 08:00 | 2026-01-19 16:00 | 2026-01-06 08:00 | 2026-01-19 16:00 | 10 | 0 |  | No |  |  | 361000 | 361000 | 361000 | 360151.77 | 848.23 | 0 | 1.0024 | 1
Update 01 | 2026-01-31 17:00 | PMP-010 | Prepare Pump Bases for Installation | Mechanical & Cooling Systems | Pumps & Pumping Systems | Not Started | 2026-08-25 08:00 | 2026-08-27 16:00 |  |  | 3 | 3 | 53 | No |  |  | 158000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | PMP-020 | Receive and Inspect Pumps | Mechanical & Cooling Systems | Pumps & Pumping Systems | Not Started | 2026-08-28 08:00 | 2026-08-29 16:00 |  |  | 2 | 2 | 53 | No |  |  | 105000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | PMP-030 | Install Primary Cooling Pumps | Mechanical & Cooling Systems | Pumps & Pumping Systems | Not Started | 2026-08-31 08:00 | 2026-09-04 16:00 |  |  | 5 | 5 | 53 | No |  |  | 185000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | PMP-040 | Install Secondary Cooling Pumps | Mechanical & Cooling Systems | Pumps & Pumping Systems | Not Started | 2026-08-31 08:00 | 2026-09-04 16:00 |  |  | 5 | 5 | 53 | No |  |  | 185000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | PMP-050 | Install Pump Suction and Discharge Connections | Mechanical & Cooling Systems | Pumps & Pumping Systems | Not Started | 2026-09-05 08:00 | 2026-09-12 16:00 |  |  | 7 | 7 | 53 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | PMP-060 | Install Pump Electrical Connections | Mechanical & Cooling Systems | Pumps & Pumping Systems | Not Started | 2026-09-02 08:00 | 2026-09-07 16:00 |  |  | 5 | 5 | 107 | No |  |  | 185000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | PMP-070 | Install Pump Controls and Instrumentation | Mechanical & Cooling Systems | Pumps & Pumping Systems | Not Started | 2026-09-02 08:00 | 2026-09-07 16:00 |  |  | 5 | 5 | 107 | No |  |  | 185000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | PMP-080 | Inspect Pumping System Installation | Mechanical & Cooling Systems | Pumps & Pumping Systems | Not Started | 2026-09-14 08:00 | 2026-09-15 16:00 |  |  | 2 | 2 | 102 | No |  |  | 140000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | PMP-090 | Pumping Systems Ready for Pre-Commissioning | Mechanical & Cooling Systems | Pumps & Pumping Systems | Not Started | 2026-09-15 16:00 | 2026-09-15 16:00 |  |  | 0 | 0 | 102 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | PRE-010 | Complete Electrical Pre-Commissioning Inspections | Testing & Commissioning | Pre-Commissioning & Inspections | Not Started | 2027-01-25 08:00 | 2027-01-26 16:00 |  |  | 2 | 2 | 2 | No |  |  | 31000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | PRE-020 | Complete Mechanical Pre-Commissioning Inspections | Testing & Commissioning | Pre-Commissioning & Inspections | Not Started | 2026-12-08 08:00 | 2026-12-09 16:00 |  |  | 2 | 2 | 43 | No |  |  | 31000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | PRE-030 | Complete Fire System Pre-Commissioning Inspections | Testing & Commissioning | Pre-Commissioning & Inspections | Not Started | 2027-01-08 08:00 | 2027-01-09 16:00 |  |  | 2 | 2 | 16 | No |  |  | 31000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | PRE-040 | Complete BMS and Controls Pre-Commissioning Inspections | Testing & Commissioning | Pre-Commissioning & Inspections | Not Started | 2027-01-15 08:00 | 2027-01-16 16:00 |  |  | 2 | 2 | 10 | No |  |  | 31000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | PRE-050 | Complete Pre-Commissioning Punch List | Testing & Commissioning | Pre-Commissioning & Inspections | Not Started | 2027-01-27 08:00 | 2027-01-29 16:00 |  |  | 3 | 3 | 2 | No |  |  | 35000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | PRE-060 | Systems Ready for Functional Commissioning | Testing & Commissioning | Pre-Commissioning & Inspections | Not Started | 2027-01-29 16:00 | 2027-01-29 16:00 |  |  | 0 | 0 | 2 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | PRM-010 | Develop Project Procurement Plan | Procurement | Procurement Management | Completed | 2026-01-06 08:00 | 2026-01-12 16:00 | 2026-01-06 08:00 | 2026-01-12 16:00 | 5 | 0 |  | No |  |  | 89000 | 89000 | 89000 | 92523.96 | -3523.96 | 0 | 0.96191 | 1
Update 01 | 2026-01-31 17:00 | PRM-020 | Develop Procurement Schedule | Procurement | Procurement Management | Completed | 2026-01-13 08:00 | 2026-01-19 16:00 | 2026-01-13 08:00 | 2026-01-19 16:00 | 5 | 0 |  | No |  |  | 89000 | 89000 | 89000 | 93208.85 | -4208.85 | 0 | 0.95484 | 1
Update 01 | 2026-01-31 17:00 | PRM-030 | Establish Approved Vendor List | Procurement | Procurement Management | In Progress | 2026-01-20 08:00 | 2026-01-28 16:00 | 2026-01-21 08:00 |  | 7 | 3 | 127 | No |  |  | 49000 | 49000 | 28000 | 29917.05 | -1917.05 | -21000 | 0.93592 | 0.57143
Update 01 | 2026-01-31 17:00 | PRM-040 | Establish Procurement Tracking Register | Procurement | Procurement Management | Not Started | 2026-02-05 08:00 | 2026-02-18 16:00 |  |  | 10 | 10 | 127 | No |  |  | 55000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | PRM-050 | Procurement Strategy Approved | Procurement | Procurement Management | Not Started | 2026-02-19 08:00 | 2026-02-27 16:00 |  |  | 7 | 7 | 127 | No |  |  | 74000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | QA-010 | Develop Project Quality Plan | Project Management & Controls | Quality Management | Completed | 2026-01-05 08:00 | 2026-01-16 16:00 | 2026-01-05 08:00 | 2026-01-16 16:00 | 10 | 0 |  | No |  |  | 361000 | 361000 | 361000 | 359321.32 | 1678.68 | 0 | 1.0047 | 1
Update 01 | 2026-01-31 17:00 | QA-020 | Quality Plan Review | Project Management & Controls | Quality Management | Completed | 2026-01-19 08:00 | 2026-01-23 16:00 | 2026-01-19 08:00 | 2026-01-23 16:00 | 5 | 0 |  | No |  |  | 130000 | 130000 | 130000 | 130312.33 | -312.33 | 0 | 0.9976 | 1
Update 01 | 2026-01-31 17:00 | QA-030 | Quality Plan Approval | Project Management & Controls | Quality Management | Completed | 2026-01-26 08:00 | 2026-01-28 16:00 | 2026-01-26 08:00 | 2026-01-28 16:00 | 3 | 0 |  | No |  |  | 168000 | 168000 | 168000 | 169290.67 | -1290.67 | 0 | 0.99238 | 1
Update 01 | 2026-01-31 17:00 | RDA-010 | Prepare Site Road Subgrade | Enabling & Site Works | Site Roads & Access | Not Started | 2026-05-04 08:00 | 2026-05-08 16:00 |  |  | 5 | 5 | 271 | No |  |  | 87000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | RDA-020 | Install Road Subbase and Base Course | Enabling & Site Works | Site Roads & Access | Not Started | 2026-05-09 08:00 | 2026-05-16 16:00 |  |  | 7 | 7 | 271 | No |  |  | 128000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | RDA-030 | Construct Heavy Equipment Access Routes | Enabling & Site Works | Site Roads & Access | Not Started | 2026-05-18 08:00 | 2026-05-22 16:00 |  |  | 5 | 5 | 271 | No |  |  | 116000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | RDA-040 | Construct Permanent Internal Roads | Enabling & Site Works | Site Roads & Access | Not Started | 2026-05-23 08:00 | 2026-06-03 16:00 |  |  | 10 | 10 | 271 | No |  |  | 143000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | RDA-050 | Construct Kerbs and Hardstanding Areas | Enabling & Site Works | Site Roads & Access | Not Started | 2026-06-04 08:00 | 2026-06-11 16:00 |  |  | 7 | 7 | 271 | No |  |  | 128000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | RDA-060 | Complete Final Road Surfacing | Enabling & Site Works | Site Roads & Access | Not Started | 2026-06-12 08:00 | 2026-06-15 16:00 |  |  | 3 | 3 | 271 | No |  |  | 75000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | RDA-070 | Site Roads and Access Complete | Enabling & Site Works | Site Roads & Access | Not Started | 2026-06-16 08:00 | 2026-06-16 08:00 |  |  | 0 | 0 | 271 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | RFS-010 | Confirm Operational Readiness | Client Acceptance & Handover | Final Acceptance & Project Closeout | Not Started | 2027-07-13 08:00 | 2027-07-19 16:00 |  |  | 5 | 5 | 0 | Yes | 1 | 55 | 29000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | RFS-020 | Confirm Systems Acceptance | Client Acceptance & Handover | Final Acceptance & Project Closeout | Not Started | 2027-06-16 08:00 | 2027-06-22 16:00 |  |  | 5 | 5 | 19 | No |  |  | 29000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | RFS-030 | Confirm Documentation and Training Complete | Client Acceptance & Handover | Final Acceptance & Project Closeout | Not Started | 2027-05-11 16:00 | 2027-05-11 16:00 |  |  | 0 | 0 | 49 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | RFS-040 | Ready for Service | Client Acceptance & Handover | Final Acceptance & Project Closeout | Not Started | 2027-07-19 16:00 | 2027-07-19 16:00 |  |  | 0 | 0 | 0 | Yes | 1 | 56 | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | RFS-050 | Complete Roof Structural Connections | Civil & Structural Works | Roof Structure | Not Started | 2026-08-25 08:00 | 2026-08-29 16:00 |  |  | 5 | 5 | 32 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | RFS-060 | Inspect Roof Structure | Civil & Structural Works | Roof Structure | Not Started | 2026-08-31 08:00 | 2026-09-02 16:00 |  |  | 3 | 3 | 32 | No |  |  | 175000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | RFS-070 | Roof Structure Complete | Civil & Structural Works | Roof Structure | Not Started | 2026-09-03 08:00 | 2026-09-03 08:00 |  |  | 0 | 0 | 32 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ROF-010 | Prepare Roof Deck for Roofing Works | Building Envelope | Roofing System | Not Started | 2026-09-03 08:00 | 2026-09-05 16:00 |  |  | 3 | 3 | 32 | No |  |  | 113000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ROF-020 | Install Roof Vapour Control Layer | Building Envelope | Roofing System | Not Started | 2026-09-07 08:00 | 2026-09-11 16:00 |  |  | 5 | 5 | 32 | No |  |  | 132000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ROF-030 | Install Roof Insulation | Building Envelope | Roofing System | Not Started | 2026-09-09 08:00 | 2026-09-14 16:00 |  |  | 5 | 5 | 32 | No |  |  | 132000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ROF-040 | Install Roofing Membrane | Building Envelope | Roofing System | Not Started | 2026-09-11 08:00 | 2026-09-19 16:00 |  |  | 8 | 8 | 32 | No |  |  | 152000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ROF-050 | Install Roof Flashings and Upstands | Building Envelope | Roofing System | Not Started | 2026-09-15 08:00 | 2026-09-19 16:00 |  |  | 5 | 5 | 32 | No |  |  | 132000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ROF-060 | Seal Roof Equipment Penetrations | Building Envelope | Roofing System | Not Started | 2026-09-21 08:00 | 2026-09-23 16:00 |  |  | 3 | 3 | 32 | No |  |  | 113000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ROF-070 | Inspect and Test Roofing System | Building Envelope | Roofing System | Not Started | 2026-09-24 08:00 | 2026-09-25 16:00 |  |  | 2 | 2 | 32 | No |  |  | 100000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | ROF-080 | Roofing System Complete | Building Envelope | Roofing System | Not Started | 2026-09-26 08:00 | 2026-09-26 08:00 |  |  | 0 | 0 | 32 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | RRT-010 | Develop Reliability Test Plan | Testing & Commissioning | Reliability / Resilience Testing | In Progress | 2026-01-23 08:00 | 2026-02-03 16:00 | 2026-01-23 08:00 |  | 10 | 4 | 343 | No |  |  | 50000 | 36948.5294 | 30000 | 29657.46 | 342.54 | -6948.5294 | 1.0115 | 0.81194
Update 01 | 2026-01-31 17:00 | RRT-020 | Perform Utility Loss Resilience Test | Testing & Commissioning | Reliability / Resilience Testing | Not Started | 2027-03-13 08:00 | 2027-03-24 16:00 |  |  | 10 | 10 | 0 | Yes | 1 | 37 | 50000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | RRT-030 | Perform Generator Failure Simulation | Testing & Commissioning | Reliability / Resilience Testing | Not Started | 2027-03-13 08:00 | 2027-03-18 16:00 |  |  | 5 | 5 | 5 | No |  |  | 34000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | RRT-040 | Perform UPS Failure Simulation | Testing & Commissioning | Reliability / Resilience Testing | Not Started | 2027-03-13 08:00 | 2027-03-18 16:00 |  |  | 5 | 5 | 5 | No |  |  | 34000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | RRT-050 | Perform Cooling Failure Simulation | Testing & Commissioning | Reliability / Resilience Testing | Not Started | 2027-03-13 08:00 | 2027-03-18 16:00 |  |  | 5 | 5 | 5 | No |  |  | 34000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | RRT-060 | Complete Reliability Demonstration | Testing & Commissioning | Reliability / Resilience Testing | Not Started | 2027-03-25 08:00 | 2027-03-26 16:00 |  |  | 2 | 2 | 0 | Yes | 1 | 38 | 31000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | RRT-070 | Reliability Testing Complete | Testing & Commissioning | Reliability / Resilience Testing | Not Started | 2027-03-26 16:00 | 2027-03-26 16:00 |  |  | 0 | 0 | 0 | Yes | 1 | 39 | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SCP-010 | Clear Existing Vegetation and Obstructions | Enabling & Site Works | Site Clearance & Preparation | Not Started | 2026-02-26 08:00 | 2026-03-05 16:00 |  |  | 7 | 7 | 32 | No |  |  | 96000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SCP-020 | Remove Existing Surface Materials | Enabling & Site Works | Site Clearance & Preparation | Not Started | 2026-03-06 08:00 | 2026-03-11 16:00 |  |  | 5 | 5 | 32 | No |  |  | 87000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SCP-030 | Remove or Divert Existing Minor Services | Enabling & Site Works | Site Clearance & Preparation | Not Started | 2026-03-12 08:00 | 2026-03-19 16:00 |  |  | 7 | 7 | 32 | No |  |  | 96000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SCP-040 | Strip and Stockpile Topsoil | Enabling & Site Works | Site Clearance & Preparation | Not Started | 2026-03-20 08:00 | 2026-03-25 16:00 |  |  | 5 | 5 | 32 | No |  |  | 87000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SCP-050 | Prepare Site for Earthworks | Enabling & Site Works | Site Clearance & Preparation | Not Started | 2026-03-26 08:00 | 2026-03-28 16:00 |  |  | 3 | 3 | 32 | No |  |  | 75000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SCP-060 | Site Clearance Complete | Enabling & Site Works | Site Clearance & Preparation | Not Started | 2026-03-30 08:00 | 2026-03-30 08:00 |  |  | 0 | 0 | 32 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SD-010 | Establish Shop Drawing Schedule | Design & Engineering | Shop Drawings & Technical Approvals | Completed | 2026-01-20 08:00 | 2026-01-26 16:00 | 2026-01-20 08:00 | 2026-01-26 16:00 | 5 | 0 |  | No |  |  | 111000 | 111000 | 111000 | 117111.14 | -6111.14 | 0 | 0.94782 | 1
Update 01 | 2026-01-31 17:00 | SD-020 | Prepare Civil and Structural Shop Drawings | Design & Engineering | Shop Drawings & Technical Approvals | Not Started | 2026-03-18 08:00 | 2026-04-07 16:00 |  |  | 15 | 15 | 149 | No |  |  | 154000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SD-030 | Prepare Architectural Shop Drawings | Design & Engineering | Shop Drawings & Technical Approvals | Not Started | 2026-02-26 08:00 | 2026-03-18 16:00 |  |  | 15 | 15 | 163 | No |  |  | 154000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SD-040 | Prepare Electrical Shop Drawings | Design & Engineering | Shop Drawings & Technical Approvals | Not Started | 2026-03-30 08:00 | 2026-04-24 16:00 |  |  | 20 | 20 | 136 | No |  |  | 168000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SD-050 | Prepare Mechanical Shop Drawings | Design & Engineering | Shop Drawings & Technical Approvals | Not Started | 2026-03-13 08:00 | 2026-04-09 16:00 |  |  | 20 | 20 | 147 | No |  |  | 168000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SD-060 | Prepare Fire and Life Safety Shop Drawings | Design & Engineering | Shop Drawings & Technical Approvals | Not Started | 2026-02-11 08:00 | 2026-03-03 16:00 |  |  | 15 | 15 | 174 | No |  |  | 154000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SD-070 | Prepare BMS DCIM and Controls Shop Drawings | Design & Engineering | Shop Drawings & Technical Approvals | Not Started | 2026-04-08 08:00 | 2026-04-28 16:00 |  |  | 15 | 15 | 134 | No |  |  | 154000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SD-080 | Consultant Review of Shop Drawings | Design & Engineering | Shop Drawings & Technical Approvals | Not Started | 2026-04-15 08:00 | 2026-04-28 16:00 |  |  | 10 | 10 | 134 | No |  |  | 23000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SD-090 | Resolve Shop Drawing Comments | Design & Engineering | Shop Drawings & Technical Approvals | Not Started | 2026-04-29 08:00 | 2026-05-12 16:00 |  |  | 10 | 10 | 134 | No |  |  | 136000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SD-100 | Technical Shop Drawings Approved | Design & Engineering | Shop Drawings & Technical Approvals | Not Started | 2026-05-12 16:00 | 2026-05-12 16:00 |  |  | 0 | 0 | 134 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SFD-010 | Install Environmental Sensors | Controls, BMS & DCIM | Sensors & Field Devices | Not Started | 2026-10-10 08:00 | 2026-10-15 16:00 |  |  | 5 | 5 | 79 | No |  |  | 126000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SFD-020 | Install Temperature and Humidity Sensors | Controls, BMS & DCIM | Sensors & Field Devices | Not Started | 2026-10-12 08:00 | 2026-10-16 16:00 |  |  | 5 | 5 | 79 | No |  |  | 126000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SFD-030 | Install Differential Pressure Sensors | Controls, BMS & DCIM | Sensors & Field Devices | Not Started | 2026-10-12 08:00 | 2026-10-16 16:00 |  |  | 5 | 5 | 79 | No |  |  | 126000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SFD-040 | Install Leak Detection Sensors | Controls, BMS & DCIM | Sensors & Field Devices | Not Started | 2026-10-12 08:00 | 2026-10-16 16:00 |  |  | 5 | 5 | 79 | No |  |  | 126000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SFD-050 | Install Energy Metering Devices | Controls, BMS & DCIM | Sensors & Field Devices | Not Started | 2026-10-12 08:00 | 2026-10-16 16:00 |  |  | 5 | 5 | 79 | No |  |  | 126000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SFD-060 | Terminate Sensor and Field Device Cabling | Controls, BMS & DCIM | Sensors & Field Devices | Not Started | 2026-11-12 08:00 | 2026-11-20 16:00 |  |  | 8 | 8 | 57 | No |  |  | 145000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SFD-070 | Sensors and Field Devices Ready for Testing | Controls, BMS & DCIM | Sensors & Field Devices | Not Started | 2026-11-20 16:00 | 2026-11-20 16:00 |  |  | 0 | 0 | 57 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SGI-010 | Prepare Generator Areas for Installation | Electrical Systems | Standby Generator System | Not Started | 2026-08-21 08:00 | 2026-08-24 16:00 |  |  | 3 | 3 | 118 | No |  |  | 214000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SGI-020 | Receive and Inspect Standby Generators | Electrical Systems | Standby Generator System | Not Started | 2026-12-12 08:00 | 2026-12-14 16:00 |  |  | 2 | 2 | 22 | No |  |  | 142000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SGI-030 | Position Standby Generators on Plinths | Electrical Systems | Standby Generator System | Not Started | 2026-12-15 08:00 | 2026-12-19 16:00 |  |  | 5 | 5 | 22 | No |  |  | 156000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SGI-040 | Install Generator Exhaust Systems | Electrical Systems | Standby Generator System | Not Started | 2026-12-21 08:00 | 2026-12-28 16:00 |  |  | 7 | 7 | 23 | No |  |  | 276000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SGI-050 | Install Generator Fuel System Connections | Electrical Systems | Standby Generator System | Not Started | 2026-12-21 08:00 | 2026-12-28 16:00 |  |  | 7 | 7 | 23 | No |  |  | 276000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SGI-060 | Install Generator Power Connections | Electrical Systems | Standby Generator System | Not Started | 2026-12-21 08:00 | 2026-12-25 16:00 |  |  | 5 | 5 | 25 | No |  |  | 249000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SGI-070 | Install Generator Control Connections | Electrical Systems | Standby Generator System | Not Started | 2026-12-21 08:00 | 2026-12-25 16:00 |  |  | 5 | 5 | 25 | No |  |  | 249000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SGI-080 | Complete Generator Installation Inspection | Electrical Systems | Standby Generator System | Not Started | 2026-12-29 08:00 | 2026-12-30 16:00 |  |  | 2 | 2 | 23 | No |  |  | 189000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SGI-090 | Standby Generators Ready for Pre-Commissioning | Electrical Systems | Standby Generator System | Not Started | 2026-12-30 16:00 | 2026-12-30 16:00 |  |  | 0 | 0 | 23 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SLB-010 | Prepare Ground Floor Subgrade | Civil & Structural Works | Ground Floor & Slabs | Not Started | 2026-07-25 08:00 | 2026-07-30 16:00 |  |  | 5 | 5 | 42 | No |  |  | 127000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SLB-020 | Install Subbase and Compact | Civil & Structural Works | Ground Floor & Slabs | Not Started | 2026-07-31 08:00 | 2026-08-05 16:00 |  |  | 5 | 5 | 42 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SLB-030 | Install Under-Slab Services | Civil & Structural Works | Ground Floor & Slabs | Not Started | 2026-08-06 08:00 | 2026-08-17 16:00 |  |  | 10 | 10 | 42 | No |  |  | 250000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SLB-040 | Install Damp-Proof Membrane | Civil & Structural Works | Ground Floor & Slabs | Not Started | 2026-08-18 08:00 | 2026-08-20 16:00 |  |  | 3 | 3 | 42 | No |  |  | 175000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SLB-050 | Install Ground Floor Reinforcement | Civil & Structural Works | Ground Floor & Slabs | Not Started | 2026-08-21 08:00 | 2026-08-29 16:00 |  |  | 8 | 8 | 42 | No |  |  | 234000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SLB-060 | Install Slab Embedded Items and Openings | Civil & Structural Works | Ground Floor & Slabs | Not Started | 2026-08-25 08:00 | 2026-08-29 16:00 |  |  | 5 | 5 | 42 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SLB-070 | Cast Ground Floor Slab | Civil & Structural Works | Ground Floor & Slabs | Not Started | 2026-08-31 08:00 | 2026-09-04 16:00 |  |  | 5 | 5 | 42 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SLB-080 | Cure Ground Floor Slab | Civil & Structural Works | Ground Floor & Slabs | Not Started | 2026-09-05 08:00 | 2026-09-12 16:00 |  |  | 7 | 7 | 42 | No |  |  | 225000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SLB-090 | Ground Floor Slab Complete | Civil & Structural Works | Ground Floor & Slabs | Not Started | 2026-09-14 08:00 | 2026-09-14 08:00 |  |  | 0 | 0 | 42 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SPR-010 | Install Sprinkler Main Pipework | Fire & Life Safety | Sprinkler System | Not Started | 2026-10-08 08:00 | 2026-10-19 16:00 |  |  | 10 | 10 | 71 | No |  |  | 101000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SPR-020 | Install Sprinkler Branch Pipework | Fire & Life Safety | Sprinkler System | Not Started | 2026-10-12 08:00 | 2026-10-22 16:00 |  |  | 10 | 10 | 71 | No |  |  | 101000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SPR-030 | Install Sprinkler Heads | Fire & Life Safety | Sprinkler System | Not Started | 2026-10-15 08:00 | 2026-10-23 16:00 |  |  | 8 | 8 | 71 | No |  |  | 95000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SPR-040 | Install Zone Control Assemblies | Fire & Life Safety | Sprinkler System | Not Started | 2026-10-10 08:00 | 2026-10-15 16:00 |  |  | 5 | 5 | 78 | No |  |  | 82000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SPR-050 | Pressure Test Sprinkler System | Fire & Life Safety | Sprinkler System | Not Started | 2026-10-24 08:00 | 2026-10-27 16:00 |  |  | 3 | 3 | 71 | No |  |  | 53000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SPR-060 | Flush Sprinkler System | Fire & Life Safety | Sprinkler System | Not Started | 2026-10-28 08:00 | 2026-11-02 16:00 |  |  | 5 | 5 | 71 | No |  |  | 51000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SPR-070 | Inspect Sprinkler Installation | Fire & Life Safety | Sprinkler System | Not Started | 2026-11-03 08:00 | 2026-11-04 16:00 |  |  | 2 | 2 | 71 | No |  |  | 63000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SPR-080 | Sprinkler System Ready for Pre-Commissioning | Fire & Life Safety | Sprinkler System | Not Started | 2026-11-04 16:00 | 2026-11-04 16:00 |  |  | 0 | 0 | 71 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | STR-010 | Mobilize Structural Steel Erection | Civil & Structural Works | Structural Frame | Not Started | 2026-07-25 08:00 | 2026-07-28 16:00 |  |  | 3 | 3 | 32 | No |  |  | 175000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | STR-020 | Erect Primary Structural Columns | Civil & Structural Works | Structural Frame | Not Started | 2026-07-29 08:00 | 2026-08-08 16:00 |  |  | 10 | 10 | 32 | No |  |  | 250000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | STR-030 | Erect Primary Structural Beams | Civil & Structural Works | Structural Frame | Not Started | 2026-08-03 08:00 | 2026-08-13 16:00 |  |  | 10 | 10 | 32 | No |  |  | 250000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | STR-040 | Install Secondary Structural Steel | Civil & Structural Works | Structural Frame | Not Started | 2026-08-07 08:00 | 2026-08-15 16:00 |  |  | 8 | 8 | 32 | No |  |  | 234000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | STR-050 | Install Structural Bracing | Civil & Structural Works | Structural Frame | Not Started | 2026-08-07 08:00 | 2026-08-12 16:00 |  |  | 5 | 5 | 35 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | STR-060 | Complete Bolting and Connections | Civil & Structural Works | Structural Frame | Not Started | 2026-08-17 08:00 | 2026-08-20 16:00 |  |  | 4 | 4 | 32 | No |  |  | 119000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | STR-070 | Structural Alignment and Inspection | Civil & Structural Works | Structural Frame | Not Started | 2026-08-21 08:00 | 2026-08-24 16:00 |  |  | 3 | 3 | 32 | No |  |  | 131000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | STR-080 | Structural Frame Complete | Civil & Structural Works | Structural Frame | Not Started | 2026-08-25 08:00 | 2026-08-25 08:00 |  |  | 0 | 0 | 32 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SUB-010 | Inspect Utility Substation Installation | Utility Connection & Energization | Utility Substation Readiness | Not Started | 2026-05-12 08:00 | 2026-05-13 16:00 |  |  | 2 | 2 | 177 | No |  |  | 123000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SUB-020 | Complete Substation Protection Testing | Utility Connection & Energization | Utility Substation Readiness | Not Started | 2026-05-14 08:00 | 2026-05-16 16:00 |  |  | 3 | 3 | 177 | No |  |  | 104000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SUB-030 | Complete Substation Metering Testing | Utility Connection & Energization | Utility Substation Readiness | Not Started | 2026-05-14 08:00 | 2026-05-16 16:00 |  |  | 3 | 3 | 177 | No |  |  | 104000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SUB-040 | Close Utility Substation Punch List | Utility Connection & Energization | Utility Substation Readiness | Not Started | 2026-05-18 08:00 | 2026-05-22 16:00 |  |  | 5 | 5 | 177 | No |  |  | 101000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SUB-050 | Utility Substation Ready for Energization | Utility Connection & Energization | Utility Substation Readiness | Not Started | 2026-05-22 16:00 | 2026-05-22 16:00 |  |  | 0 | 0 | 177 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SUR-010 | Establish Survey Control Points | Enabling & Site Works | Surveying & Setting Out | Not Started | 2026-02-14 08:00 | 2026-02-17 16:00 |  |  | 3 | 3 | 32 | No |  |  | 75000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SUR-020 | Conduct Existing Site Topographic Survey | Enabling & Site Works | Surveying & Setting Out | Not Started | 2026-02-18 08:00 | 2026-02-23 16:00 |  |  | 5 | 5 | 32 | No |  |  | 87000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SUR-030 | Verify Existing Site Levels and Boundaries | Enabling & Site Works | Surveying & Setting Out | Not Started | 2026-02-24 08:00 | 2026-02-25 16:00 |  |  | 2 | 2 | 32 | No |  |  | 66000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SUR-040 | Set Out Main Building Footprint | Enabling & Site Works | Surveying & Setting Out | Not Started | 2026-02-26 08:00 | 2026-02-28 16:00 |  |  | 3 | 3 | 91 | No |  |  | 75000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SUR-050 | Set Out External Infrastructure and Utility Routes | Enabling & Site Works | Surveying & Setting Out | Not Started | 2026-02-26 08:00 | 2026-02-28 16:00 |  |  | 3 | 3 | 91 | No |  |  | 75000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SUR-060 | Survey and Setting Out Complete | Enabling & Site Works | Surveying & Setting Out | Not Started | 2026-03-02 08:00 | 2026-03-02 08:00 |  |  | 0 | 0 | 91 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SWG-010 | Prepare MV/LV Switchgear Technical Submittal | Procurement | MV/LV Switchgear | Not Started | 2026-03-05 08:00 | 2026-03-13 16:00 |  |  | 7 | 7 | 31 | No |  |  | 186000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SWG-020 | MV/LV Switchgear Technical Submittal Approval | Procurement | MV/LV Switchgear | Not Started | 2026-03-30 08:00 | 2026-04-07 16:00 |  |  | 7 | 7 | 21 | No |  |  | 186000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SWG-030 | Issue Purchase Order - MV/LV Switchgear | Procurement | MV/LV Switchgear | Not Started | 2026-04-08 08:00 | 2026-04-10 16:00 |  |  | 3 | 3 | 21 | No |  |  | 240000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SWG-040 | Manufacture MV/LV Switchgear | Procurement | MV/LV Switchgear | Not Started | 2026-04-13 08:00 | 2026-09-25 16:00 |  |  | 120 | 120 | 21 | No |  |  | 4353000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SWG-050 | Factory Acceptance Test - MV/LV Switchgear | Procurement | MV/LV Switchgear | Not Started | 2026-09-28 08:00 | 2026-09-30 16:00 |  |  | 3 | 3 | 21 | No |  |  | 312000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SWG-060 | Ship MV/LV Switchgear | Procurement | MV/LV Switchgear | Not Started | 2026-10-01 08:00 | 2026-10-21 16:00 |  |  | 15 | 15 | 21 | No |  |  | 311000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | SWG-070 | Deliver MV/LV Switchgear to Site | Procurement | MV/LV Switchgear | Not Started | 2026-10-22 08:00 | 2026-10-23 16:00 |  |  | 2 | 2 | 21 | No |  |  | 170000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | TRE-010 | Complete Transformer Pre-Energization Checks | Utility Connection & Energization | LV System Energization | Not Started | 2026-12-26 08:00 | 2026-12-26 16:00 |  |  | 1 | 1 | 0 | Yes | 10 | 4 | 75000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | TRE-020 | Verify Transformer Protection and Controls | Utility Connection & Energization | LV System Energization | Not Started | 2026-12-28 08:00 | 2026-12-29 16:00 |  |  | 2 | 2 | 0 | Yes | 10 | 5 | 77000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | TRE-030 | Energize Transformers | Utility Connection & Energization | LV System Energization | Not Started | 2026-12-30 08:00 | 2026-12-30 16:00 |  |  | 1 | 1 | 0 | Yes | 10 | 6 | 75000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | TRE-040 | Perform Transformer Operational Checks | Utility Connection & Energization | LV System Energization | Not Started | 2026-12-31 08:00 | 2027-01-01 16:00 |  |  | 2 | 2 | 0 | Yes | 10 | 7 | 77000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | TRE-050 | Transformers Energized | Utility Connection & Energization | LV System Energization | Not Started | 2027-01-01 16:00 | 2027-01-01 16:00 |  |  | 0 | 0 | 0 | Yes | 10 | 8 | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | TRF-010 | Prepare Transformer Technical Submittal | Procurement | Transformers | Not Started | 2026-02-19 08:00 | 2026-02-27 16:00 |  |  | 7 | 7 | 20 | No |  |  | 223000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | TRF-020 | Transformer Technical Submittal Approval | Procurement | Transformers | Not Started | 2026-03-30 08:00 | 2026-04-07 16:00 |  |  | 7 | 7 | 0 | Yes | 1 | 6 | 223000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | TRF-030 | Issue Purchase Order - Transformers | Procurement | Transformers | Not Started | 2026-04-08 08:00 | 2026-04-10 16:00 |  |  | 3 | 3 | 0 | Yes | 1 | 7 | 288000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | TRF-040 | Manufacture Transformers | Procurement | Transformers | Not Started | 2026-04-13 08:00 | 2026-11-06 16:00 |  |  | 150 | 150 | 0 | Yes | 1 | 8 | 5588000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | TRF-050 | Factory Acceptance Test - Transformers | Procurement | Transformers | Not Started | 2026-11-09 08:00 | 2026-11-11 16:00 |  |  | 3 | 3 | 0 | Yes | 1 | 9 | 374000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | TRF-060 | Ship Transformers | Procurement | Transformers | Not Started | 2026-11-12 08:00 | 2026-12-09 16:00 |  |  | 20 | 20 | 0 | Yes | 1 | 10 | 407000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | TRF-070 | Deliver Transformers to Site | Procurement | Transformers | Not Started | 2026-12-10 08:00 | 2026-12-11 16:00 |  |  | 2 | 2 | 0 | Yes | 1 | 11 | 204000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | TRI-010 | Prepare Transformer Areas for Installation | Electrical Systems | Transformers | Not Started | 2026-10-08 08:00 | 2026-10-10 16:00 |  |  | 3 | 3 | 55 | No |  |  | 214000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | TRI-020 | Receive and Inspect Transformers | Electrical Systems | Transformers | Not Started | 2026-12-12 08:00 | 2026-12-14 16:00 |  |  | 2 | 2 | 0 | Yes | 1 | 12 | 142000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | TRI-030 | Position Transformers on Plinths | Electrical Systems | Transformers | Not Started | 2026-12-15 08:00 | 2026-12-17 16:00 |  |  | 3 | 3 | 0 | Yes | 1 | 13 | 134000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | TRI-040 | Install Transformer Ancillary Equipment | Electrical Systems | Transformers | Not Started | 2026-12-18 08:00 | 2026-12-23 16:00 |  |  | 5 | 5 | 0 | Yes | 10 | 1 | 249000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | TRI-050 | Complete MV Transformer Connections | Electrical Systems | Transformers | Not Started | 2026-12-18 08:00 | 2026-12-21 16:00 |  |  | 3 | 3 | 2 | No |  |  | 134000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | TRI-060 | Complete LV Transformer Connections | Electrical Systems | Transformers | Not Started | 2026-12-18 08:00 | 2026-12-21 16:00 |  |  | 3 | 3 | 0 | Yes | 1 | 14 | 134000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | TRI-070 | Complete Transformer Installation Inspection | Electrical Systems | Transformers | Not Started | 2026-12-24 08:00 | 2026-12-25 16:00 |  |  | 2 | 2 | 0 | Yes | 10 | 2 | 189000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | TRI-080 | Transformers Ready for Pre-Commissioning | Electrical Systems | Transformers | Not Started | 2026-12-25 16:00 | 2026-12-25 16:00 |  |  | 0 | 0 | 0 | Yes | 10 | 3 | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | TRN-010 | Develop Operations Training Plan | Client Acceptance & Handover | Training & Knowledge Transfer | Completed | 2026-01-23 08:00 | 2026-01-29 16:00 | 2026-01-23 08:00 | 2026-01-29 16:00 | 5 | 0 |  | No |  |  | 29000 | 29000 | 29000 | 29102.15 | -102.15 | 0 | 0.99649 | 1
Update 01 | 2026-01-31 17:00 | TRN-020 | Conduct Electrical Systems Training | Client Acceptance & Handover | Training & Knowledge Transfer | Not Started | 2027-02-16 08:00 | 2027-02-22 16:00 |  |  | 5 | 5 | 72 | No |  |  | 29000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | TRN-030 | Conduct Mechanical Systems Training | Client Acceptance & Handover | Training & Knowledge Transfer | Not Started | 2027-02-15 08:00 | 2027-02-19 16:00 |  |  | 5 | 5 | 73 | No |  |  | 29000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | TRN-040 | Conduct Fire and Life Safety Training | Client Acceptance & Handover | Training & Knowledge Transfer | Not Started | 2027-02-08 08:00 | 2027-02-12 16:00 |  |  | 5 | 5 | 78 | No |  |  | 29000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | TRN-050 | Conduct BMS and DCIM Training | Client Acceptance & Handover | Training & Knowledge Transfer | Not Started | 2027-02-18 08:00 | 2027-02-24 16:00 |  |  | 5 | 5 | 70 | No |  |  | 29000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | TRN-060 | Operations Training Complete | Client Acceptance & Handover | Training & Knowledge Transfer | Not Started | 2027-02-24 16:00 | 2027-02-24 16:00 |  |  | 0 | 0 | 70 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | TU-010 | Install Temporary Electrical Supply | Enabling & Site Works | Temporary Utilities | Not Started | 2026-02-14 08:00 | 2026-02-19 16:00 |  |  | 5 | 5 | 37 | No |  |  | 116000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | TU-020 | Install Temporary Water Supply | Enabling & Site Works | Temporary Utilities | Not Started | 2026-02-14 08:00 | 2026-02-19 16:00 |  |  | 5 | 5 | 37 | No |  |  | 116000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | TU-030 | Install Temporary Drainage Facilities | Enabling & Site Works | Temporary Utilities | Not Started | 2026-02-14 08:00 | 2026-02-19 16:00 |  |  | 5 | 5 | 37 | No |  |  | 116000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | TU-040 | Install Temporary Site Lighting | Enabling & Site Works | Temporary Utilities | Not Started | 2026-02-14 08:00 | 2026-02-19 16:00 |  |  | 5 | 5 | 37 | No |  |  | 116000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | TU-050 | Temporary Site Utilities Operational | Enabling & Site Works | Temporary Utilities | Not Started | 2026-02-20 08:00 | 2026-02-20 08:00 |  |  | 0 | 0 | 37 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | UCMV-010 | Complete Incoming Utility MV Infrastructure | Utility Connection & Energization | Incoming Utility / MV Connection | Not Started | 2026-04-18 08:00 | 2026-05-05 16:00 |  |  | 15 | 15 | 177 | No |  |  | 141000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | UCMV-020 | Install Utility Metering Equipment | Utility Connection & Energization | Incoming Utility / MV Connection | Not Started | 2026-04-22 08:00 | 2026-04-27 16:00 |  |  | 5 | 5 | 189 | No |  |  | 166000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | UCMV-030 | Complete Utility MV Cable Connections | Utility Connection & Energization | Incoming Utility / MV Connection | Not Started | 2026-05-06 08:00 | 2026-05-11 16:00 |  |  | 5 | 5 | 177 | No |  |  | 162000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | UCMV-040 | Complete Utility Protection Interfaces | Utility Connection & Energization | Incoming Utility / MV Connection | Not Started | 2026-04-24 08:00 | 2026-04-29 16:00 |  |  | 5 | 5 | 187 | No |  |  | 101000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | UCMV-050 | Incoming Utility Connection Ready | Utility Connection & Energization | Incoming Utility / MV Connection | Not Started | 2026-05-11 16:00 | 2026-05-11 16:00 |  |  | 0 | 0 | 177 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | UGU-010 | Set Out Underground Utility Routes | Enabling & Site Works | Underground Site Utilities | Not Started | 2026-04-13 08:00 | 2026-04-15 16:00 |  |  | 3 | 3 | 139 | No |  |  | 75000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | UGU-020 | Excavate Underground Utility Trenches | Enabling & Site Works | Underground Site Utilities | Not Started | 2026-04-16 08:00 | 2026-04-27 16:00 |  |  | 10 | 10 | 139 | No |  |  | 107000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | UGU-030 | Install Underground Electrical Duct Banks | Enabling & Site Works | Underground Site Utilities | Not Started | 2026-04-28 08:00 | 2026-05-08 16:00 |  |  | 10 | 10 | 139 | No |  |  | 136000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | UGU-040 | Install Underground ICT Duct Banks | Enabling & Site Works | Underground Site Utilities | Not Started | 2026-04-28 08:00 | 2026-05-06 16:00 |  |  | 8 | 8 | 141 | No |  |  | 133000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | UGU-050 | Install Underground Water Services | Enabling & Site Works | Underground Site Utilities | Not Started | 2026-04-28 08:00 | 2026-05-06 16:00 |  |  | 8 | 8 | 141 | No |  |  | 133000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | UGU-060 | Install Underground Fire Water Services | Enabling & Site Works | Underground Site Utilities | Not Started | 2026-04-28 08:00 | 2026-05-06 16:00 |  |  | 8 | 8 | 141 | No |  |  | 133000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | UGU-070 | Install Utility Chambers and Manholes | Enabling & Site Works | Underground Site Utilities | Not Started | 2026-04-28 08:00 | 2026-05-06 16:00 |  |  | 8 | 8 | 141 | No |  |  | 133000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | UGU-080 | Inspect and Test Underground Utilities | Enabling & Site Works | Underground Site Utilities | Not Started | 2026-05-09 08:00 | 2026-05-12 16:00 |  |  | 3 | 3 | 139 | No |  |  | 75000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | UGU-090 | Backfill and Compact Utility Trenches | Enabling & Site Works | Underground Site Utilities | Not Started | 2026-05-13 08:00 | 2026-05-18 16:00 |  |  | 5 | 5 | 139 | No |  |  | 87000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | UGU-100 | Underground Site Utilities Complete | Enabling & Site Works | Underground Site Utilities | Not Started | 2026-05-19 08:00 | 2026-05-19 08:00 |  |  | 0 | 0 | 139 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | UPE-010 | Complete UPS Pre-Energization Checks | Utility Connection & Energization | Generator & Backup Power Readiness | Not Started | 2027-01-13 08:00 | 2027-01-13 16:00 |  |  | 1 | 1 | 0 | Yes | 10 | 15 | 75000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | UPE-020 | Energize UPS Input Supply | Utility Connection & Energization | Generator & Backup Power Readiness | Not Started | 2027-01-14 08:00 | 2027-01-14 16:00 |  |  | 1 | 1 | 0 | Yes | 10 | 16 | 75000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | UPE-030 | Start and Configure UPS Systems | Utility Connection & Energization | Generator & Backup Power Readiness | Not Started | 2027-01-15 08:00 | 2027-01-18 16:00 |  |  | 3 | 3 | 0 | Yes | 10 | 17 | 87000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | UPE-040 | Energize UPS Output Distribution | Utility Connection & Energization | Generator & Backup Power Readiness | Not Started | 2027-01-19 08:00 | 2027-01-21 16:00 |  |  | 3 | 3 | 0 | Yes | 10 | 18 | 104000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | UPE-050 | Verify Battery System Operation | Utility Connection & Energization | Generator & Backup Power Readiness | Not Started | 2027-01-22 08:00 | 2027-01-23 16:00 |  |  | 2 | 2 | 0 | Yes | 10 | 19 | 77000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | UPE-060 | Critical Power System Energized | Utility Connection & Energization | Generator & Backup Power Readiness | Not Started | 2027-01-23 16:00 | 2027-01-23 16:00 |  |  | 0 | 0 | 0 | Yes | 10 | 20 | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | UPS-010 | Prepare UPS and Battery Technical Submittal | Procurement | UPS Systems & Batteries | Not Started | 2026-02-26 08:00 | 2026-03-06 16:00 |  |  | 7 | 7 | 52 | No |  |  | 186000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | UPS-020 | UPS and Battery Technical Submittal Approval | Procurement | UPS Systems & Batteries | Not Started | 2026-03-30 08:00 | 2026-04-07 16:00 |  |  | 7 | 7 | 37 | No |  |  | 186000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | UPS-030 | Issue Purchase Order - UPS and Batteries | Procurement | UPS Systems & Batteries | Not Started | 2026-04-08 08:00 | 2026-04-10 16:00 |  |  | 3 | 3 | 37 | No |  |  | 240000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | UPS-040 | Manufacture UPS Systems and Batteries | Procurement | UPS Systems & Batteries | Not Started | 2026-04-13 08:00 | 2026-09-25 16:00 |  |  | 120 | 120 | 37 | No |  |  | 4353000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | UPS-050 | Factory Acceptance Test - UPS Systems | Procurement | UPS Systems & Batteries | Not Started | 2026-09-28 08:00 | 2026-09-30 16:00 |  |  | 3 | 3 | 37 | No |  |  | 312000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | UPS-060 | Ship UPS Systems and Batteries | Procurement | UPS Systems & Batteries | Not Started | 2026-10-01 08:00 | 2026-10-21 16:00 |  |  | 15 | 15 | 37 | No |  |  | 311000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | UPS-070 | Deliver UPS Systems and Batteries to Site | Procurement | UPS Systems & Batteries | Not Started | 2026-10-22 08:00 | 2026-10-23 16:00 |  |  | 2 | 2 | 37 | No |  |  | 170000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | UPSI-010 | Prepare UPS and Battery Rooms for Installation | Electrical Systems | UPS Systems & Batteries | Not Started | 2026-10-10 08:00 | 2026-10-13 16:00 |  |  | 3 | 3 | 54 | No |  |  | 214000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | UPSI-020 | Receive and Inspect UPS Equipment | Electrical Systems | UPS Systems & Batteries | Not Started | 2026-10-24 08:00 | 2026-10-26 16:00 |  |  | 2 | 2 | 45 | No |  |  | 142000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | UPSI-030 | Install UPS Units | Electrical Systems | UPS Systems & Batteries | Not Started | 2026-10-27 08:00 | 2026-10-31 16:00 |  |  | 5 | 5 | 45 | No |  |  | 249000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | UPSI-040 | Install Battery Racks and Cabinets | Electrical Systems | UPS Systems & Batteries | Not Started | 2026-10-14 08:00 | 2026-10-19 16:00 |  |  | 5 | 5 | 54 | No |  |  | 249000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | UPSI-050 | Install Battery Systems | Electrical Systems | UPS Systems & Batteries | Not Started | 2026-10-20 08:00 | 2026-10-27 16:00 |  |  | 7 | 7 | 54 | No |  |  | 276000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | UPSI-060 | Install UPS Input and Output Power Connections | Electrical Systems | UPS Systems & Batteries | Not Started | 2026-12-24 08:00 | 2026-12-29 16:00 |  |  | 5 | 5 | 0 | Yes | 1 | 17 | 249000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | UPSI-070 | Install UPS Control and Monitoring Connections | Electrical Systems | UPS Systems & Batteries | Not Started | 2026-11-02 08:00 | 2026-11-06 16:00 |  |  | 5 | 5 | 45 | No |  |  | 31000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | UPSI-080 | Complete UPS and Battery Installation Inspection | Electrical Systems | UPS Systems & Batteries | Not Started | 2026-12-30 08:00 | 2026-12-31 16:00 |  |  | 2 | 2 | 0 | Yes | 1 | 18 | 189000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | UPSI-090 | UPS and Battery Systems Ready for Pre-Commissioning | Electrical Systems | UPS Systems & Batteries | Not Started | 2026-12-31 16:00 | 2026-12-31 16:00 |  |  | 0 | 0 | 0 | Yes | 1 | 19 | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | UTL-010 | Submit Utility Connection Application | Utility Connection & Energization | Utility Coordination & Approvals | Not Started | 2026-03-20 08:00 | 2026-03-25 16:00 |  |  | 5 | 5 | 177 | No |  |  | 30000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | UTL-020 | Coordinate Utility Technical Requirements | Utility Connection & Energization | Utility Coordination & Approvals | Not Started | 2026-03-26 08:00 | 2026-04-06 16:00 |  |  | 10 | 10 | 177 | No |  |  | 25000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | UTL-030 | Submit Utility Protection Study | Utility Connection & Energization | Utility Coordination & Approvals | Not Started | 2026-03-26 08:00 | 2026-04-06 16:00 |  |  | 10 | 10 | 177 | No |  |  | 37000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | UTL-040 | Resolve Utility Review Comments | Utility Connection & Energization | Utility Coordination & Approvals | Not Started | 2026-04-07 08:00 | 2026-04-17 16:00 |  |  | 10 | 10 | 177 | No |  |  | 25000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | UTL-050 | Obtain Utility Connection Approval | Utility Connection & Energization | Utility Coordination & Approvals | Not Started | 2026-04-17 16:00 | 2026-04-17 16:00 |  |  | 0 | 0 | 177 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | UTL-D-010 | Confirm Utility Power Requirements | Design & Engineering | Utility & Grid Connection Design | Not Started | 2026-02-05 08:00 | 2026-02-11 16:00 |  |  | 5 | 5 | 10 | No |  |  | 65000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | UTL-D-020 | Develop Utility Connection Design | Design & Engineering | Utility & Grid Connection Design | Not Started | 2026-02-12 08:00 | 2026-03-04 16:00 |  |  | 15 | 15 | 148 | No |  |  | 154000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | UTL-D-030 | Develop Incoming MV Connection Design | Design & Engineering | Utility & Grid Connection Design | Not Started | 2026-02-12 08:00 | 2026-03-04 16:00 |  |  | 15 | 15 | 138 | No |  |  | 154000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | UTL-D-040 | Coordinate Utility Protection Requirements | Design & Engineering | Utility & Grid Connection Design | Not Started | 2026-03-05 08:00 | 2026-03-18 16:00 |  |  | 10 | 10 | 138 | No |  |  | 23000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | UTL-D-050 | Submit Utility Connection Design | Design & Engineering | Utility & Grid Connection Design | Not Started | 2026-03-19 08:00 | 2026-03-19 16:00 |  |  | 1 | 1 | 138 | No |  |  | 17000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | UTL-D-060 | Utility Design Review | Design & Engineering | Utility & Grid Connection Design | Not Started | 2026-03-20 08:00 | 2026-04-16 16:00 |  |  | 20 | 20 | 138 | No |  |  | 28000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | UTL-D-070 | Utility Connection Design Approved | Design & Engineering | Utility & Grid Connection Design | Not Started | 2026-04-16 16:00 | 2026-04-16 16:00 |  |  | 0 | 0 | 138 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | VEN-010 | Install Ventilation Ductwork Supports | Mechanical & Cooling Systems | Ventilation & Exhaust Systems | Not Started | 2026-10-05 08:00 | 2026-10-12 16:00 |  |  | 7 | 7 | 77 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | VEN-020 | Install Ventilation and Exhaust Ductwork | Mechanical & Cooling Systems | Ventilation & Exhaust Systems | Not Started | 2026-10-07 08:00 | 2026-10-23 16:00 |  |  | 15 | 15 | 77 | No |  |  | 257000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | VEN-030 | Install Ventilation Fans | Mechanical & Cooling Systems | Ventilation & Exhaust Systems | Not Started | 2026-10-07 08:00 | 2026-10-14 16:00 |  |  | 7 | 7 | 80 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | VEN-040 | Install Dampers and Air Control Devices | Mechanical & Cooling Systems | Ventilation & Exhaust Systems | Not Started | 2026-10-10 08:00 | 2026-10-17 16:00 |  |  | 7 | 7 | 77 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | VEN-050 | Install Louvers Grilles and Terminals | Mechanical & Cooling Systems | Ventilation & Exhaust Systems | Not Started | 2026-10-10 08:00 | 2026-10-17 16:00 |  |  | 7 | 7 | 77 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | VEN-060 | Install Ventilation Controls Connections | Mechanical & Cooling Systems | Ventilation & Exhaust Systems | Not Started | 2026-10-19 08:00 | 2026-10-26 16:00 |  |  | 7 | 7 | 77 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | VEN-070 | Inspect Ventilation and Exhaust Installation | Mechanical & Cooling Systems | Ventilation & Exhaust Systems | Not Started | 2026-10-27 08:00 | 2026-10-28 16:00 |  |  | 2 | 2 | 77 | No |  |  | 140000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | VEN-080 | Ventilation and Exhaust Systems Ready for Pre-Commissioning | Mechanical & Cooling Systems | Ventilation & Exhaust Systems | Not Started | 2026-10-28 16:00 | 2026-10-28 16:00 |  |  | 0 | 0 | 77 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | VES-010 | Install VESDA Control Units | Fire & Life Safety | Smoke Detection / VESDA | Not Started | 2026-06-10 08:00 | 2026-06-15 16:00 |  |  | 5 | 5 | 187 | No |  |  | 82000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | VES-020 | Install VESDA Sampling Pipe Network | Fire & Life Safety | Smoke Detection / VESDA | Not Started | 2026-10-08 08:00 | 2026-10-16 16:00 |  |  | 8 | 8 | 81 | No |  |  | 95000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | VES-030 | Install VESDA Sampling Points | Fire & Life Safety | Smoke Detection / VESDA | Not Started | 2026-10-12 08:00 | 2026-10-16 16:00 |  |  | 5 | 5 | 81 | No |  |  | 82000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | VES-040 | Complete VESDA Electrical Connections | Fire & Life Safety | Smoke Detection / VESDA | Not Started | 2026-10-17 08:00 | 2026-10-19 16:00 |  |  | 2 | 2 | 81 | No |  |  | 39000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | VES-050 | Complete VESDA Fire Alarm Interfaces | Fire & Life Safety | Smoke Detection / VESDA | Not Started | 2026-10-22 08:00 | 2026-10-23 16:00 |  |  | 2 | 2 | 79 | No |  |  | 39000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | VES-060 | Inspect VESDA Installation | Fire & Life Safety | Smoke Detection / VESDA | Not Started | 2026-10-24 08:00 | 2026-10-26 16:00 |  |  | 2 | 2 | 79 | No |  |  | 63000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | VES-070 | VESDA System Ready for Pre-Commissioning | Fire & Life Safety | Smoke Detection / VESDA | Not Started | 2026-10-26 16:00 | 2026-10-26 16:00 |  |  | 0 | 0 | 79 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | WPF-010 | Prepare Surfaces for Waterproofing | Building Envelope | Waterproofing | Not Started | 2026-07-03 08:00 | 2026-07-04 16:00 |  |  | 2 | 2 | 32 | No |  |  | 100000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | WPF-020 | Apply Foundation Waterproofing | Building Envelope | Waterproofing | Not Started | 2026-07-06 08:00 | 2026-07-10 16:00 |  |  | 5 | 5 | 32 | No |  |  | 132000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | WPF-030 | Apply Below-Grade Wall Waterproofing | Building Envelope | Waterproofing | Not Started | 2026-07-08 08:00 | 2026-07-13 16:00 |  |  | 5 | 5 | 32 | No |  |  | 132000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | WPF-040 | Waterproof Service Penetrations | Building Envelope | Waterproofing | Not Started | 2026-07-10 08:00 | 2026-07-13 16:00 |  |  | 3 | 3 | 32 | No |  |  | 113000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | WPF-050 | Install Waterproofing Protection Layer | Building Envelope | Waterproofing | Not Started | 2026-07-14 08:00 | 2026-07-16 16:00 |  |  | 3 | 3 | 32 | No |  |  | 113000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | WPF-060 | Inspect and Test Waterproofing Works | Building Envelope | Waterproofing | Not Started | 2026-07-17 08:00 | 2026-07-18 16:00 |  |  | 2 | 2 | 32 | No |  |  | 100000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | WPF-070 | Waterproofing Complete | Building Envelope | Waterproofing | Not Started | 2026-07-20 08:00 | 2026-07-20 08:00 |  |  | 0 | 0 | 32 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | WTM-010 | Prepare Water Treatment Equipment Area | Mechanical & Cooling Systems | Water Treatment & Make-Up Systems | Not Started | 2026-08-25 08:00 | 2026-08-27 16:00 |  |  | 3 | 3 | 113 | No |  |  | 99000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | WTM-020 | Install Water Treatment Equipment | Mechanical & Cooling Systems | Water Treatment & Make-Up Systems | Not Started | 2026-08-28 08:00 | 2026-09-02 16:00 |  |  | 5 | 5 | 113 | No |  |  | 185000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | WTM-030 | Install Chemical Dosing System | Mechanical & Cooling Systems | Water Treatment & Make-Up Systems | Not Started | 2026-09-03 08:00 | 2026-09-08 16:00 |  |  | 5 | 5 | 113 | No |  |  | 185000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | WTM-040 | Install Cooling System Make-Up Water Connections | Mechanical & Cooling Systems | Water Treatment & Make-Up Systems | Not Started | 2026-09-03 08:00 | 2026-09-08 16:00 |  |  | 5 | 5 | 113 | No |  |  | 185000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | WTM-050 | Install Water Treatment Instrumentation | Mechanical & Cooling Systems | Water Treatment & Make-Up Systems | Not Started | 2026-08-31 08:00 | 2026-09-04 16:00 |  |  | 5 | 5 | 116 | No |  |  | 185000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | WTM-060 | Complete Electrical and Controls Connections | Mechanical & Cooling Systems | Water Treatment & Make-Up Systems | Not Started | 2026-09-09 08:00 | 2026-09-14 16:00 |  |  | 5 | 5 | 113 | No |  |  | 115000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | WTM-070 | Inspect Water Treatment and Make-Up Systems | Mechanical & Cooling Systems | Water Treatment & Make-Up Systems | Not Started | 2026-09-15 08:00 | 2026-09-16 16:00 |  |  | 2 | 2 | 113 | No |  |  | 105000 | 0 | 0 | 0 | 0 | 0
Update 01 | 2026-01-31 17:00 | WTM-080 | Water Treatment and Make-Up Systems Ready for Pre-Commissioning | Mechanical & Cooling Systems | Water Treatment & Make-Up Systems | Not Started | 2026-09-16 16:00 | 2026-09-16 16:00 |  |  | 0 | 0 | 113 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0
Update 02 | 2026-02-28 | PM-001 | Notice to Proceed | Project Management & Controls | Project Management | Completed | 2026-02-02 08:00 | 2026-02-02 08:00 | 2026-01-05 | 2026-01-05 | 0 | 0 |  | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | PM-010 | Project Kick-Off Meeting | Project Management & Controls | Project Management | Completed | 2026-01-05 08:00 | 2026-01-05 16:00 | 2026-01-05 08:00 | 2026-01-05 16:00 | 1 | 0 |  | No |  |  | 80000 | 80000 | 80000 | 80729.9406 | -729.9406 | 0 | 0.99096 | 1 | Available | Available | Available | Available
Update 02 | 2026-02-28 | PM-020 | Establish Project Organization | Project Management & Controls | Project Management | Completed | 2026-01-06 08:00 | 2026-01-12 16:00 | 2026-01-06 08:00 | 2026-01-12 16:00 | 5 | 0 |  | No |  |  | 293000 | 293000 | 293000 | 299727.3389 | -6727.3389 | 0 | 0.97756 | 1 | Available | Available | Available | Available
Update 02 | 2026-02-28 | PM-030 | Establish Project Management Procedures | Project Management & Controls | Project Management | Completed | 2026-01-06 08:00 | 2026-01-19 16:00 | 2026-01-06 08:00 | 2026-01-19 16:00 | 10 | 0 |  | No |  |  | 361000 | 361000 | 361000 | 363053.4606 | -2053.4606 | 0 | 0.99434 | 1 | Available | Available | Available | Available
Update 02 | 2026-02-28 | PC-010 | Develop Project Controls Procedures | Project Management & Controls | Project Controls | Completed | 2026-01-05 08:00 | 2026-01-09 16:00 | 2026-01-05 08:00 | 2026-01-09 16:00 | 5 | 0 |  | No |  |  | 293000 | 293000 | 293000 | 296590.3084 | -3590.3084 | 0 | 0.98789 | 1 | Available | Available | Available | Available
Update 02 | 2026-02-28 | PC-020 | Develop Detailed Baseline Programme | Project Management & Controls | Project Controls | Completed | 2026-01-12 08:00 | 2026-01-30 16:00 | 2026-01-12 08:00 | 2026-01-30 16:00 | 15 | 0 |  | No |  |  | 408000 | 408000 | 408000 | 423338.7948 | -15338.7948 | 0 | 0.96377 | 1 | Available | Available | Available | Available
Update 02 | 2026-02-28 | PC-030 | Baseline Schedule Review | Project Management & Controls | Project Controls | Completed | 2026-02-02 08:00 | 2026-02-06 16:00 | 2026-02-02 08:00 | 2026-02-06 16:00 | 5 | 0 | 26 | No |  |  | 130000 | 130000 | 130000 | 131122.0676 | -1122.0676 | 0 | 0.99144 | 1 | Available | Available | Available | Available
Update 02 | 2026-02-28 | PC-040 | Baseline Schedule Approval | Project Management & Controls | Project Controls | In Progress | 2026-02-09 08:00 | 2026-02-13 16:00 | 2026-02-09 08:00 |  | 5 | 5.9496 | 26 | No |  |  | 195000 | 195000 | 157965.0516 | 165303.5542 | -7338.5026 | -37034.9484 | 0.95561 | 0.81008 | Available | Available | Available | Available
Update 02 | 2026-02-28 | PC-050 | Baseline Programme Approved | Project Management & Controls | Project Controls | Completed | 2026-02-13 16:00 | 2026-02-13 16:00 | 2026-02-13 16:00 | 2026-02-13 16:00 | 0 | 0 | 26 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | HSE-010 | Develop Project HSE Plan | Project Management & Controls | HSE Management | Completed | 2026-01-05 08:00 | 2026-01-16 16:00 | 2026-01-05 08:00 | 2026-01-16 16:00 | 10 | 0 |  | No |  |  | 361000 | 361000 | 361000 | 369220.1068 | -8220.1068 | 0 | 0.97774 | 1 | Available | Available | Available | Available
Update 02 | 2026-02-28 | HSE-020 | HSE Plan Review | Project Management & Controls | HSE Management | Completed | 2026-01-19 08:00 | 2026-01-23 16:00 | 2026-01-19 08:00 | 2026-01-23 16:00 | 5 | 0 |  | No |  |  | 130000 | 130000 | 130000 | 134146.5298 | -4146.5298 | 0 | 0.96909 | 1 | Available | Available | Available | Available
Update 02 | 2026-02-28 | HSE-030 | HSE Plan Approval | Project Management & Controls | HSE Management | Completed | 2026-01-26 08:00 | 2026-01-28 16:00 | 2026-01-26 08:00 | 2026-01-28 16:00 | 3 | 0 |  | No |  |  | 168000 | 168000 | 168000 | 171047.4861 | -3047.4861 | 0 | 0.98218 | 1 | Available | Available | Available | Available
Update 02 | 2026-02-28 | QA-010 | Develop Project Quality Plan | Project Management & Controls | Quality Management | Completed | 2026-01-05 08:00 | 2026-01-16 16:00 | 2026-01-05 08:00 | 2026-01-16 16:00 | 10 | 0 |  | No |  |  | 361000 | 361000 | 361000 | 375044.404 | -14044.404 | 0 | 0.96255 | 1 | Available | Available | Available | Available
Update 02 | 2026-02-28 | QA-020 | Quality Plan Review | Project Management & Controls | Quality Management | Completed | 2026-01-19 08:00 | 2026-01-23 16:00 | 2026-01-19 08:00 | 2026-01-23 16:00 | 5 | 0 |  | No |  |  | 130000 | 130000 | 130000 | 130902.5407 | -902.5407 | 0 | 0.99311 | 1 | Available | Available | Available | Available
Update 02 | 2026-02-28 | QA-030 | Quality Plan Approval | Project Management & Controls | Quality Management | Completed | 2026-01-26 08:00 | 2026-01-28 16:00 | 2026-01-26 08:00 | 2026-01-28 16:00 | 3 | 0 |  | No |  |  | 168000 | 168000 | 168000 | 170512.229 | -2512.229 | 0 | 0.98527 | 1 | Available | Available | Available | Available
Update 02 | 2026-02-28 | COM-010 | Establish Contract Administration Procedures | Project Management & Controls | Contract & Commercial Management | Completed | 2026-01-06 08:00 | 2026-01-12 16:00 | 2026-01-06 08:00 | 2026-01-12 16:00 | 5 | 0 |  | No |  |  | 293000 | 293000 | 293000 | 295862.9147 | -2862.9147 | 0 | 0.99032 | 1 | Available | Available | Available | Available
Update 02 | 2026-02-28 | COM-020 | Establish Change and Variation Control Procedure | Project Management & Controls | Contract & Commercial Management | Completed | 2026-01-13 08:00 | 2026-01-19 16:00 | 2026-01-13 08:00 | 2026-01-19 16:00 | 5 | 0 |  | No |  |  | 293000 | 293000 | 293000 | 300765.4515 | -7765.4515 | 0 | 0.97418 | 1 | Available | Available | Available | Available
Update 02 | 2026-02-28 | COM-030 | Establish Payment and Cost Control Procedure | Project Management & Controls | Contract & Commercial Management | Completed | 2026-01-13 08:00 | 2026-01-19 16:00 | 2026-01-13 08:00 | 2026-01-19 16:00 | 5 | 0 |  | No |  |  | 293000 | 293000 | 293000 | 293343.8221 | -343.8221 | 0 | 0.99883 | 1 | Available | Available | Available | Available
Update 02 | 2026-02-28 | COM-040 | Establish Commercial Reporting Procedure | Project Management & Controls | Contract & Commercial Management | Completed | 2026-01-13 08:00 | 2026-01-19 16:00 | 2026-01-13 08:00 | 2026-01-19 16:00 | 5 | 0 |  | No |  |  | 130000 | 130000 | 130000 | 130558.1564 | -558.1564 | 0 | 0.99572 | 1 | Available | Available | Available | Available
Update 02 | 2026-02-28 | INT-010 | Develop Stakeholder Register | Project Management & Controls | Stakeholder & Interface Management | Completed | 2026-01-06 08:00 | 2026-01-12 16:00 | 2026-01-06 08:00 | 2026-01-12 16:00 | 5 | 0 |  | No |  |  | 130000 | 130000 | 130000 | 131162.7129 | -1162.7129 | 0 | 0.99114 | 1 | Available | Available | Available | Available
Update 02 | 2026-02-28 | INT-020 | Develop Interface Register | Project Management & Controls | Stakeholder & Interface Management | Completed | 2026-01-13 08:00 | 2026-01-26 16:00 | 2026-01-13 08:00 | 2026-01-26 16:00 | 10 | 0 |  | No |  |  | 160000 | 160000 | 160000 | 165325.8827 | -5325.8827 | 0 | 0.96779 | 1 | Available | Available | Available | Available
Update 02 | 2026-02-28 | INT-030 | Establish Interface Management Procedure | Project Management & Controls | Stakeholder & Interface Management | In Progress | 2026-01-27 08:00 | 2026-02-02 16:00 | 2026-01-27 08:00 |  | 5 | 0.18686 | 35 | No |  |  | 293000 | 293000 | 282050.0702 | 291925.4469 | -9875.3767 | -10949.9298 | 0.96617 | 0.96263 | Available | Available | Available | Available
Update 02 | 2026-02-28 | INT-040 | Establish Communication and Reporting Matrix | Project Management & Controls | Stakeholder & Interface Management | Completed | 2026-01-13 08:00 | 2026-01-19 16:00 | 2026-01-13 08:00 | 2026-01-19 16:00 | 5 | 0 |  | No |  |  | 130000 | 130000 | 130000 | 131669.309 | -1669.309 | 0 | 0.98732 | 1 | Available | Available | Available | Available
Update 02 | 2026-02-28 | DM-010 | Establish Design Management Plan | Design & Engineering | Design Management & Coordination | Completed | 2026-01-06 08:00 | 2026-01-12 16:00 | 2026-01-06 08:00 | 2026-01-12 16:00 | 5 | 0 |  | No |  |  | 111000 | 111000 | 111000 | 112144.9454 | -1144.9454 | 0 | 0.98979 | 1 | Available | Available | Available | Available
Update 02 | 2026-02-28 | DM-020 | Establish Design Deliverables Register | Design & Engineering | Design Management & Coordination | Completed | 2026-01-08 08:00 | 2026-01-12 16:00 | 2026-01-08 08:00 | 2026-01-12 16:00 | 3 | 0 |  | No |  |  | 16000 | 16000 | 16000 | 16020.8208 | -20.8208 | 0 | 0.9987 | 1 | Available | Available | Available | Available
Update 02 | 2026-02-28 | DM-030 | Establish Design Responsibility Matrix | Design & Engineering | Design Management & Coordination | Completed | 2026-01-08 08:00 | 2026-01-12 16:00 | 2026-01-08 08:00 | 2026-01-12 16:00 | 3 | 0 |  | No |  |  | 95000 | 95000 | 95000 | 97632.864 | -2632.864 | 0 | 0.97303 | 1 | Available | Available | Available | Available
Update 02 | 2026-02-28 | DM-040 | Develop Design Coordination Schedule | Design & Engineering | Design Management & Coordination | Completed | 2026-01-13 08:00 | 2026-01-19 16:00 | 2026-01-13 08:00 | 2026-01-19 16:00 | 5 | 0 |  | No |  |  | 18000 | 18000 | 18000 | 18464.9779 | -464.9779 | 0 | 0.97482 | 1 | Available | Available | Available | Available
Update 02 | 2026-02-28 | DM-050 | Conduct Multidiscipline Design Coordination | Design & Engineering | Design Management & Coordination | In Progress | 2026-01-20 08:00 | 2026-03-16 16:00 | 2026-01-20 08:00 |  | 40 | 12.8485 | 175 | No |  |  | 34000 | 23759.0361 | 23078.7741 | 23910.9503 | -832.1761 | -680.262 | 0.9652 | 0.97137 | Available | Available | Available | Available
Update 02 | 2026-02-28 | DM-060 | Design Coordination Complete | Design & Engineering | Design Management & Coordination | Not Started | 2026-04-16 16:00 | 2026-04-16 16:00 |  |  | 0 | 0 | 152 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | CIV-010 | Develop Civil and Structural Design Criteria | Design & Engineering | Civil & Structural Design | Completed | 2026-01-13 08:00 | 2026-01-19 16:00 | 2026-01-13 08:00 | 2026-01-20 16:00 | 5 | 0 |  | No |  |  | 111000 | 111000 | 111000 | 113377.7355 | -2377.7355 | 0 | 0.97903 | 1 | Available | Available | Available | Available
Update 02 | 2026-02-28 | CIV-020 | Develop Site Grading and Drainage Design | Design & Engineering | Civil & Structural Design | Completed | 2026-01-20 08:00 | 2026-02-02 16:00 | 2026-01-21 08:00 | 2026-02-02 16:00 | 10 | 0 | 89 | No |  |  | 136000 | 136000 | 136000 | 139132.4165 | -3132.4165 | 0 | 0.97749 | 1 | Available | Available | Available | Available
Update 02 | 2026-02-28 | CIV-030 | Develop Foundation Design | Design & Engineering | Civil & Structural Design | Completed | 2026-01-20 08:00 | 2026-02-09 16:00 | 2026-01-20 08:00 | 2026-02-09 16:00 | 15 | 0 | 85 | No |  |  | 154000 | 154000 | 154000 | 158355.6244 | -4355.6244 | 0 | 0.97249 | 1 | Available | Available | Available | Available
Update 02 | 2026-02-28 | CIV-040 | Develop Main Structural Frame Design | Design & Engineering | Civil & Structural Design | Completed | 2026-01-20 08:00 | 2026-02-16 16:00 | 2026-01-20 08:00 | 2026-02-16 16:00 | 20 | 0 | 12 | No |  |  | 170000 | 170000 | 170000 | 174269.7598 | -4269.7598 | 0 | 0.9755 | 1 | Available | Available | Available | Available
Update 02 | 2026-02-28 | CIV-050 | Develop Equipment Foundation and Plinth Design | Design & Engineering | Civil & Structural Design | In Progress | 2026-02-25 08:00 | 2026-03-10 16:00 | 2026-02-25 08:00 |  | 10 | 7.9981 | 64 | No |  |  | 136000 | 27200 | 27225.8327 | 28196.0562 | -970.2235 | 25.8327 | 0.96559 | 1.0009 | Available | Available | Available | Available
Update 02 | 2026-02-28 | CIV-060 | Civil and Structural Design Review | Design & Engineering | Civil & Structural Design | Not Started | 2026-03-11 08:00 | 2026-03-17 16:00 |  |  | 5 | 5 | 64 | No |  |  | 18000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CIV-070 | Civil and Structural Design Approved | Design & Engineering | Civil & Structural Design | Not Started | 2026-03-17 16:00 | 2026-03-17 16:00 |  |  | 0 | 0 | 64 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | ARC-010 | Develop Architectural Design Criteria | Design & Engineering | Architectural Design | Completed | 2026-01-13 08:00 | 2026-01-19 16:00 | 2026-01-13 08:00 | 2026-01-21 16:00 | 5 | 0 |  | No |  |  | 111000 | 111000 | 111000 | 114669.8565 | -3669.8565 | 0 | 0.968 | 1 | Available | Available | Available | Available
Update 02 | 2026-02-28 | ARC-020 | Develop Data Hall Layout | Design & Engineering | Architectural Design | In Progress | 2026-01-20 08:00 | 2026-02-02 16:00 | 2026-01-20 08:00 |  | 10 | 5 | 17 | No |  |  | 136000 | 136000 | 122400 | 130227.8597 | -7827.8597 | -13600 | 0.93989 | 0.9 | Available | Available | Available | Available
Update 02 | 2026-02-28 | ARC-030 | Develop Technical Room Layouts | Design & Engineering | Architectural Design | Completed | 2026-01-20 08:00 | 2026-02-02 16:00 | 2026-01-21 08:00 | 2026-02-02 16:00 | 10 | 0 | 0 | Yes | 1 | 1 | 136000 | 136000 | 136000 | 139008.6147 | -3008.6147 | 0 | 0.97836 | 1 | Available | Available | Available | Available
Update 02 | 2026-02-28 | ARC-040 | Develop Building Envelope Design | Design & Engineering | Architectural Design | In Progress | 2026-01-20 08:00 | 2026-02-09 16:00 | 2026-01-20 08:00 |  | 15 | 0.47418 | 101 | No |  |  | 154000 | 154000 | 149131.7243 | 154607.7446 | -5476.0203 | -4868.2757 | 0.96458 | 0.96839 | Available | Available | Available | Available
Update 02 | 2026-02-28 | ARC-050 | Develop Internal Partition and Door Layouts | Design & Engineering | Architectural Design | In Progress | 2026-02-05 08:00 | 2026-02-18 16:00 | 2026-02-05 08:00 |  | 10 | 0.11734 | 94 | No |  |  | 136000 | 136000 | 134404.145 | 136782.8753 | -2378.7302 | -1595.855 | 0.98261 | 0.98827 | Available | Available | Available | Available
Update 02 | 2026-02-28 | ARC-060 | Architectural Design Review | Design & Engineering | Architectural Design | In Progress | 2026-02-19 08:00 | 2026-02-25 16:00 | 2026-02-19 08:00 |  | 5 | 0.0095845 | 94 | No |  |  | 18000 | 18000 | 17965.4958 | 18292.1352 | -326.6394 | -34.5042 | 0.98214 | 0.99808 | Available | Available | Available | Available
Update 02 | 2026-02-28 | ARC-070 | Architectural Design Approved | Design & Engineering | Architectural Design | In Progress | 2026-02-25 16:00 | 2026-02-25 16:00 | 2026-02-25 16:00 |  | 0 | 0 | 94 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | ELE-D-010 | Develop Electrical Design Criteria | Design & Engineering | Electrical Design | Completed | 2026-01-13 08:00 | 2026-01-19 16:00 | 2026-01-13 08:00 | 2026-01-22 16:00 | 5 | 0 |  | No |  |  | 111000 | 111000 | 111000 | 115476.7191 | -4476.7191 | 0 | 0.96123 | 1 | Available | Available | Available | Available
Update 02 | 2026-02-28 | ELE-D-020 | Develop Electrical Load Schedule | Design & Engineering | Electrical Design | In Progress | 2026-01-20 08:00 | 2026-02-02 16:00 | 2026-01-21 08:00 |  | 10 | 0.27125 | 0 | Yes |  |  | 79000 | 79000 | 76857.1313 | 78719.5456 | -1862.4143 | -2142.8687 | 0.97634 | 0.97288 | Available | Available | Available | Available
Update 02 | 2026-02-28 | ELE-D-030 | Develop MV Distribution Design | Design & Engineering | Electrical Design | In Progress | 2026-02-12 08:00 | 2026-03-04 16:00 | 2026-02-12 08:00 |  | 15 | 3.7427 | 10 | No |  |  | 154000 | 118655.7377 | 115575.0039 | 120098.8752 | -4523.8713 | -3080.7338 | 0.96233 | 0.97404 | Available | Available | Available | Available
Update 02 | 2026-02-28 | ELE-D-040 | Develop Transformer Design and Sizing | Design & Engineering | Electrical Design | In Progress | 2026-02-05 08:00 | 2026-02-18 16:00 | 2026-02-05 08:00 |  | 10 | 0.22384 | 20 | No |  |  | 136000 | 136000 | 132955.7251 | 134778.3788 | -1822.6538 | -3044.2749 | 0.98648 | 0.97762 | Available | Available | Available | Available
Update 02 | 2026-02-28 | ELE-D-050 | Develop Generator System Design | Design & Engineering | Electrical Design | Completed | 2026-02-05 08:00 | 2026-02-18 16:00 | 2026-02-05 08:00 | 2026-02-18 16:00 | 10 | 0 | 20 | No |  |  | 136000 | 136000 | 136000 | 137850.9884 | -1850.9884 | 0 | 0.98657 | 1 | Available | Available | Available | Available
Update 02 | 2026-02-28 | ELE-D-060 | Develop LV Distribution Design | Design & Engineering | Electrical Design | Completed | 2026-02-05 08:00 | 2026-02-25 16:00 | 2026-02-05 08:00 | 2026-02-25 16:00 | 15 | 0 | 0 | Yes | 1 | 2 | 154000 | 154000 | 154000 | 159308.326 | -5308.326 | 0 | 0.96668 | 1 | Available | Available | Available | Available
Update 02 | 2026-02-28 | ELE-D-070 | Develop UPS and Battery System Design | Design & Engineering | Electrical Design | In Progress | 2026-02-05 08:00 | 2026-02-25 16:00 | 2026-02-05 08:00 |  | 15 | 9.9299 | 0 | Yes |  |  | 154000 | 154000 | 113653.4741 | 122509.3525 | -8855.8784 | -40346.5259 | 0.92771 | 0.73801 | Available | Available | Available | Available
Update 02 | 2026-02-28 | ELE-D-080 | Develop Busway and Data Hall Power Distribution Design | Design & Engineering | Electrical Design | In Progress | 2026-02-26 08:00 | 2026-03-18 16:00 | 2026-02-26 08:00 |  | 15 | 19.9915 | 0 | Yes | 1 | 3 | 154000 | 12622.9508 | 10353.4573 | 11388.204 | -1034.7467 | -2269.4935 | 0.90914 | 0.82021 | Available | Available | Available | Available
Update 02 | 2026-02-28 | ELE-D-090 | Develop Earthing and Lightning Protection Design | Design & Engineering | Electrical Design | In Progress | 2026-02-17 08:00 | 2026-03-02 16:00 | 2026-02-17 08:00 |  | 10 | 2.1058 | 12 | No |  |  | 136000 | 108800 | 107360.5082 | 110086.1477 | -2725.6395 | -1439.4918 | 0.97524 | 0.98677 | Available | Available | Available | Available
Update 02 | 2026-02-28 | ELE-D-100 | Electrical Design Review | Design & Engineering | Electrical Design | Not Started | 2026-03-19 08:00 | 2026-03-27 16:00 |  |  | 7 | 7 | 0 | Yes | 1 | 4 | 20000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | ELE-D-110 | Electrical Design Approved | Design & Engineering | Electrical Design | Not Started | 2026-03-27 16:00 | 2026-03-27 16:00 |  |  | 0 | 0 | 0 | Yes | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | MEC-D-010 | Develop Mechanical Design Criteria | Design & Engineering | Mechanical & Cooling Design | Completed | 2026-01-13 08:00 | 2026-01-19 16:00 | 2026-01-13 08:00 | 2026-01-21 16:00 | 5 | 0 |  | No |  |  | 111000 | 111000 | 111000 | 114190.4253 | -3190.4253 | 0 | 0.97206 | 1 | Available | Available | Available | Available
Update 02 | 2026-02-28 | MEC-D-020 | Develop Cooling Load Calculations | Design & Engineering | Mechanical & Cooling Design | In Progress | 2026-01-20 08:00 | 2026-02-02 16:00 | 2026-01-21 08:00 |  | 10 | 0.18291 | 39 | No |  |  | 136000 | 136000 | 133512.3909 | 138569.3409 | -5056.95 | -2487.6091 | 0.96351 | 0.98171 | Available | Available | Available | Available
Update 02 | 2026-02-28 | MEC-D-030 | Develop Cooling Plant Design | Design & Engineering | Mechanical & Cooling Design | In Progress | 2026-02-04 08:00 | 2026-02-24 16:00 | 2026-02-04 08:00 |  | 15 | 5.3143 | 39 | No |  |  | 154000 | 154000 | 140506.4481 | 149160.3706 | -8653.9225 | -13493.5519 | 0.94198 | 0.91238 | Available | Available | Available | Available
Update 02 | 2026-02-28 | MEC-D-040 | Develop Chilled Water Distribution Design | Design & Engineering | Mechanical & Cooling Design | In Progress | 2026-02-11 08:00 | 2026-03-03 16:00 | 2026-02-11 08:00 |  | 15 | 2.4818 | 39 | No |  |  | 154000 | 126229.5082 | 128520.6473 | 129668.2063 | -1147.5589 | 2291.1391 | 0.99115 | 1.0182 | Available | Available | Available | Available
Update 02 | 2026-02-28 | MEC-D-050 | Develop CRAH CRAC System Design | Design & Engineering | Mechanical & Cooling Design | In Progress | 2026-02-04 08:00 | 2026-02-17 16:00 | 2026-02-04 08:00 |  | 10 | 0.13038 | 44 | No |  |  | 136000 | 136000 | 134226.7899 | 138251.3328 | -4024.543 | -1773.2101 | 0.97089 | 0.98696 | Available | Available | Available | Available
Update 02 | 2026-02-28 | MEC-D-060 | Develop Ventilation and Exhaust Design | Design & Engineering | Mechanical & Cooling Design | In Progress | 2026-02-05 08:00 | 2026-02-18 16:00 | 2026-02-05 08:00 |  | 10 | 7.9948 | 43 | No |  |  | 136000 | 136000 | 122470.7852 | 132065.8189 | -9595.0338 | -13529.2148 | 0.92735 | 0.90052 | Available | Available | Available | Available
Update 02 | 2026-02-28 | MEC-D-070 | Develop Mechanical Controls Requirements | Design & Engineering | Mechanical & Cooling Design | In Progress | 2026-02-18 08:00 | 2026-03-03 16:00 | 2026-02-18 08:00 |  | 10 | 2.9069 | 39 | No |  |  | 79000 | 57275 | 56035.4199 | 56994.7103 | -959.2904 | -1239.5801 | 0.98317 | 0.97836 | Available | Available | Available | Available
Update 02 | 2026-02-28 | MEC-D-080 | Mechanical Design Review | Design & Engineering | Mechanical & Cooling Design | Not Started | 2026-03-04 08:00 | 2026-03-12 16:00 |  |  | 7 | 7 | 39 | No |  |  | 20000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | MEC-D-090 | Mechanical Design Approved | Design & Engineering | Mechanical & Cooling Design | Not Started | 2026-03-12 16:00 | 2026-03-12 16:00 |  |  | 0 | 0 | 39 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | FLS-D-010 | Develop Fire and Life Safety Design Criteria | Design & Engineering | Fire & Life Safety Design | Completed | 2026-01-13 08:00 | 2026-01-19 16:00 | 2026-01-13 08:00 | 2026-01-19 16:00 | 5 | 0 |  | No |  |  | 111000 | 111000 | 111000 | 114779.5872 | -3779.5872 | 0 | 0.96707 | 1 | Available | Available | Available | Available
Update 02 | 2026-02-28 | FLS-D-020 | Develop Fire Detection and Alarm Design | Design & Engineering | Fire & Life Safety Design | Completed | 2026-01-20 08:00 | 2026-02-02 16:00 | 2026-01-20 08:00 | 2026-02-02 16:00 | 10 | 0 | 113 | No |  |  | 136000 | 136000 | 136000 | 137543.4412 | -1543.4412 | 0 | 0.98878 | 1 | Available | Available | Available | Available
Update 02 | 2026-02-28 | FLS-D-030 | Develop Fire Suppression System Design | Design & Engineering | Fire & Life Safety Design | In Progress | 2026-01-20 08:00 | 2026-02-02 16:00 | 2026-01-20 08:00 |  | 10 | 0.023615 | 113 | No |  |  | 136000 | 136000 | 135678.8401 | 137974.19 | -2295.3498 | -321.1599 | 0.98336 | 0.99764 | Available | Available | Available | Available
Update 02 | 2026-02-28 | FLS-D-040 | Develop VESDA and Early Warning Detection Design | Design & Engineering | Fire & Life Safety Design | In Progress | 2026-01-20 08:00 | 2026-01-29 16:00 | 2026-01-21 08:00 |  | 8 | 0.27947 | 112 | No |  |  | 127000 | 127000 | 122563.4657 | 125496.0196 | -2932.5538 | -4436.5343 | 0.97663 | 0.96507 | Available | Available | Available | Available
Update 02 | 2026-02-28 | FLS-D-050 | Develop Fire System Interface Matrix | Design & Engineering | Fire & Life Safety Design | In Progress | 2026-01-27 08:00 | 2026-02-02 16:00 | 2026-01-27 08:00 |  | 5 | 3.906 | 112 | No |  |  | 65000 | 65000 | 53221.8806 | 58571.0936 | -5349.213 | -11778.1194 | 0.90867 | 0.8188 | Available | Available | Available | Available
Update 02 | 2026-02-28 | FLS-D-060 | Fire and Life Safety Design Review | Design & Engineering | Fire & Life Safety Design | In Progress | 2026-02-04 08:00 | 2026-02-10 16:00 | 2026-02-04 08:00 |  | 5 | 3.8124 | 145 | No |  |  | 18000 | 18000 | 15075.5205 | 16562.2184 | -1486.698 | -2924.4795 | 0.91024 | 0.83753 | Available | Available | Available | Available
Update 02 | 2026-02-28 | FLS-D-070 | Fire and Life Safety Design Approved | Design & Engineering | Fire & Life Safety Design | In Progress | 2026-02-10 16:00 | 2026-02-10 16:00 | 2026-02-10 16:00 |  | 0 | 0 | 145 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | BMS-D-010 | Develop BMS Design Architecture | Design & Engineering | BMS, DCIM & Controls Design | In Progress | 2026-01-20 08:00 | 2026-02-02 16:00 | 2026-01-20 08:00 |  | 10 | 0.045451 | 103 | No |  |  | 136000 | 136000 | 135381.8704 | 140888.9145 | -5507.0441 | -618.1296 | 0.96091 | 0.99545 | Available | Available | Available | Available
Update 02 | 2026-02-28 | BMS-D-020 | Develop Mechanical Controls Architecture | Design & Engineering | BMS, DCIM & Controls Design | Not Started | 2026-03-04 08:00 | 2026-03-17 16:00 |  |  | 10 | 10 | 82 | No |  |  | 79000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | BMS-D-030 | Develop Electrical Monitoring Architecture | Design & Engineering | BMS, DCIM & Controls Design | In Progress | 2026-02-26 08:00 | 2026-03-11 16:00 | 2026-02-26 08:00 |  | 10 | 8.7638 | 86 | No |  |  | 23000 | 2875 | 2843.1973 | 2868.123 | -24.9257 | -31.8027 | 0.99131 | 0.98894 | Available | Available | Available | Available
Update 02 | 2026-02-28 | BMS-D-040 | Develop DCIM Architecture | Design & Engineering | BMS, DCIM & Controls Design | In Progress | 2026-02-03 08:00 | 2026-02-16 16:00 | 2026-02-03 08:00 |  | 10 | 7.8267 | 103 | No |  |  | 79000 | 79000 | 64569.2016 | 67521.965 | -2952.7634 | -14430.7984 | 0.95627 | 0.81733 | Available | Available | Available | Available
Update 02 | 2026-02-28 | BMS-D-050 | Develop Controls Integration Matrix | Design & Engineering | BMS, DCIM & Controls Design | Not Started | 2026-03-18 08:00 | 2026-03-31 16:00 |  |  | 10 | 10 | 82 | No |  |  | 79000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | BMS-D-060 | BMS DCIM and Controls Design Review | Design & Engineering | BMS, DCIM & Controls Design | Not Started | 2026-04-01 08:00 | 2026-04-07 16:00 |  |  | 5 | 5 | 82 | No |  |  | 18000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | BMS-D-070 | BMS DCIM and Controls Design Approved | Design & Engineering | BMS, DCIM & Controls Design | Not Started | 2026-04-07 16:00 | 2026-04-07 16:00 |  |  | 0 | 0 | 82 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | ICT-D-010 | Develop ICT Infrastructure Design | Design & Engineering | ICT & Security Systems Design | Completed | 2026-01-13 08:00 | 2026-01-26 16:00 | 2026-01-13 08:00 | 2026-01-26 16:00 | 10 | 0 |  | No |  |  | 136000 | 136000 | 136000 | 138370.4065 | -2370.4065 | 0 | 0.98287 | 1 | Available | Available | Available | Available
Update 02 | 2026-02-28 | ICT-D-020 | Develop Structured Cabling Design | Design & Engineering | ICT & Security Systems Design | In Progress | 2026-01-27 08:00 | 2026-02-09 16:00 | 2026-01-27 08:00 |  | 10 | 0.23981 | 98 | No |  |  | 136000 | 136000 | 132738.5214 | 136385.0821 | -3646.5607 | -3261.4786 | 0.97326 | 0.97602 | Available | Available | Available | Available
Update 02 | 2026-02-28 | ICT-D-030 | Develop CCTV System Design | Design & Engineering | ICT & Security Systems Design | In Progress | 2026-01-27 08:00 | 2026-02-05 16:00 | 2026-01-27 08:00 |  | 8 | 0.10932 | 100 | No |  |  | 127000 | 127000 | 125264.5053 | 130366.4643 | -5101.959 | -1735.4947 | 0.96086 | 0.98633 | Available | Available | Available | Available
Update 02 | 2026-02-28 | ICT-D-040 | Develop Access Control System Design | Design & Engineering | ICT & Security Systems Design | Completed | 2026-01-27 08:00 | 2026-02-05 16:00 | 2026-01-27 08:00 | 2026-02-05 16:00 | 8 | 0 | 100 | No |  |  | 127000 | 127000 | 127000 | 131523.0836 | -4523.0836 | 0 | 0.96561 | 1 | Available | Available | Available | Available
Update 02 | 2026-02-28 | ICT-D-050 | Develop Security System Integration Design | Design & Engineering | ICT & Security Systems Design | In Progress | 2026-02-10 08:00 | 2026-02-23 16:00 | 2026-02-10 08:00 |  | 10 | 0.33485 | 98 | No |  |  | 136000 | 136000 | 131445.978 | 133192.1803 | -1746.2023 | -4554.022 | 0.98689 | 0.96651 | Available | Available | Available | Available
Update 02 | 2026-02-28 | ICT-D-060 | ICT and Security Design Review | Design & Engineering | ICT & Security Systems Design | In Progress | 2026-02-24 08:00 | 2026-03-02 16:00 | 2026-02-24 08:00 |  | 5 | 2.1065 | 185 | No |  |  | 18000 | 10421.0526 | 10416.5232 | 10531.5298 | -115.0066 | -4.5294 | 0.98908 | 0.99957 | Available | Available | Available | Available
Update 02 | 2026-02-28 | ICT-D-070 | ICT and Security Design Approved | Design & Engineering | ICT & Security Systems Design | Not Started | 2026-03-02 16:00 | 2026-03-02 16:00 |  |  | 0 | 0 | 185 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | UTL-D-010 | Confirm Utility Power Requirements | Design & Engineering | Utility & Grid Connection Design | In Progress | 2026-02-05 08:00 | 2026-02-11 16:00 | 2026-02-05 08:00 |  | 5 | 0.16768 | 10 | No |  |  | 65000 | 65000 | 62820.1897 | 63031.9472 | -211.7575 | -2179.8103 | 0.99664 | 0.96646 | Available | Available | Available | Available
Update 02 | 2026-02-28 | UTL-D-020 | Develop Utility Connection Design | Design & Engineering | Utility & Grid Connection Design | In Progress | 2026-02-12 08:00 | 2026-03-04 16:00 | 2026-02-12 08:00 |  | 15 | 3.879 | 148 | No |  |  | 154000 | 118655.7377 | 114175.8611 | 116245.7209 | -2069.8598 | -4479.8766 | 0.98219 | 0.96224 | Available | Available | Available | Available
Update 02 | 2026-02-28 | UTL-D-030 | Develop Incoming MV Connection Design | Design & Engineering | Utility & Grid Connection Design | In Progress | 2026-02-12 08:00 | 2026-03-04 16:00 | 2026-02-12 08:00 |  | 15 | 3.3295 | 138 | No |  |  | 154000 | 118655.7377 | 119817.067 | 120743.16 | -926.0929 | 1161.3293 | 0.99233 | 1.0098 | Available | Available | Available | Available
Update 02 | 2026-02-28 | UTL-D-040 | Coordinate Utility Protection Requirements | Design & Engineering | Utility & Grid Connection Design | Not Started | 2026-03-05 08:00 | 2026-03-18 16:00 |  |  | 10 | 10 | 138 | No |  |  | 23000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | UTL-D-050 | Submit Utility Connection Design | Design & Engineering | Utility & Grid Connection Design | Not Started | 2026-03-19 08:00 | 2026-03-19 16:00 |  |  | 1 | 1 | 138 | No |  |  | 17000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | UTL-D-060 | Utility Design Review | Design & Engineering | Utility & Grid Connection Design | Not Started | 2026-03-20 08:00 | 2026-04-16 16:00 |  |  | 20 | 20 | 138 | No |  |  | 28000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | UTL-D-070 | Utility Connection Design Approved | Design & Engineering | Utility & Grid Connection Design | Not Started | 2026-04-16 16:00 | 2026-04-16 16:00 |  |  | 0 | 0 | 138 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | SD-010 | Establish Shop Drawing Schedule | Design & Engineering | Shop Drawings & Technical Approvals | Completed | 2026-01-20 08:00 | 2026-01-26 16:00 | 2026-01-20 08:00 | 2026-01-26 16:00 | 5 | 0 |  | No |  |  | 111000 | 111000 | 111000 | 114117.0436 | -3117.0436 | 0 | 0.97269 | 1 | Available | Available | Available | Available
Update 02 | 2026-02-28 | SD-020 | Prepare Civil and Structural Shop Drawings | Design & Engineering | Shop Drawings & Technical Approvals | Not Started | 2026-03-18 08:00 | 2026-04-07 16:00 |  |  | 15 | 15 | 149 | No |  |  | 154000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | SD-030 | Prepare Architectural Shop Drawings | Design & Engineering | Shop Drawings & Technical Approvals | In Progress | 2026-02-26 08:00 | 2026-03-18 16:00 | 2026-02-26 08:00 |  | 15 | 13.7982 | 163 | No |  |  | 154000 | 12622.9508 | 12338.3673 | 12582.4378 | -244.0705 | -284.5835 | 0.9806 | 0.97746 | Available | Available | Available | Available
Update 02 | 2026-02-28 | SD-040 | Prepare Electrical Shop Drawings | Design & Engineering | Shop Drawings & Technical Approvals | Not Started | 2026-03-30 08:00 | 2026-04-24 16:00 |  |  | 20 | 20 | 136 | No |  |  | 168000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | SD-050 | Prepare Mechanical Shop Drawings | Design & Engineering | Shop Drawings & Technical Approvals | Not Started | 2026-03-13 08:00 | 2026-04-09 16:00 |  |  | 20 | 20 | 147 | No |  |  | 168000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | SD-060 | Prepare Fire and Life Safety Shop Drawings | Design & Engineering | Shop Drawings & Technical Approvals | In Progress | 2026-02-11 08:00 | 2026-03-03 16:00 | 2026-02-11 08:00 |  | 15 | 2.5062 | 174 | No |  |  | 154000 | 126229.5082 | 128269.707 | 132704.1059 | -4434.3989 | 2040.1988 | 0.96658 | 1.0162 | Available | Available | Available | Available
Update 02 | 2026-02-28 | SD-070 | Prepare BMS DCIM and Controls Shop Drawings | Design & Engineering | Shop Drawings & Technical Approvals | Not Started | 2026-04-08 08:00 | 2026-04-28 16:00 |  |  | 15 | 15 | 134 | No |  |  | 154000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | SD-080 | Consultant Review of Shop Drawings | Design & Engineering | Shop Drawings & Technical Approvals | Not Started | 2026-04-15 08:00 | 2026-04-28 16:00 |  |  | 10 | 10 | 134 | No |  |  | 23000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | SD-090 | Resolve Shop Drawing Comments | Design & Engineering | Shop Drawings & Technical Approvals | Not Started | 2026-04-29 08:00 | 2026-05-12 16:00 |  |  | 10 | 10 | 134 | No |  |  | 136000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | SD-100 | Technical Shop Drawings Approved | Design & Engineering | Shop Drawings & Technical Approvals | Not Started | 2026-05-12 16:00 | 2026-05-12 16:00 |  |  | 0 | 0 | 134 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | PRM-010 | Develop Project Procurement Plan | Procurement | Procurement Management | Completed | 2026-01-06 08:00 | 2026-01-12 16:00 | 2026-01-06 08:00 | 2026-01-12 16:00 | 5 | 0 |  | No |  |  | 89000 | 89000 | 89000 | 92535.1745 | -3535.1745 | 0 | 0.9618 | 1 | Available | Available | Available | Available
Update 02 | 2026-02-28 | PRM-020 | Develop Procurement Schedule | Procurement | Procurement Management | Completed | 2026-01-13 08:00 | 2026-01-19 16:00 | 2026-01-13 08:00 | 2026-01-19 16:00 | 5 | 0 |  | No |  |  | 89000 | 89000 | 89000 | 91057.547 | -2057.547 | 0 | 0.9774 | 1 | Available | Available | Available | Available
Update 02 | 2026-02-28 | PRM-030 | Establish Approved Vendor List | Procurement | Procurement Management | Completed | 2026-01-20 08:00 | 2026-01-28 16:00 | 2026-01-21 08:00 | 2026-01-28 16:00 | 7 | 0 | 127 | No |  |  | 49000 | 49000 | 49000 | 49497.7333 | -497.7333 | 0 | 0.98994 | 1 | Available | Available | Available | Available
Update 02 | 2026-02-28 | PRM-040 | Establish Procurement Tracking Register | Procurement | Procurement Management | Completed | 2026-02-05 08:00 | 2026-02-18 16:00 | 2026-02-05 08:00 | 2026-02-18 16:00 | 10 | 0 | 127 | No |  |  | 55000 | 55000 | 55000 | 56079.2831 | -1079.2831 | 0 | 0.98075 | 1 | Available | Available | Available | Available
Update 02 | 2026-02-28 | PRM-050 | Procurement Strategy Approved | Procurement | Procurement Management | Completed | 2026-02-19 08:00 | 2026-02-27 16:00 | 2026-02-19 08:00 | 2026-02-27 16:00 | 7 | 0 | 127 | No |  |  | 74000 | 74000 | 74000 | 75015.2222 | -1015.2222 | 0 | 0.98647 | 1 | Available | Available | Available | Available
Update 02 | 2026-02-28 | SWG-010 | Prepare MV/LV Switchgear Technical Submittal | Procurement | MV/LV Switchgear | Not Started | 2026-03-05 08:00 | 2026-03-13 16:00 |  |  | 7 | 7 | 31 | No |  |  | 186000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | SWG-020 | MV/LV Switchgear Technical Submittal Approval | Procurement | MV/LV Switchgear | Not Started | 2026-03-30 08:00 | 2026-04-07 16:00 |  |  | 7 | 7 | 21 | No |  |  | 186000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | SWG-030 | Issue Purchase Order - MV/LV Switchgear | Procurement | MV/LV Switchgear | Not Started | 2026-04-08 08:00 | 2026-04-10 16:00 |  |  | 3 | 3 | 21 | No |  |  | 240000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | SWG-040 | Manufacture MV/LV Switchgear | Procurement | MV/LV Switchgear | Not Started | 2026-04-13 08:00 | 2026-09-25 16:00 |  |  | 120 | 120 | 21 | No |  |  | 4353000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | SWG-050 | Factory Acceptance Test - MV/LV Switchgear | Procurement | MV/LV Switchgear | Not Started | 2026-09-28 08:00 | 2026-09-30 16:00 |  |  | 3 | 3 | 21 | No |  |  | 312000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | SWG-060 | Ship MV/LV Switchgear | Procurement | MV/LV Switchgear | Not Started | 2026-10-01 08:00 | 2026-10-21 16:00 |  |  | 15 | 15 | 21 | No |  |  | 311000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | SWG-070 | Deliver MV/LV Switchgear to Site | Procurement | MV/LV Switchgear | Not Started | 2026-10-22 08:00 | 2026-10-23 16:00 |  |  | 2 | 2 | 21 | No |  |  | 170000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | TRF-010 | Prepare Transformer Technical Submittal | Procurement | Transformers | In Progress | 2026-02-19 08:00 | 2026-02-27 16:00 | 2026-02-19 08:00 |  | 7 | 0.24032 | 20 | No |  |  | 223000 | 223000 | 215343.964 | 217547.3742 | -2203.4102 | -7656.036 | 0.98987 | 0.96567 | Available | Available | Available | Available
Update 02 | 2026-02-28 | TRF-020 | Transformer Technical Submittal Approval | Procurement | Transformers | Not Started | 2026-03-30 08:00 | 2026-04-07 16:00 |  |  | 7 | 7 | 0 | Yes | 1 | 6 | 223000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | TRF-030 | Issue Purchase Order - Transformers | Procurement | Transformers | Not Started | 2026-04-08 08:00 | 2026-04-10 16:00 |  |  | 3 | 3 | 0 | Yes | 1 | 7 | 288000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | TRF-040 | Manufacture Transformers | Procurement | Transformers | Not Started | 2026-04-13 08:00 | 2026-11-06 16:00 |  |  | 150 | 150 | 0 | Yes | 1 | 8 | 5588000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | TRF-050 | Factory Acceptance Test - Transformers | Procurement | Transformers | Not Started | 2026-11-09 08:00 | 2026-11-11 16:00 |  |  | 3 | 3 | 0 | Yes | 1 | 9 | 374000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | TRF-060 | Ship Transformers | Procurement | Transformers | Not Started | 2026-11-12 08:00 | 2026-12-09 16:00 |  |  | 20 | 20 | 0 | Yes | 1 | 10 | 407000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | TRF-070 | Deliver Transformers to Site | Procurement | Transformers | Not Started | 2026-12-10 08:00 | 2026-12-11 16:00 |  |  | 2 | 2 | 0 | Yes | 1 | 11 | 204000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | UPS-010 | Prepare UPS and Battery Technical Submittal | Procurement | UPS Systems & Batteries | In Progress | 2026-02-26 08:00 | 2026-03-06 16:00 | 2026-02-26 08:00 |  | 7 | 5.5773 | 52 | No |  |  | 186000 | 37200 | 37802.967 | 38986.6475 | -1183.6805 | 602.967 | 0.96964 | 1.0162 | Available | Available | Available | Available
Update 02 | 2026-02-28 | UPS-020 | UPS and Battery Technical Submittal Approval | Procurement | UPS Systems & Batteries | Not Started | 2026-03-30 08:00 | 2026-04-07 16:00 |  |  | 7 | 7 | 37 | No |  |  | 186000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | UPS-030 | Issue Purchase Order - UPS and Batteries | Procurement | UPS Systems & Batteries | Not Started | 2026-04-08 08:00 | 2026-04-10 16:00 |  |  | 3 | 3 | 37 | No |  |  | 240000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | UPS-040 | Manufacture UPS Systems and Batteries | Procurement | UPS Systems & Batteries | Not Started | 2026-04-13 08:00 | 2026-09-25 16:00 |  |  | 120 | 120 | 37 | No |  |  | 4353000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | UPS-050 | Factory Acceptance Test - UPS Systems | Procurement | UPS Systems & Batteries | Not Started | 2026-09-28 08:00 | 2026-09-30 16:00 |  |  | 3 | 3 | 37 | No |  |  | 312000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | UPS-060 | Ship UPS Systems and Batteries | Procurement | UPS Systems & Batteries | Not Started | 2026-10-01 08:00 | 2026-10-21 16:00 |  |  | 15 | 15 | 37 | No |  |  | 311000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | UPS-070 | Deliver UPS Systems and Batteries to Site | Procurement | UPS Systems & Batteries | Not Started | 2026-10-22 08:00 | 2026-10-23 16:00 |  |  | 2 | 2 | 37 | No |  |  | 170000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | GEN-010 | Prepare Standby Generator Technical Submittal | Procurement | Standby Generators | In Progress | 2026-02-19 08:00 | 2026-02-27 16:00 | 2026-02-19 08:00 |  | 7 | 4.7964 | 38 | No |  |  | 208000 | 208000 | 184334.2872 | 202744.0425 | -18409.7553 | -23665.7128 | 0.9092 | 0.88622 | Available | Available | Available | Available
Update 02 | 2026-02-28 | GEN-020 | Standby Generator Technical Submittal Approval | Procurement | Standby Generators | Not Started | 2026-03-30 08:00 | 2026-04-07 16:00 |  |  | 7 | 7 | 18 | No |  |  | 208000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | GEN-030 | Issue Purchase Order - Standby Generators | Procurement | Standby Generators | Not Started | 2026-04-08 08:00 | 2026-04-10 16:00 |  |  | 3 | 3 | 18 | No |  |  | 269000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | GEN-040 | Manufacture Standby Generators | Procurement | Standby Generators | Not Started | 2026-04-13 08:00 | 2026-11-06 16:00 |  |  | 150 | 150 | 18 | No |  |  | 5213000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | GEN-050 | Factory Acceptance Test - Standby Generators | Procurement | Standby Generators | Not Started | 2026-11-09 08:00 | 2026-11-11 16:00 |  |  | 3 | 3 | 18 | No |  |  | 349000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | GEN-060 | Ship Standby Generators | Procurement | Standby Generators | Not Started | 2026-11-12 08:00 | 2026-12-09 16:00 |  |  | 20 | 20 | 18 | No |  |  | 380000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | GEN-070 | Deliver Standby Generators to Site | Procurement | Standby Generators | Not Started | 2026-12-10 08:00 | 2026-12-11 16:00 |  |  | 2 | 2 | 18 | No |  |  | 190000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CLP-010 | Prepare Cooling Plant Equipment Technical Submittal | Procurement | Cooling Plant Equipment | In Progress | 2026-02-25 08:00 | 2026-03-05 16:00 | 2026-02-25 08:00 |  | 7 | 11.1187 | 44 | No |  |  | 178000 | 56960 | 47839.3688 | 52467.7551 | -4628.3864 | -9120.6312 | 0.91179 | 0.83988 | Available | Available | Available | Available
Update 02 | 2026-02-28 | CLP-020 | Cooling Plant Equipment Technical Submittal Approval | Procurement | Cooling Plant Equipment | Not Started | 2026-03-13 08:00 | 2026-03-23 16:00 |  |  | 7 | 7 | 39 | No |  |  | 178000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CLP-030 | Issue Purchase Order - Cooling Plant Equipment | Procurement | Cooling Plant Equipment | Not Started | 2026-03-24 08:00 | 2026-03-26 16:00 |  |  | 3 | 3 | 39 | No |  |  | 230000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CLP-040 | Manufacture Cooling Plant Equipment | Procurement | Cooling Plant Equipment | Not Started | 2026-03-27 08:00 | 2026-07-30 16:00 |  |  | 90 | 90 | 39 | No |  |  | 3833000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CLP-050 | Factory Acceptance Test - Cooling Plant Equipment | Procurement | Cooling Plant Equipment | Not Started | 2026-07-31 08:00 | 2026-08-04 16:00 |  |  | 3 | 3 | 39 | No |  |  | 299000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CLP-060 | Ship Cooling Plant Equipment | Procurement | Cooling Plant Equipment | Not Started | 2026-08-05 08:00 | 2026-08-25 16:00 |  |  | 15 | 15 | 39 | No |  |  | 299000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CLP-070 | Deliver Cooling Plant Equipment to Site | Procurement | Cooling Plant Equipment | Not Started | 2026-08-26 08:00 | 2026-08-27 16:00 |  |  | 2 | 2 | 39 | No |  |  | 163000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CRAH-010 | Prepare CRAH/CRAC Technical Submittal | Procurement | CRAH/CRAC Units | Completed | 2026-02-18 08:00 | 2026-02-26 16:00 | 2026-02-18 08:00 | 2026-02-26 16:00 | 7 | 0 | 63 | No |  |  | 148000 | 148000 | 148000 | 148166.9757 | -166.9757 | 0 | 0.99887 | 1 | Available | Available | Available | Available
Update 02 | 2026-02-28 | CRAH-020 | CRAH/CRAC Technical Submittal Approval | Procurement | CRAH/CRAC Units | Not Started | 2026-03-13 08:00 | 2026-03-23 16:00 |  |  | 7 | 7 | 53 | No |  |  | 148000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CRAH-030 | Issue Purchase Order - CRAH/CRAC Units | Procurement | CRAH/CRAC Units | Not Started | 2026-03-24 08:00 | 2026-03-26 16:00 |  |  | 3 | 3 | 53 | No |  |  | 192000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CRAH-040 | Manufacture CRAH/CRAC Units | Procurement | CRAH/CRAC Units | Not Started | 2026-03-27 08:00 | 2026-07-30 16:00 |  |  | 90 | 90 | 53 | No |  |  | 3194000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CRAH-050 | Factory Acceptance Test - CRAH/CRAC Units | Procurement | CRAH/CRAC Units | Not Started | 2026-07-31 08:00 | 2026-08-04 16:00 |  |  | 3 | 3 | 53 | No |  |  | 249000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CRAH-060 | Ship CRAH/CRAC Units | Procurement | CRAH/CRAC Units | Not Started | 2026-08-05 08:00 | 2026-08-25 16:00 |  |  | 15 | 15 | 53 | No |  |  | 249000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CRAH-070 | Deliver CRAH/CRAC Units to Site | Procurement | CRAH/CRAC Units | Not Started | 2026-08-26 08:00 | 2026-08-27 16:00 |  |  | 2 | 2 | 53 | No |  |  | 136000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | FLS-P-010 | Prepare Fire and Life Safety Equipment Submittal | Procurement | Fire & Life Safety Equipment | In Progress | 2026-02-04 08:00 | 2026-02-10 16:00 | 2026-02-04 08:00 |  | 5 | 0.15683 | 145 | No |  |  | 94000 | 94000 | 91051.5819 | 94790.3551 | -3738.7732 | -2948.4181 | 0.96056 | 0.96863 | Available | Available | Available | Available
Update 02 | 2026-02-28 | FLS-P-020 | Fire and Life Safety Equipment Submittal Approval | Procurement | Fire & Life Safety Equipment | In Progress | 2026-02-11 08:00 | 2026-02-19 16:00 | 2026-02-11 08:00 |  | 7 | 0.22463 | 145 | No |  |  | 104000 | 104000 | 100662.5706 | 101977.4323 | -1314.8616 | -3337.4294 | 0.98711 | 0.96791 | Available | Available | Available | Available
Update 02 | 2026-02-28 | FLS-P-030 | Issue Purchase Order - Fire and Life Safety Equipment | Procurement | Fire & Life Safety Equipment | In Progress | 2026-02-20 08:00 | 2026-02-24 16:00 | 2026-02-20 08:00 |  | 3 | 7.5362 | 145 | No |  |  | 134000 | 134000 | 110049.6422 | 116868.232 | -6818.5898 | -23950.3578 | 0.94166 | 0.82127 | Available | Available | Available | Available
Update 02 | 2026-02-28 | FLS-P-040 | Manufacture Fire and Life Safety Equipment | Procurement | Fire & Life Safety Equipment | In Progress | 2026-02-25 08:00 | 2026-05-19 16:00 | 2026-02-25 08:00 |  | 60 | 58.1338 | 145 | No |  |  | 1980000 | 63360 | 61585.0671 | 62071.3977 | -486.3306 | -1774.9329 | 0.99216 | 0.97199 | Available | Available | Available | Available
Update 02 | 2026-02-28 | FLS-P-050 | Factory Testing - Fire and Life Safety Equipment | Procurement | Fire & Life Safety Equipment | Not Started | 2026-05-20 08:00 | 2026-05-22 16:00 |  |  | 3 | 3 | 145 | No |  |  | 107000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | FLS-P-060 | Ship Fire and Life Safety Equipment | Procurement | Fire & Life Safety Equipment | Not Started | 2026-05-25 08:00 | 2026-06-05 16:00 |  |  | 10 | 10 | 145 | No |  |  | 154000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | FLS-P-070 | Deliver Fire and Life Safety Equipment to Site | Procurement | Fire & Life Safety Equipment | Not Started | 2026-06-08 08:00 | 2026-06-09 16:00 |  |  | 2 | 2 | 145 | No |  |  | 95000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | BMS-P-010 | Prepare BMS DCIM and Controls Equipment Submittal | Procurement | BMS, DCIM & Controls Equipment | Not Started | 2026-04-01 08:00 | 2026-04-07 16:00 |  |  | 5 | 5 | 82 | No |  |  | 101000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | BMS-P-020 | BMS DCIM and Controls Equipment Submittal Approval | Procurement | BMS, DCIM & Controls Equipment | Not Started | 2026-04-08 08:00 | 2026-04-16 16:00 |  |  | 7 | 7 | 82 | No |  |  | 111000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | BMS-P-030 | Issue Purchase Order - BMS DCIM and Controls Equipment | Procurement | BMS, DCIM & Controls Equipment | Not Started | 2026-04-17 08:00 | 2026-04-21 16:00 |  |  | 3 | 3 | 82 | No |  |  | 144000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | BMS-P-040 | Configure and Manufacture Controls Equipment | Procurement | BMS, DCIM & Controls Equipment | Not Started | 2026-04-22 08:00 | 2026-07-14 16:00 |  |  | 60 | 60 | 82 | No |  |  | 1414000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | BMS-P-050 | Factory Testing - BMS DCIM and Controls | Procurement | BMS, DCIM & Controls Equipment | Not Started | 2026-07-15 08:00 | 2026-07-21 16:00 |  |  | 5 | 5 | 82 | No |  |  | 134000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | BMS-P-060 | Ship BMS DCIM and Controls Equipment | Procurement | BMS, DCIM & Controls Equipment | Not Started | 2026-07-22 08:00 | 2026-08-04 16:00 |  |  | 10 | 10 | 82 | No |  |  | 165000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | BMS-P-070 | Deliver BMS DCIM and Controls Equipment to Site | Procurement | BMS, DCIM & Controls Equipment | Not Started | 2026-08-05 08:00 | 2026-08-06 16:00 |  |  | 2 | 2 | 82 | No |  |  | 102000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | ICT-P-010 | Prepare ICT and Security Equipment Submittal | Procurement | ICT & Security Equipment | In Progress | 2026-02-24 08:00 | 2026-03-02 16:00 | 2026-02-24 08:00 |  | 5 | 2.0927 | 242 | No |  |  | 67000 | 38789.4737 | 38957.7828 | 40360.6249 | -1402.8421 | 168.3091 | 0.96524 | 1.0043 | Available | Available | Available | Available
Update 02 | 2026-02-28 | ICT-P-020 | ICT and Security Equipment Submittal Approval | Procurement | ICT & Security Equipment | Not Started | 2026-03-03 08:00 | 2026-03-09 16:00 |  |  | 5 | 5 | 242 | No |  |  | 67000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | ICT-P-030 | Issue Purchase Order - ICT and Security Equipment | Procurement | ICT & Security Equipment | Not Started | 2026-03-10 08:00 | 2026-03-12 16:00 |  |  | 3 | 3 | 242 | No |  |  | 96000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | ICT-P-040 | Procure ICT and Security Equipment | Procurement | ICT & Security Equipment | Not Started | 2026-03-13 08:00 | 2026-04-23 16:00 |  |  | 30 | 30 | 242 | No |  |  | 153000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | ICT-P-050 | Factory Configuration and Testing - ICT and Security | Procurement | ICT & Security Equipment | Not Started | 2026-04-24 08:00 | 2026-04-30 16:00 |  |  | 5 | 5 | 242 | No |  |  | 89000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | ICT-P-060 | Ship ICT and Security Equipment | Procurement | ICT & Security Equipment | Not Started | 2026-05-01 08:00 | 2026-05-14 16:00 |  |  | 10 | 10 | 242 | No |  |  | 110000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | ICT-P-070 | Deliver ICT and Security Equipment to Site | Procurement | ICT & Security Equipment | Not Started | 2026-05-15 08:00 | 2026-05-18 16:00 |  |  | 2 | 2 | 242 | No |  |  | 68000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | ABM-010 | Prepare Architectural Materials Submittals | Procurement | Architectural & Building Materials | In Progress | 2026-02-26 08:00 | 2026-03-04 16:00 | 2026-02-26 08:00 |  | 5 | 5.8085 | 94 | No |  |  | 67000 | 17631.5789 | 15965.6153 | 17390.6595 | -1425.0442 | -1665.9636 | 0.91806 | 0.90551 | Available | Available | Available | Available
Update 02 | 2026-02-28 | ABM-020 | Architectural Materials Submittals Approval | Procurement | Architectural & Building Materials | Not Started | 2026-03-05 08:00 | 2026-03-11 16:00 |  |  | 5 | 5 | 94 | No |  |  | 67000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | ABM-030 | Procure Roofing and Waterproofing Materials | Procurement | Architectural & Building Materials | Not Started | 2026-03-12 08:00 | 2026-04-01 16:00 |  |  | 15 | 15 | 94 | No |  |  | 124000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | ABM-040 | Procure External Cladding Materials | Procurement | Architectural & Building Materials | Not Started | 2026-04-02 08:00 | 2026-04-29 16:00 |  |  | 20 | 20 | 94 | No |  |  | 136000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | ABM-050 | Procure Doors Louvers and Fire-Rated Assemblies | Procurement | Architectural & Building Materials | Not Started | 2026-04-30 08:00 | 2026-05-20 16:00 |  |  | 15 | 15 | 94 | No |  |  | 174000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | ABM-060 | Deliver Architectural Materials to Site | Procurement | Architectural & Building Materials | Not Started | 2026-05-21 08:00 | 2026-05-25 16:00 |  |  | 3 | 3 | 94 | No |  |  | 77000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | LLE-010 | Identify Long-Lead Equipment | Procurement | Long-Lead Equipment Management | Not Started | 2026-03-02 08:00 | 2026-03-06 16:00 |  |  | 5 | 5 | 127 | No |  |  | 89000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | LLE-020 | Establish Long-Lead Equipment Register | Procurement | Long-Lead Equipment Management | Not Started | 2026-03-09 08:00 | 2026-03-13 16:00 |  |  | 5 | 5 | 127 | No |  |  | 45000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | LLE-030 | Confirm Required-on-Site Dates | Procurement | Long-Lead Equipment Management | Not Started | 2026-03-16 08:00 | 2026-03-20 16:00 |  |  | 5 | 5 | 127 | No |  |  | 89000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | LLE-040 | Monitor Vendor Engineering and Manufacturing | Procurement | Long-Lead Equipment Management | Not Started | 2026-04-08 08:00 | 2026-08-11 16:00 |  |  | 90 | 90 | 115 | No |  |  | 106000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | LLE-050 | Monitor FAT and Shipping Readiness | Procurement | Long-Lead Equipment Management | Not Started | 2026-08-12 08:00 | 2026-08-18 16:00 |  |  | 5 | 5 | 115 | No |  |  | 45000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | LLE-060 | Long-Lead Equipment Delivery Readiness Confirmed | Procurement | Long-Lead Equipment Management | Not Started | 2026-11-11 16:00 | 2026-11-11 16:00 |  |  | 0 | 0 | 54 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | MOB-010 | Mobilize Project Team to Site | Enabling & Site Works | Mobilization & Temporary Facilities | Completed | 2026-01-06 08:00 | 2026-01-10 16:00 | 2026-01-06 08:00 | 2026-01-10 16:00 | 5 | 0 |  | No |  |  | 87000 | 87000 | 87000 | 88816.8951 | -1816.8951 | 0 | 0.97954 | 1 | Available | Available | Available | Available
Update 02 | 2026-02-28 | MOB-020 | Establish Site Offices and Welfare Facilities | Enabling & Site Works | Mobilization & Temporary Facilities | Completed | 2026-01-12 08:00 | 2026-01-16 16:00 | 2026-01-12 08:00 | 2026-01-16 16:00 | 5 | 0 |  | No |  |  | 87000 | 87000 | 87000 | 88189.2704 | -1189.2704 | 0 | 0.98651 | 1 | Available | Available | Available | Available
Update 02 | 2026-02-28 | MOB-030 | Install Temporary Site Fencing and Hoarding | Enabling & Site Works | Mobilization & Temporary Facilities | Completed | 2026-01-12 08:00 | 2026-01-16 16:00 | 2026-01-12 08:00 | 2026-01-16 16:00 | 5 | 0 |  | No |  |  | 116000 | 116000 | 116000 | 116206.2742 | -206.2742 | 0 | 0.99822 | 1 | Available | Available | Available | Available
Update 02 | 2026-02-28 | MOB-040 | Establish Temporary Storage and Laydown Areas | Enabling & Site Works | Mobilization & Temporary Facilities | Completed | 2026-01-12 08:00 | 2026-01-16 16:00 | 2026-01-12 08:00 | 2026-01-16 16:00 | 5 | 0 |  | No |  |  | 87000 | 87000 | 87000 | 89556.1244 | -2556.1244 | 0 | 0.97146 | 1 | Available | Available | Available | Available
Update 02 | 2026-02-28 | MOB-050 | Establish Site Security and Access Control | Enabling & Site Works | Mobilization & Temporary Facilities | Completed | 2026-01-12 08:00 | 2026-01-16 16:00 | 2026-01-12 08:00 | 2026-01-16 16:00 | 5 | 0 |  | No |  |  | 87000 | 87000 | 87000 | 87262.456 | -262.456 | 0 | 0.99699 | 1 | Available | Available | Available | Available
Update 02 | 2026-02-28 | MOB-060 | Site Mobilization Complete | Enabling & Site Works | Mobilization & Temporary Facilities | In Progress | 2026-02-14 08:00 | 2026-02-14 08:00 | 2026-02-14 08:00 |  | 0 | 4 | 32 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | SUR-010 | Establish Survey Control Points | Enabling & Site Works | Surveying & Setting Out | In Progress | 2026-02-14 08:00 | 2026-02-17 16:00 | 2026-02-14 08:00 |  | 3 | 0.10094 | 32 | No |  |  | 75000 | 75000 | 72476.5383 | 75057.4966 | -2580.9583 | -2523.4617 | 0.96561 | 0.96635 | Available | Available | Available | Available
Update 02 | 2026-02-28 | SUR-020 | Conduct Existing Site Topographic Survey | Enabling & Site Works | Surveying & Setting Out | Completed | 2026-02-18 08:00 | 2026-02-23 16:00 | 2026-02-18 08:00 | 2026-02-23 16:00 | 5 | 0 | 32 | No |  |  | 87000 | 87000 | 87000 | 88428.8599 | -1428.8599 | 0 | 0.98384 | 1 | Available | Available | Available | Available
Update 02 | 2026-02-28 | SUR-030 | Verify Existing Site Levels and Boundaries | Enabling & Site Works | Surveying & Setting Out | Completed | 2026-02-24 08:00 | 2026-02-25 16:00 | 2026-02-24 08:00 | 2026-02-25 16:00 | 2 | 0 | 32 | No |  |  | 66000 | 66000 | 66000 | 67436.7215 | -1436.7215 | 0 | 0.9787 | 1 | Available | Available | Available | Available
Update 02 | 2026-02-28 | SUR-040 | Set Out Main Building Footprint | Enabling & Site Works | Surveying & Setting Out | In Progress | 2026-02-26 08:00 | 2026-02-28 16:00 | 2026-02-26 08:00 |  | 3 | 0.94056 | 91 | No |  |  | 75000 | 53571.4286 | 51485.9039 | 53388.3575 | -1902.4536 | -2085.5246 | 0.96437 | 0.96107 | Available | Available | Available | Available
Update 02 | 2026-02-28 | SUR-050 | Set Out External Infrastructure and Utility Routes | Enabling & Site Works | Surveying & Setting Out | In Progress | 2026-02-26 08:00 | 2026-02-28 16:00 | 2026-02-26 08:00 |  | 3 | 0.84041 | 91 | No |  |  | 75000 | 53571.4286 | 53989.7692 | 55699.4281 | -1709.6589 | 418.3406 | 0.96931 | 1.0078 | Available | Available | Available | Available
Update 02 | 2026-02-28 | SUR-060 | Survey and Setting Out Complete | Enabling & Site Works | Surveying & Setting Out | Not Started | 2026-03-02 08:00 | 2026-03-02 08:00 |  |  | 0 | 0 | 91 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | SCP-010 | Clear Existing Vegetation and Obstructions | Enabling & Site Works | Site Clearance & Preparation | In Progress | 2026-02-26 08:00 | 2026-03-05 16:00 | 2026-02-26 08:00 |  | 7 | 5.4149 | 32 | No |  |  | 96000 | 21818.1818 | 21738.7843 | 21854.4038 | -115.6195 | -79.3975 | 0.99471 | 0.99636 | Available | Available | Available | Available
Update 02 | 2026-02-28 | SCP-020 | Remove Existing Surface Materials | Enabling & Site Works | Site Clearance & Preparation | Not Started | 2026-03-06 08:00 | 2026-03-11 16:00 |  |  | 5 | 5 | 32 | No |  |  | 87000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | SCP-030 | Remove or Divert Existing Minor Services | Enabling & Site Works | Site Clearance & Preparation | Not Started | 2026-03-12 08:00 | 2026-03-19 16:00 |  |  | 7 | 7 | 32 | No |  |  | 96000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | SCP-040 | Strip and Stockpile Topsoil | Enabling & Site Works | Site Clearance & Preparation | Not Started | 2026-03-20 08:00 | 2026-03-25 16:00 |  |  | 5 | 5 | 32 | No |  |  | 87000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | SCP-050 | Prepare Site for Earthworks | Enabling & Site Works | Site Clearance & Preparation | Not Started | 2026-03-26 08:00 | 2026-03-28 16:00 |  |  | 3 | 3 | 32 | No |  |  | 75000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | SCP-060 | Site Clearance Complete | Enabling & Site Works | Site Clearance & Preparation | Not Started | 2026-03-30 08:00 | 2026-03-30 08:00 |  |  | 0 | 0 | 32 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | EW-010 | Bulk Excavation | Enabling & Site Works | Earthworks & Excavation | Not Started | 2026-03-30 08:00 | 2026-04-09 16:00 |  |  | 10 | 10 | 32 | No |  |  | 107000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | EW-020 | Excavate Building Formation | Enabling & Site Works | Earthworks & Excavation | Not Started | 2026-04-10 08:00 | 2026-04-21 16:00 |  |  | 10 | 10 | 32 | No |  |  | 107000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | EW-030 | Excavate Utility and Drainage Routes | Enabling & Site Works | Earthworks & Excavation | Not Started | 2026-04-01 08:00 | 2026-04-11 16:00 |  |  | 10 | 10 | 139 | No |  |  | 107000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | EW-040 | Place Engineered Fill | Enabling & Site Works | Earthworks & Excavation | Not Started | 2026-04-22 08:00 | 2026-04-29 16:00 |  |  | 7 | 7 | 32 | No |  |  | 96000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | EW-050 | Compact and Test Formation | Enabling & Site Works | Earthworks & Excavation | Not Started | 2026-04-30 08:00 | 2026-05-02 16:00 |  |  | 3 | 3 | 32 | No |  |  | 75000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | EW-060 | Prepare Formation for Foundations | Enabling & Site Works | Earthworks & Excavation | Not Started | 2026-05-04 08:00 | 2026-05-08 16:00 |  |  | 5 | 5 | 32 | No |  |  | 116000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | EW-070 | Earthworks Complete | Enabling & Site Works | Earthworks & Excavation | Not Started | 2026-05-09 08:00 | 2026-05-09 08:00 |  |  | 0 | 0 | 300 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | TU-010 | Install Temporary Electrical Supply | Enabling & Site Works | Temporary Utilities | In Progress | 2026-02-14 08:00 | 2026-02-19 16:00 | 2026-02-14 08:00 |  | 5 | 0.076229 | 37 | No |  |  | 116000 | 116000 | 114231.4981 | 117164.433 | -2932.9349 | -1768.5019 | 0.97497 | 0.98475 | Available | Available | Available | Available
Update 02 | 2026-02-28 | TU-020 | Install Temporary Water Supply | Enabling & Site Works | Temporary Utilities | Completed | 2026-02-14 08:00 | 2026-02-19 16:00 | 2026-02-14 08:00 | 2026-02-19 16:00 | 5 | 0 | 37 | No |  |  | 116000 | 116000 | 116000 | 116618.1197 | -618.1197 | 0 | 0.9947 | 1 | Available | Available | Available | Available
Update 02 | 2026-02-28 | TU-030 | Install Temporary Drainage Facilities | Enabling & Site Works | Temporary Utilities | In Progress | 2026-02-14 08:00 | 2026-02-19 16:00 | 2026-02-14 08:00 |  | 5 | 0.12565 | 37 | No |  |  | 116000 | 116000 | 113084.9634 | 116646.5927 | -3561.6294 | -2915.0366 | 0.96947 | 0.97487 | Available | Available | Available | Available
Update 02 | 2026-02-28 | TU-040 | Install Temporary Site Lighting | Enabling & Site Works | Temporary Utilities | Completed | 2026-02-14 08:00 | 2026-02-19 16:00 | 2026-02-14 08:00 | 2026-02-19 16:00 | 5 | 0 | 37 | No |  |  | 116000 | 116000 | 116000 | 120305.6024 | -4305.6024 | 0 | 0.96421 | 1 | Available | Available | Available | Available
Update 02 | 2026-02-28 | TU-050 | Temporary Site Utilities Operational | Enabling & Site Works | Temporary Utilities | In Progress | 2026-02-20 08:00 | 2026-02-20 08:00 | 2026-02-20 08:00 |  | 0 | 4 | 37 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | UGU-010 | Set Out Underground Utility Routes | Enabling & Site Works | Underground Site Utilities | Not Started | 2026-04-13 08:00 | 2026-04-15 16:00 |  |  | 3 | 3 | 139 | No |  |  | 75000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | UGU-020 | Excavate Underground Utility Trenches | Enabling & Site Works | Underground Site Utilities | Not Started | 2026-04-16 08:00 | 2026-04-27 16:00 |  |  | 10 | 10 | 139 | No |  |  | 107000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | UGU-030 | Install Underground Electrical Duct Banks | Enabling & Site Works | Underground Site Utilities | Not Started | 2026-04-28 08:00 | 2026-05-08 16:00 |  |  | 10 | 10 | 139 | No |  |  | 136000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | UGU-040 | Install Underground ICT Duct Banks | Enabling & Site Works | Underground Site Utilities | Not Started | 2026-04-28 08:00 | 2026-05-06 16:00 |  |  | 8 | 8 | 141 | No |  |  | 133000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | UGU-050 | Install Underground Water Services | Enabling & Site Works | Underground Site Utilities | Not Started | 2026-04-28 08:00 | 2026-05-06 16:00 |  |  | 8 | 8 | 141 | No |  |  | 133000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | UGU-060 | Install Underground Fire Water Services | Enabling & Site Works | Underground Site Utilities | Not Started | 2026-04-28 08:00 | 2026-05-06 16:00 |  |  | 8 | 8 | 141 | No |  |  | 133000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | UGU-070 | Install Utility Chambers and Manholes | Enabling & Site Works | Underground Site Utilities | Not Started | 2026-04-28 08:00 | 2026-05-06 16:00 |  |  | 8 | 8 | 141 | No |  |  | 133000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | UGU-080 | Inspect and Test Underground Utilities | Enabling & Site Works | Underground Site Utilities | Not Started | 2026-05-09 08:00 | 2026-05-12 16:00 |  |  | 3 | 3 | 139 | No |  |  | 75000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | UGU-090 | Backfill and Compact Utility Trenches | Enabling & Site Works | Underground Site Utilities | Not Started | 2026-05-13 08:00 | 2026-05-18 16:00 |  |  | 5 | 5 | 139 | No |  |  | 87000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | UGU-100 | Underground Site Utilities Complete | Enabling & Site Works | Underground Site Utilities | Not Started | 2026-05-19 08:00 | 2026-05-19 08:00 |  |  | 0 | 0 | 139 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | RDA-010 | Prepare Site Road Subgrade | Enabling & Site Works | Site Roads & Access | Not Started | 2026-05-04 08:00 | 2026-05-08 16:00 |  |  | 5 | 5 | 271 | No |  |  | 87000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | RDA-020 | Install Road Subbase and Base Course | Enabling & Site Works | Site Roads & Access | Not Started | 2026-05-09 08:00 | 2026-05-16 16:00 |  |  | 7 | 7 | 271 | No |  |  | 128000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | RDA-030 | Construct Heavy Equipment Access Routes | Enabling & Site Works | Site Roads & Access | Not Started | 2026-05-18 08:00 | 2026-05-22 16:00 |  |  | 5 | 5 | 271 | No |  |  | 116000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | RDA-040 | Construct Permanent Internal Roads | Enabling & Site Works | Site Roads & Access | Not Started | 2026-05-23 08:00 | 2026-06-03 16:00 |  |  | 10 | 10 | 271 | No |  |  | 143000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | RDA-050 | Construct Kerbs and Hardstanding Areas | Enabling & Site Works | Site Roads & Access | Not Started | 2026-06-04 08:00 | 2026-06-11 16:00 |  |  | 7 | 7 | 271 | No |  |  | 128000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | RDA-060 | Complete Final Road Surfacing | Enabling & Site Works | Site Roads & Access | Not Started | 2026-06-12 08:00 | 2026-06-15 16:00 |  |  | 3 | 3 | 271 | No |  |  | 75000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | RDA-070 | Site Roads and Access Complete | Enabling & Site Works | Site Roads & Access | Not Started | 2026-06-16 08:00 | 2026-06-16 08:00 |  |  | 0 | 0 | 271 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | DRN-010 | Set Out External Drainage Network | Enabling & Site Works | External Drainage | Not Started | 2026-04-13 08:00 | 2026-04-15 16:00 |  |  | 3 | 3 | 277 | No |  |  | 75000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | DRN-020 | Excavate Drainage Trenches | Enabling & Site Works | External Drainage | Not Started | 2026-04-16 08:00 | 2026-04-24 16:00 |  |  | 8 | 8 | 277 | No |  |  | 100000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | DRN-030 | Install Stormwater Drainage Pipework | Enabling & Site Works | External Drainage | Not Started | 2026-04-25 08:00 | 2026-05-06 16:00 |  |  | 10 | 10 | 277 | No |  |  | 143000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | DRN-040 | Install Drainage Manholes and Catch Basins | Enabling & Site Works | External Drainage | Not Started | 2026-04-18 08:00 | 2026-04-27 16:00 |  |  | 8 | 8 | 285 | No |  |  | 133000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | DRN-050 | Construct Stormwater Management Facilities | Enabling & Site Works | External Drainage | Not Started | 2026-04-18 08:00 | 2026-04-29 16:00 |  |  | 10 | 10 | 283 | No |  |  | 143000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | DRN-060 | Test and Inspect External Drainage | Enabling & Site Works | External Drainage | Not Started | 2026-05-07 08:00 | 2026-05-09 16:00 |  |  | 3 | 3 | 277 | No |  |  | 75000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | DRN-070 | Backfill Drainage Trenches | Enabling & Site Works | External Drainage | Not Started | 2026-05-11 08:00 | 2026-05-15 16:00 |  |  | 5 | 5 | 277 | No |  |  | 87000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | DRN-080 | External Drainage Complete | Enabling & Site Works | External Drainage | Not Started | 2026-05-16 08:00 | 2026-05-16 08:00 |  |  | 0 | 0 | 277 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | FND-010 | Set Out Building Foundations | Civil & Structural Works | Foundations | Not Started | 2026-05-09 08:00 | 2026-05-12 16:00 |  |  | 3 | 3 | 32 | No |  |  | 175000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | FND-020 | Excavate Building Foundations | Civil & Structural Works | Foundations | Not Started | 2026-05-13 08:00 | 2026-05-23 16:00 |  |  | 10 | 10 | 32 | No |  |  | 250000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | FND-030 | Prepare Foundation Formation | Civil & Structural Works | Foundations | Not Started | 2026-05-25 08:00 | 2026-05-29 16:00 |  |  | 5 | 5 | 32 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | FND-040 | Place Blinding Concrete | Civil & Structural Works | Foundations | Not Started | 2026-05-30 08:00 | 2026-06-02 16:00 |  |  | 3 | 3 | 32 | No |  |  | 175000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | FND-050 | Install Foundation Reinforcement | Civil & Structural Works | Foundations | Not Started | 2026-06-03 08:00 | 2026-06-13 16:00 |  |  | 10 | 10 | 32 | No |  |  | 250000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | FND-060 | Install Foundation Formwork | Civil & Structural Works | Foundations | Not Started | 2026-06-06 08:00 | 2026-06-15 16:00 |  |  | 8 | 8 | 32 | No |  |  | 234000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | FND-070 | Install Foundation Embedded Items | Civil & Structural Works | Foundations | Not Started | 2026-06-06 08:00 | 2026-06-11 16:00 |  |  | 5 | 5 | 35 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | FND-080 | Cast Foundation Concrete | Civil & Structural Works | Foundations | Not Started | 2026-06-16 08:00 | 2026-06-20 16:00 |  |  | 5 | 5 | 32 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | FND-090 | Cure Foundation Concrete | Civil & Structural Works | Foundations | Not Started | 2026-06-22 08:00 | 2026-06-29 16:00 |  |  | 7 | 7 | 32 | No |  |  | 225000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | FND-100 | Strip Foundation Formwork | Civil & Structural Works | Foundations | Not Started | 2026-06-30 08:00 | 2026-07-02 16:00 |  |  | 3 | 3 | 32 | No |  |  | 175000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | FND-110 | Backfill Around Foundations | Civil & Structural Works | Foundations | Not Started | 2026-07-20 08:00 | 2026-07-24 16:00 |  |  | 5 | 5 | 32 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | FND-120 | Building Foundations Complete | Civil & Structural Works | Foundations | Not Started | 2026-07-25 08:00 | 2026-07-25 08:00 |  |  | 0 | 0 | 32 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | SLB-010 | Prepare Ground Floor Subgrade | Civil & Structural Works | Ground Floor & Slabs | Not Started | 2026-07-25 08:00 | 2026-07-30 16:00 |  |  | 5 | 5 | 42 | No |  |  | 127000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | SLB-020 | Install Subbase and Compact | Civil & Structural Works | Ground Floor & Slabs | Not Started | 2026-07-31 08:00 | 2026-08-05 16:00 |  |  | 5 | 5 | 42 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | SLB-030 | Install Under-Slab Services | Civil & Structural Works | Ground Floor & Slabs | Not Started | 2026-08-06 08:00 | 2026-08-17 16:00 |  |  | 10 | 10 | 42 | No |  |  | 250000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | SLB-040 | Install Damp-Proof Membrane | Civil & Structural Works | Ground Floor & Slabs | Not Started | 2026-08-18 08:00 | 2026-08-20 16:00 |  |  | 3 | 3 | 42 | No |  |  | 175000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | SLB-050 | Install Ground Floor Reinforcement | Civil & Structural Works | Ground Floor & Slabs | Not Started | 2026-08-21 08:00 | 2026-08-29 16:00 |  |  | 8 | 8 | 42 | No |  |  | 234000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | SLB-060 | Install Slab Embedded Items and Openings | Civil & Structural Works | Ground Floor & Slabs | Not Started | 2026-08-25 08:00 | 2026-08-29 16:00 |  |  | 5 | 5 | 42 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | SLB-070 | Cast Ground Floor Slab | Civil & Structural Works | Ground Floor & Slabs | Not Started | 2026-08-31 08:00 | 2026-09-04 16:00 |  |  | 5 | 5 | 42 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | SLB-080 | Cure Ground Floor Slab | Civil & Structural Works | Ground Floor & Slabs | Not Started | 2026-09-05 08:00 | 2026-09-12 16:00 |  |  | 7 | 7 | 42 | No |  |  | 225000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | SLB-090 | Ground Floor Slab Complete | Civil & Structural Works | Ground Floor & Slabs | Not Started | 2026-09-14 08:00 | 2026-09-14 08:00 |  |  | 0 | 0 | 42 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | STR-010 | Mobilize Structural Steel Erection | Civil & Structural Works | Structural Frame | Not Started | 2026-07-25 08:00 | 2026-07-28 16:00 |  |  | 3 | 3 | 32 | No |  |  | 175000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | STR-020 | Erect Primary Structural Columns | Civil & Structural Works | Structural Frame | Not Started | 2026-07-29 08:00 | 2026-08-08 16:00 |  |  | 10 | 10 | 32 | No |  |  | 250000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | STR-030 | Erect Primary Structural Beams | Civil & Structural Works | Structural Frame | Not Started | 2026-08-03 08:00 | 2026-08-13 16:00 |  |  | 10 | 10 | 32 | No |  |  | 250000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | STR-040 | Install Secondary Structural Steel | Civil & Structural Works | Structural Frame | Not Started | 2026-08-07 08:00 | 2026-08-15 16:00 |  |  | 8 | 8 | 32 | No |  |  | 234000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | STR-050 | Install Structural Bracing | Civil & Structural Works | Structural Frame | Not Started | 2026-08-07 08:00 | 2026-08-12 16:00 |  |  | 5 | 5 | 35 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | STR-060 | Complete Bolting and Connections | Civil & Structural Works | Structural Frame | Not Started | 2026-08-17 08:00 | 2026-08-20 16:00 |  |  | 4 | 4 | 32 | No |  |  | 119000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | STR-070 | Structural Alignment and Inspection | Civil & Structural Works | Structural Frame | Not Started | 2026-08-21 08:00 | 2026-08-24 16:00 |  |  | 3 | 3 | 32 | No |  |  | 131000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | STR-080 | Structural Frame Complete | Civil & Structural Works | Structural Frame | Not Started | 2026-08-25 08:00 | 2026-08-25 08:00 |  |  | 0 | 0 | 32 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | DHS-010 | Construct Data Hall Structural Frame | Civil & Structural Works | Data Hall Structure | Not Started | 2026-08-08 08:00 | 2026-08-25 16:00 |  |  | 15 | 15 | 59 | No |  |  | 295000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | DHS-020 | Install Data Hall Floor Structure | Civil & Structural Works | Data Hall Structure | Not Started | 2026-08-14 08:00 | 2026-08-22 16:00 |  |  | 8 | 8 | 61 | No |  |  | 234000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | DHS-030 | Install Data Hall Roof Support Structure | Civil & Structural Works | Data Hall Structure | Not Started | 2026-08-17 08:00 | 2026-08-25 16:00 |  |  | 8 | 8 | 59 | No |  |  | 234000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | DHS-040 | Install Data Hall Equipment Support Steel | Civil & Structural Works | Data Hall Structure | Not Started | 2026-08-17 08:00 | 2026-08-21 16:00 |  |  | 5 | 5 | 62 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | DHS-050 | Complete Data Hall Structural Connections | Civil & Structural Works | Data Hall Structure | Not Started | 2026-08-26 08:00 | 2026-08-29 16:00 |  |  | 4 | 4 | 59 | No |  |  | 119000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | DHS-060 | Inspect Data Hall Structure | Civil & Structural Works | Data Hall Structure | Not Started | 2026-08-31 08:00 | 2026-09-02 16:00 |  |  | 3 | 3 | 59 | No |  |  | 131000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | DHS-070 | Data Hall Structure Complete | Civil & Structural Works | Data Hall Structure | Not Started | 2026-09-03 08:00 | 2026-09-03 08:00 |  |  | 0 | 0 | 59 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | EUS-010 | Construct Electrical Room Structure | Civil & Structural Works | Electrical & UPS Rooms Structure | Not Started | 2026-09-14 08:00 | 2026-09-24 16:00 |  |  | 10 | 10 | 42 | No |  |  | 250000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | EUS-020 | Construct UPS and Battery Room Structure | Civil & Structural Works | Electrical & UPS Rooms Structure | Not Started | 2026-09-14 08:00 | 2026-09-24 16:00 |  |  | 10 | 10 | 42 | No |  |  | 250000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | EUS-030 | Construct MV and LV Switchgear Room Structure | Civil & Structural Works | Electrical & UPS Rooms Structure | Not Started | 2026-09-14 08:00 | 2026-09-24 16:00 |  |  | 10 | 10 | 42 | No |  |  | 250000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | EUS-040 | Construct Transformer Room Structure | Civil & Structural Works | Electrical & UPS Rooms Structure | Not Started | 2026-09-14 08:00 | 2026-09-24 16:00 |  |  | 10 | 10 | 42 | No |  |  | 250000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | EUS-050 | Install Equipment Support Steel | Civil & Structural Works | Electrical & UPS Rooms Structure | Not Started | 2026-09-25 08:00 | 2026-09-30 16:00 |  |  | 5 | 5 | 42 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | EUS-060 | Complete Equipment Access Openings | Civil & Structural Works | Electrical & UPS Rooms Structure | Not Started | 2026-10-01 08:00 | 2026-10-03 16:00 |  |  | 3 | 3 | 42 | No |  |  | 109000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | EUS-070 | Electrical and UPS Rooms Structure Complete | Civil & Structural Works | Electrical & UPS Rooms Structure | Not Started | 2026-10-05 08:00 | 2026-10-05 08:00 |  |  | 0 | 0 | 42 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | GUS-010 | Construct Generator Foundations | Civil & Structural Works | Generator & Utility Structures | Not Started | 2026-07-25 08:00 | 2026-08-05 16:00 |  |  | 10 | 10 | 118 | No |  |  | 250000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | GUS-020 | Construct Generator Support Structures | Civil & Structural Works | Generator & Utility Structures | Not Started | 2026-08-06 08:00 | 2026-08-14 16:00 |  |  | 8 | 8 | 118 | No |  |  | 234000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | GUS-030 | Construct Utility and MV Structures | Civil & Structural Works | Generator & Utility Structures | Not Started | 2026-08-06 08:00 | 2026-08-14 16:00 |  |  | 8 | 8 | 123 | No |  |  | 234000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | GUS-040 | Construct Fuel System Structural Supports | Civil & Structural Works | Generator & Utility Structures | Not Started | 2026-08-06 08:00 | 2026-08-11 16:00 |  |  | 5 | 5 | 121 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | GUS-050 | Install Generator Equipment Plinths | Civil & Structural Works | Generator & Utility Structures | Not Started | 2026-08-15 08:00 | 2026-08-20 16:00 |  |  | 5 | 5 | 118 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | GUS-060 | Generator and Utility Structures Complete | Civil & Structural Works | Generator & Utility Structures | Not Started | 2026-08-21 08:00 | 2026-08-21 08:00 |  |  | 0 | 0 | 118 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | CPS-010 | Construct Cooling Plant Foundations | Civil & Structural Works | Cooling Plant Structures | Not Started | 2026-07-25 08:00 | 2026-08-05 16:00 |  |  | 10 | 10 | 44 | No |  |  | 250000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CPS-020 | Construct Chiller Equipment Bases | Civil & Structural Works | Cooling Plant Structures | Not Started | 2026-08-06 08:00 | 2026-08-11 16:00 |  |  | 5 | 5 | 55 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CPS-030 | Construct Pump Equipment Bases | Civil & Structural Works | Cooling Plant Structures | Not Started | 2026-08-06 08:00 | 2026-08-11 16:00 |  |  | 5 | 5 | 55 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CPS-040 | Construct Cooling Plant Structural Supports | Civil & Structural Works | Cooling Plant Structures | Not Started | 2026-08-06 08:00 | 2026-08-14 16:00 |  |  | 8 | 8 | 44 | No |  |  | 234000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CPS-050 | Install Pipework Support Structures | Civil & Structural Works | Cooling Plant Structures | Not Started | 2026-08-15 08:00 | 2026-08-24 16:00 |  |  | 8 | 8 | 44 | No |  |  | 234000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CPS-060 | Cooling Plant Structures Complete | Civil & Structural Works | Cooling Plant Structures | Not Started | 2026-08-25 08:00 | 2026-08-25 08:00 |  |  | 0 | 0 | 44 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | RFS-010 | Confirm Operational Readiness | Client Acceptance & Handover | Final Acceptance & Project Closeout | Not Started | 2027-07-13 08:00 | 2027-07-19 16:00 |  |  | 5 | 5 | 0 | Yes | 1 | 55 | 29000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | RFS-020 | Confirm Systems Acceptance | Client Acceptance & Handover | Final Acceptance & Project Closeout | Not Started | 2027-06-16 08:00 | 2027-06-22 16:00 |  |  | 5 | 5 | 19 | No |  |  | 29000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | RFS-030 | Confirm Documentation and Training Complete | Client Acceptance & Handover | Final Acceptance & Project Closeout | Not Started | 2027-05-11 16:00 | 2027-05-11 16:00 |  |  | 0 | 0 | 49 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | RFS-040 | Ready for Service | Client Acceptance & Handover | Final Acceptance & Project Closeout | Not Started | 2027-07-19 16:00 | 2027-07-19 16:00 |  |  | 0 | 0 | 0 | Yes | 1 | 56 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | RFS-050 | Complete Roof Structural Connections | Civil & Structural Works | Roof Structure | Not Started | 2026-08-25 08:00 | 2026-08-29 16:00 |  |  | 5 | 5 | 32 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | RFS-060 | Inspect Roof Structure | Civil & Structural Works | Roof Structure | Not Started | 2026-08-31 08:00 | 2026-09-02 16:00 |  |  | 3 | 3 | 32 | No |  |  | 175000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | RFS-070 | Roof Structure Complete | Civil & Structural Works | Roof Structure | Not Started | 2026-09-03 08:00 | 2026-09-03 08:00 |  |  | 0 | 0 | 32 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | EPF-010 | Confirm Equipment Foundation Requirements | Civil & Structural Works | Equipment Plinths & Foundations | Not Started | 2026-09-14 08:00 | 2026-09-18 16:00 |  |  | 5 | 5 | 55 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | EPF-020 | Set Out Equipment Foundations and Plinths | Civil & Structural Works | Equipment Plinths & Foundations | Not Started | 2026-09-19 08:00 | 2026-09-22 16:00 |  |  | 3 | 3 | 55 | No |  |  | 175000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | EPF-030 | Construct Transformer Plinths | Civil & Structural Works | Equipment Plinths & Foundations | Not Started | 2026-09-23 08:00 | 2026-09-28 16:00 |  |  | 5 | 5 | 55 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | EPF-040 | Construct Switchgear and UPS Equipment Plinths | Civil & Structural Works | Equipment Plinths & Foundations | Not Started | 2026-09-23 08:00 | 2026-09-28 16:00 |  |  | 5 | 5 | 55 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | EPF-050 | Construct Generator Equipment Plinths | Civil & Structural Works | Equipment Plinths & Foundations | Not Started | 2026-09-23 08:00 | 2026-09-28 16:00 |  |  | 5 | 5 | 55 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | EPF-060 | Construct Cooling Equipment Plinths | Civil & Structural Works | Equipment Plinths & Foundations | Not Started | 2026-09-23 08:00 | 2026-09-28 16:00 |  |  | 5 | 5 | 55 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | EPF-070 | Install Equipment Anchor Bolts and Embedded Plates | Civil & Structural Works | Equipment Plinths & Foundations | Not Started | 2026-09-29 08:00 | 2026-10-03 16:00 |  |  | 5 | 5 | 55 | No |  |  | 203000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | EPF-080 | Inspect Equipment Foundations and Plinths | Civil & Structural Works | Equipment Plinths & Foundations | Not Started | 2026-10-05 08:00 | 2026-10-07 16:00 |  |  | 3 | 3 | 55 | No |  |  | 175000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | EPF-090 | Equipment Foundations Ready for Installation | Civil & Structural Works | Equipment Plinths & Foundations | Not Started | 2026-10-08 08:00 | 2026-10-08 08:00 |  |  | 0 | 0 | 55 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | CLD-010 | Set Out External Wall and Cladding System | Building Envelope | External Walls & Cladding | Not Started | 2026-08-08 08:00 | 2026-08-11 16:00 |  |  | 3 | 3 | 48 | No |  |  | 113000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CLD-020 | Install External Wall Framing and Supports | Building Envelope | External Walls & Cladding | Not Started | 2026-08-12 08:00 | 2026-08-22 16:00 |  |  | 10 | 10 | 48 | No |  |  | 163000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CLD-030 | Install External Wall Insulation | Building Envelope | External Walls & Cladding | Not Started | 2026-08-15 08:00 | 2026-08-24 16:00 |  |  | 8 | 8 | 48 | No |  |  | 152000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CLD-040 | Install External Cladding Panels | Building Envelope | External Walls & Cladding | Not Started | 2026-08-19 08:00 | 2026-09-01 16:00 |  |  | 12 | 12 | 48 | No |  |  | 177000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CLD-050 | Install Flashings and Interface Seals | Building Envelope | External Walls & Cladding | Not Started | 2026-08-27 08:00 | 2026-09-01 16:00 |  |  | 5 | 5 | 48 | No |  |  | 132000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CLD-060 | Complete Cladding Joint Sealing | Building Envelope | External Walls & Cladding | Not Started | 2026-09-02 08:00 | 2026-09-04 16:00 |  |  | 3 | 3 | 48 | No |  |  | 113000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CLD-070 | Inspect External Walls and Cladding | Building Envelope | External Walls & Cladding | Not Started | 2026-09-05 08:00 | 2026-09-07 16:00 |  |  | 2 | 2 | 48 | No |  |  | 100000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CLD-080 | External Walls and Cladding Complete | Building Envelope | External Walls & Cladding | Not Started | 2026-09-08 08:00 | 2026-09-08 08:00 |  |  | 0 | 0 | 48 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | ROF-010 | Prepare Roof Deck for Roofing Works | Building Envelope | Roofing System | Not Started | 2026-09-03 08:00 | 2026-09-05 16:00 |  |  | 3 | 3 | 32 | No |  |  | 113000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | ROF-020 | Install Roof Vapour Control Layer | Building Envelope | Roofing System | Not Started | 2026-09-07 08:00 | 2026-09-11 16:00 |  |  | 5 | 5 | 32 | No |  |  | 132000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | ROF-030 | Install Roof Insulation | Building Envelope | Roofing System | Not Started | 2026-09-09 08:00 | 2026-09-14 16:00 |  |  | 5 | 5 | 32 | No |  |  | 132000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | ROF-040 | Install Roofing Membrane | Building Envelope | Roofing System | Not Started | 2026-09-11 08:00 | 2026-09-19 16:00 |  |  | 8 | 8 | 32 | No |  |  | 152000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | ROF-050 | Install Roof Flashings and Upstands | Building Envelope | Roofing System | Not Started | 2026-09-15 08:00 | 2026-09-19 16:00 |  |  | 5 | 5 | 32 | No |  |  | 132000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | ROF-060 | Seal Roof Equipment Penetrations | Building Envelope | Roofing System | Not Started | 2026-09-21 08:00 | 2026-09-23 16:00 |  |  | 3 | 3 | 32 | No |  |  | 113000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | ROF-070 | Inspect and Test Roofing System | Building Envelope | Roofing System | Not Started | 2026-09-24 08:00 | 2026-09-25 16:00 |  |  | 2 | 2 | 32 | No |  |  | 100000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | ROF-080 | Roofing System Complete | Building Envelope | Roofing System | Not Started | 2026-09-26 08:00 | 2026-09-26 08:00 |  |  | 0 | 0 | 32 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | WPF-010 | Prepare Surfaces for Waterproofing | Building Envelope | Waterproofing | Not Started | 2026-07-03 08:00 | 2026-07-04 16:00 |  |  | 2 | 2 | 32 | No |  |  | 100000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | WPF-020 | Apply Foundation Waterproofing | Building Envelope | Waterproofing | Not Started | 2026-07-06 08:00 | 2026-07-10 16:00 |  |  | 5 | 5 | 32 | No |  |  | 132000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | WPF-030 | Apply Below-Grade Wall Waterproofing | Building Envelope | Waterproofing | Not Started | 2026-07-08 08:00 | 2026-07-13 16:00 |  |  | 5 | 5 | 32 | No |  |  | 132000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | WPF-040 | Waterproof Service Penetrations | Building Envelope | Waterproofing | Not Started | 2026-07-10 08:00 | 2026-07-13 16:00 |  |  | 3 | 3 | 32 | No |  |  | 113000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | WPF-050 | Install Waterproofing Protection Layer | Building Envelope | Waterproofing | Not Started | 2026-07-14 08:00 | 2026-07-16 16:00 |  |  | 3 | 3 | 32 | No |  |  | 113000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | WPF-060 | Inspect and Test Waterproofing Works | Building Envelope | Waterproofing | Not Started | 2026-07-17 08:00 | 2026-07-18 16:00 |  |  | 2 | 2 | 32 | No |  |  | 100000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | WPF-070 | Waterproofing Complete | Building Envelope | Waterproofing | Not Started | 2026-07-20 08:00 | 2026-07-20 08:00 |  |  | 0 | 0 | 32 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | EDL-010 | Prepare External Door and Louver Openings | Building Envelope | External Doors & Louvers | Not Started | 2026-08-15 08:00 | 2026-08-18 16:00 |  |  | 3 | 3 | 49 | No |  |  | 71000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | EDL-020 | Install External Door Frames | Building Envelope | External Doors & Louvers | Not Started | 2026-08-19 08:00 | 2026-08-24 16:00 |  |  | 5 | 5 | 49 | No |  |  | 132000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | EDL-030 | Install External Doors | Building Envelope | External Doors & Louvers | Not Started | 2026-08-21 08:00 | 2026-08-26 16:00 |  |  | 5 | 5 | 49 | No |  |  | 132000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | EDL-040 | Install External Louvers | Building Envelope | External Doors & Louvers | Not Started | 2026-08-21 08:00 | 2026-08-26 16:00 |  |  | 5 | 5 | 53 | No |  |  | 132000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | EDL-050 | Install Door Hardware and Security Interfaces | Building Envelope | External Doors & Louvers | Not Started | 2026-08-27 08:00 | 2026-08-31 16:00 |  |  | 4 | 4 | 49 | No |  |  | 124000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | EDL-060 | Seal Door and Louver Interfaces | Building Envelope | External Doors & Louvers | Not Started | 2026-09-01 08:00 | 2026-09-03 16:00 |  |  | 3 | 3 | 49 | No |  |  | 71000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | EDL-070 | Inspect External Doors and Louvers | Building Envelope | External Doors & Louvers | Not Started | 2026-09-04 08:00 | 2026-09-05 16:00 |  |  | 2 | 2 | 49 | No |  |  | 75000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | EDL-080 | External Doors and Louvers Complete | Building Envelope | External Doors & Louvers | Not Started | 2026-09-07 08:00 | 2026-09-07 08:00 |  |  | 0 | 0 | 49 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | PAR-010 | Set Out Internal Partitions | Building Envelope | Internal Partitions & Fire-Rated Enclosures | Not Started | 2026-09-14 08:00 | 2026-09-17 16:00 |  |  | 4 | 4 | 67 | No |  |  | 77000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | PAR-020 | Install Internal Partition Framing | Building Envelope | Internal Partitions & Fire-Rated Enclosures | Not Started | 2026-09-18 08:00 | 2026-09-26 16:00 |  |  | 8 | 8 | 67 | No |  |  | 152000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | PAR-030 | Install Fire-Rated Wall Systems | Building Envelope | Internal Partitions & Fire-Rated Enclosures | Not Started | 2026-09-22 08:00 | 2026-09-28 16:00 |  |  | 6 | 6 | 67 | No |  |  | 140000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | PAR-040 | Construct Electrical Room Fire-Rated Enclosures | Building Envelope | Internal Partitions & Fire-Rated Enclosures | Not Started | 2026-09-24 08:00 | 2026-10-02 16:00 |  |  | 8 | 8 | 69 | No |  |  | 152000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | PAR-050 | Construct UPS and Battery Room Fire-Rated Enclosures | Building Envelope | Internal Partitions & Fire-Rated Enclosures | Not Started | 2026-09-24 08:00 | 2026-10-02 16:00 |  |  | 8 | 8 | 69 | No |  |  | 152000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | PAR-060 | Construct Data Hall Fire-Rated Enclosures | Building Envelope | Internal Partitions & Fire-Rated Enclosures | Not Started | 2026-09-24 08:00 | 2026-10-05 16:00 |  |  | 10 | 10 | 67 | No |  |  | 163000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | PAR-070 | Install Fire-Stopping at Service Penetrations | Building Envelope | Internal Partitions & Fire-Rated Enclosures | Not Started | 2026-09-30 08:00 | 2026-10-05 16:00 |  |  | 5 | 5 | 67 | No |  |  | 132000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | PAR-080 | Inspect Fire-Rated Partitions and Enclosures | Building Envelope | Internal Partitions & Fire-Rated Enclosures | Not Started | 2026-10-06 08:00 | 2026-10-07 16:00 |  |  | 2 | 2 | 67 | No |  |  | 75000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | PAR-090 | Internal Partitions and Fire-Rated Enclosures Complete | Building Envelope | Internal Partitions & Fire-Rated Enclosures | Not Started | 2026-10-08 08:00 | 2026-10-08 08:00 |  |  | 0 | 0 | 67 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | ENV-010 | Inspect Building Envelope Interfaces | Building Envelope | Weather-Tightness & Envelope Completion | Not Started | 2026-09-26 08:00 | 2026-09-28 16:00 |  |  | 2 | 2 | 32 | No |  |  | 75000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | ENV-020 | Perform Roof Water-Tightness Testing | Building Envelope | Weather-Tightness & Envelope Completion | Not Started | 2026-09-29 08:00 | 2026-10-01 16:00 |  |  | 3 | 3 | 32 | No |  |  | 113000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | ENV-030 | Perform External Wall Water-Tightness Testing | Building Envelope | Weather-Tightness & Envelope Completion | Not Started | 2026-09-29 08:00 | 2026-10-01 16:00 |  |  | 3 | 3 | 32 | No |  |  | 85000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | ENV-040 | Inspect Doors Louvers and Penetration Seals | Building Envelope | Weather-Tightness & Envelope Completion | Not Started | 2026-09-29 08:00 | 2026-09-30 16:00 |  |  | 2 | 2 | 33 | No |  |  | 75000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | ENV-050 | Rectify Building Envelope Defects | Building Envelope | Weather-Tightness & Envelope Completion | Not Started | 2026-10-02 08:00 | 2026-10-07 16:00 |  |  | 5 | 5 | 32 | No |  |  | 83000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | ENV-060 | Complete Final Building Envelope Inspection | Building Envelope | Weather-Tightness & Envelope Completion | Not Started | 2026-10-08 08:00 | 2026-10-09 16:00 |  |  | 2 | 2 | 32 | No |  |  | 75000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | ENV-070 | Building Weather-Tight | Building Envelope | Weather-Tightness & Envelope Completion | Not Started | 2026-10-10 08:00 | 2026-10-10 08:00 |  |  | 0 | 0 | 32 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | MV-010 | Set Out MV Power Infrastructure | Electrical Systems | Utility / MV Power Infrastructure | Not Started | 2026-05-19 08:00 | 2026-05-20 16:00 |  |  | 2 | 2 | 139 | No |  |  | 118000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | MV-020 | Install MV Cable Duct Banks | Electrical Systems | Utility / MV Power Infrastructure | Not Started | 2026-05-21 08:00 | 2026-06-06 16:00 |  |  | 15 | 15 | 139 | No |  |  | 352000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | MV-030 | Install MV Cable Chambers and Pull Pits | Electrical Systems | Utility / MV Power Infrastructure | Not Started | 2026-05-27 08:00 | 2026-06-06 16:00 |  |  | 10 | 10 | 139 | No |  |  | 307000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | MV-040 | Install Incoming MV Cables | Electrical Systems | Utility / MV Power Infrastructure | Not Started | 2026-06-08 08:00 | 2026-06-18 16:00 |  |  | 10 | 10 | 139 | No |  |  | 307000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | MV-050 | Terminate Incoming MV Cables | Electrical Systems | Utility / MV Power Infrastructure | Not Started | 2026-06-19 08:00 | 2026-06-24 16:00 |  |  | 5 | 5 | 139 | No |  |  | 249000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | MV-060 | Test Incoming MV Cable System | Electrical Systems | Utility / MV Power Infrastructure | Not Started | 2026-06-25 08:00 | 2026-06-27 16:00 |  |  | 3 | 3 | 139 | No |  |  | 214000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | MV-070 | MV Power Infrastructure Ready | Electrical Systems | Utility / MV Power Infrastructure | Not Started | 2026-06-27 16:00 | 2026-06-27 16:00 |  |  | 0 | 0 | 139 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | MVSG-010 | Prepare MV Switchgear Room for Installation | Electrical Systems | MV Switchgear | Not Started | 2026-10-10 08:00 | 2026-10-13 16:00 |  |  | 3 | 3 | 37 | No |  |  | 214000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | MVSG-020 | Receive and Inspect MV Switchgear | Electrical Systems | MV Switchgear | Not Started | 2026-10-24 08:00 | 2026-10-26 16:00 |  |  | 2 | 2 | 26 | No |  |  | 142000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | MVSG-030 | Position and Install MV Switchgear | Electrical Systems | MV Switchgear | Not Started | 2026-10-27 08:00 | 2026-10-31 16:00 |  |  | 5 | 5 | 26 | No |  |  | 249000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | MVSG-040 | Assemble MV Switchgear Sections | Electrical Systems | MV Switchgear | Not Started | 2026-11-02 08:00 | 2026-11-06 16:00 |  |  | 5 | 5 | 26 | No |  |  | 156000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | MVSG-050 | Install MV Switchgear Control Wiring | Electrical Systems | MV Switchgear | Not Started | 2026-11-04 08:00 | 2026-11-09 16:00 |  |  | 5 | 5 | 29 | No |  |  | 249000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | MVSG-060 | Terminate MV Power Cables | Electrical Systems | MV Switchgear | Not Started | 2026-11-07 08:00 | 2026-11-12 16:00 |  |  | 5 | 5 | 26 | No |  |  | 249000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | MVSG-070 | Complete MV Switchgear Installation Inspection | Electrical Systems | MV Switchgear | Not Started | 2026-11-13 08:00 | 2026-11-14 16:00 |  |  | 2 | 2 | 26 | No |  |  | 189000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | MVSG-080 | MV Switchgear Ready for Pre-Commissioning | Electrical Systems | MV Switchgear | Not Started | 2026-11-14 16:00 | 2026-11-14 16:00 |  |  | 0 | 0 | 26 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | TRI-010 | Prepare Transformer Areas for Installation | Electrical Systems | Transformers | Not Started | 2026-10-08 08:00 | 2026-10-10 16:00 |  |  | 3 | 3 | 55 | No |  |  | 214000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | TRI-020 | Receive and Inspect Transformers | Electrical Systems | Transformers | Not Started | 2026-12-12 08:00 | 2026-12-14 16:00 |  |  | 2 | 2 | 0 | Yes | 1 | 12 | 142000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | TRI-030 | Position Transformers on Plinths | Electrical Systems | Transformers | Not Started | 2026-12-15 08:00 | 2026-12-17 16:00 |  |  | 3 | 3 | 0 | Yes | 1 | 13 | 134000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | TRI-040 | Install Transformer Ancillary Equipment | Electrical Systems | Transformers | Not Started | 2026-12-18 08:00 | 2026-12-23 16:00 |  |  | 5 | 5 | 0 | Yes | 10 | 1 | 249000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | TRI-050 | Complete MV Transformer Connections | Electrical Systems | Transformers | Not Started | 2026-12-18 08:00 | 2026-12-21 16:00 |  |  | 3 | 3 | 2 | No |  |  | 134000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | TRI-060 | Complete LV Transformer Connections | Electrical Systems | Transformers | Not Started | 2026-12-18 08:00 | 2026-12-21 16:00 |  |  | 3 | 3 | 0 | Yes | 1 | 14 | 134000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | TRI-070 | Complete Transformer Installation Inspection | Electrical Systems | Transformers | Not Started | 2026-12-24 08:00 | 2026-12-25 16:00 |  |  | 2 | 2 | 0 | Yes | 10 | 2 | 189000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | TRI-080 | Transformers Ready for Pre-Commissioning | Electrical Systems | Transformers | Not Started | 2026-12-25 16:00 | 2026-12-25 16:00 |  |  | 0 | 0 | 0 | Yes | 10 | 3 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | SGI-010 | Prepare Generator Areas for Installation | Electrical Systems | Standby Generator System | Not Started | 2026-08-21 08:00 | 2026-08-24 16:00 |  |  | 3 | 3 | 118 | No |  |  | 214000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | SGI-020 | Receive and Inspect Standby Generators | Electrical Systems | Standby Generator System | Not Started | 2026-12-12 08:00 | 2026-12-14 16:00 |  |  | 2 | 2 | 22 | No |  |  | 142000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | SGI-030 | Position Standby Generators on Plinths | Electrical Systems | Standby Generator System | Not Started | 2026-12-15 08:00 | 2026-12-19 16:00 |  |  | 5 | 5 | 22 | No |  |  | 156000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | SGI-040 | Install Generator Exhaust Systems | Electrical Systems | Standby Generator System | Not Started | 2026-12-21 08:00 | 2026-12-28 16:00 |  |  | 7 | 7 | 23 | No |  |  | 276000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | SGI-050 | Install Generator Fuel System Connections | Electrical Systems | Standby Generator System | Not Started | 2026-12-21 08:00 | 2026-12-28 16:00 |  |  | 7 | 7 | 23 | No |  |  | 276000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | SGI-060 | Install Generator Power Connections | Electrical Systems | Standby Generator System | Not Started | 2026-12-21 08:00 | 2026-12-25 16:00 |  |  | 5 | 5 | 25 | No |  |  | 249000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | SGI-070 | Install Generator Control Connections | Electrical Systems | Standby Generator System | Not Started | 2026-12-21 08:00 | 2026-12-25 16:00 |  |  | 5 | 5 | 25 | No |  |  | 249000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | SGI-080 | Complete Generator Installation Inspection | Electrical Systems | Standby Generator System | Not Started | 2026-12-29 08:00 | 2026-12-30 16:00 |  |  | 2 | 2 | 23 | No |  |  | 189000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | SGI-090 | Standby Generators Ready for Pre-Commissioning | Electrical Systems | Standby Generator System | Not Started | 2026-12-30 16:00 | 2026-12-30 16:00 |  |  | 0 | 0 | 23 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | LV-010 | Prepare LV Electrical Rooms for Installation | Electrical Systems | LV Main Distribution | Not Started | 2026-10-10 08:00 | 2026-10-13 16:00 |  |  | 3 | 3 | 42 | No |  |  | 214000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | LV-020 | Receive and Inspect LV Switchgear | Electrical Systems | LV Main Distribution | Not Started | 2026-10-24 08:00 | 2026-10-26 16:00 |  |  | 2 | 2 | 38 | No |  |  | 142000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | LV-030 | Position and Install LV Switchgear | Electrical Systems | LV Main Distribution | Not Started | 2026-10-27 08:00 | 2026-10-31 16:00 |  |  | 5 | 5 | 38 | No |  |  | 249000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | LV-040 | Install Main LV Cable Containment | Electrical Systems | LV Main Distribution | Not Started | 2026-10-14 08:00 | 2026-10-22 16:00 |  |  | 8 | 8 | 42 | No |  |  | 287000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | LV-050 | Install Main LV Power Cables | Electrical Systems | LV Main Distribution | Not Started | 2026-10-16 08:00 | 2026-10-27 16:00 |  |  | 10 | 10 | 42 | No |  |  | 307000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | LV-060 | Terminate Main LV Power Cables | Electrical Systems | LV Main Distribution | Not Started | 2026-11-02 08:00 | 2026-11-06 16:00 |  |  | 5 | 5 | 38 | No |  |  | 249000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | LV-070 | Install LV Control and Interlock Wiring | Electrical Systems | LV Main Distribution | Not Started | 2026-11-02 08:00 | 2026-11-06 16:00 |  |  | 5 | 5 | 38 | No |  |  | 249000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | LV-080 | Complete LV Distribution Installation Inspection | Electrical Systems | LV Main Distribution | Not Started | 2026-12-22 08:00 | 2026-12-23 16:00 |  |  | 2 | 2 | 0 | Yes | 1 | 15 | 189000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | LV-090 | LV Main Distribution Ready for Pre-Commissioning | Electrical Systems | LV Main Distribution | Not Started | 2026-12-23 16:00 | 2026-12-23 16:00 |  |  | 0 | 0 | 0 | Yes | 1 | 16 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | UPSI-010 | Prepare UPS and Battery Rooms for Installation | Electrical Systems | UPS Systems & Batteries | Not Started | 2026-10-10 08:00 | 2026-10-13 16:00 |  |  | 3 | 3 | 54 | No |  |  | 214000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | UPSI-020 | Receive and Inspect UPS Equipment | Electrical Systems | UPS Systems & Batteries | Not Started | 2026-10-24 08:00 | 2026-10-26 16:00 |  |  | 2 | 2 | 45 | No |  |  | 142000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | UPSI-030 | Install UPS Units | Electrical Systems | UPS Systems & Batteries | Not Started | 2026-10-27 08:00 | 2026-10-31 16:00 |  |  | 5 | 5 | 45 | No |  |  | 249000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | UPSI-040 | Install Battery Racks and Cabinets | Electrical Systems | UPS Systems & Batteries | Not Started | 2026-10-14 08:00 | 2026-10-19 16:00 |  |  | 5 | 5 | 54 | No |  |  | 249000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | UPSI-050 | Install Battery Systems | Electrical Systems | UPS Systems & Batteries | Not Started | 2026-10-20 08:00 | 2026-10-27 16:00 |  |  | 7 | 7 | 54 | No |  |  | 276000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | UPSI-060 | Install UPS Input and Output Power Connections | Electrical Systems | UPS Systems & Batteries | Not Started | 2026-12-24 08:00 | 2026-12-29 16:00 |  |  | 5 | 5 | 0 | Yes | 1 | 17 | 249000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | UPSI-070 | Install UPS Control and Monitoring Connections | Electrical Systems | UPS Systems & Batteries | Not Started | 2026-11-02 08:00 | 2026-11-06 16:00 |  |  | 5 | 5 | 45 | No |  |  | 31000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | UPSI-080 | Complete UPS and Battery Installation Inspection | Electrical Systems | UPS Systems & Batteries | Not Started | 2026-12-30 08:00 | 2026-12-31 16:00 |  |  | 2 | 2 | 0 | Yes | 1 | 18 | 189000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | UPSI-090 | UPS and Battery Systems Ready for Pre-Commissioning | Electrical Systems | UPS Systems & Batteries | Not Started | 2026-12-31 16:00 | 2026-12-31 16:00 |  |  | 0 | 0 | 0 | Yes | 1 | 19 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | BUS-010 | Set Out PDU and Busway Routes | Electrical Systems | PDUs & Busway Distribution | Not Started | 2026-09-03 08:00 | 2026-09-05 16:00 |  |  | 3 | 3 | 72 | No |  |  | 214000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | BUS-020 | Install Busway Support Systems | Electrical Systems | PDUs & Busway Distribution | Not Started | 2026-09-07 08:00 | 2026-09-17 16:00 |  |  | 10 | 10 | 72 | No |  |  | 307000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | BUS-030 | Install Main Busway Distribution | Electrical Systems | PDUs & Busway Distribution | Not Started | 2026-09-10 08:00 | 2026-09-26 16:00 |  |  | 15 | 15 | 72 | No |  |  | 347000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | BUS-040 | Install Power Distribution Units | Electrical Systems | PDUs & Busway Distribution | Not Started | 2026-09-19 08:00 | 2026-09-26 16:00 |  |  | 7 | 7 | 72 | No |  |  | 276000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | BUS-050 | Install Busway Tap-Off Units | Electrical Systems | PDUs & Busway Distribution | Not Started | 2026-09-28 08:00 | 2026-10-08 16:00 |  |  | 10 | 10 | 72 | No |  |  | 307000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | BUS-060 | Complete Busway and PDU Connections | Electrical Systems | PDUs & Busway Distribution | Not Started | 2027-01-01 08:00 | 2027-01-06 16:00 |  |  | 5 | 5 | 0 | Yes | 1 | 20 | 249000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | BUS-070 | Inspect PDU and Busway Installation | Electrical Systems | PDUs & Busway Distribution | Not Started | 2027-01-07 08:00 | 2027-01-08 16:00 |  |  | 2 | 2 | 13 | No |  |  | 189000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | BUS-080 | PDU and Busway Distribution Ready for Pre-Commissioning | Electrical Systems | PDUs & Busway Distribution | Not Started | 2027-01-08 16:00 | 2027-01-08 16:00 |  |  | 0 | 0 | 13 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | DHP-010 | Install Data Hall Cable Containment | Electrical Systems | Data Hall Power Distribution | Not Started | 2026-09-03 08:00 | 2026-09-14 16:00 |  |  | 10 | 10 | 90 | No |  |  | 307000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | DHP-020 | Install Data Hall Power Distribution Cables | Electrical Systems | Data Hall Power Distribution | Not Started | 2026-09-07 08:00 | 2026-09-23 16:00 |  |  | 15 | 15 | 90 | No |  |  | 347000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | DHP-030 | Install Rack Power Distribution Connections | Electrical Systems | Data Hall Power Distribution | Not Started | 2026-09-28 08:00 | 2026-10-08 16:00 |  |  | 10 | 10 | 77 | No |  |  | 307000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | DHP-040 | Install Data Hall Power Monitoring Devices | Electrical Systems | Data Hall Power Distribution | Not Started | 2026-09-15 08:00 | 2026-09-22 16:00 |  |  | 7 | 7 | 101 | No |  |  | 34000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | DHP-050 | Terminate Data Hall Power Circuits | Electrical Systems | Data Hall Power Distribution | Not Started | 2027-01-07 08:00 | 2027-01-18 16:00 |  |  | 10 | 10 | 0 | Yes | 1 | 21 | 307000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | DHP-060 | Test Data Hall Distribution Circuits | Electrical Systems | Data Hall Power Distribution | Not Started | 2027-01-19 08:00 | 2027-01-23 16:00 |  |  | 5 | 5 | 0 | Yes | 1 | 22 | 187000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | DHP-070 | Data Hall Power Distribution Ready for Pre-Commissioning | Electrical Systems | Data Hall Power Distribution | Not Started | 2027-01-23 16:00 | 2027-01-23 16:00 |  |  | 0 | 0 | 0 | Yes | 1 | 23 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | LPS-010 | Install Roof Lightning Protection Network | Electrical Systems | Lightning Protection | Not Started | 2026-09-21 08:00 | 2026-09-28 16:00 |  |  | 7 | 7 | 98 | No |  |  | 276000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | LPS-020 | Install Lightning Protection Down Conductors | Electrical Systems | Lightning Protection | Not Started | 2026-09-23 08:00 | 2026-09-28 16:00 |  |  | 5 | 5 | 98 | No |  |  | 249000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | LPS-030 | Connect Lightning Protection to Earth Network | Electrical Systems | Lightning Protection | Not Started | 2026-09-29 08:00 | 2026-10-01 16:00 |  |  | 3 | 3 | 98 | No |  |  | 134000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | LPS-040 | Test Lightning Protection System | Electrical Systems | Lightning Protection | Not Started | 2026-10-02 08:00 | 2026-10-03 16:00 |  |  | 2 | 2 | 98 | No |  |  | 142000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | LPS-050 | Lightning Protection System Complete | Electrical Systems | Lightning Protection | Not Started | 2026-10-03 16:00 | 2026-10-03 16:00 |  |  | 0 | 0 | 98 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | ERT-010 | Install Main Site Earthing Grid | Electrical Systems | Earthing & Bonding | Not Started | 2026-04-13 08:00 | 2026-04-23 16:00 |  |  | 10 | 10 | 215 | No |  |  | 307000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | ERT-020 | Install Building Earthing Network | Electrical Systems | Earthing & Bonding | Not Started | 2026-06-12 08:00 | 2026-06-23 16:00 |  |  | 10 | 10 | 166 | No |  |  | 307000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | ERT-030 | Install Electrical Room Earth Bars | Electrical Systems | Earthing & Bonding | Not Started | 2026-10-05 08:00 | 2026-10-09 16:00 |  |  | 5 | 5 | 78 | No |  |  | 249000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | ERT-040 | Bond Transformers and Switchgear | Electrical Systems | Earthing & Bonding | Not Started | 2026-12-18 08:00 | 2026-12-23 16:00 |  |  | 5 | 5 | 24 | No |  |  | 156000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | ERT-050 | Bond UPS and Generator Equipment | Electrical Systems | Earthing & Bonding | Not Started | 2026-12-21 08:00 | 2026-12-25 16:00 |  |  | 5 | 5 | 22 | No |  |  | 156000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | ERT-060 | Bond Mechanical and Data Hall Equipment | Electrical Systems | Earthing & Bonding | Not Started | 2026-10-22 08:00 | 2026-11-02 16:00 |  |  | 10 | 10 | 68 | No |  |  | 192000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | ERT-070 | Perform Earthing Resistance Tests | Electrical Systems | Earthing & Bonding | Not Started | 2026-12-26 08:00 | 2026-12-29 16:00 |  |  | 3 | 3 | 22 | No |  |  | 160000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | ERT-080 | Earthing and Bonding System Complete | Electrical Systems | Earthing & Bonding | Not Started | 2026-12-29 16:00 | 2026-12-29 16:00 |  |  | 0 | 0 | 22 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | ERA-010 | Install Electrical Room Cable Trays and Containment | Electrical Systems | Electrical Rooms & Ancillary Systems | Not Started | 2026-10-05 08:00 | 2026-10-15 16:00 |  |  | 10 | 10 | 86 | No |  |  | 307000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | ERA-020 | Install Electrical Room Lighting | Electrical Systems | Electrical Rooms & Ancillary Systems | Not Started | 2026-10-08 08:00 | 2026-10-15 16:00 |  |  | 7 | 7 | 86 | No |  |  | 276000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | ERA-030 | Install Electrical Room Small Power | Electrical Systems | Electrical Rooms & Ancillary Systems | Not Started | 2026-10-08 08:00 | 2026-10-15 16:00 |  |  | 7 | 7 | 86 | No |  |  | 276000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | ERA-040 | Install Emergency Lighting | Electrical Systems | Electrical Rooms & Ancillary Systems | Not Started | 2026-10-10 08:00 | 2026-10-15 16:00 |  |  | 5 | 5 | 86 | No |  |  | 249000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | ERA-050 | Install Electrical Room Identification and Labels | Electrical Systems | Electrical Rooms & Ancillary Systems | Not Started | 2027-01-01 08:00 | 2027-01-04 16:00 |  |  | 3 | 3 | 17 | No |  |  | 214000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | ERA-060 | Complete Electrical Room Fire-Stopping | Electrical Systems | Electrical Rooms & Ancillary Systems | Not Started | 2026-12-30 08:00 | 2027-01-04 16:00 |  |  | 5 | 5 | 17 | No |  |  | 156000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | ERA-070 | Complete Electrical Room Installation Inspection | Electrical Systems | Electrical Rooms & Ancillary Systems | Not Started | 2027-01-05 08:00 | 2027-01-06 16:00 |  |  | 2 | 2 | 17 | No |  |  | 189000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | ERA-080 | Electrical Rooms Ready for Commissioning | Electrical Systems | Electrical Rooms & Ancillary Systems | Not Started | 2027-01-06 16:00 | 2027-01-06 16:00 |  |  | 0 | 0 | 17 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | CLG-010 | Prepare Cooling Plant Area for Installation | Mechanical & Cooling Systems | Cooling Plant | Not Started | 2026-08-25 08:00 | 2026-08-27 16:00 |  |  | 3 | 3 | 108 | No |  |  | 158000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CLG-020 | Install Cooling Plant Equipment Supports | Mechanical & Cooling Systems | Cooling Plant | Not Started | 2026-08-28 08:00 | 2026-09-02 16:00 |  |  | 5 | 5 | 108 | No |  |  | 185000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CLG-030 | Install Cooling Plant Main Headers | Mechanical & Cooling Systems | Cooling Plant | Not Started | 2026-09-03 08:00 | 2026-09-14 16:00 |  |  | 10 | 10 | 108 | No |  |  | 227000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CLG-040 | Install Cooling Plant Valves and Accessories | Mechanical & Cooling Systems | Cooling Plant | Not Started | 2026-09-15 08:00 | 2026-09-19 16:00 |  |  | 5 | 5 | 108 | No |  |  | 185000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CLG-050 | Install Cooling Plant Electrical Interfaces | Mechanical & Cooling Systems | Cooling Plant | Not Started | 2026-09-09 08:00 | 2026-09-14 16:00 |  |  | 5 | 5 | 113 | No |  |  | 185000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CLG-060 | Install Cooling Plant Controls Interfaces | Mechanical & Cooling Systems | Cooling Plant | Not Started | 2026-09-09 08:00 | 2026-09-14 16:00 |  |  | 5 | 5 | 113 | No |  |  | 185000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CLG-070 | Inspect Cooling Plant Installation | Mechanical & Cooling Systems | Cooling Plant | Not Started | 2026-09-21 08:00 | 2026-09-22 16:00 |  |  | 2 | 2 | 108 | No |  |  | 140000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CLG-080 | Cooling Plant Ready for Pre-Commissioning | Mechanical & Cooling Systems | Cooling Plant | Not Started | 2026-09-22 16:00 | 2026-09-22 16:00 |  |  | 0 | 0 | 108 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | CHR-010 | Prepare Chiller and Heat Rejection Equipment Areas | Mechanical & Cooling Systems | Chillers / Heat Rejection Equipment | Not Started | 2026-08-28 08:00 | 2026-08-31 16:00 |  |  | 3 | 3 | 47 | No |  |  | 99000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CHR-020 | Receive and Inspect Chillers and Heat Rejection Equipment | Mechanical & Cooling Systems | Chillers / Heat Rejection Equipment | Not Started | 2026-09-01 08:00 | 2026-09-02 16:00 |  |  | 2 | 2 | 47 | No |  |  | 105000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CHR-030 | Position Chillers on Equipment Bases | Mechanical & Cooling Systems | Chillers / Heat Rejection Equipment | Not Started | 2026-09-03 08:00 | 2026-09-08 16:00 |  |  | 5 | 5 | 47 | No |  |  | 115000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CHR-040 | Position Heat Rejection Equipment | Mechanical & Cooling Systems | Chillers / Heat Rejection Equipment | Not Started | 2026-09-03 08:00 | 2026-09-08 16:00 |  |  | 5 | 5 | 99 | No |  |  | 115000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CHR-050 | Install Chiller Mechanical Connections | Mechanical & Cooling Systems | Chillers / Heat Rejection Equipment | Not Started | 2026-09-09 08:00 | 2026-09-19 16:00 |  |  | 10 | 10 | 47 | No |  |  | 227000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CHR-060 | Install Heat Rejection Equipment Connections | Mechanical & Cooling Systems | Chillers / Heat Rejection Equipment | Not Started | 2026-09-09 08:00 | 2026-09-16 16:00 |  |  | 7 | 7 | 99 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CHR-070 | Install Electrical and Controls Connections | Mechanical & Cooling Systems | Chillers / Heat Rejection Equipment | Not Started | 2026-09-05 08:00 | 2026-09-12 16:00 |  |  | 7 | 7 | 102 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CHR-080 | Complete Chiller Installation Inspection | Mechanical & Cooling Systems | Chillers / Heat Rejection Equipment | Not Started | 2026-09-21 08:00 | 2026-09-22 16:00 |  |  | 2 | 2 | 96 | No |  |  | 140000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CHR-090 | Chillers and Heat Rejection Equipment Ready for Pre-Commissioning | Mechanical & Cooling Systems | Chillers / Heat Rejection Equipment | Not Started | 2026-09-22 16:00 | 2026-09-22 16:00 |  |  | 0 | 0 | 96 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | PMP-010 | Prepare Pump Bases for Installation | Mechanical & Cooling Systems | Pumps & Pumping Systems | Not Started | 2026-08-25 08:00 | 2026-08-27 16:00 |  |  | 3 | 3 | 53 | No |  |  | 158000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | PMP-020 | Receive and Inspect Pumps | Mechanical & Cooling Systems | Pumps & Pumping Systems | Not Started | 2026-08-28 08:00 | 2026-08-29 16:00 |  |  | 2 | 2 | 53 | No |  |  | 105000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | PMP-030 | Install Primary Cooling Pumps | Mechanical & Cooling Systems | Pumps & Pumping Systems | Not Started | 2026-08-31 08:00 | 2026-09-04 16:00 |  |  | 5 | 5 | 53 | No |  |  | 185000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | PMP-040 | Install Secondary Cooling Pumps | Mechanical & Cooling Systems | Pumps & Pumping Systems | Not Started | 2026-08-31 08:00 | 2026-09-04 16:00 |  |  | 5 | 5 | 53 | No |  |  | 185000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | PMP-050 | Install Pump Suction and Discharge Connections | Mechanical & Cooling Systems | Pumps & Pumping Systems | Not Started | 2026-09-05 08:00 | 2026-09-12 16:00 |  |  | 7 | 7 | 53 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | PMP-060 | Install Pump Electrical Connections | Mechanical & Cooling Systems | Pumps & Pumping Systems | Not Started | 2026-09-02 08:00 | 2026-09-07 16:00 |  |  | 5 | 5 | 107 | No |  |  | 185000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | PMP-070 | Install Pump Controls and Instrumentation | Mechanical & Cooling Systems | Pumps & Pumping Systems | Not Started | 2026-09-02 08:00 | 2026-09-07 16:00 |  |  | 5 | 5 | 107 | No |  |  | 185000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | PMP-080 | Inspect Pumping System Installation | Mechanical & Cooling Systems | Pumps & Pumping Systems | Not Started | 2026-09-14 08:00 | 2026-09-15 16:00 |  |  | 2 | 2 | 102 | No |  |  | 140000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | PMP-090 | Pumping Systems Ready for Pre-Commissioning | Mechanical & Cooling Systems | Pumps & Pumping Systems | Not Started | 2026-09-15 16:00 | 2026-09-15 16:00 |  |  | 0 | 0 | 102 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | CHW-010 | Set Out Chilled Water Pipework Routes | Mechanical & Cooling Systems | Chilled Water Distribution | Not Started | 2026-08-25 08:00 | 2026-08-27 16:00 |  |  | 3 | 3 | 44 | No |  |  | 158000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CHW-020 | Install Chilled Water Pipe Supports | Mechanical & Cooling Systems | Chilled Water Distribution | Not Started | 2026-08-28 08:00 | 2026-09-08 16:00 |  |  | 10 | 10 | 44 | No |  |  | 227000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CHW-030 | Install Main Chilled Water Pipework | Mechanical & Cooling Systems | Chilled Water Distribution | Not Started | 2026-09-01 08:00 | 2026-09-17 16:00 |  |  | 15 | 15 | 44 | No |  |  | 262000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CHW-040 | Install Chilled Water Branch Pipework | Mechanical & Cooling Systems | Chilled Water Distribution | Not Started | 2026-09-07 08:00 | 2026-09-23 16:00 |  |  | 15 | 15 | 44 | No |  |  | 257000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CHW-050 | Install Chilled Water Valves and Accessories | Mechanical & Cooling Systems | Chilled Water Distribution | Not Started | 2026-09-16 08:00 | 2026-09-23 16:00 |  |  | 7 | 7 | 44 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CHW-060 | Pressure Test Chilled Water Pipework | Mechanical & Cooling Systems | Chilled Water Distribution | Not Started | 2026-09-24 08:00 | 2026-10-01 16:00 |  |  | 7 | 7 | 44 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CHW-070 | Flush and Clean Chilled Water System | Mechanical & Cooling Systems | Chilled Water Distribution | Not Started | 2026-10-02 08:00 | 2026-10-07 16:00 |  |  | 5 | 5 | 44 | No |  |  | 115000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CHW-080 | Install Chilled Water Pipe Insulation | Mechanical & Cooling Systems | Chilled Water Distribution | Not Started | 2026-09-26 08:00 | 2026-10-07 16:00 |  |  | 10 | 10 | 95 | No |  |  | 227000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CHW-090 | Chilled Water Distribution Ready for Pre-Commissioning | Mechanical & Cooling Systems | Chilled Water Distribution | Not Started | 2026-10-07 16:00 | 2026-10-07 16:00 |  |  | 0 | 0 | 95 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | CRAC-010 | Prepare CRAH/CRAC Installation Areas | Mechanical & Cooling Systems | CRAH / CRAC Systems | Not Started | 2026-09-03 08:00 | 2026-09-05 16:00 |  |  | 3 | 3 | 59 | No |  |  | 158000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CRAC-020 | Receive and Inspect CRAH/CRAC Units | Mechanical & Cooling Systems | CRAH / CRAC Systems | Not Started | 2026-09-07 08:00 | 2026-09-08 16:00 |  |  | 2 | 2 | 59 | No |  |  | 105000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CRAC-030 | Position and Install CRAH/CRAC Units | Mechanical & Cooling Systems | CRAH / CRAC Systems | Not Started | 2026-10-10 08:00 | 2026-10-21 16:00 |  |  | 10 | 10 | 32 | No |  |  | 227000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CRAC-040 | Install CRAH/CRAC Chilled Water Connections | Mechanical & Cooling Systems | CRAH / CRAC Systems | Not Started | 2026-10-22 08:00 | 2026-11-02 16:00 |  |  | 10 | 10 | 32 | No |  |  | 227000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CRAC-050 | Install CRAH/CRAC Condensate Connections | Mechanical & Cooling Systems | CRAH / CRAC Systems | Not Started | 2026-10-22 08:00 | 2026-10-29 16:00 |  |  | 7 | 7 | 62 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CRAC-060 | Install CRAH/CRAC Electrical Connections | Mechanical & Cooling Systems | CRAH / CRAC Systems | Not Started | 2026-10-22 08:00 | 2026-10-29 16:00 |  |  | 7 | 7 | 62 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CRAC-070 | Install CRAH/CRAC Controls Connections | Mechanical & Cooling Systems | CRAH / CRAC Systems | Not Started | 2026-10-22 08:00 | 2026-10-29 16:00 |  |  | 7 | 7 | 62 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CRAC-080 | Complete CRAH/CRAC Installation Inspection | Mechanical & Cooling Systems | CRAH / CRAC Systems | Not Started | 2026-11-03 08:00 | 2026-11-04 16:00 |  |  | 2 | 2 | 59 | No |  |  | 140000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CRAC-090 | CRAH/CRAC Systems Ready for Pre-Commissioning | Mechanical & Cooling Systems | CRAH / CRAC Systems | Not Started | 2026-11-04 16:00 | 2026-11-04 16:00 |  |  | 0 | 0 | 59 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | DHC-010 | Set Out Data Hall Cooling Distribution | Mechanical & Cooling Systems | Data Hall Cooling Distribution | Not Started | 2026-09-03 08:00 | 2026-09-05 16:00 |  |  | 3 | 3 | 70 | No |  |  | 99000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | DHC-020 | Install Data Hall Cooling Pipe Supports | Mechanical & Cooling Systems | Data Hall Cooling Distribution | Not Started | 2026-09-07 08:00 | 2026-09-14 16:00 |  |  | 7 | 7 | 70 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | DHC-030 | Install Data Hall Cooling Distribution Pipework | Mechanical & Cooling Systems | Data Hall Cooling Distribution | Not Started | 2026-09-10 08:00 | 2026-09-26 16:00 |  |  | 15 | 15 | 70 | No |  |  | 257000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | DHC-040 | Install Data Hall Cooling Valves and Accessories | Mechanical & Cooling Systems | Data Hall Cooling Distribution | Not Started | 2026-09-19 08:00 | 2026-09-26 16:00 |  |  | 7 | 7 | 70 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | DHC-050 | Connect Cooling Distribution to CRAH/CRAC Systems | Mechanical & Cooling Systems | Data Hall Cooling Distribution | Not Started | 2026-10-22 08:00 | 2026-11-02 16:00 |  |  | 10 | 10 | 49 | No |  |  | 142000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | DHC-060 | Pressure Test Data Hall Cooling Distribution | Mechanical & Cooling Systems | Data Hall Cooling Distribution | Not Started | 2026-11-03 08:00 | 2026-11-07 16:00 |  |  | 5 | 5 | 49 | No |  |  | 138000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | DHC-070 | Flush Data Hall Cooling Distribution | Mechanical & Cooling Systems | Data Hall Cooling Distribution | Not Started | 2026-11-09 08:00 | 2026-11-13 16:00 |  |  | 5 | 5 | 51 | No |  |  | 115000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | DHC-080 | Insulate Data Hall Cooling Pipework | Mechanical & Cooling Systems | Data Hall Cooling Distribution | Not Started | 2026-11-05 08:00 | 2026-11-16 16:00 |  |  | 10 | 10 | 49 | No |  |  | 227000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | DHC-090 | Data Hall Cooling Distribution Ready for Pre-Commissioning | Mechanical & Cooling Systems | Data Hall Cooling Distribution | Not Started | 2026-11-16 16:00 | 2026-11-16 16:00 |  |  | 0 | 0 | 49 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | VEN-010 | Install Ventilation Ductwork Supports | Mechanical & Cooling Systems | Ventilation & Exhaust Systems | Not Started | 2026-10-05 08:00 | 2026-10-12 16:00 |  |  | 7 | 7 | 77 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | VEN-020 | Install Ventilation and Exhaust Ductwork | Mechanical & Cooling Systems | Ventilation & Exhaust Systems | Not Started | 2026-10-07 08:00 | 2026-10-23 16:00 |  |  | 15 | 15 | 77 | No |  |  | 257000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | VEN-030 | Install Ventilation Fans | Mechanical & Cooling Systems | Ventilation & Exhaust Systems | Not Started | 2026-10-07 08:00 | 2026-10-14 16:00 |  |  | 7 | 7 | 80 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | VEN-040 | Install Dampers and Air Control Devices | Mechanical & Cooling Systems | Ventilation & Exhaust Systems | Not Started | 2026-10-10 08:00 | 2026-10-17 16:00 |  |  | 7 | 7 | 77 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | VEN-050 | Install Louvers Grilles and Terminals | Mechanical & Cooling Systems | Ventilation & Exhaust Systems | Not Started | 2026-10-10 08:00 | 2026-10-17 16:00 |  |  | 7 | 7 | 77 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | VEN-060 | Install Ventilation Controls Connections | Mechanical & Cooling Systems | Ventilation & Exhaust Systems | Not Started | 2026-10-19 08:00 | 2026-10-26 16:00 |  |  | 7 | 7 | 77 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | VEN-070 | Inspect Ventilation and Exhaust Installation | Mechanical & Cooling Systems | Ventilation & Exhaust Systems | Not Started | 2026-10-27 08:00 | 2026-10-28 16:00 |  |  | 2 | 2 | 77 | No |  |  | 140000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | VEN-080 | Ventilation and Exhaust Systems Ready for Pre-Commissioning | Mechanical & Cooling Systems | Ventilation & Exhaust Systems | Not Started | 2026-10-28 16:00 | 2026-10-28 16:00 |  |  | 0 | 0 | 77 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | MCI-010 | Install Mechanical Control Panels | Mechanical & Cooling Systems | Mechanical Controls & Instrumentation | Not Started | 2026-10-22 08:00 | 2026-10-27 16:00 |  |  | 5 | 5 | 40 | No |  |  | 185000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | MCI-020 | Install Temperature Sensors | Mechanical & Cooling Systems | Mechanical Controls & Instrumentation | Not Started | 2026-10-24 08:00 | 2026-10-31 16:00 |  |  | 7 | 7 | 43 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | MCI-030 | Install Pressure Sensors | Mechanical & Cooling Systems | Mechanical Controls & Instrumentation | Not Started | 2026-10-24 08:00 | 2026-10-31 16:00 |  |  | 7 | 7 | 43 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | MCI-040 | Install Flow Measurement Devices | Mechanical & Cooling Systems | Mechanical Controls & Instrumentation | Not Started | 2026-10-24 08:00 | 2026-10-31 16:00 |  |  | 7 | 7 | 43 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | MCI-050 | Install Control Valves and Actuators | Mechanical & Cooling Systems | Mechanical Controls & Instrumentation | Not Started | 2026-11-03 08:00 | 2026-11-13 16:00 |  |  | 10 | 10 | 32 | No |  |  | 227000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | MCI-060 | Complete Mechanical Controls Field Wiring | Mechanical & Cooling Systems | Mechanical Controls & Instrumentation | Not Started | 2026-11-14 08:00 | 2026-11-25 16:00 |  |  | 10 | 10 | 32 | No |  |  | 142000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | MCI-070 | Complete BMS Interface Connections | Mechanical & Cooling Systems | Mechanical Controls & Instrumentation | Not Started | 2026-11-26 08:00 | 2026-12-03 16:00 |  |  | 7 | 7 | 32 | No |  |  | 128000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | MCI-080 | Inspect Mechanical Controls and Instrumentation | Mechanical & Cooling Systems | Mechanical Controls & Instrumentation | Not Started | 2026-12-04 08:00 | 2026-12-07 16:00 |  |  | 3 | 3 | 32 | No |  |  | 119000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | MCI-090 | Mechanical Controls Ready for Pre-Commissioning | Mechanical & Cooling Systems | Mechanical Controls & Instrumentation | Not Started | 2026-12-07 16:00 | 2026-12-07 16:00 |  |  | 0 | 0 | 32 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | WTM-010 | Prepare Water Treatment Equipment Area | Mechanical & Cooling Systems | Water Treatment & Make-Up Systems | Not Started | 2026-08-25 08:00 | 2026-08-27 16:00 |  |  | 3 | 3 | 113 | No |  |  | 99000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | WTM-020 | Install Water Treatment Equipment | Mechanical & Cooling Systems | Water Treatment & Make-Up Systems | Not Started | 2026-08-28 08:00 | 2026-09-02 16:00 |  |  | 5 | 5 | 113 | No |  |  | 185000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | WTM-030 | Install Chemical Dosing System | Mechanical & Cooling Systems | Water Treatment & Make-Up Systems | Not Started | 2026-09-03 08:00 | 2026-09-08 16:00 |  |  | 5 | 5 | 113 | No |  |  | 185000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | WTM-040 | Install Cooling System Make-Up Water Connections | Mechanical & Cooling Systems | Water Treatment & Make-Up Systems | Not Started | 2026-09-03 08:00 | 2026-09-08 16:00 |  |  | 5 | 5 | 113 | No |  |  | 185000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | WTM-050 | Install Water Treatment Instrumentation | Mechanical & Cooling Systems | Water Treatment & Make-Up Systems | Not Started | 2026-08-31 08:00 | 2026-09-04 16:00 |  |  | 5 | 5 | 116 | No |  |  | 185000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | WTM-060 | Complete Electrical and Controls Connections | Mechanical & Cooling Systems | Water Treatment & Make-Up Systems | Not Started | 2026-09-09 08:00 | 2026-09-14 16:00 |  |  | 5 | 5 | 113 | No |  |  | 115000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | WTM-070 | Inspect Water Treatment and Make-Up Systems | Mechanical & Cooling Systems | Water Treatment & Make-Up Systems | Not Started | 2026-09-15 08:00 | 2026-09-16 16:00 |  |  | 2 | 2 | 113 | No |  |  | 105000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | WTM-080 | Water Treatment and Make-Up Systems Ready for Pre-Commissioning | Mechanical & Cooling Systems | Water Treatment & Make-Up Systems | Not Started | 2026-09-16 16:00 | 2026-09-16 16:00 |  |  | 0 | 0 | 113 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | MCA-010 | Install Mechanical Equipment Drainage Connections | Mechanical & Cooling Systems | Mechanical Ancillary Systems | Not Started | 2026-10-22 08:00 | 2026-10-29 16:00 |  |  | 7 | 7 | 73 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | MCA-020 | Install Condensate Drainage Systems | Mechanical & Cooling Systems | Mechanical Ancillary Systems | Not Started | 2026-10-22 08:00 | 2026-10-29 16:00 |  |  | 7 | 7 | 73 | No |  |  | 204000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | MCA-030 | Install Mechanical Equipment Identification and Labels | Mechanical & Cooling Systems | Mechanical Ancillary Systems | Not Started | 2026-09-07 08:00 | 2026-09-11 16:00 |  |  | 5 | 5 | 114 | No |  |  | 185000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | MCA-040 | Complete Mechanical Equipment Fire-Stopping | Mechanical & Cooling Systems | Mechanical Ancillary Systems | Not Started | 2026-10-14 08:00 | 2026-10-19 16:00 |  |  | 5 | 5 | 82 | No |  |  | 115000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | MCA-050 | Complete Mechanical Plant Access and Maintenance Provisions | Mechanical & Cooling Systems | Mechanical Ancillary Systems | Not Started | 2026-09-07 08:00 | 2026-09-11 16:00 |  |  | 5 | 5 | 114 | No |  |  | 115000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | MCA-060 | Complete Mechanical Installation Inspection | Mechanical & Cooling Systems | Mechanical Ancillary Systems | Not Started | 2026-10-30 08:00 | 2026-11-02 16:00 |  |  | 3 | 3 | 73 | No |  |  | 158000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | MCA-070 | Mechanical Systems Installation Complete | Mechanical & Cooling Systems | Mechanical Ancillary Systems | Not Started | 2026-11-02 16:00 | 2026-11-02 16:00 |  |  | 0 | 0 | 73 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | FAD-010 | Install Fire Alarm Control Panels | Fire & Life Safety | Fire Detection & Alarm | Not Started | 2026-06-10 08:00 | 2026-06-15 16:00 |  |  | 5 | 5 | 175 | No |  |  | 82000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | FAD-020 | Install Fire Alarm Cabling | Fire & Life Safety | Fire Detection & Alarm | Not Started | 2026-10-08 08:00 | 2026-10-19 16:00 |  |  | 10 | 10 | 67 | No |  |  | 106000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | FAD-030 | Install Smoke and Heat Detectors | Fire & Life Safety | Fire Detection & Alarm | Not Started | 2026-10-10 08:00 | 2026-10-19 16:00 |  |  | 8 | 8 | 67 | No |  |  | 95000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | FAD-040 | Install Manual Call Points | Fire & Life Safety | Fire Detection & Alarm | Not Started | 2026-10-10 08:00 | 2026-10-14 16:00 |  |  | 4 | 4 | 71 | No |  |  | 77000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | FAD-050 | Install Notification Devices | Fire & Life Safety | Fire Detection & Alarm | Not Started | 2026-10-10 08:00 | 2026-10-16 16:00 |  |  | 6 | 6 | 69 | No |  |  | 87000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | FAD-060 | Complete Fire Alarm Device Addressing | Fire & Life Safety | Fire Detection & Alarm | Not Started | 2026-10-20 08:00 | 2026-10-21 16:00 |  |  | 2 | 2 | 67 | No |  |  | 39000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | FAD-070 | Inspect Fire Detection and Alarm Installation | Fire & Life Safety | Fire Detection & Alarm | Not Started | 2026-10-22 08:00 | 2026-10-23 16:00 |  |  | 2 | 2 | 67 | No |  |  | 63000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | FAD-080 | Fire Detection and Alarm Ready for Pre-Commissioning | Fire & Life Safety | Fire Detection & Alarm | Not Started | 2026-10-23 16:00 | 2026-10-23 16:00 |  |  | 0 | 0 | 67 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | SPR-010 | Install Sprinkler Main Pipework | Fire & Life Safety | Sprinkler System | Not Started | 2026-10-08 08:00 | 2026-10-19 16:00 |  |  | 10 | 10 | 71 | No |  |  | 101000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | SPR-020 | Install Sprinkler Branch Pipework | Fire & Life Safety | Sprinkler System | Not Started | 2026-10-12 08:00 | 2026-10-22 16:00 |  |  | 10 | 10 | 71 | No |  |  | 101000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | SPR-030 | Install Sprinkler Heads | Fire & Life Safety | Sprinkler System | Not Started | 2026-10-15 08:00 | 2026-10-23 16:00 |  |  | 8 | 8 | 71 | No |  |  | 95000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | SPR-040 | Install Zone Control Assemblies | Fire & Life Safety | Sprinkler System | Not Started | 2026-10-10 08:00 | 2026-10-15 16:00 |  |  | 5 | 5 | 78 | No |  |  | 82000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | SPR-050 | Pressure Test Sprinkler System | Fire & Life Safety | Sprinkler System | Not Started | 2026-10-24 08:00 | 2026-10-27 16:00 |  |  | 3 | 3 | 71 | No |  |  | 53000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | SPR-060 | Flush Sprinkler System | Fire & Life Safety | Sprinkler System | Not Started | 2026-10-28 08:00 | 2026-11-02 16:00 |  |  | 5 | 5 | 71 | No |  |  | 51000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | SPR-070 | Inspect Sprinkler Installation | Fire & Life Safety | Sprinkler System | Not Started | 2026-11-03 08:00 | 2026-11-04 16:00 |  |  | 2 | 2 | 71 | No |  |  | 63000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | SPR-080 | Sprinkler System Ready for Pre-Commissioning | Fire & Life Safety | Sprinkler System | Not Started | 2026-11-04 16:00 | 2026-11-04 16:00 |  |  | 0 | 0 | 71 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | CAF-010 | Prepare Clean Agent Protected Areas | Fire & Life Safety | Clean Agent Fire Suppression | Not Started | 2026-10-08 08:00 | 2026-10-13 16:00 |  |  | 5 | 5 | 73 | No |  |  | 51000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CAF-020 | Install Clean Agent Cylinders | Fire & Life Safety | Clean Agent Fire Suppression | Not Started | 2026-10-14 08:00 | 2026-10-19 16:00 |  |  | 5 | 5 | 76 | No |  |  | 82000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CAF-030 | Install Clean Agent Distribution Pipework | Fire & Life Safety | Clean Agent Fire Suppression | Not Started | 2026-10-14 08:00 | 2026-10-22 16:00 |  |  | 8 | 8 | 73 | No |  |  | 95000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CAF-040 | Install Clean Agent Discharge Nozzles | Fire & Life Safety | Clean Agent Fire Suppression | Not Started | 2026-10-23 08:00 | 2026-10-28 16:00 |  |  | 5 | 5 | 73 | No |  |  | 82000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CAF-050 | Install Release and Control Interfaces | Fire & Life Safety | Clean Agent Fire Suppression | Not Started | 2026-10-22 08:00 | 2026-10-27 16:00 |  |  | 5 | 5 | 74 | No |  |  | 82000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CAF-060 | Complete Room Integrity Preparations | Fire & Life Safety | Clean Agent Fire Suppression | Not Started | 2026-10-29 08:00 | 2026-10-30 16:00 |  |  | 2 | 2 | 73 | No |  |  | 39000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CAF-070 | Inspect Clean Agent Suppression Installation | Fire & Life Safety | Clean Agent Fire Suppression | Not Started | 2026-10-31 08:00 | 2026-11-02 16:00 |  |  | 2 | 2 | 73 | No |  |  | 63000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CAF-080 | Clean Agent Suppression Ready for Pre-Commissioning | Fire & Life Safety | Clean Agent Fire Suppression | Not Started | 2026-11-02 16:00 | 2026-11-02 16:00 |  |  | 0 | 0 | 73 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | FPW-010 | Prepare Fire Pump Room | Fire & Life Safety | Fire Pump & Water Supply | Not Started | 2026-06-10 08:00 | 2026-06-15 16:00 |  |  | 5 | 5 | 178 | No |  |  | 51000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | FPW-020 | Install Fire Water Tank Connections | Fire & Life Safety | Fire Pump & Water Supply | Not Started | 2026-06-16 08:00 | 2026-06-20 16:00 |  |  | 5 | 5 | 178 | No |  |  | 82000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | FPW-030 | Install Main Fire Pumps | Fire & Life Safety | Fire Pump & Water Supply | Not Started | 2026-06-16 08:00 | 2026-06-20 16:00 |  |  | 5 | 5 | 178 | No |  |  | 82000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | FPW-040 | Install Jockey Pump | Fire & Life Safety | Fire Pump & Water Supply | Not Started | 2026-06-16 08:00 | 2026-06-20 16:00 |  |  | 5 | 5 | 178 | No |  |  | 82000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | FPW-050 | Install Fire Pump Pipework and Valves | Fire & Life Safety | Fire Pump & Water Supply | Not Started | 2026-06-22 08:00 | 2026-06-30 16:00 |  |  | 8 | 8 | 178 | No |  |  | 95000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | FPW-060 | Install Fire Pump Electrical Connections | Fire & Life Safety | Fire Pump & Water Supply | Not Started | 2026-06-22 08:00 | 2026-06-26 16:00 |  |  | 5 | 5 | 181 | No |  |  | 82000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | FPW-070 | Install Fire Pump Controls | Fire & Life Safety | Fire Pump & Water Supply | Not Started | 2026-10-22 08:00 | 2026-10-27 16:00 |  |  | 5 | 5 | 76 | No |  |  | 82000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | FPW-080 | Inspect Fire Pump and Water Supply Installation | Fire & Life Safety | Fire Pump & Water Supply | Not Started | 2026-10-28 08:00 | 2026-10-29 16:00 |  |  | 2 | 2 | 76 | No |  |  | 63000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | FPW-090 | Fire Pump and Water Supply Ready for Pre-Commissioning | Fire & Life Safety | Fire Pump & Water Supply | Not Started | 2026-10-29 16:00 | 2026-10-29 16:00 |  |  | 0 | 0 | 76 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | VES-010 | Install VESDA Control Units | Fire & Life Safety | Smoke Detection / VESDA | Not Started | 2026-06-10 08:00 | 2026-06-15 16:00 |  |  | 5 | 5 | 187 | No |  |  | 82000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | VES-020 | Install VESDA Sampling Pipe Network | Fire & Life Safety | Smoke Detection / VESDA | Not Started | 2026-10-08 08:00 | 2026-10-16 16:00 |  |  | 8 | 8 | 81 | No |  |  | 95000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | VES-030 | Install VESDA Sampling Points | Fire & Life Safety | Smoke Detection / VESDA | Not Started | 2026-10-12 08:00 | 2026-10-16 16:00 |  |  | 5 | 5 | 81 | No |  |  | 82000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | VES-040 | Complete VESDA Electrical Connections | Fire & Life Safety | Smoke Detection / VESDA | Not Started | 2026-10-17 08:00 | 2026-10-19 16:00 |  |  | 2 | 2 | 81 | No |  |  | 39000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | VES-050 | Complete VESDA Fire Alarm Interfaces | Fire & Life Safety | Smoke Detection / VESDA | Not Started | 2026-10-22 08:00 | 2026-10-23 16:00 |  |  | 2 | 2 | 79 | No |  |  | 39000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | VES-060 | Inspect VESDA Installation | Fire & Life Safety | Smoke Detection / VESDA | Not Started | 2026-10-24 08:00 | 2026-10-26 16:00 |  |  | 2 | 2 | 79 | No |  |  | 63000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | VES-070 | VESDA System Ready for Pre-Commissioning | Fire & Life Safety | Smoke Detection / VESDA | Not Started | 2026-10-26 16:00 | 2026-10-26 16:00 |  |  | 0 | 0 | 79 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | EML-010 | Install Emergency Lighting Fixtures | Fire & Life Safety | Emergency Lighting & Exit Systems | Not Started | 2026-12-25 08:00 | 2026-12-30 16:00 |  |  | 5 | 5 | 21 | No |  |  | 82000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | EML-020 | Install Exit Signage | Fire & Life Safety | Emergency Lighting & Exit Systems | Not Started | 2026-12-25 08:00 | 2026-12-30 16:00 |  |  | 5 | 5 | 21 | No |  |  | 82000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | EML-030 | Install Emergency Lighting Circuits | Fire & Life Safety | Emergency Lighting & Exit Systems | Not Started | 2026-12-24 08:00 | 2026-12-29 16:00 |  |  | 5 | 5 | 17 | No |  |  | 82000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | EML-040 | Install Emergency Lighting Controls | Fire & Life Safety | Emergency Lighting & Exit Systems | Not Started | 2026-12-30 08:00 | 2027-01-04 16:00 |  |  | 5 | 5 | 17 | No |  |  | 82000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | EML-050 | Inspect Emergency Lighting and Exit Systems | Fire & Life Safety | Emergency Lighting & Exit Systems | Not Started | 2027-01-05 08:00 | 2027-01-06 16:00 |  |  | 2 | 2 | 17 | No |  |  | 47000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | EML-060 | Emergency Lighting and Exit Systems Ready for Testing | Fire & Life Safety | Emergency Lighting & Exit Systems | Not Started | 2027-01-06 16:00 | 2027-01-06 16:00 |  |  | 0 | 0 | 17 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | FSI-010 | Install Fire Alarm Interface Modules | Fire & Life Safety | Fire System Interfaces | Not Started | 2026-10-24 08:00 | 2026-10-29 16:00 |  |  | 5 | 5 | 67 | No |  |  | 82000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | FSI-020 | Connect Fire Alarm to Mechanical Systems | Fire & Life Safety | Fire System Interfaces | Not Started | 2026-12-08 08:00 | 2026-12-12 16:00 |  |  | 5 | 5 | 34 | No |  |  | 51000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | FSI-030 | Connect Fire Alarm to Electrical Systems | Fire & Life Safety | Fire System Interfaces | Not Started | 2026-12-24 08:00 | 2026-12-29 16:00 |  |  | 5 | 5 | 20 | No |  |  | 51000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | FSI-040 | Connect Fire Alarm to Access Control System | Fire & Life Safety | Fire System Interfaces | Not Started | 2026-10-30 08:00 | 2026-11-04 16:00 |  |  | 5 | 5 | 67 | No |  |  | 51000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | FSI-050 | Connect Fire Alarm to BMS | Fire & Life Safety | Fire System Interfaces | Not Started | 2026-12-29 08:00 | 2027-01-02 16:00 |  |  | 5 | 5 | 16 | No |  |  | 51000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | FSI-060 | Complete Fire Cause and Effect Configuration | Fire & Life Safety | Fire System Interfaces | Not Started | 2027-01-04 08:00 | 2027-01-05 16:00 |  |  | 2 | 2 | 16 | No |  |  | 39000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | FSI-070 | Inspect Fire System Interfaces | Fire & Life Safety | Fire System Interfaces | Not Started | 2027-01-06 08:00 | 2027-01-07 16:00 |  |  | 2 | 2 | 16 | No |  |  | 47000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | FSI-080 | Fire System Interfaces Ready for Integrated Testing | Fire & Life Safety | Fire System Interfaces | Not Started | 2027-01-07 16:00 | 2027-01-07 16:00 |  |  | 0 | 0 | 16 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | LSC-010 | Conduct Internal Fire and Life Safety Inspection | Fire & Life Safety | Life Safety Compliance & Inspections | Not Started | 2027-02-08 08:00 | 2027-02-09 16:00 |  |  | 2 | 2 | 63 | No |  |  | 47000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | LSC-020 | Conduct Fire-Stopping Inspection | Fire & Life Safety | Life Safety Compliance & Inspections | Not Started | 2026-10-08 08:00 | 2026-10-09 16:00 |  |  | 2 | 2 | 168 | No |  |  | 47000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | LSC-030 | Conduct Emergency Egress Inspection | Fire & Life Safety | Life Safety Compliance & Inspections | Not Started | 2026-10-08 08:00 | 2026-10-09 16:00 |  |  | 2 | 2 | 168 | No |  |  | 47000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | LSC-040 | Conduct Fire System Compliance Review | Fire & Life Safety | Life Safety Compliance & Inspections | Not Started | 2027-02-10 08:00 | 2027-02-15 16:00 |  |  | 5 | 5 | 63 | No |  |  | 10000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | LSC-050 | Rectify Fire and Life Safety Inspection Comments | Fire & Life Safety | Life Safety Compliance & Inspections | Not Started | 2027-02-16 08:00 | 2027-02-17 16:00 |  |  | 2 | 2 | 63 | No |  |  | 47000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | LSC-060 | Prepare Authority Inspection Documentation | Fire & Life Safety | Life Safety Compliance & Inspections | Not Started | 2027-02-18 08:00 | 2027-02-19 16:00 |  |  | 2 | 2 | 63 | No |  |  | 47000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | LSC-070 | Fire and Life Safety Systems Ready for Authority Inspection | Fire & Life Safety | Life Safety Compliance & Inspections | Not Started | 2027-02-19 16:00 | 2027-02-19 16:00 |  |  | 0 | 0 | 63 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | BMSI-010 | Prepare BMS Installation Areas | Controls, BMS & DCIM | BMS Infrastructure | Not Started | 2026-10-10 08:00 | 2026-10-15 16:00 |  |  | 5 | 5 | 44 | No |  |  | 126000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | BMSI-020 | Install BMS Control Panels | Controls, BMS & DCIM | BMS Infrastructure | Not Started | 2026-10-16 08:00 | 2026-10-21 16:00 |  |  | 5 | 5 | 65 | No |  |  | 126000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | BMSI-030 | Install BMS Network Infrastructure | Controls, BMS & DCIM | BMS Infrastructure | Not Started | 2026-10-16 08:00 | 2026-10-24 16:00 |  |  | 8 | 8 | 44 | No |  |  | 145000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | BMSI-040 | Install BMS Field Cabling | Controls, BMS & DCIM | BMS Infrastructure | Not Started | 2026-10-19 08:00 | 2026-10-29 16:00 |  |  | 10 | 10 | 65 | No |  |  | 150000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | BMSI-050 | Complete BMS Panel Power Connections | Controls, BMS & DCIM | BMS Infrastructure | Not Started | 2026-12-24 08:00 | 2026-12-25 16:00 |  |  | 2 | 2 | 16 | No |  |  | 60000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | BMSI-060 | Inspect BMS Infrastructure Installation | Controls, BMS & DCIM | BMS Infrastructure | Not Started | 2026-12-26 08:00 | 2026-12-28 16:00 |  |  | 2 | 2 | 16 | No |  |  | 96000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | BMSI-070 | BMS Infrastructure Ready for Pre-Commissioning | Controls, BMS & DCIM | BMS Infrastructure | Not Started | 2026-12-28 16:00 | 2026-12-28 16:00 |  |  | 0 | 0 | 16 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | EMC-010 | Install Electrical Monitoring Devices | Controls, BMS & DCIM | Electrical Monitoring & Controls | Not Started | 2026-11-16 08:00 | 2026-11-20 16:00 |  |  | 5 | 5 | 50 | No |  |  | 16000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | EMC-020 | Install Power Metering Devices | Controls, BMS & DCIM | Electrical Monitoring & Controls | Not Started | 2026-12-24 08:00 | 2026-12-29 16:00 |  |  | 5 | 5 | 17 | No |  |  | 126000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | EMC-030 | Install Switchgear Monitoring Interfaces | Controls, BMS & DCIM | Electrical Monitoring & Controls | Not Started | 2026-11-16 08:00 | 2026-11-21 16:00 |  |  | 6 | 6 | 49 | No |  |  | 17000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | EMC-040 | Install UPS Monitoring Interfaces | Controls, BMS & DCIM | Electrical Monitoring & Controls | Not Started | 2027-01-01 08:00 | 2027-01-06 16:00 |  |  | 5 | 5 | 10 | No |  |  | 16000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | EMC-050 | Install Generator Monitoring Interfaces | Controls, BMS & DCIM | Electrical Monitoring & Controls | Not Started | 2026-12-12 08:00 | 2026-12-18 16:00 |  |  | 6 | 6 | 26 | No |  |  | 17000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | EMC-060 | Complete Monitoring Communication Connections | Controls, BMS & DCIM | Electrical Monitoring & Controls | Not Started | 2027-01-07 08:00 | 2027-01-08 16:00 |  |  | 2 | 2 | 10 | No |  |  | 12000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | EMC-070 | Electrical Monitoring Ready for Pre-Commissioning | Controls, BMS & DCIM | Electrical Monitoring & Controls | Not Started | 2027-01-08 16:00 | 2027-01-08 16:00 |  |  | 0 | 0 | 10 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | MMC-010 | Install Mechanical Monitoring Interfaces | Controls, BMS & DCIM | Mechanical Monitoring & Controls | Not Started | 2026-12-08 08:00 | 2026-12-11 16:00 |  |  | 4 | 4 | 32 | No |  |  | 15000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | MMC-020 | Connect Chiller Monitoring Points | Controls, BMS & DCIM | Mechanical Monitoring & Controls | Not Started | 2026-09-23 08:00 | 2026-09-28 16:00 |  |  | 5 | 5 | 96 | No |  |  | 16000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | MMC-030 | Connect Pump Monitoring Points | Controls, BMS & DCIM | Mechanical Monitoring & Controls | Not Started | 2026-09-16 08:00 | 2026-09-21 16:00 |  |  | 5 | 5 | 102 | No |  |  | 16000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | MMC-040 | Connect CRAH CRAC Monitoring Points | Controls, BMS & DCIM | Mechanical Monitoring & Controls | Not Started | 2026-11-05 08:00 | 2026-11-10 16:00 |  |  | 5 | 5 | 59 | No |  |  | 16000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | MMC-050 | Connect Cooling Sensors to BMS | Controls, BMS & DCIM | Mechanical Monitoring & Controls | Not Started | 2026-11-17 08:00 | 2026-11-21 16:00 |  |  | 5 | 5 | 49 | No |  |  | 79000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | MMC-060 | Verify Mechanical Control Wiring | Controls, BMS & DCIM | Mechanical Monitoring & Controls | Not Started | 2026-12-12 08:00 | 2026-12-14 16:00 |  |  | 2 | 2 | 32 | No |  |  | 60000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | MMC-070 | Mechanical Monitoring Ready for Pre-Commissioning | Controls, BMS & DCIM | Mechanical Monitoring & Controls | Not Started | 2026-12-14 16:00 | 2026-12-14 16:00 |  |  | 0 | 0 | 32 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | DCIM-010 | Install DCIM Server Infrastructure | Controls, BMS & DCIM | DCIM Platform | Not Started | 2026-11-12 08:00 | 2026-11-17 16:00 |  |  | 5 | 5 | 44 | No |  |  | 126000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | DCIM-020 | Configure DCIM Platform | Controls, BMS & DCIM | DCIM Platform | Not Started | 2026-11-18 08:00 | 2026-11-26 16:00 |  |  | 8 | 8 | 44 | No |  |  | 91000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | DCIM-030 | Configure Data Hall Asset Database | Controls, BMS & DCIM | DCIM Platform | Not Started | 2026-11-27 08:00 | 2026-12-05 16:00 |  |  | 8 | 8 | 44 | No |  |  | 91000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | DCIM-040 | Configure Power Monitoring Integration | Controls, BMS & DCIM | DCIM Platform | Not Started | 2027-01-09 08:00 | 2027-01-14 16:00 |  |  | 5 | 5 | 10 | No |  |  | 16000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | DCIM-050 | Configure Cooling Monitoring Integration | Controls, BMS & DCIM | DCIM Platform | Not Started | 2026-12-15 08:00 | 2026-12-19 16:00 |  |  | 5 | 5 | 32 | No |  |  | 16000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | DCIM-060 | Configure Alarm and Event Management | Controls, BMS & DCIM | DCIM Platform | Not Started | 2026-11-27 08:00 | 2026-12-02 16:00 |  |  | 5 | 5 | 47 | No |  |  | 79000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | DCIM-070 | DCIM Platform Ready for Functional Testing | Controls, BMS & DCIM | DCIM Platform | Not Started | 2027-01-14 16:00 | 2027-01-14 16:00 |  |  | 0 | 0 | 10 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | SFD-010 | Install Environmental Sensors | Controls, BMS & DCIM | Sensors & Field Devices | Not Started | 2026-10-10 08:00 | 2026-10-15 16:00 |  |  | 5 | 5 | 79 | No |  |  | 126000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | SFD-020 | Install Temperature and Humidity Sensors | Controls, BMS & DCIM | Sensors & Field Devices | Not Started | 2026-10-12 08:00 | 2026-10-16 16:00 |  |  | 5 | 5 | 79 | No |  |  | 126000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | SFD-030 | Install Differential Pressure Sensors | Controls, BMS & DCIM | Sensors & Field Devices | Not Started | 2026-10-12 08:00 | 2026-10-16 16:00 |  |  | 5 | 5 | 79 | No |  |  | 126000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | SFD-040 | Install Leak Detection Sensors | Controls, BMS & DCIM | Sensors & Field Devices | Not Started | 2026-10-12 08:00 | 2026-10-16 16:00 |  |  | 5 | 5 | 79 | No |  |  | 126000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | SFD-050 | Install Energy Metering Devices | Controls, BMS & DCIM | Sensors & Field Devices | Not Started | 2026-10-12 08:00 | 2026-10-16 16:00 |  |  | 5 | 5 | 79 | No |  |  | 126000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | SFD-060 | Terminate Sensor and Field Device Cabling | Controls, BMS & DCIM | Sensors & Field Devices | Not Started | 2026-11-12 08:00 | 2026-11-20 16:00 |  |  | 8 | 8 | 57 | No |  |  | 145000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | SFD-070 | Sensors and Field Devices Ready for Testing | Controls, BMS & DCIM | Sensors & Field Devices | Not Started | 2026-11-20 16:00 | 2026-11-20 16:00 |  |  | 0 | 0 | 57 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | CNW-010 | Install Controls Network Switches | Controls, BMS & DCIM | Controls Network | Not Started | 2026-10-26 08:00 | 2026-10-30 16:00 |  |  | 5 | 5 | 44 | No |  |  | 126000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CNW-020 | Install Controls Network Cabling | Controls, BMS & DCIM | Controls Network | Not Started | 2026-10-19 08:00 | 2026-10-27 16:00 |  |  | 8 | 8 | 47 | No |  |  | 145000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CNW-030 | Configure Controls Network | Controls, BMS & DCIM | Controls Network | Not Started | 2026-10-31 08:00 | 2026-11-04 16:00 |  |  | 4 | 4 | 44 | No |  |  | 74000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CNW-040 | Configure Network Segmentation | Controls, BMS & DCIM | Controls Network | Not Started | 2026-11-05 08:00 | 2026-11-07 16:00 |  |  | 3 | 3 | 44 | No |  |  | 68000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CNW-050 | Perform Controls Network Connectivity Testing | Controls, BMS & DCIM | Controls Network | Not Started | 2026-11-09 08:00 | 2026-11-11 16:00 |  |  | 3 | 3 | 44 | No |  |  | 81000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CNW-060 | Controls Network Ready | Controls, BMS & DCIM | Controls Network | Not Started | 2026-11-11 16:00 | 2026-11-11 16:00 |  |  | 0 | 0 | 44 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | CSI-010 | Integrate BMS with Electrical Systems | Controls, BMS & DCIM | System Integration | Not Started | 2027-01-09 08:00 | 2027-01-13 16:00 |  |  | 4 | 4 | 33 | No |  |  | 74000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CSI-020 | Integrate BMS with Mechanical Systems | Controls, BMS & DCIM | System Integration | Not Started | 2026-12-29 08:00 | 2027-01-01 16:00 |  |  | 4 | 4 | 43 | No |  |  | 74000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CSI-030 | Integrate BMS with Fire Alarm System | Controls, BMS & DCIM | System Integration | Not Started | 2027-01-08 08:00 | 2027-01-11 16:00 |  |  | 3 | 3 | 35 | No |  |  | 68000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CSI-040 | Integrate BMS with UPS and Generator Systems | Controls, BMS & DCIM | System Integration | Not Started | 2027-01-09 08:00 | 2027-01-13 16:00 |  |  | 4 | 4 | 33 | No |  |  | 74000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CSI-050 | Integrate DCIM with Power Monitoring | Controls, BMS & DCIM | System Integration | Not Started | 2027-01-15 08:00 | 2027-01-19 16:00 |  |  | 4 | 4 | 28 | No |  |  | 15000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CSI-060 | Integrate DCIM with Cooling Monitoring | Controls, BMS & DCIM | System Integration | Not Started | 2027-01-15 08:00 | 2027-01-19 16:00 |  |  | 4 | 4 | 28 | No |  |  | 15000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CSI-070 | Verify System Integration Interfaces | Controls, BMS & DCIM | System Integration | Not Started | 2027-01-20 08:00 | 2027-01-21 16:00 |  |  | 2 | 2 | 28 | No |  |  | 60000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CSI-080 | Controls Integration Ready for IST | Controls, BMS & DCIM | System Integration | Not Started | 2027-01-21 16:00 | 2027-01-21 16:00 |  |  | 0 | 0 | 28 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | GCP-010 | Develop BMS Control Logic | Controls, BMS & DCIM | Graphics, Configuration & Programming | Not Started | 2026-08-07 08:00 | 2026-08-15 16:00 |  |  | 8 | 8 | 130 | No |  |  | 91000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | GCP-020 | Configure BMS Alarm Logic | Controls, BMS & DCIM | Graphics, Configuration & Programming | Not Started | 2026-08-10 08:00 | 2026-08-14 16:00 |  |  | 5 | 5 | 133 | No |  |  | 79000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | GCP-030 | Develop BMS Graphics | Controls, BMS & DCIM | Graphics, Configuration & Programming | Not Started | 2026-08-10 08:00 | 2026-08-18 16:00 |  |  | 8 | 8 | 130 | No |  |  | 91000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | GCP-040 | Configure DCIM Dashboards | Controls, BMS & DCIM | Graphics, Configuration & Programming | Not Started | 2026-08-10 08:00 | 2026-08-14 16:00 |  |  | 5 | 5 | 133 | No |  |  | 79000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | GCP-050 | Configure Trend Logging and Reporting | Controls, BMS & DCIM | Graphics, Configuration & Programming | Not Started | 2026-08-10 08:00 | 2026-08-13 16:00 |  |  | 4 | 4 | 134 | No |  |  | 15000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | GCP-060 | Complete Controls Software Configuration | Controls, BMS & DCIM | Graphics, Configuration & Programming | Not Started | 2026-08-19 08:00 | 2026-08-21 16:00 |  |  | 3 | 3 | 130 | No |  |  | 68000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | GCP-070 | BMS and DCIM Configuration Complete | Controls, BMS & DCIM | Graphics, Configuration & Programming | Not Started | 2026-08-21 16:00 | 2026-08-21 16:00 |  |  | 0 | 0 | 130 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | UTL-010 | Submit Utility Connection Application | Utility Connection & Energization | Utility Coordination & Approvals | Not Started | 2026-03-20 08:00 | 2026-03-25 16:00 |  |  | 5 | 5 | 177 | No |  |  | 30000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | UTL-020 | Coordinate Utility Technical Requirements | Utility Connection & Energization | Utility Coordination & Approvals | Not Started | 2026-03-26 08:00 | 2026-04-06 16:00 |  |  | 10 | 10 | 177 | No |  |  | 25000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | UTL-030 | Submit Utility Protection Study | Utility Connection & Energization | Utility Coordination & Approvals | Not Started | 2026-03-26 08:00 | 2026-04-06 16:00 |  |  | 10 | 10 | 177 | No |  |  | 37000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | UTL-040 | Resolve Utility Review Comments | Utility Connection & Energization | Utility Coordination & Approvals | Not Started | 2026-04-07 08:00 | 2026-04-17 16:00 |  |  | 10 | 10 | 177 | No |  |  | 25000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | UTL-050 | Obtain Utility Connection Approval | Utility Connection & Energization | Utility Coordination & Approvals | Not Started | 2026-04-17 16:00 | 2026-04-17 16:00 |  |  | 0 | 0 | 177 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | UCMV-010 | Complete Incoming Utility MV Infrastructure | Utility Connection & Energization | Incoming Utility / MV Connection | Not Started | 2026-04-18 08:00 | 2026-05-05 16:00 |  |  | 15 | 15 | 177 | No |  |  | 141000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | UCMV-020 | Install Utility Metering Equipment | Utility Connection & Energization | Incoming Utility / MV Connection | Not Started | 2026-04-22 08:00 | 2026-04-27 16:00 |  |  | 5 | 5 | 189 | No |  |  | 166000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | UCMV-030 | Complete Utility MV Cable Connections | Utility Connection & Energization | Incoming Utility / MV Connection | Not Started | 2026-05-06 08:00 | 2026-05-11 16:00 |  |  | 5 | 5 | 177 | No |  |  | 162000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | UCMV-040 | Complete Utility Protection Interfaces | Utility Connection & Energization | Incoming Utility / MV Connection | Not Started | 2026-04-24 08:00 | 2026-04-29 16:00 |  |  | 5 | 5 | 187 | No |  |  | 101000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | UCMV-050 | Incoming Utility Connection Ready | Utility Connection & Energization | Incoming Utility / MV Connection | Not Started | 2026-05-11 16:00 | 2026-05-11 16:00 |  |  | 0 | 0 | 177 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | SUB-010 | Inspect Utility Substation Installation | Utility Connection & Energization | Utility Substation Readiness | Not Started | 2026-05-12 08:00 | 2026-05-13 16:00 |  |  | 2 | 2 | 177 | No |  |  | 123000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | SUB-020 | Complete Substation Protection Testing | Utility Connection & Energization | Utility Substation Readiness | Not Started | 2026-05-14 08:00 | 2026-05-16 16:00 |  |  | 3 | 3 | 177 | No |  |  | 104000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | SUB-030 | Complete Substation Metering Testing | Utility Connection & Energization | Utility Substation Readiness | Not Started | 2026-05-14 08:00 | 2026-05-16 16:00 |  |  | 3 | 3 | 177 | No |  |  | 104000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | SUB-040 | Close Utility Substation Punch List | Utility Connection & Energization | Utility Substation Readiness | Not Started | 2026-05-18 08:00 | 2026-05-22 16:00 |  |  | 5 | 5 | 177 | No |  |  | 101000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | SUB-050 | Utility Substation Ready for Energization | Utility Connection & Energization | Utility Substation Readiness | Not Started | 2026-05-22 16:00 | 2026-05-22 16:00 |  |  | 0 | 0 | 177 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | MVE-010 | Complete MV Pre-Energization Checks | Utility Connection & Energization | MV System Energization | Not Started | 2026-11-16 08:00 | 2026-11-17 16:00 |  |  | 2 | 2 | 26 | No |  |  | 92000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | MVE-020 | Verify MV Protection Settings | Utility Connection & Energization | MV System Energization | Not Started | 2026-11-18 08:00 | 2026-11-19 16:00 |  |  | 2 | 2 | 26 | No |  |  | 77000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | MVE-030 | Obtain MV Energization Permit | Utility Connection & Energization | MV System Energization | Not Started | 2026-11-20 08:00 | 2026-11-21 16:00 |  |  | 2 | 2 | 26 | No |  |  | 92000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | MVE-040 | Energize Incoming MV System | Utility Connection & Energization | MV System Energization | Not Started | 2026-11-23 08:00 | 2026-11-23 16:00 |  |  | 1 | 1 | 26 | No |  |  | 75000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | MVE-050 | Verify MV System Operation | Utility Connection & Energization | MV System Energization | Not Started | 2026-11-24 08:00 | 2026-11-25 16:00 |  |  | 2 | 2 | 26 | No |  |  | 77000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | MVE-060 | MV System Energized | Utility Connection & Energization | MV System Energization | Not Started | 2026-11-25 16:00 | 2026-11-25 16:00 |  |  | 0 | 0 | 26 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | TRE-010 | Complete Transformer Pre-Energization Checks | Utility Connection & Energization | LV System Energization | Not Started | 2026-12-26 08:00 | 2026-12-26 16:00 |  |  | 1 | 1 | 0 | Yes | 10 | 4 | 75000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | TRE-020 | Verify Transformer Protection and Controls | Utility Connection & Energization | LV System Energization | Not Started | 2026-12-28 08:00 | 2026-12-29 16:00 |  |  | 2 | 2 | 0 | Yes | 10 | 5 | 77000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | TRE-030 | Energize Transformers | Utility Connection & Energization | LV System Energization | Not Started | 2026-12-30 08:00 | 2026-12-30 16:00 |  |  | 1 | 1 | 0 | Yes | 10 | 6 | 75000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | TRE-040 | Perform Transformer Operational Checks | Utility Connection & Energization | LV System Energization | Not Started | 2026-12-31 08:00 | 2027-01-01 16:00 |  |  | 2 | 2 | 0 | Yes | 10 | 7 | 77000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | TRE-050 | Transformers Energized | Utility Connection & Energization | LV System Energization | Not Started | 2027-01-01 16:00 | 2027-01-01 16:00 |  |  | 0 | 0 | 0 | Yes | 10 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | LVE-010 | Complete LV Pre-Energization Checks | Utility Connection & Energization | UPS & Critical Power Energization | Not Started | 2027-01-02 08:00 | 2027-01-02 16:00 |  |  | 1 | 1 | 0 | Yes | 10 | 9 | 75000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | LVE-020 | Verify LV Protection Settings | Utility Connection & Energization | UPS & Critical Power Energization | Not Started | 2027-01-04 08:00 | 2027-01-05 16:00 |  |  | 2 | 2 | 0 | Yes | 10 | 10 | 77000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | LVE-030 | Energize Main LV Switchgear | Utility Connection & Energization | UPS & Critical Power Energization | Not Started | 2027-01-06 08:00 | 2027-01-06 16:00 |  |  | 1 | 1 | 0 | Yes | 10 | 11 | 75000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | LVE-040 | Energize LV Distribution Boards | Utility Connection & Energization | UPS & Critical Power Energization | Not Started | 2027-01-07 08:00 | 2027-01-09 16:00 |  |  | 3 | 3 | 0 | Yes | 10 | 12 | 104000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | LVE-050 | Verify LV System Operation | Utility Connection & Energization | UPS & Critical Power Energization | Not Started | 2027-01-11 08:00 | 2027-01-12 16:00 |  |  | 2 | 2 | 0 | Yes | 10 | 13 | 77000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | LVE-060 | LV System Energized | Utility Connection & Energization | UPS & Critical Power Energization | Not Started | 2027-01-12 16:00 | 2027-01-12 16:00 |  |  | 0 | 0 | 0 | Yes | 10 | 14 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | UPE-010 | Complete UPS Pre-Energization Checks | Utility Connection & Energization | Generator & Backup Power Readiness | Not Started | 2027-01-13 08:00 | 2027-01-13 16:00 |  |  | 1 | 1 | 0 | Yes | 10 | 15 | 75000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | UPE-020 | Energize UPS Input Supply | Utility Connection & Energization | Generator & Backup Power Readiness | Not Started | 2027-01-14 08:00 | 2027-01-14 16:00 |  |  | 1 | 1 | 0 | Yes | 10 | 16 | 75000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | UPE-030 | Start and Configure UPS Systems | Utility Connection & Energization | Generator & Backup Power Readiness | Not Started | 2027-01-15 08:00 | 2027-01-18 16:00 |  |  | 3 | 3 | 0 | Yes | 10 | 17 | 87000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | UPE-040 | Energize UPS Output Distribution | Utility Connection & Energization | Generator & Backup Power Readiness | Not Started | 2027-01-19 08:00 | 2027-01-21 16:00 |  |  | 3 | 3 | 0 | Yes | 10 | 18 | 104000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | UPE-050 | Verify Battery System Operation | Utility Connection & Energization | Generator & Backup Power Readiness | Not Started | 2027-01-22 08:00 | 2027-01-23 16:00 |  |  | 2 | 2 | 0 | Yes | 10 | 19 | 77000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | UPE-060 | Critical Power System Energized | Utility Connection & Energization | Generator & Backup Power Readiness | Not Started | 2027-01-23 16:00 | 2027-01-23 16:00 |  |  | 0 | 0 | 0 | Yes | 10 | 20 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | GBP-010 | Complete Generator Pre-Start Checks | Utility Connection & Energization | Data Hall Power-On | Not Started | 2026-12-31 08:00 | 2026-12-31 16:00 |  |  | 1 | 1 | 23 | No |  |  | 63000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | GBP-020 | Complete Generator Fuel System Readiness Checks | Utility Connection & Energization | Data Hall Power-On | Not Started | 2026-12-31 08:00 | 2026-12-31 16:00 |  |  | 1 | 1 | 23 | No |  |  | 63000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | GBP-030 | Start Standby Generators | Utility Connection & Energization | Data Hall Power-On | Not Started | 2027-01-01 08:00 | 2027-01-02 16:00 |  |  | 2 | 2 | 23 | No |  |  | 77000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | GBP-040 | Verify Generator Controls and Protection | Utility Connection & Energization | Data Hall Power-On | Not Started | 2027-01-04 08:00 | 2027-01-05 16:00 |  |  | 2 | 2 | 23 | No |  |  | 77000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | GBP-050 | Verify Generator Automatic Transfer Sequence | Utility Connection & Energization | Data Hall Power-On | Not Started | 2027-01-13 08:00 | 2027-01-14 16:00 |  |  | 2 | 2 | 17 | No |  |  | 77000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | GBP-060 | Backup Power System Ready | Utility Connection & Energization | Data Hall Power-On | Not Started | 2027-01-14 16:00 | 2027-01-14 16:00 |  |  | 0 | 0 | 17 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | DPO-010 | Verify Data Hall Electrical Installation Readiness | Utility Connection & Energization | Data Hall Power-On | Not Started | 2027-01-25 08:00 | 2027-01-26 16:00 |  |  | 2 | 2 | 0 | Yes | 1 | 24 | 123000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | DPO-020 | Verify UPS and PDU Availability | Utility Connection & Energization | Data Hall Power-On | Not Started | 2027-01-25 08:00 | 2027-01-26 16:00 |  |  | 2 | 2 | 0 | Yes | 10 | 21 | 77000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | DPO-030 | Verify Data Hall Earthing and Bonding | Utility Connection & Energization | Data Hall Power-On | Not Started | 2026-12-30 08:00 | 2026-12-31 16:00 |  |  | 2 | 2 | 22 | No |  |  | 77000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | DPO-040 | Energize Data Hall Busway Distribution | Utility Connection & Energization | Data Hall Power-On | Not Started | 2027-01-27 08:00 | 2027-01-28 16:00 |  |  | 2 | 2 | 0 | Yes | 1 | 25 | 123000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | DPO-050 | Energize Data Hall Power Distribution | Utility Connection & Energization | Data Hall Power-On | Not Started | 2027-01-29 08:00 | 2027-02-01 16:00 |  |  | 3 | 3 | 0 | Yes | 1 | 26 | 104000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | DPO-060 | Verify Data Hall Power Availability | Utility Connection & Energization | Data Hall Power-On | Not Started | 2027-02-02 08:00 | 2027-02-03 16:00 |  |  | 2 | 2 | 0 | Yes | 1 | 27 | 77000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | DPO-070 | Data Hall Power-On Complete | Utility Connection & Energization | Data Hall Power-On | Not Started | 2027-02-03 16:00 | 2027-02-03 16:00 |  |  | 0 | 0 | 0 | Yes | 1 | 28 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | CXP-010 | Develop Commissioning Management Plan | Testing & Commissioning | Commissioning Management & Planning | Completed | 2026-01-06 08:00 | 2026-01-10 16:00 | 2026-01-06 08:00 | 2026-01-10 16:00 | 5 | 0 |  | No |  |  | 41000 | 41000 | 41000 | 41289.5817 | -289.5817 | 0 | 0.99299 | 1 | Available | Available | Available | Available
Update 02 | 2026-02-28 | CXP-020 | Develop Commissioning Schedule | Testing & Commissioning | Commissioning Management & Planning | Completed | 2026-01-12 08:00 | 2026-01-16 16:00 | 2026-01-12 08:00 | 2026-01-16 16:00 | 5 | 0 |  | No |  |  | 41000 | 41000 | 41000 | 42163.1382 | -1163.1382 | 0 | 0.97241 | 1 | Available | Available | Available | Available
Update 02 | 2026-02-28 | CXP-030 | Develop Commissioning Procedures | Testing & Commissioning | Commissioning Management & Planning | Completed | 2026-01-12 08:00 | 2026-01-16 16:00 | 2026-01-12 08:00 | 2026-01-16 16:00 | 5 | 0 |  | No |  |  | 41000 | 41000 | 41000 | 42453.8369 | -1453.8369 | 0 | 0.96575 | 1 | Available | Available | Available | Available
Update 02 | 2026-02-28 | CXP-040 | Develop Systems Completion Matrix | Testing & Commissioning | Commissioning Management & Planning | Completed | 2026-01-12 08:00 | 2026-01-16 16:00 | 2026-01-12 08:00 | 2026-01-16 16:00 | 5 | 0 |  | No |  |  | 34000 | 34000 | 34000 | 34107.821 | -107.821 | 0 | 0.99684 | 1 | Available | Available | Available | Available
Update 02 | 2026-02-28 | CXP-050 | Establish Commissioning Documentation Register | Testing & Commissioning | Commissioning Management & Planning | Completed | 2026-01-12 08:00 | 2026-01-22 16:00 | 2026-01-12 08:00 | 2026-01-22 16:00 | 10 | 0 |  | No |  |  | 8000 | 8000 | 8000 | 8276.2507 | -276.2507 | 0 | 0.96662 | 1 | Available | Available | Available | Available
Update 02 | 2026-02-28 | CXP-060 | Commissioning Plan Approved | Testing & Commissioning | Commissioning Management & Planning | Completed | 2026-01-22 16:00 | 2026-01-22 16:00 | 2026-01-22 16:00 | 2026-01-22 16:00 | 0 | 0 |  | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | PRE-010 | Complete Electrical Pre-Commissioning Inspections | Testing & Commissioning | Pre-Commissioning & Inspections | Not Started | 2027-01-25 08:00 | 2027-01-26 16:00 |  |  | 2 | 2 | 2 | No |  |  | 31000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | PRE-020 | Complete Mechanical Pre-Commissioning Inspections | Testing & Commissioning | Pre-Commissioning & Inspections | Not Started | 2026-12-08 08:00 | 2026-12-09 16:00 |  |  | 2 | 2 | 43 | No |  |  | 31000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | PRE-030 | Complete Fire System Pre-Commissioning Inspections | Testing & Commissioning | Pre-Commissioning & Inspections | Not Started | 2027-01-08 08:00 | 2027-01-09 16:00 |  |  | 2 | 2 | 16 | No |  |  | 31000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | PRE-040 | Complete BMS and Controls Pre-Commissioning Inspections | Testing & Commissioning | Pre-Commissioning & Inspections | Not Started | 2027-01-15 08:00 | 2027-01-16 16:00 |  |  | 2 | 2 | 10 | No |  |  | 31000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | PRE-050 | Complete Pre-Commissioning Punch List | Testing & Commissioning | Pre-Commissioning & Inspections | Not Started | 2027-01-27 08:00 | 2027-01-29 16:00 |  |  | 3 | 3 | 2 | No |  |  | 35000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | PRE-060 | Systems Ready for Functional Commissioning | Testing & Commissioning | Pre-Commissioning & Inspections | Not Started | 2027-01-29 16:00 | 2027-01-29 16:00 |  |  | 0 | 0 | 2 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | ELC-CX-010 | Commission MV Switchgear | Testing & Commissioning | Electrical Systems Commissioning | Not Started | 2027-02-04 08:00 | 2027-02-09 16:00 |  |  | 5 | 5 | 5 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | ELC-CX-020 | Commission Transformers | Testing & Commissioning | Electrical Systems Commissioning | Not Started | 2027-01-30 08:00 | 2027-02-04 16:00 |  |  | 5 | 5 | 9 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | ELC-CX-030 | Commission LV Switchgear | Testing & Commissioning | Electrical Systems Commissioning | Not Started | 2027-01-30 08:00 | 2027-02-04 16:00 |  |  | 5 | 5 | 9 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | ELC-CX-040 | Commission UPS Systems | Testing & Commissioning | Electrical Systems Commissioning | Not Started | 2027-01-30 08:00 | 2027-02-04 16:00 |  |  | 5 | 5 | 9 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | ELC-CX-050 | Commission Battery Systems | Testing & Commissioning | Electrical Systems Commissioning | Not Started | 2027-01-30 08:00 | 2027-02-04 16:00 |  |  | 5 | 5 | 9 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | ELC-CX-060 | Commission Standby Generators | Testing & Commissioning | Electrical Systems Commissioning | Not Started | 2027-01-30 08:00 | 2027-02-04 16:00 |  |  | 5 | 5 | 9 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | ELC-CX-070 | Commission PDU and Busway Distribution | Testing & Commissioning | Electrical Systems Commissioning | Not Started | 2027-02-04 08:00 | 2027-02-15 16:00 |  |  | 10 | 10 | 0 | Yes | 8 | 1 | 62000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | ELC-CX-080 | Electrical Systems Functional Testing Complete | Testing & Commissioning | Electrical Systems Commissioning | Not Started | 2027-02-15 16:00 | 2027-02-15 16:00 |  |  | 0 | 0 | 0 | Yes | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | MEC-CX-010 | Commission Chillers and Heat Rejection Equipment | Testing & Commissioning | Mechanical & Cooling Commissioning | Not Started | 2027-01-30 08:00 | 2027-02-04 16:00 |  |  | 5 | 5 | 2 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | MEC-CX-020 | Commission Cooling Pumps | Testing & Commissioning | Mechanical & Cooling Commissioning | Not Started | 2027-01-30 08:00 | 2027-02-04 16:00 |  |  | 5 | 5 | 2 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | MEC-CX-030 | Commission Chilled Water System | Testing & Commissioning | Mechanical & Cooling Commissioning | Not Started | 2027-01-30 08:00 | 2027-02-04 16:00 |  |  | 5 | 5 | 2 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | MEC-CX-040 | Commission CRAH CRAC Systems | Testing & Commissioning | Mechanical & Cooling Commissioning | Not Started | 2027-01-30 08:00 | 2027-02-04 16:00 |  |  | 5 | 5 | 2 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | MEC-CX-050 | Perform Air and Water Balancing | Testing & Commissioning | Mechanical & Cooling Commissioning | Not Started | 2027-02-05 08:00 | 2027-02-10 16:00 |  |  | 5 | 5 | 2 | No |  |  | 34000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | MEC-CX-060 | Verify Cooling System Controls | Testing & Commissioning | Mechanical & Cooling Commissioning | Not Started | 2027-02-11 08:00 | 2027-02-12 16:00 |  |  | 2 | 2 | 2 | No |  |  | 26000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | MEC-CX-070 | Mechanical Systems Functional Testing Complete | Testing & Commissioning | Mechanical & Cooling Commissioning | Not Started | 2027-02-12 16:00 | 2027-02-12 16:00 |  |  | 0 | 0 | 2 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | FLS-CX-010 | Commission Fire Detection and Alarm System | Testing & Commissioning | Fire & Life Safety Commissioning | Not Started | 2027-01-30 08:00 | 2027-02-04 16:00 |  |  | 5 | 5 | 10 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | FLS-CX-020 | Commission Sprinkler System | Testing & Commissioning | Fire & Life Safety Commissioning | Not Started | 2027-01-30 08:00 | 2027-02-04 16:00 |  |  | 5 | 5 | 10 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | FLS-CX-030 | Commission Clean Agent Fire Suppression | Testing & Commissioning | Fire & Life Safety Commissioning | Not Started | 2027-01-30 08:00 | 2027-02-04 16:00 |  |  | 5 | 5 | 10 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | FLS-CX-040 | Commission Fire Pumps | Testing & Commissioning | Fire & Life Safety Commissioning | Not Started | 2027-01-30 08:00 | 2027-02-04 16:00 |  |  | 5 | 5 | 10 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | FLS-CX-050 | Commission VESDA System | Testing & Commissioning | Fire & Life Safety Commissioning | Not Started | 2027-01-30 08:00 | 2027-02-04 16:00 |  |  | 5 | 5 | 10 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | FLS-CX-060 | Verify Fire Cause and Effect Matrix | Testing & Commissioning | Fire & Life Safety Commissioning | Not Started | 2027-02-05 08:00 | 2027-02-06 16:00 |  |  | 2 | 2 | 10 | No |  |  | 26000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | FLS-CX-070 | Fire and Life Safety Commissioning Complete | Testing & Commissioning | Fire & Life Safety Commissioning | Not Started | 2027-02-06 16:00 | 2027-02-06 16:00 |  |  | 0 | 0 | 10 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | BMS-CX-010 | Commission BMS Infrastructure | Testing & Commissioning | BMS & DCIM Commissioning | Not Started | 2027-01-30 08:00 | 2027-02-04 16:00 |  |  | 5 | 5 | 5 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | BMS-CX-020 | Verify BMS Field Points | Testing & Commissioning | BMS & DCIM Commissioning | Not Started | 2027-02-05 08:00 | 2027-02-06 16:00 |  |  | 2 | 2 | 5 | No |  |  | 26000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | BMS-CX-030 | Commission BMS Graphics and Alarms | Testing & Commissioning | BMS & DCIM Commissioning | Not Started | 2027-02-08 08:00 | 2027-02-12 16:00 |  |  | 5 | 5 | 5 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | BMS-CX-040 | Commission DCIM Platform | Testing & Commissioning | BMS & DCIM Commissioning | Not Started | 2027-01-30 08:00 | 2027-02-04 16:00 |  |  | 5 | 5 | 10 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | BMS-CX-050 | Verify DCIM Power Monitoring | Testing & Commissioning | BMS & DCIM Commissioning | Not Started | 2027-02-16 08:00 | 2027-02-17 16:00 |  |  | 2 | 2 | 1 | No |  |  | 5000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | BMS-CX-060 | Verify DCIM Cooling Monitoring | Testing & Commissioning | BMS & DCIM Commissioning | Not Started | 2027-02-13 08:00 | 2027-02-15 16:00 |  |  | 2 | 2 | 3 | No |  |  | 5000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | BMS-CX-070 | BMS and DCIM Commissioning Complete | Testing & Commissioning | BMS & DCIM Commissioning | Not Started | 2027-02-17 16:00 | 2027-02-17 16:00 |  |  | 0 | 0 | 1 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | INT-CX-010 | Verify Electrical to BMS Integration | Testing & Commissioning | Controls & Systems Integration | Not Started | 2027-02-18 08:00 | 2027-02-19 16:00 |  |  | 2 | 2 | 1 | No |  |  | 26000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | INT-CX-020 | Verify Mechanical to BMS Integration | Testing & Commissioning | Controls & Systems Integration | Not Started | 2027-02-18 08:00 | 2027-02-19 16:00 |  |  | 2 | 2 | 1 | No |  |  | 26000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | INT-CX-030 | Verify Fire System Integration | Testing & Commissioning | Controls & Systems Integration | Not Started | 2027-02-18 08:00 | 2027-02-19 16:00 |  |  | 2 | 2 | 1 | No |  |  | 26000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | INT-CX-040 | Verify UPS and Generator Controls Integration | Testing & Commissioning | Controls & Systems Integration | Not Started | 2027-02-18 08:00 | 2027-02-19 16:00 |  |  | 2 | 2 | 1 | No |  |  | 26000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | INT-CX-050 | Complete Integrated Controls Testing | Testing & Commissioning | Controls & Systems Integration | Not Started | 2027-02-20 08:00 | 2027-02-22 16:00 |  |  | 2 | 2 | 1 | No |  |  | 31000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | INT-CX-060 | Systems Integration Complete | Testing & Commissioning | Controls & Systems Integration | Not Started | 2027-02-22 16:00 | 2027-02-22 16:00 |  |  | 0 | 0 | 1 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | IST-010 | Prepare Integrated Systems Test Scripts | Testing & Commissioning | Integrated Systems Testing (IST) | In Progress | 2026-01-23 08:00 | 2026-02-03 16:00 | 2026-01-23 08:00 |  | 10 | 0.30783 | 328 | No |  |  | 50000 | 50000 | 48460.8402 | 50238.2909 | -1777.4507 | -1539.1598 | 0.96462 | 0.96922 | Available | Available | Available | Available
Update 02 | 2026-02-28 | IST-020 | Conduct Utility Power Failure Scenario | Testing & Commissioning | Integrated Systems Testing (IST) | Not Started | 2027-02-24 08:00 | 2027-03-01 16:00 |  |  | 5 | 5 | 0 | Yes | 1 | 34 | 34000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | IST-030 | Conduct Generator Transfer Scenario | Testing & Commissioning | Integrated Systems Testing (IST) | Not Started | 2027-02-24 08:00 | 2027-03-01 16:00 |  |  | 5 | 5 | 0 | Yes | 4 | 1 | 34000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | IST-040 | Conduct UPS Battery Ride-Through Scenario | Testing & Commissioning | Integrated Systems Testing (IST) | Not Started | 2027-02-24 08:00 | 2027-03-01 16:00 |  |  | 5 | 5 | 0 | Yes | 5 | 1 | 34000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | IST-050 | Conduct Cooling Failure Scenario | Testing & Commissioning | Integrated Systems Testing (IST) | Not Started | 2027-02-24 08:00 | 2027-03-01 16:00 |  |  | 5 | 5 | 0 | Yes | 6 | 1 | 34000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | IST-060 | Conduct Fire Alarm Integration Scenario | Testing & Commissioning | Integrated Systems Testing (IST) | Not Started | 2027-02-24 08:00 | 2027-03-01 16:00 |  |  | 5 | 5 | 0 | Yes | 7 | 1 | 34000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | IST-070 | Conduct BMS DCIM Alarm Response Testing | Testing & Commissioning | Integrated Systems Testing (IST) | Not Started | 2027-02-24 08:00 | 2027-02-26 16:00 |  |  | 3 | 3 | 2 | No |  |  | 35000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | IST-080 | Resolve IST Deficiencies | Testing & Commissioning | Integrated Systems Testing (IST) | Not Started | 2027-03-02 08:00 | 2027-03-12 16:00 |  |  | 10 | 10 | 0 | Yes | 1 | 35 | 42000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | IST-090 | Integrated Systems Testing Complete | Testing & Commissioning | Integrated Systems Testing (IST) | Not Started | 2027-03-12 16:00 | 2027-03-12 16:00 |  |  | 0 | 0 | 0 | Yes | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | LBT-010 | Mobilize Load Bank Equipment | Testing & Commissioning | Load Bank & Performance Testing | Not Started | 2027-02-04 08:00 | 2027-02-09 16:00 |  |  | 5 | 5 | 0 | Yes | 1 | 29 | 41000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | LBT-020 | Connect Load Bank Equipment | Testing & Commissioning | Load Bank & Performance Testing | Not Started | 2027-02-10 08:00 | 2027-02-15 16:00 |  |  | 5 | 5 | 0 | Yes | 1 | 30 | 41000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | LBT-030 | Perform UPS Load Bank Testing | Testing & Commissioning | Load Bank & Performance Testing | Not Started | 2027-02-16 08:00 | 2027-02-20 16:00 |  |  | 5 | 5 | 0 | Yes | 1 | 31 | 41000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | LBT-040 | Perform Generator Load Bank Testing | Testing & Commissioning | Load Bank & Performance Testing | Not Started | 2027-02-16 08:00 | 2027-02-20 16:00 |  |  | 5 | 5 | 0 | Yes | 8 | 3 | 41000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | LBT-050 | Perform Cooling Performance Testing | Testing & Commissioning | Load Bank & Performance Testing | Not Started | 2027-02-16 08:00 | 2027-02-20 16:00 |  |  | 5 | 5 | 0 | Yes | 9 | 1 | 41000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | LBT-060 | Verify Data Hall Environmental Performance | Testing & Commissioning | Load Bank & Performance Testing | Not Started | 2027-02-22 08:00 | 2027-02-23 16:00 |  |  | 2 | 2 | 0 | Yes | 1 | 32 | 26000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | LBT-070 | Load Bank and Performance Testing Complete | Testing & Commissioning | Load Bank & Performance Testing | Not Started | 2027-02-23 16:00 | 2027-02-23 16:00 |  |  | 0 | 0 | 0 | Yes | 1 | 33 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | RRT-010 | Develop Reliability Test Plan | Testing & Commissioning | Reliability / Resilience Testing | In Progress | 2026-01-23 08:00 | 2026-02-03 16:00 | 2026-01-23 08:00 |  | 10 | 4.6892 | 343 | No |  |  | 50000 | 50000 | 36553.9541 | 40148.07 | -3594.1159 | -13446.0459 | 0.91048 | 0.73108 | Available | Available | Available | Available
Update 02 | 2026-02-28 | RRT-020 | Perform Utility Loss Resilience Test | Testing & Commissioning | Reliability / Resilience Testing | Not Started | 2027-03-13 08:00 | 2027-03-24 16:00 |  |  | 10 | 10 | 0 | Yes | 1 | 37 | 50000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | RRT-030 | Perform Generator Failure Simulation | Testing & Commissioning | Reliability / Resilience Testing | Not Started | 2027-03-13 08:00 | 2027-03-18 16:00 |  |  | 5 | 5 | 5 | No |  |  | 34000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | RRT-040 | Perform UPS Failure Simulation | Testing & Commissioning | Reliability / Resilience Testing | Not Started | 2027-03-13 08:00 | 2027-03-18 16:00 |  |  | 5 | 5 | 5 | No |  |  | 34000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | RRT-050 | Perform Cooling Failure Simulation | Testing & Commissioning | Reliability / Resilience Testing | Not Started | 2027-03-13 08:00 | 2027-03-18 16:00 |  |  | 5 | 5 | 5 | No |  |  | 34000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | RRT-060 | Complete Reliability Demonstration | Testing & Commissioning | Reliability / Resilience Testing | Not Started | 2027-03-25 08:00 | 2027-03-26 16:00 |  |  | 2 | 2 | 0 | Yes | 1 | 38 | 31000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | RRT-070 | Reliability Testing Complete | Testing & Commissioning | Reliability / Resilience Testing | Not Started | 2027-03-26 16:00 | 2027-03-26 16:00 |  |  | 0 | 0 | 0 | Yes | 1 | 39 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | CXC-010 | Compile Commissioning Defects List | Testing & Commissioning | Commissioning Defects & Closeout | Not Started | 2027-03-27 08:00 | 2027-04-07 16:00 |  |  | 10 | 10 | 0 | Yes | 1 | 40 | 50000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CXC-020 | Rectify Electrical Commissioning Defects | Testing & Commissioning | Commissioning Defects & Closeout | Not Started | 2027-04-08 08:00 | 2027-04-13 16:00 |  |  | 5 | 5 | 2 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CXC-030 | Rectify Mechanical Commissioning Defects | Testing & Commissioning | Commissioning Defects & Closeout | Not Started | 2027-04-08 08:00 | 2027-04-13 16:00 |  |  | 5 | 5 | 2 | No |  |  | 41000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CXC-040 | Rectify Controls and BMS Defects | Testing & Commissioning | Commissioning Defects & Closeout | Not Started | 2027-04-08 08:00 | 2027-04-15 16:00 |  |  | 7 | 7 | 0 | Yes | 1 | 41 | 38000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CXC-050 | Rectify Fire System Defects | Testing & Commissioning | Commissioning Defects & Closeout | Not Started | 2027-04-08 08:00 | 2027-04-15 16:00 |  |  | 7 | 7 | 0 | Yes | 3 | 1 | 38000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CXC-060 | Close Commissioning Punch List | Testing & Commissioning | Commissioning Defects & Closeout | Not Started | 2027-04-16 08:00 | 2027-04-27 16:00 |  |  | 10 | 10 | 0 | Yes | 1 | 42 | 50000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CXC-070 | Commissioning Complete | Testing & Commissioning | Commissioning Defects & Closeout | Not Started | 2027-04-27 16:00 | 2027-04-27 16:00 |  |  | 0 | 0 | 0 | Yes | 1 | 43 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | HND-010 | Conduct Client Pre-Handover Inspection | Client Acceptance & Handover | Punch List / Snagging | Not Started | 2027-04-28 08:00 | 2027-04-29 16:00 |  |  | 2 | 2 | 0 | Yes | 1 | 44 | 44000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | HND-020 | Prepare Final Punch List | Client Acceptance & Handover | Punch List / Snagging | Not Started | 2027-04-30 08:00 | 2027-05-13 16:00 |  |  | 10 | 10 | 0 | Yes | 1 | 45 | 35000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | HND-030 | Rectify Final Punch List Items | Client Acceptance & Handover | Punch List / Snagging | Not Started | 2027-05-14 08:00 | 2027-05-27 16:00 |  |  | 10 | 10 | 0 | Yes | 1 | 46 | 35000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | HND-040 | Verify Punch List Closure | Client Acceptance & Handover | Punch List / Snagging | Not Started | 2027-05-28 08:00 | 2027-05-31 16:00 |  |  | 2 | 2 | 0 | Yes | 1 | 47 | 22000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | ASB-010 | Compile Civil and Architectural As-Built Drawings | Client Acceptance & Handover | As-Built Documentation | Not Started | 2026-08-25 08:00 | 2026-09-07 16:00 |  |  | 10 | 10 | 172 | No |  |  | 35000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | ASB-020 | Compile Electrical As-Built Drawings | Client Acceptance & Handover | As-Built Documentation | Not Started | 2027-01-11 08:00 | 2027-01-22 16:00 |  |  | 10 | 10 | 73 | No |  |  | 35000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | ASB-030 | Compile Mechanical As-Built Drawings | Client Acceptance & Handover | As-Built Documentation | Not Started | 2026-12-15 08:00 | 2026-12-28 16:00 |  |  | 10 | 10 | 92 | No |  |  | 35000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | ASB-040 | Compile Controls and Fire As-Built Drawings | Client Acceptance & Handover | As-Built Documentation | Not Started | 2027-01-08 08:00 | 2027-01-21 16:00 |  |  | 10 | 10 | 74 | No |  |  | 35000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | ASB-050 | Submit Final As-Built Documentation | Client Acceptance & Handover | As-Built Documentation | Not Started | 2027-01-25 08:00 | 2027-02-05 16:00 |  |  | 10 | 10 | 73 | No |  |  | 18000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | OMM-010 | Compile Electrical O&M Manuals | Client Acceptance & Handover | O&M Manuals | Not Started | 2026-12-14 08:00 | 2026-12-25 16:00 |  |  | 10 | 10 | 93 | No |  |  | 35000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | OMM-020 | Compile Mechanical O&M Manuals | Client Acceptance & Handover | O&M Manuals | Not Started | 2026-08-28 08:00 | 2026-09-10 16:00 |  |  | 10 | 10 | 169 | No |  |  | 35000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | OMM-030 | Compile Fire and Life Safety O&M Manuals | Client Acceptance & Handover | O&M Manuals | Not Started | 2026-06-10 08:00 | 2026-06-23 16:00 |  |  | 10 | 10 | 226 | No |  |  | 35000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | OMM-040 | Compile BMS and DCIM O&M Manuals | Client Acceptance & Handover | O&M Manuals | Not Started | 2026-08-07 08:00 | 2026-08-20 16:00 |  |  | 10 | 10 | 184 | No |  |  | 35000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | OMM-050 | Submit Final O&M Manuals | Client Acceptance & Handover | O&M Manuals | Not Started | 2026-12-28 08:00 | 2027-01-08 16:00 |  |  | 10 | 10 | 93 | No |  |  | 18000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | TRN-010 | Develop Operations Training Plan | Client Acceptance & Handover | Training & Knowledge Transfer | Completed | 2026-01-23 08:00 | 2026-01-29 16:00 | 2026-01-23 08:00 | 2026-01-29 16:00 | 5 | 0 |  | No |  |  | 29000 | 29000 | 29000 | 30141.2916 | -1141.2916 | 0 | 0.96214 | 1 | Available | Available | Available | Available
Update 02 | 2026-02-28 | TRN-020 | Conduct Electrical Systems Training | Client Acceptance & Handover | Training & Knowledge Transfer | Not Started | 2027-02-16 08:00 | 2027-02-22 16:00 |  |  | 5 | 5 | 72 | No |  |  | 29000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | TRN-030 | Conduct Mechanical Systems Training | Client Acceptance & Handover | Training & Knowledge Transfer | Not Started | 2027-02-15 08:00 | 2027-02-19 16:00 |  |  | 5 | 5 | 73 | No |  |  | 29000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | TRN-040 | Conduct Fire and Life Safety Training | Client Acceptance & Handover | Training & Knowledge Transfer | Not Started | 2027-02-08 08:00 | 2027-02-12 16:00 |  |  | 5 | 5 | 78 | No |  |  | 29000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | TRN-050 | Conduct BMS and DCIM Training | Client Acceptance & Handover | Training & Knowledge Transfer | Not Started | 2027-02-18 08:00 | 2027-02-24 16:00 |  |  | 5 | 5 | 70 | No |  |  | 29000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | TRN-060 | Operations Training Complete | Client Acceptance & Handover | Training & Knowledge Transfer | Not Started | 2027-02-24 16:00 | 2027-02-24 16:00 |  |  | 0 | 0 | 70 | No |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Missing | Available | Available | Missing
Update 02 | 2026-02-28 | AUT-010 | Submit Final Authority Inspection Request | Client Acceptance & Handover | Authority / Regulatory Approvals | Not Started | 2027-02-22 08:00 | 2027-02-23 16:00 |  |  | 2 | 2 | 52 | No |  |  | 11000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | AUT-020 | Conduct Fire Authority Inspection | Client Acceptance & Handover | Authority / Regulatory Approvals | Not Started | 2027-02-24 08:00 | 2027-02-25 16:00 |  |  | 2 | 2 | 52 | No |  |  | 44000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | AUT-030 | Conduct Electrical Authority Inspection | Client Acceptance & Handover | Authority / Regulatory Approvals | Not Started | 2027-02-24 08:00 | 2027-02-25 16:00 |  |  | 2 | 2 | 52 | No |  |  | 44000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | AUT-040 | Resolve Authority Inspection Comments | Client Acceptance & Handover | Authority / Regulatory Approvals | Not Started | 2027-02-26 08:00 | 2027-03-01 16:00 |  |  | 2 | 2 | 52 | No |  |  | 44000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | AUT-050 | Obtain Final Authority Approvals | Client Acceptance & Handover | Authority / Regulatory Approvals | Not Started | 2027-03-02 08:00 | 2027-03-10 16:00 |  |  | 7 | 7 | 52 | No |  |  | 16000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CFI-010 | Conduct Client Final Technical Inspection | Client Acceptance & Handover | Client Final Inspections | Not Started | 2027-06-01 08:00 | 2027-06-02 16:00 |  |  | 2 | 2 | 0 | Yes | 1 | 48 | 44000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CFI-020 | Conduct Client Operations Readiness Review | Client Acceptance & Handover | Client Final Inspections | Not Started | 2027-06-03 08:00 | 2027-06-09 16:00 |  |  | 5 | 5 | 0 | Yes | 1 | 49 | 10000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CFI-030 | Resolve Client Final Inspection Comments | Client Acceptance & Handover | Client Final Inspections | Not Started | 2027-06-10 08:00 | 2027-06-11 16:00 |  |  | 2 | 2 | 0 | Yes | 1 | 50 | 44000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | CFI-040 | Client Final Inspection Accepted | Client Acceptance & Handover | Client Final Inspections | Not Started | 2027-06-14 08:00 | 2027-06-15 16:00 |  |  | 2 | 2 | 0 | Yes | 1 | 51 | 44000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | DFC-010 | Compile Outstanding Defects Register | Client Acceptance & Handover | Final Documentation & Turnover | Not Started | 2027-06-16 08:00 | 2027-06-29 16:00 |  |  | 10 | 10 | 0 | Yes | 1 | 52 | 12000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | DFC-020 | Rectify Outstanding Construction Defects | Client Acceptance & Handover | Final Documentation & Turnover | Not Started | 2027-06-30 08:00 | 2027-07-08 16:00 |  |  | 7 | 7 | 0 | Yes | 1 | 53 | 80000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | DFC-030 | Rectify Outstanding Systems Defects | Client Acceptance & Handover | Final Documentation & Turnover | Not Started | 2027-06-30 08:00 | 2027-07-08 16:00 |  |  | 7 | 7 | 0 | Yes | 2 | 1 | 32000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | DFC-040 | Verify Outstanding Defects Closure | Client Acceptance & Handover | Final Documentation & Turnover | Not Started | 2027-07-09 08:00 | 2027-07-12 16:00 |  |  | 2 | 2 | 0 | Yes | 1 | 54 | 22000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | FDT-010 | Compile Final Handover Dossier | Client Acceptance & Handover | Ready for Service | Not Started | 2027-02-08 08:00 | 2027-02-12 16:00 |  |  | 5 | 5 | 73 | No |  |  | 29000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | FDT-020 | Submit Commissioning Records | Client Acceptance & Handover | Ready for Service | Not Started | 2027-04-28 08:00 | 2027-05-04 16:00 |  |  | 5 | 5 | 16 | No |  |  | 14000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | FDT-030 | Submit Testing Certificates | Client Acceptance & Handover | Ready for Service | Not Started | 2027-03-29 08:00 | 2027-03-31 16:00 |  |  | 3 | 3 | 40 | No |  |  | 12000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | FDT-040 | Submit Equipment Warranties | Client Acceptance & Handover | Ready for Service | Not Started | 2026-11-12 08:00 | 2026-11-18 16:00 |  |  | 5 | 5 | 135 | No |  |  | 14000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available
Update 02 | 2026-02-28 | FDT-050 | Final Handover Documentation Accepted | Client Acceptance & Handover | Ready for Service | Not Started | 2027-05-05 08:00 | 2027-05-11 16:00 |  |  | 5 | 5 | 16 | No |  |  | 29000 | 0 | 0 | 0 | 0 | 0 |  |  | Available | Available | Available | Available

## DATA_QUALITY
Check | Status | Severity | Count | Details
Missing task IDs | PASS | ERROR | 0 | Every activity should have a task_id.
Missing activity IDs | PASS | WARNING | 0 | Activities without task codes should be reviewed.
Missing WBS mapping | PASS | ERROR | 0 | Activities should map to a valid WBS hierarchy.
Planned finish before planned start | PASS | ERROR | 0 | Planned finish dates must not precede planned start dates.
Missing BAC source values | WARNING | WARNING | 96 | BAC is currently zero-filled for compatibility; investigate missing source records.
Missing AC source values | WARNING | WARNING | 96 | AC is currently zero-filled for compatibility; investigate missing source records.
Missing EV source values | PASS | WARNING | 0 | EV is currently zero-filled for compatibility; investigate missing UDF values.
Missing PV source values | PASS | WARNING | 0 | PV is currently zero-filled for compatibility; investigate missing UDF values.
Project CPI calculation | PASS | ERROR | 0 | CPI = EV / AC using aggregated project totals.
Project SPI calculation | PASS | ERROR | 0 | SPI = EV / PV using aggregated project totals.
WBS BAC reconciliation | PASS | ERROR | 0 | Absolute difference: $0.00.
WBS PV reconciliation | PASS | ERROR | 0 | Absolute difference: $0.00.
WBS EV reconciliation | PASS | ERROR | 0 | Absolute difference: $0.00.
WBS AC reconciliation | PASS | ERROR | 0 | Absolute difference: $0.00.
Broken predecessor activity references | PASS | ERROR | 0 | TASKPRED predecessor IDs should exist in TASK.
Broken successor activity references | PASS | ERROR | 0 | TASKPRED successor IDs should exist in TASK.

## FORECAST_SCENARIOS
Update_ID | Project_ID | Data_Date | Scenario | EAC | ETC | VAC | VAC_Percent_of_BAC | Assumption | Primary_Scenario
Update 02 | DC-HYP-FINAL-6 | 2026-02-28 | Budget Rate | 120348084.2547 | 106981515.3303 | -348084.2547 | -0.0029007 | Remaining work is completed at the original budgeted cost rate. | No
Update 02 | DC-HYP-FINAL-6 | 2026-02-28 | CPI Based | 123208523.2362 | 109841954.3118 | -3208523.2362 | -0.026738 | Current cost efficiency continues for the remaining work. Primary scenario. | Yes
Update 02 | DC-HYP-FINAL-6 | 2026-02-28 | CPI + SPI | 126013874.8001 | 112647305.8757 | -6013874.8001 | -0.050116 | Current cost and schedule efficiency continue to influence the remaining forecast. | No

## SCHEDULE_ANALYSIS
Update_ID | Project_ID | Data_Date | Planned_Start | Current_Forecast_Finish | Baseline_Finish | Finish_Variance_Days | Critical_Activities | Negative_Float_Activities | Low_Float_Activities_10_Days_or_Less | SPI | Schedule_Status | Method_Note
Update 02 | DC-HYP-FINAL-6 | 2026-02-28 | 2026-01-05 | 2027-07-19 16:00 |  |  | 89 | 0 | 140 | 0.97774 | Within Threshold | Baseline finish variance is not calculated because a separate baseline finish field is not present in the source data used by this pipeline.

## EXCEPTIONS
Exception_ID | Update_ID | Project_ID | Data_Date | Category | Severity | Metric | Current_Value | Threshold | Description | Required_Investigation | Status
EX-001 | Update 02 | DC-HYP-FINAL-6 | 2026-02-28 | Forecast | Medium | VAC % of BAC | -0.026738 | -0.02 | Primary CPI-based forecast indicates an unfavorable variance at completion. | Review EAC assumptions, remaining cost, productivity, and scope/commercial exposure. | Open
EX-002 | Update 02 | DC-HYP-FINAL-6 | 2026-02-28 | Schedule | Medium | Low Float Activities | 140 | 10 | A material number of activities have 10 days or less total float. | Review the low-float population and confirm near-term monitoring priorities. | Open
EX-003 | Update 02 | DC-HYP-FINAL-6 | 2026-02-28 | Data Quality | Medium | Missing BAC Source Values | 96 | 0 | Some activity BAC values are missing from source cost records. | Confirm whether missing BAC records are intentional, not applicable, or incomplete in P6. | Open
EX-004 | Update 02 | DC-HYP-FINAL-6 | 2026-02-28 | Data Quality | Medium | Missing AC Source Values | 96 | 0 | Some activity AC values are missing from source cost records. | Confirm whether missing actual-cost records are expected for not-started work or require investigation. | Open

## MANAGEMENT_ACTIONS
Exception_ID | Update_ID | Project_ID | Data_Date | Issue | Investigation_or_Action | Owner | Due_Date | Status | Comments
EX-001 | Update 02 | DC-HYP-FINAL-6 | 2026-02-28 | Primary CPI-based forecast indicates an unfavorable variance at completion. | Review EAC assumptions, remaining cost, productivity, and scope/commercial exposure. | To Be Assigned |  | Open | Management owner and due date to be assigned after review.
EX-002 | Update 02 | DC-HYP-FINAL-6 | 2026-02-28 | A material number of activities have 10 days or less total float. | Review the low-float population and confirm near-term monitoring priorities. | To Be Assigned |  | Open | Management owner and due date to be assigned after review.
EX-003 | Update 02 | DC-HYP-FINAL-6 | 2026-02-28 | Some activity BAC values are missing from source cost records. | Confirm whether missing BAC records are intentional, not applicable, or incomplete in P6. | To Be Assigned |  | Open | Management owner and due date to be assigned after review.
EX-004 | Update 02 | DC-HYP-FINAL-6 | 2026-02-28 | Some activity AC values are missing from source cost records. | Confirm whether missing actual-cost records are expected for not-started work or require investigation. | To Be Assigned |  | Open | Management owner and due date to be assigned after review.

## METHODOLOGY
Section | Metric | Formula | Assumption
Forecast | EAC — Budget Rate | AC + (BAC - EV) | Remaining work is completed at the original budgeted cost rate.
Forecast | EAC — CPI Based | BAC / CPI | Current cost efficiency continues for remaining work. Primary scenario.
Forecast | EAC — CPI + SPI | BAC / (CPI × SPI) | Current cost and schedule efficiency continue to influence the remaining forecast.
Forecast | ETC | EAC - AC | Remaining expected cost equals forecast EAC less actual cost to date.
Forecast | VAC | BAC - EAC | Positive VAC is favorable; negative VAC indicates forecast cost above BAC.
Schedule | Critical Activity | Total Float <= 0 hours | Blank total float is treated as unknown, not automatically critical.
Schedule | Low Float | 0 to 10 total-float days | Configured monitoring threshold for schedule exposure.
Exception | CPI Threshold | CPI < 0.95 | Configured management trigger; adjustable.
Exception | SPI Threshold | SPI < 0.95 | Configured management trigger; adjustable.
Exception | VAC Threshold | VAC / BAC < -2% | Configured forecast trigger; adjustable.
Data Quality | Missing Source Values | Source record unavailable | Missing values are reported separately from reported zero values.

## STAGE2_QA
Check | Status | Count | Details
Budget Rate EAC available | PASS | 0 | EAC is available for the scenario.
CPI Based EAC available | PASS | 0 | EAC is available for the scenario.
CPI + SPI EAC available | PASS | 0 | EAC is available for the scenario.
Budget Rate ETC reconciliation | PASS | 0 | ETC = EAC - AC.
Budget Rate VAC reconciliation | PASS | 0 | VAC = BAC - EAC.
CPI Based ETC reconciliation | PASS | 0 | ETC = EAC - AC.
CPI Based VAC reconciliation | PASS | 0 | VAC = BAC - EAC.
CPI + SPI ETC reconciliation | PASS | 0 | ETC = EAC - AC.
CPI + SPI VAC reconciliation | PASS | 0 | VAC = BAC - EAC.
Exception engine structure | PASS | 0 | Required exception fields are present.
Methodology table structure | PASS | 0 | Required methodology fields are present.